## Sheet3
WBS | WBS Name | Activity ID | Activity Name | BL Project Start | BL Project Finish
I2S - Program - DD 24-Mar - EOM - Mar 2026 - JM-PD review- 20-Mar |  |  |  | 2024-09-30 | 2027-04-30
Key Dates |  |  |  | 2024-09-30 | 2027-04-30
Contractural Milestones |  |  |  | 2024-09-30 | 2027-04-30
I2S-7688-MP-74.KD.1 | Contractural Milestones | I.GG.1050 | Key Date - Contract Milestone - Date for Overall Practical Completion of the Works - I2S |  | 2027-04-30
I2S-7688-MP-74.KD.1 | Contractural Milestones | I.GG.16360 | Key Date - I2S ECW Agreement Executed
I2S-7688-MP-74.KD.1 | Contractural Milestones | I.GG.1000 | Key Date - Contract Milestone - I2S Deed Execution Date (30th September 2024) | 2024-09-30
Intermediate Milestones |  |  |  | 2026-09-14 | 2027-04-30
Returned Works A - CRN Track |  |  |  | 2026-09-14 | 2026-10-13
I2S-7688-MP-74.KD.2.2 | Returned Works A - CRN Track | I.GG.1020 | Key Date - Returned Works A - CRN Track - Construction complete |  | 2026-09-14
I2S-7688-MP-74.KD.2.2 | Returned Works A - CRN Track | I.GG.5260 | Key Date - Returned Works A - CRN Track - Contractors Contingency (SRA /10% of Con.Dur-TBR) | 2026-09-14 | 2026-10-13
I2S-7688-MP-74.KD.2.2 | Returned Works A - CRN Track | I.GG.5320 | Key Date - Returned Works A - CRN Track - completion |  | 2026-10-13
Stockinbingal to Parkes S2P - Section 6 |  |  |  | 2026-09-14 | 2026-10-18
I2S-7688-MP-74.KD.2.3 | Stockinbingal to Parkes S2P - Section 6 | I.GG.1030 | Key Date - ARTC Stockinbingal to Parkes S2P - Construction complete |  | 2026-09-14
I2S-7688-MP-74.KD.2.3 | Stockinbingal to Parkes S2P - Section 6 | I.GG.5270 | Key Date - ARTC Stockinbingal to Parkes S2P - Contractors Contingency (SRA /10% of Con.Dur-TBR) | 2026-09-15 | 2026-10-18
I2S-7688-MP-74.KD.2.3 | Stockinbingal to Parkes S2P - Section 6 | I.GG.5330 | Key Date - ARTC Stockinbingal to Parkes S2P - completion |  | 2026-10-18
Returned Works B - BGW (Burley Griffin Way) |  |  |  | 2026-11-03 | 2026-12-11
I2S-7688-MP-74.KD.2.4 | Returned Works B - BGW (Burley Griffin Way) | I.GG.5220 | Key Date - Returned Works B - BGW Road - Con.works - complete |  | 2026-11-03
I2S-7688-MP-74.KD.2.4 | Returned Works B - BGW (Burley Griffin Way) | I.GG.5280 | Key Date - Returned Works B - BGW Road - all works - Con.Contingency (SRA /10% of Con.Dur-TBR) | 2026-11-04 | 2026-12-11
I2S-7688-MP-74.KD.2.4 | Returned Works B - BGW (Burley Griffin Way) | I.GG.5340 | Key Date - Returned Works B - BGW - all works - completion |  | 2026-12-11
I2S Track |  |  |  | 2027-03-15 | 2027-04-11
I2S-7688-MP-74.KD.2.5 | I2S Track | I.GG.5230 | Key Date - I2S Track - Construction complete |  | 2027-03-15
I2S-7688-MP-74.KD.2.5 | I2S Track | I.GG.5290 | Key Date - I2S Track - Contractors Contingency (SRA /10% of Con.Dur-TBR) | 2027-03-15 | 2027-04-11
I2S-7688-MP-74.KD.2.5 | I2S Track | I.GG.5350 | Key Date - I2S Track - completion |  | 2027-04-11
Sections 1 to 6 |  |  |  | 2027-04-03 | 2027-04-30
I2S-7688-MP-74.KD.2.6 | Sections 1 to 6 | I.GG.5360 | Key Date - Sections 1 to 6 - Works - Forecast Date of Practical Completion |  | 2027-04-30
I2S-7688-MP-74.KD.2.6 | Sections 1 to 6 | I.GG.15000 | Key Date - Sections 1 to 6 - Works - Construction complete |  | 2027-04-03
I2S-7688-MP-74.KD.2.6 | Sections 1 to 6 | I.GG.15010 | Key Date - Sections 1 to 6 - Works - Contractors Contingency (SRA /10% of Con.Dur-TBR) | 2027-04-04 | 2027-04-30
IRPL Milestones |  |  |  | 2024-09-30 | 2024-11-27
I2S-7688-MP-74.KD.3 | IRPL Milestones | I.GG.PM.PA-2502 | IRPL - MIL - IRPL 100% retirement of Biodiversity Credits
I2S-7688-MP-74.KD.3 | IRPL Milestones | I.GG.PM.PA-2282 | IRPL - MIL - LIW Approval (Low impact works) works can commence | 2024-11-27
CSSI |  |  |  | 2024-09-30 | 2024-09-30
I2S-7688-MP-74.KD.3.3 | CSSI | I.GG.PM.PA-2252 | CSSI Approval Granted | 2024-09-30
EPBC |  |  |  | 2024-09-30 | 2024-11-08
I2S-7688-MP-74.KD.3.1 | EPBC | I.GG.PM.PA-1802 | EPBC Approval Granted (IRPL to Issue - As late as possible |  | 2024-11-08
I2S-7688-MP-74.KD.3.1 | EPBC | I.GG.PM.PA-2262 | EPBC Approval Granted (IRPL to Issue - required by) | 2024-09-30
Signalling |  |  |  | 2024-10-02 | 2024-10-02
I2S-7688-MP-74.KD.3.2 | Signalling | I.GG.15590 | IRPL to Issue Updated O/S from IRPL | 2024-10-02
I2S-7688-MP-74.KD.3.2 | Signalling | I.GG.15740 | IRPL to Issue Editable Reference Design SFS from IRPL | 2024-10-02
I2S-7688-MP-74.KD.3.2 | Signalling | I.GG.15750 | IRPL to Issue CAD Reference Design Signalling Plans from IRPL | 2024-10-02
Site Access Dates |  |  |  | 2024-10-21 | 2025-03-17
Land Access Agreements |  |  |  | 2024-10-21 | 2025-03-17
I2S-7688-MP-74.KD.4.LA | Land Access Agreements | I.GG.15650 | FInal Site Access - ' McKenzie land' |  | 2024-10-21
T - Temporary land required |  |  |  | 2024-11-27 | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-1522 | NLPA Land Access required by - (Ch. 0) - PETER JAMES CURRAN, PAMELA JUNE MCINERNEY | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-1912 | NLPA Land Access required by - (Ch. 2800) - DAVID LESLIE THOMPSON | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-1922 | NLPA Land Access required by - (Ch. 5600) - HELEN MARGARET DUNSTAN | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-1932 | NLPA Land Access required by - (Ch. 8400) - JOHN DAVID KENNETH GREEN, ANTHONY EDWARD LLOYD-JONES | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-1942 | NLPA Land Access required by - (Ch. 9450) - OWEN MALCOLM LLOYD-JONES, MARIA JANE LLOYD-JONES | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-1952 | NLPA Land Access required by - (Ch. 11400) - A P A C PTY LIMITED | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-1962 | NLPA Land Access required by - (Ch. 15950) - APAC PTY LTD, CAROLINE ELIZABETH HERMES & ASHLEY RENE HERMES | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-1972 | NLPA Land Access required by - (Ch. 18575) - ERIC LINDSAY MCKENZIE | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-1982 | NLPA Land Access required by - (Ch. 21950) - IR & DA FRIEND NO. 2 PTY LTD, | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-1992 | NLPA Land Access required by - (Ch. 22250) - LAGOON CREEK NOMINEES PTY LTD | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-2002 | NLPA Land Access required by - (Ch. 28200) - CHARLES CLIVE RYALS, CHRISTINE LOUISE & NIGEL JAMES CHARLMERS EMERY | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-2012 | NLPA Land Access required by - (Ch. 30850) - MCCLINTOCK'S DAUGHTERS PTY LTD | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-2022 | NLPA Land Access required by - (Ch. 32150) - RUNNYMEDE STOCK PTY LTD | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-2032 | NLPA Land Access required by - (Ch. 33050) - ANTHONY ROLAND HILL, DIANA LEA HILL | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-2042 | NLPA Land Access required by - (Ch. 33775) - K AND S BERRYMAN SUPER PTY LTD | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-2062 | NLPA Land Access required by - (Ch. 37300) - GRAHAM JOHN COOPER, STEPHANIE ANN COOPER | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-2072 | NLPA Land Access required by - (Ch. 37450) - LINX BULK HAULAGE PTY LIMITED | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-2082 | NLPA Land Access required by - (Ch. 37650) - GRANT WILLIAM LITTLE, ROBYN MAY GRAY | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-2092 | NLPA Land Access required by - (Ch. 41300) - CRAIG JOSEPH MORTON | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-2102 | NLPA Land Access required by - (Ch. 17400-17500) - ERIC LINDSAY MCKENZIE | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-2112 | NLPA Land Access required by - (Ch. 19000) - CHRISTOPHER ROSS FRIEND | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-2122 | NLPA Land Access required by - (Ch. 21200-21300) - CHRISTOPHER ROSS FRIEND | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-2132 | NLPA Land Access required by - (Ch. 11800-12100) - A P A C PTY LIMITED | 2024-11-27
I2S-7688-MP-74.KD.4.LA.1 | T - Temporary land required | I.GG.PM.PA-2052 | NLPA Land Access required by - (Ch. 35650) - PETER KEPREOTES | 2024-11-27
P - permanent land required |  |  |  | 2025-03-17 | 2025-03-17
I2S-7688-MP-74.KD.4.LA.2 | P - permanent land required | I.GG.PM.PA-1412 | Land Access required by - All Licenced Areas in Table 1 | 2025-03-17
Construction Management |  |  |  | 2024-09-30 | 2027-03-29
CSSI Conditions of Approval (CoA) |  |  |  | 2024-09-30 | 2027-02-26
Part A - Reporting Requirements |  |  |  | 2024-09-30 | 2025-08-14
A7 - Notification of LIW (was A36) |  |  |  | 2024-09-30 | 2024-10-29
I2S-7688-MP-74.CM.CoA.7.1 | A7 - Notification of LIW (was A36) | I.GG.15690 | CoA - A7 JH Notification of Commencement of Low Impact Works (LIW) (1 month prior to LIW) | 2024-09-30 | 2024-10-29
A8 - Notice of Commencement (was A37) |  |  |  | 2025-06-13 | 2025-07-10
I2S-7688-MP-74.CM.CoA.7.2 | A8 - Notice of Commencement (was A37) | CoA-1350 | CoA - A8 - Notice of Commencement (One month before the commencement of works, construction and operation) | 2025-06-13 | 2025-07-10
A18 - Temporary Accommodation Facility Management Plan (was A21) |  |  |  | 2025-04-28 | 2025-08-14
I2S-7688-MP-74.CM.CoA.7.24 | A18 - Temporary Accommodation Facility Management Plan (was A21) | CoA-1290 | CoA - A18 - Temporary Accommodation Facility Management Plan - ACMP Approval (1 month before occupation) | 2025-04-28 | 2025-05-27
I2S-7688-MP-74.CM.CoA.7.24 | A18 - Temporary Accommodation Facility Management Plan (was A21) | CoA-2240 | CoA - E111 Temporary workforce accommodation facilities must be completed prior to commencement of construction | 2025-08-14 | 2025-08-14
A30 - Environmental Representative Appointment (was A21) |  |  |  | 2024-09-30 | 2024-11-25
I2S-7688-MP-74.CM.CoA.7.11 | A30 - Environmental Representative Appointment (was A21) | I.GG.15660 | CoA - A30 - IRPL Nomination & Approval by Planning Secretary of Environmental Representative | 2024-09-30 | 2024-10-28
I2S-7688-MP-74.CM.CoA.7.11 | A30 - Environmental Representative Appointment (was A21) | CoA-1320 | CoA - A30 - Work must not commence until an Environmental Representative (ER) has been approved (1 month) | 2024-10-29 | 2024-11-25
Part C - Construction Environmental Management |  |  |  | 2024-09-30 | 2025-07-04
C5 - Site Establishment Management Plan (was A22) |  |  |  | 2025-04-16 | 2025-05-16
I2S-7688-MP-74.CM.CoA.6.25 | C5 - Site Establishment Management Plan (was A22) | I.GG.CEMP.16300 | CoA - C5 -CSEMP - Site Establishment Management Plan ( 1 month before works) | 2025-04-16 | 2025-05-16
C6 - Community Communication Strategy (was A23) |  |  |  | 2025-07-04 | 2025-07-04
I2S-7688-MP-74.CM.CoA.6.2 | C6 - Community Communication Strategy (was A23) | I.GG.CEMP.16260 | CoA - C6 - The use of an ancillary facility for construction must not commence until the CEMP approved by Planning Secre | 2025-07-04 | 2025-07-04
C9 - Minor Ancillary Facilities (was A26) |  |  |  | 2024-09-30 | 2024-11-26
I2S-7688-MP-74.CM.CoA.6.5 | C9 - Minor Ancillary Facilities (was A26) | I.GG.15380 | CoA - C9 - Develop Minor Ancillary Facilities strategy | 2024-09-30 | 2024-10-15
I2S-7688-MP-74.CM.CoA.6.5 | C9 - Minor Ancillary Facilities (was A26) | I.GG.15390 | CoA - C9 - Submit to Environmental Representative for Assesment - Minor Ancillary Facility Strategy | 2024-10-29 | 2024-11-25
I2S-7688-MP-74.CM.CoA.6.5 | C9 - Minor Ancillary Facilities (was A26) | CoA-1300 | CoA - C9 - Minor Ancillary Facilities strategy Approval - for LIW Approval | 2024-11-26 | 2024-11-26
Part D - Operational Environmental Management |  |  |  | 2025-07-08 | 2025-10-22
D1 to D4, D12 - Operational Environmental Management Plan (OEMP) |  |  |  | 2025-07-08 | 2025-10-22
I2S-7688-MP-74.CM.CoA.1.1 | D1 to D4, D12 - Operational Environmental Management Plan (OEMP) | CoA-2000 | CoA - D1, D2, D3, D4 - Operational Environmental Management Plan (OEMP) - Prepare | 2025-07-08 | 2025-09-02
I2S-7688-MP-74.CM.CoA.1.1 | D1 to D4, D12 - Operational Environmental Management Plan (OEMP) | CoA-2060 | CoA - D1, D2, D3, D4 - Operational Environmental Management Plan (OEMP) - made public | 2025-10-01 | 2025-10-22
I2S-7688-MP-74.CM.CoA.1.1 | D1 to D4, D12 - Operational Environmental Management Plan (OEMP) | CoA-2070 | CoA - D1, D2, D3, D4 - OEMP - reviewed/approved by Planning Secretary | 2025-09-03 | 2025-09-30
Part B - Communication Information and Reporting |  |  |  | 2024-09-30 | 2024-11-26
B1 to B5 - Community Communication Strategy |  |  |  | 2024-09-30 | 2024-11-26
I2S-7688-MP-74.CM.CoA.5.3 | B1 to B5 - Community Communication Strategy | I.GG.14840 | CoA - B4 - Community/stakeholder engagement and Social performance/local content workshop | 2024-11-26 | 2024-11-26
I2S-7688-MP-74.CM.CoA.5.3 | B1 to B5 - Community Communication Strategy | I.GG.15330 | CoA - B1, B2, B3 - Develop Community Communications Strategy (CCS) by IRPL | 2024-09-30 | 2024-10-21
I2S-7688-MP-74.CM.CoA.5.3 | B1 to B5 - Community Communication Strategy | I.GG.15340 | CoA - B4 - Submit to Planning Secretary for Approval - Community Communications Strategy (CCS) | 2024-10-22 | 2024-10-28
I2S-7688-MP-74.CM.CoA.5.3 | B1 to B5 - Community Communication Strategy | I.GG.15345 | CoA - B5 - Approval by Planning Secretary - Community Communications Strategy (CCS) | 2024-10-29 | 2024-11-25
I2S-7688-MP-74.CM.CoA.5.3 | B1 to B5 - Community Communication Strategy | I.GG.16170 | CoA - B5 - DPHI review - Community Communications Strategy (CCS) | 2024-10-29 | 2024-11-25
B6 to B19 - Community Complaints Mediator ( was B14) |  |  |  | 2024-09-30 | 2024-11-25
I2S-7688-MP-74.CM.CoA.5.2 | B6 to B19 - Community Complaints Mediator ( was B14) | I.GG.15350 | CoA - B12 - Nomination to Planning Secretary of Community Complaints Mediator - IRPL | 2024-09-30 | 2024-10-28
I2S-7688-MP-74.CM.CoA.5.2 | B6 to B19 - Community Complaints Mediator ( was B14) | CoA-1820 | CoA - B12 - Community Complaints Mediator (1 month before commencement of Work) | 2024-10-29 | 2024-11-25
I2S-7688-MP-74.CM.CoA.5.2 | B6 to B19 - Community Complaints Mediator ( was B14) | CoA-1910 | CoA - B15 - Community Complaints Mediator - copy of recommendations, response to recommedations, within one month of rec | 2024-10-29 | 2024-11-25
I2S-7688-MP-74.CM.CoA.5.2 | B6 to B19 - Community Complaints Mediator ( was B14) | CoA-1920 | CoA - B18 - A website or webpage providing information in relation to the CSSI must be established | 2024-10-29 | 2024-11-25
Key Issues - Noise and Vibration |  |  |  | 2024-11-29 | 2027-01-18
E10 - Blasting Management Strategy |  |  |  | 2024-11-29 | 2025-03-14
I2S-7688-MP-74.CM.CoA.n.9 | E10 - Blasting Management Strategy | CoA-3220 | CoA - E10 - IRPL Review Period
I2S-7688-MP-74.CM.CoA.n.9 | E10 - Blasting Management Strategy | CoA-3230 | CoA - E10 - Blast Mgmt Strategy - IRPL Comments - JH update and address
I2S-7688-MP-74.CM.CoA.n.9 | E10 - Blasting Management Strategy | CoA-3240 | CoA - E10 - Blast Mgmt Strategy - Submit to DPHI and review
I2S-7688-MP-74.CM.CoA.n.9 | E10 - Blasting Management Strategy | CoA-3250 | CoA - E10 - Blast Mgmt Strategy - DPHI comments - JH update and address and Submit to DPHI
I2S-7688-MP-74.CM.CoA.n.9 | E10 - Blasting Management Strategy | CoA-1560 | CoA - E10 - Develop Blasting Strategy and Issue to IRPL | 2024-11-29 | 2025-02-07
I2S-7688-MP-74.CM.CoA.n.9 | E10 - Blasting Management Strategy | CoA-1870 | CoA - E10 - Blast Mgmt Strategy - DPHI for review and approval | 2025-02-10 | 2025-03-14
I2S-7688-MP-74.CM.CoA.n.9 | E10 - Blasting Management Strategy | CoA-3580 | CoA - E10 - Blast Mgmt Strategy - Amend document for Independendant Reviewer
E16 - Operational Noise Compliance Report (ONCR) (was E20) |  |  |  | 2026-09-15 | 2026-11-17
I2S-7688-MP-74.CM.CoA.n.3 | E16 - Operational Noise Compliance Report (ONCR) (was E20) | CoA-2940 | CoA - E16 - ONCR - Rail - Independant Reviewer
I2S-7688-MP-74.CM.CoA.n.3 | E16 - Operational Noise Compliance Report (ONCR) (was E20) | CoA-1500 | CoA - E16 - ONCR - Rail - Develop Draft Operation Noise Compliance Report - Within 1 year of Operations | 2026-09-15 | 2026-10-13
I2S-7688-MP-74.CM.CoA.n.3 | E16 - Operational Noise Compliance Report (ONCR) (was E20) | CoA-1940 | CoA - E16 - ONCR - Rail - Submission to EPA and Planning Secretary | 2026-10-14 | 2026-11-10
I2S-7688-MP-74.CM.CoA.n.3 | E16 - Operational Noise Compliance Report (ONCR) (was E20) | CoA-1950 | CoA - E16 - ONCR - Rail - ONCR be publicly available | 2026-11-11 | 2026-11-17
I2S-7688-MP-74.CM.CoA.n.3 | E16 - Operational Noise Compliance Report (ONCR) (was E20) | CoA-2810 | CoA - E16 - ONCR - Rail - IRPL review
I2S-7688-MP-74.CM.CoA.n.3 | E16 - Operational Noise Compliance Report (ONCR) (was E20) | CoA-2820 | CoA - E16 - ONCR - Rail - JH Respond to incoporate comments
I2S-7688-MP-74.CM.CoA.n.3 | E16 - Operational Noise Compliance Report (ONCR) (was E20) | CoA-2830 | CoA - E16 - ONCR - Rail - 2nd Round Submission to IRPL for review and final endorsement
E15 - Operational Noise and Vibration Review (ONVR) Rail
I2S-7688-MP-74.CM.CoA.n.10 | E15 - Operational Noise and Vibration Review (ONVR) Rail | CoA-2740 | CoA - E15 - ONVR - Rail - Submit to IRPL & IRPL Review
I2S-7688-MP-74.CM.CoA.n.10 | E15 - Operational Noise and Vibration Review (ONVR) Rail | CoA-2630 | CoA - E15 - ONVR - Rail - Submission to EPA - Operational Noise and Vibration Review
I2S-7688-MP-74.CM.CoA.n.10 | E15 - Operational Noise and Vibration Review (ONVR) Rail | CoA-2760 | CoA - E15 - ONVR - Rail - Submission to Planning Secretary
I2S-7688-MP-74.CM.CoA.n.10 | E15 - Operational Noise and Vibration Review (ONVR) Rail | CoA-2580 | CoA - E15 - NEW - Develop Draft Operation Noise and Vibration Review (ONVR) - Rail
I2S-7688-MP-74.CM.CoA.n.10 | E15 - Operational Noise and Vibration Review (ONVR) Rail | CoA-2590 | CoA - E15 - NEW - Complete Modelling
I2S-7688-MP-74.CM.CoA.n.10 | E15 - Operational Noise and Vibration Review (ONVR) Rail | CoA-2600 | CoA - E15 - NEW - Complete review of mitigation measures identified in the EIS
I2S-7688-MP-74.CM.CoA.n.10 | E15 - Operational Noise and Vibration Review (ONVR) Rail | CoA-2610 | CoA - E15 - ONVR - Rail - Delivery of Draft ONVR report
I2S-7688-MP-74.CM.CoA.n.10 | E15 - Operational Noise and Vibration Review (ONVR) Rail | CoA-2620 | CoA - E15 - NEW - Provision of final design and inputs by John Holland
I2S-7688-MP-74.CM.CoA.n.10 | E15 - Operational Noise and Vibration Review (ONVR) Rail | CoA-2750 | CoA - E15 - ONVR - Rail - JH Respond to incorporate any comments
I2S-7688-MP-74.CM.CoA.n.10 | E15 - Operational Noise and Vibration Review (ONVR) Rail | CoA-2640 | CoA - E15 - ONVR - Rail - Update and resubmit for final approval
I2S-7688-MP-74.CM.CoA.n.10 | E15 - Operational Noise and Vibration Review (ONVR) Rail | CoA-2650 | CoA - E15 - ONVR - Rail - Approved prior to Operations
I2S-7688-MP-74.CM.CoA.n.10 | E15 - Operational Noise and Vibration Review (ONVR) Rail | CoA-3590 | CoA - E15 - ONVR - Rail - Validation of data (ARTC Train Speeds)
I2S-7688-MP-74.CM.CoA.n.10 | E15 - Operational Noise and Vibration Review (ONVR) Rail | CoA-3600 | CoA - E15 - ONVR - Rail - Train Speeds - Data modelling
E17 - Operational Noise and Vibration Review (ONVR) Road
I2S-7688-MP-74.CM.CoA.n.11 | E17 - Operational Noise and Vibration Review (ONVR) Road | CoA-2730 | CoA - E17 - ONVR - Road - Approved prior to Operations
I2S-7688-MP-74.CM.CoA.n.11 | E17 - Operational Noise and Vibration Review (ONVR) Road | CoA-2950 | CoA - E17 - ONVR - Road - Independant Reviewer
I2S-7688-MP-74.CM.CoA.n.11 | E17 - Operational Noise and Vibration Review (ONVR) Road | CoA-2720 | CoA - E17 - ONVR - Road - Update and resubmit for final approval
I2S-7688-MP-74.CM.CoA.n.11 | E17 - Operational Noise and Vibration Review (ONVR) Road | CoA-2780 | CoA - E17 - ONVR - Road - JH Respond to and incorporate any comments
I2S-7688-MP-74.CM.CoA.n.11 | E17 - Operational Noise and Vibration Review (ONVR) Road | CoA-2770 | CoA - E17 - NEW - IRPL Review
I2S-7688-MP-74.CM.CoA.n.11 | E17 - Operational Noise and Vibration Review (ONVR) Road | CoA-2670 | CoA - E17 - NEW - Develop Draft Operation Noise and Vibration Review (ONVR) - Rail
I2S-7688-MP-74.CM.CoA.n.11 | E17 - Operational Noise and Vibration Review (ONVR) Road | CoA-2680 | CoA - E17 - NEW - Complete Modelling
I2S-7688-MP-74.CM.CoA.n.11 | E17 - Operational Noise and Vibration Review (ONVR) Road | CoA-2690 | CoA - E17 - NEW - Complete review of mitigation measures identified in the EIS
I2S-7688-MP-74.CM.CoA.n.11 | E17 - Operational Noise and Vibration Review (ONVR) Road | CoA-2700 | CoA - E17 - NEW - JH prepare of Draft ONVR report
I2S-7688-MP-74.CM.CoA.n.11 | E17 - Operational Noise and Vibration Review (ONVR) Road | CoA-2660 | CoA - E17 - NEW - Provision of final design and inputs by John Holland
I2S-7688-MP-74.CM.CoA.n.11 | E17 - Operational Noise and Vibration Review (ONVR) Road | CoA-2790 | CoA - E17 - ONVR - Road - Consultation & Submission to EPA
I2S-7688-MP-74.CM.CoA.n.11 | E17 - Operational Noise and Vibration Review (ONVR) Road | CoA-2710 | CoA - E17 - ONVR - Road - Submission Planning Secretary
E18 - Operational Noise Compliance Report (ONCR) |  |  |  | 2026-09-15 | 2026-11-17
I2S-7688-MP-74.CM.CoA.n.4 | E18 - Operational Noise Compliance Report (ONCR) | CoA-2960 | CoA - E18 - ONCR - Road - Independant Reviewer
I2S-7688-MP-74.CM.CoA.n.4 | E18 - Operational Noise Compliance Report (ONCR) | CoA-2450 | CoA - E18 - ONCR - Road - Submission to EPA and Planning Secretary | 2026-10-14 | 2026-11-10
I2S-7688-MP-74.CM.CoA.n.4 | E18 - Operational Noise Compliance Report (ONCR) | CoA-2460 | CoA - E18 - ONCR - Road - ONCR be publicly available | 2026-11-11 | 2026-11-17
I2S-7688-MP-74.CM.CoA.n.4 | E18 - Operational Noise Compliance Report (ONCR) | CoA-2470 | CoA - E18 - ONCR - Road - Develop Draft - after 1 year of ops | 2026-09-15 | 2026-10-13
I2S-7688-MP-74.CM.CoA.n.4 | E18 - Operational Noise Compliance Report (ONCR) | CoA-2840 | CoA - E18 - ONCR - Road - IRPL review
I2S-7688-MP-74.CM.CoA.n.4 | E18 - Operational Noise Compliance Report (ONCR) | CoA-2850 | CoA - E18 - ONCR - Road - JH Respond to incoporate comments
I2S-7688-MP-74.CM.CoA.n.4 | E18 - Operational Noise Compliance Report (ONCR) | CoA-2860 | CoA - E18 - ONCR - Road - 2nd Round Submission to IRPL for review and final endorsement
E19 - Noise and Vibration Control Measurest - Rail |  |  |  | 2026-10-14 | 2026-10-27
I2S-7688-MP-74.CM.CoA.n.1 | E19 - Noise and Vibration Control Measurest - Rail | CoA-1480 | CoA - E19 - Rail - Noise and vibration control measures identified in the ONVRs | 2026-10-14 | 2026-10-27
I2S-7688-MP-74.CM.CoA.n.1 | E19 - Noise and Vibration Control Measurest - Rail | CoA-2880 | CoA - E19 - Rail - Implement Consultation Strategy
I2S-7688-MP-74.CM.CoA.n.1 | E19 - Noise and Vibration Control Measurest - Rail | CoA-2890 | CoA - E19 - Rail - Undertake dilapidation inspections and surveys
I2S-7688-MP-74.CM.CoA.n.1 | E19 - Noise and Vibration Control Measurest - Rail | CoA-2900 | CoA - E19 - Rail - Install treaments
I2S-7688-MP-74.CM.CoA.n.1 | E19 - Noise and Vibration Control Measurest - Rail | CoA-2970 | CoA - E19 - Rail - Procure contractors to undertake installation of property treatments
I2S-7688-MP-74.CM.CoA.n.1 | E19 - Noise and Vibration Control Measurest - Rail | CoA-2980 | CoA - E19 - Rail - Procurement of products
I2S-7688-MP-74.CM.CoA.n.1 | E19 - Noise and Vibration Control Measurest - Rail | CoA-3050 | CoA - E19 - Rail - Provide formal offer of property Treatments
E19 - Noise and Vibration Control Measurest - Road
I2S-7688-MP-74.CM.CoA.n.6 | E19 - Noise and Vibration Control Measurest - Road | CoA-2990 | CoA - E19 - Road - Noise and vibration control measures identified in the ONVRs
I2S-7688-MP-74.CM.CoA.n.6 | E19 - Noise and Vibration Control Measurest - Road | CoA-3000 | CoA - E19 - Road - Implement Consultation Strategy
I2S-7688-MP-74.CM.CoA.n.6 | E19 - Noise and Vibration Control Measurest - Road | CoA-3010 | CoA - E19 - Road - Undertake dilapidation inspections and surveys
I2S-7688-MP-74.CM.CoA.n.6 | E19 - Noise and Vibration Control Measurest - Road | CoA-3020 | CoA - E19 - Road - Install treaments
I2S-7688-MP-74.CM.CoA.n.6 | E19 - Noise and Vibration Control Measurest - Road | CoA-3030 | CoA - E19 - Road - Procure contractors to undertake installation of property treatments
I2S-7688-MP-74.CM.CoA.n.6 | E19 - Noise and Vibration Control Measurest - Road | CoA-3040 | CoA - E19 - Road - Procurement of products
I2S-7688-MP-74.CM.CoA.n.6 | E19 - Noise and Vibration Control Measurest - Road | CoA-3060 | CoA - E19 - Road - Provide formal offer of property Treatments
E20 - Operational noise mitigation measures (was E17) |  |  |  | 2026-10-28 | 2026-11-17
I2S-7688-MP-74.CM.CoA.n.5 | E20 - Operational noise mitigation measures (was E17) | CoA-1850 | CoA - E20 - Noise and vibration mitigation measures implemented - Road | 2026-10-28 | 2026-11-17
I2S-7688-MP-74.CM.CoA.n.5 | E20 - Operational noise mitigation measures (was E17) | CoA-2800 | CoA - E20 - Noise and vibration mitigation measures implemented - Rail
E21 - Operational Noise Compliance Report (ONCR) (was E18) - Rail
I2S-7688-MP-74.CM.CoA.n.2 | E21 - Operational Noise Compliance Report (ONCR) (was E18) - Rail | CoA-3160 | CoA - E21 - ONCR - Rail - Submission to IRPL for review
I2S-7688-MP-74.CM.CoA.n.2 | E21 - Operational Noise Compliance Report (ONCR) (was E18) - Rail | CoA-3170 | CoA - E21 - ONCR - Rail - JH update report and address any comments
I2S-7688-MP-74.CM.CoA.n.2 | E21 - Operational Noise Compliance Report (ONCR) (was E18) - Rail | CoA-3180 | CoA - E21 - ONCR - Rail - Submit to ER for review and endorsement
I2S-7688-MP-74.CM.CoA.n.2 | E21 - Operational Noise Compliance Report (ONCR) (was E18) - Rail | CoA-3200 | CoA - E21 - ONCR - Rail - JH update report and adress any comments
I2S-7688-MP-74.CM.CoA.n.2 | E21 - Operational Noise Compliance Report (ONCR) (was E18) - Rail | CoA-3210 | CoA - E21 - ONCR - Rail - Submission to DPHI and acceptance
I2S-7688-MP-74.CM.CoA.n.2 | E21 - Operational Noise Compliance Report (ONCR) (was E18) - Rail | CoA-3140 | CoA - E21 - ONCR - Rail - Draft Report
I2S-7688-MP-74.CM.CoA.n.2 | E21 - Operational Noise Compliance Report (ONCR) (was E18) - Rail | CoA-3150 | CoA - E21 - ONCR - Rail - JH Review and Update
E21 - Operational Noise Compliance Report (ONCR) (was E18) - Road |  |  |  | 2026-12-09 | 2027-01-18
I2S-7688-MP-74.CM.CoA.n.7 | E21 - Operational Noise Compliance Report (ONCR) (was E18) - Road | CoA-1860 | CoA - E21 - ONCR - Road - Draft Report | 2026-12-09 | 2027-01-18
I2S-7688-MP-74.CM.CoA.n.7 | E21 - Operational Noise Compliance Report (ONCR) (was E18) - Road | CoA-3080 | CoA - E21 - ONCR - Road - JH Review and Update
I2S-7688-MP-74.CM.CoA.n.7 | E21 - Operational Noise Compliance Report (ONCR) (was E18) - Road | CoA-3090 | CoA - E21 - ONCR - Road - Submission to IRPL for review
I2S-7688-MP-74.CM.CoA.n.7 | E21 - Operational Noise Compliance Report (ONCR) (was E18) - Road | CoA-3100 | CoA - E21 - ONCR - Road - JH update report and address any comments
I2S-7688-MP-74.CM.CoA.n.7 | E21 - Operational Noise Compliance Report (ONCR) (was E18) - Road | CoA-3110 | CoA - E21 - ONCR - Road - Submit to ER for review and endorsement
I2S-7688-MP-74.CM.CoA.n.7 | E21 - Operational Noise Compliance Report (ONCR) (was E18) - Road | CoA-3120 | CoA - E21 - ONCR - Road - JH update report and adress any comments
I2S-7688-MP-74.CM.CoA.n.7 | E21 - Operational Noise Compliance Report (ONCR) (was E18) - Road | CoA-3130 | CoA - E21 - ONCR - Road - Submission to DPHI and acceptance
Key Issues - Biodiversity |  |  |  | 2024-09-30 | 2026-03-10
Biodiversity |  |  |  | 2025-02-03 | 2025-06-20
E24 - Evidence of reductions to SAII in detailed design
I2S-7688-MP-74.CM.CoA.b.1.1 | E24 - Evidence of reductions to SAII in detailed design | I.GG.PM.PA-2612 | CoA - E24 - Submit to DPHI for Review
I2S-7688-MP-74.CM.CoA.b.1.1 | E24 - Evidence of reductions to SAII in detailed design | I.GG.PM.PA-2622 | CoA - E24 - JH review and incoporate comments
I2S-7688-MP-74.CM.CoA.b.1.1 | E24 - Evidence of reductions to SAII in detailed design | I.GG.PM.PA-2512 | CoA - E24 - Review PDD design Footprint
I2S-7688-MP-74.CM.CoA.b.1.1 | E24 - Evidence of reductions to SAII in detailed design | I.GG.PM.PA-2532 | CoA - E24 - Draft report for IRPL review
I2S-7688-MP-74.CM.CoA.b.1.1 | E24 - Evidence of reductions to SAII in detailed design | I.GG.PM.PA-2522 | CoA - E24 - Propose reductions in clearing limits
I2S-7688-MP-74.CM.CoA.b.1.1 | E24 - Evidence of reductions to SAII in detailed design | I.GG.PM.PA-2542 | CoA - E24 - IRPL Review
I2S-7688-MP-74.CM.CoA.b.1.1 | E24 - Evidence of reductions to SAII in detailed design | I.GG.PM.PA-2562 | CoA - E24 - Update report and Issue of final document
I2S-7688-MP-74.CM.CoA.b.1.1 | E24 - Evidence of reductions to SAII in detailed design | I.GG.PM.PA-2552 | CoA - E24 - Submit to BCS for Review
E28 to E30 - Evidence of Retirement Credits (was E26,E28) c |  |  |  | 2025-02-03 | 2025-06-20
I2S-7688-MP-74.CM.CoA.b.1.5 | E28 to E30 - Evidence of Retirement Credits (was E26,E28) c | I.GG.PM.PA-2162 | CoA - E28,29 - IRPL Prepare & Submit Report to DPHI - Environmental -Evidence of the retirement of credits | 2025-02-03 | 2025-03-07
I2S-7688-MP-74.CM.CoA.b.1.5 | E28 to E30 - Evidence of Retirement Credits (was E26,E28) c | I.GG.PM.PA-2172 | CoA - E28,29 - Review and Credits retired - Environmental -Evidence of the retirement of credits | 2025-06-06 | 2025-06-20
I2S-7688-MP-74.CM.CoA.b.1.5 | E28 to E30 - Evidence of Retirement Credits (was E26,E28) c | I.GG.PM.PA-2302 | CoA - E28,29 - DPHI Review and issue Comments - Environmental -Evidence of the retirement of credits | 2025-05-09 | 2025-06-05
Unsurveyed Areas - NEW |  |  |  | 2024-09-30 | 2025-01-10
E31 to E33 - Biodiversity Surveys |  |  |  | 2024-09-30 | 2025-01-10
I2S-7688-MP-74.CM.CoA.b.7.5 | E31 to E33 - Biodiversity Surveys | I.GG.PM.PA-2382 | CoA - E31 _NEW- IRPL Issue Biodiversity surveys of unsurveyed land identified to confirm CSSI ( awaiting land access) | 2024-09-30 | 2024-10-29
I2S-7688-MP-74.CM.CoA.b.7.5 | E31 to E33 - Biodiversity Surveys | I.GG.PM.PA-2402 | CoA - E33_NEW - IRPL/ARTC - Report prepared and issued in consultation with BCS submitted to planning secretary | 2024-11-04 | 2024-11-29
I2S-7688-MP-74.CM.CoA.b.7.5 | E31 to E33 - Biodiversity Surveys | I.GG.PM.PA-2412 | CoA - E33_NEW - IRPL/ARTC - Planning secretary reviewed and approves Report of unsurveyed areas | 2024-12-02 | 2025-01-10
Seed Collection, Revegetation and Rehabilitation - NEW
E39 - Seed Collection, Revegetation and Rehabilitation
I2S-7688-MP-74.CM.CoA.b.10.1 | E39 - Seed Collection, Revegetation and Rehabilitation | I.GG.PM.PA-2572 | CoA - E39_New - Undertake pre-clearance survey
I2S-7688-MP-74.CM.CoA.b.10.1 | E39 - Seed Collection, Revegetation and Rehabilitation | I.GG.PM.PA-2582 | CoA - E39 - Collection of seeds
I2S-7688-MP-74.CM.CoA.b.10.1 | E39 - Seed Collection, Revegetation and Rehabilitation | I.GG.PM.PA-2592 | CoA - E39 - Storage confirmed in safe location and confirmation of all species collected
I2S-7688-MP-74.CM.CoA.b.10.1 | E39 - Seed Collection, Revegetation and Rehabilitation | I.GG.PM.PA-2602 | CoA - E39 - Documentation of seed collection completed prior to commencement of veg clearing
Fauna Connectivity - NEW |  |  |  | 2024-10-21 | 2025-06-13
E40 to E41 - Fauna Crossings - Baseline Monitoring |  |  |  | 2025-05-02 | 2025-06-13
I2S-7688-MP-74.CM.CoA.b.11.4 | E40 to E41 - Fauna Crossings - Baseline Monitoring | I.GG.PM.BI-1440 | CoA - E40 - IRPL Winter Bird Surverys
I2S-7688-MP-74.CM.CoA.b.11.4 | E40 to E41 - Fauna Crossings - Baseline Monitoring | I.GG.PM.BI-1450 | CoA - E40 - BCS Consultation on Methodology
I2S-7688-MP-74.CM.CoA.b.11.4 | E40 to E41 - Fauna Crossings - Baseline Monitoring | I.GG.PM.BI-1360 | CoA - E40 - Purchase and procument collars (Start in Autumn)
I2S-7688-MP-74.CM.CoA.b.11.4 | E40 to E41 - Fauna Crossings - Baseline Monitoring | I.GG.PM.BI-1370 | CoA - E40 - Undertake Survey for squirrel glider
I2S-7688-MP-74.CM.CoA.b.11.4 | E40 to E41 - Fauna Crossings - Baseline Monitoring | I.GG.PM.BI-1380 | CoA - E40 - Complete Fauna connectivity Baseline Monitoring report
I2S-7688-MP-74.CM.CoA.b.11.4 | E40 to E41 - Fauna Crossings - Baseline Monitoring | I.GG.PM.BI-1250 | CoA - E40, E41_NEW - Update & address and Comments - Environmental - Fauna Crossing - Baseline Monitoring | 2025-05-30 | 2025-06-13
I2S-7688-MP-74.CM.CoA.b.11.4 | E40 to E41 - Fauna Crossings - Baseline Monitoring | I.GG.PM.BI-1230 | CoA - E40, E41_NEW - IRPL Review and issue Comments -Environmental - Fauna Crossing - Baseline Monitoring | 2025-05-02 | 2025-05-29
E44 - Fauna Connectivity Strategy |  |  |  | 2024-10-21 | 2025-06-13
I2S-7688-MP-74.CM.CoA.b.11.6 | E44 - Fauna Connectivity Strategy | I.GG.PM.BI-1460 | CoA - E44 - Fauna Con.Strategy - Consultation with BCS
I2S-7688-MP-74.CM.CoA.b.11.6 | E44 - Fauna Connectivity Strategy | I.GG.PM.BI-1470 | CoA - E44_A9 - JH to draft A9 letter
I2S-7688-MP-74.CM.CoA.b.11.6 | E44 - Fauna Connectivity Strategy | I.GG.PM.BI-1480 | CoA - E44_A9 - Submit to Inland Rail for review / Approval
I2S-7688-MP-74.CM.CoA.b.11.6 | E44 - Fauna Connectivity Strategy | I.GG.PM.BI-1490 | CoA - E44_A9 - Submit to DPHI for review / Approval
I2S-7688-MP-74.CM.CoA.b.11.6 | E44 - Fauna Connectivity Strategy | I.GG.PM.BI-1430 | CoA - E44_NEW - Inland Rail Review
I2S-7688-MP-74.CM.CoA.b.11.6 | E44 - Fauna Connectivity Strategy | I.GG.PM.BI-1260 | CoA - E44 - Fauna Con.Strategy - Finalise | 2025-03-11 | 2025-04-14
I2S-7688-MP-74.CM.CoA.b.11.6 | E44 - Fauna Connectivity Strategy | I.GG.PM.BI-1270 | CoA - E44 - Fauna Con.Strategy - Submit to DPHI for approval | 2025-05-30 | 2025-06-13
I2S-7688-MP-74.CM.CoA.b.11.6 | E44 - Fauna Connectivity Strategy | I.GG.PM.BI-1280 | CoA - E44 - Fauna Con.Strategy - IRPL Review and issue Comments | 2025-04-15 | 2025-05-15
I2S-7688-MP-74.CM.CoA.b.11.6 | E44 - Fauna Connectivity Strategy | I.GG.PM.BI-1320 | CoA - E44_NEW - Draft Fauna Connectivity Strategy | 2024-10-21 | 2024-11-29
I2S-7688-MP-74.CM.CoA.b.11.6 | E44 - Fauna Connectivity Strategy | I.GG.PM.BI-1330 | CoA - E44 - Fauna Con.Strategy - Consultation with DPHI | 2025-01-13 | 2025-03-10
E45 - NEW- Fauna funnel fencing &exclusion fencing |  |  |  | 2025-07-11 | 2025-07-24
I2S-7688-MP-74.CM.CoA.b.13 | E45 - NEW- Fauna funnel fencing &exclusion fencing | I.GG.PM.PA-2472 | CoA - E45 - Fauna funnel fencing - to prevent fauna from accessing rail alignment | 2025-07-11 | 2025-07-24
E68, E69, E70 - Operational Erosion Mitigation and Monitoring Program (OEMMP) (was E76, E77, E78) |  |  |  | 2025-05-20 | 2026-03-10
I2S-7688-MP-74.CM.CoA.b.5 | E68, E69, E70 - Operational Erosion Mitigation and Monitoring Program (OEMMP) (was E76, E77, E78) | I.GG.PM.PA-2222 | CoA - E70 - Operational Erosion and Mitigation and Monitoring Program - (OEMMP) - Submit to IRPL | 2025-12-04 | 2026-01-27
I2S-7688-MP-74.CM.CoA.b.5 | E68, E69, E70 - Operational Erosion Mitigation and Monitoring Program (OEMMP) (was E76, E77, E78) | I.GG.PM.PA-2232 | CoA - E70 - OEMMP - JH submit to IRPL for Final approval | 2026-02-25 | 2026-03-10
I2S-7688-MP-74.CM.CoA.b.5 | E68, E69, E70 - Operational Erosion Mitigation and Monitoring Program (OEMMP) (was E76, E77, E78) | CoA-1650 | CoA - E68 - Prepare Operational Erosion and Mitigation and Monitoring Program - (OEMMP) | 2025-05-20 | 2025-06-18
I2S-7688-MP-74.CM.CoA.b.5 | E68, E69, E70 - Operational Erosion Mitigation and Monitoring Program (OEMMP) (was E76, E77, E78) | I.GG.PM.PA-2322 | CoA - E69 - OEMMP - Update & address and Comments - Environmental | 2026-01-28 | 2026-02-24
I2S-7688-MP-74.CM.CoA.b.5 | E68, E69, E70 - Operational Erosion Mitigation and Monitoring Program (OEMMP) (was E76, E77, E78) | CoA-2090 | CoA - E69 - OEMMP - Prepare in consult with BCS, DCCEEW | 2025-05-20 | 2025-06-17
I2S-7688-MP-74.CM.CoA.b.5 | E68, E69, E70 - Operational Erosion Mitigation and Monitoring Program (OEMMP) (was E76, E77, E78) | CoA-3560 | CoA - E69 - OEMMP - JH update OEMMP as per IRPL comments
I2S-7688-MP-74.CM.CoA.b.5 | E68, E69, E70 - Operational Erosion Mitigation and Monitoring Program (OEMMP) (was E76, E77, E78) | CoA-3570 | CoA - E69 - OEMMP - JH update OEMMP as per IRPL comments - Stage 2
Key Issues - Heritage |  |  |  | 2024-09-30 | 2025-02-04
A17 - Unexpected and Incidental Finds Protocol (was A19) |  |  |  | 2024-09-30 | 2024-11-19
I2S-7688-MP-74.CM.CoA.12.7 | A17 - Unexpected and Incidental Finds Protocol (was A19) | I.GG.15360 | CoA - A17 - Develop Unexpected Heritage & Incidental Finds Protocol | 2024-09-30 | 2024-10-28
I2S-7688-MP-74.CM.CoA.12.7 | A17 - Unexpected and Incidental Finds Protocol (was A19) | I.GG.15370 | CoA - A17 - Make Protocol publicly available - Unexpected Heritage and Incidental Find Protocol | 2024-10-29 | 2024-11-18
I2S-7688-MP-74.CM.CoA.12.7 | A17 - Unexpected and Incidental Finds Protocol (was A19) | CoA-1760 | CoA - A17 - Unexpected Heritage & Incidental Finds Protocol - Approval - for LIW Approval | 2024-11-19 | 2024-11-19
E132 - Aboriginal Community and Stakeholder Engagement Strategy (was E145) |  |  |  | 2024-09-30 | 2024-10-28
I2S-7688-MP-74.CM.CoA.12.12 | E132 - Aboriginal Community and Stakeholder Engagement Strategy (was E145) | CoA-1590 | COA - E132 - Develop Aboriginal Community and Stakeholder Engagement Strategy | 2024-09-30 | 2024-10-28
I2S-7688-MP-74.CM.CoA.12.12 | E132 - Aboriginal Community and Stakeholder Engagement Strategy (was E145) | I.GG.CEMP.16610 | COA - E132- JH Respond to stakeholder comments -
I2S-7688-MP-74.CM.CoA.12.12 | E132 - Aboriginal Community and Stakeholder Engagement Strategy (was E145) | I.GG.CEMP.16620 | COA - E132- JH Submission to RAPS for consideration
I2S-7688-MP-74.CM.CoA.12.12 | E132 - Aboriginal Community and Stakeholder Engagement Strategy (was E145) | I.GG.CEMP.16600 | COA - E132 - Initial submiission to IRPL for review (4 weeks/ 28 cd)
I2S-7688-MP-74.CM.CoA.12.12 | E132 - Aboriginal Community and Stakeholder Engagement Strategy (was E145) | I.GG.CEMP.16590 | COA - E132- Submit of Draft of Engagement Strategy methodology to IRPL
I2S-7688-MP-74.CM.CoA.12.12 | E132 - Aboriginal Community and Stakeholder Engagement Strategy (was E145) | I.GG.CEMP.16630 | COA - E132- Knowledge Keeper Review Period
E143 - Unexpected Heritage Finds and Human Remains Procedure (was E154) |  |  |  | 2024-12-10 | 2025-02-04
I2S-7688-MP-74.CM.CoA.12.27 | E143 - Unexpected Heritage Finds and Human Remains Procedure (was E154) | I.GG.MR.AnF.5-314 | CoA - E143 - Update Plan to Reflect any Comments - Unexpected Heritage Finds and Human Remains Procedure (Del incl A17) | 2025-01-21 | 2025-02-04
I2S-7688-MP-74.CM.CoA.12.27 | E143 - Unexpected Heritage Finds and Human Remains Procedure (was E154) | I.GG.MR.AnF.5-324 | CoA - E143 - IRPL to review updated documents and Approve - Unexpected Heritage Finds and Human Remains Procedure |  | 2025-02-04
I2S-7688-MP-74.CM.CoA.12.27 | E143 - Unexpected Heritage Finds and Human Remains Procedure (was E154) | I.GG.MR.AnF.5-304 | CoA - E143 - IRPL/ Planning Sec Review Period - Unexpected Heritage Finds and Human Remains Procedure (Del incl A17) | 2024-12-10 | 2025-01-20
Key Issues - Water and Flooding |  |  |  | 2024-10-03 | 2025-05-12
E59 - Flood Design Consultation Protocol (was E35 - E54) |  |  |  | 2024-10-03 | 2024-10-24
I2S-7688-MP-74.CM.CoA.4.22 | E59 - Flood Design Consultation Protocol (was E35 - E54) | I.GG.16570 | CoA - E59 - FDCP Accepted by IRPL & Made Publicly Available on Website by IRPL
I2S-7688-MP-74.CM.CoA.4.22 | E59 - Flood Design Consultation Protocol (was E35 - E54) | I.GG.16580 | CoA - E59 - IRPL Review & Approve protocol
I2S-7688-MP-74.CM.CoA.4.22 | E59 - Flood Design Consultation Protocol (was E35 - E54) | I.GG.16540 | CoA - E59 - JHG to submit Flood Design Consultation Protocol
I2S-7688-MP-74.CM.CoA.4.22 | E59 - Flood Design Consultation Protocol (was E35 - E54) | I.GG.16550 | CoA - E59 - IRPL Review
I2S-7688-MP-74.CM.CoA.4.22 | E59 - Flood Design Consultation Protocol (was E35 - E54) | I.GG.15550 | CoA - E59 - Flood Design Consultation Protocol - Prepare | 2024-10-03 | 2024-10-24
I2S-7688-MP-74.CM.CoA.4.22 | E59 - Flood Design Consultation Protocol (was E35 - E54) | I.GG.16560 | CoA - E59 - JH Update comments & Re-submit to IRPL
E60,61,62,63 - Erosion Threshold Velocities Methodologies (was E36/37/38/39 - E55,56,57,58) |  |  |  | 2025-01-08 | 2025-05-12
I2S-7688-MP-74.CM.CoA.4.15 | E60,61,62,63 - Erosion Threshold Velocities Methodologies (was E36/37/38/39 - E55,56,57,58) | I.DE.95.8020 | CoA - E60, E61, E62, E63 - Provide appraisal of design velocity limits - design of drainage infrastructure (ETV) - CoA | 2025-01-15 | 2025-01-21
I2S-7688-MP-74.CM.CoA.4.15 | E60,61,62,63 - Erosion Threshold Velocities Methodologies (was E36/37/38/39 - E55,56,57,58) | I.DE.95.8010 | CoA - E60, E61, E62, E63 - Review ETV results / the soil testing results (ETV results) | 2025-01-08 | 2025-01-14
I2S-7688-MP-74.CM.CoA.4.15 | E60,61,62,63 - Erosion Threshold Velocities Methodologies (was E36/37/38/39 - E55,56,57,58) | CoA-1670 | CoA - E60, E61, E62, E63 - Erosion Threshold Velocities (ETV) Methodologies/Report | 2025-01-08 | 2025-02-05
I2S-7688-MP-74.CM.CoA.4.15 | E60,61,62,63 - Erosion Threshold Velocities Methodologies (was E36/37/38/39 - E55,56,57,58) | CoA-1960 | CoA - E60, E61, E62, E63 - Submission to Planning Secetary - Erosion Threshold Velocities (ETV) Methodologies/Report | 2025-03-06 | 2025-03-12
I2S-7688-MP-74.CM.CoA.4.15 | E60,61,62,63 - Erosion Threshold Velocities Methodologies (was E36/37/38/39 - E55,56,57,58) | CoA-1970 | CoA - E60, E61, E62, E63 - Review/Approval by Planning Secetary- Erosion Threshold Velocities (ETV) Methodologies/Report | 2025-04-10 | 2025-05-12
E48 - Flood Modelling Assessment (was E43 ) |  |  |  | 2024-10-03 | 2025-04-09
I2S-7688-MP-74.CM.CoA.4.1 | E48 - Flood Modelling Assessment (was E43 ) | I.DE.00.9700 | CoA - E48 - Flooding Model / Assessment- 1st Issue | 2024-10-03 | 2024-12-05
I2S-7688-MP-74.CM.CoA.4.1 | E48 - Flood Modelling Assessment (was E43 ) | I.DE.00.9710 | CoA - E48 - Flooding Model/Assessment -Final Issue | 2025-02-06 | 2025-04-09
E71 - Spatially defined monitoring zones - Flood review report (was E81) |  |  |  | 2024-10-25 | 2024-12-19
I2S-7688-MP-74.CM.CoA.4.14 | E71 - Spatially defined monitoring zones - Flood review report (was E81) | CoA-1660 | CoA - E71 - Spatially Defined Monitoring Zones/ Flood - Develop report | 2024-10-25 | 2024-11-21
I2S-7688-MP-74.CM.CoA.4.14 | E71 - Spatially defined monitoring zones - Flood review report (was E81) | CoA-2100 | CoA - E72 - Spatially Defined Monitoring Zones/ Flood - Review (To be completed 6M before Operational) | 2024-11-22 | 2024-12-19
E60 to E63 - Erosion Threshold Velocities (ETVs) - E60-E63 (NEW)
Landloch Desktop Study
I2S-7688-MP-74.CM.CoA.4.2.1 | Landloch Desktop Study | I.DE.95.1021 | COA - ETV - E60 to E63 - Landloch Technical Memorandum submission to JHG
I2S-7688-MP-74.CM.CoA.4.2.1 | Landloch Desktop Study | I.DE.95.1030 | COA - ETV - E60 to E63 - JHG review of technical memorandum
I2S-7688-MP-74.CM.CoA.4.2.1 | Landloch Desktop Study | I.DE.95.8040 | COA - ETV - E60 to E63 - DPHI Approval Process
I2S-7688-MP-74.CM.CoA.4.2.1 | Landloch Desktop Study | I.DE.95.1001 | COA - ETV - E60 to E63 - Submission of Landloch methodology to IRPL
I2S-7688-MP-74.CM.CoA.4.2.1 | Landloch Desktop Study | I.DE.95.1010 | COA - ETV - E60 to E63 - Landloch Geo-mapping
Landloch ETV Report
I2S-7688-MP-74.CM.CoA.4.2.2 | Landloch ETV Report | I.DE.95.8050 | COA - ETV - E60 to E63 - Landloch geo-lab testings - Part 2
I2S-7688-MP-74.CM.CoA.4.2.2 | Landloch ETV Report | I.DE.95.1040 | COA - ETV - E60 to E63 - Landloch field works
I2S-7688-MP-74.CM.CoA.4.2.2 | Landloch ETV Report | I.DE.95.1050 | COA - ETV - E60 to E63 - Landloch geo-lab testings - Part 1
I2S-7688-MP-74.CM.CoA.4.2.2 | Landloch ETV Report | I.DE.95.1060 | COA - ETV - E60 to E63 - Landloch advise of ETV Values to JHG to be adopted
I2S-7688-MP-74.CM.CoA.4.2.2 | Landloch ETV Report | I.DE.95.1100 | COA - ETV - E60 to E63 - Landloch ETV Report compilation
I2S-7688-MP-74.CM.CoA.4.2.2 | Landloch ETV Report | I.DE.95.1110 | COA - ETV - E60 to E63 - ETV Report submission to JHG
JHG submit ETV Report to IRPL
I2S-7688-MP-74.CM.CoA.4.2.3 | JHG submit ETV Report to IRPL | I.DE.95.8030 | COA - ETV - E60 to E63 - IRPL Approval
I2S-7688-MP-74.CM.CoA.4.2.3 | JHG submit ETV Report to IRPL | I.DE.95.1120 | COA - ETV - E60 to E63 - JHG submit ETV Report to IRPL
Planning Secretary Review of ETV report
I2S-7688-MP-74.CM.CoA.4.2.4 | Planning Secretary Review of ETV report | I.DE.95.1160 | COA - ETV - E60 to E63 - Planning Secretary Review of ETV report
I2S-7688-MP-74.CM.CoA.4.2.4 | Planning Secretary Review of ETV report | I.DE.95.8220 | COA - ETV - E60 to E63 - Update and Address comments
E64, E65, E66 - Flood Design Verification Report FDVR (was E40 / E41/E42 ) |  |  |  | 2024-10-25 | 2025-02-28
I2S-7688-MP-74.CM.CoA.4.19 | E64, E65, E66 - Flood Design Verification Report FDVR (was E40 / E41/E42 ) | CoA-1620 | CoA - E64, E65, E66 - Flood Design Verification Report (FDVR)- 1st Issue | 2024-10-25 | 2024-11-21
I2S-7688-MP-74.CM.CoA.4.19 | E64, E65, E66 - Flood Design Verification Report FDVR (was E40 / E41/E42 ) | CoA-1900 | CoA - E64, E65, E66 - Flood Design Verification Report (FDVR) - Final Issue - not required | 2025-02-03 | 2025-02-28
I2S-7688-MP-74.CM.CoA.4.19 | E64, E65, E66 - Flood Design Verification Report FDVR (was E40 / E41/E42 ) | I.DE.00.9730 | CoA - E66 - update comments to Flood Design Verification Report (FDVR | 2025-01-17 | 2025-01-31
E64 to E66 - Flood Design Verification Report (FDVR) - E64 to E66 (NEW) |  |  |  | 2025-04-10 | 2025-05-12
E64-E66 - FDVR - D9 Flood Modelling and Impact Assessment development
I2S-7688-MP-74.CM.CoA.4.3.1 | E64-E66 - FDVR - D9 Flood Modelling and Impact Assessment development | I.DE.95.1070 | CoA - D9 - E64 to E66 - Incorporate ETV values from Landloch
I2S-7688-MP-74.CM.CoA.4.3.1 | E64-E66 - FDVR - D9 Flood Modelling and Impact Assessment development | I.DE.95.1080 | CoA - D9 - E64 to E66 - Continue flood modelling development after incorporate ETV Values
Approval of Compliant Design
I2S-7688-MP-74.CM.CoA.4.3.8 | Approval of Compliant Design | I.DE.95.1210 | CoA - E64 to E66 - FDVR - Develop and submit Tech memo to IRPL - Stockinbingal - Flooding Summary - IR2200-RFI-000057
I2S-7688-MP-74.CM.CoA.4.3.8 | Approval of Compliant Design | I.DE.95.8130 | CoA - E64 to E66 - FDVR - Tech memo - IRPL - review and approve
I2S-7688-MP-74.CM.CoA.4.3.8 | Approval of Compliant Design | I.DE.95.8170 | CoA - E64 to E66 - FDVR - Develop and submit Tech memo to IRPL - ARR 2019 V4.2 - Design Implications
I2S-7688-MP-74.CM.CoA.4.3.8 | Approval of Compliant Design | I.DE.95.8180 | CoA - E64 to E66 - FDVR - update to flow model and Tech memo to IRPL - ARR 2019 V4.2 - Design Implications
I2S-7688-MP-74.CM.CoA.4.3.8 | Approval of Compliant Design | I.DE.95.8190 | CoA - E64 to E66 - FDVR - Tech memo - DPHI - review and acceptance
E64-E66 - FDVR - Independent Review of Flood Modelling (E65)
I2S-7688-MP-74.CM.CoA.4.3.2 | E64-E66 - FDVR - Independent Review of Flood Modelling (E65) | I.DE.95.8070 | CoA - E65 - DPHI Acceptance of Peer Reviewer Candidate
I2S-7688-MP-74.CM.CoA.4.3.2 | E64-E66 - FDVR - Independent Review of Flood Modelling (E65) | I.DE.95.1090 | CoA - E65 - Issue flood modelling log to KBR
I2S-7688-MP-74.CM.CoA.4.3.2 | E64-E66 - FDVR - Independent Review of Flood Modelling (E65) | I.DE.95.1130 | CoA - E65 - Independent flood modelling review
I2S-7688-MP-74.CM.CoA.4.3.2 | E64-E66 - FDVR - Independent Review of Flood Modelling (E65) | I.DE.95.1150 | CoA - E65 - Comment close out
I2S-7688-MP-74.CM.CoA.4.3.2 | E64-E66 - FDVR - Independent Review of Flood Modelling (E65) | I.DE.95.1140 | CoA - E65 - KBR complete flood modelling comparison report
E64-E66 - FDVR - Compilation of FDVR incorporating (D9, Independent Review and ETV) |  |  |  | 2025-04-10 | 2025-05-12
I2S-7688-MP-74.CM.CoA.4.3.3 | E64-E66 - FDVR - Compilation of FDVR incorporating (D9, Independent Review and ETV) | I.DE.95.8120 | CoA - E64 to E66 - FDVR - Commence Community and Road Authority Consultation - Flooding Report Approvals
I2S-7688-MP-74.CM.CoA.4.3.3 | E64-E66 - FDVR - Compilation of FDVR incorporating (D9, Independent Review and ETV) | I.DE.95.8080 | CoA - E64 to E66 - FDVR - Update (D9) Flood Modelling
I2S-7688-MP-74.CM.CoA.4.3.3 | E64-E66 - FDVR - Compilation of FDVR incorporating (D9, Independent Review and ETV) | I.DE.95.8090 | CoA - E64 to E66 - FDVR - Comment Close Out workshop with IRPL
I2S-7688-MP-74.CM.CoA.4.3.3 | E64-E66 - FDVR - Compilation of FDVR incorporating (D9, Independent Review and ETV) | I.DE.95.8060 | CoA - E64 to E66 - FDVR - IRPL Review (Inc D9)
I2S-7688-MP-74.CM.CoA.4.3.3 | E64-E66 - FDVR - Compilation of FDVR incorporating (D9, Independent Review and ETV) | I.DE.95.1170 | CoA - E64 to E66 - FDVR - Compilation of FDVR incorporating (D9, Independent Review and ETV)
I2S-7688-MP-74.CM.CoA.4.3.3 | E64-E66 - FDVR - Compilation of FDVR incorporating (D9, Independent Review and ETV) | I.DE.95.1180 | CoA - E64 to E66 - FDVR - Review of FDVR incl. flood modelling by Stakeholders (BCS, DCCEEW Water, TfNSW, Councils)
I2S-7688-MP-74.CM.CoA.4.3.3 | E64-E66 - FDVR - Compilation of FDVR incorporating (D9, Independent Review and ETV) | I.DE.95.1190 | CoA - E64 to E66 - FDVR - Address comments from external stakeholders (BCS, DCCEEW Water, TfNSW, Councils)
I2S-7688-MP-74.CM.CoA.4.3.3 | E64-E66 - FDVR - Compilation of FDVR incorporating (D9, Independent Review and ETV) | I.DE.95.8110 | CoA - E64 to E66 - FDVR - IRPL to submit FDVR to DPHI
I2S-7688-MP-74.CM.CoA.4.3.3 | E64-E66 - FDVR - Compilation of FDVR incorporating (D9, Independent Review and ETV) | I.DE.95.1200 | CoA - E64 to E66 - FDVR - update CPHR DCCEEW and submit FDVR to IRPL (Allow for Doc Control)
I2S-7688-MP-74.CM.CoA.4.3.3 | E64-E66 - FDVR - Compilation of FDVR incorporating (D9, Independent Review and ETV) | I.DE.00.9740 | CoA - E64 to E66 - FDVR - 1st A9 submission - DPHI Review of Flood Design Verification Report | 2025-04-10 | 2025-05-12
I2S-7688-MP-74.CM.CoA.4.3.3 | E64-E66 - FDVR - Compilation of FDVR incorporating (D9, Independent Review and ETV) | I.DE.95.1220 | CoA - E64 to E66 - FDVR - 1st A9 submission - approval - low risk activities
I2S-7688-MP-74.CM.CoA.4.3.3 | E64-E66 - FDVR - Compilation of FDVR incorporating (D9, Independent Review and ETV) | I.DE.95.1230 | CoA - E64 to E66 - FDVR - Review and Approval of FDVR by Stakeholders (BCS, DCCEEW Water, Councils)
I2S-7688-MP-74.CM.CoA.4.3.3 | E64-E66 - FDVR - Compilation of FDVR incorporating (D9, Independent Review and ETV) | I.DE.95.8140 | CoA - E64 to E66 - FDVR - Issue Updated Flood Modelling - KBR Independent Review
I2S-7688-MP-74.CM.CoA.4.3.3 | E64-E66 - FDVR - Compilation of FDVR incorporating (D9, Independent Review and ETV) | I.DE.95.8150 | CoA - E64 to E66 - FDVR - Update FDVR based on Flood Modelling and final JH review
I2S-7688-MP-74.CM.CoA.4.3.3 | E64-E66 - FDVR - Compilation of FDVR incorporating (D9, Independent Review and ETV) | I.DE.95.8160 | CoA - E64 to E66 - FDVR - Submit FDVR to IRPL (and DPHI for Information)
I2S-7688-MP-74.CM.CoA.4.3.3 | E64-E66 - FDVR - Compilation of FDVR incorporating (D9, Independent Review and ETV) | I.DE.95.8200 | CoA - E64 to E66 - FDVR - TfNSW comments addresed concurrent with DPHI review
I2S-7688-MP-74.CM.CoA.4.3.3 | E64-E66 - FDVR - Compilation of FDVR incorporating (D9, Independent Review and ETV) | I.DE.95.8210 | CoA - E64 to E66 - FDVR - Issue Updated Flood Modelling - post KBR Independent Review
I2S-7688-MP-74.CM.CoA.4.3.3 | E64-E66 - FDVR - Compilation of FDVR incorporating (D9, Independent Review and ETV) | I.DE.00.12320 | CoA - E64 to E66 - FDVR - DPHI Review of Flood Design Verification Report
I2S-7688-MP-74.CM.CoA.4.3.3 | E64-E66 - FDVR - Compilation of FDVR incorporating (D9, Independent Review and ETV) | I.DE.95.8230 | CoA - E64 to E66 - FDVR - FDVR - approval - high risk activities
E73 - Flood Emergency Response Plan (FERP) (was E79/80)
I2S-7688-MP-74.CM.CoA.4.17 | E73 - Flood Emergency Response Plan (FERP) (was E79/80) | CoA-3260 | CoA - E73 - JH Inital Submission of Plan to IRPL for Review
I2S-7688-MP-74.CM.CoA.4.17 | E73 - Flood Emergency Response Plan (FERP) (was E79/80) | CoA-3270 | CoA - E73 - JH Internal Review
I2S-7688-MP-74.CM.CoA.4.17 | E73 - Flood Emergency Response Plan (FERP) (was E79/80) | CoA-3280 | CoA - E73 - JH Resubmission of plan to IRPL for ARTC review
I2S-7688-MP-74.CM.CoA.4.17 | E73 - Flood Emergency Response Plan (FERP) (was E79/80) | CoA-3290 | CoA - E73 - FERP - IRPL to review updated documents and Approve
I2S-7688-MP-74.CM.CoA.4.17 | E73 - Flood Emergency Response Plan (FERP) (was E79/80) | CoA-3540 | CoA - E73 - JH Resubmission of plan - IRPL - Comments close out
I2S-7688-MP-74.CM.CoA.4.17 | E73 - Flood Emergency Response Plan (FERP) (was E79/80) | CoA-3550 | CoA - E73 - JH Resubmission of plan - IRPL - Review
E85 - Surface Water Monitoring Program (was E93) |  |  |  | 2024-12-12 | 2025-01-22
I2S-7688-MP-74.CM.CoA.4.35 | E85 - Surface Water Monitoring Program (was E93) | CoA-1800 | CoA - E85 - Surface Water Monitoring Program submitted to and approved by the PS (Captured in Soil & Water Mtg Plan) | 2024-12-12 | 2025-01-22
E80 - Farm Dam Register |  |  |  | 2024-10-03 | 2025-01-09
I2S-7688-MP-74.CM.CoA.4.6 | E80 - Farm Dam Register | CoA-1530 | CoA - E79 + E80 - Farm Dam - landowner and road authority consultation - prior to construction - Culvert design | 2024-10-03 | 2024-11-07
I2S-7688-MP-74.CM.CoA.4.6 | E80 - Farm Dam Register | CoA-1980 | CoA - E80_NEW - Collate data for Farm Dam Register (80 to 100 off (4pd)) | 2024-11-08 | 2024-12-12
I2S-7688-MP-74.CM.CoA.4.6 | E80 - Farm Dam Register | CoA-1990 | CoA - E80_NEW - Finalise Farm Dam Register | 2024-12-13 | 2025-01-09
I2S-7688-MP-74.CM.CoA.4.6 | E80 - Farm Dam Register | CoA-2110 | CoA - E81 _NEW - Design longitudinal drainage and the cross drainage | 2024-12-13 | 2025-01-09
I2S-7688-MP-74.CM.CoA.4.6 | E80 - Farm Dam Register | CoA-2120 | CoA - E82_NEW- designed to pass flood and surface water flows through the rail formation | 2024-12-12 | 2025-01-08
E149 - Water Reuse Strategy (was E92 (E90)) |  |  |  | 2024-10-03 | 2024-10-31
I2S-7688-MP-74.CM.CoA.4.8 | E149 - Water Reuse Strategy (was E92 (E90)) | CoA-3480 | CoA - E149_NEW - Submit to IRPL for review
I2S-7688-MP-74.CM.CoA.4.8 | E149 - Water Reuse Strategy (was E92 (E90)) | CoA-3490 | CoA - E149_NEW - JH to adress comments and resubmit
I2S-7688-MP-74.CM.CoA.4.8 | E149 - Water Reuse Strategy (was E92 (E90)) | CoA-3500 | CoA - E149_NEW - IRPL review and Approve
I2S-7688-MP-74.CM.CoA.4.8 | E149 - Water Reuse Strategy (was E92 (E90)) | CoA-1550 | CoA - E149_NEW - Develop Water reuse Strategy | 2024-10-03 | 2024-10-31
Key Issues - Roads and Traffic |  |  |  | 2024-09-30 | 2025-08-05
Burley Griffin Way Minsterial Process Section 99B of Transport Administration Act |  |  |  | 2025-03-05 | 2025-08-05
I2S-7688-MP-74.CM.CoA.8.3 | Burley Griffin Way Minsterial Process Section 99B of Transport Administration Act | I.GG.MR.AnF.5-1074 | COA - BGW LX closure - Minister reviews documentation to close level crossings (6 months) | 2025-03-05 | 2025-08-05
I2S-7688-MP-74.CM.CoA.8.3 | Burley Griffin Way Minsterial Process Section 99B of Transport Administration Act | I.GG.MR.AnF.5-1474 | COA - BGW LX closure - IRPL prepare briefing note
I2S-7688-MP-74.CM.CoA.8.3 | Burley Griffin Way Minsterial Process Section 99B of Transport Administration Act | I.GG.MR.AnF.5-1484 | COA - BGW LX closure - JH update briefing note
I2S-7688-MP-74.CM.CoA.8.3 | Burley Griffin Way Minsterial Process Section 99B of Transport Administration Act | I.GG.MR.AnF.5-1494 | COA - BGW LX closure - issue briefing note to IRPL for review
I2S-7688-MP-74.CM.CoA.8.3 | Burley Griffin Way Minsterial Process Section 99B of Transport Administration Act | I.GG.MR.AnF.5-1504 | COA - BGW LX closure - IRPL changes
I2S-7688-MP-74.CM.CoA.8.3 | Burley Griffin Way Minsterial Process Section 99B of Transport Administration Act | I.GG.MR.AnF.5-1514 | COA - BGW LX closure - Consultation with local council and TfNSW to obtain 'No Objection' - revised procedure
I2S-7688-MP-74.CM.CoA.8.3 | Burley Griffin Way Minsterial Process Section 99B of Transport Administration Act | I.GG.MR.AnF.5-1524 | COA - BGW LX closure - Issue a letter to the public of the proposed changes
I2S-7688-MP-74.CM.CoA.8.3 | Burley Griffin Way Minsterial Process Section 99B of Transport Administration Act | I.GG.MR.AnF.5-1534 | COA - BGW LX closure - Issue briefing note and evidence to Minister for approval
I2S-7688-MP-74.CM.CoA.8.3 | Burley Griffin Way Minsterial Process Section 99B of Transport Administration Act | I.GG.MR.AnF.5-1544 | COA - BGW LX closure - Approval to close BGW LX received
I2S-7688-MP-74.CM.CoA.8.3 | Burley Griffin Way Minsterial Process Section 99B of Transport Administration Act | I.GG.MR.AnF.5-1634 | COA - BGW LX closure - IRPL review of briefing note -as advised by AT (IRPL)
I2S-7688-MP-74.CM.CoA.8.3 | Burley Griffin Way Minsterial Process Section 99B of Transport Administration Act | I.GG.MR.AnF.5-1644 | COA - BGW LX closure - briefing note to IRPL for review - re-issue
I2S-7688-MP-74.CM.CoA.8.3 | Burley Griffin Way Minsterial Process Section 99B of Transport Administration Act | I.GG.MR.AnF.5-1664 | COA - BGW LX closure - Advise Minister on LX decommission date - 60 days notice prior to final possession start
I2S-7688-MP-74.CM.CoA.8.3 | Burley Griffin Way Minsterial Process Section 99B of Transport Administration Act | I.GG.MR.AnF.5-1674 | COA - BGW LX closure - IRPL issue to TfNSW
I2S-7688-MP-74.CM.CoA.8.3 | Burley Griffin Way Minsterial Process Section 99B of Transport Administration Act | I.GG.MR.AnF.5-1684 | COA - BGW LX closure - TfNSW issue to Minister - Initial
E86 - Construction traffic |  |  |  | 2024-09-30 | 2025-05-07
I2S-7688-MP-74.CM.CoA.8.1 | E86 - Construction traffic | CoA-2130 | CoA - E86 - requirements for road use - no local road use permitted unless no alternatives are available | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.CoA.8.1 | E86 - Construction traffic | I.GG.CG.6960 | CoA - E100 - Road Closure /Diversion Notification - 1 M movement restrictions on Old Coota Road underbridge | 2025-04-23 | 2025-05-07
E102 - NEW - Road Upgrade |  |  |  | 2024-09-30 | 2025-04-29
Management - /Council |  |  |  | 2024-11-28 | 2025-02-27
I2S-7688-MP-74.CM.CoA.8.2.4 | Management - /Council | CoA-3510 | CoA - E102 - NEW - Road Dilapidation Report Submission to IRPL. CA received from IRPL
I2S-7688-MP-74.CM.CoA.8.2.4 | Management - /Council | CoA-3520 | CoA - E102 - NEW - Road Dilapidation Report Submission to IRPL. Final response to CA
I2S-7688-MP-74.CM.CoA.8.2.4 | Management - /Council | CoA-3530 | CoA - E102 - NEW - Road Dilapidation Report Submission to IRPL. Provide 2 weeks before construction/road use.
I2S-7688-MP-74.CM.CoA.8.2.4 | Management - /Council | CoA-2150 | CoA - E102 - NEW - Road Upgrade - Initial consultation with Council | 2024-11-28 | 2025-02-27
Eng |  |  |  | 2024-11-28 | 2025-01-08
I2S-7688-MP-74.CM.CoA.8.2.1 | Eng | CoA-2440 | CoA - E102 - NEW - Road Dilapidation Survey - Prepare and issue Report | 2024-11-28 | 2025-01-08
Proc |  |  |  | 2024-09-30 | 2025-04-29
I2S-7688-MP-74.CM.CoA.8.2.2 | Proc | CoA-2140 | CoA - E102 - NEW - Road Dilapidation Survey - Prepare subcontractor package | 2024-09-30 | 2024-10-04
I2S-7688-MP-74.CM.CoA.8.2.2 | Proc | CoA-2190 | CoA - E102 - NEW - Road Upgrade - Procurement | 2025-02-21 | 2025-04-29
I2S-7688-MP-74.CM.CoA.8.2.2 | Proc | CoA-2200 | CoA - E102 - NEW - Road Upgrade - Subcontractor agreements | 2025-03-07 | 2025-04-29
I2S-7688-MP-74.CM.CoA.8.2.2 | Proc | CoA-2400 | CoA - E102 - NEW - Road Dilapidation Survey - Issue to market and tender | 2024-10-08 | 2024-10-18
I2S-7688-MP-74.CM.CoA.8.2.2 | Proc | CoA-2410 | CoA - E102 - NEW - Road Dilapidation Survey - Negotiate and award contract | 2024-10-21 | 2024-10-25
Site works / Construction |  |  |  | 2024-10-28 | 2025-02-27
I2S-7688-MP-74.CM.CoA.8.2.3 | Site works / Construction | CoA-2160 | CoA - E102 - NEW - Road Upgrade - Council independent review of local roads | 2025-02-13 | 2025-02-27
I2S-7688-MP-74.CM.CoA.8.2.3 | Site works / Construction | CoA-2420 | CoA - E102 - NEW - Road Dilapidation Survey - Mobilise to site (depending on availability) | 2024-10-28 | 2024-11-11
I2S-7688-MP-74.CM.CoA.8.2.3 | Site works / Construction | CoA-2430 | CoA - E102 - NEW - Road Dilapidation Survey - Conduct survey | 2024-11-12 | 2024-11-27
Post Construction |  |  |  | 2024-11-28 | 2025-04-29
I2S-7688-MP-74.CM.CoA.8.2.5 | Post Construction | CoA-2180 | CoA - E102 - Road Upgrade - Design - Stage 2 - post council comments | 2025-02-28 | 2025-04-29
I2S-7688-MP-74.CM.CoA.8.2.5 | Post Construction | CoA-2230 | CoA - E102 - Road Upgrade - Design - stage 1 - post dilap report | 2024-11-28 | 2025-02-20
E88 - Public Level Crossing Treatment Report (was E99) |  |  |  | 2024-09-30 | 2024-12-09
I2S-7688-MP-74.CM.CoA.8.29 | E88 - Public Level Crossing Treatment Report (was E99) | I.GG.MR.AnF.5-1694 | CoA - E88 - Public LX Rpt - Junee Council - Acceptance Letter - Old Sydney Rd & Unnamed Rd
I2S-7688-MP-74.CM.CoA.8.29 | E88 - Public Level Crossing Treatment Report (was E99) | I.GG.MR.AnF.5-1704 | CoA - E88 - Public LX Rpt - IRPL Comment closeout - Public LX
I2S-7688-MP-74.CM.CoA.8.29 | E88 - Public Level Crossing Treatment Report (was E99) | I.GG.MR.AnF.5-1714 | CoA - E88 - Public LX Rpt - Re-Submission to IRPL (Rev -C) - Public LX
I2S-7688-MP-74.CM.CoA.8.29 | E88 - Public Level Crossing Treatment Report (was E99) | I.GG.MR.AnF.5-954 | CoA - E88 - Prepare & Submit to IRPL PM / Project Verifier - Public Level Crossing Treatment Report | 2024-09-30 | 2024-11-11
I2S-7688-MP-74.CM.CoA.8.29 | E88 - Public Level Crossing Treatment Report (was E99) | I.GG.MR.AnF.5-964 | CoA - E88 - IRPL Review Period - Public Level Crossing Treatment Report | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.CM.CoA.8.29 | E88 - Public Level Crossing Treatment Report (was E99) | I.GG.MR.AnF.5-1334 | CoA - E88 - Public LX Rpt - Re-Submission to IRPL (Rev -B) - Public LX
I2S-7688-MP-74.CM.CoA.8.29 | E88 - Public Level Crossing Treatment Report (was E99) | I.GG.MR.AnF.5-1344 | CoA - E88 - Public LX Rpt - Consultation with TfNSW & Councils - Public LX
I2S-7688-MP-74.CM.CoA.8.29 | E88 - Public Level Crossing Treatment Report (was E99) | I.GG.MR.AnF.5-1354 | CoA - E88 - Public LX Rpt - Submit to Planning Secretary for review - Public LX
I2S-7688-MP-74.CM.CoA.8.29 | E88 - Public Level Crossing Treatment Report (was E99) | I.GG.MR.AnF.5-1364 | CoA - E88 - Public LX Rpt - Planning Secretary Approval - Public LX
I2S-7688-MP-74.CM.CoA.8.29 | E88 - Public Level Crossing Treatment Report (was E99) | I.GG.MR.AnF.5-1374 | CoA - E88 - Public LX Rpt - Construction commencement of Roadworks - Public LX
I2S-7688-MP-74.CM.CoA.8.29 | E88 - Public Level Crossing Treatment Report (was E99) | I.GG.MR.AnF.5-1384 | CoA - E88 - JH respond to comments, update LX treatment Report & re-issue to IRPL for comment close-out - Public LX
I2S-7688-MP-74.CM.CoA.8.29 | E88 - Public Level Crossing Treatment Report (was E99) | I.GG.MR.AnF.5-1454 | CoA - E88 - Public LX Rpt - Design Endorsed by TfNSW - Public LX
I2S-7688-MP-74.CM.CoA.8.29 | E88 - Public Level Crossing Treatment Report (was E99) | I.GG.MR.AnF.5-1554 | CoA - E88 - Public LX Rpt - Junee Council - Acceptance Letter - Ironbong Rd
I2S-7688-MP-74.CM.CoA.8.29 | E88 - Public Level Crossing Treatment Report (was E99) | I.GG.MR.AnF.5-1564 | CoA - E88 - Public LX Rpt - Cootamundra Council - Acceptance letter
I2S-7688-MP-74.CM.CoA.8.29 | E88 - Public Level Crossing Treatment Report (was E99) | I.GG.MR.AnF.5-1574 | CoA - E88 - Public LX Rpt - Re-submit designs to IRPL post Council approvals on designs
I2S-7688-MP-74.CM.CoA.8.29 | E88 - Public Level Crossing Treatment Report (was E99) | I.GG.MR.AnF.5-1724 | CoA - E88 - Public LX Rpt - Junee Council - Sec.138 - Approval
I2S-7688-MP-74.CM.CoA.8.29 | E88 - Public Level Crossing Treatment Report (was E99) | I.GG.MR.AnF.5-1734 | CoA - E88 - Public LX Rpt - Coota Council - Sec.138 - Approval
E89 - Private Level Crossing Treatment Report
I2S-7688-MP-74.CM.CoA.8.4 | E89 - Private Level Crossing Treatment Report | I.GG.MR.AnF.5-1584 | CoA - E89 - Address comments and IRPL Approve - Private LX
I2S-7688-MP-74.CM.CoA.8.4 | E89 - Private Level Crossing Treatment Report | I.GG.MR.AnF.5-1594 | CoA - E89 - Private LX Rpt - Individual Design Criteria forms
I2S-7688-MP-74.CM.CoA.8.4 | E89 - Private Level Crossing Treatment Report | I.GG.MR.AnF.5-1604 | CoA - E89 - Private LX Rpt - Resubmission to IRPL
I2S-7688-MP-74.CM.CoA.8.4 | E89 - Private Level Crossing Treatment Report | I.GG.MR.AnF.5-1614 | CoA - E89 - Private LX Rpt - IRPL Review Period
I2S-7688-MP-74.CM.CoA.8.4 | E89 - Private Level Crossing Treatment Report | I.GG.MR.AnF.5-1244 | CoA - E89 - Prepare & Submit to IRPL PM / Project Verifier - Private Level Crossing Treatment Report
I2S-7688-MP-74.CM.CoA.8.4 | E89 - Private Level Crossing Treatment Report | I.GG.MR.AnF.5-1254 | CoA - E89 - IRPL Review Period - Private Level Crossing Treatment Report
I2S-7688-MP-74.CM.CoA.8.4 | E89 - Private Level Crossing Treatment Report | I.GG.MR.AnF.5-1394 | CoA - E89 - JH respond to to comments, update LX treatment Report & re-issue to IRPL for comment close-out - Private LX
I2S-7688-MP-74.CM.CoA.8.4 | E89 - Private Level Crossing Treatment Report | I.GG.MR.AnF.5-1404 | CoA - E89 - IRPL Initial Comments Received - Private LX
I2S-7688-MP-74.CM.CoA.8.4 | E89 - Private Level Crossing Treatment Report | I.GG.MR.AnF.5-1414 | CoA - E89 - Private LX Rpt - Design Consultation with landowners - part 2
I2S-7688-MP-74.CM.CoA.8.4 | E89 - Private Level Crossing Treatment Report | I.GG.MR.AnF.5-1424 | CoA - E90 - Private LX Rpt - Submit to Planning Secretary for review
I2S-7688-MP-74.CM.CoA.8.4 | E89 - Private Level Crossing Treatment Report | I.GG.MR.AnF.5-1434 | CoA - E90 - Private LX Rpt - Planning Secretary Approval - (30 days prior to Construction)
I2S-7688-MP-74.CM.CoA.8.4 | E89 - Private Level Crossing Treatment Report | I.GG.MR.AnF.5-1444 | CoA - E90 - Private LX Rpt - Construction commencement of Roadworks
I2S-7688-MP-74.CM.CoA.8.4 | E89 - Private Level Crossing Treatment Report | I.GG.MR.AnF.5-1464 | CoA - E88 - Private LX Rpt - Design Endorsed
I2S-7688-MP-74.CM.CoA.8.4 | E89 - Private Level Crossing Treatment Report | I.GG.MR.AnF.5-1624 | CoA - E89 - Private LX Rpt - Design Consultation with landowners - part 1
Key Issues - misc |  |  |  | 2024-09-30 | 2025-11-24
E5 - Out-of-Hours Work Protocol |  |  |  | 2024-10-03 | 2024-12-13
I2S-7688-MP-74.CM.CoA.9.7 | E5 - Out-of-Hours Work Protocol | CoA-1540 | CoA - E5 - Prepare out of Hours (OOH) Protocol - LIW | 2024-10-03 | 2024-10-24
I2S-7688-MP-74.CM.CoA.9.7 | E5 - Out-of-Hours Work Protocol | CoA-1880 | CoA - E5 - Submit out of Hours (OOH) Protocol to Planning Secretary for approval - LIW | 2024-10-25 | 2024-11-21
I2S-7688-MP-74.CM.CoA.9.7 | E5 - Out-of-Hours Work Protocol | CoA-1890 | CoA - E5 - Approval of out of Hours (OOH) Protocol before LIW | 2024-11-22 | 2024-11-22
I2S-7688-MP-74.CM.CoA.9.7 | E5 - Out-of-Hours Work Protocol | CoA-2530 | CoA - E5 - Prepare out of Hours (OOH) Protocol before Main Works | 2024-10-25 | 2024-11-14
I2S-7688-MP-74.CM.CoA.9.7 | E5 - Out-of-Hours Work Protocol | CoA-2540 | CoA - E5 - Submit out of Hours (OOH) Protocol to Planning Secretary for approval before Main Works | 2024-11-15 | 2024-12-12
I2S-7688-MP-74.CM.CoA.9.7 | E5 - Out-of-Hours Work Protocol | CoA-2550 | CoA - E5 - Approval of out of Hours (OOH) Protocol before Main Works | 2024-12-13 | 2024-12-13
E117 - Workforce Code of Conduct (was E94 - E129) |  |  |  | 2024-09-30 | 2025-01-06
I2S-7688-MP-74.CM.CoA.9.28 | E117 - Workforce Code of Conduct (was E94 - E129) | I.GG.MR.AnF.5-914 | CoA - E117 - Prepare & Submit to IRPL PM / Project Verifier - Workforce Code of Conduct | 2024-09-30 | 2024-11-11
I2S-7688-MP-74.CM.CoA.9.28 | E117 - Workforce Code of Conduct (was E94 - E129) | I.GG.MR.AnF.5-924 | CoA - E117 - Project Verifier /IRPL Review Period - Workforce Code of Conduct | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.CM.CoA.9.28 | E117 - Workforce Code of Conduct (was E94 - E129) | I.GG.MR.AnF.5-934 | CoA - E117 - Update Plan to Reflect any Comments - Workforce Code of Conduct | 2024-12-10 | 2025-01-06
I2S-7688-MP-74.CM.CoA.9.28 | E117 - Workforce Code of Conduct (was E94 - E129) | I.GG.MR.AnF.5-944 | CoA - E117 - IRPL to review updated documents and Approve - Workforce Code of Conduct CoA |  | 2025-01-06
E126 - Visual and Landscape Impact Mitigation Plan (was e137) |  |  |  | 2024-09-30 | 2025-11-24
I2S-7688-MP-74.CM.CoA.9.31 | E126 - Visual and Landscape Impact Mitigation Plan (was e137) | I.GG.MR.AnF.5-814 | CoA - E126 - Consultation with Landowners with residences 100m/500m of CSSI - Visual Awareness and Landscape MP | 2024-09-30 | 2024-11-11
I2S-7688-MP-74.CM.CoA.9.31 | E126 - Visual and Landscape Impact Mitigation Plan (was e137) | I.GG.MR.AnF.5-1184 | CoA - E148 - CSSI must achieve a minimum excellent. Rating for both Design and As built civil works |  | 2025-11-24
Key Issues - Contamination Investigations |  |  |  | 2024-11-27 | 2027-02-26
E154 - Sampling and Analysis Quality Plan (SAQP) |  |  |  | 2024-11-27 | 2024-12-18
I2S-7688-MP-74.CM.CoA.10.1 | E154 - Sampling and Analysis Quality Plan (SAQP) | CoA-3400 | CoA - E154 - Project Verifier / IRPL Review Period - SAQP MP
I2S-7688-MP-74.CM.CoA.10.1 | E154 - Sampling and Analysis Quality Plan (SAQP) | CoA-3410 | CoA - E154 - Update Plan to Reflect any Comments - SAQP MP
I2S-7688-MP-74.CM.CoA.10.1 | E154 - Sampling and Analysis Quality Plan (SAQP) | CoA-3420 | CoA - E154 - McMahon update and re-submit to JH
I2S-7688-MP-74.CM.CoA.10.1 | E154 - Sampling and Analysis Quality Plan (SAQP) | CoA-3430 | CoA - E154 - JH submit to site auditor for review
I2S-7688-MP-74.CM.CoA.10.1 | E154 - Sampling and Analysis Quality Plan (SAQP) | CoA-3440 | CoA - E154 - McMahon update the SAQP based on auditors comments
I2S-7688-MP-74.CM.CoA.10.1 | E154 - Sampling and Analysis Quality Plan (SAQP) | CoA-3450 | CoA - E154 - IRPL to review updated documents and Approve - SAQP MP
I2S-7688-MP-74.CM.CoA.10.1 | E154 - Sampling and Analysis Quality Plan (SAQP) | CoA-3460 | CoA - E154 - JH and McMahon's update IRPL comments
I2S-7688-MP-74.CM.CoA.10.1 | E154 - Sampling and Analysis Quality Plan (SAQP) | CoA-3470 | CoA - E154 - Resubmit for final version
I2S-7688-MP-74.CM.CoA.10.1 | E154 - Sampling and Analysis Quality Plan (SAQP) | CoA-2270 | CoA - E154 - Sampling and Analysis Quality Plan (SAQP) - site | 2024-11-27 | 2024-12-18
E155 - Detailed Site Investigations (DSI)
I2S-7688-MP-74.CM.CoA.10.2 | E155 - Detailed Site Investigations (DSI) | CoA-3300 | CoA - E155 - Undertake sampling at DSI locations
I2S-7688-MP-74.CM.CoA.10.2 | E155 - Detailed Site Investigations (DSI) | CoA-3310 | CoA - E155 - Contamination Inv - Compile data and analyse
I2S-7688-MP-74.CM.CoA.10.2 | E155 - Detailed Site Investigations (DSI) | CoA-3320 | CoA - E155 - Contamination Inv - Finalise draft DSI's and submit to JH for review
I2S-7688-MP-74.CM.CoA.10.2 | E155 - Detailed Site Investigations (DSI) | CoA-3330 | CoA - E155 - Contamination Inv - JH Review
I2S-7688-MP-74.CM.CoA.10.2 | E155 - Detailed Site Investigations (DSI) | CoA-3340 | CoA - E155 - Contamination Inv - McMahon update DSI and provide to JH
I2S-7688-MP-74.CM.CoA.10.2 | E155 - Detailed Site Investigations (DSI) | CoA-3350 | CoA - E155 - Contamination Inv - Auditor review
I2S-7688-MP-74.CM.CoA.10.2 | E155 - Detailed Site Investigations (DSI) | CoA-3360 | CoA - E155 - Contamination Inv - McMahon Update DSI based on Auditors comments
I2S-7688-MP-74.CM.CoA.10.2 | E155 - Detailed Site Investigations (DSI) | CoA-3370 | CoA - E155 - Contamination Inv - Submit to IRPL and IRPL undertake review
I2S-7688-MP-74.CM.CoA.10.2 | E155 - Detailed Site Investigations (DSI) | CoA-3380 | CoA - E155 - Contamination Inv - JH and McMahon's update IRPL comments
I2S-7688-MP-74.CM.CoA.10.2 | E155 - Detailed Site Investigations (DSI) | CoA-3390 | CoA - E155 - Contamination Inv - Resubmit for final version
E156 - Remedial Action Plan (RAP) |  |  |  | 2025-02-18 | 2027-02-26
I2S-7688-MP-74.CM.CoA.10.5 | E156 - Remedial Action Plan (RAP) | CoA-2390 | CoA - E156 - RAP - Prepare Remedial Action Plan - (5 days per RAP) est 8 off - Not required | 2025-02-18 | 2025-04-22
I2S-7688-MP-74.CM.CoA.10.5 | E156 - Remedial Action Plan (RAP) | CoA-2560 | CoA - E156 - RAP - Post Remediation Validation Reports - Not required | 2027-01-22 | 2027-02-26
I2S-7688-MP-74.CM.CoA.10.5 | E156 - Remedial Action Plan (RAP) | CoA-2570 | CoA - E156 - RAP - Implement Remedial Action Plan - (5 days per RAP) est 8 off - Not required | 2026-07-22 | 2026-09-15
E159 - Contaminated land |  |  |  | 2025-04-16 | 2025-05-12
I2S-7688-MP-74.CM.CoA.10.3 | E159 - Contaminated land | CoA-2290 | CoA - E159 - Contaminated land must not be used for the purpose approved | 2025-04-16 | 2025-05-12
E161- Unexpected Finds Procedure for Contamination |  |  |  | 2025-02-06 | 2025-02-27
I2S-7688-MP-74.CM.CoA.10.4 | E161- Unexpected Finds Procedure for Contamination | CoA-2300 | CoA - E161 - NEW - An Unexpected Finds Procedure for Contamination | 2025-02-06 | 2025-02-27
Key Issues - Site Auditor |  |  |  | 2024-09-30 | 2025-07-09
E151, E152, E153, E157, E158 - Site Auditor(s) must be engaged (was E162) |  |  |  | 2024-09-30 | 2025-07-09
I2S-7688-MP-74.CM.CoA.11.26 | E151, E152, E153, E157, E158 - Site Auditor(s) must be engaged (was E162) | CoA-2320 | CoA - E152 -Site Auditor review of Sampling and Analysis Quality Plan (SAQP) (E154) | 2024-12-19 | 2025-01-22
I2S-7688-MP-74.CM.CoA.11.26 | E151, E152, E153, E157, E158 - Site Auditor(s) must be engaged (was E162) | CoA-2330 | CoA - E152 - Site Auditor review of Detailed Site Investigation Report(s) in Condition DSI (E155) | 2025-02-18 | 2025-03-10
I2S-7688-MP-74.CM.CoA.11.26 | E151, E152, E153, E157, E158 - Site Auditor(s) must be engaged (was E162) | CoA-2340 | CoA - E152 - Site Auditor review of Remedial Action Plans in Condition (E156) | 2025-04-23 | 2025-05-21
I2S-7688-MP-74.CM.CoA.11.26 | E151, E152, E153, E157, E158 - Site Auditor(s) must be engaged (was E162) | CoA-2370 | CoA - E152 -Site Auditor review of (E161/162) | 2025-02-28 | 2025-03-13
I2S-7688-MP-74.CM.CoA.11.26 | E151, E152, E153, E157, E158 - Site Auditor(s) must be engaged (was E162) | CoA-2380 | CoA - E157 - Site Audit Statement for Remedial Action Plans (RAP) (10 days per audit by site Auditor | 2025-02-26 | 2025-07-02
I2S-7688-MP-74.CM.CoA.11.26 | E151, E152, E153, E157, E158 - Site Auditor(s) must be engaged (was E162) | CoA-1720 | CoA - E151 - Site Auditors must be engaged before the commencement of contamination investigation | 2024-09-30 | 2024-11-11
I2S-7688-MP-74.CM.CoA.11.26 | E151, E152, E153, E157, E158 - Site Auditor(s) must be engaged (was E162) | CoA-2250 | CoA - E152 -recommendations made by the Site Auditor must be implemented before commencing work | 2025-06-03 | 2025-07-01
I2S-7688-MP-74.CM.CoA.11.26 | E151, E152, E153, E157, E158 - Site Auditor(s) must be engaged (was E162) | CoA-2260 | CoA - E153 - Evidence that a Site Auditor has reviewed each of the required plans and reports | 2025-07-03 | 2025-07-09
I2S-7688-MP-74.CM.CoA.11.26 | E151, E152, E153, E157, E158 - Site Auditor(s) must be engaged (was E162) | CoA-2310 | CoA - E158 - Site Audit Statement for Contaminated Land prepared by the Site Auditor | 2025-05-13 | 2025-06-03
Environmental Protection Licence (EPL) |  |  |  | 2024-09-30 | 2025-07-11
inputs |  |  |  | 2025-07-04 | 2025-07-04
I2S-7688-MP-74.CM.CoA.2.6 | inputs | I.GG.CEMP.16280 | CEMP - DPHI approved Construction Environmental Management Plan |  | 2025-07-04
EPL |  |  |  | 2024-09-30 | 2025-07-11
I2S-7688-MP-74.CM.CoA.2.4 | EPL | I.GG.PM.PA-1742 | JH Prepare and submit to EPA (Greenfield and existing Railway) | 2024-12-20 | 2025-01-31
I2S-7688-MP-74.CM.CoA.2.4 | EPL | I.GG.PM.PA-1752 | EPA Review - Updated Maps to Expand EPL Boundary | 2025-02-03 | 2025-04-30
I2S-7688-MP-74.CM.CoA.2.4 | EPL | I.GG.PM.PA-1762 | Update & address and Comments - EPA | 2025-05-23 | 2025-06-05
I2S-7688-MP-74.CM.CoA.2.4 | EPL | I.GG.PM.PA-1772 | Draft EPL Issued for Review | 2025-07-04
I2S-7688-MP-74.CM.CoA.2.4 | EPL | I.GG.PM.PA-1782 | EPL - Agree for Approval - | 2025-07-04 | 2025-07-10
I2S-7688-MP-74.CM.CoA.2.4 | EPL | I.GG.PM.PA-1792 | EPL - Updated and Approved - Updated Maps to Expand EPL Boundary | 2025-07-11
I2S-7688-MP-74.CM.CoA.2.4 | EPL | I.GG.PM.PA-2272 | JH Review exisitng EPL - IRPL to Issue (required for LIW Approval) | 2024-10-15 | 2024-11-11
I2S-7688-MP-74.CM.CoA.2.4 | EPL | I.GG.15400 | Request to work under IRPL Operational EPL for site investigation works at brownfield tie-ins | 2024-09-30 | 2024-10-14
Council and TfNSW Approval Dates |  |  |  | 2024-09-30 | 2025-03-24
Third Party Agreements with Councils |  |  |  | 2024-09-30 | 2024-09-30
I2S-7688-MP-74.CM.CoA.C.3P | Third Party Agreements with Councils | I.GG.PM.PA-1162 | Illabo LGA /Council - Third Party Agreement Executed by IRPL (IRPL response through (IR2200-RTRFI-000141) | 2024-09-30
I2S-7688-MP-74.CM.CoA.C.3P | Third Party Agreements with Councils | I.GG.PM.PA-1822 | Bethungra LGA/ Council - Third Party Agreement Executed by IRPL (IRPL response through (IR2200-RTRFI-000141) | 2024-09-30
I2S-7688-MP-74.CM.CoA.C.3P | Third Party Agreements with Councils | I.GG.PM.PA-1832 | Dirnaseer LGA / Council - Third Party Agreement Executed by IRPL (IRPL response through (IR2200-RTRFI-000141) | 2024-09-30
I2S-7688-MP-74.CM.CoA.C.3P | Third Party Agreements with Councils | I.GG.PM.PA-1842 | Cootamundra LGA / Council - Third Party Agreement Executed by IRPL (IRPL response through (IR2200-RTRFI-000141) | 2024-09-30
I2S-7688-MP-74.CM.CoA.C.3P | Third Party Agreements with Councils | I.GG.PM.PA-1852 | Stockinbingal LGA / Council - Third Party Agreement Executed by IRPL (IRPL response through (IR2200-RTRFI-000141) | 2024-09-30
I2S-7688-MP-74.CM.CoA.C.3P | Third Party Agreements with Councils | I.GG.PM.PA-1862 | Forbes Council - Third Party Agreement Executed by IRPL (IRPL response through (IR2200-RTRFI-000141) | 2024-09-30
TfNSW Design Approvals |  |  |  | 2025-03-24 | 2025-03-24
I2S-7688-MP-74.CM.CoA.C.2 | TfNSW Design Approvals | I.GG.PM.PA-892 | TfNSW Design Approvals - Burley Griffin Bridge - TfNSW Design Approval received | 2025-03-24
TfNSW Major Works Authorisation Deed Executed |  |  |  | 2024-09-30 | 2024-09-30
I2S-7688-MP-74.CM.CoA.C.3 | TfNSW Major Works Authorisation Deed Executed | I.GG.PM.PA-982 | Burley Griffin Bridge - Executed TfNSW Major Works Authorisation Deed received from TfNSW | 2024-09-30
Council Design Approval |  |  |  | 2024-09-30 | 2024-09-30
I2S-7688-MP-74.CM.CoA.C.4 | Council Design Approval | I.GG.PM.PA-1052 | Council Design Approval - Package Council approval received | 2024-09-30
Project Management Plans (PMPs) |  |  |  | 2024-09-30 | 2025-07-04
Project Management Plans |  |  |  | 2024-09-30 | 2025-01-20
1 - Project Management Plan (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-06
I2S-7688-MP-74.CM.MP.1.1 | 1 - Project Management Plan (20 Bdays) | I.GG.MR.AnF.2-4 | IRPL to review updated documents and Approve - Project MP | 2024-12-10 | 2025-01-06
I2S-7688-MP-74.CM.MP.1.1 | 1 - Project Management Plan (20 Bdays) | I.GG.MR.AnF.2-1 | Prepare & Submit to IRPL PM / Project Verifier - Project MP (20 Bdays after Date of Deed) | 2024-09-30 | 2024-10-28
I2S-7688-MP-74.CM.MP.1.1 | 1 - Project Management Plan (20 Bdays) | I.GG.MR.AnF.2-2 | Project Verifier /IRPL Review Period - Project MP | 2024-10-29 | 2024-11-25
I2S-7688-MP-74.CM.MP.1.1 | 1 - Project Management Plan (20 Bdays) | I.GG.MR.AnF.2-3 | Update Plan to Reflect any Comments - Project MP | 2024-11-26 | 2024-12-09
2.1.1 - Project Pandemic Management Plan (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-06
I2S-7688-MP-74.CM.MP.1.1.1 | 2.1.1 - Project Pandemic Management Plan (20 Bdays) | I.GG.MR.AnF.2-19 | Update Plan to Reflect any Comments - Project Pandemic MP | 2024-11-26 | 2024-12-09
I2S-7688-MP-74.CM.MP.1.1.1 | 2.1.1 - Project Pandemic Management Plan (20 Bdays) | I.GG.MR.AnF.2-20 | IRPL to review updated documents and Approve - Project Pandemic MP | 2024-12-10 | 2025-01-06
I2S-7688-MP-74.CM.MP.1.1.1 | 2.1.1 - Project Pandemic Management Plan (20 Bdays) | I.GG.MR.AnF.2-17 | Prepare & Submit to IRPL PM / Project Verifier - Project Pandemic MP (20 Bdays after Date of Deed) | 2024-09-30 | 2024-10-28
I2S-7688-MP-74.CM.MP.1.1.1 | 2.1.1 - Project Pandemic Management Plan (20 Bdays) | I.GG.MR.AnF.2-18 | Project Verifier /IRPL Review Period - Project Pandemic MP | 2024-10-29 | 2024-11-25
2 - Project Controls Management Plan (30 Bdays) |  |  |  | 2024-09-30 | 2025-01-20
I2S-7688-MP-74.CM.MP.1.2 | 2 - Project Controls Management Plan (30 Bdays) | I.GG.MR.AnF.2-5 | Prepare & Submit to IRPL PM / Project Verifier - Project Controls MP (30 Bdays after Date of Deed) | 2024-09-30 | 2024-11-11
I2S-7688-MP-74.CM.MP.1.2 | 2 - Project Controls Management Plan (30 Bdays) | I.GG.MR.AnF.2-6 | Project Verifier /IRPL Review Period - Project Controls MP | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.CM.MP.1.2 | 2 - Project Controls Management Plan (30 Bdays) | I.GG.MR.AnF.2-7 | Update Plan to Reflect any Comments - Project Controls MP | 2024-12-10 | 2025-01-06
I2S-7688-MP-74.CM.MP.1.2 | 2 - Project Controls Management Plan (30 Bdays) | I.GG.MR.AnF.2-8 | IRPL to review updated documents and Approve - Project Controls MP | 2025-01-07 | 2025-01-20
3 - Quality Management Plan (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-06
I2S-7688-MP-74.CM.MP.1.3 | 3 - Quality Management Plan (20 Bdays) | I.GG.MR.AnF.6-1 | Prepare & Submit to IRPL PM / Project Verifier - Quality MP (20 Bdays after Date of Deed) | 2024-09-30 | 2024-10-28
I2S-7688-MP-74.CM.MP.1.3 | 3 - Quality Management Plan (20 Bdays) | I.GG.MR.AnF.6-2 | Project Verifier /IRPL Review Period - Quality MP | 2024-10-29 | 2024-11-25
I2S-7688-MP-74.CM.MP.1.3 | 3 - Quality Management Plan (20 Bdays) | I.GG.MR.AnF.6-3 | Update Plan to Reflect any Comments - Quality MP | 2024-11-26 | 2024-12-09
I2S-7688-MP-74.CM.MP.1.3 | 3 - Quality Management Plan (20 Bdays) | I.GG.MR.AnF.6-4 | IRPL to review updated documents and Approve - Quality MP | 2024-12-10 | 2025-01-06
4 - Project Risk Management Plan (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-06
I2S-7688-MP-74.CM.MP.1.4 | 4 - Project Risk Management Plan (20 Bdays) | I.GG.MR.AnF.3-1 | Prepare & Submit to IRPL PM / Project Verifier - Risk MP (20 Bdays after Date of Deed) | 2024-09-30 | 2024-10-28
I2S-7688-MP-74.CM.MP.1.4 | 4 - Project Risk Management Plan (20 Bdays) | I.GG.MR.AnF.3-2 | Project Verifier /IRPL Review Period - Risk MP | 2024-10-29 | 2024-11-25
I2S-7688-MP-74.CM.MP.1.4 | 4 - Project Risk Management Plan (20 Bdays) | I.GG.MR.AnF.3-3 | Update Plan to Reflect any Comments - Risk MP | 2024-11-26 | 2024-12-09
I2S-7688-MP-74.CM.MP.1.4 | 4 - Project Risk Management Plan (20 Bdays) | I.GG.MR.AnF.3-4 | IRPL to review updated documents and Approve - Risk MP | 2024-12-10 | 2025-01-06
5 - Subcontract Packaging and Procurement Management Plan (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-06
I2S-7688-MP-74.CM.MP.1.5 | 5 - Subcontract Packaging and Procurement Management Plan (20 Bdays) | I.GG.MR.AnF.2-11 | Update Plan to Reflect any Comments - Subcontract Packaging MP | 2024-11-26 | 2024-12-09
I2S-7688-MP-74.CM.MP.1.5 | 5 - Subcontract Packaging and Procurement Management Plan (20 Bdays) | I.GG.MR.AnF.2-12 | IRPL to review updated documents and Approve - Subcontract Packaging MP | 2024-12-10 | 2025-01-06
I2S-7688-MP-74.CM.MP.1.5 | 5 - Subcontract Packaging and Procurement Management Plan (20 Bdays) | I.GG.MR.AnF.2-9 | Prepare & Submit to IRPL PM / Project Verifier - Subcontract Packaging MP (20 Bdays after Date of Deed) | 2024-09-30 | 2024-10-28
I2S-7688-MP-74.CM.MP.1.5 | 5 - Subcontract Packaging and Procurement Management Plan (20 Bdays) | I.GG.MR.AnF.2-10 | Project Verifier /IRPL Review Period - Subcontract Packaging MP | 2024-10-29 | 2024-11-25
6 - Information Management Plan (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-06
I2S-7688-MP-74.CM.MP.1.7 | 6 - Information Management Plan (20 Bdays) | I.GG.MR.AnF.2-110 | Prepare & Submit to IRPL PM / Project Verifier - Information Management Plan (20 Bdays after Date of Deed) | 2024-09-30 | 2024-10-28
I2S-7688-MP-74.CM.MP.1.7 | 6 - Information Management Plan (20 Bdays) | I.GG.MR.AnF.2-120 | Project Verifier /IRPL Review Period - Information Management Plan | 2024-10-29 | 2024-11-25
I2S-7688-MP-74.CM.MP.1.7 | 6 - Information Management Plan (20 Bdays) | I.GG.MR.AnF.2-130 | Update Plan to Reflect any Comments - Information Management Plan | 2024-11-26 | 2024-12-09
I2S-7688-MP-74.CM.MP.1.7 | 6 - Information Management Plan (20 Bdays) | I.GG.MR.AnF.2-140 | IRPL to review updated documents and Approve - Information Management Plan | 2024-12-10 | 2025-01-06
7 - Master Information Deliverables Plan (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-06
I2S-7688-MP-74.CM.MP.1.6 | 7 - Master Information Deliverables Plan (20 Bdays) | I.GG.MR.AnF.2-13 | Prepare & Submit to IRPL PM / Project Verifier - Master Information Deliverables Plan (20 Bdays after Date of Deed) | 2024-09-30 | 2024-10-28
I2S-7688-MP-74.CM.MP.1.6 | 7 - Master Information Deliverables Plan (20 Bdays) | I.GG.MR.AnF.2-14 | Project Verifier /IRPL Review Period - Master Information Deliverables Plan | 2024-10-29 | 2024-11-25
I2S-7688-MP-74.CM.MP.1.6 | 7 - Master Information Deliverables Plan (20 Bdays) | I.GG.MR.AnF.2-15 | Update Plan to Reflect any Comments - Master Information Deliverables Plan | 2024-11-26 | 2024-12-09
I2S-7688-MP-74.CM.MP.1.6 | 7 - Master Information Deliverables Plan (20 Bdays) | I.GG.MR.AnF.2-16 | IRPL to review updated documents and Approve - Master Information Deliverables Plan | 2024-12-10 | 2025-01-06
Engineering Management Plans |  |  |  | 2024-09-30 | 2025-01-28
I2S-7688-MP-74.CM.MP.2 | Engineering Management Plans | I.GG.MR.AnF.3-54 | Complete Engineering Management Plans |  | 2025-01-28
7 - Safety Assurance Plan (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-13
I2S-7688-MP-74.CM.MP.2.7 | 7 - Safety Assurance Plan (20 Bdays) | I.GG.MR.AnF.3-14 | Prepare & Submit to IRPL PM / Project Verifier - Safety Assurance Plan (20 Bdays after Date of Deed) | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.MP.2.7 | 7 - Safety Assurance Plan (20 Bdays) | I.GG.MR.AnF.3-24 | Project Verifier /IRPL Review Period - Safety Assurance Plan | 2024-11-05 | 2024-12-02
I2S-7688-MP-74.CM.MP.2.7 | 7 - Safety Assurance Plan (20 Bdays) | I.GG.MR.AnF.3-34 | Update Plan to Reflect any Comments - Safety Assurance Plan | 2024-12-03 | 2024-12-16
I2S-7688-MP-74.CM.MP.2.7 | 7 - Safety Assurance Plan (20 Bdays) | I.GG.MR.AnF.3-44 | IRPL to review updated documents and Approve - Safety Assurance Plan | 2024-12-17 | 2025-01-13
8 - Competency Management Plan (30 Bdays) |  |  |  | 2024-09-30 | 2025-01-28
I2S-7688-MP-74.CM.MP.2.8 | 8 - Competency Management Plan (30 Bdays) | I.GG.MR.AnF.11-54 | Prepare & Submit to IRPL PM / Project Verifier - Competency MP (30 Bdays after Date of Deed) | 2024-09-30 | 2024-11-18
I2S-7688-MP-74.CM.MP.2.8 | 8 - Competency Management Plan (30 Bdays) | I.GG.MR.AnF.11-64 | Project Verifier /IRPL Review Period - Competency MP | 2024-11-19 | 2024-12-16
I2S-7688-MP-74.CM.MP.2.8 | 8 - Competency Management Plan (30 Bdays) | I.GG.MR.AnF.11-74 | Update Plan to Reflect any Comments - Competency MP | 2024-12-17 | 2025-01-13
I2S-7688-MP-74.CM.MP.2.8 | 8 - Competency Management Plan (30 Bdays) | I.GG.MR.AnF.11-84 | IRPL to review updated documents and Approve - Competency MP | 2025-01-14 | 2025-01-28
9 - Interface Management Plan (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-06
I2S-7688-MP-74.CM.MP.2.9 | 9 - Interface Management Plan (20 Bdays) | I.GG.MR.AnF.6-14 | Prepare & Submit to IRPL PM / Project Verifier - Interface MP (20 Bdays after Date of Deed) | 2024-09-30 | 2024-10-28
I2S-7688-MP-74.CM.MP.2.9 | 9 - Interface Management Plan (20 Bdays) | I.GG.MR.AnF.6-24 | Project Verifier /IRPL Review Period - Interface MP | 2024-10-29 | 2024-11-25
I2S-7688-MP-74.CM.MP.2.9 | 9 - Interface Management Plan (20 Bdays) | I.GG.MR.AnF.6-34 | Update Plan to Reflect any Comments - Interface MP | 2024-11-26 | 2024-12-09
I2S-7688-MP-74.CM.MP.2.9 | 9 - Interface Management Plan (20 Bdays) | I.GG.MR.AnF.6-44 | IRPL to review updated documents and Approve - Interface MP | 2024-12-10 | 2025-01-06
10 - Integration Management Plan (30 Bdays) |  |  |  | 2024-09-30 | 2025-01-20
I2S-7688-MP-74.CM.MP.2.10 | 10 - Integration Management Plan (30 Bdays) | I.GG.MR.AnF.11-4 | IRPL to review updated documents and Approve - Integration MP (Not required) | 2025-01-07 | 2025-01-20
I2S-7688-MP-74.CM.MP.2.10 | 10 - Integration Management Plan (30 Bdays) | I.GG.MR.AnF.11-1 | Prepare & Submit to IRPL PM / Project Verifier - Integration MP (30 Bdays after Date of Deed) (Not required) | 2024-09-30 | 2024-11-11
I2S-7688-MP-74.CM.MP.2.10 | 10 - Integration Management Plan (30 Bdays) | I.GG.MR.AnF.11-2 | Project Verifier /IRPL Review Period - Integration MP (Not required) | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.CM.MP.2.10 | 10 - Integration Management Plan (30 Bdays) | I.GG.MR.AnF.11-3 | Update Plan to Reflect any Comments - Integration MP (Not required) | 2024-12-10 | 2025-01-06
11 - Digital Engineering Management Plan (30 Bdays) |  |  |  | 2024-09-30 | 2025-01-20
I2S-7688-MP-74.CM.MP.2.11 | 11 - Digital Engineering Management Plan (30 Bdays) | I.GG.MR.AnF.11-24 | Project Verifier /IRPL Review Period - Digital Engineering MP | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.CM.MP.2.11 | 11 - Digital Engineering Management Plan (30 Bdays) | I.GG.MR.AnF.11-34 | Update Plan to Reflect any Comments - Digital Engineering MP | 2024-12-10 | 2025-01-06
I2S-7688-MP-74.CM.MP.2.11 | 11 - Digital Engineering Management Plan (30 Bdays) | I.GG.MR.AnF.11-44 | Digital Engineering MP - IRPL to review updated documents and Approve | 2025-01-07 | 2025-01-20
I2S-7688-MP-74.CM.MP.2.11 | 11 - Digital Engineering Management Plan (30 Bdays) | I.GG.MR.AnF.11-14 | Prepare & Submit to IRPL PM / Project Verifier - Digital Engineering MP (30 Bdays after Date of Deed) | 2024-09-30 | 2024-11-11
12 - System Engineering Management Plan (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-06
I2S-7688-MP-74.CM.MP.2.12 | 12 - System Engineering Management Plan (20 Bdays) | I.GG.MR.AnF.2-30 | Prepare & Submit to IRPL PM / Project Verifier - System Engineering MP (20 Bdays after Date of Deed) | 2024-09-30 | 2024-10-28
I2S-7688-MP-74.CM.MP.2.12 | 12 - System Engineering Management Plan (20 Bdays) | I.GG.MR.AnF.2-40 | Project Verifier /IRPL Review Period - System Engineering MP | 2024-10-29 | 2024-11-25
I2S-7688-MP-74.CM.MP.2.12 | 12 - System Engineering Management Plan (20 Bdays) | I.GG.MR.AnF.2-50 | Update Plan to Reflect any Comments - System Engineering MP | 2024-11-26 | 2024-12-09
I2S-7688-MP-74.CM.MP.2.12 | 12 - System Engineering Management Plan (20 Bdays) | I.GG.MR.AnF.2-60 | IRPL to review updated documents and Approve -System Engineering MP | 2024-12-10 | 2025-01-06
12.1 - Requirements Management Plan (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-06
I2S-7688-MP-74.CM.MP.2.12.1 | 12.1 - Requirements Management Plan (20 Bdays) | I.GG.MR.AnF.2-70 | Prepare & Submit to IRPL PM / Project Verifier - Requirements MP (20 Bdays after Date of Deed) | 2024-09-30 | 2024-10-28
I2S-7688-MP-74.CM.MP.2.12.1 | 12.1 - Requirements Management Plan (20 Bdays) | I.GG.MR.AnF.2-80 | Project Verifier /IRPL Review Period - Requirements MP | 2024-10-29 | 2024-11-25
I2S-7688-MP-74.CM.MP.2.12.1 | 12.1 - Requirements Management Plan (20 Bdays) | I.GG.MR.AnF.2-90 | Update Plan to Reflect any Comments - Requirements MP | 2024-11-26 | 2024-12-09
I2S-7688-MP-74.CM.MP.2.12.1 | 12.1 - Requirements Management Plan (20 Bdays) | I.GG.MR.AnF.2-100 | IRPL to review updated documents and Approve - Requirements MP | 2024-12-10 | 2025-01-06
13 - Innovation and Value Management Plan (30 Bdays) |  |  |  | 2024-09-30 | 2025-01-20
I2S-7688-MP-74.CM.MP.2.13 | 13 - Innovation and Value Management Plan (30 Bdays) | I.GG.MR.AnF.11-94 | Prepare & Submit to IRPL PM / Project Verifier - innovation and Value MP (30 Bdays after Date of Deed) | 2024-09-30 | 2024-11-11
I2S-7688-MP-74.CM.MP.2.13 | 13 - Innovation and Value Management Plan (30 Bdays) | I.GG.MR.AnF.11-104 | Project Verifier /IRPL Review Period - innovation and Value MP | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.CM.MP.2.13 | 13 - Innovation and Value Management Plan (30 Bdays) | I.GG.MR.AnF.11-114 | Update Plan to Reflect any Comments -innovation and Value MP | 2024-12-10 | 2025-01-06
I2S-7688-MP-74.CM.MP.2.13 | 13 - Innovation and Value Management Plan (30 Bdays) | I.GG.MR.AnF.11-124 | IRPL to review updated documents and Approve - innovation and Value MP | 2025-01-07 | 2025-01-20
Design Management Requirements |  |  |  | 2024-09-30 | 2025-01-28
I2S-7688-MP-74.CM.MP.3 | Design Management Requirements | I.GG.MR.AnF.4-94 | Complete Design Management Plans |  | 2025-01-28
14 - Design Management Plan (30 Bdays) |  |  |  | 2024-09-30 | 2025-01-28
I2S-7688-MP-74.CM.MP.3.14 | 14 - Design Management Plan (30 Bdays) | I.GG.MR.AnF.4-1 | Prepare & Submit to IRPL PM / Project Verifier - Design MP (30 Bdays after Date of Deed) | 2024-09-30 | 2024-11-18
I2S-7688-MP-74.CM.MP.3.14 | 14 - Design Management Plan (30 Bdays) | I.GG.MR.AnF.4-2 | Project Verifier /IRPL Review Period - Design MP | 2024-11-19 | 2024-12-16
I2S-7688-MP-74.CM.MP.3.14 | 14 - Design Management Plan (30 Bdays) | I.GG.MR.AnF.4-3 | Update Plan to Reflect any Comments - Design MP | 2024-12-17 | 2025-01-13
I2S-7688-MP-74.CM.MP.3.14 | 14 - Design Management Plan (30 Bdays) | I.GG.MR.AnF.4-4 | IRPL to review updated documents and Approve - Design MP | 2025-01-14 | 2025-01-28
4.1.1 - Construction Phase (CPS) Management Plan (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-13
I2S-7688-MP-74.CM.MP.3.14.1 | 4.1.1 - Construction Phase (CPS) Management Plan (20 Bdays) | I.GG.MR.AnF.4-14 | Prepare & Submit to IRPL PM / Project Verifier - CPS MP (20 Bdays after Date of Deed) | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.MP.3.14.1 | 4.1.1 - Construction Phase (CPS) Management Plan (20 Bdays) | I.GG.MR.AnF.4-24 | Project Verifier /IRPL Review Period - CPS MP | 2024-11-05 | 2024-12-02
I2S-7688-MP-74.CM.MP.3.14.1 | 4.1.1 - Construction Phase (CPS) Management Plan (20 Bdays) | I.GG.MR.AnF.4-34 | Update Plan to Reflect any Comments - CPS MP | 2024-12-03 | 2024-12-16
I2S-7688-MP-74.CM.MP.3.14.1 | 4.1.1 - Construction Phase (CPS) Management Plan (20 Bdays) | I.GG.MR.AnF.4-44 | IRPL to review updated documents and Approve - CPS MP | 2024-12-17 | 2025-01-13
Construction Management Plans |  |  |  | 2024-09-30 | 2025-05-02
I2S-7688-MP-74.CM.MP.4 | Construction Management Plans | I.GG.MR.AnF.15 | Complete Construction Project Management Plans PMPs |  | 2025-05-02
I2S-7688-MP-74.CM.MP.4 | Construction Management Plans | I.GG.MR.AnF.16614 | Publication of Management Plans | 2025-04-28 | 2025-05-02
15 - Construction Management Plan (30 Bdays)- |  |  |  | 2024-09-30 | 2025-04-24
I2S-7688-MP-74.CM.MP.4.15 | 15 - Construction Management Plan (30 Bdays)- | I.GG.MR.AnF.1514 | Prepare & Submit to IRPL PM / Project Verifier - Construction MP (30 Bdays after Date of Deed) | 2024-09-30 | 2024-11-11
I2S-7688-MP-74.CM.MP.4.15 | 15 - Construction Management Plan (30 Bdays)- | I.GG.MR.AnF.1524 | Project Verifier /IRPL Review Period - Construction MP | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.CM.MP.4.15 | 15 - Construction Management Plan (30 Bdays)- | I.GG.MR.AnF.1534 | Update Plan to Reflect any Comments - Construction MP | 2024-12-10 | 2025-01-06
I2S-7688-MP-74.CM.MP.4.15 | 15 - Construction Management Plan (30 Bdays)- | I.GG.MR.AnF.1544 | IRPL to review updated documents and Approve - Construction MP | 2025-01-07 | 2025-01-20
15.2 - Construction Packages and Construction Staging Management Plan (30 Bdays) |  |  |  | 2024-09-30 | 2025-01-28
I2S-7688-MP-74.CM.MP.4.15.2 | 15.2 - Construction Packages and Construction Staging Management Plan (30 Bdays) | I.GG.MR.AnF.5-334 | Prepare & Submit to IRPL PM / Project Verifier - Construction Staging MP (30 Bdays after Date of Deed) | 2024-09-30 | 2024-11-18
I2S-7688-MP-74.CM.MP.4.15.2 | 15.2 - Construction Packages and Construction Staging Management Plan (30 Bdays) | I.GG.MR.AnF.5-344 | Project Verifier /IRPL Review Period - Construction Staging MP | 2024-11-19 | 2024-12-16
I2S-7688-MP-74.CM.MP.4.15.2 | 15.2 - Construction Packages and Construction Staging Management Plan (30 Bdays) | I.GG.MR.AnF.5-354 | Update Plan to Reflect any Comments - Construction Staging MP | 2024-12-17 | 2025-01-13
I2S-7688-MP-74.CM.MP.4.15.2 | 15.2 - Construction Packages and Construction Staging Management Plan (30 Bdays) | I.GG.MR.AnF.5-364 | IRPL to review updated documents and Approve - Construction Staging MP | 2025-01-14 | 2025-01-28
15.3 - Mobilisation Plan (30 Bdays) |  |  |  | 2024-09-30 | 2025-01-28
I2S-7688-MP-74.CM.MP.4.15.3 | 15.3 - Mobilisation Plan (30 Bdays) | I.GG.MR.AnF.5-434 | Update Plan to Reflect any Comments - Mobilisation Plan | 2024-12-17 | 2025-01-13
I2S-7688-MP-74.CM.MP.4.15.3 | 15.3 - Mobilisation Plan (30 Bdays) | I.GG.MR.AnF.5-444 | IRPL to review updated documents and Approve - Mobilisation Plan | 2025-01-14 | 2025-01-28
I2S-7688-MP-74.CM.MP.4.15.3 | 15.3 - Mobilisation Plan (30 Bdays) | I.GG.MR.AnF.5-414 | Prepare & Submit to IRPL PM / Project Verifier - Mobilisation Plan (30 Bdays after Date of Deed) | 2024-09-30 | 2024-11-18
I2S-7688-MP-74.CM.MP.4.15.3 | 15.3 - Mobilisation Plan (30 Bdays) | I.GG.MR.AnF.5-424 | Project Verifier /IRPL Review Period - Mobilisation Plan | 2024-11-19 | 2024-12-16
15.4 - Demobilisation Plan (30 Bdays) |  |  |  | 2024-09-30 | 2025-01-20
I2S-7688-MP-74.CM.MP.4.15.4 | 15.4 - Demobilisation Plan (30 Bdays) | I.GG.MR.AnF.5-484 | IRPL to review updated documents and Approve - Demobilisation Plan | 2025-01-07 | 2025-01-20
I2S-7688-MP-74.CM.MP.4.15.4 | 15.4 - Demobilisation Plan (30 Bdays) | I.GG.MR.AnF.5-454 | Prepare & Submit to IRPL PM / Project Verifier - Demobilisation Plan (30 Bdays after Date of Deed) | 2024-09-30 | 2024-11-11
I2S-7688-MP-74.CM.MP.4.15.4 | 15.4 - Demobilisation Plan (30 Bdays) | I.GG.MR.AnF.5-464 | Project Verifier /IRPL Review Period - Demobilisation Plan | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.CM.MP.4.15.4 | 15.4 - Demobilisation Plan (30 Bdays) | I.GG.MR.AnF.5-474 | Update Plan to Reflect any Comments - Demobilisation Plan | 2024-12-10 | 2025-01-06
15.5 - Demolition Plan (30 Bdays) |  |  |  | 2024-09-30 | 2025-01-20
I2S-7688-MP-74.CM.MP.4.15.5 | 15.5 - Demolition Plan (30 Bdays) | I.GG.MR.AnF.5-534 | Prepare & Submit to IRPL PM / Project Verifier - Demolition Plan (30 Bdays after Date of Deed) | 2024-09-30 | 2024-11-11
I2S-7688-MP-74.CM.MP.4.15.5 | 15.5 - Demolition Plan (30 Bdays) | I.GG.MR.AnF.5-544 | Project Verifier /IRPL Review Period - Demolition Plan | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.CM.MP.4.15.5 | 15.5 - Demolition Plan (30 Bdays) | I.GG.MR.AnF.5-554 | Update Plan to Reflect any Comments - Demolition Plan | 2024-12-10 | 2025-01-06
I2S-7688-MP-74.CM.MP.4.15.5 | 15.5 - Demolition Plan (30 Bdays) | I.GG.MR.AnF.5-564 | IRPL to review updated documents and Approve - Demolition Plan | 2025-01-07 | 2025-01-20
15.6 - Construction Water Management Plan (30 Bdays) |  |  |  | 2024-09-30 | 2025-01-23
I2S-7688-MP-74.CM.MP.4.15.6 | 15.6 - Construction Water Management Plan (30 Bdays) | I.GG.MR.AnF.5-54 | Prepare & Submit to IRPL PM / Project Verifier - Construction Water MP (30 Bdays after Date of Deed) | 2024-09-30 | 2024-11-11
I2S-7688-MP-74.CM.MP.4.15.6 | 15.6 - Construction Water Management Plan (30 Bdays) | I.GG.MR.AnF.5-64 | Project Verifier /IRPL Review Period - Construction Water MP | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.CM.MP.4.15.6 | 15.6 - Construction Water Management Plan (30 Bdays) | I.GG.MR.AnF.5-74 | Update Plan to Reflect any Comments - Construction Water MP | 2024-12-10 | 2025-01-06
I2S-7688-MP-74.CM.MP.4.15.6 | 15.6 - Construction Water Management Plan (30 Bdays) | I.GG.MR.AnF.5-84 | IRPL to review updated documents and Approve - Construction Water MP | 2025-01-10 | 2025-01-23
15.7 - Rail Access Management Plan (30 Bdays) |  |  |  | 2024-09-30 | 2025-01-20
I2S-7688-MP-74.CM.MP.4.15.7 | 15.7 - Rail Access Management Plan (30 Bdays) | I.GG.MR.AnF.5-134 | Prepare & Submit to IRPL PM / Project Verifier - Rail Access MP (30 Bdays after Date of Deed) | 2024-09-30 | 2024-11-11
I2S-7688-MP-74.CM.MP.4.15.7 | 15.7 - Rail Access Management Plan (30 Bdays) | I.GG.MR.AnF.5-144 | Project Verifier /IRPL Review Period - Rail Access MP | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.CM.MP.4.15.7 | 15.7 - Rail Access Management Plan (30 Bdays) | I.GG.MR.AnF.5-154 | Update Plan to Reflect any Comments -Rail Access MP | 2024-12-10 | 2025-01-06
I2S-7688-MP-74.CM.MP.4.15.7 | 15.7 - Rail Access Management Plan (30 Bdays) | I.GG.MR.AnF.5-164 | IRPL to review updated documents and Approve - Rail Access MP | 2025-01-07 | 2025-01-20
15.8 - Construction Monitoring Management Plan (30 Bdays) |  |  |  | 2024-09-30 | 2025-02-20
I2S-7688-MP-74.CM.MP.4.15.8 | 15.8 - Construction Monitoring Management Plan (30 Bdays) | I.GG.MR.AnF.5-124 | IRPL to review updated documents and Approve - Construction Monitoring MP | 2025-02-07 | 2025-02-20
I2S-7688-MP-74.CM.MP.4.15.8 | 15.8 - Construction Monitoring Management Plan (30 Bdays) | I.GG.MR.AnF.5-94 | Prepare & Submit to IRPL PM / Project Verifier - Construction Monitoring MP (30 Bdays after Date of Deed) | 2024-09-30 | 2024-10-28
I2S-7688-MP-74.CM.MP.4.15.8 | 15.8 - Construction Monitoring Management Plan (30 Bdays) | I.GG.MR.AnF.5-104 | Project Verifier /IRPL Review Period - Construction Monitoring MP | 2024-10-29 | 2024-11-25
I2S-7688-MP-74.CM.MP.4.15.8 | 15.8 - Construction Monitoring Management Plan (30 Bdays) | I.GG.MR.AnF.5-114 | Update Plan to Reflect any Comments - Construction Monitoring MP | 2025-01-23 | 2025-02-06
15.9 - Material Management Plan (30 Bdays) |  |  |  | 2024-09-30 | 2025-01-20
I2S-7688-MP-74.CM.MP.4.15.9 | 15.9 - Material Management Plan (30 Bdays) | I.GG.MR.AnF.5-374 | Prepare & Submit to IRPL PM / Project Verifier - Material Management MP (30 Bdays after Date of Deed) | 2024-09-30 | 2024-11-11
I2S-7688-MP-74.CM.MP.4.15.9 | 15.9 - Material Management Plan (30 Bdays) | I.GG.MR.AnF.5-384 | Project Verifier /IRPL Review Period - Material Management MP | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.CM.MP.4.15.9 | 15.9 - Material Management Plan (30 Bdays) | I.GG.MR.AnF.5-394 | Update Plan to Reflect any Comments - Material Management MP | 2024-12-10 | 2025-01-06
I2S-7688-MP-74.CM.MP.4.15.9 | 15.9 - Material Management Plan (30 Bdays) | I.GG.MR.AnF.5-404 | IRPL to review updated documents and Approve - Material Management MP | 2025-01-07 | 2025-01-20
15.12 - Temporary Accommodation Facility Management Plan TAFMP - A18 (was A21) |  |  |  | 2024-09-30 | 2025-04-24
I2S-7688-MP-74.CM.MP.4.15.12 | 15.12 - Temporary Accommodation Facility Management Plan TAFMP - A18 (was A21) | I.GG.MR.AnF.5-1194 | TAFMP - Consulatation with Council, NSW police and NSW Ambulance (CoA - A18)
I2S-7688-MP-74.CM.MP.4.15.12 | 15.12 - Temporary Accommodation Facility Management Plan TAFMP - A18 (was A21) | I.GG.MR.AnF.5-1204 | TAFMP - Prepare RevB for consultation including plans
I2S-7688-MP-74.CM.MP.4.15.12 | 15.12 - Temporary Accommodation Facility Management Plan TAFMP - A18 (was A21) | I.GG.MR.AnF.5-1214 | TAFMP - Submit to Environmental Representaive Rev B
I2S-7688-MP-74.CM.MP.4.15.12 | 15.12 - Temporary Accommodation Facility Management Plan TAFMP - A18 (was A21) | I.GG.MR.AnF.5-1224 | TAFMP - ER Approval Period
I2S-7688-MP-74.CM.MP.4.15.12 | 15.12 - Temporary Accommodation Facility Management Plan TAFMP - A18 (was A21) | I.GG.MR.AnF.5-864 | TAFMP - IRPL Review Period - Accommodation Facility MP (CoA - A18) | 2025-02-19 | 2025-03-18
I2S-7688-MP-74.CM.MP.4.15.12 | 15.12 - Temporary Accommodation Facility Management Plan TAFMP - A18 (was A21) | I.GG.MR.AnF.5-874 | TAFMP - Update Plan to Reflect any Comments- Accommodation Facility MP (CoA - A18) | 2025-03-19 | 2025-04-01
I2S-7688-MP-74.CM.MP.4.15.12 | 15.12 - Temporary Accommodation Facility Management Plan TAFMP - A18 (was A21) | I.GG.MR.AnF.5-884 | TAFMP - Complete & Approved- Accomm. Facility MP (CoA - A18) (1 month before Occupation | 2025-04-16 | 2025-04-24
I2S-7688-MP-74.CM.MP.4.15.12 | 15.12 - Temporary Accommodation Facility Management Plan TAFMP - A18 (was A21) | I.GG.MR.AnF.5-894 | TAFMP - CoA - A18 - Submit to Environmental Rep for endorsement - Temp Accommodation Facility MP | 2024-12-10 | 2025-02-18
I2S-7688-MP-74.CM.MP.4.15.12 | 15.12 - Temporary Accommodation Facility Management Plan TAFMP - A18 (was A21) | I.GG.15310 | TAFMP - Develop Temporary Accommodation Facility Management Plan (CoA - A18) | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.CM.MP.4.15.12 | 15.12 - Temporary Accommodation Facility Management Plan TAFMP - A18 (was A21) | I.GG.15320 | TAFMP - Submit Accommodation Facility Management Plan to Planning Secretary for Approval (CoA - A18) | 2024-12-10 | 2025-02-18
I2S-7688-MP-74.CM.MP.4.15.12 | 15.12 - Temporary Accommodation Facility Management Plan TAFMP - A18 (was A21) | I.GG.MR.AnF.5-854 | TAFMP - JH Contract Execution | 2024-09-30 | 2024-12-09
Safety Management Requirements and Plans |  |  |  | 2024-09-30 | 2025-01-13
I2S-7688-MP-74.CM.MP.5 | Safety Management Requirements and Plans | I.GG.MR.AnF.16 | Complete Safety Management Plans |  | 2025-01-13
16. Project Safety Management Plan (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-13
I2S-7688-MP-74.CM.MP.5.16 | 16. Project Safety Management Plan (20 Bdays) | I.GG.MR.AnF.16574 | Prepare & Submit to IRPL PM / Project Verifier - Project Safety MP (20 Bdays after Date of Deed) | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.MP.5.16 | 16. Project Safety Management Plan (20 Bdays) | I.GG.MR.AnF.16584 | Project Verifier /IRPL Review Period - Project Safety MP | 2024-11-05 | 2024-12-02
I2S-7688-MP-74.CM.MP.5.16 | 16. Project Safety Management Plan (20 Bdays) | I.GG.MR.AnF.16594 | Update Plan to Reflect any Comments - Project Safety MP | 2024-12-03 | 2024-12-16
I2S-7688-MP-74.CM.MP.5.16 | 16. Project Safety Management Plan (20 Bdays) | I.GG.MR.AnF.16604 | IRPL to review updated documents and Approve - Project Safety MP | 2024-12-17 | 2025-01-13
16.1 - Emergency Management Plan (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-13
I2S-7688-MP-74.CM.MP.5.16.1 | 16.1 - Emergency Management Plan (20 Bdays) | I.GG.MR.AnF.5-614 | Prepare & Submit to IRPL PM / Project Verifier - Emergency MP (20 Bdays after Date of Deed) | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.MP.5.16.1 | 16.1 - Emergency Management Plan (20 Bdays) | I.GG.MR.AnF.5-624 | Project Verifier /IRPL Review Period - Emergency MP | 2024-11-05 | 2024-12-02
I2S-7688-MP-74.CM.MP.5.16.1 | 16.1 - Emergency Management Plan (20 Bdays) | I.GG.MR.AnF.5-634 | Update Plan to Reflect any Comments - Emergency MP | 2024-12-03 | 2024-12-16
I2S-7688-MP-74.CM.MP.5.16.1 | 16.1 - Emergency Management Plan (20 Bdays) | I.GG.MR.AnF.5-644 | IRPL to review updated documents and Approve - Emergency MP | 2024-12-17 | 2025-01-13
16.2 - Occupational Health, Hygiene and Wellness Management Plan (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-13
I2S-7688-MP-74.CM.MP.5.16.2 | 16.2 - Occupational Health, Hygiene and Wellness Management Plan (20 Bdays) | I.GG.MR.AnF.5-654 | Prepare & Submit to IRPL PM / Project Verifier - Occupational Health, Hygiene & Wellnes MP (20 Bdays after Date of Deed) | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.MP.5.16.2 | 16.2 - Occupational Health, Hygiene and Wellness Management Plan (20 Bdays) | I.GG.MR.AnF.5-664 | Project Verifier /IRPL Review Period - Occupational Health, Hygiene & Wellness MP | 2024-11-05 | 2024-12-02
I2S-7688-MP-74.CM.MP.5.16.2 | 16.2 - Occupational Health, Hygiene and Wellness Management Plan (20 Bdays) | I.GG.MR.AnF.5-674 | Update Plan to Reflect any Comments - Occupational Health, Hygiene & Wellness MP | 2024-12-03 | 2024-12-16
I2S-7688-MP-74.CM.MP.5.16.2 | 16.2 - Occupational Health, Hygiene and Wellness Management Plan (20 Bdays) | I.GG.MR.AnF.5-684 | IRPL to review updated documents and Approve - Occupational Health, Hygiene & Wellness MP | 2024-12-17 | 2025-01-13
16.3 - Security Management Plan (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-13
I2S-7688-MP-74.CM.MP.5.16.3 | 16.3 - Security Management Plan (20 Bdays) | I.GG.MR.AnF.5-744 | Project Verifier /IRPL Review Period - Security MP | 2024-11-05 | 2024-12-02
I2S-7688-MP-74.CM.MP.5.16.3 | 16.3 - Security Management Plan (20 Bdays) | I.GG.MR.AnF.5-754 | Update Plan to Reflect any Comments - Security MP | 2024-12-03 | 2024-12-16
I2S-7688-MP-74.CM.MP.5.16.3 | 16.3 - Security Management Plan (20 Bdays) | I.GG.MR.AnF.5-764 | IRPL to review updated documents and Approve - Security MP | 2024-12-17 | 2025-01-13
I2S-7688-MP-74.CM.MP.5.16.3 | 16.3 - Security Management Plan (20 Bdays) | I.GG.MR.AnF.5-734 | Prepare & Submit to IRPL PM / Project Verifier - Security MP (20 Bdays after Date of Deed) | 2024-09-30 | 2024-11-04
16.4 - Asbestos Management Plan (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-13
I2S-7688-MP-74.CM.MP.5.16.4 | 16.4 - Asbestos Management Plan (20 Bdays) | I.GG.MR.AnF.5-694 | Prepare & Submit to IRPL PM / Project Verifier - Asbestos MP (20 Bdays after Date of Deed) | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.MP.5.16.4 | 16.4 - Asbestos Management Plan (20 Bdays) | I.GG.MR.AnF.5-704 | Project Verifier /IRPL Review Period - Asbestos MP | 2024-11-05 | 2024-12-02
I2S-7688-MP-74.CM.MP.5.16.4 | 16.4 - Asbestos Management Plan (20 Bdays) | I.GG.MR.AnF.5-714 | Update Plan to Reflect any Comments - Asbestos MP | 2024-12-03 | 2024-12-16
I2S-7688-MP-74.CM.MP.5.16.4 | 16.4 - Asbestos Management Plan (20 Bdays) | I.GG.MR.AnF.5-724 | IRPL to review updated documents and Approve - Asbestos MP | 2024-12-17 | 2025-01-13
16.5 - Heavy Vehicle Chain of Responsibility Management plan (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-13
I2S-7688-MP-74.CM.MP.5.16.5 | 16.5 - Heavy Vehicle Chain of Responsibility Management plan (20 Bdays) | I.GG.MR.AnF.5-784 | Project Verifier /IRPL Review Period - Heavy Vehicle CoR MP | 2024-11-05 | 2024-12-02
I2S-7688-MP-74.CM.MP.5.16.5 | 16.5 - Heavy Vehicle Chain of Responsibility Management plan (20 Bdays) | I.GG.MR.AnF.5-794 | Update Plan to Reflect any Comments - Heavy Vehicle CoR MP | 2024-12-03 | 2024-12-16
I2S-7688-MP-74.CM.MP.5.16.5 | 16.5 - Heavy Vehicle Chain of Responsibility Management plan (20 Bdays) | I.GG.MR.AnF.5-804 | IRPL to review updated documents and Approve - Heavy Vehicle CoR MP | 2024-12-17 | 2025-01-13
I2S-7688-MP-74.CM.MP.5.16.5 | 16.5 - Heavy Vehicle Chain of Responsibility Management plan (20 Bdays) | I.GG.MR.AnF.5-774 | Prepare & Submit to IRPL PM / Project Verifier - Heavy Vehicle CoR MP (20 Bdays after Date of Deed) | 2024-09-30 | 2024-11-04
Construction Site Establishment Management Plan (SEMP) - CoA - C5 |  |  |  | 2024-09-30 | 2025-04-15
I2S-7688-MP-74.CM.MP.17 | Construction Site Establishment Management Plan (SEMP) - CoA - C5 | I.GG.CEMP.15990 | CSEMP - JH Finalise draft - Construction Site Establishment Management Plan (CoA - C5) | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.MP.17 | Construction Site Establishment Management Plan (SEMP) - CoA - C5 | I.GG.CEMP.16000 | CSEMP - JH Internal review - Construction Site Establishment Management Plan (CoA - C5) | 2024-11-05 | 2024-11-11
I2S-7688-MP-74.CM.MP.17 | Construction Site Establishment Management Plan (SEMP) - CoA - C5 | I.GG.CEMP.16010 | CSEMP - Consultation with relevant Government agencies (up to 3 weeks) (CoA - C5) | 2024-12-10 | 2025-01-13
I2S-7688-MP-74.CM.MP.17 | Construction Site Establishment Management Plan (SEMP) - CoA - C5 | I.GG.CEMP.16020 | CSEMP - Respond to stakeholder comments (CoA - C5) | 2025-01-14 | 2025-01-20
I2S-7688-MP-74.CM.MP.17 | Construction Site Establishment Management Plan (SEMP) - CoA - C5 | I.GG.CEMP.16030 | CSEMP - Submission to ER for review and endorsement (CoA - C5) | 2025-01-21 | 2025-02-18
I2S-7688-MP-74.CM.MP.17 | Construction Site Establishment Management Plan (SEMP) - CoA - C5 | I.GG.CEMP.16060 | CSEMP - DPHI Lodgement and DPHI Review (2 weeks/ 14 cd) (CoA - C5) | 2025-02-19 | 2025-03-04
I2S-7688-MP-74.CM.MP.17 | Construction Site Establishment Management Plan (SEMP) - CoA - C5 | I.GG.CEMP.16070 | CSEMP approved for commencement of Establishment (1 month before works (CoA - C5) |  | 2025-04-15
I2S-7688-MP-74.CM.MP.17 | Construction Site Establishment Management Plan (SEMP) - CoA - C5 | I.GG.CEMP.16080 | CSEMP - IRPL to review (4 weeks/ 28 cd) (CoA - C5) | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.CM.MP.17 | Construction Site Establishment Management Plan (SEMP) - CoA - C5 | I.GG.CEMP.16240 | CSEMP - JH Respond and incorporate to DPHI comments - Construction Site Establishment Management Plan (CoA - C5) | 2025-03-05 | 2025-03-18
I2S-7688-MP-74.CM.MP.17 | Construction Site Establishment Management Plan (SEMP) - CoA - C5 | I.GG.CEMP.16250 | CSEMP - DPHI Completion of Approval (4 weeks/ 28 cd) - Construction Site Establishment Management Plan (CoA - C5) | 2025-03-19 | 2025-04-15
I2S-7688-MP-74.CM.MP.17 | Construction Site Establishment Management Plan (SEMP) - CoA - C5 | I.GG.CEMP.16320 | CSEMP - IRPL to review updated documents and Approve - Construction Site Establishment Management Plan - CoA - C5 | 2025-03-19 | 2025-04-01
Construction Environmental Management Plan (CEMP) - CoA - C12 to C18 |  |  |  | 2024-09-30 | 2025-07-04
Key CEMP Milestones |  |  |  | 2025-07-03 | 2025-07-04
I2S-7688-MP-74.CM.MP.10.2 | Key CEMP Milestones | I.GG.SMP.1789 | Complete (CEMP/SEMP) Environmental, Sustainability and Social Performance Management plans |  | 2025-07-04
I2S-7688-MP-74.CM.MP.10.2 | Key CEMP Milestones | I.GG.CEMP.14680 | Earliest for accelerated CEMP approved (excluding ACHAR / ACHMP) |  | 2025-07-03
17.1 CEMP - Main Plan |  |  |  | 2024-09-30 | 2025-07-03
I2S-7688-MP-74.CM.MP.10.1 | 17.1 CEMP - Main Plan | I.GG.CEMP.11111 | CEMP - Prepare & Submit to IRPL PM / Project Verifier (30 Bdays after Date of Deed) | 2024-09-30 | 2024-11-11
I2S-7688-MP-74.CM.MP.10.1 | 17.1 CEMP - Main Plan | I.GG.CEMP.11112 | CEMP - Project Verifier /IRPL Review Period | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.CM.MP.10.1 | 17.1 CEMP - Main Plan | I.GG.CEMP.11113 | CEMP - Update Plan to Reflect any Comments | 2024-12-10 | 2025-01-06
I2S-7688-MP-74.CM.MP.10.1 | 17.1 CEMP - Main Plan | I.GG.CEMP.10010 | CEMP - Finalise draft CEMP Report | 2025-01-10 | 2025-01-31
I2S-7688-MP-74.CM.MP.10.1 | 17.1 CEMP - Main Plan | I.GG.CEMP.10020 | CEMP - Rail internal review | 2025-02-03 | 2025-02-07
I2S-7688-MP-74.CM.MP.10.1 | 17.1 CEMP - Main Plan | I.GG.CEMP.10030 | CEMP - Resubmission to ER for review and endorsement (4 weeks/ 28 cd) | 2025-04-17 | 2025-05-19
I2S-7688-MP-74.CM.MP.10.1 | 17.1 CEMP - Main Plan | I.GG.CEMP.10040 | CEMP - Respond to ER Comments on Main CEMP | 2025-05-20 | 2025-05-26
I2S-7688-MP-74.CM.MP.10.1 | 17.1 CEMP - Main Plan | I.GG.CEMP.10050 | CEMP - Resubmission to DPHI of Main CEMP and Sub- Plans for Final Comments (1m after SIMP) | 2025-05-27 | 2025-05-27
I2S-7688-MP-74.CM.MP.10.1 | 17.1 CEMP - Main Plan | I.GG.CEMP.10060 | CEMP - Respond to DPHI comments and re-submit for approval | 2025-06-26 | 2025-07-02
I2S-7688-MP-74.CM.MP.10.1 | 17.1 CEMP - Main Plan | I.GG.CEMP.10070 | CEMP - DPHI approve Main CEMP & Subplans- Construction Environmental Management Plan | 2025-07-03 | 2025-07-03
I2S-7688-MP-74.CM.MP.10.1 | 17.1 CEMP - Main Plan | I.GG.CEMP.16270 | CEMP - IRPL to review updated documents and Approve including JH resubmission (4 weeks/ 28 cd) | 2025-05-23 | 2025-06-20
I2S-7688-MP-74.CM.MP.10.1 | 17.1 CEMP - Main Plan | I.GG.CEMP.16340 | CEMP - DPHI Completion of Final Review (4 weeks/ 28 cd) | 2025-05-28 | 2025-06-25
17.1.1 CEMP Sub-Plans |  |  |  | 2024-09-30 | 2025-05-22
Biosecurity Management Plan (BMP)-- C17- Satge 1 |  |  |  | 2024-09-30 | 2025-04-01
I2S-7688-MP-74.CM.MP.10.7.5 | Biosecurity Management Plan (BMP)-- C17- Satge 1 | I.GG.CEMP.16390 | CBSMP - 2nd Round Submission to ER for review and final endorsement and IRPL Review | 2025-01-21 | 2025-02-18
I2S-7688-MP-74.CM.MP.10.7.5 | Biosecurity Management Plan (BMP)-- C17- Satge 1 | I.GG.CEMP.16400 | CBSMP - DPHI Lodgement and DPHI Review (2 weeks/ 14 cd) (1 month after SIMP approval) | 2025-02-19 | 2025-03-04
I2S-7688-MP-74.CM.MP.10.7.5 | Biosecurity Management Plan (BMP)-- C17- Satge 1 | I.GG.CEMP.16410 | CBSMP - JH Respond and incorporate to DPHI comments | 2025-03-05 | 2025-03-18
I2S-7688-MP-74.CM.MP.10.7.5 | Biosecurity Management Plan (BMP)-- C17- Satge 1 | I.GG.CEMP.16420 | CBSMP - DPHI Completion of Review/Approval (2 weeks/ 14 cd) | 2025-03-19 | 2025-04-01
I2S-7688-MP-74.CM.MP.10.7.5 | Biosecurity Management Plan (BMP)-- C17- Satge 1 | I.GG.CEMP.16430 | CBSMP approved - BioSecurity Management Plan - CoA C17 |  | 2025-04-01
I2S-7688-MP-74.CM.MP.10.7.5 | Biosecurity Management Plan (BMP)-- C17- Satge 1 | I.GG.CEMP.16440 | CBSMP - Initial submission to IRPL for review (4 weeks/ 28 cd) | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.CM.MP.10.7.5 | Biosecurity Management Plan (BMP)-- C17- Satge 1 | I.GG.CEMP.16350 | CBSMP - JH Finalise draft - BioSecurity Management Plan - CoA C17 | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.MP.10.7.5 | Biosecurity Management Plan (BMP)-- C17- Satge 1 | I.GG.CEMP.16360 | CBSMP - JH Internal review of draft inline with EPBC | 2024-11-05 | 2024-11-11
I2S-7688-MP-74.CM.MP.10.7.5 | Biosecurity Management Plan (BMP)-- C17- Satge 1 | I.GG.CEMP.16370 | CBSMP - Consultation with relevant Government agencies (up to 3 weeks) | 2024-12-10 | 2025-01-13
I2S-7688-MP-74.CM.MP.10.7.5 | Biosecurity Management Plan (BMP)-- C17- Satge 1 | I.GG.CEMP.16930 | CBSMP - ER to review updated documents
I2S-7688-MP-74.CM.MP.10.7.5 | Biosecurity Management Plan (BMP)-- C17- Satge 1 | I.GG.CEMP.16650 | CBSMP - Resubmission of plan to IRPL for review
I2S-7688-MP-74.CM.MP.10.7.5 | Biosecurity Management Plan (BMP)-- C17- Satge 1 | I.GG.CEMP.16660 | CBSMP - IRPL to review updated documents
Construction Noise and Vibration Management Plan (CNVMP) - C19 (was C8) -Stage 2 |  |  |  | 2024-09-30 | 2025-04-15
I2S-7688-MP-74.CM.MP.10.7.3 | Construction Noise and Vibration Management Plan (CNVMP) - C19 (was C8) -Stage 2 | I.GG.CEMP.10350 | CNVMP - JH Finalise draft - Construction Noise and Vibration Sub- Plan CoA C19 | 2024-09-30 | 2024-11-11
I2S-7688-MP-74.CM.MP.10.7.3 | Construction Noise and Vibration Management Plan (CNVMP) - C19 (was C8) -Stage 2 | I.GG.CEMP.10360 | CNVMP - JH Internal review - Construction Noise and Vibration Sub- Plan - CoA - C19 | 2024-11-12 | 2024-11-18
I2S-7688-MP-74.CM.MP.10.7.3 | Construction Noise and Vibration Management Plan (CNVMP) - C19 (was C8) -Stage 2 | I.GG.CEMP.10370 | CNVMP - Consultation with relevant Government agencies (up to 3 weeks) - Construction Noise and Vibration Sub- Plan CoA | 2024-12-17 | 2025-01-20
I2S-7688-MP-74.CM.MP.10.7.3 | Construction Noise and Vibration Management Plan (CNVMP) - C19 (was C8) -Stage 2 | I.GG.CEMP.10390 | CNVMP - 2nd Submission to ER for review and endorsement and IRPL Review - Construction Noise and Vibration Sub- Plan CoA | 2025-01-29 | 2025-02-25
I2S-7688-MP-74.CM.MP.10.7.3 | Construction Noise and Vibration Management Plan (CNVMP) - C19 (was C8) -Stage 2 | I.GG.CEMP.10400 | CNVMP - DPHI Lodgement and DPHI Review (2 weeks/ 14 cd) - CoA - C19 (1 month after SIMP approval) | 2025-02-26 | 2025-03-11
I2S-7688-MP-74.CM.MP.10.7.3 | Construction Noise and Vibration Management Plan (CNVMP) - C19 (was C8) -Stage 2 | I.GG.CEMP.10410 | CNVMP - JH Respond and incorporate to DPHI comments - CoA - C19 | 2025-03-12 | 2025-03-18
I2S-7688-MP-74.CM.MP.10.7.3 | Construction Noise and Vibration Management Plan (CNVMP) - C19 (was C8) -Stage 2 | I.GG.CEMP.10420 | CNVMP - DPHI Completion of Review/Approval - CoA - C19 | 2025-03-19 | 2025-04-15
I2S-7688-MP-74.CM.MP.10.7.3 | Construction Noise and Vibration Management Plan (CNVMP) - C19 (was C8) -Stage 2 | I.GG.CEMP.10430 | CNVMP - Construction Noise and Vibration Sub- Plan approved - CoA - C19 |  | 2025-04-15
I2S-7688-MP-74.CM.MP.10.7.3 | Construction Noise and Vibration Management Plan (CNVMP) - C19 (was C8) -Stage 2 | I.GG.CEMP.16110 | CNVMP - Initial submiission to IRPL for review (4 weeks/ 28 cd) - CoA - C19 | 2024-11-19 | 2024-12-16
I2S-7688-MP-74.CM.MP.10.7.3 | Construction Noise and Vibration Management Plan (CNVMP) - C19 (was C8) -Stage 2 | I.GG.CEMP.16950 | CNVMP - ER to review updated documents
I2S-7688-MP-74.CM.MP.10.7.3 | Construction Noise and Vibration Management Plan (CNVMP) - C19 (was C8) -Stage 2 | I.GG.CEMP.16670 | CNVMP - Resubmission of plan to IRPL for review
I2S-7688-MP-74.CM.MP.10.7.3 | Construction Noise and Vibration Management Plan (CNVMP) - C19 (was C8) -Stage 2 | I.GG.CEMP.16680 | CNVMP - IRPL to review updated documents
Construction Biodiversity Management Plan (CBMP) - C20 , C25 (was C9) - Stage 2 |  |  |  | 2024-09-30 | 2025-04-15
I2S-7688-MP-74.CM.MP.10.7.4 | Construction Biodiversity Management Plan (CBMP) - C20 , C25 (was C9) - Stage 2 | I.GG.CEMP.16960 | CBMP - ER to review updated documents
I2S-7688-MP-74.CM.MP.10.7.4 | Construction Biodiversity Management Plan (CBMP) - C20 , C25 (was C9) - Stage 2 | I.GG.CEMP.16690 | CBMP - Resubmission of plan to IRPL for review
I2S-7688-MP-74.CM.MP.10.7.4 | Construction Biodiversity Management Plan (CBMP) - C20 , C25 (was C9) - Stage 2 | I.GG.CEMP.16700 | CBMP - IRPL to review updated documents
I2S-7688-MP-74.CM.MP.10.7.4 | Construction Biodiversity Management Plan (CBMP) - C20 , C25 (was C9) - Stage 2 | I.GG.CEMP.10260 | CBMP - JH Finalise draft - Biodiversity BCS - CoA - C20 | 2024-09-30 | 2024-11-18
I2S-7688-MP-74.CM.MP.10.7.4 | Construction Biodiversity Management Plan (CBMP) - C20 , C25 (was C9) - Stage 2 | I.GG.CEMP.10270 | CBMP - JH Internal review draft inline with EPBC - CoA - C20 | 2024-11-19 | 2024-11-25
I2S-7688-MP-74.CM.MP.10.7.4 | Construction Biodiversity Management Plan (CBMP) - C20 , C25 (was C9) - Stage 2 | I.GG.CEMP.10280 | CBMP - Consultation with relevant Government agencies (up to 3 weeks) - CoA - C20 | 2025-01-07 | 2025-01-28
I2S-7688-MP-74.CM.MP.10.7.4 | Construction Biodiversity Management Plan (CBMP) - C20 , C25 (was C9) - Stage 2 | I.GG.CEMP.10300 | CBMP - 2nd round Submission to ER for review and endorsement and IRPL Review - CoA - C20 | 2025-02-05 | 2025-03-04
I2S-7688-MP-74.CM.MP.10.7.4 | Construction Biodiversity Management Plan (CBMP) - C20 , C25 (was C9) - Stage 2 | I.GG.CEMP.10310 | CBMP - DPHI Lodgement and DPHI Review (2 weeks/ 14 cd) - CoA - C20 (1 month after SIMP approval) | 2025-03-05 | 2025-03-18
I2S-7688-MP-74.CM.MP.10.7.4 | Construction Biodiversity Management Plan (CBMP) - C20 , C25 (was C9) - Stage 2 | I.GG.CEMP.10320 | CBMP - JH Respond and incorporate to DPHI comments - CoA - C20 | 2025-03-19 | 2025-04-01
I2S-7688-MP-74.CM.MP.10.7.4 | Construction Biodiversity Management Plan (CBMP) - C20 , C25 (was C9) - Stage 2 | I.GG.CEMP.10330 | CBMP - DPHI Completion of Review/Approval (2 weeks/ 14 cd) - CoA - C20 | 2025-04-02 | 2025-04-15
I2S-7688-MP-74.CM.MP.10.7.4 | Construction Biodiversity Management Plan (CBMP) - C20 , C25 (was C9) - Stage 2 | I.GG.CEMP.10340 | CBMP - The Biodiversity Management Sub- Plan approved - CoA - C20, C25-NEW |  | 2025-04-15
I2S-7688-MP-74.CM.MP.10.7.4 | Construction Biodiversity Management Plan (CBMP) - C20 , C25 (was C9) - Stage 2 | I.GG.CEMP.16120 | CBMP - Initial submiission to IRPL for review (4 weeks/ 28 cd) - CoA - C20 | 2024-11-26 | 2025-01-06
Construction Pest and Weed Management Plan (CPWMP)-Included in CBMP/C20 |  |  |  | 2024-09-30 | 2025-04-01
I2S-7688-MP-74.CM.MP.10.7.4.5 | Construction Pest and Weed Management Plan (CPWMP)-Included in CBMP/C20 | I.GG.CEMP.17020 | CPWMP - ER to review updated documents and Approve
I2S-7688-MP-74.CM.MP.10.7.4.5 | Construction Pest and Weed Management Plan (CPWMP)-Included in CBMP/C20 | I.GG.CEMP.16710 | CPWMP - Resubmission of plan to IRPL for review
I2S-7688-MP-74.CM.MP.10.7.4.5 | Construction Pest and Weed Management Plan (CPWMP)-Included in CBMP/C20 | I.GG.CEMP.16720 | CPWMP - IRPL to review updated documents
I2S-7688-MP-74.CM.MP.10.7.4.5 | Construction Pest and Weed Management Plan (CPWMP)-Included in CBMP/C20 | I.GG.CEMP.10620 | CPWMP - JH Finalise draft | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.MP.10.7.4.5 | Construction Pest and Weed Management Plan (CPWMP)-Included in CBMP/C20 | I.GG.CEMP.10630 | CPWMP - JH Internal review of draft inline with EPBC | 2024-11-05 | 2024-11-11
I2S-7688-MP-74.CM.MP.10.7.4.5 | Construction Pest and Weed Management Plan (CPWMP)-Included in CBMP/C20 | I.GG.CEMP.10640 | CPWMP - Consultation with relevant Government agencies (up to 3 weeks) | 2024-12-10 | 2025-01-13
I2S-7688-MP-74.CM.MP.10.7.4.5 | Construction Pest and Weed Management Plan (CPWMP)-Included in CBMP/C20 | I.GG.CEMP.10670 | CPWMP - DPHI Lodgement and DPHI Review (2 weeks/ 14 cd) (1 month after SIMP approval) | 2025-02-19 | 2025-03-04
I2S-7688-MP-74.CM.MP.10.7.4.5 | Construction Pest and Weed Management Plan (CPWMP)-Included in CBMP/C20 | I.GG.CEMP.10680 | CPWMP - JH Respond and incorporate to DPHI comments | 2025-03-05 | 2025-03-18
I2S-7688-MP-74.CM.MP.10.7.4.5 | Construction Pest and Weed Management Plan (CPWMP)-Included in CBMP/C20 | I.GG.CEMP.10690 | CPWMP - DPHI Completion of Review/Approval (2 weeks/ 14 cd) | 2025-03-19 | 2025-04-01
I2S-7688-MP-74.CM.MP.10.7.4.5 | Construction Pest and Weed Management Plan (CPWMP)-Included in CBMP/C20 | I.GG.CEMP.10700 | CPWMP approved |  | 2025-04-01
I2S-7688-MP-74.CM.MP.10.7.4.5 | Construction Pest and Weed Management Plan (CPWMP)-Included in CBMP/C20 | I.GG.CEMP.16130 | CPWMP - Initial submiission to IRPL for review (4 weeks/ 28 cd) | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.CM.MP.10.7.4.5 | Construction Pest and Weed Management Plan (CPWMP)-Included in CBMP/C20 | I.GG.CEMP.10660 | CPWMP - 2nd Round Submission to ER for review and endorsement and IRPL Review | 2025-01-21 | 2025-02-18
Construction Traffic, Transport and Access Management Plan (CTTAMP) - C21 (was C10)-Srage 2 |  |  |  | 2024-09-30 | 2025-04-08
I2S-7688-MP-74.CM.MP.10.7.2 | Construction Traffic, Transport and Access Management Plan (CTTAMP) - C21 (was C10)-Srage 2 | I.GG.CEMP.10210 | CTTAMP - TfNSW endorsement - CoA - C21 | 2025-01-29 | 2025-02-25
I2S-7688-MP-74.CM.MP.10.7.2 | Construction Traffic, Transport and Access Management Plan (CTTAMP) - C21 (was C10)-Srage 2 | I.GG.CEMP.10220 | CTTAMP - DPHI Lodgement and DPHI Review and approve (2 weeks/ 14 cd) - CoA - C21 | 2025-02-26 | 2025-03-11
I2S-7688-MP-74.CM.MP.10.7.2 | Construction Traffic, Transport and Access Management Plan (CTTAMP) - C21 (was C10)-Srage 2 | I.GG.CEMP.10250 | CTTAMP - Traffic, Transport and Access Management Sub- Plan approved - CoA - C21 |  | 2025-04-08
I2S-7688-MP-74.CM.MP.10.7.2 | Construction Traffic, Transport and Access Management Plan (CTTAMP) - C21 (was C10)-Srage 2 | I.GG.CEMP.16100 | CTTAMP - Initial submission to IRPL for review (4 weeks/ 28 cd) - CoA - C21 | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.CM.MP.10.7.2 | Construction Traffic, Transport and Access Management Plan (CTTAMP) - C21 (was C10)-Srage 2 | I.GG.CEMP.16890 | CTTAMP - Submission of CTTAMP to IRPL
I2S-7688-MP-74.CM.MP.10.7.2 | Construction Traffic, Transport and Access Management Plan (CTTAMP) - C21 (was C10)-Srage 2 | I.GG.CEMP.16900 | CTTAMP - IRPL, LGAs & TfNSW initial review
I2S-7688-MP-74.CM.MP.10.7.2 | Construction Traffic, Transport and Access Management Plan (CTTAMP) - C21 (was C10)-Srage 2 | I.GG.CEMP.16910 | CTTAMP - IRPL, LGAs, & TfNSW Comments received & inperson workshop held
I2S-7688-MP-74.CM.MP.10.7.2 | Construction Traffic, Transport and Access Management Plan (CTTAMP) - C21 (was C10)-Srage 2 | I.GG.CEMP.16920 | CTTAMP - CTTAMP Updated and Resubmitted
I2S-7688-MP-74.CM.MP.10.7.2 | Construction Traffic, Transport and Access Management Plan (CTTAMP) - C21 (was C10)-Srage 2 | I.GG.CEMP.16940 | CTTAMP - IRPL, LGAs & TfNSW second review + inperson workshop held
I2S-7688-MP-74.CM.MP.10.7.2 | Construction Traffic, Transport and Access Management Plan (CTTAMP) - C21 (was C10)-Srage 2 | I.GG.CEMP.17390 | CTTAMP - Updated Comments and Resubmitted to IRPL & TfNSW 3rd time
I2S-7688-MP-74.CM.MP.10.7.2 | Construction Traffic, Transport and Access Management Plan (CTTAMP) - C21 (was C10)-Srage 2 | I.GG.CEMP.17400 | CTTAMP - IRPL, LGAs & TfNSW 3rd review
I2S-7688-MP-74.CM.MP.10.7.2 | Construction Traffic, Transport and Access Management Plan (CTTAMP) - C21 (was C10)-Srage 2 | I.GG.CEMP.16730 | CTTAMP - First revision CTTAMP being developed
I2S-7688-MP-74.CM.MP.10.7.2 | Construction Traffic, Transport and Access Management Plan (CTTAMP) - C21 (was C10)-Srage 2 | I.GG.CEMP.10170 | CTTAMP - JH Finalise draft - Physical Conditions of Local Roads (including monitoring program - CoA - C21 | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.MP.10.7.2 | Construction Traffic, Transport and Access Management Plan (CTTAMP) - C21 (was C10)-Srage 2 | I.GG.CEMP.10180 | CTTAMP - JH Internal review - CoA - C21 | 2024-11-05 | 2024-11-11
I2S-7688-MP-74.CM.MP.10.7.2 | Construction Traffic, Transport and Access Management Plan (CTTAMP) - C21 (was C10)-Srage 2 | I.GG.CEMP.10190 | CTTAMP - Consultation with TfNSW - CoA - C21 | 2024-12-10 | 2025-01-20
Construction Soil and Water Management Plan (CSWMP) - C22 (was C11) - Stage 1 |  |  |  | 2024-09-30 | 2025-04-15
I2S-7688-MP-74.CM.MP.10.7.1 | Construction Soil and Water Management Plan (CSWMP) - C22 (was C11) - Stage 1 | I.GG.CEMP.10090 | CSWMP - JH Internal review draft inline with EPBC - CoA - C22 | 2024-11-19 | 2024-11-25
I2S-7688-MP-74.CM.MP.10.7.1 | Construction Soil and Water Management Plan (CSWMP) - C22 (was C11) - Stage 1 | I.GG.CEMP.10100 | CSWMP - Consultation with NRAA Water Group/ EES and Councils (up to 3 weeks) - CoA - C22 | 2025-01-07 | 2025-01-28
I2S-7688-MP-74.CM.MP.10.7.1 | Construction Soil and Water Management Plan (CSWMP) - C22 (was C11) - Stage 1 | I.GG.CEMP.10120 | CSWMP - 2nd round Submission to ER for review and endorsement and IRPL Review (4 weeks/ 28 cd) - CoA - C22 | 2025-02-05 | 2025-03-04
I2S-7688-MP-74.CM.MP.10.7.1 | Construction Soil and Water Management Plan (CSWMP) - C22 (was C11) - Stage 1 | I.GG.CEMP.10130 | CSWMP - DPHI Lodgement and DPHI Review (2 weeks/ 14 cd) - CoA - C22 (1 month after SIMP approval) | 2025-03-05 | 2025-03-18
I2S-7688-MP-74.CM.MP.10.7.1 | Construction Soil and Water Management Plan (CSWMP) - C22 (was C11) - Stage 1 | I.GG.CEMP.10140 | CSWMP - JH Respond and incorporate to DPHI comments - CoA - C22 | 2025-03-19 | 2025-04-01
I2S-7688-MP-74.CM.MP.10.7.1 | Construction Soil and Water Management Plan (CSWMP) - C22 (was C11) - Stage 1 | I.GG.CEMP.10150 | CSWMP - DPHI Completion of Review/Approval (2 weeks/ 14 cd) - CoA - C22 | 2025-04-02 | 2025-04-15
I2S-7688-MP-74.CM.MP.10.7.1 | Construction Soil and Water Management Plan (CSWMP) - C22 (was C11) - Stage 1 | I.GG.CEMP.10160 | CSWMP - The Soil and Water Management Sub- Plan approved - CoA - C22 |  | 2025-04-15
I2S-7688-MP-74.CM.MP.10.7.1 | Construction Soil and Water Management Plan (CSWMP) - C22 (was C11) - Stage 1 | I.GG.CEMP.16090 | CSWMP - Initial submission to IRPL for review (4 weeks/ 28 cd) - CoA - C22 | 2024-11-26 | 2025-01-06
I2S-7688-MP-74.CM.MP.10.7.1 | Construction Soil and Water Management Plan (CSWMP) - C22 (was C11) - Stage 1 | I.GG.CEMP.16970 | CSWMP - ER to review updated documents and Approve
I2S-7688-MP-74.CM.MP.10.7.1 | Construction Soil and Water Management Plan (CSWMP) - C22 (was C11) - Stage 1 | I.GG.CEMP.16750 | CSWMP - Resubmission of plan to IRPL for review
I2S-7688-MP-74.CM.MP.10.7.1 | Construction Soil and Water Management Plan (CSWMP) - C22 (was C11) - Stage 1 | I.GG.CEMP.16760 | CSWMP - IRPL to review updated documents and Approve
I2S-7688-MP-74.CM.MP.10.7.1 | Construction Soil and Water Management Plan (CSWMP) - C22 (was C11) - Stage 1 | I.GG.CEMP.10080 | CSWMP - JH Finalise draft - Water Usage (including monitoring program) - CoA - C22 | 2024-09-30 | 2024-11-18
Construction Air Quality Management Plan (CAQMP) - Included in CSWMP/C22 |  |  |  | 2024-09-30 | 2025-04-01
I2S-7688-MP-74.CM.MP.10.7.1.6 | Construction Air Quality Management Plan (CAQMP) - Included in CSWMP/C22 | I.GG.CEMP.17030 | CAQMP - Resubmission of plan to IRPL for review
I2S-7688-MP-74.CM.MP.10.7.1.6 | Construction Air Quality Management Plan (CAQMP) - Included in CSWMP/C22 | I.GG.CEMP.17040 | CAQMP - IRPL to review updated documents and Approve
I2S-7688-MP-74.CM.MP.10.7.1.6 | Construction Air Quality Management Plan (CAQMP) - Included in CSWMP/C22 | I.GG.CEMP.17050 | CAQMP - ER to review updated documents and Approve
I2S-7688-MP-74.CM.MP.10.7.1.6 | Construction Air Quality Management Plan (CAQMP) - Included in CSWMP/C22 | I.GG.CEMP.10530 | CAQMP - JH Finalise draft - Air Quality (including monitoring program) | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.MP.10.7.1.6 | Construction Air Quality Management Plan (CAQMP) - Included in CSWMP/C22 | I.GG.CEMP.10540 | CAQMP - JH Internal review | 2024-11-05 | 2024-11-11
I2S-7688-MP-74.CM.MP.10.7.1.6 | Construction Air Quality Management Plan (CAQMP) - Included in CSWMP/C22 | I.GG.CEMP.10550 | CAQMP - Consultation with relevant Government agencies (up to 3 weeks) | 2024-12-10 | 2025-01-13
I2S-7688-MP-74.CM.MP.10.7.1.6 | Construction Air Quality Management Plan (CAQMP) - Included in CSWMP/C22 | I.GG.CEMP.10570 | CAQMP - 2nd Submission to ER for review and endorsement and IRPL Review | 2025-01-21 | 2025-02-18
I2S-7688-MP-74.CM.MP.10.7.1.6 | Construction Air Quality Management Plan (CAQMP) - Included in CSWMP/C22 | I.GG.CEMP.10580 | CAQMP - DPHI Lodgement and DPHI Review (2 weeks/ 14 cd) (1 month after SIMP approval) | 2025-02-19 | 2025-03-04
I2S-7688-MP-74.CM.MP.10.7.1.6 | Construction Air Quality Management Plan (CAQMP) - Included in CSWMP/C22 | I.GG.CEMP.10590 | CAQMP - JH Respond and incorporate to DPHI comments | 2025-03-05 | 2025-03-18
I2S-7688-MP-74.CM.MP.10.7.1.6 | Construction Air Quality Management Plan (CAQMP) - Included in CSWMP/C22 | I.GG.CEMP.10600 | CAQMP - DPHI Completion of Review/Approval (2 weeks/ 14 cd) | 2025-03-19 | 2025-04-01
I2S-7688-MP-74.CM.MP.10.7.1.6 | Construction Air Quality Management Plan (CAQMP) - Included in CSWMP/C22 | I.GG.CEMP.10610 | CAQMP approved |  | 2025-04-01
I2S-7688-MP-74.CM.MP.10.7.1.6 | Construction Air Quality Management Plan (CAQMP) - Included in CSWMP/C22 | I.GG.CEMP.16140 | CAQMP - Initial submiission to IRPL for review (4 weeks/ 28 cd) | 2024-11-12 | 2024-12-09
Aboriginal Cultural Heritage Management Plan (ACHMP) - C23 (was C12) - Stage 1 |  |  |  | 2024-10-30 | 2025-05-22
I2S-7688-MP-74.CM.MP.10.7.12 | Aboriginal Cultural Heritage Management Plan (ACHMP) - C23 (was C12) - Stage 1 | I.GG.CEMP.16040 | ACHMP - IRPL to review updated documents and Approve
I2S-7688-MP-74.CM.MP.10.7.12 | Aboriginal Cultural Heritage Management Plan (ACHMP) - C23 (was C12) - Stage 1 | I.GG.CEMP.16790 | ACHMP - Resubmission of plan to IRPL for review
I2S-7688-MP-74.CM.MP.10.7.12 | Aboriginal Cultural Heritage Management Plan (ACHMP) - C23 (was C12) - Stage 1 | I.GG.CEMP.15360 | ACHMP - JH Finalise draft - Heritage Management Sub- Plan - CoA C23 | 2024-10-30 | 2024-12-03
I2S-7688-MP-74.CM.MP.10.7.12 | Aboriginal Cultural Heritage Management Plan (ACHMP) - C23 (was C12) - Stage 1 | I.GG.CEMP.15370 | ACHMP - JH Internal review - CoA - C23 | 2024-12-04 | 2024-12-10
I2S-7688-MP-74.CM.MP.10.7.12 | Aboriginal Cultural Heritage Management Plan (ACHMP) - C23 (was C12) - Stage 1 | I.GG.CEMP.15380 | ACHMP - Consultation with relevant Government agencies (up to 3 weeks) - CoA - C23 | 2025-02-11 | 2025-03-03
I2S-7688-MP-74.CM.MP.10.7.12 | Aboriginal Cultural Heritage Management Plan (ACHMP) - C23 (was C12) - Stage 1 | I.GG.CEMP.15400 | ACHMP - 2nd Submission to ER for review and endorsement and IRPL Review - CoA - C23 | 2025-03-11 | 2025-04-07
I2S-7688-MP-74.CM.MP.10.7.12 | Aboriginal Cultural Heritage Management Plan (ACHMP) - C23 (was C12) - Stage 1 | I.GG.CEMP.15410 | ACHMP - DPHI Lodgement and DPHI Review (2 weeks/ 14 cd) - CoA - C23 (1 month after SIMP approval) | 2025-04-08 | 2025-04-23
I2S-7688-MP-74.CM.MP.10.7.12 | Aboriginal Cultural Heritage Management Plan (ACHMP) - C23 (was C12) - Stage 1 | I.GG.CEMP.15420 | ACHMP - JH Respond and incorporate to DPHI comments - CoA - C23 | 2025-04-24 | 2025-05-08
I2S-7688-MP-74.CM.MP.10.7.12 | Aboriginal Cultural Heritage Management Plan (ACHMP) - C23 (was C12) - Stage 1 | I.GG.CEMP.15430 | ACHMP - DPHI Completion of Review/Approval (2 weeks/ 14 cd) - CoA - C23 | 2025-05-09 | 2025-05-22
I2S-7688-MP-74.CM.MP.10.7.12 | Aboriginal Cultural Heritage Management Plan (ACHMP) - C23 (was C12) - Stage 1 | I.GG.CEMP.15440 | ACHMP - Heritage Management Sub- Plan approved - CoA - C23 |  | 2025-05-22
I2S-7688-MP-74.CM.MP.10.7.12 | Aboriginal Cultural Heritage Management Plan (ACHMP) - C23 (was C12) - Stage 1 | I.GG.CEMP.16180 | ACHMP - Initial submiission to IRPL for review (4 weeks/ 28 cd) - CoA - C23 | 2025-01-13 | 2025-02-10
I2S-7688-MP-74.CM.MP.10.7.12 | Aboriginal Cultural Heritage Management Plan (ACHMP) - C23 (was C12) - Stage 1 | I.GG.CEMP.16450 | ACHMP - JH prepare a procedure for addiitonal survey - Heritage Management Sub- Plan - CoA C23 | 2024-12-04 | 2025-01-07
I2S-7688-MP-74.CM.MP.10.7.12 | Aboriginal Cultural Heritage Management Plan (ACHMP) - C23 (was C12) - Stage 1 | I.GG.CEMP.16980 | ACHMP - ER to review updated documents and Approve
Construction Flood Emergency Management Plan (CFEMP) - C24 and E98 (was C13 /E133)Stage 1 |  |  |  | 2024-09-30 | 2025-05-19
I2S-7688-MP-74.CM.MP.10.7.7 | Construction Flood Emergency Management Plan (CFEMP) - C24 and E98 (was C13 /E133)Stage 1 | I.GG.CEMP.10480 | CFEMP - 2nd Submission to ER for review and endorsement -Flood Emergency Plan CoA -C24, E98 | 2025-03-06 | 2025-04-02
I2S-7688-MP-74.CM.MP.10.7.7 | Construction Flood Emergency Management Plan (CFEMP) - C24 and E98 (was C13 /E133)Stage 1 | I.GG.CEMP.17350 | CFEMP - CPHR Comment close out -Flood Emergency Plan CoA -C24, E98
I2S-7688-MP-74.CM.MP.10.7.7 | Construction Flood Emergency Management Plan (CFEMP) - C24 and E98 (was C13 /E133)Stage 1 | I.GG.CEMP.17360 | CFEMP - DPHI Lodgement and DPHI Review / Approve -Flood Emergency Plan CoA -C24, E98
I2S-7688-MP-74.CM.MP.10.7.7 | Construction Flood Emergency Management Plan (CFEMP) - C24 and E98 (was C13 /E133)Stage 1 | I.GG.CEMP.17370 | CFEMP - JH Respond and incorporate to DPHI comments -Flood Emergency Plan CoA -C24, E98
I2S-7688-MP-74.CM.MP.10.7.7 | Construction Flood Emergency Management Plan (CFEMP) - C24 and E98 (was C13 /E133)Stage 1 | I.GG.CEMP.17380 | CFEMP - DPHI Completion of Review / Approve -Flood Emergency Plan CoA -C24, E98
I2S-7688-MP-74.CM.MP.10.7.7 | Construction Flood Emergency Management Plan (CFEMP) - C24 and E98 (was C13 /E133)Stage 1 | I.GG.CEMP.16770 | CFEMP - IRPL to review updated documents and Approve
I2S-7688-MP-74.CM.MP.10.7.7 | Construction Flood Emergency Management Plan (CFEMP) - C24 and E98 (was C13 /E133)Stage 1 | I.GG.CEMP.16780 | CFEMP - Resubmission of plan to IRPL for review
I2S-7688-MP-74.CM.MP.10.7.7 | Construction Flood Emergency Management Plan (CFEMP) - C24 and E98 (was C13 /E133)Stage 1 | I.GG.CEMP.10520 | CFEMP - Flood Emergency Management Sub- Plan approved - CoA - C24 ,CoA - E98 |  | 2025-05-19
I2S-7688-MP-74.CM.MP.10.7.7 | Construction Flood Emergency Management Plan (CFEMP) - C24 and E98 (was C13 /E133)Stage 1 | I.GG.CEMP.16150 | CFEMP - Initial submiission to IRPL for review (4 weeks/ 28 cd)-Flood Emergency Plan CoA -C24, E98 | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.CM.MP.10.7.7 | Construction Flood Emergency Management Plan (CFEMP) - C24 and E98 (was C13 /E133)Stage 1 | I.GG.CEMP.10440 | CFEMP - JH Finalise draft -Flood Emergency Plan CoA -C24, E98 | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.MP.10.7.7 | Construction Flood Emergency Management Plan (CFEMP) - C24 and E98 (was C13 /E133)Stage 1 | I.GG.CEMP.10450 | CFEMP - JH Internal review -Flood Emergency Plan CoA -C24, E98 | 2024-11-05 | 2024-11-11
I2S-7688-MP-74.CM.MP.10.7.7 | Construction Flood Emergency Management Plan (CFEMP) - C24 and E98 (was C13 /E133)Stage 1 | I.GG.CEMP.10460 | CFEMP - Consultation with relevant Government agencies -Flood Emergency Plan CoA -C24, E98 | 2025-02-06 | 2025-02-26
Construction Bushfire Emergency Management Plan (CFEMP) - C24 and E98 (was C13 /E133)- Stage 1
I2S-7688-MP-74.CM.MP.10.7.6 | Construction Bushfire Emergency Management Plan (CFEMP) - C24 and E98 (was C13 /E133)- Stage 1 | I.GG.CEMP.17300 | CFEMP - Consultation with relevant Government agencies - Bushfire Emergency Plan CoA -C24, E98
I2S-7688-MP-74.CM.MP.10.7.6 | Construction Bushfire Emergency Management Plan (CFEMP) - C24 and E98 (was C13 /E133)- Stage 1 | I.GG.CEMP.17240 | CFEMP - IRPL to review updated documents and Approve
I2S-7688-MP-74.CM.MP.10.7.6 | Construction Bushfire Emergency Management Plan (CFEMP) - C24 and E98 (was C13 /E133)- Stage 1 | I.GG.CEMP.17250 | CFEMP - Resubmission of plan to IRPL for review
I2S-7688-MP-74.CM.MP.10.7.6 | Construction Bushfire Emergency Management Plan (CFEMP) - C24 and E98 (was C13 /E133)- Stage 1 | I.GG.CEMP.17270 | CFEMP - Initial submiission to IRPL for review (4 weeks/ 28 cd) - Bushfire Emergency Plan CoA -C24, E98
I2S-7688-MP-74.CM.MP.10.7.6 | Construction Bushfire Emergency Management Plan (CFEMP) - C24 and E98 (was C13 /E133)- Stage 1 | I.GG.CEMP.17280 | CFEMP - JH Finalise draft - Bushfire Emergency Plan CoA -C24, E98
I2S-7688-MP-74.CM.MP.10.7.6 | Construction Bushfire Emergency Management Plan (CFEMP) - C24 and E98 (was C13 /E133)- Stage 1 | I.GG.CEMP.17290 | CFEMP - JH Internal review - Bushfire Emergency Plan CoA -C24, E98
I2S-7688-MP-74.CM.MP.10.7.6 | Construction Bushfire Emergency Management Plan (CFEMP) - C24 and E98 (was C13 /E133)- Stage 1 | I.GG.CEMP.17260 | CFEMP - Bushfire Emergency Plan approved - CoA - C24 ,CoA - E98
Contaminated Land and Hazardous Materials Management Plan - Stage 1 |  |  |  | 2024-09-30 | 2025-04-15
I2S-7688-MP-74.CM.MP.10.7.11 | Contaminated Land and Hazardous Materials Management Plan - Stage 1 | I.GG.CEMP.16800 | CLHMMP - Resubmission of plan to IRPL for review
I2S-7688-MP-74.CM.MP.10.7.11 | Contaminated Land and Hazardous Materials Management Plan - Stage 1 | I.GG.CEMP.16810 | CLHMMP - IRPL to review updated documents and Approve
I2S-7688-MP-74.CM.MP.10.7.11 | Contaminated Land and Hazardous Materials Management Plan - Stage 1 | I.GG.CEMP.15010 | CLHMMP - JH Internal review | 2024-11-05 | 2024-11-11
I2S-7688-MP-74.CM.MP.10.7.11 | Contaminated Land and Hazardous Materials Management Plan - Stage 1 | I.GG.CEMP.15020 | CLHMMP - Consultation with relevant Government agencies (up to 3 weeks) | 2024-12-10 | 2025-01-13
I2S-7688-MP-74.CM.MP.10.7.11 | Contaminated Land and Hazardous Materials Management Plan - Stage 1 | I.GG.CEMP.15030 | CLHMMP - Respond to stakeholder comments | 2025-01-14 | 2025-01-20
I2S-7688-MP-74.CM.MP.10.7.11 | Contaminated Land and Hazardous Materials Management Plan - Stage 1 | I.GG.CEMP.15040 | CLHMMP - Submission to ER for review and endorsement and IRPL Review | 2025-01-21 | 2025-02-18
I2S-7688-MP-74.CM.MP.10.7.11 | Contaminated Land and Hazardous Materials Management Plan - Stage 1 | I.GG.CEMP.15080 | CLHMMP - approved |  | 2025-04-15
I2S-7688-MP-74.CM.MP.10.7.11 | Contaminated Land and Hazardous Materials Management Plan - Stage 1 | I.GG.CEMP.16160 | CLHMMP - Initial submiission to IRPL for review (4 weeks/ 28 cd) | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.CM.MP.10.7.11 | Contaminated Land and Hazardous Materials Management Plan - Stage 1 | I.GG.CEMP.15000 | CLHMMP - JH Finalise draft | 2024-09-30 | 2024-11-04
Unexpected Contaminated Land and Asbestos Finds Procedure - E166 |  |  |  | 2024-12-10 | 2025-03-18
I2S-7688-MP-74.CM.MP.10.7.11.9 | Unexpected Contaminated Land and Asbestos Finds Procedure - E166 | I.GG.MR.AnF.5-1034 | CoA - E166 - Prepare & Submit to IRPL PM / Project Verifier - Unexpected Contaminated Land and Asbestos Procedure | 2024-12-10 | 2025-02-04
I2S-7688-MP-74.CM.MP.10.7.11.9 | Unexpected Contaminated Land and Asbestos Finds Procedure - E166 | I.GG.MR.AnF.5-1044 | CoA - E166 - Project Verifier /IRPL Review Period - Unexpected Contaminated Land and Asbestos Procedure | 2025-02-05 | 2025-03-04
I2S-7688-MP-74.CM.MP.10.7.11.9 | Unexpected Contaminated Land and Asbestos Finds Procedure - E166 | I.GG.MR.AnF.5-1054 | CoA - E166 - Update Plan to Reflect any Comments - Unexpected Contaminated Land and Asbestos Procedure | 2025-03-05 | 2025-03-18
I2S-7688-MP-74.CM.MP.10.7.11.9 | Unexpected Contaminated Land and Asbestos Finds Procedure - E166 | I.GG.MR.AnF.5-1064 | CoA - E166 - Complete & Approved - Unexpected Contaminated Land and Asbestos Finds Procedure |  | 2025-03-18
Construction Waste Management Plan - Stage 1 |  |  |  | 2024-09-30 | 2025-04-01
I2S-7688-MP-74.CM.MP.10.7.16 | Construction Waste Management Plan - Stage 1 | I.GG.CEMP.16820 | CWMP - Resubmission of plan to IRPL for review
I2S-7688-MP-74.CM.MP.10.7.16 | Construction Waste Management Plan - Stage 1 | I.GG.CEMP.16830 | CWMP - IRPL to review updated documents and Approve
I2S-7688-MP-74.CM.MP.10.7.16 | Construction Waste Management Plan - Stage 1 | I.GG.CEMP.16200 | CWMP - Initial submiission to IRPL for review (4 weeks/ 28 cd) | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.CM.MP.10.7.16 | Construction Waste Management Plan - Stage 1 | I.GG.CEMP.15450 | CWMP - JH Finalise draft | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.MP.10.7.16 | Construction Waste Management Plan - Stage 1 | I.GG.CEMP.15460 | CWMP - JH Internal review | 2024-11-05 | 2024-11-11
I2S-7688-MP-74.CM.MP.10.7.16 | Construction Waste Management Plan - Stage 1 | I.GG.CEMP.15470 | CWMP - Consultation with relevant Government agencies (up to 3 weeks) | 2024-12-10 | 2025-01-13
I2S-7688-MP-74.CM.MP.10.7.16 | Construction Waste Management Plan - Stage 1 | I.GG.CEMP.15480 | CWMP - Respond to stakeholder comments | 2025-01-14 | 2025-01-20
I2S-7688-MP-74.CM.MP.10.7.16 | Construction Waste Management Plan - Stage 1 | I.GG.CEMP.15490 | CWMP - Submission to ER for review and endorsement and IRPL Review | 2025-01-21 | 2025-02-18
I2S-7688-MP-74.CM.MP.10.7.16 | Construction Waste Management Plan - Stage 1 | I.GG.CEMP.15530 | CWMP - approved |  | 2025-04-01
Construction Social Impact Management Plan - Stage 1 |  |  |  | 2024-09-30 | 2025-04-01
I2S-7688-MP-74.CM.MP.10.7.17 | Construction Social Impact Management Plan - Stage 1 | I.GG.CEMP.16640 | CSIMP - Resubmission of plan to IRPL for review -
I2S-7688-MP-74.CM.MP.10.7.17 | Construction Social Impact Management Plan - Stage 1 | I.GG.CEMP.15810 | CSIMP - JH Finalise draft | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.MP.10.7.17 | Construction Social Impact Management Plan - Stage 1 | I.GG.CEMP.15820 | CSIMP - JH Internal review | 2024-11-05 | 2024-11-11
I2S-7688-MP-74.CM.MP.10.7.17 | Construction Social Impact Management Plan - Stage 1 | I.GG.CEMP.15830 | CSIMP - Consultation with relevant Government agencies and Stakeholders (up to 3 weeks) | 2024-12-10 | 2025-01-13
I2S-7688-MP-74.CM.MP.10.7.17 | Construction Social Impact Management Plan - Stage 1 | I.GG.CEMP.15850 | CSIMP - Submission to ER for review and endorsement and IRPL Review | 2025-01-21 | 2025-02-18
I2S-7688-MP-74.CM.MP.10.7.17 | Construction Social Impact Management Plan - Stage 1 | I.GG.CEMP.15860 | CSIMP - DPHI Lodgement and DPHI Review (2 weeks/ 14 cd) | 2025-02-19 | 2025-03-04
I2S-7688-MP-74.CM.MP.10.7.17 | Construction Social Impact Management Plan - Stage 1 | I.GG.CEMP.15870 | CSIMP - JH Respond and incorporate to DPHI comments | 2025-03-05 | 2025-03-18
I2S-7688-MP-74.CM.MP.10.7.17 | Construction Social Impact Management Plan - Stage 1 | I.GG.CEMP.15880 | CSIMP -DPHI Completion of Review/Approval (2 weeks/ 14 cd) | 2025-03-19 | 2025-04-01
I2S-7688-MP-74.CM.MP.10.7.17 | Construction Social Impact Management Plan - Stage 1 | I.GG.CEMP.15890 | CSIMP - approved (1 month prior to submission of CEMP) |  | 2025-04-01
I2S-7688-MP-74.CM.MP.10.7.17 | Construction Social Impact Management Plan - Stage 1 | I.GG.CEMP.16210 | CSIMP - Initial submission to IRPL for review (4 weeks/ 28 cd) | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.CM.MP.10.7.17 | Construction Social Impact Management Plan - Stage 1 | I.GG.CEMP.17060 | CSIMP - IRPL Review period
I2S-7688-MP-74.CM.MP.10.7.17 | Construction Social Impact Management Plan - Stage 1 | I.GG.CEMP.17070 | CSIMP - JH to respond to comments
Construction Groundwater Mitigation and Management Plan - Stage 2 |  |  |  | 2024-09-30 | 2025-04-01
I2S-7688-MP-74.CM.MP.10.7.19 | Construction Groundwater Mitigation and Management Plan - Stage 2 | I.GG.CEMP.16860 | CGMMP - Resubmission of plan to IRPL for review
I2S-7688-MP-74.CM.MP.10.7.19 | Construction Groundwater Mitigation and Management Plan - Stage 2 | I.GG.CEMP.16870 | CGMMP - IRPL to review updated documents and Approve
I2S-7688-MP-74.CM.MP.10.7.19 | Construction Groundwater Mitigation and Management Plan - Stage 2 | I.GG.CEMP.15630 | CGMMP - JH Finalise draft | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.MP.10.7.19 | Construction Groundwater Mitigation and Management Plan - Stage 2 | I.GG.CEMP.15640 | CGMMP - JH Internal review | 2024-11-05 | 2024-11-11
I2S-7688-MP-74.CM.MP.10.7.19 | Construction Groundwater Mitigation and Management Plan - Stage 2 | I.GG.CEMP.15710 | CGMMP - approved |  | 2025-04-01
I2S-7688-MP-74.CM.MP.10.7.19 | Construction Groundwater Mitigation and Management Plan - Stage 2 | I.GG.CEMP.16230 | CGMMP - Initial submiission to IRPL for review (4 weeks/ 28 cd) | 2024-11-12 | 2024-12-09
Sustainability and Social Performance Requirements |  |  |  | 2024-09-30 | 2025-01-28
18. Social Delivery Management Plan (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-13
I2S-7688-MP-74.CM.MP.6.18 | 18. Social Delivery Management Plan (20 Bdays) | I.GG.MR.AnF.8-4 | IRPL to review updated documents and Approve - Social Delivery MP | 2024-12-17 | 2025-01-13
I2S-7688-MP-74.CM.MP.6.18 | 18. Social Delivery Management Plan (20 Bdays) | I.GG.MR.AnF.8-1 | Prepare & Submit to IRPL PM / Project Verifier - Social Delivery MP (20 Bdays after Date of Deed) | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.MP.6.18 | 18. Social Delivery Management Plan (20 Bdays) | I.GG.MR.AnF.8-2 | Project Verifier /IRPL Review Period - Social Delivery MP | 2024-11-05 | 2024-12-02
I2S-7688-MP-74.CM.MP.6.18 | 18. Social Delivery Management Plan (20 Bdays) | I.GG.MR.AnF.8-3 | Update Plan to Reflect any Comments - Social Delivery MP | 2024-12-03 | 2024-12-16
18.1 - Local and Indigenous Industry Participation (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-06
I2S-7688-MP-74.CM.MP.6.18.1 | 18.1 - Local and Indigenous Industry Participation (20 Bdays) | I.GG.MR.AnF.7-15 | Prepare & Submit to IRPL PM / Project Verifier - Local & Indigenous Participation (20 Bdays after Date of Deed) | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.MP.6.18.1 | 18.1 - Local and Indigenous Industry Participation (20 Bdays) | I.GG.MR.AnF.7-25 | Project Verifier /IRPL Review Period - Local & Indigenous Participation | 2024-11-05 | 2024-12-02
I2S-7688-MP-74.CM.MP.6.18.1 | 18.1 - Local and Indigenous Industry Participation (20 Bdays) | I.GG.MR.AnF.7-35 | Update Plan to Reflect any Comments - Local & Indigenous Participation | 2024-12-03 | 2024-12-09
I2S-7688-MP-74.CM.MP.6.18.1 | 18.1 - Local and Indigenous Industry Participation (20 Bdays) | I.GG.MR.AnF.7-45 | IRPL to review updated documents and Approve - Local & Indigenous Participation | 2024-12-10 | 2025-01-06
18.2 - Workforce Management (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-13
I2S-7688-MP-74.CM.MP.6.18.2 | 18.2 - Workforce Management (20 Bdays) | I.GG.MR.AnF.10-114 | Update Plan to Reflect any Comments - Workforce MP | 2024-12-03 | 2024-12-16
I2S-7688-MP-74.CM.MP.6.18.2 | 18.2 - Workforce Management (20 Bdays) | I.GG.MR.AnF.10-124 | IRPL to review updated documents and Approve - Workforce MP | 2024-12-17 | 2025-01-13
I2S-7688-MP-74.CM.MP.6.18.2 | 18.2 - Workforce Management (20 Bdays) | I.GG.MR.AnF.10-94 | Prepare & Submit to IRPL PM / Project Verifier - Workforce MP (20 Bdays after Date of Deed) | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.MP.6.18.2 | 18.2 - Workforce Management (20 Bdays) | I.GG.MR.AnF.10-104 | Project Verifier /IRPL Review Period - Workforce MP | 2024-11-05 | 2024-12-02
18.3 - Housing and accommodation (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-13
I2S-7688-MP-74.CM.MP.6.18.3 | 18.3 - Housing and accommodation (20 Bdays) | I.GG.MR.AnF.9-54 | Prepare & Submit to IRPL PM / Project Verifier - Housing and Accommodation (20 Bdays after Date of Deed) | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.MP.6.18.3 | 18.3 - Housing and accommodation (20 Bdays) | I.GG.MR.AnF.9-64 | Project Verifier /IRPL Review Period - Housing and Accommodation | 2024-11-05 | 2024-12-02
I2S-7688-MP-74.CM.MP.6.18.3 | 18.3 - Housing and accommodation (20 Bdays) | I.GG.MR.AnF.9-74 | Update Plan to Reflect any Comments - Housing and Accommodation | 2024-12-03 | 2024-12-16
I2S-7688-MP-74.CM.MP.6.18.3 | 18.3 - Housing and accommodation (20 Bdays) | I.GG.MR.AnF.9-84 | IRPL to review updated documents and Approve - Housing and Accommodation | 2024-12-17 | 2025-01-13
18.4 - Community Health and Wellbeing (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-13
I2S-7688-MP-74.CM.MP.6.18.4 | 18.4 - Community Health and Wellbeing (20 Bdays) | I.GG.MR.AnF.14-18 | Prepare & Submit to IRPL PM / Project Verifier - Community Management Plan (20 Bdays after Date of Deed) | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.MP.6.18.4 | 18.4 - Community Health and Wellbeing (20 Bdays) | I.GG.MR.AnF.14-28 | Project Verifier /IRPL Review Period - Community Health & wellbeing Management Plan | 2024-11-05 | 2024-12-02
I2S-7688-MP-74.CM.MP.6.18.4 | 18.4 - Community Health and Wellbeing (20 Bdays) | I.GG.MR.AnF.14-38 | Update Plan to Reflect any Comments - Community Health & wellbeing Management Plan | 2024-12-03 | 2024-12-16
I2S-7688-MP-74.CM.MP.6.18.4 | 18.4 - Community Health and Wellbeing (20 Bdays) | I.GG.MR.AnF.14-48 | IRPL to review updated documents and Approve - Community Health & wellbeing Management Plan | 2024-12-17 | 2025-01-13
19 - Sustainability Management Plan (30 Bdays) |  |  |  | 2024-09-30 | 2025-01-28
I2S-7688-MP-74.CM.MP.6.19 | 19 - Sustainability Management Plan (30 Bdays) | I.GG.SMP.11154 | Prepare & Submit to IRPL PM / Project Verifier - Sustainability MP (30 Bdays after Date of Deed) | 2024-09-30 | 2024-11-18
I2S-7688-MP-74.CM.MP.6.19 | 19 - Sustainability Management Plan (30 Bdays) | I.GG.SMP.11164 | Project Verifier /IRPL Review Period - Sustainability MP | 2024-11-19 | 2024-12-16
I2S-7688-MP-74.CM.MP.6.19 | 19 - Sustainability Management Plan (30 Bdays) | I.GG.SMP.11174 | Update Plan to Reflect any Comments - Sustainability MP | 2024-12-17 | 2025-01-13
I2S-7688-MP-74.CM.MP.6.19 | 19 - Sustainability Management Plan (30 Bdays) | I.GG.SMP.11194 | IRPL to review updated documents and Approve - Sustainability MP | 2025-01-14 | 2025-01-28
Communication and Stakeholder Engagement Management Requirements |  |  |  | 2024-09-30 | 2025-01-13
20 - Community & Stakeholder Engagement Management Plan (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-13
I2S-7688-MP-74.CM.MP.7.20 | 20 - Community & Stakeholder Engagement Management Plan (20 Bdays) | I.GG.MR.AnF.15-1 | Prepare & Submit to IRPL PM / Project Verifier - Community & Stakeholder Engagement MP (20 Bdays after DoD) | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.MP.7.20 | 20 - Community & Stakeholder Engagement Management Plan (20 Bdays) | I.GG.MR.AnF.15-2 | Project Verifier /IRPL Review Period - Community & Stakeholder Engagement MP | 2024-11-05 | 2024-12-02
I2S-7688-MP-74.CM.MP.7.20 | 20 - Community & Stakeholder Engagement Management Plan (20 Bdays) | I.GG.MR.AnF.15-3 | Update Plan to Reflect any Comments - Community & Stakeholder Engagement MP | 2024-12-03 | 2024-12-16
I2S-7688-MP-74.CM.MP.7.20 | 20 - Community & Stakeholder Engagement Management Plan (20 Bdays) | I.GG.MR.AnF.15-4 | IRPL to review updated documents and Approve - Community & Stakeholder Engagement MP | 2024-12-17 | 2025-01-13
21 - Incident Management Plan (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-06
I2S-7688-MP-74.CM.MP.7.21 | 21 - Incident Management Plan (20 Bdays) | I.GG.MR.AnF.15-14 | Prepare & Submit to IRPL PM / Project Verifier - Incident MP (Not Required) | 2024-09-30 | 2024-10-28
I2S-7688-MP-74.CM.MP.7.21 | 21 - Incident Management Plan (20 Bdays) | I.GG.MR.AnF.15-24 | Project Verifier /IRPL Review Period - Incident MP (Not Required) | 2024-10-29 | 2024-11-25
I2S-7688-MP-74.CM.MP.7.21 | 21 - Incident Management Plan (20 Bdays) | I.GG.MR.AnF.15-34 | Update Plan to Reflect any Comments - Incident MP (Not Required) | 2024-11-26 | 2024-12-09
I2S-7688-MP-74.CM.MP.7.21 | 21 - Incident Management Plan (20 Bdays) | I.GG.MR.AnF.15-44 | IRPL to review updated documents and Approve - Incident MP (Not Required) | 2024-12-10 | 2025-01-06
Industrial Relations Management |  |  |  | 2024-09-30 | 2025-01-13
22 - Industrial Relations Management Plan (20 Bdays) |  |  |  | 2024-09-30 | 2025-01-13
I2S-7688-MP-74.CM.MP.8.22 | 22 - Industrial Relations Management Plan (20 Bdays) | I.GG.MR.AnF.16-1 | Prepare & Submit to IRPL PM / Project Verifier - Industrial Relations MP (20 Bdays after Date of Deed) | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.MP.8.22 | 22 - Industrial Relations Management Plan (20 Bdays) | I.GG.MR.AnF.16-2 | Project Verifier /IRPL Review Period - Industrial Relations MP | 2024-11-05 | 2024-12-02
I2S-7688-MP-74.CM.MP.8.22 | 22 - Industrial Relations Management Plan (20 Bdays) | I.GG.MR.AnF.16-3 | Update Plan to Reflect any Comments - Industrial Relations MP | 2024-12-03 | 2024-12-16
I2S-7688-MP-74.CM.MP.8.22 | 22 - Industrial Relations Management Plan (20 Bdays) | I.GG.MR.AnF.16-4 | IRPL to review updated documents and Approve - Industrial Relations MP | 2024-12-17 | 2025-01-13
Completion and Handover Requirements |  |  |  | 2025-01-14 | 2025-06-06
23 - Completion and Handover Management Plan (60 Bdays) |  |  |  | 2025-01-14 | 2025-06-06
I2S-7688-MP-74.CM.MP.9.23 | 23 - Completion and Handover Management Plan (60 Bdays) | I.GG.MR.AnF.12-1 | Prepare & Submit to IRPL PM / Project Verifier - Completion & Handover MP (60 Bdays after Date of Deed) | 2025-01-14 | 2025-04-08
I2S-7688-MP-74.CM.MP.9.23 | 23 - Completion and Handover Management Plan (60 Bdays) | I.GG.MR.AnF.12-2 | Project Verifier /IRPL Review Period - Completion & Handover MP | 2025-04-09 | 2025-05-09
I2S-7688-MP-74.CM.MP.9.23 | 23 - Completion and Handover Management Plan (60 Bdays) | I.GG.MR.AnF.12-3 | Update Plan to Reflect any Comments - Completion & Handover MP | 2025-05-12 | 2025-05-23
I2S-7688-MP-74.CM.MP.9.23 | 23 - Completion and Handover Management Plan (60 Bdays) | I.GG.MR.AnF.12-4 | IRPL to review updated documents and Approve - Completion & Handover MP | 2025-05-26 | 2025-06-06
Country Rail Network / Inland Rail Interface
24 - Country Rail Network / Inland Rail Interface (60 Bdays)
I2S-7688-MP-74.CM.MP.11.23 | 24 - Country Rail Network / Inland Rail Interface (60 Bdays) | I.GG.MR.AnF.12-14 | Prepare & Submit to IRPL PM / Project Verifier - Country Rail Network / Inland Rail Interf (60 Bdays after Date of Deed)
I2S-7688-MP-74.CM.MP.11.23 | 24 - Country Rail Network / Inland Rail Interface (60 Bdays) | I.GG.MR.AnF.12-24 | Project Verifier /IRPL Review Period - Country Rail Network / Inland Rail Interface MP
I2S-7688-MP-74.CM.MP.11.23 | 24 - Country Rail Network / Inland Rail Interface (60 Bdays) | I.GG.MR.AnF.12-34 | Update Plan to Reflect any Comments - Country Rail Network / Inland Rail Interface MP
I2S-7688-MP-74.CM.MP.11.23 | 24 - Country Rail Network / Inland Rail Interface (60 Bdays) | I.GG.MR.AnF.12-44 | Country Rail Network / Inland Rail Interface MP - IRPL to review updated documents and Approve
15.11 - Visual Awarness and Landscape Mitigation Management Plan - E137 |  |  |  | 2024-11-12 | 2025-03-04
I2S-7688-MP-74.CM.MP.12 | 15.11 - Visual Awarness and Landscape Mitigation Management Plan - E137 | I.GG.MR.AnF.5-824 | Project Verifier /IRPL Review Period - Visual Awareness and Landscape MP - CoA E126 | 2025-01-07 | 2025-02-04
I2S-7688-MP-74.CM.MP.12 | 15.11 - Visual Awarness and Landscape Mitigation Management Plan - E137 | I.GG.MR.AnF.5-834 | Visual Awareness and Landscape MP - CoA E126 - Update Plan to Reflect any Comments | 2025-02-05 | 2025-02-18
I2S-7688-MP-74.CM.MP.12 | 15.11 - Visual Awarness and Landscape Mitigation Management Plan - E137 | I.GG.MR.AnF.5-844 | Visual Awareness and Landscape MP - CoA E126 - IRPL to review updated documents and Approve | 2025-02-19 | 2025-03-04
I2S-7688-MP-74.CM.MP.12 | 15.11 - Visual Awarness and Landscape Mitigation Management Plan - E137 | I.GG.MR.AnF.5-904 | Prepare & Submit to IRPL PM / Project Verifier - Visual Awareness and Landscape MP - CoA E126 | 2024-11-12 | 2025-01-06
Aboriginal Cultural Value Plan |  |  |  | 2025-04-08 | 2025-05-22
I2S-7688-MP-74.CM.11 | Aboriginal Cultural Value Plan | I.GG.CEMP.16290 | ACVP - Aboriginal Cultural Heritage Assessment Report approved |  | 2025-05-22
I2S-7688-MP-74.CM.11 | Aboriginal Cultural Value Plan | I.GG.CEMP.15980 | ACVP - Aboriginal Cultural Heritage Plan approved |  | 2025-05-22
I2S-7688-MP-74.CM.11 | Aboriginal Cultural Value Plan | I.GG.CEMP.16460 | ACVP - Prepare Draft of CVA methodology by JHL
I2S-7688-MP-74.CM.11 | Aboriginal Cultural Value Plan | I.GG.CEMP.16480 | ACVP - Undertake interviews and develop consultation strategy
I2S-7688-MP-74.CM.11 | Aboriginal Cultural Value Plan | I.GG.CEMP.16490 | ACVP - Complete Engagement Strategy and Assessment Report
I2S-7688-MP-74.CM.11 | Aboriginal Cultural Value Plan | I.GG.CEMP.16500 | ACVP -Submit Strategy and Assessment Report to IRPL
I2S-7688-MP-74.CM.11 | Aboriginal Cultural Value Plan | I.GG.CEMP.16510 | ACVP - IRPL Review period
I2S-7688-MP-74.CM.11 | Aboriginal Cultural Value Plan | I.GG.CEMP.16530 | ACVP - Submit Cultural Value Report to the Knowledge Keepers for review and finalisation
I2S-7688-MP-74.CM.11 | Aboriginal Cultural Value Plan | I.GG.CEMP.16540 | ACVP - Update Comments from IRPL
I2S-7688-MP-74.CM.11 | Aboriginal Cultural Value Plan | I.GG.CEMP.16550 | ACVP - Knowledge Keeper Review Period
I2S-7688-MP-74.CM.11 | Aboriginal Cultural Value Plan | I.GG.CEMP.16560 | ACVP - Submit to DPHI for Review (I month prior to Construction)
I2S-7688-MP-74.CM.11 | Aboriginal Cultural Value Plan | I.GG.CEMP.16570 | ACVP - JH Final Submission to DPHI for Approval
I2S-7688-MP-74.CM.11 | Aboriginal Cultural Value Plan | I.GG.CEMP.15960 | ACVP - JH Respond and incorporate to DPHI comments | 2025-04-24 | 2025-05-08
I2S-7688-MP-74.CM.11 | Aboriginal Cultural Value Plan | I.GG.CEMP.15970 | ACVP - DPHI Completion of Review/Approval (2 weeks/ 14 cd) | 2025-05-09 | 2025-05-22
I2S-7688-MP-74.CM.11 | Aboriginal Cultural Value Plan | I.GG.CEMP.17320 | ACVP - A9 - JHG Prepare A9 Draft letter (Extension of 30 days past Construction Commencement)
I2S-7688-MP-74.CM.11 | Aboriginal Cultural Value Plan | I.GG.CEMP.17330 | ACVP - A9 - Submit A9 Letter to Inland Rail for review / Approval
I2S-7688-MP-74.CM.11 | Aboriginal Cultural Value Plan | I.GG.CEMP.17340 | ACVP - A9 - Submit A9 Letter to DPHI for review / Approval
I2S-7688-MP-74.CM.11 | Aboriginal Cultural Value Plan | I.GG.CEMP.16580 | ACVP - Knowledge Keepers Review Period
I2S-7688-MP-74.CM.11 | Aboriginal Cultural Value Plan | I.GG.CEMP.15950 | ACVP - DPHI Lodgement and DPHI Review (2 weeks/ 14 cd) | 2025-04-08 | 2025-04-23
Aboriginal Heritage Consultation Process (AHCP) |  |  |  | 2024-09-30 | 2024-11-19
Stage 1 - Notification of Project Proposal and registration of interest |  |  |  | 2024-09-30 | 2024-11-19
(New WBS) |  |  |  | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.CM.12.2.1 | (New WBS) | I.GG.MR.AnF.15-54 | AHCP - S1 - Specialist Contractor onboard and mobilised | 2024-09-30 | 2024-09-30
I2S-7688-MP-74.CM.12.2.1 | (New WBS) | I.GG.MR.AnF.15-64 | AHCP - S1 - Notification of the project to the Aboriginal individuals and Organisations via letter,email,phone(28cd) | 2024-10-08 | 2024-11-04
I2S-7688-MP-74.CM.12.2.1 | (New WBS) | I.GG.MR.AnF.15-584 | AHCP - S1 - Request to agencies for list of Aboriginal individuals and groups interested in the Project area | 2024-10-01 | 2024-10-01
(New WBS)-1 |  |  |  | 2024-10-02 | 2024-11-19
I2S-7688-MP-74.CM.12.2.2 | (New WBS)-1 | I.GG.MR.AnF.15-274 | AHCP - S1 - Aboriginal people - 14 days post notice published to register an interest.(Same as I.GG.MR.AnF.15-6) | 2024-11-05 | 2024-11-18
I2S-7688-MP-74.CM.12.2.2 | (New WBS)-1 | I.GG.MR.AnF.15-294 | AHCP - S1 - Proponent records names of Aboriginal people who have registered an interest in consulation (RAP) | 2024-11-06 | 2024-11-19
I2S-7688-MP-74.CM.12.2.2 | (New WBS)-1 | I.GG.MR.AnF.15-334 | AHCP - S1 - Proponent writes to the Aboriginal people - names provided by organisations (Same as I.GG.MR.AnF.15-64) | 2024-10-08 | 2024-10-14
I2S-7688-MP-74.CM.12.2.2 | (New WBS)-1 | I.GG.MR.AnF.15-74 | AHCP - S1 - Notification in the local newspaper as per Heritage NSW requirements (min 10cd) | 2024-10-15 | 2024-11-12
I2S-7688-MP-74.CM.12.2.2 | (New WBS)-1 | I.GG.MR.AnF.15-254 | AHCP - S1 - Proponents must compile a list of Aboriginal people interested in the proposed project area | 2024-10-02 | 2024-10-04
Stage 2 - Consultation & Finalization of Methodolgy
I2S-7688-MP-74.CM.12.1 | Stage 2 - Consultation & Finalization of Methodolgy | I.GG.MR.AnF.15-914 | AHCP - S2 - Submit Survey and excavation methodologies 1 month prior to commencement of works to DPHI
I2S-7688-MP-74.CM.12.1 | Stage 2 - Consultation & Finalization of Methodolgy | I.GG.MR.AnF.15-634 | AHCP - S2 - Submit updated excavation and survey methodologies for IRPL endorsement
I2S-7688-MP-74.CM.12.1 | Stage 2 - Consultation & Finalization of Methodolgy | I.GG.MR.AnF.15-644 | AHCP - S2 - Submit out methodologies to the RAPs
I2S-7688-MP-74.CM.12.1 | Stage 2 - Consultation & Finalization of Methodolgy | I.GG.MR.AnF.15-654 | AHCP - S2 - Submit to Heritage NSW
I2S-7688-MP-74.CM.12.1 | Stage 2 - Consultation & Finalization of Methodolgy | I.GG.MR.AnF.15-874 | AHCP - S2 - RAP Review Period
I2S-7688-MP-74.CM.12.1 | Stage 2 - Consultation & Finalization of Methodolgy | I.GG.MR.AnF.15-884 | AHCP - S2 - Heritage Review Period
Stage 3 - Survey, Excavation and Surface Collection
I2S-7688-MP-74.CM.12.3 | Stage 3 - Survey, Excavation and Surface Collection | I.GG.MR.AnF.15-664 | AHCP - S3 - Commencement of surveys, excavations and surface collection onsite (Zones 5,6,9 & 10)
I2S-7688-MP-74.CM.12.3 | Stage 3 - Survey, Excavation and Surface Collection | I.GG.MR.AnF.15-674 | AHCP - S3 - Quantify the findings of the excavations and prepare the salvage methodology
I2S-7688-MP-74.CM.12.3 | Stage 3 - Survey, Excavation and Surface Collection | I.GG.MR.AnF.15-894 | AHCP - S3 - Back Filling of Trenching
I2S-7688-MP-74.CM.12.3 | Stage 3 - Survey, Excavation and Surface Collection | I.GG.MR.AnF.15-934 | AHCP - S3 - If no findings (Zones 5,6,9 & 10) - Confirm Zones are Cleared by RAP's
I2S-7688-MP-74.CM.12.3 | Stage 3 - Survey, Excavation and Surface Collection | I.GG.MR.AnF.15-944 | AHCP - S3 - RAP Approval (if nothing found) zones 5, 6, 9 & 10
I2S-7688-MP-74.CM.12.3 | Stage 3 - Survey, Excavation and Surface Collection | I.GG.MR.AnF.15-964 | AHCP - S3 - Surface Collection Zones 3, 4, 7, 8, 11e
I2S-7688-MP-74.CM.12.3 | Stage 3 - Survey, Excavation and Surface Collection | I.GG.MR.AnF.15-974 | AHCP - S3 - Approval for Zones 3, 4, 7, 8 & 11e
Stage 4 - Reporting & Preperation of Salvage Methodolgy
I2S-7688-MP-74.CM.12.4 | Stage 4 - Reporting & Preperation of Salvage Methodolgy | I.GG.MR.AnF.15-784 | AHCP - S4 - Provide & Submit Salvage methodology to IRPL
I2S-7688-MP-74.CM.12.4 | Stage 4 - Reporting & Preperation of Salvage Methodolgy | I.GG.MR.AnF.15-794 | AHCP - S4 - IRPL Final Review Period
I2S-7688-MP-74.CM.12.4 | Stage 4 - Reporting & Preperation of Salvage Methodolgy | I.GG.MR.AnF.15-804 | AHCP - S4 - RAPS Review Period
I2S-7688-MP-74.CM.12.4 | Stage 4 - Reporting & Preperation of Salvage Methodolgy | I.GG.MR.AnF.15-814 | AHCP - S4 - Heritage NSW Review Period
I2S-7688-MP-74.CM.12.4 | Stage 4 - Reporting & Preperation of Salvage Methodolgy | I.GG.MR.AnF.15-824 | AHCP - S4 - Updates & Comments for RAPs
I2S-7688-MP-74.CM.12.4 | Stage 4 - Reporting & Preperation of Salvage Methodolgy | I.GG.MR.AnF.15-904 | AHCP - S4 - Submission of Methodology to DPHI 1 month prior to commencement of Salvage
I2S-7688-MP-74.CM.12.4 | Stage 4 - Reporting & Preperation of Salvage Methodolgy | I.GG.MR.AnF.15-684 | AHCP - S4 - IRPL Review Period (Should be pushed for 5 days only, IRPL is involved in the process)
I2S-7688-MP-74.CM.12.4 | Stage 4 - Reporting & Preperation of Salvage Methodolgy | I.GG.MR.AnF.15-694 | AHCP - S4 - Update Comments and resubmission to IRPL
I2S-7688-MP-74.CM.12.4 | Stage 4 - Reporting & Preperation of Salvage Methodolgy | I.GG.MR.AnF.15-714 | AHCP - S4 - Submit Salvage methodology to Heritage NSW 1 month prior to commencement of salvage
I2S-7688-MP-74.CM.12.4 | Stage 4 - Reporting & Preperation of Salvage Methodolgy | I.GG.MR.AnF.15-704 | AHCP - S4 - Submit findings and salvage methodology for the RAPS Review
Stage 5 - Completion of Salvage
I2S-7688-MP-74.CM.12.5 | Stage 5 - Completion of Salvage | I.GG.MR.AnF.15-724 | AHCP - S5 - Attend site and complete salvage in relevant zones (5, 6, 9 & 10)
I2S-7688-MP-74.CM.12.5 | Stage 5 - Completion of Salvage | I.GG.MR.AnF.15-1004 | AHCP - S5 - Attend site and complete salvage in relevant zones (1,2)
Stage 6 - Completion of Consultation & Reporting of Site Investigation
I2S-7688-MP-74.CM.12.6 | Stage 6 - Completion of Consultation & Reporting of Site Investigation | I.GG.MR.AnF.15-924 | AHCP - S6 - Submission of report to DPHI within 24 months of all excavations and salvage
I2S-7688-MP-74.CM.12.6 | Stage 6 - Completion of Consultation & Reporting of Site Investigation | I.GG.MR.AnF.15-734 | AHCP - S6 - Submit Final Report to IRPL for review and complete submission of ASRIF to AHIMS
I2S-7688-MP-74.CM.12.6 | Stage 6 - Completion of Consultation & Reporting of Site Investigation | I.GG.MR.AnF.15-744 | AHCP - S6 - Update Reports based on comments
I2S-7688-MP-74.CM.12.6 | Stage 6 - Completion of Consultation & Reporting of Site Investigation | I.GG.MR.AnF.15-754 | AHCP - S6 - Submit Report to RAPs for Final review
I2S-7688-MP-74.CM.12.6 | Stage 6 - Completion of Consultation & Reporting of Site Investigation | I.GG.MR.AnF.15-774 | AHCP - S6 - Submit to Heritage NSW for Final Review
I2S-7688-MP-74.CM.12.6 | Stage 6 - Completion of Consultation & Reporting of Site Investigation | I.GG.MR.AnF.15-834 | AHCP - S6 - IRPL Review Period
I2S-7688-MP-74.CM.12.6 | Stage 6 - Completion of Consultation & Reporting of Site Investigation | I.GG.MR.AnF.15-844 | AHCP - S6 - RAPs Final Review Period
I2S-7688-MP-74.CM.12.6 | Stage 6 - Completion of Consultation & Reporting of Site Investigation | I.GG.MR.AnF.15-854 | AHCP - S6 - Heritage NSW for final review
I2S-7688-MP-74.CM.12.6 | Stage 6 - Completion of Consultation & Reporting of Site Investigation | I.GG.MR.AnF.15-984 | AHCP - S6 - Approval for Zones 1 & 2
I2S-7688-MP-74.CM.12.6 | Stage 6 - Completion of Consultation & Reporting of Site Investigation | I.GG.MR.AnF.15-994 | AHCP - S6 - Approval for Zones 5, 6, 9 & 10 (if items found)
I2S-7688-MP-74.CM.12.6 | Stage 6 - Completion of Consultation & Reporting of Site Investigation | I.GG.MR.AnF.15-1014 | AHCP - S6 - Prepare Draft Report of ASRIF
Low Impact Works (LIW) and Survey |  |  |  | 2024-11-27 | 2025-01-15
Low Impact Works - Monitoring (CMPs) |  |  |  | 2024-11-27 | 2025-01-15
I2S-7688-MP-74.CM.LIW.2 | Low Impact Works - Monitoring (CMPs) | I.GG.16370 | Low impact Works (post LIW Approval) - CAT B Utility Site Investigation
I2S-7688-MP-74.CM.LIW.2 | Low Impact Works - Monitoring (CMPs) | I.GG.16380 | Low impact Works (post LIW Approval) - Overhead Utility Site Investigation
I2S-7688-MP-74.CM.LIW.2 | Low Impact Works - Monitoring (CMPs) | I.GG.15230 | Low impact Works (post LIW Approval) - Site survey/ test pits (was in Sept 24 Possession /Survey Tie - ins) | 2024-11-27 | 2024-12-04
I2S-7688-MP-74.CM.LIW.2 | Low Impact Works - Monitoring (CMPs) | I.GG.15250 | Low impact Works (post LIW Approval) - Signalling correlation | 2024-11-27 | 2024-12-03
I2S-7688-MP-74.CM.LIW.2 | Low Impact Works - Monitoring (CMPs) | I.GG.15260 | Low impact Works (post LIW Approval) - Site investigations in existing corridor (Survey / Boreholes / ETV) | 2024-11-27 | 2025-01-14
I2S-7688-MP-74.CM.LIW.2 | Low Impact Works - Monitoring (CMPs) | I.GG.15470 | Low impact Works (post LIW Approval) - First Survey Data back | 2024-12-04 | 2024-12-04
I2S-7688-MP-74.CM.LIW.2 | Low Impact Works - Monitoring (CMPs) | I.GG.15640 | Low impact Works (post LIW Approval) - Early Access required for Site investigations | 2024-11-27
I2S-7688-MP-74.CM.LIW.2 | Low Impact Works - Monitoring (CMPs) | I.GG.15730 | Low impact Works (post LIW Approval) - All Survey Data back | 2025-01-15 | 2025-01-15
I2S-7688-MP-74.CM.LIW.2 | Low Impact Works - Monitoring (CMPs) | I.GG.15510 | Low impact Works (post LIW Approval) - Site walk over and analysis | 2024-11-27 | 2024-12-03
I2S-7688-MP-74.CM.LIW.2 | Low Impact Works - Monitoring (CMPs) | I.GG.16415 | Low impact Works (post LIW Approval) - CAT C Site Investigation - zone 7 (22,240 - 24,350)
I2S-7688-MP-74.CM.LIW.2 | Low Impact Works - Monitoring (CMPs) | I.GG.16440 | Low impact Works (post LIW Approval) - CAT C Site Investigation - Z2 (7665 - 8400) - CEMP aprvl received, not reqd
I2S-7688-MP-74.CM.LIW.2 | Low Impact Works - Monitoring (CMPs) | I.GG.16450 | Low impact Works (post LIW Approval) - CAT C Site Investigation - zone 3 (11,300 - 11,445)
I2S-7688-MP-74.CM.LIW.2 | Low Impact Works - Monitoring (CMPs) | I.GG.16460 | Low impact Works (post LIW Approval) - CAT C Site Investigation - zone 4 (12,190 - 14,275)
I2S-7688-MP-74.CM.LIW.2 | Low Impact Works - Monitoring (CMPs) | I.GG.16470 | Low impact Works (post LIW Approval) - CAT C Site Investigation - zone 1 (430 - 1347) - CEMP aprvl received, not reqd
I2S-7688-MP-74.CM.LIW.2 | Low Impact Works - Monitoring (CMPs) | I.GG.16480 | Low impact Works (post LIW Approval) - CAT C Site Investigation - zone 8 (25,590 - 26,890)
I2S-7688-MP-74.CM.LIW.2 | Low Impact Works - Monitoring (CMPs) | I.GG.16490 | Low impact Works (post LIW Approval) - CAT C Site Investigation -zone 11e (37,700 - 38,170)
I2S-7688-MP-74.CM.LIW.2 | Low Impact Works - Monitoring (CMPs) | I.GG.16500 | Low impact Works (post LIW Approval) - CAT C (Heritage) Site Investigation- zone 5 (14,235 - 18,530)
I2S-7688-MP-74.CM.LIW.2 | Low Impact Works - Monitoring (CMPs) | I.GG.16510 | Low impact Works (post LIW Approval) - CAT C Site Investigation - zone 6 (18,440 - 21,000)
I2S-7688-MP-74.CM.LIW.2 | Low Impact Works - Monitoring (CMPs) | I.GG.16520 | Low impact Works (post LIW Approval) - CAT C Site Inestigation - zone 9 (33,760 - 35,040)
I2S-7688-MP-74.CM.LIW.2 | Low Impact Works - Monitoring (CMPs) | I.GG.16530 | Low impact Works (post LIW Approval) - CAT C Site Investigation - zone 10 (35,900 - 36,500)
Works Authorisation Deed (WAD) Process |  |  |  | 2024-09-30 | 2026-11-19
Major WAD |  |  |  | 2024-09-30 | 2026-11-19
Burley Griffin Way Returned Works |  |  |  | 2024-09-30 | 2026-11-19
1 - Reference Design Review |  |  |  | 2024-09-30 | 2025-02-17
IRPL /JH |  |  |  | 2024-09-30 | 2024-11-11
I2S-7688-MP-74.CM.W.1.8.1.1 | IRPL /JH | I.GG.MR.AnF.5-1134 | WAD - Major - BGW - TIA (Traffic Impact Assessment) | 2024-09-30 | 2024-10-21
I2S-7688-MP-74.CM.W.1.8.1.1 | IRPL /JH | I.GG.MR.AnF.5-1144 | WAD - Major - BGW - Traffic management risk workshop | 2024-10-22 | 2024-11-11
I2S-7688-MP-74.CM.W.1.8.1.1 | IRPL /JH | I.GG.MR.AnF.5-1154 | WAD - Major - BGW - Request Copy of G10 Traffic Management document | 2024-09-30 | 2024-10-04
I2S-7688-MP-74.CM.W.1.8.1.1 | IRPL /JH | I.GG.WAD.1000 | WAD - Major - BGW - IRPL requests Planning Approval with DPE | 2024-09-30 | 2024-10-14
I2S-7688-MP-74.CM.W.1.8.1.1 | IRPL /JH | I.GG.WAD.1010 | WAD - Major - BGW - IRPL provides presentation on scope of Inland Rail Project | 2024-10-15 | 2024-10-28
I2S-7688-MP-74.CM.W.1.8.1.1 | IRPL /JH | I.GG.WAD.1020 | WAD - Major - BGW - IRPL initiates Roads Act 1993 Works & Structures application - TfNSW Develop Services | 2024-10-29 | 2024-11-11
TfNSW |  |  |  | 2025-01-06 | 2025-02-17
I2S-7688-MP-74.CM.W.1.8.1.2 | TfNSW | I.GG.WAD.1030 | WAD - Major - BGW - TfNSW Strategic Design Development | 2025-01-06 | 2025-02-03
I2S-7688-MP-74.CM.W.1.8.1.2 | TfNSW | I.GG.WAD.1040 | WAD - Major - BGW - TfNSW Strategic Design Review and Acceptance | 2025-02-04 | 2025-02-17
I2S-7688-MP-74.CM.W.1.8.1.2 | TfNSW | I.GG.WAD.2410 | WAD - Major - BGW - IRPL attend IRG (14th of May)
2 - WAD Administration |  |  |  | 2025-02-18 | 2025-03-24
TfNSW |  |  |  | 2025-02-18 | 2025-03-24
I2S-7688-MP-74.CM.W.1.8.2.2 | TfNSW | I.GG.WAD.1050 | WAD - Major - BGW - TfNSW WAD Administration | 2025-02-18 | 2025-03-24
3 - Design Review |  |  |  | 2025-07-30 | 2025-09-01
IRPL /JH |  |  |  | 2025-08-06 | 2025-08-06
I2S-7688-MP-74.CM.W.1.8.3.1 | IRPL /JH | I.GG.WAD.1080 | WAD - Major - BGW - Hold Point - IRPL obtained planning Approval, satisfied relevant conditions and completed TTAP |  | 2025-08-06
TfNSW |  |  |  | 2025-07-30 | 2025-09-01
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.1400 | WAD - Major - BGW - IV workshop (JH/IRPL/IV)
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.1410 | WAD - Major - BGW - IV / TfNSW workshop (JH/IRPL/IV/TfNSW)
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.1420 | WAD - Major - M3 - BGW - ARR 4.1 updates - submission to IRPL/TfNSW/IV - Milestone
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.2590 | WAD - Major - M3 - BGW - TfNSW Review and approve #6 & #7 (2-weeks)
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.1370 | WAD - Major - BGW - Develop Detailed Design (stage 2) - based on ARR 4.1
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.2170 | WAD - Major - M3 - BGW - ARR 4.1 - Design to IFC
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.1070 | WAD - Major - M3 - BGW - Stage 2 - DDD - ARR 4.1 - Detailed Design Acceptance - Milestone |  | 2025-08-06
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.1090 | WAD - Major - BGW - TfNSW signs WAD | 2025-08-07
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.1100 | WAD - Major - M3 - BGW - ARR 4.1 - TfNSW Project Officer sends IRPL/ARTC Detailed Design Acceptance letter | 2025-08-19 | 2025-09-01
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.1350 | WAD - Major - BGW - Develop and submit Concept Design and Project Mgmt Plans (stage 1)
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.1360 | WAD - Major - BGW - Concept Design Review and Approve - Stage 1 (PDD) - review #1
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.1380 | WAD - Major - BGW - JH review comments and issue update
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.1390 | WAD - Major - BGW - Concept Design Review - Stage 1 (PDD) - review #2
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.2640 | WAD - Major - BGW - Submit concessions to TfNSW
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.2650 | WAD - Major - BGW - TfNSW - review and approve - geotech concessions (Tier 5 - SME aprvl) - ARR 4.1 - acceptance
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.2770 | WAD - Major - M3 - BGW - TfNSW Review and approve #8 (3-weeks) - Tier 3 - SME approval
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.2760 | WAD - Major - BGW - Update Detail Design (stage 1) - submit deviations 6 (AEP) + 7 (Tie in) + 8 (ARR 4.1+4.2)
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.2790 | WAD - Major - M3 - BGW - Stage 2 - submission to IRPL/TfNSW/IV - ARR 4.2 changed to ARR 4.1
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.3000 | WAD - Major - BGW - DDD - Stage 2 - HP - 1 - Traffic & Construction Staging Report - Issued to TfNSW
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.3010 | WAD - Major - BGW - DDD - Stage 2 - HP - 2 - AGS Data - Issued to TfNSW
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.3020 | WAD - Major - BGW - DDD - Stage 2 - HP - 3 - Asbestos Management procedure - Issued to TfNSW
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.3030 | WAD - Major - BGW - DDD - Stage 2 - HP - 4 - Acid Sulphate Soil MP - Issued to TfNSW
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.2820 | WAD - Major - M3 - BGW - Stage 2 - ARR 4.1 - Comments close out workshops and submit update to TfNSW
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.2830 | WAD - Major - M3 - BGW - Stage 2 - ARR 4.1 - Independant Verification (IV)
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.2850 | WAD - Major - M3 - BGW - Stage 2 - ARR 4.1 - Update Detailed Design - comments close out
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.2860 | WAD - Major - M3 - BGW - Stage 2 - DDD - ARR 4.1 - TfNSW review
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.2870 | WAD - Major - M3 - BGW - Stage 2 - DDD - ARR 4.1 - TfNSW/IV - design approval
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.2660 | WAD - Major - BGW - TfNSW review and approve - (Tier 4 - SME aprvl) - hydrology concessions - ARR 4.1 - rejected
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.3110 | WAD - Major - M3 - BGW - Stage 2 - ARR 4.2 changed to ARR 4.1 - collate additional details for TfNSW
I2S-7688-MP-74.CM.W.1.8.3.2 | TfNSW | I.GG.WAD.3170 | WAD - Major - M3 - BGW - Stage 2 - ARR 4.1 - TfNSW Review
4 - Pre-Construction |  |  |  | 2025-09-17 | 2025-10-01
IRPL /JH |  |  |  | 2025-09-17 | 2025-10-01
I2S-7688-MP-74.CM.W.1.8.4.1 | IRPL /JH | I.GG.WAD.3040 | WAD - Major - M3 - BGW - WAD Cl 12.3(f) - re-submission of Prescribed plans post comments close out to Project Verifier
I2S-7688-MP-74.CM.W.1.8.4.1 | IRPL /JH | I.GG.WAD.1460 | WAD - Major - M3 - BGW - WAD Cl 12.3(e) - Provide Proof Engineer certificate for Stage 2 Design - pending workshops
I2S-7688-MP-74.CM.W.1.8.4.1 | IRPL /JH | I.GG.WAD.1470 | WAD - Major - M3 - BGW - WAD Cl 12.3(f) - Provide Prescribed Plans to TfNSW
I2S-7688-MP-74.CM.W.1.8.4.1 | IRPL /JH | I.GG.WAD.1480 | WAD - Major - BGW - WAD Cl 12.3 (g) - Provide WHS Management Plan to IRPL + TfNSW
I2S-7688-MP-74.CM.W.1.8.4.1 | IRPL /JH | I.GG.WAD.1490 | WAD - Major - M3 - BGW - TfNSW issues Approval to Commence Construction letter
I2S-7688-MP-74.CM.W.1.8.4.1 | IRPL /JH | I.GG.WAD.1500 | WAD - Major - M3 - BGW - Issue all Cl 12.3 Documentation for Information
I2S-7688-MP-74.CM.W.1.8.4.1 | IRPL /JH | I.GG.WAD.1180 | WAD - Major - M3 - BGW - WAD Cl 12.3 (h) - Provide written notice of intent to commence construction (10 days prior) | 2025-09-17 | 2025-09-17
I2S-7688-MP-74.CM.W.1.8.4.1 | IRPL /JH | I.GG.WAD.1190 | WAD - Major - M3 - BGW - Organise pre-start up meeting (on site) | 2025-09-18 | 2025-10-01
I2S-7688-MP-74.CM.W.1.8.4.1 | IRPL /JH | I.GG.WAD.1430 | WAD - Major - M3 - BGW - WAD Cl 12.3(a) - Provide insurances - start
I2S-7688-MP-74.CM.W.1.8.4.1 | IRPL /JH | I.GG.WAD.1440 | WAD - Major - BGW - WAD Cl 12.3(b) - obtain Statutory Approvals and provide from IRPL + TfNSW - PDD
I2S-7688-MP-74.CM.W.1.8.4.1 | IRPL /JH | I.GG.WAD.1450 | WAD - Major - M3 - BGW - WAD Cl 12.3(c) - Provide Project Verifier certificate for Stage 2 Design
I2S-7688-MP-74.CM.W.1.8.4.1 | IRPL /JH | I.GG.WAD.2890 | WAD - Major - M3 - BGW - Road Occupancy Licence - ROL - TfNSW
I2S-7688-MP-74.CM.W.1.8.4.1 | IRPL /JH | I.GG.WAD.2670 | WAD - Major - M3 - BGW - WAD Cl 12.3(f) - prescribed plans by Project Verifier - comments closed - Stage 1
I2S-7688-MP-74.CM.W.1.8.4.1 | IRPL /JH | I.GG.WAD.2680 | WAD - Major - BGW - WAD Cl 12.3(f) - Project Verifier review period - Stage 1
I2S-7688-MP-74.CM.W.1.8.4.1 | IRPL /JH | I.GG.WAD.3050 | WAD - Major - M3 - BGW - WAD Cl 12.3(f) - Certification of prescirbed plans by Project Verifier - 3/10
I2S-7688-MP-74.CM.W.1.8.4.1 | IRPL /JH | I.GG.WAD.3090 | WAD - Major - M3 - BGW - WAD Cl 12.3(a) - Provide insurances - finish
I2S-7688-MP-74.CM.W.1.8.4.1 | IRPL /JH | I.GG.WAD.3130 | WAD - Major - M3 - BGW - WAD Cl 12.3(f) - Prescribed Plans to TfNSW - review
5 - Construction |  |  |  | 2026-04-28 | 2026-11-10
IRPL /JH |  |  |  | 2026-04-28 | 2026-11-03
I2S-7688-MP-74.CM.W.1.8.5.1 | IRPL /JH | I.GG.WAD.1250 | WAD - Major - M3 - BGW - Organise RSA 4 | 2026-06-24 | 2026-07-07
I2S-7688-MP-74.CM.W.1.8.5.1 | IRPL /JH | I.GG.WAD.1260 | WAD - Major - M3 - BGW - Formally requests PC | 2026-09-22 | 2026-09-28
I2S-7688-MP-74.CM.W.1.8.5.1 | IRPL /JH | I.GG.WAD.1280 | WAD - Major - M3 - BGW - Practical Completion PC achieved |  | 2026-11-03
I2S-7688-MP-74.CM.W.1.8.5.1 | IRPL /JH | I.GG.WAD.1300 | WAD - Major - M3 - BGW - Rectifiy items on list and provides written notice when complete | 2026-10-21 | 2026-11-03
I2S-7688-MP-74.CM.W.1.8.5.1 | IRPL /JH | I.GG.WAD.1210 | WAD - Major - M3 - BGW - Send any QA documents to IPV ( for major WADs) or Project Officer (for minor WADs) | 2026-04-28 | 2026-05-11
I2S-7688-MP-74.CM.W.1.8.5.1 | IRPL /JH | I.GG.WAD.1230 | WAD - Major - M3 - BGW - Advice Project Officer of anticpated date of Practical Completion (20 B.days prior to PC) | 2026-05-26 | 2026-06-09
TfNSW |  |  |  | 2026-05-12 | 2026-11-10
I2S-7688-MP-74.CM.W.1.8.5.2 | TfNSW | I.GG.WAD.1220 | WAD - Major - M3 - BGW - TfNSW - reviews documents for Acceptance. Documents Accepted | 2026-05-12 | 2026-05-25
I2S-7688-MP-74.CM.W.1.8.5.2 | TfNSW | I.GG.WAD.1240 | WAD - Major - M3 - BGW - TfNSW - Project Officer send Notice of Anticipated Date of Completion letter to ARTC | 2026-06-10 | 2026-06-23
I2S-7688-MP-74.CM.W.1.8.5.2 | TfNSW | I.GG.WAD.1270 | WAD - Major - M3 - BGW - TfNSW - Project Officer organises joint inspection of the works | 2026-09-29 | 2026-10-13
I2S-7688-MP-74.CM.W.1.8.5.2 | TfNSW | I.GG.WAD.1290 | WAD - Major - M3 - BGW - TfNSW - Project Officer issues a notice containing list of items necessary to achieve PC | 2026-10-28 | 2026-11-03
I2S-7688-MP-74.CM.W.1.8.5.2 | TfNSW | I.GG.WAD.1310 | WAD - Major - M3 - BGW - TfNSW - Project Officer issues Notice of Practical Completion letter | 2026-11-04 | 2026-11-10
6 - Post Construction |  |  |  | 2026-11-11 | 2026-11-11
IRPL /JH |  |  |  | 2026-11-11 | 2026-11-11
I2S-7688-MP-74.CM.W.1.8.6.1 | IRPL /JH | I.GG.WAD.1320 | WAD - Major - M3 - BGW - IRPL hands over works to TfNSW | 2026-11-11 | 2026-11-11
7 - Project Completion |  |  |  | 2026-11-12 | 2026-11-19
IRPL /JH |  |  |  | 2026-11-12 | 2026-11-18
I2S-7688-MP-74.CM.W.1.8.7.1 | IRPL /JH | I.GG.WAD.1330 | WAD - Major - M3 - BGW - IRPL organises joint inspection of works | 2026-11-12 | 2026-11-18
TfNSW |  |  |  | 2026-11-19 | 2026-11-19
I2S-7688-MP-74.CM.W.1.8.7.2 | TfNSW | I.GG.WAD.1340 | WAD - Major - M3 - BGW - Project Officer issues Final Certification to IRPL | 2026-11-19 | 2026-11-19
Minor WAD
Minor WAD - Gate 8, 9 & 10 - Burley Griffin Way / Hibernia St (M5)
I2S-7688-MP-74.CM.W.2.2 | Minor WAD - Gate 8, 9 & 10 - Burley Griffin Way / Hibernia St (M5) | I.GG.WAD.3210 | WAD - Minor - M5 - BGW+HS - Comments close out after TfNSW review
I2S-7688-MP-74.CM.W.2.2 | Minor WAD - Gate 8, 9 & 10 - Burley Griffin Way / Hibernia St (M5) | I.GG.WAD.2030 | WAD - Minor - M5 - BGW+HS - WAD Agreed with TfNSW
I2S-7688-MP-74.CM.W.2.2 | Minor WAD - Gate 8, 9 & 10 - Burley Griffin Way / Hibernia St (M5) | I.GG.WAD.2040 | WAD - Minor - M5 - BGW+HS - (1a) IRPL Initiates Roads Act 1993 Works & Structures Application with TFSW
I2S-7688-MP-74.CM.W.2.2 | Minor WAD - Gate 8, 9 & 10 - Burley Griffin Way / Hibernia St (M5) | I.GG.WAD.2050 | WAD - Minor - M5 - BGW+HS - Strategic Design Developed
I2S-7688-MP-74.CM.W.2.2 | Minor WAD - Gate 8, 9 & 10 - Burley Griffin Way / Hibernia St (M5) | I.GG.WAD.2060 | WAD - Minor - M5 - BGW+HS - Strategic Design Submit to IRPL for review
I2S-7688-MP-74.CM.W.2.2 | Minor WAD - Gate 8, 9 & 10 - Burley Griffin Way / Hibernia St (M5) | I.GG.WAD.2070 | WAD - Minor - M5 - BGW+HS - (1b) Strategic Design Submit TfNSW for review
I2S-7688-MP-74.CM.W.2.2 | Minor WAD - Gate 8, 9 & 10 - Burley Griffin Way / Hibernia St (M5) | I.GG.WAD.2080 | WAD - Minor - M5 - BGW+HS - JH address comments
I2S-7688-MP-74.CM.W.2.2 | Minor WAD - Gate 8, 9 & 10 - Burley Griffin Way / Hibernia St (M5) | I.GG.WAD.2090 | WAD - Minor - M5 - BGW+HS - IRPL & TfNSW review/approve Strategic Design comment close out
I2S-7688-MP-74.CM.W.2.2 | Minor WAD - Gate 8, 9 & 10 - Burley Griffin Way / Hibernia St (M5) | I.GG.WAD.2100 | WAD - Minor - M5 - BGW+HS - TfNSW administers WAD to IRPL for execution - Draft
I2S-7688-MP-74.CM.W.2.2 | Minor WAD - Gate 8, 9 & 10 - Burley Griffin Way / Hibernia St (M5) | I.GG.WAD.2110 | WAD - Minor - M5 - BGW+HS - Develop Detailed Design Documentation
I2S-7688-MP-74.CM.W.2.2 | Minor WAD - Gate 8, 9 & 10 - Burley Griffin Way / Hibernia St (M5) | I.GG.WAD.2120 | WAD - Minor - M5 - BGW+HS - Submit to IRPL & TfNSW - Detail Design Docs for review/ approval
I2S-7688-MP-74.CM.W.2.2 | Minor WAD - Gate 8, 9 & 10 - Burley Griffin Way / Hibernia St (M5) | I.GG.WAD.2140 | WAD - Minor - M5 - BGW+HS - Design IFC
I2S-7688-MP-74.CM.W.2.2 | Minor WAD - Gate 8, 9 & 10 - Burley Griffin Way / Hibernia St (M5) | I.GG.WAD.2910 | WAD - Minor - M5 - BGW+HS - submission
I2S-7688-MP-74.CM.W.2.2 | Minor WAD - Gate 8, 9 & 10 - Burley Griffin Way / Hibernia St (M5) | I.GG.WAD.3070 | WAD - Minor - M5 - BGW+HS - JH to review TfNSW comments and resubmit
I2S-7688-MP-74.CM.W.2.2 | Minor WAD - Gate 8, 9 & 10 - Burley Griffin Way / Hibernia St (M5) | I.GG.WAD.3080 | WAD - Minor - M5 - BGW+HS - IRPL & TfNSW review/approve Strategic Design
I2S-7688-MP-74.CM.W.2.2 | Minor WAD - Gate 8, 9 & 10 - Burley Griffin Way / Hibernia St (M5) | I.GG.WAD.3180 | WAD - Minor - M5 - BGW+HS - TfNSW review
Pre-Construction
I2S-7688-MP-74.CM.W.2.2.1 | Pre-Construction | I.GG.WAD.2960 | WAD - Minor - M5 - BGW+HS - Provide written notice of intent to commence construction
I2S-7688-MP-74.CM.W.2.2.1 | Pre-Construction | I.GG.WAD.2940 | WAD - Minor - M5 - BGW+HS - Management Plans List - Collate
I2S-7688-MP-74.CM.W.2.2.1 | Pre-Construction | I.GG.WAD.2470 | WAD - Minor - M5 - BGW+HS - TfNSW Project Officer sends IRPL approval to commence Construction letter
I2S-7688-MP-74.CM.W.2.2.1 | Pre-Construction | I.GG.WAD.2920 | WAD - Minor - M5 - BGW+HS - Road Occupancy Licence - ROL - TfNSW
I2S-7688-MP-74.CM.W.2.2.1 | Pre-Construction | I.GG.WAD.2950 | WAD - Minor - M5 - BGW+HS - Management Plans List - Submit to TfNSW
I2S-7688-MP-74.CM.W.2.2.1 | Pre-Construction | I.GG.WAD.3190 | WAD - Minor - M5 - BGW+HS - Management Plans List - TfNSW review
I2S-7688-MP-74.CM.W.2.2.1 | Pre-Construction | I.GG.WAD.3200 | WAD - Minor - M5 - BGW+HS - Comments close out after TfNSW review
Minor WAD - Burley Griffin Way - Temporary Diversion (M4)
I2S-7688-MP-74.CM.W.2.8 | Minor WAD - Burley Griffin Way - Temporary Diversion (M4) | I.GG.WAD.1880 | WAD - Minor - M4 - BGW - Temp Div - Issue Detailed Design - IRPL / TfNSW / IV
I2S-7688-MP-74.CM.W.2.8 | Minor WAD - Burley Griffin Way - Temporary Diversion (M4) | I.GG.WAD.1820 | WAD - Minor - BGW - M4-Temp Div - (1b) Strategic Design Submit TfNSW for review
I2S-7688-MP-74.CM.W.2.8 | Minor WAD - Burley Griffin Way - Temporary Diversion (M4) | I.GG.WAD.1830 | WAD - Minor - BGW - M4-Temp Div - JH address comments
I2S-7688-MP-74.CM.W.2.8 | Minor WAD - Burley Griffin Way - Temporary Diversion (M4) | I.GG.WAD.1840 | WAD - Minor - BGW - M4-Temp Div - IRPL & TfNSW review/approve Strategic Design comment close out
I2S-7688-MP-74.CM.W.2.8 | Minor WAD - Burley Griffin Way - Temporary Diversion (M4) | I.GG.WAD.1850 | WAD - Minor - M4 - BGW - Temp Div - TfNSW and IRPL administer WAD for execution (Not required)
I2S-7688-MP-74.CM.W.2.8 | Minor WAD - Burley Griffin Way - Temporary Diversion (M4) | I.GG.WAD.1860 | WAD - Minor - M4 - BGW - Temp Div - Develop - Detailed Design
I2S-7688-MP-74.CM.W.2.8 | Minor WAD - Burley Griffin Way - Temporary Diversion (M4) | I.GG.WAD.1870 | WAD - Minor - M4 - BGW - Temp Div - Detailed Design Documentation - review/ approval by IRPL/TfNSW
I2S-7688-MP-74.CM.W.2.8 | Minor WAD - Burley Griffin Way - Temporary Diversion (M4) | I.GG.WAD.1980 | WAD - Minor - M4 - BGW - Temp Div - Independant review
I2S-7688-MP-74.CM.W.2.8 | Minor WAD - Burley Griffin Way - Temporary Diversion (M4) | I.GG.WAD.1990 | WAD - Minor - M4 - BGW - Temp Div - Comment close out and submit to IV
I2S-7688-MP-74.CM.W.2.8 | Minor WAD - Burley Griffin Way - Temporary Diversion (M4) | I.GG.WAD.1780 | WAD - Minor - BGW - M4-Temp Div - WAD Agreed with TfNSW
I2S-7688-MP-74.CM.W.2.8 | Minor WAD - Burley Griffin Way - Temporary Diversion (M4) | I.GG.WAD.1790 | WAD - Minor - BGW - M4-Temp Div - (1a) IRPL Initiates Roads Act 1993 Works & Structures Application with TFSW
I2S-7688-MP-74.CM.W.2.8 | Minor WAD - Burley Griffin Way - Temporary Diversion (M4) | I.GG.WAD.1800 | WAD - Minor - BGW - M4-Temp Div - Strategic Design Developed
I2S-7688-MP-74.CM.W.2.8 | Minor WAD - Burley Griffin Way - Temporary Diversion (M4) | I.GG.WAD.1810 | WAD - Minor - BGW - M4-Temp Div - Strategic Design Submit to IRPL for review
I2S-7688-MP-74.CM.W.2.8 | Minor WAD - Burley Griffin Way - Temporary Diversion (M4) | I.GG.WAD.2630 | WAD - Minor - M4 - BGW - Temp Div - Design IFC
I2S-7688-MP-74.CM.W.2.8 | Minor WAD - Burley Griffin Way - Temporary Diversion (M4) | I.GG.WAD.2690 | WAD - Minor - BGW - M4-Temp Div - Develop - PMP Documentation - same as M3 PDD finah
I2S-7688-MP-74.CM.W.2.8 | Minor WAD - Burley Griffin Way - Temporary Diversion (M4) | I.GG.WAD.3140 | WAD - Minor - M4 - BGW - Temp Div - Comment Closeout and submit update to TfNSW
I2S-7688-MP-74.CM.W.2.8 | Minor WAD - Burley Griffin Way - Temporary Diversion (M4) | I.GG.WAD.3150 | WAD - Minor - M4 - BGW - Temp Div - TfNSW/IV review
I2S-7688-MP-74.CM.W.2.8 | Minor WAD - Burley Griffin Way - Temporary Diversion (M4) | I.GG.WAD.3160 | WAD - Minor - M4 - BGW - Temp Div - TfNSW/IV - comments close out
Pre-Construction
I2S-7688-MP-74.CM.W.2.8.1 | Pre-Construction | I.GG.WAD.2480 | WAD - Minor - M4 - BGW - Temp Div - TfNSW Project Officer sends IRPL approval to commence Construction letter
I2S-7688-MP-74.CM.W.2.8.1 | Pre-Construction | I.GG.WAD.2930 | WAD - Minor - M4 - BGW - Temp Div - Road Occupancy Licence - ROL - TfNSW
I2S-7688-MP-74.CM.W.2.8.1 | Pre-Construction | I.GG.WAD.2980 | WAD - Minor - M4 - BGW - Temp Div - Management Plans List - Submit to TfNSW
I2S-7688-MP-74.CM.W.2.8.1 | Pre-Construction | I.GG.WAD.2990 | WAD - Minor - M4 - BGW - Temp Div - Provide written notice of intent to commence construction (10 days prior)
I2S-7688-MP-74.CM.W.2.8.1 | Pre-Construction | I.GG.WAD.2970 | WAD - Minor - M4 - BGW - Temp Div - Management Plans List - Collate
Post Construction
I2S-7688-MP-74.CM.W.2.8.3 | Post Construction | I.GG.WAD.2550 | WAD - Minor - M4 - BGW - Prj Officer - Notice of Anticipated Completion letter - ARTC/TfNSW - 20d before I.CN.50.15180
I2S-7688-MP-74.CM.W.2.8.3 | Post Construction | I.GG.WAD.2560 | WAD - Minor - M4 - BGW - Temp Div - Project Officer organises joint inspection of the works
I2S-7688-MP-74.CM.W.2.8.3 | Post Construction | I.GG.WAD.2570 | WAD - Minor - M4 - BGW - Temp Div - Project Officer issues a notice containing list of items necessary to achieve PC
I2S-7688-MP-74.CM.W.2.8.3 | Post Construction | I.GG.WAD.2580 | WAD - Minor - M4 - BGW - Temp Div - Project Officer issues Notice of Practical Completion letter
Section 138 Approvals
Junee Shire Council
I2S-7688-MP-74.CM.W.3.1 | Junee Shire Council | I.GG.WAD.2190 | WAD - Junee Shire Council - Sec.138 - Application Drafted - JSC
I2S-7688-MP-74.CM.W.3.1 | Junee Shire Council | I.GG.WAD.2200 | WAD - Junee Shire Council - Sec.138 - Develop design and Submit
I2S-7688-MP-74.CM.W.3.1 | Junee Shire Council | I.GG.WAD.2210 | WAD - Junee Shire Council - Sec.138 - JH Address Comments
I2S-7688-MP-74.CM.W.3.1 | Junee Shire Council | I.GG.WAD.2220 | WAD - Junee Shire Council - Sec.138 - Council / IRPL approve design and issue certificate
I2S-7688-MP-74.CM.W.3.1 | Junee Shire Council | I.GG.WAD.2230 | Sec.138 - Junee Shire Council - Sec.138 - Design IFC - 80%
I2S-7688-MP-74.CM.W.3.1 | Junee Shire Council | I.GG.WAD.2400 | WAD - Junee Shire Council - Sec.138 - IRPL and Council Review
I2S-7688-MP-74.CM.W.3.1 | Junee Shire Council | I.GG.WAD.2700 | Sec.138 - Junee Shire Council - Sec.138 - Design IFC - 80% - address comments
I2S-7688-MP-74.CM.W.3.1 | Junee Shire Council | I.GG.WAD.2710 | Sec.138 - Junee Shire Council - Sec.138 - Design IFC - 100 %
I2S-7688-MP-74.CM.W.3.1 | Junee Shire Council | I.GG.WAD.2180 | WAD - Junee Shire Council - Sec.138 - Agreed with Council - JSC
Pre-Construction
I2S-7688-MP-74.CM.W.3.1.1 | Pre-Construction | I.GG.WAD.2420 | WAD - Junee Shire Council - Sec.138 - Apply for ROL and sends approved ROL to Project Officer
I2S-7688-MP-74.CM.W.3.1.1 | Pre-Construction | I.GG.WAD.2430 | WAD - Junee Shire Council - Sec.138 - Provide written notice of intention to commence construction (10 days prior)
I2S-7688-MP-74.CM.W.3.1.1 | Pre-Construction | I.GG.WAD.2440 | WAD - Junee Shire Council - Sec.138 - Organise pre-start up meeting (on site)
Construction
I2S-7688-MP-74.CM.W.3.1.2 | Construction | I.GG.WAD.3100 | Sec.138 - Junee Shire Council - All Gates - Submit & receive PC letter
I2S-7688-MP-74.CM.W.3.1.2 | Construction | I.GG.WAD.3060 | Sec.138 - Junee Shire Council - Gate No. 6A & 6B - Dirnasser Rd - Seal Gates
I2S-7688-MP-74.CM.W.3.1.2 | Construction | I.GG.WAD.2330 | Sec.138 - Junee Shire Council - Gate No. 5 - Dirnaseer Rd - Construct
I2S-7688-MP-74.CM.W.3.1.2 | Construction | I.GG.WAD.2340 | Sec.138 - Junee Shire Council - Gate No. 5A - Ironbong Rd - Construct
I2S-7688-MP-74.CM.W.3.1.2 | Construction | I.GG.WAD.2350 | WAD - Junee Shire Council - Sec.138 - Gate No. 6 - Dirnasser Rd - Construct & Submit
I2S-7688-MP-74.CM.W.3.1.2 | Construction | I.GG.WAD.2240 | Sec.138 - Junee Shire Council - Gate No. 3 - Old Sydney Rd - Construct
I2S-7688-MP-74.CM.W.3.1.2 | Construction | I.GG.WAD.2320 | Sec.138 - Junee Shire Council - Gate No. 4A & 4B - Ironbong Rd - Construct
Cootamundra - Gundagai Regional Council
I2S-7688-MP-74.CM.W.3.2 | Cootamundra - Gundagai Regional Council | I.GG.WAD.2280 | Sec.138 - Coota GR Council - JH Address Comments - 80%
I2S-7688-MP-74.CM.W.3.2 | Cootamundra - Gundagai Regional Council | I.GG.WAD.2290 | Sec.138 - Coota GR Council - Council - approve design 80%
I2S-7688-MP-74.CM.W.3.2 | Cootamundra - Gundagai Regional Council | I.GG.WAD.2300 | Sec.138 - Coota GR Council - 80% Design
I2S-7688-MP-74.CM.W.3.2 | Cootamundra - Gundagai Regional Council | I.GG.WAD.2540 | Sec.138 - Coota GR Council - Council - approval for 7A & 7B
I2S-7688-MP-74.CM.W.3.2 | Cootamundra - Gundagai Regional Council | I.GG.WAD.2250 | Sec.138 - Coota GR Council - Agreed with Council - CGR
I2S-7688-MP-74.CM.W.3.2 | Cootamundra - Gundagai Regional Council | I.GG.WAD.2260 | Sec.138 - Coota GR Council - Application Drafted - CGR
I2S-7688-MP-74.CM.W.3.2 | Cootamundra - Gundagai Regional Council | I.GG.WAD.2270 | Sec.138 - Coota GR Council - Develop design and Submit - 7A & 7B
I2S-7688-MP-74.CM.W.3.2 | Cootamundra - Gundagai Regional Council | I.GG.WAD.2810 | Sec.138 - Coota GR Council - Develop design and Submit - Remaining gates
I2S-7688-MP-74.CM.W.3.2 | Cootamundra - Gundagai Regional Council | I.GG.WAD.2720 | Sec.138 - Coota GR Council - JH Address Comments - 100%
I2S-7688-MP-74.CM.W.3.2 | Cootamundra - Gundagai Regional Council | I.GG.WAD.2730 | Sec.138 - Coota GR Council - Council - Review and approve design - 100%
I2S-7688-MP-74.CM.W.3.2 | Cootamundra - Gundagai Regional Council | I.GG.WAD.2740 | Sec.138 - Coota GR Council - Design IFC - 100%
Pre-Construction
I2S-7688-MP-74.CM.W.3.2.1 | Pre-Construction | I.GG.WAD.2520 | Sec.138 - Coota GR Council - Apply for ROL and sends approved ROL to Project Officer
I2S-7688-MP-74.CM.W.3.2.1 | Pre-Construction | I.GG.WAD.2510 | Sec.138 - Coota GR Council - Provide written notice of intention to commence construction (10 days prior)
I2S-7688-MP-74.CM.W.3.2.1 | Pre-Construction | I.GG.WAD.2530 | Sec.138 - Coota GR Council - Organise pre-start up meeting (on site)
Construction
I2S-7688-MP-74.CM.W.3.2.2 | Construction | I.GG.WAD.2310 | Sec.138 - Coota GR Council - Gate No. 7A - Private Entry - Old Coota - Construct
I2S-7688-MP-74.CM.W.3.2.2 | Construction | I.GG.WAD.2360 | Sec.138 - Coota GR Council - Gate No. 7B - Old Coota - Construct
I2S-7688-MP-74.CM.W.3.2.2 | Construction | I.GG.WAD.2370 | Sec.138 - Coota GR Council - Gate No. 11 - Grogan Rd - Construct
I2S-7688-MP-74.CM.W.3.2.2 | Construction | I.GG.WAD.2380 | Sec.138 - Coota GR Council - Gate No. 13 - West St - Construct
I2S-7688-MP-74.CM.W.3.2.2 | Construction | I.GG.WAD.2390 | Sec.138 - Coota GR Council - Gate No. 14 - Rail Yard - Dudauman Rd - Construct
I2S-7688-MP-74.CM.W.3.2.2 | Construction | I.GG.WAD.3120 | Sec.138 - Coota GR Council - All gates Submit & receive PC letter
Utilities |  |  |  | 2024-09-30 | 2024-12-16
Utility Design Coordination |  |  |  | 2024-09-30 | 2024-12-16
I2S-7688-MP-74.CM.Ut.1 | Utility Design Coordination | I.GG.PM.UTIL-1 | UTIL - Commence Utility Design Co-ordination | 2024-10-17 | 2024-10-17
I2S-7688-MP-74.CM.Ut.1 | Utility Design Coordination | I.GG.PM.UTIL-2 | UTIL - All in ground services to be coordinated together Stormwater/CSR/Lighting | 2024-10-17 | 2024-11-13
I2S-7688-MP-74.CM.Ut.1 | Utility Design Coordination | I.GG.PM.UTIL-3 | UTIL - Horizontal / Vertical alignment & spaceproofing | 2024-11-14 | 2024-12-11
I2S-7688-MP-74.CM.Ut.1 | Utility Design Coordination | I.GG.15270 | UTIL - Engage non contestable utilities providers | 2024-09-30 | 2024-10-04
I2S-7688-MP-74.CM.Ut.1 | Utility Design Coordination | I.GG.15280 | UTIL - Procure construction water | 2024-11-12 | 2024-12-16
Utility Providers
Essential Energy (EE)
Essential Energy (EE) Design Process
Essential Energy (EE) Design Process - ELO-13
I2S-7688-MP-74.CM.Ut.2.1.8.1 | Essential Energy (EE) Design Process - ELO-13 | I.GG.PM.UTIL-1372 | UTIL - DSN - EE - ELO13 - Lodge Application
I2S-7688-MP-74.CM.Ut.2.1.8.1 | Essential Energy (EE) Design Process - ELO-13 | I.GG.PM.UTIL-1382 | UTIL - DSN - EE - ELO13 - Receive Design Information Packs
I2S-7688-MP-74.CM.Ut.2.1.8.1 | Essential Energy (EE) Design Process - ELO-13 | I.GG.PM.UTIL-1402 | UTIL - DSN - EE - ELO13 - Submit final design
Essential Energy (EE) Design Process - PS-01
I2S-7688-MP-74.CM.Ut.2.1.8.2 | Essential Energy (EE) Design Process - PS-01 | I.GG.PM.UTIL-1432 | UTIL - DSN - EE - PS-01 - Receive Design Information Packs
I2S-7688-MP-74.CM.Ut.2.1.8.2 | Essential Energy (EE) Design Process - PS-01 | I.GG.PM.UTIL-1442 | UTIL - DSN - EE - PS-01 - ARTC Approval (not required)
I2S-7688-MP-74.CM.Ut.2.1.8.2 | Essential Energy (EE) Design Process - PS-01 | I.GG.PM.UTIL-1452 | UTIL - DSN - EE - PS-01 - Submit final design
I2S-7688-MP-74.CM.Ut.2.1.8.2 | Essential Energy (EE) Design Process - PS-01 | I.GG.PM.UTIL-1422 | UTIL - DSN - EE - PS-01 - Lodge Application
Essential Energy (EE) Design Process - ELO-13, PS-01 [ECN-111187]
I2S-7688-MP-74.CM.Ut.2.1.8.1A | Essential Energy (EE) Design Process - ELO-13, PS-01 [ECN-111187] | I.CN.22.14390 | UTIL - DSN - EE - ELO-13 & PS-01 - Essential Energy - Cut Over Planning and Notification (inc permit)
I2S-7688-MP-74.CM.Ut.2.1.8.1A | Essential Energy (EE) Design Process - ELO-13, PS-01 [ECN-111187] | I.GG.PM.UTIL-1462 | UTIL - DSN - EE - ELO-13 & PS-01 - Essential Energy Certify Design
I2S-7688-MP-74.CM.Ut.2.1.8.1A | Essential Energy (EE) Design Process - ELO-13, PS-01 [ECN-111187] | I.GG.PM.UTIL-2082 | UTIL - DSN - EE - ELO-13 & PS-01 - Submit Easement Proposal to IRPL
I2S-7688-MP-74.CM.Ut.2.1.8.1A | Essential Energy (EE) Design Process - ELO-13, PS-01 [ECN-111187] | I.GG.PM.UTIL-2092 | UTIL - DSN - EE - ELO-13 & PS-01 - IRPL to Finalise Easement ECN-111187 - comments received
I2S-7688-MP-74.CM.Ut.2.1.8.1A | Essential Energy (EE) Design Process - ELO-13, PS-01 [ECN-111187] | I.CN.22.14480 | UTIL - DSN - EE - ELO-13 & PS-01 - Design and Easement Approved
I2S-7688-MP-74.CM.Ut.2.1.8.1A | Essential Energy (EE) Design Process - ELO-13, PS-01 [ECN-111187] | I.GG.PM.UTIL-2142 | UTIL - DSN - EE - ELO-13 & PS-01 - Update Easement Plan and resubmit to IRPL
I2S-7688-MP-74.CM.Ut.2.1.8.1A | Essential Energy (EE) Design Process - ELO-13, PS-01 [ECN-111187] | I.GG.PM.UTIL-2152 | UTIL - DSN - EE - ELO-13 & PS-01 - IRPL to Finalise and register Easement ECN-111187
I2S-7688-MP-74.CM.Ut.2.1.8.1A | Essential Energy (EE) Design Process - ELO-13, PS-01 [ECN-111187] | I.CN.22.15100 | UTIL - DSN - EE - ELO-13 & PS-01 - Essential Energy - Cut Over Planning and Notification Complete
Essential Energy (EE) Design Process - ELO-01, ELO-03, ELO-08, ELO-09
I2S-7688-MP-74.CM.Ut.2.1.8.3 | Essential Energy (EE) Design Process - ELO-01, ELO-03, ELO-08, ELO-09 | I.GG.PM.UTIL-1472 | UTIL - DSN - EE - ELO-01 - Lodge Application
I2S-7688-MP-74.CM.Ut.2.1.8.3 | Essential Energy (EE) Design Process - ELO-01, ELO-03, ELO-08, ELO-09 | I.GG.PM.UTIL-1482 | UTIL - DSN - EE - ELO-01 - Receive Design Information Packs
I2S-7688-MP-74.CM.Ut.2.1.8.3 | Essential Energy (EE) Design Process - ELO-01, ELO-03, ELO-08, ELO-09 | I.GG.PM.UTIL-1492 | UTIL - DSN - EE - ELO-01 - ARTC Approval
I2S-7688-MP-74.CM.Ut.2.1.8.3 | Essential Energy (EE) Design Process - ELO-01, ELO-03, ELO-08, ELO-09 | I.GG.PM.UTIL-1502 | UTIL - DSN - EE - ELO-01 - Submit final design
Essential Energy (EE) Design Process - ELO-01, ELO-08 [ECN-098333]
I2S-7688-MP-74.CM.Ut.2.1.8.3A | Essential Energy (EE) Design Process - ELO-01, ELO-08 [ECN-098333] | I.GG.PM.UTIL-1512 | UTIL - DSN - EE - ELO-01, ELO-08 - Essesntial Energy Certify Design
I2S-7688-MP-74.CM.Ut.2.1.8.3A | Essential Energy (EE) Design Process - ELO-01, ELO-08 [ECN-098333] | I.GG.PM.UTIL-1642 | UTIL - DSN - EE - ELO-01, ELO-08 - Design Approved
I2S-7688-MP-74.CM.Ut.2.1.8.3A | Essential Energy (EE) Design Process - ELO-01, ELO-08 [ECN-098333] | I.GG.PM.UTIL-2232 | UTIL - DSN - EE - ELO-01, ELO-08 - Cut Over Planning and Notification Complete
I2S-7688-MP-74.CM.Ut.2.1.8.3A | Essential Energy (EE) Design Process - ELO-01, ELO-08 [ECN-098333] | I.GG.PM.UTIL-2762 | UTIL - DSN - EE - ELO-01, ELO-08 - Project Procurement
I2S-7688-MP-74.CM.Ut.2.1.8.3A | Essential Energy (EE) Design Process - ELO-01, ELO-08 [ECN-098333] | I.GG.PM.UTIL-2792 | UTIL - DSN - EE - ELO-01, ELO-08 - Cut Over Planning and Notification (inc permit)
Essential Energy (EE) Design Process - ELO-09 [ECN-098331]
I2S-7688-MP-74.CM.Ut.2.1.8.3B | Essential Energy (EE) Design Process - ELO-09 [ECN-098331] | I.GG.PM.UTIL-1512-2 | UTIL - DSN - EE - ELO-09 - Essential Energy Certify Design
I2S-7688-MP-74.CM.Ut.2.1.8.3B | Essential Energy (EE) Design Process - ELO-09 [ECN-098331] | I.CN.22.14360 | UTIL - DSN - EE - ELO-09 - Essential energy - Cut Over Planning and Notification (inc permit)
I2S-7688-MP-74.CM.Ut.2.1.8.3B | Essential Energy (EE) Design Process - ELO-09 [ECN-098331] | I.GG.PM.UTIL-2242 | UTIL - DSN - EE - ELO-09 - Design Approved
I2S-7688-MP-74.CM.Ut.2.1.8.3B | Essential Energy (EE) Design Process - ELO-09 [ECN-098331] | I.GG.PM.UTIL-2772 | UTIL - DSN - EE - ELO-09 - Project Procurement
I2S-7688-MP-74.CM.Ut.2.1.8.3B | Essential Energy (EE) Design Process - ELO-09 [ECN-098331] | I.CN.22.15110 | UTIL - DSN - EE - ELO-09 - Essential energy - Cut Over Planning and Notification Complete
Essential Energy (EE) Design Process - ELO-03 [ECN-098334]
I2S-7688-MP-74.CM.Ut.2.1.8.3C | Essential Energy (EE) Design Process - ELO-03 [ECN-098334] | I.GG.PM.UTIL-1512-3 | UTIL - DSN - EE - ELO-03 - Essential Energy Certify Design - LO easement approval
I2S-7688-MP-74.CM.Ut.2.1.8.3C | Essential Energy (EE) Design Process - ELO-03 [ECN-098334] | I.GG.PM.UTIL-2182 | UTIL - DSN - EE - ELO-03 - Submit Easement Proposal to IRPL
I2S-7688-MP-74.CM.Ut.2.1.8.3C | Essential Energy (EE) Design Process - ELO-03 [ECN-098334] | I.GG.PM.UTIL-2192 | UTIL - DSN - EE - ELO-03 - IRPL to Finalise Easement ELO 3 (Indicative) - comments received
I2S-7688-MP-74.CM.Ut.2.1.8.3C | Essential Energy (EE) Design Process - ELO-03 [ECN-098334] | I.GG.PM.UTIL-2252 | UTIL - DSN - EE - ELO-03 - Update Easement Plan and resubmit to IRPL
I2S-7688-MP-74.CM.Ut.2.1.8.3C | Essential Energy (EE) Design Process - ELO-03 [ECN-098334] | I.GG.PM.UTIL-2262 | UTIL - DSN - EE - ELO-03 - IRPL to Finalise and register Easement - LO easement approval
I2S-7688-MP-74.CM.Ut.2.1.8.3C | Essential Energy (EE) Design Process - ELO-03 [ECN-098334] | I.CN.22.14580 | UTIL - DSN - EE - ELO-03 - Design and Easement Approved
I2S-7688-MP-74.CM.Ut.2.1.8.3C | Essential Energy (EE) Design Process - ELO-03 [ECN-098334] | I.CN.22.14590 | UTIL - DSN - EE - ELO-03 - Essential Energy - Cut Over Planning and Notification (inc permit)
I2S-7688-MP-74.CM.Ut.2.1.8.3C | Essential Energy (EE) Design Process - ELO-03 [ECN-098334] | I.CN.22.15030 | UTIL - DSN - EE - ELO-03 - Project Procurement
I2S-7688-MP-74.CM.Ut.2.1.8.3C | Essential Energy (EE) Design Process - ELO-03 [ECN-098334] | I.CN.22.15120 | UTIL - DSN - EE - ELO-03 - Essential Energy - Cut Over Planning and Notification Complete
Essential Energy (EE) Design Process - PS-02
I2S-7688-MP-74.CM.Ut.2.1.8.4 | Essential Energy (EE) Design Process - PS-02 | I.GG.PM.UTIL-1522 | UTIL - DSN - EE - PS-02 - Lodge Application
I2S-7688-MP-74.CM.Ut.2.1.8.4 | Essential Energy (EE) Design Process - PS-02 | I.GG.PM.UTIL-1532 | UTIL - DSN - EE - PS-02 - Receive Design Information Packs
I2S-7688-MP-74.CM.Ut.2.1.8.4 | Essential Energy (EE) Design Process - PS-02 | I.GG.PM.UTIL-1542 | UTIL - DSN - EE - PS-02 - ARTC Approval
I2S-7688-MP-74.CM.Ut.2.1.8.4 | Essential Energy (EE) Design Process - PS-02 | I.GG.PM.UTIL-1552 | UTIL - DSN - EE - PS-02 - Submit final design
I2S-7688-MP-74.CM.Ut.2.1.8.4 | Essential Energy (EE) Design Process - PS-02 | I.GG.PM.UTIL-2102 | UTIL - DSN - EE - PS-02 - Submit Easement Proposal to IRPL
Essential Energy (EE) Design Process - ELO-02
I2S-7688-MP-74.CM.Ut.2.1.8.5 | Essential Energy (EE) Design Process - ELO-02 | I.GG.PM.UTIL-1582 | UTIL - DSN - EE - EL-02 - Receive Design Information Packs
I2S-7688-MP-74.CM.Ut.2.1.8.5 | Essential Energy (EE) Design Process - ELO-02 | I.GG.PM.UTIL-1602 | UTIL - DSN - EE - EL-02 - Submit final design
I2S-7688-MP-74.CM.Ut.2.1.8.5 | Essential Energy (EE) Design Process - ELO-02 | I.GG.PM.UTIL-1572 | UTIL - DSN - EE - EL-02 - Lodge Application
Essential Energy (EE) Design Process - PS-02, ELO-02 [ECN-109630]
I2S-7688-MP-74.CM.Ut.2.1.8.4A | Essential Energy (EE) Design Process - PS-02, ELO-02 [ECN-109630] | I.GG.PM.UTIL-1562 | UTIL - DSN - EE - PS02, EL02 - Essential Energy Certify Design
I2S-7688-MP-74.CM.Ut.2.1.8.4A | Essential Energy (EE) Design Process - PS-02, ELO-02 [ECN-109630] | I.GG.PM.UTIL-2112 | UTIL - DSN - EE - PS02, EL02 - IRPL to Finalise Easement - comments received
I2S-7688-MP-74.CM.Ut.2.1.8.4A | Essential Energy (EE) Design Process - PS-02, ELO-02 [ECN-109630] | I.GG.PM.UTIL-1592 | UTIL - DSN - EE - PS02, EL02 - ARTC Approval
I2S-7688-MP-74.CM.Ut.2.1.8.4A | Essential Energy (EE) Design Process - PS-02, ELO-02 [ECN-109630] | I.GG.PM.UTIL-2272 | UTIL - DSN - EE - PS02, EL02 - Update Easement Plan and resubmit to IRPL
I2S-7688-MP-74.CM.Ut.2.1.8.4A | Essential Energy (EE) Design Process - PS-02, ELO-02 [ECN-109630] | I.GG.PM.UTIL-2282 | UTIL - DSN - EE - PS02, EL02 - IRPL to Finalise and register Easement
I2S-7688-MP-74.CM.Ut.2.1.8.4A | Essential Energy (EE) Design Process - PS-02, ELO-02 [ECN-109630] | I.CN.22.14600 | UTIL - DSN - EE - PS02, EL02 - Design and Easement Approved
I2S-7688-MP-74.CM.Ut.2.1.8.4A | Essential Energy (EE) Design Process - PS-02, ELO-02 [ECN-109630] | I.CN.22.14610 | UTIL - DSN - EE - PS02, EL02 - Essential Energy - Cut Over Planning and Notification (inc permit)
I2S-7688-MP-74.CM.Ut.2.1.8.4A | Essential Energy (EE) Design Process - PS-02, ELO-02 [ECN-109630] | I.CN.22.15040 | UTIL - DSN - EE - PS02, EL02 - Project Procurement
I2S-7688-MP-74.CM.Ut.2.1.8.4A | Essential Energy (EE) Design Process - PS-02, ELO-02 [ECN-109630] | I.CN.22.15130 | UTIL - DSN - EE - PS02, EL02 - Essential Energy - Cut Over Planning and Notification Complete
Essential Energy (EE) Design Process - ELO-04, ELO-10, ELO-14
I2S-7688-MP-74.CM.Ut.2.1.8.6 | Essential Energy (EE) Design Process - ELO-04, ELO-10, ELO-14 | I.GG.PM.UTIL-1692 | UTIL - DSN - EE - ELO-04, ELO-10, ELO-14 - ARTC Approval
I2S-7688-MP-74.CM.Ut.2.1.8.6 | Essential Energy (EE) Design Process - ELO-04, ELO-10, ELO-14 | I.GG.PM.UTIL-1702 | UTIL - DSN - EE - ELO-04, ELO-10, ELO-14 - Submit final design
I2S-7688-MP-74.CM.Ut.2.1.8.6 | Essential Energy (EE) Design Process - ELO-04, ELO-10, ELO-14 | I.GG.PM.UTIL-1672 | UTIL - DSN - EE - ELO-04, ELO-10, ELO-14 - Lodge Application
I2S-7688-MP-74.CM.Ut.2.1.8.6 | Essential Energy (EE) Design Process - ELO-04, ELO-10, ELO-14 | I.GG.PM.UTIL-1682 | UTIL - DSN - EE - ELO-04, ELO-10, ELO-14 - Receive Design Information Packs
Essential Energy (EE) Design Process - ELO-10 [ECN-099001]
I2S-7688-MP-74.CM.Ut.2.1.8.6A | Essential Energy (EE) Design Process - ELO-10 [ECN-099001] | I.GG.PM.UTIL-1712 | UTIL - DSN - EE - ELO-10 - Essential Energy Certify Design
I2S-7688-MP-74.CM.Ut.2.1.8.6A | Essential Energy (EE) Design Process - ELO-10 [ECN-099001] | I.CN.22.14340 | UTIL - DSN - EE - ELO-10 - Essential energy - Cut Over Planning and Notification
I2S-7688-MP-74.CM.Ut.2.1.8.6A | Essential Energy (EE) Design Process - ELO-10 [ECN-099001] | I.GG.PM.UTIL-2292 | UTIL - DSN - EE - ELO-10 - Design Approved
I2S-7688-MP-74.CM.Ut.2.1.8.6A | Essential Energy (EE) Design Process - ELO-10 [ECN-099001] | I.CN.22.15050 | UTIL - DSN - EE - ELO-10 - Project Procurement & Final approvals
I2S-7688-MP-74.CM.Ut.2.1.8.6A | Essential Energy (EE) Design Process - ELO-10 [ECN-099001] | I.CN.22.15140 | UTIL - DSN - EE - ELO-10 - Essential energy - Cut Over Planning and Notification Complete
Essential Energy (EE) Design Process - ELO-04 [ECN-099002]
I2S-7688-MP-74.CM.Ut.2.1.8.6B | Essential Energy (EE) Design Process - ELO-04 [ECN-099002] | I.GG.PM.UTIL-2212 | UTIL - DSN - EE - ELO-04 - Essential Energy Certify Design
I2S-7688-MP-74.CM.Ut.2.1.8.6B | Essential Energy (EE) Design Process - ELO-04 [ECN-099002] | I.CN.22.14650 | UTIL - DSN - EE - ELO-04 - Essential energy - Cut Over Planning and Notification (inc permit)
I2S-7688-MP-74.CM.Ut.2.1.8.6B | Essential Energy (EE) Design Process - ELO-04 [ECN-099002] | I.GG.PM.UTIL-2302 | UTIL - DSN - EE - ELO-04 - Design Approved
I2S-7688-MP-74.CM.Ut.2.1.8.6B | Essential Energy (EE) Design Process - ELO-04 [ECN-099002] | I.CN.22.15060 | UTIL - DSN - EE - ELO-04 - Project Procurement
I2S-7688-MP-74.CM.Ut.2.1.8.6B | Essential Energy (EE) Design Process - ELO-04 [ECN-099002] | I.CN.22.15150 | UTIL - DSN - EE - ELO-04 - Essential energy - Cut Over Planning and Notification Complete
Essential Energy (EE) Design Process - ELO-14 [ECN-099004]
I2S-7688-MP-74.CM.Ut.2.1.8.6C | Essential Energy (EE) Design Process - ELO-14 [ECN-099004] | I.GG.PM.UTIL-2222 | UTIL - DSN - EE - ELO-14 - Essential Energy Certify Design
I2S-7688-MP-74.CM.Ut.2.1.8.6C | Essential Energy (EE) Design Process - ELO-14 [ECN-099004] | I.CN.22.14660 | UTIL - DSN - EE - ELO-14 - Essential energy - Cut Over Planning and Notification (inc permit)
I2S-7688-MP-74.CM.Ut.2.1.8.6C | Essential Energy (EE) Design Process - ELO-14 [ECN-099004] | I.GG.PM.UTIL-2312 | UTIL - DSN - EE - ELO-14 - Design Approved
I2S-7688-MP-74.CM.Ut.2.1.8.6C | Essential Energy (EE) Design Process - ELO-14 [ECN-099004] | I.CN.22.15070 | UTIL - DSN - EE - ELO-14 - Project Procurement
I2S-7688-MP-74.CM.Ut.2.1.8.6C | Essential Energy (EE) Design Process - ELO-14 [ECN-099004] | I.CN.22.15160 | UTIL - DSN - EE - ELO-14 - Essential energy - Cut Over Planning and Notification Complete
Essential Energy (EE) Design Process - ELO-05, ELO-06, ELO-12
I2S-7688-MP-74.CM.Ut.2.1.8.7 | Essential Energy (EE) Design Process - ELO-05, ELO-06, ELO-12 | I.GG.PM.UTIL-1722 | UTIL - DSN - EE - ELO-05, ELO-06, ELO-12 - Lodge Application
Essential Energy (EE) Design Process - ELO-05, ELO-06, ELO-07, ELO-11, PS-05 [ECN-111186]
I2S-7688-MP-74.CM.Ut.2.1.8.7A | Essential Energy (EE) Design Process - ELO-05, ELO-06, ELO-07, ELO-11, PS-05 [ECN-111186] | I.CN.22.14320 | UTIL - DSN - EE - ECN-111186 - Sec.6 - Essential Energy - Cut Over Planning and Notification (inc permit)
I2S-7688-MP-74.CM.Ut.2.1.8.7A | Essential Energy (EE) Design Process - ELO-05, ELO-06, ELO-07, ELO-11, PS-05 [ECN-111186] | I.GG.PM.UTIL-1732 | UTIL - DSN - EE - ECN-111186 - Receive Design Information Packs
I2S-7688-MP-74.CM.Ut.2.1.8.7A | Essential Energy (EE) Design Process - ELO-05, ELO-06, ELO-07, ELO-11, PS-05 [ECN-111186] | I.GG.PM.UTIL-1742 | UTIL - DSN - EE - ECN-111186 - ARTC Approval
I2S-7688-MP-74.CM.Ut.2.1.8.7A | Essential Energy (EE) Design Process - ELO-05, ELO-06, ELO-07, ELO-11, PS-05 [ECN-111186] | I.GG.PM.UTIL-1752 | UTIL - DSN - EE - ECN-111186 - Finalise and Submit final design
I2S-7688-MP-74.CM.Ut.2.1.8.7A | Essential Energy (EE) Design Process - ELO-05, ELO-06, ELO-07, ELO-11, PS-05 [ECN-111186] | I.GG.PM.UTIL-1762 | UTIL - DSN - EE - ECN-111186 - Essential Energy Certify Design
I2S-7688-MP-74.CM.Ut.2.1.8.7A | Essential Energy (EE) Design Process - ELO-05, ELO-06, ELO-07, ELO-11, PS-05 [ECN-111186] | I.GG.PM.UTIL-2162 | UTIL - DSN - EE - ECN-111186 - Submit Easement Proposal to IRPL
I2S-7688-MP-74.CM.Ut.2.1.8.7A | Essential Energy (EE) Design Process - ELO-05, ELO-06, ELO-07, ELO-11, PS-05 [ECN-111186] | I.GG.PM.UTIL-2172 | UTIL - DSN - EE - ECN-111186 - IRPL to Finalise Easement
I2S-7688-MP-74.CM.Ut.2.1.8.7A | Essential Energy (EE) Design Process - ELO-05, ELO-06, ELO-07, ELO-11, PS-05 [ECN-111186] | I.CN.22.15000 | UTIL - DSN - EE - ECN-111186 - Design Approved
I2S-7688-MP-74.CM.Ut.2.1.8.7A | Essential Energy (EE) Design Process - ELO-05, ELO-06, ELO-07, ELO-11, PS-05 [ECN-111186] | I.CN.22.15080 | UTIL - DSN - EE - ECN-111186 - Easement Approved
I2S-7688-MP-74.CM.Ut.2.1.8.7A | Essential Energy (EE) Design Process - ELO-05, ELO-06, ELO-07, ELO-11, PS-05 [ECN-111186] | I.CN.22.15170 | UTIL - DSN - EE - ECN-111186 - Sec.6 - Essential Energy - Cut Over Planning and Notification Complete
Essential Energy (EE) Design Process - ELO-12 [ECN-119227]
I2S-7688-MP-74.CM.Ut.2.1.8.7B | Essential Energy (EE) Design Process - ELO-12 [ECN-119227] | I.GG.PM.UTIL-2322 | UTIL - DSN - EE - ELO-12 - Receive Design Information Packs
I2S-7688-MP-74.CM.Ut.2.1.8.7B | Essential Energy (EE) Design Process - ELO-12 [ECN-119227] | I.GG.PM.UTIL-2332 | UTIL - DSN - EE - ELO-12 - SL asset owner Approval
I2S-7688-MP-74.CM.Ut.2.1.8.7B | Essential Energy (EE) Design Process - ELO-12 [ECN-119227] | I.GG.PM.UTIL-2342 | UTIL - DSN - EE - ELO-12 - Submit final design
I2S-7688-MP-74.CM.Ut.2.1.8.7B | Essential Energy (EE) Design Process - ELO-12 [ECN-119227] | I.GG.PM.UTIL-2352 | UTIL - DSN - EE - ELO-12 - Essential Energy Certify Design
I2S-7688-MP-74.CM.Ut.2.1.8.7B | Essential Energy (EE) Design Process - ELO-12 [ECN-119227] | I.GG.PM.UTIL-2362 | UTIL - DSN - EE - ELO-12 - Design Approved
I2S-7688-MP-74.CM.Ut.2.1.8.7B | Essential Energy (EE) Design Process - ELO-12 [ECN-119227] | I.GG.PM.UTIL-2372 | UTIL - DSN - EE - ELO-12 - Essential energy - Cut Over Planning and Notification (inc permit)
I2S-7688-MP-74.CM.Ut.2.1.8.7B | Essential Energy (EE) Design Process - ELO-12 [ECN-119227] | I.GG.PM.UTIL-2802 | UTIL - DSN - EE - ELO-12 - Essential energy - Cut Over Planning and Notification Complete
Essential Energy (EE) Design Process - PS-05
I2S-7688-MP-74.CM.Ut.2.1.8.8 | Essential Energy (EE) Design Process - PS-05 | I.GG.PM.UTIL-1822 | UTIL - DSN - EE - PS05 - Lodge Application
I2S-7688-MP-74.CM.Ut.2.1.8.8 | Essential Energy (EE) Design Process - PS-05 | I.GG.PM.UTIL-1832 | UTIL - DSN - EE - PS05 - Receive Design Information Packs
I2S-7688-MP-74.CM.Ut.2.1.8.8 | Essential Energy (EE) Design Process - PS-05 | I.GG.PM.UTIL-1842 | UTIL - DSN - EE - PS05 - ARTC Approval (Not required)
Essential Energy (EE) Design Process - Camp Site
I2S-7688-MP-74.CM.Ut.2.1.8.9 | Essential Energy (EE) Design Process - Camp Site | I.GG.PM.UTIL-1622 | UTIL - DSN - EE - Camp Site - Lodge Application
I2S-7688-MP-74.CM.Ut.2.1.8.9 | Essential Energy (EE) Design Process - Camp Site | I.GG.PM.UTIL-1632 | UTIL - DSN - EE - Camp Site - Receive Design Information Packs
I2S-7688-MP-74.CM.Ut.2.1.8.9 | Essential Energy (EE) Design Process - Camp Site | I.GG.PM.UTIL-1652 | UTIL - DSN - EE - Camp Site - Submit final design (Decision made to use generators, not required)
I2S-7688-MP-74.CM.Ut.2.1.8.9 | Essential Energy (EE) Design Process - Camp Site | I.GG.PM.UTIL-1662 | UTIL - DSN - EE - Camp Site - Certify Design
Essential Energy (EE) Design Process - ELO-07, ELO-11
I2S-7688-MP-74.CM.Ut.2.1.8.10 | Essential Energy (EE) Design Process - ELO-07, ELO-11 | I.GG.PM.UTIL-1772 | UTIL - DSN - EE - ELO-07, ELO-11 - Lodge Application
I2S-7688-MP-74.CM.Ut.2.1.8.10 | Essential Energy (EE) Design Process - ELO-07, ELO-11 | I.GG.PM.UTIL-1782 | UTIL - DSN - EE - ELO-07, ELO-11 - Receive Design Information Packs
Goldenfields Water
Goldenfields Water Design Process
Goldenfields Water Design Process - WA01-01,WA01-04
I2S-7688-MP-74.CM.Ut.2.3.4.1 | Goldenfields Water Design Process - WA01-01,WA01-04 | I.CN.22.14350 | UTIL - DSN - WA - Sec.4 - PUP - WA01-01 - Goldenfields Water - Cut Over Planning and Notification
I2S-7688-MP-74.CM.Ut.2.3.4.1 | Goldenfields Water Design Process - WA01-01,WA01-04 | I.CN.22.14380 | UTIL - DSN - WA - Sec.2 - PUP - WA01-04 - Goldenfields Water - Cut Over Planning and Notification
I2S-7688-MP-74.CM.Ut.2.3.4.1 | Goldenfields Water Design Process - WA01-01,WA01-04 | I.GG.PM.UTIL-1872 | UTIL - DSN - WA - 01-01, 01-04 - Site Investigations
I2S-7688-MP-74.CM.Ut.2.3.4.1 | Goldenfields Water Design Process - WA01-01,WA01-04 | I.GG.PM.UTIL-1882 | UTIL - DSN - WA - 01-01, 01-04 - Prepare Plan & Long Section
I2S-7688-MP-74.CM.Ut.2.3.4.1 | Goldenfields Water Design Process - WA01-01,WA01-04 | I.GG.PM.UTIL-1892 | UTIL - DSN - WA - 01-01, 01-04 - Goldenfields Design Approval
I2S-7688-MP-74.CM.Ut.2.3.4.1 | Goldenfields Water Design Process - WA01-01,WA01-04 | I.CN.22.15180 | UTIL - DSN - WA - Sec.4 - PUP - WA01-01 - Goldenfields Water - Cut Over Planning and Notification Complete
I2S-7688-MP-74.CM.Ut.2.3.4.1 | Goldenfields Water Design Process - WA01-01,WA01-04 | I.CN.22.15190 | UTIL - DSN - WA - Sec.2 - PUP - WA01-04 - Goldenfields Water - Cut Over Planning and Notification Complete
Goldenfields Water Design Process - WA01-03
I2S-7688-MP-74.CM.Ut.2.3.4.2 | Goldenfields Water Design Process - WA01-03 | I.GG.PM.UTIL-1902 | UTIL - DSN - WA - 01-03 - Site Investigations
I2S-7688-MP-74.CM.Ut.2.3.4.2 | Goldenfields Water Design Process - WA01-03 | I.GG.PM.UTIL-1912 | UTIL - DSN - WA - 01-03 - Prepare Plan & Long Section
I2S-7688-MP-74.CM.Ut.2.3.4.2 | Goldenfields Water Design Process - WA01-03 | I.GG.PM.UTIL-1922 | UTIL - DSN - WA - 01-03 - Goldenfields Design Approval
I2S-7688-MP-74.CM.Ut.2.3.4.2 | Goldenfields Water Design Process - WA01-03 | I.GG.PM.UTIL-2442 | UTIL - DSN - WA - 01-03 - IRPL agree Landowner access - GL property
I2S-7688-MP-74.CM.Ut.2.3.4.2 | Goldenfields Water Design Process - WA01-03 | I.CN.22.14910 | UTIL - DSN - WA - 01-03 - Sec.6 - Goldenfields Water - Cut Over Planning and Notification
I2S-7688-MP-74.CM.Ut.2.3.4.2 | Goldenfields Water Design Process - WA01-03 | I.GG.PM.UTIL-2432 | UTIL - DSN - WA - 01-03 - WAP submission
I2S-7688-MP-74.CM.Ut.2.3.4.2 | Goldenfields Water Design Process - WA01-03 | I.GG.PM.UTIL-2732 | UTIL - DSN - WA - 01-03 - WAP approval
I2S-7688-MP-74.CM.Ut.2.3.4.2 | Goldenfields Water Design Process - WA01-03 | I.CN.22.15200 | UTIL - DSN - WA - 01-03 - Sec.6 - Goldenfields Water - Cut Over Planning and Notification Complete
Goldenfields Water Design Process - WA01-02
I2S-7688-MP-74.CM.Ut.2.3.4.3 | Goldenfields Water Design Process - WA01-02 | I.CN.22.14330 | UTIL - DSN - WA - 01-02 - Sec.6 - PUP - Goldenfields Water - Cut Over Planning and Notification
I2S-7688-MP-74.CM.Ut.2.3.4.3 | Goldenfields Water Design Process - WA01-02 | I.GG.PM.UTIL-2452 | UTIL - DSN - WA - 01-02 - Site Investigations
I2S-7688-MP-74.CM.Ut.2.3.4.3 | Goldenfields Water Design Process - WA01-02 | I.GG.PM.UTIL-2462 | UTIL - DSN - WA - 01-02 - Prepare Plan & Long Section
I2S-7688-MP-74.CM.Ut.2.3.4.3 | Goldenfields Water Design Process - WA01-02 | I.GG.PM.UTIL-2472 | UTIL - DSN - WA - 01-02 - Goldenfields Design Approval
I2S-7688-MP-74.CM.Ut.2.3.4.3 | Goldenfields Water Design Process - WA01-02 | I.GG.PM.UTIL-2422 | UTIL - DSN - WA - 01-02 - IRPL agree Landowner access - TB property
I2S-7688-MP-74.CM.Ut.2.3.4.3 | Goldenfields Water Design Process - WA01-02 | I.CN.22.15210 | UTIL - DSN - WA - 01-02 - Sec.6 - PUP - Goldenfields Water - Cut Over Planning and Notification Complete
APA Group
APA Group Design Process
APA Group Design Process - NG02-01
I2S-7688-MP-74.CM.Ut.2.8.1.1 | APA Group Design Process - NG02-01 | I.GG.PM.UTIL-1932 | UTIL - DSN - GAS - APA - NG02-01 - Site Investigations
I2S-7688-MP-74.CM.Ut.2.8.1.1 | APA Group Design Process - NG02-01 | I.GG.PM.UTIL-1942 | UTIL - DSN - GAS - APA - NG02-01 - Prepare Plan & Long Section
I2S-7688-MP-74.CM.Ut.2.8.1.1 | APA Group Design Process - NG02-01 | I.GG.PM.UTIL-1952 | UTIL - DSN - GAS - APA - NG02-01 - APA Design Approval
I2S-7688-MP-74.CM.Ut.2.8.1.1 | APA Group Design Process - NG02-01 | I.GG.PM.UTIL-1962 | UTIL - DSN - GAS - APA - NG02-01 - Letter of Offer
I2S-7688-MP-74.CM.Ut.2.8.1.1 | APA Group Design Process - NG02-01 | I.GG.PM.UTIL-1972 | UTIL - DSN - GAS - APA - NG02-01 - Contractor awarded and mobilised
Communications (Telstra)
Telstra Design Process - Assets
Telstra Design - TE02-01 - Olympic Highway - CH1500
I2S-7688-MP-74.CM.Ut.2.2.7.9 | Telstra Design - TE02-01 - Olympic Highway - CH1500 | I.GG.PM.UTIL-1222 | UTIL - DSN - TEL-02-01 - Sec.1 - Site Investigations
I2S-7688-MP-74.CM.Ut.2.2.7.9 | Telstra Design - TE02-01 - Olympic Highway - CH1500 | I.GG.PM.UTIL-1232 | UTIL - DSN - TEL-02-01 - Sec.1 - Prepare Plan & Long Section
I2S-7688-MP-74.CM.Ut.2.2.7.9 | Telstra Design - TE02-01 - Olympic Highway - CH1500 | I.GG.PM.UTIL-1242 | UTIL - DSN - TEL-02-01 - Sec.1 - Telstra Design Approval
I2S-7688-MP-74.CM.Ut.2.2.7.9 | Telstra Design - TE02-01 - Olympic Highway - CH1500 | I.GG.PM.UTIL-1252 | UTIL - DSN - TEL-02-01 - Sec.1 - Letter of Offer
I2S-7688-MP-74.CM.Ut.2.2.7.9 | Telstra Design - TE02-01 - Olympic Highway - CH1500 | I.GG.PM.UTIL-1262 | UTIL - DSN - TEL-02-01 - Sec.1 - Contract awarded
Telstra Design - TE02-02,TE02-03 - Old Sydney Rd, LX - CH 5600 - Protection - Fiber
I2S-7688-MP-74.CM.Ut.2.2.7.2 | Telstra Design - TE02-02,TE02-03 - Old Sydney Rd, LX - CH 5600 - Protection - Fiber | I.GG.PM.UTIL-2482 | UTIL - DSN - TEL - 02-02 + 02-03 - Sec.2 - Site Investigations
I2S-7688-MP-74.CM.Ut.2.2.7.2 | Telstra Design - TE02-02,TE02-03 - Old Sydney Rd, LX - CH 5600 - Protection - Fiber | I.GG.PM.UTIL-2492 | UTIL - DSN - TEL - 02-02 + 02-03 - Sec.2 - Prepare Plan & Long Section
I2S-7688-MP-74.CM.Ut.2.2.7.2 | Telstra Design - TE02-02,TE02-03 - Old Sydney Rd, LX - CH 5600 - Protection - Fiber | I.GG.PM.UTIL-2502 | UTIL - DSN - TEL - 02-02 + 02-03 - Sec.2 - Telstra Design
I2S-7688-MP-74.CM.Ut.2.2.7.2 | Telstra Design - TE02-02,TE02-03 - Old Sydney Rd, LX - CH 5600 - Protection - Fiber | I.GG.PM.UTIL-2512 | UTIL - DSN - TEL - 02-02 + 02-03 - Sec.2 - Letter of Offer
I2S-7688-MP-74.CM.Ut.2.2.7.2 | Telstra Design - TE02-02,TE02-03 - Old Sydney Rd, LX - CH 5600 - Protection - Fiber | I.GG.PM.UTIL-2522 | UTIL - DSN - TEL - 02-02 + 02-03 - Sec.2 - Contract awarded + Mobilisation
I2S-7688-MP-74.CM.Ut.2.2.7.2 | Telstra Design - TE02-02,TE02-03 - Old Sydney Rd, LX - CH 5600 - Protection - Fiber | I.GG.PM.UTIL-2742 | UTIL - DSN - TEL - 02-02 + 02-03 - Sec.2 - Telstra Design Approval
I2S-7688-MP-74.CM.Ut.2.2.7.2 | Telstra Design - TE02-02,TE02-03 - Old Sydney Rd, LX - CH 5600 - Protection - Fiber | I.GG.PM.UTIL-2752 | UTIL - DSN - TEL - 02-02 + 02-03 - Sec.2 - ARTC Approval
Telstra Design - TE02-04,TE02-05 - Ironbong Road, LX - CH 8200
I2S-7688-MP-74.CM.Ut.2.2.7.3 | Telstra Design - TE02-04,TE02-05 - Ironbong Road, LX - CH 8200 | I.GG.PM.UTIL-2532 | UTIL - DSN - TEL - 02-04 + 02-05 - Sec.2 - Site Investigations
I2S-7688-MP-74.CM.Ut.2.2.7.3 | Telstra Design - TE02-04,TE02-05 - Ironbong Road, LX - CH 8200 | I.GG.PM.UTIL-2542 | UTIL - DSN - TEL - 02-04 + 02-05 - Sec.2 - Prepare Plan & Long Section
I2S-7688-MP-74.CM.Ut.2.2.7.3 | Telstra Design - TE02-04,TE02-05 - Ironbong Road, LX - CH 8200 | I.GG.PM.UTIL-2552 | UTIL - DSN - TEL - 02-04 + 02-05 - Sec.2 - Telstra Design Approval
I2S-7688-MP-74.CM.Ut.2.2.7.3 | Telstra Design - TE02-04,TE02-05 - Ironbong Road, LX - CH 8200 | I.GG.PM.UTIL-2562 | UTIL - DSN - TEL - 02-04 + 02-05 - Sec.2 - Letter of Offer
I2S-7688-MP-74.CM.Ut.2.2.7.3 | Telstra Design - TE02-04,TE02-05 - Ironbong Road, LX - CH 8200 | I.GG.PM.UTIL-2572 | UTIL - DSN - TEL - 02-04 + 02-05 - Sec.2 - Contract awarded
Telstra Design - TE02-06,TE02-07,TE02-08 - Dinaseer Rd, Rail Over Road Bridge - CH15900 - CH22270
I2S-7688-MP-74.CM.Ut.2.2.7.1 | Telstra Design - TE02-06,TE02-07,TE02-08 - Dinaseer Rd, Rail Over Road Bridge - CH15900 - CH22270 | I.GG.PM.UTIL-1322 | UTIL - DSN - TEL - 02-06 + 02-07 + 02-08 - Sec.3 - Site Investigations
I2S-7688-MP-74.CM.Ut.2.2.7.1 | Telstra Design - TE02-06,TE02-07,TE02-08 - Dinaseer Rd, Rail Over Road Bridge - CH15900 - CH22270 | I.GG.PM.UTIL-1332 | UTIL - DSN - TEL - 02-06 + 02-07 + 02-08 - Sec.3 - Prepare Plan & Long Section
I2S-7688-MP-74.CM.Ut.2.2.7.1 | Telstra Design - TE02-06,TE02-07,TE02-08 - Dinaseer Rd, Rail Over Road Bridge - CH15900 - CH22270 | I.GG.PM.UTIL-1342 | UTIL - DSN - TEL - 02-06 + 02-07 + 02-08 - Sec.3 - Telstra Design Approval
I2S-7688-MP-74.CM.Ut.2.2.7.1 | Telstra Design - TE02-06,TE02-07,TE02-08 - Dinaseer Rd, Rail Over Road Bridge - CH15900 - CH22270 | I.GG.PM.UTIL-1352 | UTIL - DSN - TEL - 02-06 + 02-07 + 02-08 - Sec.3 - Letter of Offer
I2S-7688-MP-74.CM.Ut.2.2.7.1 | Telstra Design - TE02-06,TE02-07,TE02-08 - Dinaseer Rd, Rail Over Road Bridge - CH15900 - CH22270 | I.GG.PM.UTIL-1362 | UTIL - DSN - TEL - 02-06 + 02-07 + 02-08 - Sec.3 - Contract awarded
Telstra Design - TE02-09 - Old Cootamundra Road, Rail Over Road Bridge - CH28300
I2S-7688-MP-74.CM.Ut.2.2.7.4 | Telstra Design - TE02-09 - Old Cootamundra Road, Rail Over Road Bridge - CH28300 | I.GG.PM.UTIL-2582 | UTIL - DSN - TEL - 02-09 - Sec.4 - Site Investigations
I2S-7688-MP-74.CM.Ut.2.2.7.4 | Telstra Design - TE02-09 - Old Cootamundra Road, Rail Over Road Bridge - CH28300 | I.GG.PM.UTIL-2592 | UTIL - DSN - TEL - 02-09 - Sec.4 - Prepare Plan & Long Section
I2S-7688-MP-74.CM.Ut.2.2.7.4 | Telstra Design - TE02-09 - Old Cootamundra Road, Rail Over Road Bridge - CH28300 | I.GG.PM.UTIL-2602 | UTIL - DSN - TEL - 02-09 - Sec.4 - Telstra Design Approval
I2S-7688-MP-74.CM.Ut.2.2.7.4 | Telstra Design - TE02-09 - Old Cootamundra Road, Rail Over Road Bridge - CH28300 | I.GG.PM.UTIL-2612 | UTIL - DSN - TEL - 02-09 - Sec.4 - Letter of Offer
I2S-7688-MP-74.CM.Ut.2.2.7.4 | Telstra Design - TE02-09 - Old Cootamundra Road, Rail Over Road Bridge - CH28300 | I.GG.PM.UTIL-2622 | UTIL - DSN - TEL - 02-09 - Sec.4 - Contract awarded
Telstra Design - TE02-10 - Dudauman Road, Private LX - CH30800
I2S-7688-MP-74.CM.Ut.2.2.7.8 | Telstra Design - TE02-10 - Dudauman Road, Private LX - CH30800 | I.GG.PM.UTIL-1282 | UTIL - DSN - TEL - 02-10 - Sec.5 - Prepare Plan & Long Section
I2S-7688-MP-74.CM.Ut.2.2.7.8 | Telstra Design - TE02-10 - Dudauman Road, Private LX - CH30800 | I.GG.PM.UTIL-1292 | UTIL - DSN - TEL - 02-10 - Sec.5 - Telstra Design Approval
I2S-7688-MP-74.CM.Ut.2.2.7.8 | Telstra Design - TE02-10 - Dudauman Road, Private LX - CH30800 | I.GG.PM.UTIL-1302 | UTIL - DSN - TEL - 02-10 - Sec.5 - Letter of Offer
I2S-7688-MP-74.CM.Ut.2.2.7.8 | Telstra Design - TE02-10 - Dudauman Road, Private LX - CH30800 | I.GG.PM.UTIL-1312 | UTIL - DSN - TEL - 02-10 - Sec.5 - Contract awarded
I2S-7688-MP-74.CM.Ut.2.2.7.8 | Telstra Design - TE02-10 - Dudauman Road, Private LX - CH30800 | I.GG.PM.UTIL-1272 | UTIL - DSN - TEL - 02-10 - Sec.5 - Site Investigations
Telstra Design - TE02-11 - Corbys Lane, LX - CH33800
I2S-7688-MP-74.CM.Ut.2.2.7.5 | Telstra Design - TE02-11 - Corbys Lane, LX - CH33800 | I.GG.PM.UTIL-2632 | UTIL - DSN - TEL - 02-11 - Sec.5 - Prepare Plan & Long Section
I2S-7688-MP-74.CM.Ut.2.2.7.5 | Telstra Design - TE02-11 - Corbys Lane, LX - CH33800 | I.GG.PM.UTIL-2642 | UTIL - DSN - TEL - 02-11 - Sec.5 - Telstra Design Approval
I2S-7688-MP-74.CM.Ut.2.2.7.5 | Telstra Design - TE02-11 - Corbys Lane, LX - CH33800 | I.GG.PM.UTIL-2652 | UTIL - DSN - TEL - 02-11 - Sec.5 - Letter of Offer
I2S-7688-MP-74.CM.Ut.2.2.7.5 | Telstra Design - TE02-11 - Corbys Lane, LX - CH33800 | I.GG.PM.UTIL-2662 | UTIL - DSN - TEL - 02-11 - Sec.5 - Contract awarded
I2S-7688-MP-74.CM.Ut.2.2.7.5 | Telstra Design - TE02-11 - Corbys Lane, LX - CH33800 | I.GG.PM.UTIL-2672 | UTIL - DSN - TEL - 02-11 - Sec.5 - Site Investigations
Telstra Design - TE02-12,TE02-13,TE02-14 - Burley Griffin Way, Realignment and Rail LX - CH37300
I2S-7688-MP-74.CM.Ut.2.2.7.6 | Telstra Design - TE02-12,TE02-13,TE02-14 - Burley Griffin Way, Realignment and Rail LX - CH37300 | I.GG.PM.UTIL-2692 | UTIL - DSN - TEL - 02-12 + 02-13 + 02-14 - Sec.6 - Telstra Design Approval
I2S-7688-MP-74.CM.Ut.2.2.7.6 | Telstra Design - TE02-12,TE02-13,TE02-14 - Burley Griffin Way, Realignment and Rail LX - CH37300 | I.GG.PM.UTIL-2702 | UTIL - DSN - TEL - 02-12 + 02-13 + 02-14 - Sec.6 - Letter of Offer
I2S-7688-MP-74.CM.Ut.2.2.7.6 | Telstra Design - TE02-12,TE02-13,TE02-14 - Burley Griffin Way, Realignment and Rail LX - CH37300 | I.GG.PM.UTIL-2712 | UTIL - DSN - TEL - 02-12 + 02-13 + 02-14 - Sec.6 - Contract awarded
I2S-7688-MP-74.CM.Ut.2.2.7.6 | Telstra Design - TE02-12,TE02-13,TE02-14 - Burley Griffin Way, Realignment and Rail LX - CH37300 | I.GG.PM.UTIL-2682 | UTIL - DSN - TEL - 02-12 + 02-13 + 02-14 - Sec.6 - Prepare Plan & Long Section
I2S-7688-MP-74.CM.Ut.2.2.7.6 | Telstra Design - TE02-12,TE02-13,TE02-14 - Burley Griffin Way, Realignment and Rail LX - CH37300 | I.GG.PM.UTIL-2722 | UTIL - DSN - TEL - 02-12 + 02-13 + 02-14 - Sec.6 - Site Investigations
Communications (Optus)
Optus Design Process (New)
Optus Design Process OF01-01 (New)
I2S-7688-MP-74.CM.Ut.2.5.1.1 | Optus Design Process OF01-01 (New) | I.GG.PM.UTIL-2002 | UTIL - DSN - Optus OF01-01 - Optus Design Approval
I2S-7688-MP-74.CM.Ut.2.5.1.1 | Optus Design Process OF01-01 (New) | I.GG.PM.UTIL-2202 | UTIL - DSN - Optus OF01-01 - Civil Works Pannelist Engaged Stage 1/2/3 - mobilise to site
I2S-7688-MP-74.CM.Ut.2.5.1.1 | Optus Design Process OF01-01 (New) | I.GG.PM.UTIL-2012 | UTIL - DSN - Optus OF01-01 - Letter of Offer
I2S-7688-MP-74.CM.Ut.2.5.1.1 | Optus Design Process OF01-01 (New) | I.GG.PM.UTIL-2022 | UTIL - DSN - Optus OF01-01 - Contractor awarded
I2S-7688-MP-74.CM.Ut.2.5.1.1 | Optus Design Process OF01-01 (New) | I.GG.PM.UTIL-1982 | UTIL - DSN - Optus OF01-01 - Site Investigations
I2S-7688-MP-74.CM.Ut.2.5.1.1 | Optus Design Process OF01-01 (New) | I.GG.PM.UTIL-1992 | UTIL - DSN - Optus OF01-01 - Prepare Plan & Long Section
Communications ( NBN)
NBN Design Process
NBN Design Process - NBN-01 - Sec.6
I2S-7688-MP-74.CM.Ut.2.7.1.1 | NBN Design Process - NBN-01 - Sec.6 | I.GG.PM.UTIL-2382 | UTIL - DSN - NBN-01 - Sec.6 - Update Easement Plan and resubmit to IRPL
I2S-7688-MP-74.CM.Ut.2.7.1.1 | NBN Design Process - NBN-01 - Sec.6 | I.GG.PM.UTIL-2392 | UTIL - DSN - NBN-01 - Sec.6 - IRPL to Finalise and register Easement ECN-113426
I2S-7688-MP-74.CM.Ut.2.7.1.1 | NBN Design Process - NBN-01 - Sec.6 | I.CN.22.14850 | UTIL - DSN - NBN-01 - Sec.6 - Design Approved
I2S-7688-MP-74.CM.Ut.2.7.1.1 | NBN Design Process - NBN-01 - Sec.6 | I.GG.PM.UTIL-2402 | UTIL - DSN - NBN-01 - Sec.6 - Cut Over Planning and Notification (inc permit)
I2S-7688-MP-74.CM.Ut.2.7.1.1 | NBN Design Process - NBN-01 - Sec.6 | I.GG.PM.UTIL-2412 | UTIL - DSN - NBN-01 - Sec.6 - WAP Application and Approval
I2S-7688-MP-74.CM.Ut.2.7.1.1 | NBN Design Process - NBN-01 - Sec.6 | I.GG.PM.UTIL-2032 | UTIL - DSN - NBN-01 - Sec.6 - Lodge Application
I2S-7688-MP-74.CM.Ut.2.7.1.1 | NBN Design Process - NBN-01 - Sec.6 | I.GG.PM.UTIL-2042 | UTIL - DSN - NBN-01 - Sec.6 - Receive Design Information Packs
I2S-7688-MP-74.CM.Ut.2.7.1.1 | NBN Design Process - NBN-01 - Sec.6 | I.GG.PM.UTIL-2052 | UTIL - DSN - NBN-01 - Sec.6 - ARTC Approval
I2S-7688-MP-74.CM.Ut.2.7.1.1 | NBN Design Process - NBN-01 - Sec.6 | I.GG.PM.UTIL-2062 | UTIL - DSN - NBN-01 - Sec.6 - Submit final design
I2S-7688-MP-74.CM.Ut.2.7.1.1 | NBN Design Process - NBN-01 - Sec.6 | I.GG.PM.UTIL-2072 | UTIL - DSN - NBN-01 - Sec.6 - Essential Energy Certify Design
I2S-7688-MP-74.CM.Ut.2.7.1.1 | NBN Design Process - NBN-01 - Sec.6 | I.GG.PM.UTIL-2782 | UTIL - DSN - NBN-01 - Sec.6 - Project Procurement
I2S-7688-MP-74.CM.Ut.2.7.1.1 | NBN Design Process - NBN-01 - Sec.6 | I.CN.22.15090 | UTIL - DSN - NBN-01 - Sec.6 - Easement Approved
Construction Requirements Notifications |  |  |  | 2024-09-30 | 2026-03-11
Track Possession Applications |  |  |  | 2024-09-30 | 2026-03-11
I2S-7688-MP-74.CM.GG.2 | Track Possession Applications | I.GG.CG.6360 | Site Wide - Apply for a Firm 60Hour Mar 25 Possession #1 - 30 Weeks | 2024-10-01 | 2024-10-01
I2S-7688-MP-74.CM.GG.2 | Track Possession Applications | I.GG.CG.6370 | Site Wide - Apply for a Firm 60Hour Sept 25 Possession #2 - 52 Weeks | 2024-10-02 | 2024-10-02
I2S-7688-MP-74.CM.GG.2 | Track Possession Applications | I.GG.CG.6910 | Site Wide - Apply for a Firm 60Hour Sept 26 Possession #4 - 52 Weeks | 2025-09-10 | 2025-09-10
I2S-7688-MP-74.CM.GG.2 | Track Possession Applications | I.GG.CG.6920 | Site Wide - Apply for a Firm 60Hour Mar 26 Possession #3 - 52 Weeks | 2025-03-12 | 2025-03-12
I2S-7688-MP-74.CM.GG.2 | Track Possession Applications | I.GG.CG.6930 | Site Wide - Apply for a 48 to 60Hour Dec 26 Possession - 52 Weeks- Required if previous possession cancelled | 2025-11-24 | 2025-11-24
I2S-7688-MP-74.CM.GG.2 | Track Possession Applications | I.GG.CG.6950 | Site Wide - Apply for a Firm 60Hour Mar 27 Possession #5 - 52 Weeks | 2026-03-11 | 2026-03-11
I2S-7688-MP-74.CM.GG.2 | Track Possession Applications | I.GG.15300 | JH Application requested for firm 60 hour Possessions | 2024-09-30 | 2024-09-30
Safeworking Track Possession Requests - 52 weeks |  |  |  | 2024-09-30 | 2024-09-30
I2S-7688-MP-74.CM.GG.7 | Safeworking Track Possession Requests - 52 weeks | I.GG.CG.6800 | Site Wide - Apply for PSW (For July 25) - (note NOT 52 weeks) | 2024-09-30 | 2024-09-30
Road Closure Notifications |  |  |  | 2025-06-10 | 2025-06-11
I2S-7688-MP-74.CM.GG.4 | Road Closure Notifications | I.GG.CG.6940 | Submit a Works Access Deed application to Coota Council for approval to construct additional Gates 7A | 2025-06-11 | 2025-06-11
I2S-7688-MP-74.CM.GG.4 | Road Closure Notifications | I.GG.CG.6660 | Road Closure /Diversion Notification - 3 Months - Burley Griffin Way | 2025-06-10 | 2025-06-10
I2S-7688-MP-74.CM.GG.4 | Road Closure Notifications | I.GG.CG.6900 | Road Closure /Diversion Notification - 3 Months - Ironbong Road | 2025-06-11 | 2025-06-11
I2S-7688-MP-74.CM.GG.4 | Road Closure Notifications | I.GG.CG.7070 | Submit a Works Access Deed application to Junee Council for approval to construct additional Gates 4A, 5A
Safeworking Track ATP Possession Requests - 26 weeks |  |  |  | 2025-01-10 | 2025-02-17
I2S-7688-MP-74.CM.GG.1 | Safeworking Track ATP Possession Requests - 26 weeks | I.GG.CG.6420 | Sec.1 - Apply for a TOA on the Main (6 months) | 2025-01-10 | 2025-01-10
I2S-7688-MP-74.CM.GG.1 | Safeworking Track ATP Possession Requests - 26 weeks | I.GG.CG.6450 | Sec.6 - Apply for a TWA on the Main (6 months) | 2025-02-17 | 2025-02-17
Track Possession Planning Requirements |  |  |  | 2024-11-07 | 2027-03-29
Pre- Possession Planning #1 (22/3/25 to 24/3/25) |  |  |  | 2024-11-07 | 2025-04-14
I2S-7688-MP-74.CM.TP.2 | Pre- Possession Planning #1 (22/3/25 to 24/3/25) | I.GG.POS02.030 | Possession #1 (22/3/25 to 24/3/25) - Notification of Work Activities (T - 13 weeks) | 2024-12-13 | 2024-12-13
I2S-7688-MP-74.CM.TP.2 | Pre- Possession Planning #1 (22/3/25 to 24/3/25) | I.GG.POS02.090 | Possession #1 (22/3/25 to 24/3/25) - Worksite Access Programs (T - 10 Bdays) | 2025-03-14 | 2025-03-14
I2S-7688-MP-74.CM.TP.2 | Pre- Possession Planning #1 (22/3/25 to 24/3/25) | I.GG.POS02.010 | Possession #1 (22/3/25 to 24/3/25) - Track Possession Program (Draft) (T - 90 Bdays) - 8/11/24 | 2024-11-07 | 2024-11-07
I2S-7688-MP-74.CM.TP.2 | Pre- Possession Planning #1 (22/3/25 to 24/3/25) | I.GG.POS02.040 | Possession #1 (22/3/25 to 24/3/25) - Track Possession Program (Final) (T - 60 Bdays) | 2024-12-19 | 2024-12-19
I2S-7688-MP-74.CM.TP.2 | Pre- Possession Planning #1 (22/3/25 to 24/3/25) | I.GG.POS02.020 | Possession #1 (22/3/25 to 24/3/25) - Pre-agreed Track Possession Notification (T - 13 weeks) | 2024-12-13 | 2024-12-13
I2S-7688-MP-74.CM.TP.2 | Pre- Possession Planning #1 (22/3/25 to 24/3/25) | I.GG.POS02.050 | Possession #1 (22/3/25 to 24/3/25) - Works Coordination, Pre- Planning, Risk (T - 12 weeks) | 2025-01-15 | 2025-01-15
I2S-7688-MP-74.CM.TP.2 | Pre- Possession Planning #1 (22/3/25 to 24/3/25) | I.GG.POS02.060 | Possession #1 (22/3/25 to 24/3/25) - Planning, Program, Risk (T - 6 weeks) | 2025-02-14 | 2025-02-14
I2S-7688-MP-74.CM.TP.2 | Pre- Possession Planning #1 (22/3/25 to 24/3/25) | I.GG.POS02.070 | Possession #1 (22/3/25 to 24/3/25) - Finalisation, Worksite Specific Planning (T - 4 weeks) | 2025-02-28 | 2025-02-28
I2S-7688-MP-74.CM.TP.2 | Pre- Possession Planning #1 (22/3/25 to 24/3/25) | I.GG.POS02.080 | Possession #1 (22/3/25 to 24/3/25) - Review & Finalisation Meeting (T - 2 weeks) | 2025-03-14 | 2025-03-14
I2S-7688-MP-74.CM.TP.2 | Pre- Possession Planning #1 (22/3/25 to 24/3/25) | I.GG.POS02.100 | Possession #1 (22/3/25 to 24/3/25)- Pre- Possession meeting (T - 1 day) - 24/3/25 | 2025-03-27 | 2025-03-27
I2S-7688-MP-74.CM.TP.2 | Pre- Possession Planning #1 (22/3/25 to 24/3/25) | I.GG.POS02.110 | Possession #1 (22/3/25 to 24/3/25) - Track Possession debrief (T + 2 weeks) | 2025-04-14 | 2025-04-14
Possession #1 (22/3/25 to 24/3/25) |  |  |  | 2025-03-29 | 2025-03-31
I2S-7688-MP-74.CM.TP.02 | Possession #1 (22/3/25 to 24/3/25) | I.GG.MSTP.1140 | I2S #1 - 60 hours - Main Line - Albury to Junee | 2025-03-29 | 2025-03-31
I2S-7688-MP-74.CM.TP.02 | Possession #1 (22/3/25 to 24/3/25) | I.GG.MSTP.1180 | S2P#1 - 60 hours - Main Line - Cootamundra West to Parkes | 2025-03-29 | 2025-03-31
Pre- Possession Planning #2 (13/9/25 to 15/9/25) |  |  |  | 2025-05-08 | 2025-09-29
I2S-7688-MP-74.CM.TP.3 | Pre- Possession Planning #2 (13/9/25 to 15/9/25) | I.GG.POS03.110 | Possession #2 (13/9/25 to 15/9/25) - Track Possession debrief (T + 2 weeks) | 2025-09-29 | 2025-09-29
I2S-7688-MP-74.CM.TP.3 | Pre- Possession Planning #2 (13/9/25 to 15/9/25) | I.GG.POS03.030 | Possession #2 (13/9/25 to 15/9/25) - Notification of Wok Activities (T - 13 weeks) | 2025-06-13 | 2025-06-13
I2S-7688-MP-74.CM.TP.3 | Pre- Possession Planning #2 (13/9/25 to 15/9/25) | I.GG.POS0M10 | Possession #2 (13/9/25 to 15/9/25) - Worksite Access Programs (T - 10 Bdays)
I2S-7688-MP-74.CM.TP.3 | Pre- Possession Planning #2 (13/9/25 to 15/9/25) | I.GG.POS03.010 | Possession #2 (13/9/25 to 15/9/25) - Track Possession Program (Draft) (T - 90 Bdays) - 8/5/25 | 2025-05-08 | 2025-05-08
I2S-7688-MP-74.CM.TP.3 | Pre- Possession Planning #2 (13/9/25 to 15/9/25) | I.GG.POS03.040 | Possession #2 (13/9/25 to 15/9/25) - Track Possession Program (Final) (T - 60 Bdays) | 2025-06-20 | 2025-06-20
I2S-7688-MP-74.CM.TP.3 | Pre- Possession Planning #2 (13/9/25 to 15/9/25) | I.GG.POS03.020 | Possession #2 (13/9/25 to 15/9/25) - Pre-agreed Track Possession Notification (T - 13 weeks) | 2025-06-13 | 2025-06-13
I2S-7688-MP-74.CM.TP.3 | Pre- Possession Planning #2 (13/9/25 to 15/9/25) | I.GG.POS03.050 | Possession #2 (13/9/25 to 15/9/25) - Works Coordination, Pre- Planning, Risk (T - 12 weeks) | 2025-06-20 | 2025-06-20
I2S-7688-MP-74.CM.TP.3 | Pre- Possession Planning #2 (13/9/25 to 15/9/25) | I.GG.POS03.060 | Possession #2 (13/9/25 to 15/9/25) - Planning, Program, Risk (T - 6 weeks) | 2025-08-01 | 2025-08-01
I2S-7688-MP-74.CM.TP.3 | Pre- Possession Planning #2 (13/9/25 to 15/9/25) | I.GG.POS03.070 | Possession #2 (13/9/25 to 15/9/25) - Finalisation, Worksite Specific Planning (T - 4 weeks) | 2025-08-15 | 2025-08-15
I2S-7688-MP-74.CM.TP.3 | Pre- Possession Planning #2 (13/9/25 to 15/9/25) | I.GG.POS03.080 | Possession #2 (13/9/25 to 15/9/25) - Review & Finalisation Meeting (T - 2 weeks) | 2025-08-29 | 2025-08-29
I2S-7688-MP-74.CM.TP.3 | Pre- Possession Planning #2 (13/9/25 to 15/9/25) | I.GG.POS03.100 | Possession #2 (13/9/25 to 15/9/25) - Pre- Possession meeting (T - 1 day) - 11/9/25 | 2025-09-11 | 2025-09-11
Possession #2 (13/9/25 to 15/9/25) |  |  |  | 2025-09-13 | 2025-09-15
I2S-7688-MP-74.CM.TP.03 | Possession #2 (13/9/25 to 15/9/25) | I.GG.MSTP.1150 | I2S #2 - 60 hours - Main Line - Albury to Junee | 2025-09-13 | 2025-09-15
I2S-7688-MP-74.CM.TP.03 | Possession #2 (13/9/25 to 15/9/25) | I.GG.MSTP.1190 | S2P#2 - 60 hours - Main Line - Cootamundra West to Parkes | 2025-09-13 | 2025-09-15
Pre- Possession Planning #3 (6/12/25 to 7/12/25)
I2S-7688-MP-74.CM.TP.6 | Pre- Possession Planning #3 (6/12/25 to 7/12/25) | I.GG.POS06.030 | Possession #3 (6/12/25 to 7/12/25) - Notification of Wok Activities (T - 13 weeks)
I2S-7688-MP-74.CM.TP.6 | Pre- Possession Planning #3 (6/12/25 to 7/12/25) | I.GG.POS06.090 | Possession #3 (6/12/25 to 7/12/25) - Worksite Access Programs (T - 10 Bdays)
I2S-7688-MP-74.CM.TP.6 | Pre- Possession Planning #3 (6/12/25 to 7/12/25) | I.GG.POS06.010 | Possession #3 (6/12/25 to 7/12/25) - Track Possession Program (Draft) (T - 90 Bdays) - 26/09/25
I2S-7688-MP-74.CM.TP.6 | Pre- Possession Planning #3 (6/12/25 to 7/12/25) | I.GG.POS06.040 | Possession #3 (6/12/25 to 7/12/25) - Track Possession Program (Final) (T - 60 Bdays)
I2S-7688-MP-74.CM.TP.6 | Pre- Possession Planning #3 (6/12/25 to 7/12/25) | I.GG.POS06.020 | Possession #3 (6/12/25 to 7/12/25) - Pre-agreed Track Possession Notification (T - 13 weeks)
I2S-7688-MP-74.CM.TP.6 | Pre- Possession Planning #3 (6/12/25 to 7/12/25) | I.GG.POS06.050 | Possession #3 (6/12/25 to 7/12/25) - Works Coordination, Pre- Planning, Risk (T - 12 weeks)
I2S-7688-MP-74.CM.TP.6 | Pre- Possession Planning #3 (6/12/25 to 7/12/25) | I.GG.POS06.060 | Possession #3 (6/12/25 to 7/12/25) - Planning, Program, Risk (T - 6 weeks)
I2S-7688-MP-74.CM.TP.6 | Pre- Possession Planning #3 (6/12/25 to 7/12/25) | I.GG.POS06.070 | Possession #3 (6/12/25 to 7/12/25) - Finalisation, Worksite Specific Planning (T - 4 weeks)
I2S-7688-MP-74.CM.TP.6 | Pre- Possession Planning #3 (6/12/25 to 7/12/25) | I.GG.POS06.080 | Possession #3 (6/12/25 to 7/12/25) - Review & Finalisation Meeting (T - 2 weeks)
I2S-7688-MP-74.CM.TP.6 | Pre- Possession Planning #3 (6/12/25 to 7/12/25) | I.GG.POS06.100 | Possession #3 (6/12/25 to 7/12/25) - Pre- Possession meeting (T - 1 day) - 05/12/25
I2S-7688-MP-74.CM.TP.6 | Pre- Possession Planning #3 (6/12/25 to 7/12/25) | I.GG.POS06.110 | Possession #3 (6/12/25 to 7/12/25) - Track Possession debrief (T + 2 weeks)
Possession #3(6/12/25 to 7/12/25)
I2S-7688-MP-74.CM.TP.8 | Possession #3(6/12/25 to 7/12/25) | I.GG.MSTP.1220 | S2P#3 - 36 hours - Main Line - Cootamundra West to Parkes
I2S-7688-MP-74.CM.TP.8 | Possession #3(6/12/25 to 7/12/25) | I.GG.MSTP.1230 | I2S #3 - 36 hours - Main Line - Albury to Junee
Pre- Possession Planning #4 (28/2/26 to 3/3/26) |  |  |  | 2025-10-23 | 2026-03-30
I2S-7688-MP-74.CM.TP.4 | Pre- Possession Planning #4 (28/2/26 to 3/3/26) | I.GG.POS04.030 | Possession #4 (28/2/26 to 3/3/26) - Notification of Wok Activities (T - 13 weeks) | 2025-12-12 | 2025-12-12
I2S-7688-MP-74.CM.TP.4 | Pre- Possession Planning #4 (28/2/26 to 3/3/26) | I.GG.POS04.090 | Possession #4 (28/2/26 to 3/3/26) - Worksite Access Programs (T - 10 Bdays) | 2026-02-27 | 2026-02-27
I2S-7688-MP-74.CM.TP.4 | Pre- Possession Planning #4 (28/2/26 to 3/3/26) | I.GG.POS04.010 | Possession #4 (28/2/26 to 3/3/26) - Track Possession Program (Draft) (T - 90 Bdays) - 09/10/25 | 2025-10-23 | 2025-10-23
I2S-7688-MP-74.CM.TP.4 | Pre- Possession Planning #4 (28/2/26 to 3/3/26) | I.GG.POS04.040 | Possession #4 (28/2/26 to 3/3/26) - Track Possession Program (Final) (T - 60 Bdays) | 2025-12-04 | 2025-12-04
I2S-7688-MP-74.CM.TP.4 | Pre- Possession Planning #4 (28/2/26 to 3/3/26) | I.GG.POS04.020 | Possession #4 (28/2/26 to 3/3/26) - Pre-agreed Track Possession Notification (T - 13 weeks) | 2025-12-12 | 2025-12-12
I2S-7688-MP-74.CM.TP.4 | Pre- Possession Planning #4 (28/2/26 to 3/3/26) | I.GG.POS04.050 | Possession #4 (28/2/26 to 3/3/26) - Works Coordination, Pre- Planning, Risk (T - 12 weeks) | 2025-12-19 | 2025-12-19
I2S-7688-MP-74.CM.TP.4 | Pre- Possession Planning #4 (28/2/26 to 3/3/26) | I.GG.POS04.060 | Possession #4 (28/2/26 to 3/3/26) - Planning, Program, Risk (T - 6 weeks) | 2026-01-30 | 2026-01-30
I2S-7688-MP-74.CM.TP.4 | Pre- Possession Planning #4 (28/2/26 to 3/3/26) | I.GG.POS04.070 | Possession #4 (28/2/26 to 3/3/26) - Finalisation, Worksite Specific Planning (T - 4 weeks) | 2026-02-13 | 2026-02-13
I2S-7688-MP-74.CM.TP.4 | Pre- Possession Planning #4 (28/2/26 to 3/3/26) | I.GG.POS04.080 | Possession #4 (28/2/26 to 3/3/26) - Review & Finalisation Meeting (T - 2 weeks) | 2026-02-27 | 2026-02-27
I2S-7688-MP-74.CM.TP.4 | Pre- Possession Planning #4 (28/2/26 to 3/3/26) | I.GG.POS04.100 | Possession #4 (28/2/26 to 3/3/26) - Pre- Possession meeting (T - 1 day) - 27/2/26 | 2026-03-12 | 2026-03-12
I2S-7688-MP-74.CM.TP.4 | Pre- Possession Planning #4 (28/2/26 to 3/3/26) | I.GG.POS04.110 | Possession #4 (28/2/26 to 3/3/26) - Track Possession debrief (T + 2 weeks) | 2026-03-30 | 2026-03-30
Possession #4 (28/2/26 to 3/3/26) - OD 42.5 hrs - 14-Jan-2026 upd |  |  |  | 2026-03-14 | 2026-03-16
I2S-7688-MP-74.CM.TP.04 | Possession #4 (28/2/26 to 3/3/26) - OD 42.5 hrs - 14-Jan-2026 upd | I.GG.MSTP.1200 | S2P - Possession #4 - 28/2/26 to 4/3/26 - 42.5 hours - Main Line - Cootamundra West to Parkes | 2026-03-14 | 2026-03-16
I2S-7688-MP-74.CM.TP.04 | Possession #4 (28/2/26 to 3/3/26) - OD 42.5 hrs - 14-Jan-2026 upd | I.GG.MSTP.1160 | I2S - Possession #4 - 28/2/26 to 4/3/26 - 42.5 hours - Main Line - Albury to Junee | 2026-03-14 | 2026-03-16
Pre- Possession Planning #5 (2/5/26 to 4/5/26) - OD changed to 96h - 16-Feb-2026
I2S-7688-MP-74.CM.TP.9 | Pre- Possession Planning #5 (2/5/26 to 4/5/26) - OD changed to 96h - 16-Feb-2026 | I.GG.POS07.030 | Possession #5 - 2/5/26 to 5/5/26 - Notification of Wok Activities (T - 13 weeks)
I2S-7688-MP-74.CM.TP.9 | Pre- Possession Planning #5 (2/5/26 to 4/5/26) - OD changed to 96h - 16-Feb-2026 | I.GG.POS07.090 | Possession #5 - 2/5/26 to 5/5/26 - Worksite Access Programs (T - 10 Bdays)
I2S-7688-MP-74.CM.TP.9 | Pre- Possession Planning #5 (2/5/26 to 4/5/26) - OD changed to 96h - 16-Feb-2026 | I.GG.POS07.010 | Possession #5 - 2/5/26 to 5/5/26 - Track Possession Program (Draft) (T - 90 Bdays)
I2S-7688-MP-74.CM.TP.9 | Pre- Possession Planning #5 (2/5/26 to 4/5/26) - OD changed to 96h - 16-Feb-2026 | I.GG.POS07.040 | Possession #5 - 2/5/26 to 5/5/26 - Track Possession Program (Final) (T - 60 Bdays)
I2S-7688-MP-74.CM.TP.9 | Pre- Possession Planning #5 (2/5/26 to 4/5/26) - OD changed to 96h - 16-Feb-2026 | I.GG.POS07.020 | Possession #5 - 2/5/26 to 5/5/26 - Pre-agreed Track Possession Notification (T - 13 weeks)
I2S-7688-MP-74.CM.TP.9 | Pre- Possession Planning #5 (2/5/26 to 4/5/26) - OD changed to 96h - 16-Feb-2026 | I.GG.POS07.050 | Possession #5 - 2/5/26 to 5/5/26 - Works Coordination, Pre- Planning, Risk (T - 12 weeks)
I2S-7688-MP-74.CM.TP.9 | Pre- Possession Planning #5 (2/5/26 to 4/5/26) - OD changed to 96h - 16-Feb-2026 | I.GG.POS07.060 | Possession #5 - 2/5/26 to 5/5/26 - Planning, Program, Risk (T - 6 weeks)
I2S-7688-MP-74.CM.TP.9 | Pre- Possession Planning #5 (2/5/26 to 4/5/26) - OD changed to 96h - 16-Feb-2026 | I.GG.POS07.070 | Possession #5 - 2/5/26 to 5/5/26 - Finalisation, Worksite Specific Planning (T - 4 weeks)
I2S-7688-MP-74.CM.TP.9 | Pre- Possession Planning #5 (2/5/26 to 4/5/26) - OD changed to 96h - 16-Feb-2026 | I.GG.POS07.080 | Possession #5 - 2/5/26 to 5/5/26 - Review & Finalisation Meeting (T - 2 weeks)
I2S-7688-MP-74.CM.TP.9 | Pre- Possession Planning #5 (2/5/26 to 4/5/26) - OD changed to 96h - 16-Feb-2026 | I.GG.POS07.100 | Possession #5 - 2/5/26 to 5/5/26 - Pre- Possession meeting (T - 1 day) - 1/5/26
I2S-7688-MP-74.CM.TP.9 | Pre- Possession Planning #5 (2/5/26 to 4/5/26) - OD changed to 96h - 16-Feb-2026 | I.GG.POS07.110 | Possession #5 - 2/5/26 to 5/5/26 - Track Possession debrief (T + 2 weeks)
Possession #5 (2/5/26 to 4/5/26) - OD changed to 96h - 16-Feb-2026
I2S-7688-MP-74.CM.TP.10 | Possession #5 (2/5/26 to 4/5/26) - OD changed to 96h - 16-Feb-2026 | I.GG.MSTP.1240 | S2P - Possession #5 - 2/5/26 to 5/5/26 - 96 hours - Main Line - Cootamundra West to Parkes
I2S-7688-MP-74.CM.TP.10 | Possession #5 (2/5/26 to 4/5/26) - OD changed to 96h - 16-Feb-2026 | I.GG.MSTP.1250 | I2S - Possession #5 - 2/5/26 to 5/5/26 - 96 hours - Main Line - Albury to Junee
Pre- Possession Planning #6 (12/9/26 to 14/9/26) |  |  |  | 2026-05-07 | 2026-09-28
I2S-7688-MP-74.CM.TP.5 | Pre- Possession Planning #6 (12/9/26 to 14/9/26) | I.GG.POS05.030 | Possession #6 (12/9/26 to 14/9/26) - Notification of Work Activities (T - 13 weeks) | 2026-06-12 | 2026-06-12
I2S-7688-MP-74.CM.TP.5 | Pre- Possession Planning #6 (12/9/26 to 14/9/26) | I.GG.POS05.090 | Possession #6 (12/9/26 to 14/9/26) - Worksite Access Programs (T - 10 Bdays) | 2026-08-28 | 2026-08-28
I2S-7688-MP-74.CM.TP.5 | Pre- Possession Planning #6 (12/9/26 to 14/9/26) | I.GG.POS05.010 | Possession #6 (12/9/26 to 14/9/26) - Track Possession Program (Draft) (T - 90 Bdays) - 8/5/25 | 2026-05-07 | 2026-05-07
I2S-7688-MP-74.CM.TP.5 | Pre- Possession Planning #6 (12/9/26 to 14/9/26) | I.GG.POS05.040 | Possession #6 (12/9/26 to 14/9/26) - Track Possession Program (Final) (T - 60 Bdays) | 2026-06-19 | 2026-06-19
I2S-7688-MP-74.CM.TP.5 | Pre- Possession Planning #6 (12/9/26 to 14/9/26) | I.GG.POS05.020 | Possession #6 (12/9/26 to 14/9/26) - Pre-agreed Track Possession Notification (T - 13 weeks) | 2026-06-12 | 2026-06-12
I2S-7688-MP-74.CM.TP.5 | Pre- Possession Planning #6 (12/9/26 to 14/9/26) | I.GG.POS05.050 | Possession #6 (12/9/26 to 14/9/26) - Works Coordination, Pre- Planning, Risk (T - 12 weeks) | 2026-06-19 | 2026-06-19
I2S-7688-MP-74.CM.TP.5 | Pre- Possession Planning #6 (12/9/26 to 14/9/26) | I.GG.POS05.060 | Possession #6 (12/9/26 to 14/9/26) - Planning, Program, Risk (T - 6 weeks) | 2026-07-31 | 2026-07-31
I2S-7688-MP-74.CM.TP.5 | Pre- Possession Planning #6 (12/9/26 to 14/9/26) | I.GG.POS05.070 | Possession #6 (12/9/26 to 14/9/26) - Finalisation, Worksite Specific Planning (T - 4 weeks) | 2026-08-17 | 2026-08-17
I2S-7688-MP-74.CM.TP.5 | Pre- Possession Planning #6 (12/9/26 to 14/9/26) | I.GG.POS05.080 | Possession #6 (12/9/26 to 14/9/26) - Review & Finalisation Meeting (T - 2 weeks) | 2026-08-28 | 2026-08-28
I2S-7688-MP-74.CM.TP.5 | Pre- Possession Planning #6 (12/9/26 to 14/9/26) | I.GG.POS05.100 | Possession #6 (12/9/26 to 14/9/26) - Pre- Possession meeting (T - 1 day) - 10/9/26 | 2026-09-10 | 2026-09-10
I2S-7688-MP-74.CM.TP.5 | Pre- Possession Planning #6 (12/9/26 to 14/9/26) | I.GG.POS05.110 | Possession #6 (12/9/26 to 14/9/26) - Track Possession debrief (T + 2 weeks) | 2026-09-28 | 2026-09-28
I2S-7688-MP-74.CM.TP.5 | Pre- Possession Planning #6 (12/9/26 to 14/9/26) | I.GG.POS05.120 | Possession #6 (12/9/26 to 14/9/26) - CCB Gate 6 Tracker close out (T + 6 weeks)
Possession #6 (12/9/26 to 14/9/26) |  |  |  | 2026-09-12 | 2026-09-14
I2S-7688-MP-74.CM.TP.05 | Possession #6 (12/9/26 to 14/9/26) | I.GG.MSTP.1175 | I2S - Possession #6 - 12/9/26 to 14/9/26 - 60 hours - Main Line - Albury to Junee | 2026-09-12 | 2026-09-14
I2S-7688-MP-74.CM.TP.05 | Possession #6 (12/9/26 to 14/9/26) | I.GG.MSTP.1210 | S2P - Possession #6 - 12/9/26 to 14/9/26 - 60 hours - Main Line - Cootamundra West to Parkes | 2026-09-12 | 2026-09-14
Pre- Possession Planning #7 (12/3/27 to 14/3/27) |  |  |  | 2026-10-22 | 2027-03-29
I2S-7688-MP-74.CM.TP.1 | Pre- Possession Planning #7 (12/3/27 to 14/3/27) | I.GG.POS01.030 | Possession #7 (12/3/27 to 14/3/27) - Notification of Work Activities (T - 13 weeks) - 15/6/24 | 2026-11-11 | 2026-11-11
I2S-7688-MP-74.CM.TP.1 | Pre- Possession Planning #7 (12/3/27 to 14/3/27) | I.GG.POS01.090 | Possession #7 (12/3/27 to 14/3/27) - Worksite Access Programs (T - 10 Bdays) | 2027-02-26 | 2027-02-26
I2S-7688-MP-74.CM.TP.1 | Pre- Possession Planning #7 (12/3/27 to 14/3/27) | I.GG.POS01.010 | Possession #7 (12/3/27 to 14/3/27) - Track Possession Program (Draft) (T - 90 Bdays) - 22/10/26 | 2026-10-22 | 2026-10-22
I2S-7688-MP-74.CM.TP.1 | Pre- Possession Planning #7 (12/3/27 to 14/3/27) | I.GG.POS01.040 | Possession #7 (12/3/27 to 14/3/27) - Track Possession Program (Final) (T - 60 Bdays) | 2026-12-03 | 2026-12-03
I2S-7688-MP-74.CM.TP.1 | Pre- Possession Planning #7 (12/3/27 to 14/3/27) | I.GG.POS01.020 | Possession #7 (12/3/27 to 14/3/27) - Pre-agreed Track Possession Notification (T - 13 weeks) | 2026-11-11 | 2026-11-11
I2S-7688-MP-74.CM.TP.1 | Pre- Possession Planning #7 (12/3/27 to 14/3/27) | I.GG.POS01.050 | Possession #7 (12/3/27 to 14/3/27) - Works Coordination, Pre- Planning, Risk (T - 12 weeks) | 2026-12-18 | 2026-12-18
I2S-7688-MP-74.CM.TP.1 | Pre- Possession Planning #7 (12/3/27 to 14/3/27) | I.GG.POS01.060 | Possession #7 (12/3/27 to 14/3/27) - Planning, Program, Risk (T - 6 weeks) | 2027-01-29 | 2027-01-29
I2S-7688-MP-74.CM.TP.1 | Pre- Possession Planning #7 (12/3/27 to 14/3/27) | I.GG.POS01.070 | Possession #7 (12/3/27 to 14/3/27) - Finalisation, Worksite Specific Planning (T - 4 weeks) | 2027-02-12 | 2027-02-12
I2S-7688-MP-74.CM.TP.1 | Pre- Possession Planning #7 (12/3/27 to 14/3/27) | I.GG.POS01.080 | Possession #7 (12/3/27 to 14/3/27) - Review & Finalisation Meeting (T - 2 weeks) | 2027-02-26 | 2027-02-26
I2S-7688-MP-74.CM.TP.1 | Pre- Possession Planning #7 (12/3/27 to 14/3/27) | I.GG.POS01.100 | Possession #7 (12/3/27 to 14/3/27) - Pre- Possession meeting (T - 1 day) | 2027-03-11 | 2027-03-11
I2S-7688-MP-74.CM.TP.1 | Pre- Possession Planning #7 (12/3/27 to 14/3/27) | I.GG.POS01.110 | Possession #7 (12/3/27 to 14/3/27) - Track Possession debrief (T + 2 weeks) | 2027-03-29 | 2027-03-29
Possession #7 (12/3/27 to 14/3/27) |  |  |  | 2027-03-13 | 2027-03-15
I2S-7688-MP-74.CM.TP.01 | Possession #7 (12/3/27 to 14/3/27) | I.GG.MSTP.1130 | I2S - Possession #7 - 13/3/27 to 15/3/27 - 60 hours - Main Line - Albury to Junee | 2027-03-13 | 2027-03-15
I2S-7688-MP-74.CM.TP.01 | Possession #7 (12/3/27 to 14/3/27) | I.GG.MSTP.1170 | S2P- Possession #7 - 13/3/27 to 15/3/27 - 60 hours - Main Line - Cootamundra West to Parkes | 2027-03-13 | 2027-03-15
Pre- Possession Planning - Possession - Sep-2027 - (11/9/27 to 13/9/27) - T-Minus gates
I2S-7688-MP-74.CM.TP.11 | Pre- Possession Planning - Possession - Sep-2027 - (11/9/27 to 13/9/27) - T-Minus gates | I.GG.POS01.120 | Possession - Sep-2027 - (11/9/27 to 13/9/27) - Notification of Work Activities (T - 13 weeks)
I2S-7688-MP-74.CM.TP.11 | Pre- Possession Planning - Possession - Sep-2027 - (11/9/27 to 13/9/27) - T-Minus gates | I.GG.POS01.130 | Possession - Sep-2027 - (11/9/27 to 13/9/27) - Worksite Access Programs (T - 10 Bdays)
I2S-7688-MP-74.CM.TP.11 | Pre- Possession Planning - Possession - Sep-2027 - (11/9/27 to 13/9/27) - T-Minus gates | I.GG.POS01.140 | Possession - Sep-2027 - (11/9/27 to 13/9/27) - Track Possession Program (Draft) (T - 90 Bdays)
I2S-7688-MP-74.CM.TP.11 | Pre- Possession Planning - Possession - Sep-2027 - (11/9/27 to 13/9/27) - T-Minus gates | I.GG.POS01.150 | Possession - Sep-2027 - (11/9/27 to 13/9/27) - Track Possession Program (Final) (T - 60 Bdays)
I2S-7688-MP-74.CM.TP.11 | Pre- Possession Planning - Possession - Sep-2027 - (11/9/27 to 13/9/27) - T-Minus gates | I.GG.POS01.160 | Possession - Sep-2027 - (11/9/27 to 13/9/27) - Pre-agreed Track Possession Notification (T - 13 weeks)
I2S-7688-MP-74.CM.TP.11 | Pre- Possession Planning - Possession - Sep-2027 - (11/9/27 to 13/9/27) - T-Minus gates | I.GG.POS01.170 | Possession - Sep-2027 - (11/9/27 to 13/9/27) - Works Coordination, Pre- Planning, Risk (T - 12 weeks)
I2S-7688-MP-74.CM.TP.11 | Pre- Possession Planning - Possession - Sep-2027 - (11/9/27 to 13/9/27) - T-Minus gates | I.GG.POS01.180 | Possession - Sep-2027 - (11/9/27 to 13/9/27) - Planning, Program, Risk (T - 6 weeks)
I2S-7688-MP-74.CM.TP.11 | Pre- Possession Planning - Possession - Sep-2027 - (11/9/27 to 13/9/27) - T-Minus gates | I.GG.POS01.190 | Possession - Sep-2027 - (11/9/27 to 13/9/27) - Finalisation, Worksite Specific Planning (T - 4 weeks)
I2S-7688-MP-74.CM.TP.11 | Pre- Possession Planning - Possession - Sep-2027 - (11/9/27 to 13/9/27) - T-Minus gates | I.GG.POS01.200 | Possession - Sep-2027 - (11/9/27 to 13/9/27) - Review & Finalisation Meeting (T - 2 weeks)
I2S-7688-MP-74.CM.TP.11 | Pre- Possession Planning - Possession - Sep-2027 - (11/9/27 to 13/9/27) - T-Minus gates | I.GG.POS01.210 | Possession - Sep-2027 - (11/9/27 to 13/9/27) - Pre- Possession meeting (T - 1 day)
I2S-7688-MP-74.CM.TP.11 | Pre- Possession Planning - Possession - Sep-2027 - (11/9/27 to 13/9/27) - T-Minus gates | I.GG.POS01.220 | Possession - Sep-2027 - (11/9/27 to 13/9/27) - Track Possession debrief (T + 2 weeks)
I2S-7688-MP-74.CM.TP.11 | Pre- Possession Planning - Possession - Sep-2027 - (11/9/27 to 13/9/27) - T-Minus gates | I.GG.POS01.230 | Possession - Sep-2027 - (11/9/27 to 13/9/27) - CCB Gate 6 Tracker close out (T + 6 weeks)
Possession - Sep-2027 - (11/9/27 to 13/9/27)
I2S-7688-MP-74.CM.TP.12 | Possession - Sep-2027 - (11/9/27 to 13/9/27) | I.GG.MSTP.1260 | Possession - Sep-2027 - (11/9/27 to 13/9/27) - I2S and S2P - Main Line works - 60 hours
ISC Rating Process - Key Sustainability Milestone Dates |  |  |  | 2024-10-01 | 2025-03-18
Registration |  |  |  | 2024-10-01 | 2024-10-22
I2S-7688-MP-74.CM.IS.1 | Registration | I.GG.MR.ISC.1010 | ISC - Reg - Completion of IS Rating Agreement | 2024-10-09 | 2024-10-15
I2S-7688-MP-74.CM.IS.1 | Registration | I.GG.MR.ISC.1020 | ISC - Reg - Completion of Project Detail Form | 2024-10-16 | 2024-10-22
I2S-7688-MP-74.CM.IS.1 | Registration | I.GG.MR.ISC.1000 | ISC - Reg - Registration of Interest with ISC | 2024-10-01 | 2024-10-08
Assessment |  |  |  | 2024-11-19 | 2025-03-17
I2S-7688-MP-74.CM.IS.2 | Assessment | I.GG.MR.ISC.1290 | ISC - Assess - Construction ready sustainability awareness session (30 B.days prior to construction start) | 2025-03-11 | 2025-03-17
I2S-7688-MP-74.CM.IS.2 | Assessment | I.GG.MR.ISC.1300 | ISC - Assess - Climate Change Workshop
I2S-7688-MP-74.CM.IS.2 | Assessment | I.GG.MR.ISC.1040 | ISC - Assess - Sustainability Kick-off workshop - Within 90 days of the commencement date | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.CM.IS.2 | Assessment | I.GG.MR.ISC.1050 | ISC - Assess - Sustainability Management Plan / SuMP - 30 days from contract award | 2024-11-19
I2S-7688-MP-74.CM.IS.2 | Assessment | I.GG.MR.ISC.1060 | ISC - Assess - Verifier appointment | 2024-11-19 | 2024-11-25
I2S-7688-MP-74.CM.IS.2 | Assessment | I.GG.MR.ISC.1070 | ISC - Assess - ISC Weightings assessment and report - Within 100 B.days following commencement date | 2024-11-26 | 2024-12-09
Base Case Submission
I2S-7688-MP-74.CM.IS.2.1 | Base Case Submission | I.GG.MR.ISC.1320 | ISC - Base Case - Submission - JH Develop BCP
I2S-7688-MP-74.CM.IS.2.1 | Base Case Submission | I.GG.MR.ISC.1330 | ISC - Base Case - IRPL Review BCP and JH updates as required
I2S-7688-MP-74.CM.IS.2.1 | Base Case Submission | I.GG.MR.ISC.1340 | ISC - Base Case - IRPL Submit BCP to IS Council and IS Council Verify
I2S-7688-MP-74.CM.IS.2.1 | Base Case Submission | I.GG.MR.ISC.1350 | ISC - Base Case - JH Updates as required and resubmit to IS Council
I2S-7688-MP-74.CM.IS.2.1 | Base Case Submission | I.GG.MR.ISC.1360 | ISC - Base Case - BCP is verified by IS Council
Ongoing Audits / Meetings |  |  |  | 2025-01-20 | 2025-03-18
I2S-7688-MP-74.CM.IS.5 | Ongoing Audits / Meetings | I.GG.MR.ISC.1190 | ISC - Audit - Quarterly ISP reviews and reporting | 2025-02-11 | 2025-02-11
I2S-7688-MP-74.CM.IS.5 | Ongoing Audits / Meetings | I.GG.MR.ISC.1200 | ISC - Audit - Internal and external inspections and audits | 2025-03-18 | 2025-03-18
I2S-7688-MP-74.CM.IS.5 | Ongoing Audits / Meetings | I.GG.MR.ISC.1210 | ISC - Audit - External Annual Sustainability Audit | 2025-01-20 | 2025-01-20
I2S-7688-MP-74.CM.IS.5 | Ongoing Audits / Meetings | I.GG.MR.ISC.1220 | ISC - Audit - Annual Independent stakeholder review/audit | 2025-02-12 | 2025-02-12
Verification
ISC Design Round 1 Submission
I2S-7688-MP-74.CM.IS.3.1 | ISC Design Round 1 Submission | I.GG.MR.ISC.1370 | ISC Design - R1 - Submission - JH Prepare ISC Design Submission R1
I2S-7688-MP-74.CM.IS.3.1 | ISC Design Round 1 Submission | I.GG.MR.ISC.1380 | ISC Design - R1 - Submission - IRPL Review DR1 and JH Updates as required
I2S-7688-MP-74.CM.IS.3.1 | ISC Design Round 1 Submission | I.GG.MR.ISC.1390 | ISC Design - R1 - Submission - IRPL Submit DR1 to IS Council and IS Council Verify
I2S-7688-MP-74.CM.IS.3.1 | ISC Design Round 1 Submission | I.GG.MR.ISC.1410 | ISC Design - R1 - Submission - DR1 is verified by IS Council
ISC Design Round 2 Submission
I2S-7688-MP-74.CM.IS.3.2 | ISC Design Round 2 Submission | I.GG.MR.ISC.1520 | ISC Design - R2 - Submission - JH Prepare ISC Design Submission R2
I2S-7688-MP-74.CM.IS.3.2 | ISC Design Round 2 Submission | I.GG.MR.ISC.1530 | ISC Design - R2 - Submission - IRPL Review DR2 and JH Updates as required
I2S-7688-MP-74.CM.IS.3.2 | ISC Design Round 2 Submission | I.GG.MR.ISC.1540 | ISC Design - R2 - Submission - IRPL Submit DR2 to IS Council and IS Council Verify
I2S-7688-MP-74.CM.IS.3.2 | ISC Design Round 2 Submission | I.GG.MR.ISC.1550 | ISC Design - R2 - Submission - JH Appeals / Meetings
I2S-7688-MP-74.CM.IS.3.2 | ISC Design Round 2 Submission | I.GG.MR.ISC.1560 | ISC Design - R2 - Submission - DR2 is Verification / Certification by IS Council
ISC As-built
ISC As-built Round 1 Submission
I2S-7688-MP-74.CM.IS.6.2 | ISC As-built Round 1 Submission | I.GG.MR.ISC.1470 | ISC As-built - R1 - Submission - JH Prepare ISC As built Submission R1
I2S-7688-MP-74.CM.IS.6.2 | ISC As-built Round 1 Submission | I.GG.MR.ISC.1480 | ISC As-built - R1 - Submission - IRPL Review As built R1 and JH Updates as required
I2S-7688-MP-74.CM.IS.6.2 | ISC As-built Round 1 Submission | I.GG.MR.ISC.1490 | ISC As-built - R1 - Submission - IRPL Submit As built R1 to IS Council and IS Council Verify
I2S-7688-MP-74.CM.IS.6.2 | ISC As-built Round 1 Submission | I.GG.MR.ISC.1500 | ISC As-built - R1 - Submission - As built R1 is verified by IS Council
Design and Engineering |  |  |  | 2024-09-30 | 2027-04-08
Key Dates |  |  |  | 2025-11-24 | 2025-11-24
I2S-7688-MP-74.D.1 | Key Dates | I.DE.95.8000 | DSN - I2S Detailed Design/Procurement (HO) complete target date |  | 2025-11-24
Design Stage 1 - Feasibility Design - FDD - Milestones
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10170 | DSN - FDD Package Complete - H3 - Dirnaseer Road Underbridge
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10180 | DSN - FDD Package Complete - H4 - Isobel Creek Underbridge
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10190 | DSN - FDD Package Complete - H5 - Isobel Creek Tributary Underbridge
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10200 | DSN - FDD Package Complete - H6 - Billabong Creek Underbridge
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10210 | DSN - FDD Package Complete - H7 - Powder Horn Creek Underbridges
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10230 | DSN - FDD Package Complete - H9 - Dudauman Creek Underbridge
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10240 | DSN - FDD Package Complete - L1 - Stock Underpasses and Miscellaneous Structures
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10250 | DSN - FDD Package Complete - L2 - Maintenance Responsibility Plans
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10260 | DSN - FDD Package Complete - L3 - Maintenance Access and RMAR
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10030 | DSN - FDD Package Complete - D7 - Geotechnical and Hydrogeological Interpretative Report
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10040 | DSN - FDD Package Complete - D8 - Geotechnical Monitoring
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10050 | DSN - FDD Package Complete - D9 - Flood Assessment
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10060 | DSN - FDD Package Complete - E1 - Rail Track, Earthworks and Formation
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10270 | DSN - FDD Package Complete - L4 - Rail Systems Civil Works
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10280 | DSN - FDD Package Complete - L5 - Landscape
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10290 | DSN - FDD Package Complete - L6 - Fencing and Security
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10300 | DSN - FDD Package Complete - L7 - Corridor Signage
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10310 | DSN - FDD Package Complete - L8 - Utilities - Coordination Packs (For Information only)
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10320 | DSN - FDD Package Complete - M1 - Roads - Public (Junee Shire Council)
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10330 | DSN - FDD Package Complete - M2 - Roads - Public (Cootamundra-Gundagai Regional Council)
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10340 | DSN - FDD Package Complete - M3 - Public (TfNSW)
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.11490 | DSN - FDD - All FDD Packages Complete
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10070 | DSN - FDD Package Complete - E2 - LXs (Public - Junee Shire Council)
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10080 | DSN - FDD Package Complete - E3 - LXs (Public - Cootamundra-Gundagai Regional Council)
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10090 | DSN - FDD Package Complete - E4 - LXs General
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10100 | DSN - FDD Package Complete - E5 - LXs (Public - Crown)
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10110 | DSN - FDD Package Complete - E6 - LXs (Private)
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10120 | DSN - FDD Package Complete - E7 - Drainage
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10130 | DSN - FDD Package Complete - E8 - Burley Griffin Way Overbridge
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10140 | DSN - FDD Package Complete - E9 - Old Cootamundra Road Underbridge
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10150 | DSN - FDD Package Complete - H1 - Ulandra Creek Underbridge
I2S-7688-MP-74.D.1.1 | Design Stage 1 - Feasibility Design - FDD - Milestones | I.DE.00.10160 | DSN - FDD Package Complete - H2 - Run Boundary Creek Underbridge
Design Stage 2 - Preliminary Design - PDD - Milestones
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10440 | DSN - PDD Package Complete - E1 - Rail Track, Earthworks and Formation
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10450 | DSN - PDD Package Complete - E2 - LXs (Public - Junee Shire Council)
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10460 | DSN - PDD Package Complete - E3 - LXs (Public - Cootamundra-Gundagai Regional Council)
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10470 | DSN - PDD Package Complete - E4 - LXs General
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10480 | DSN - PDD Package Complete - E5 - LXs (Public - Crown)
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10490 | DSN - PDD Package Complete - E6 - LXs (Private)
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10500 | DSN - PDD Package Complete - E7 - Drainage
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10510 | DSN - PDD Package Complete - E8 - Burley Griffin Way Overbridge
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10520 | DSN - PDD Package Complete - E9 - Old Cootamundra Road Underbridge
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10530 | DSN - PDD Package Complete - H1 - Ulandra Creek Underbridge
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10540 | DSN - PDD Package Complete - H2 - Run Boundary Creek Underbridge
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10550 | DSN - PDD Package Complete - H3 - Dirnaseer Road Underbridge
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10560 | DSN - PDD Package Complete - H4 - Isobel Creek Underbridge
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10570 | DSN - PDD Package Complete - H5 - Isobel Creek Tributary Underbridge
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10580 | DSN - PDD Package Complete - H6 - Billabong Creek Underbridge
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10590 | DSN - PDD Package Complete - H7 - Powder Horn Creek Underbridges
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10610 | DSN - PDD Package Complete - H9 - Dudauman Creek Underbridge
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10620 | DSN - PDD Package Complete - L1 - Stock Underpasses and Miscellaneous Structures
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10640 | DSN - PDD Package Complete - L3 - Maintenance Access and RMAR
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10650 | DSN - PDD Package Complete - L4 - Rail Systems Civil Works
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10670 | DSN - PDD Package Complete - L6 - Fencing and Security
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10680 | DSN - PDD Package Complete - L7 - Corridor Signage
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10690 | DSN - PDD Package Complete - L8 - Utilities - Coordination Packs (For Information only)
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10700 | DSN - PDD Package Complete - M1 - Roads - Public (Junee Shire Council)
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10710 | DSN - PDD Package Complete - M2 - Roads - Public (Cootamundra-Gundagai Regional Council)
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.10720 | DSN - PDD Package Complete - M3 - Public (TfNSW)
I2S-7688-MP-74.D.1.2 | Design Stage 2 - Preliminary Design - PDD - Milestones | I.DE.00.11500 | DSN - PDD - All PDD Packages Complete
Design Stage 3 - Detailed Design - DDD - Milestones
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.12060 | DSN - DDD Package - Complete L2 - Corridor (Maintenance Responsiblity Plans)
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.12070 | DSN - DDD Package - Complete D9 -Flood Assessment
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.11090 | DSN - DDD Package - Complete M2 - Roads - Public (Cootamundra-Gundagai Regional Council)
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.11100 | DSN - DDD Package Complete - M3 - Public (TfNSW)
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.11510 | DSN - DDD - All DDD Packages Complete
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10750 | DSN - DDD Package - Complete D3 - Signalling Plan
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10760 | DSN - DDD Package - Complete D4 - Control Tables
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10770 | DSN - DDD Package Complete - D5 - Circuit Books
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10780 | DSN - DDD Package Complete - D6 - Microlok Data
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10790 | DSN - DDD Package - Complete D7 - Geotechnical and Hydrogeological Interpretative Report
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10800 | DSN - DDD Package - Complete D8 - Geotechnical Monitoring
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10820 | DSN - DDD Package - Complete E1 - Rail Track, Earthworks and Formation
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10830 | DSN - DDD Package - Complete E2 - LXs (Public - Junee Shire Council)
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10840 | DSN - DDD Package - Complete E3 - LXs (Public - Cootamundra-Gundagai Regional Council)
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10850 | DSN - DDD Package - Complete E4 - LXs General
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10860 | DSN - DDD Package - Complete E5 - LXs (Public - Crown)
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10870 | DSN - DDD Package - Complete E6 - LXs (Private)
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10880 | DSN - DDD Package Complete - E7 - Drainage
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10890 | DSN - DDD Package Complete - E8 - Burley Griffin Way Overbridge
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10900 | DSN - DDD Package - Complete E9 - Old Cootamundra Road Underbridge
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10910 | DSN - DDD Package - Complete H1 - Ulandra Creek Underbridge
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10920 | DSN - DDD Package - Complete H2 - Run Boundary Creek Underbridge
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10930 | DSN - DDD Package - Complete H3 - Dirnaseer Road Underbridge
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.11060 | DSN - DDD Package Complete - L7 - Corridor Signage
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.11070 | DSN - DDD Package - Complete L8 - Utilities - Coordination Packs (For Information only)
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10960 | DSN - DDD Package - Complete H6 - Billabong Creek Underbridge
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.11080 | DSN - DDD Package - Complete M1 - Roads - Public (Junee Shire Council)
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10940 | DSN - DDD Package - Complete H4 - Isobel Creek Underbridge
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.11000 | DSN - DDD Package - Complete L1 - Stock Underpasses and Miscellaneous Structures
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10950 | DSN - DDD Package - Complete H5 - Isobel Creek Tributary Underbridge
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10970 | DSN - DDD Package - Complete H7 - Powder Horn Creek Underbridges
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.10990 | DSN - DDD Package - Complete H9 - Dudauman Creek Underbridge
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.11020 | DSN - DDD Package Complete - L3 - Maintenance Access and RMAR
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.11030 | DSN - DDD Package - Complete L4 - Rail Systems Civil Works
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.11040 | DSN - DDD Package Complete - L5 - Landscape
I2S-7688-MP-74.D.1.3 | Design Stage 3 - Detailed Design - DDD - Milestones | I.DE.00.11050 | DSN - DDD Package - Complete L6 - Fencing and Security
Design Stage 4 - Issue For Construction - IFC - Milestones
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11120 | DSN - IFC Package - Complete D2 - Signalling Functional Specification (SFS)
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11130 | DSN - IFC Package - Complete D3 - Signalling Plan
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11140 | DSN - IFC Package - Complete D4 - Control Tables
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11150 | DSN - IFC Package - Complete D5 - Circuit Books
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11160 | DSN - IFC Package - Complete D6 - Microlok Data
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11170 | DSN - IFC Package - Complete D7 - Geotechnical and Hydrogeological Interpretative Report
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11180 | DSN - IFC Package - Complete D8 - Geotechnical Monitoring
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11190 | DSN - IFC Package - Complete D9 - Flood Assessment
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11200 | DSN - IFC Package - Complete E1 - Rail Track, Earthworks and Formation
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11210 | DSN - IFC Package - Complete E2 - LXs (Public - Junee Shire Council)
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11220 | DSN - IFC Package - Complete E3 - LXs (Public - Cootamundra-Gundagai Regional Council)
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11230 | DSN - IFC Package - Complete E4 - LXs General
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11240 | DSN - IFC Package - Complete E5 - LXs (Public - Crown)
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11250 | DSN - IFC Package - Complete E6 - LXs (Private)
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11260 | DSN - IFC Package - Complete E7 - Drainage
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11270 | DSN - IFC Package - Complete E8 - Burley Griffin Way Overbridge
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11280 | DSN - IFC Package - Complete E9 - Old Cootamundra Road Underbridge
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11290 | DSN - IFC Package - Complete H1 - Ulandra Creek Underbridge
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11300 | DSN - IFC Package - Complete H2 - Run Boundary Creek Underbridge
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11310 | DSN - IFC Package - Complete H3 - Dirnaseer Road Underbridge
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11320 | DSN - IFC Package - Complete H4 - Isobel Creek Underbridge
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11370 | DSN - IFC Package - Complete H9 - Dudauman Creek Underbridge
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11330 | DSN - IFC Package - Complete H5 - Isobel Creek Tributary Underbridge
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11340 | DSN - IFC Package - Complete H6 - Billabong Creek Underbridge
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11350 | DSN - IFC Package - Complete H7 - Powder Horn Creek Underbridges
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11380 | DSN - IFC Package - Complete L1 - Stock Underpasses and Miscellaneous Structures
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11390 | DSN - IFC Package - Complete L2 - Maintenance Responsibility Plans
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11400 | DSN - IFC Package - Complete L3 - Maintenance Access and RMAR
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11410 | DSN - IFC Package - Complete L4 - Rail Systems Civil Works
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11420 | DSN - IFC Package - Complete L5 - Landscape
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11430 | DSN - IFC Package - Complete L6 - Fencing and Security
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11440 | DSN - IFC Package - Complete L7 - Corridor Signage
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11450 | DSN - IFC Package - Complete L8 - Utilities - Coordination Packs (For Information only)
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11460 | DSN - IFC Package - Complete M1 - Roads - Public (Junee Shire Council)
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11470 | DSN - IFC Package - Complete M2 - Roads - Public (Cootamundra-Gundagai Regional Council)
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11480 | DSN - IFC Package - Complete M3 - Public (TfNSW)
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11520 | DSN - IFC Packages - All IFC packages Complete
I2S-7688-MP-74.D.1.4 | Design Stage 4 - Issue For Construction - IFC - Milestones | I.DE.00.11110 | DSN - IFC Package - Complete D1 - Operational Specification Technical Addendum
Initial Contract start up Works - General |  |  |  | 2024-09-30 | 2025-01-14
Start up and work shops |  |  |  | 2024-09-30 | 2024-10-29
I2S-7688-MP-74.D.6.5 | Start up and work shops | I.GG.14820 | DSN - I2S Project start-up meeting | 2024-09-30 | 2024-09-30
I2S-7688-MP-74.D.6.5 | Start up and work shops | I.GG.14870 | DSN - Project Delivery Alignment start-up workshop | 2024-10-29 | 2024-10-29
I2S-7688-MP-74.D.6.5 | Start up and work shops | I.GG.15290 | DSN - JH Review other proponents IP | 2024-10-03 | 2024-10-08
I2S-7688-MP-74.D.6.5 | Start up and work shops | I.GG.15450 | DSN - Gap Analysis and Survey Brief (incl Utilities) for LIW Approval | 2024-10-02 | 2024-10-16
I2S-7688-MP-74.D.6.5 | Start up and work shops | I.DE.95.1020 | DSN - Design Team / Subcontractors Mobilised | 2024-10-02 | 2024-10-02
I2S-7688-MP-74.D.6.5 | Start up and work shops | I.DE.95.1000 | DSN - Consultant Service Agreement (CSA) between JH/Pitt & Sherry Signed | 2024-09-30 | 2024-09-30
I2S-7688-MP-74.D.6.5 | Start up and work shops | I.GG.15410 | DSN - Pitt & Sherry Design Management Plan (DMP) | 2024-10-02 | 2024-10-16
I2S-7688-MP-74.D.6.5 | Start up and work shops | I.GG.15420 | DSN - Develop and Submit Digital Execution Plan (DEXP) | 2024-10-02 | 2024-10-18
I2S-7688-MP-74.D.6.5 | Start up and work shops | I.GG.15430 | DSN - JH team mobilsation | 2024-09-30 | 2024-10-01
Safety |  |  |  | 2024-09-30 | 2025-01-14
I2S-7688-MP-74.D.6.3 | Safety | I.GG.15700 | DSN - Construction Risk Assessment / Safety workshop (safety culture/ risk and alignment) for Delivery | 2025-01-14 | 2025-01-14
I2S-7688-MP-74.D.6.3 | Safety | I.GG.14860 | DSN - Early Works Construction Risk Assessment / Safety Workshop with IRPL (safety culture/ risk and alignment) for LIW | 2024-10-22 | 2024-10-28
I2S-7688-MP-74.D.6.3 | Safety | I.GG.15710 | DSN - Develop Early Works Safety Management Plan | 2024-09-30 | 2024-10-21
I2S-7688-MP-74.D.6.3 | Safety | I.GG.15720 | DSN - IRPL review and approval of EW Safety Management Plan | 2024-10-22 | 2024-11-18
Set-up /HR |  |  |  | 2024-10-01 | 2024-10-22
I2S-7688-MP-74.D.6.4 | Set-up /HR | I.GG.14830 | DSN - HR/ Employee Relation start-up meeting | 2024-10-01 | 2024-10-01
I2S-7688-MP-74.D.6.4 | Set-up /HR | I.GG.14900 | DSN - Consultation/co-ordination meetings with regulatory authorities | 2024-10-01 | 2024-10-01
I2S-7688-MP-74.D.6.4 | Set-up /HR | I.GG.15200 | DSN - Early Access Request Pack | 2024-10-01 | 2024-10-22
Insurances and Bonds.Bank Guarantees |  |  |  | 2024-09-30 | 2024-10-01
I2S-7688-MP-74.D.6.2 | Insurances and Bonds.Bank Guarantees | I.GG.14880 | DSN - Compile insurances and submit to IRPL | 2024-09-30 | 2024-09-30
I2S-7688-MP-74.D.6.2 | Insurances and Bonds.Bank Guarantees | I.GG.14890 | DSN - Prepare bonds/bank guarantees and submit to IRPL | 2024-10-01 | 2024-10-01
Initial Contract start up Works - Design |  |  |  | 2024-10-02 | 2025-02-27
Geotech |  |  |  | 2024-10-02 | 2025-02-27
I2S-7688-MP-74.D.4.6 | Geotech | I.GG.16230 | DSN - GE-03 - Geotechnical and Hydrogeological Interpretative Report (GHIR) - Final | 2025-01-16 | 2025-02-27
I2S-7688-MP-74.D.4.6 | Geotech | I.GG.16250 | DSN - GE-01 - Geotechnical and Site Investigation/Survey Plan (GIP) - Final Issue | 2024-11-07 | 2024-12-11
I2S-7688-MP-74.D.4.6 | Geotech | I.GG.15490 | DSN - GE-01 - Geotechnical and Site Investigation/Survey Plan (GIP) - 1st Issue | 2024-10-02 | 2024-11-06
I2S-7688-MP-74.D.4.6 | Geotech | I.GG.15520 | DSN - GE-02 - Geotechnical and Site Investigations Factual Report (GFR) - 1st Issue | 2024-11-21 | 2025-01-15
I2S-7688-MP-74.D.4.6 | Geotech | I.GG.15530 | DSN - L9 - GE-02 - Geotechnical and Site Investigations Factual Report (GFR) - Final Issue | 2025-01-16 | 2025-02-27
I2S-7688-MP-74.D.4.6 | Geotech | I.GG.15560 | DSN - GE-03 - Geotechnical and Hydrogeological Interpretative Report (GHIR) - 1st Issue | 2024-10-25 | 2024-12-05
Flooding |  |  |  | 2024-12-11 | 2025-01-23
I2S-7688-MP-74.D.4.5 | Flooding | I.GG.15210 | DSN - Commence Flood Modelling with certainty (post ETV review) | 2025-01-23 | 2025-01-23
I2S-7688-MP-74.D.4.5 | Flooding | I.GG.15580 | DSN - Develop Hydraulic Model and review Culvert designs | 2024-12-11 | 2025-01-21
Design Packages |  |  |  | 2024-10-02 | 2024-11-06
I2S-7688-MP-74.D.4.3 | Design Packages | I.GG.16210 | DSN - DU-01 - Durability Report | 2024-10-02 | 2024-11-06
I2S-7688-MP-74.D.4.3 | Design Packages | I.GG.16240 | DSN - TR-01 - Maintenance Responsibility Plan | 2024-10-02 | 2024-11-06
I2S-7688-MP-74.D.4.3 | Design Packages | I.GG.15600 | DSN - MGA94 - MGA 2020 (all design packages) Conversion | 2024-10-02 | 2024-10-23
I2S-7688-MP-74.D.4.3 | Design Packages | I.GG.15610 | DSN - Setting up workflows (for DEXP) - Project wise | 2024-10-02 | 2024-10-23
I2S-7688-MP-74.D.4.3 | Design Packages | I.GG.15620 | DSN - Set up drawings | 2024-10-17 | 2024-10-23
I2S-7688-MP-74.D.4.3 | Design Packages | I.GG.16180 | DSN - UT-01 - Utility and Rail Investigation/Survey Plan | 2024-10-02 | 2024-11-06
Project Wide Design |  |  |  | 2024-09-30 | 2025-11-03
Design Package D1 - Operational spec -D1 - Rail Systems (Operational Specfication ) (Was W.01 |  |  |  | 2024-10-02 | 2024-11-29
I2S-7688-MP-74.D.W.15 | Design Package D1 - Operational spec -D1 - Rail Systems (Operational Specfication ) (Was W.01 | I.GG.16190 | DSN - D1 - Rail Sys - Operational Spec - Produce O/S addendum draft | 2024-10-02 | 2024-10-02
I2S-7688-MP-74.D.W.15 | Design Package D1 - Operational spec -D1 - Rail Systems (Operational Specfication ) (Was W.01 | I.GG.16200 | DSN - D1 - Rail Sys - Operational Spec - IRPL draft review and comment | 2024-10-03 | 2024-10-10
I2S-7688-MP-74.D.W.15 | Design Package D1 - Operational spec -D1 - Rail Systems (Operational Specfication ) (Was W.01 | I.GG.16220 | DSN - D1 - Rail Sys - Operational Spec - Update draft and Produce O/S addendum final | 2024-10-11 | 2024-10-24
I2S-7688-MP-74.D.W.15 | Design Package D1 - Operational spec -D1 - Rail Systems (Operational Specfication ) (Was W.01 | I.GG.16260 | DSN - D1 - Rail Sys - Operational Spec - Check O/S addendum | 2024-10-25 | 2024-10-28
I2S-7688-MP-74.D.W.15 | Design Package D1 - Operational spec -D1 - Rail Systems (Operational Specfication ) (Was W.01 | I.GG.16270 | DSN - D1 - Rail Sys - Operational Spec - Verify O/S addendum | 2024-10-29 | 2024-10-29
I2S-7688-MP-74.D.W.15 | Design Package D1 - Operational spec -D1 - Rail Systems (Operational Specfication ) (Was W.01 | I.GG.16280 | DSN - D1 - Rail Sys - Operational Spec - Issue to IRPL | 2024-10-30 | 2024-10-30
I2S-7688-MP-74.D.W.15 | Design Package D1 - Operational spec -D1 - Rail Systems (Operational Specfication ) (Was W.01 | I.GG.16290 | DSN - D1 - Rail Sys - Operational Spec - IRPL review period | 2024-10-31 | 2024-11-26
I2S-7688-MP-74.D.W.15 | Design Package D1 - Operational spec -D1 - Rail Systems (Operational Specfication ) (Was W.01 | I.GG.16300 | DSN - D1 - Rail Sys - Operational Spec - O/S returned to JH with comments | 2024-11-27 | 2024-11-27
I2S-7688-MP-74.D.W.15 | Design Package D1 - Operational spec -D1 - Rail Systems (Operational Specfication ) (Was W.01 | I.GG.16310 | DSN - D1 - Rail Sys - Operational Spec - Update comments/check | 2024-11-28 | 2024-11-28
I2S-7688-MP-74.D.W.15 | Design Package D1 - Operational spec -D1 - Rail Systems (Operational Specfication ) (Was W.01 | I.GG.16320 | DSN - D1 - Rail Sys - Operational Spec - IRPL approve O/S | 2024-11-29 | 2024-11-29
Design Package D2 - Initial Design - D2 - Rail Systems (SFS) (Was W.01 |  |  |  | 2024-10-25 | 2025-03-20
I2S-7688-MP-74.D.W.16 | Design Package D2 - Initial Design - D2 - Rail Systems (SFS) (Was W.01 | I.GG.15940 | DSN - D2 - Rail Sys - SFS - CBI I/O List | 2024-11-19 | 2024-11-21
I2S-7688-MP-74.D.W.16 | Design Package D2 - Initial Design - D2 - Rail Systems (SFS) (Was W.01 | I.GG.15950 | DSN - D2 - Rail Sys - SFS - Communication Architecture | 2024-11-22 | 2024-11-26
I2S-7688-MP-74.D.W.16 | Design Package D2 - Initial Design - D2 - Rail Systems (SFS) (Was W.01 | I.GG.15960 | DSN - D2 - Rail Sys - SFS - Stage Works Diagram | 2024-11-27 | 2024-11-29
I2S-7688-MP-74.D.W.16 | Design Package D2 - Initial Design - D2 - Rail Systems (SFS) (Was W.01 | I.GG.15970 | DSN - D2 - Rail Sys - SFS - SFS Report | 2024-12-02 | 2024-12-13
I2S-7688-MP-74.D.W.16 | Design Package D2 - Initial Design - D2 - Rail Systems (SFS) (Was W.01 | I.GG.15880 | DSN - D2 - Rail Sys - SFS - Signalling Plan for SFS | 2024-10-25 | 2024-10-28
I2S-7688-MP-74.D.W.16 | Design Package D2 - Initial Design - D2 - Rail Systems (SFS) (Was W.01 | I.GG.15890 | DSN - D2 - Rail Sys - SFS - Braking Calculations | 2024-10-29 | 2024-10-31
I2S-7688-MP-74.D.W.16 | Design Package D2 - Initial Design - D2 - Rail Systems (SFS) (Was W.01 | I.GG.15900 | DSN - D2 - Rail Sys - SFS - Power Calculations | 2024-11-01 | 2024-11-07
I2S-7688-MP-74.D.W.16 | Design Package D2 - Initial Design - D2 - Rail Systems (SFS) (Was W.01 | I.GG.15910 | DSN - D2 - Rail Sys - SFS - Power Schematics | 2024-11-08 | 2024-11-11
I2S-7688-MP-74.D.W.16 | Design Package D2 - Initial Design - D2 - Rail Systems (SFS) (Was W.01 | I.GG.15920 | DSN - D2 - Rail Sys - SFS - Aspect Sequence Chart | 2024-11-12 | 2024-11-13
I2S-7688-MP-74.D.W.16 | Design Package D2 - Initial Design - D2 - Rail Systems (SFS) (Was W.01 | I.GG.15930 | DSN - D2 - Rail Sys - SFS - CBI Architecture | 2024-11-14 | 2024-11-18
Internal Review |  |  |  | 2025-01-16 | 2025-02-03
I2S-7688-MP-74.D.W.16.3 | Internal Review | I.GG.15980 | DSN - D2 - Rail Sys - SFS - Internal Review - Issue SFS for INternal Review (P&S, JH) | 2025-01-16 | 2025-01-16
I2S-7688-MP-74.D.W.16.3 | Internal Review | I.GG.15990 | DSN - D2 - Rail Sys - SFS - Internal Review - IDR Review | 2025-01-17 | 2025-01-23
I2S-7688-MP-74.D.W.16.3 | Internal Review | I.GG.16000 | DSN - D2 - Rail Sys - SFS - Internal Review - IDR Review Workshop | 2025-01-24 | 2025-01-24
I2S-7688-MP-74.D.W.16.3 | Internal Review | I.GG.16010 | DSN - D2 - Rail Sys - SFS - Internal Review - Update to IR Comments | 2025-01-28 | 2025-02-03
Stakeholder Consultation |  |  |  | 2025-02-04 | 2025-03-19
I2S-7688-MP-74.D.W.16.4 | Stakeholder Consultation | I.GG.16020 | DSN - D2 - Rail Sys - SFS - S.Consult - Issue SFS for Review (IRPL) | 2025-02-04 | 2025-02-04
I2S-7688-MP-74.D.W.16.4 | Stakeholder Consultation | I.GG.16030 | DSN - D2 - Rail Sys - SFS - S.Consult - IRPL Review (20 B.days) | 2025-02-05 | 2025-03-04
I2S-7688-MP-74.D.W.16.4 | Stakeholder Consultation | I.GG.16040 | DSN - D2 - Rail Sys - SFS - S.Consult - Review Workshop | 2025-03-05 | 2025-03-05
I2S-7688-MP-74.D.W.16.4 | Stakeholder Consultation | I.GG.16050 | DSN - D2 - Rail Sys - SFS - S.Consult - Update SFS to comments | 2025-03-06 | 2025-03-19
Approved SFS -D2 |  |  |  | 2025-03-20 | 2025-03-20
I2S-7688-MP-74.D.W.16.5 | Approved SFS -D2 | I.GG.16060 | DSN - D2 - Rail Sys - SFS - Appoval - Issue Approved SFS | 2025-03-20 | 2025-03-20
I2S-7688-MP-74.D.W.16.5 | Approved SFS -D2 | Cost-IFC-D2 | DSN - D2 - Rail Sys - SFS - Appoval - Cost IFC
Design Package D3 - RS-01- Rail Systems (Signalling Plan) (Was W.01) |  |  |  | 2024-09-30 | 2025-08-12
Detailed out Feasibility - Preiminary Design Stage (FDD + PDD) 18 weeks |  |  |  | 2024-09-30 | 2025-03-20
I2S-7688-MP-74.D.W.2.7 | Detailed out Feasibility - Preiminary Design Stage (FDD + PDD) 18 weeks | I.DE.00.9690 | DSN - D3 - Signalling Design FDD+DDD to compare (approx 18 weeks) - LOE | 2024-10-25 | 2025-03-20
Signalling Plan - D3 |  |  |  | 2024-09-30 | 2024-10-08
I2S-7688-MP-74.D.W.2.7.6 | Signalling Plan - D3 | I.GG.16400 | DSN - D3 - Rail Sys - Sig Plan - Site Signal Correlation - IIlabo
I2S-7688-MP-74.D.W.2.7.6 | Signalling Plan - D3 | I.GG.15630 | DSN - D3 - Rail Sys - Sig Plan - Request Circuit Books for tie-in areas from IRPL | 2024-09-30 | 2024-10-01
I2S-7688-MP-74.D.W.2.7.6 | Signalling Plan - D3 | I.GG.16110 | DSN - D3 - Rail Sys - Sig Plan - Site Signal Correlation - Stockinbingal | 2024-10-02 | 2024-10-03
I2S-7688-MP-74.D.W.2.7.6 | Signalling Plan - D3 | I.GG.15860 | DSN - D3 - Rail Sys - Sig Plan - Signalling Design Management Plan | 2024-10-02 | 2024-10-03
I2S-7688-MP-74.D.W.2.7.6 | Signalling Plan - D3 | I.GG.15870 | DSN - D3 - Rail Sys - Sig Plan - Request Source Records (O/S, editable reference design, CAD etc) | 2024-09-30 | 2024-10-01
I2S-7688-MP-74.D.W.2.7.6 | Signalling Plan - D3 | I.GG.16070 | DSN - D3 - Rail Sys - Sig Plan - Update Concept Signalling Plans | 2024-10-02 | 2024-10-03
I2S-7688-MP-74.D.W.2.7.6 | Signalling Plan - D3 | I.GG.16080 | DSN - D3 - Rail Sys - Sig Plan - IRPL & Stakeholder Reciept of Concept Signalling Plans for Workshop | 2024-10-04 | 2024-10-08
Stakeholder Engagement |  |  |  | 2024-10-09 | 2024-10-24
I2S-7688-MP-74.D.W.2.7.1 | Stakeholder Engagement | I.GG.15760 | DSN - D3 - Rail Sys - Sig Plan - Stakeholder Engagement Workshop #1 (Not under taken) | 2024-10-09 | 2024-10-09
I2S-7688-MP-74.D.W.2.7.1 | Stakeholder Engagement | I.GG.16090 | DSN - D3 - Rail Sys - Sig Plan - Stakeholder review of workshop presentations | 2024-10-10 | 2024-10-23
I2S-7688-MP-74.D.W.2.7.1 | Stakeholder Engagement | I.GG.16100 | DSN - D3 - Rail Sys - Sig Plan - Stakeholder Engagement Workshop #2 (Not under taken) | 2024-10-24 | 2024-10-24
Design Stage 3 - Detailed Design - DDD |  |  |  | 2024-10-25 | 2025-07-04
I2S-7688-MP-74.D.W.2.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.7220 | DSN - D3 - DDD - Rail Sys - Sig Plan - Safety Assurance / SiD - W.01 - Stage 2 | 2025-03-10 | 2025-03-14
I2S-7688-MP-74.D.W.2.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-D3 | DSN - D3 - DDD - Rail Sys - Sig Plan - Cost
I2S-7688-MP-74.D.W.2.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.7280 | DSN - D3 - DDD - Rail Sys - Sig Plan - Design Development | 2025-04-15 | 2025-05-22
I2S-7688-MP-74.D.W.2.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.7290 | DSN - D3 - DDD - Rail Sys - Sig Plan - Internal IDR workshop (By BGE) | 2025-05-19 | 2025-05-22
I2S-7688-MP-74.D.W.2.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.7310 | DSN - D3 - DDD - Rail Sys - Sig Plan - Review of IDR comment response and final review | 2025-05-23 | 2025-05-29
I2S-7688-MP-74.D.W.2.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.7320 | DSN - D3 - DDD - Rail Sys - Sig Plan - Incorporate IDR comments | 2025-05-30 | 2025-06-05
I2S-7688-MP-74.D.W.2.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.7330 | DSN - D3 - DDD - Rail Sys - Sig Plan - Issue Responses & Receive Comment Closeout | 2025-05-30 | 2025-06-05
I2S-7688-MP-74.D.W.2.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.7340 | DSN - D3 - DDD - Rail Sys - Sig Plan - Submission to IRPL | 2025-06-06 | 2025-06-06
I2S-7688-MP-74.D.W.2.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.7350 | DSN - D3 - DDD - Rail Sys - Sig Plan - IRPL Review (20 B.days) | 2025-06-06 | 2025-07-04
I2S-7688-MP-74.D.W.2.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11900 | DSN - D3 - DDD - Rail Sys - Sig Plan - Design Presentation to IRPL - DPK Presentation
I2S-7688-MP-74.D.W.2.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11890 | DSN - D3 - DDD - Rail Sys - Sig Plan - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.2.4 | Design Stage 3 - Detailed Design - DDD | I.DE.04.12250 | DSN - D3 - DDD - Rail Sys - Sig Plan - Start Package W.01 | 2024-10-25
CCB Gate 4 (Combined D3 & D4) |  |  |  | 2025-06-10 | 2025-07-17
I2S-7688-MP-74.D.W.2.1 | CCB Gate 4 (Combined D3 & D4) | I.DE.CCB.1030 | DSN - D3 - CCB G4 - Rail Sys - Sig Plan - Meeting - Presentation of CCR Submission to SM Sub CCB - Rail Syste | 2025-07-16 | 2025-07-16
I2S-7688-MP-74.D.W.2.1 | CCB Gate 4 (Combined D3 & D4) | I.DE.CCB.1000 | DSN - D3 - CCB G4 - Rail Sys - Sig Plan - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-06-10 | 2025-06-16
I2S-7688-MP-74.D.W.2.1 | CCB Gate 4 (Combined D3 & D4) | I.DE.CCB.1010 | DSN - D3 - CCB G4 - Rail Sys - Sig Plan - IRPL Reviews & Approves CCR Submission | 2025-06-18 | 2025-07-04
I2S-7688-MP-74.D.W.2.1 | CCB Gate 4 (Combined D3 & D4) | I.DE.CCB.1020 | DSN - D3 - CCB G4 - Rail Sys - Sig Plan - IRPL Submits CCB to SM Sub CCB | 2025-07-07 | 2025-07-07
I2S-7688-MP-74.D.W.2.1 | CCB Gate 4 (Combined D3 & D4) | I.DE.CCB.1040 | DSN - D3 - CCB G4 - Rail Sys - Sig Plan - Configuration Change Acceptance Notice | 2025-07-17 | 2025-07-17
CRN CCB Gate 2
I2S-7688-MP-74.D.W.2.6 | CRN CCB Gate 2 | I.DE.CCB.7600 | DSN - D3 - CCB G2 - Rail Sys - Sig Plan - CCB Gate 2 Meeting - Presentation of CCR Submission
I2S-7688-MP-74.D.W.2.6 | CRN CCB Gate 2 | I.DE.CCB.7610 | DSN - D3 - CCB G2 - Rail Sys - Sig Plan - Prepare & Submit CCR Checklist /Presentation Material
I2S-7688-MP-74.D.W.2.6 | CRN CCB Gate 2 | I.DE.CCB.7620 | DSN - D3 - CCB G2 - Rail Sys - Sig Plan - UGLRL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.W.2.6 | CRN CCB Gate 2 | I.DE.CCB.7630 | DSN - D3 - CCB G2 - Rail Sys - Sig Plan - UGLRL Submits CCB
I2S-7688-MP-74.D.W.2.6 | CRN CCB Gate 2 | I.DE.CCB.7640 | DSN - D3 - CCB G2 - Rail Sys - Sig Plan - Configuration Change Acceptance Notice
CRN CCB Gate 3
I2S-7688-MP-74.D.W.2.2 | CRN CCB Gate 3 | I.DE.CCB.7650 | DSN - D3 - CCB G3 - Rail Sys - Sig Plan - CCB Gate 3 Meeting - Presentation of CCR Submission
I2S-7688-MP-74.D.W.2.2 | CRN CCB Gate 3 | I.DE.CCB.7660 | DSN - D3 - CCB G3 - Rail Sys - Sig Plan - Prepare & Submit CCR Checklist /Presentation Material
I2S-7688-MP-74.D.W.2.2 | CRN CCB Gate 3 | I.DE.CCB.7670 | DSN - D3 - CCB G3 - Rail Sys - Sig Plan - UGLRL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.W.2.2 | CRN CCB Gate 3 | I.DE.CCB.7680 | DSN - D3 - CCB G3 - Rail Sys - Sig Plan - UGLRL Submits CCB
I2S-7688-MP-74.D.W.2.2 | CRN CCB Gate 3 | I.DE.CCB.7690 | DSN - D3 - CCB G3 - Rail Sys - Sig Plan - Configuration Change Acceptance Notice
Design Stage 4 - IFC |  |  |  | 2025-06-17 | 2025-08-12
I2S-7688-MP-74.D.W.2.5 | Design Stage 4 - IFC | I.DE.CCB.1035 | DSN - D3 - IFC - Rail Sys - Sig Plan - Close Out D3 & D4 CCB Comments
I2S-7688-MP-74.D.W.2.5 | Design Stage 4 - IFC | I.DE.00.7360 | DSN - D3 - IFC - Rail Sys - Sig Plan - Prepare IFC Documentation - Stage 4 - Rail Systems (Signalling Plan) | 2025-06-17 | 2025-07-21
I2S-7688-MP-74.D.W.2.5 | Design Stage 4 - IFC | I.DE.00.7370 | DSN - D3 - IFC - Rail Sys - Sig Plan - Submission to IRPL | 2025-07-22 | 2025-08-05
I2S-7688-MP-74.D.W.2.5 | Design Stage 4 - IFC | I.DE.00.7380 | DSN - D3 - IFC - Rail Sys - Sig Plan - IRPL Review (5 B.days) | 2025-08-06 | 2025-08-12
I2S-7688-MP-74.D.W.2.5 | Design Stage 4 - IFC | I.DE.00.7390 | DSN - D3 - IFC - Rail Sys - Sig Plan - IFC Package Complete D3 - Rail Systems (Signalling Plan) |  | 2025-08-12
I2S-7688-MP-74.D.W.2.5 | Design Stage 4 - IFC | Cost-IFC-D3 | DSN - D3 - IFC - Rail Sys - Sig Plan - Cost
Design Package D4 -RS-01- Rail Systems (Control Tables) (Was W.01
Design Stage 3 - Detailed Design - DDD
I2S-7688-MP-74.D.W.35.39 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11530 | DSN - D4 - DDD - Rail Sys - Control Tables - Safety Assurance / SiD
I2S-7688-MP-74.D.W.35.39 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11540 | DSN - D4 - DDD - Rail Sys - Control Tables - Design Development
I2S-7688-MP-74.D.W.35.39 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11550 | DSN - D4 - DDD - Rail Sys - Control Tables - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.35.39 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11560 | DSN - D4 - DDD - Rail Sys - Control Tables - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.35.39 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11570 | DSN - D4 - DDD - Rail Sys - Control Tables - Incorporate IDR comments
I2S-7688-MP-74.D.W.35.39 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11580 | DSN - D4 - DDD - Rail Sys - Control Tables - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.35.39 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11590 | DSN - D4 - DDD - Rail Sys - Control Tables - Submission to IRPL
I2S-7688-MP-74.D.W.35.39 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11600 | DSN - D4 - DDD - Rail Sys - Control Tables - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.35.39 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11910 | DSN - D4 - DDD - Rail Sys - Control Tables - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.35.39 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11920 | DSN - D4 - DDD - Rail Sys - Control Tables - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.35.39 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-D4 | DSN - D4 - DDD - Rail Sys - Control Tables - Cost
Design Stage 4 - IFC
I2S-7688-MP-74.D.W.35.5 | Design Stage 4 - IFC | I.DE.00.11610 | DSN - D4 - IFC - Rail Sys - Control Tables - Prepare IFC Documentation - IFC Submission
I2S-7688-MP-74.D.W.35.5 | Design Stage 4 - IFC | I.DE.00.11620 | DSN - D4 - IFC - Rail Sys - Control Tables - Submission to IRPL
I2S-7688-MP-74.D.W.35.5 | Design Stage 4 - IFC | I.DE.00.11630 | DSN - D4 - IFC - Rail Sys - Control Tables - IRPL Review (5 B.days)
I2S-7688-MP-74.D.W.35.5 | Design Stage 4 - IFC | I.DE.00.11640 | DSN - D4 - IFC - Rail Sys - Control Tables - IFC Package Complete
I2S-7688-MP-74.D.W.35.5 | Design Stage 4 - IFC | Cost-IFC-D4 | DSN - D4 - IFC - Rail Sys - Control Tables - Cost
Design Package D5 - RS-01- Rail Systems Circuit Books) (Was W.01
Design Stage 3 - Detailed Design - DDD
Design Stage 3 - A1 - Detailed Design - DDD
I2S-7688-MP-74.D.W.37.1.42 | Design Stage 3 - A1 - Detailed Design - DDD | I.DE.00.12130 | DSN - D5-A1 - DDD - Rail Sys - Circuit Book - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.37.1.42 | Design Stage 3 - A1 - Detailed Design - DDD | I.DE.00.12140 | DSN - D5-A1 - DDD - Rail Sys - Circuit Book - Submission to IRPL
I2S-7688-MP-74.D.W.37.1.42 | Design Stage 3 - A1 - Detailed Design - DDD | I.DE.00.12160 | DSN - D5-A1 - DDD - Rail Sys - Circuit Book - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.37.1.42 | Design Stage 3 - A1 - Detailed Design - DDD | I.DE.00.12150 | DSN - D5-A1 - DDD - Rail Sys - Circuit Book - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.37.1.42 | Design Stage 3 - A1 - Detailed Design - DDD | I.DE.00.12120 | DSN - D5-A1 - DDD - Rail Sys - Circuit Book - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.37.1.42 | Design Stage 3 - A1 - Detailed Design - DDD | I.DE.00.12110 | DSN - D5-A1 - DDD - Rail Sys - Circuit Book - Incorporate IDR comments
Design Stage 3 - A2 - Detailed Design - DDD
I2S-7688-MP-74.D.W.37.1.43 | Design Stage 3 - A2 - Detailed Design - DDD | I.DE.00.12190 | DSN - D5-A2 - DDD - Rail Sys - Circuit Book - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.37.1.43 | Design Stage 3 - A2 - Detailed Design - DDD | I.DE.00.12200 | DSN - D5-A2 - DDD - Rail Sys - Circuit Book - Submission to IRPL
I2S-7688-MP-74.D.W.37.1.43 | Design Stage 3 - A2 - Detailed Design - DDD | I.DE.00.12220 | DSN - D5-A2 - DDD - Rail Sys - Circuit Book - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.37.1.43 | Design Stage 3 - A2 - Detailed Design - DDD | I.DE.00.12210 | DSN - D5-A2 - DDD - Rail Sys - Circuit Book - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.37.1.43 | Design Stage 3 - A2 - Detailed Design - DDD | I.DE.00.12180 | DSN - D5-A2 - DDD - Rail Sys - Circuit Book - Review of comment response and final review
I2S-7688-MP-74.D.W.37.1.43 | Design Stage 3 - A2 - Detailed Design - DDD | I.DE.00.12170 | DSN - D5-A2 - DDD - Rail Sys - Circuit Book - Incorporate IDR comments
Design Stage 3 - A3 - Detailed Design - DDD - Stockinbingal
I2S-7688-MP-74.D.W.37.1.41 | Design Stage 3 - A3 - Detailed Design - DDD - Stockinbingal | I.DE.00.11700 | DSN - D5-A3 - DDD - Rail Sys - Circuit Book - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.37.1.41 | Design Stage 3 - A3 - Detailed Design - DDD - Stockinbingal | I.DE.00.11710 | DSN - D5-A3 - DDD - Rail Sys - Circuit Book - Submission to IRPL
I2S-7688-MP-74.D.W.37.1.41 | Design Stage 3 - A3 - Detailed Design - DDD - Stockinbingal | I.DE.00.11720 | DSN - D5-A3 - DDD - Rail Sys - Circuit Book - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.37.1.41 | Design Stage 3 - A3 - Detailed Design - DDD - Stockinbingal | I.DE.00.11930 | DSN - D5 - DDD - Rail Sys - Circuit Book - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.37.1.41 | Design Stage 3 - A3 - Detailed Design - DDD - Stockinbingal | I.DE.00.11940 | DSN - D5-A3 - DDD - Rail Sys - Circuit Book - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.37.1.41 | Design Stage 3 - A3 - Detailed Design - DDD - Stockinbingal | Cost-DDD-D5 | DSN - D5 - DDD - Rail Sys - Circuit Book - Cost
I2S-7688-MP-74.D.W.37.1.41 | Design Stage 3 - A3 - Detailed Design - DDD - Stockinbingal | I.DE.00.11650 | DSN - D5 - DDD - Rail Sys - Circuit Book - Safety Assurance / SiD
I2S-7688-MP-74.D.W.37.1.41 | Design Stage 3 - A3 - Detailed Design - DDD - Stockinbingal | I.DE.00.11660 | DSN - D5 - DDD - Rail Sys - Circuit Book - Design Development
I2S-7688-MP-74.D.W.37.1.41 | Design Stage 3 - A3 - Detailed Design - DDD - Stockinbingal | I.DE.00.11670 | DSN - D5 - DDD - Rail Sys - Circuit Book - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.37.1.41 | Design Stage 3 - A3 - Detailed Design - DDD - Stockinbingal | I.DE.00.11680 | DSN - D5-A3 - DDD - Rail Sys - Circuit Book - Review of comment response and final review
I2S-7688-MP-74.D.W.37.1.41 | Design Stage 3 - A3 - Detailed Design - DDD - Stockinbingal | I.DE.00.11690 | DSN - D5-A3 - DDD - Rail Sys - Circuit Book - Incorporate IDR comments
CCB Gate 4 - D5
I2S-7688-MP-74.D.W.37.2 | CCB Gate 4 - D5 | I.DE.CCB.6770 | DSN - D5 - CCB G4 - Rail Sys - Circuit Book - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.W.37.2 | CCB Gate 4 - D5 | I.DE.CCB.6780 | DSN - D5 - CCB G4 - Rail Sys - Circuit Book - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.D.W.37.2 | CCB Gate 4 - D5 | I.DE.CCB.6790 | DSN - D5 - CCB G4 - Rail Sys - Circuit Book - Configuration Change Acceptance Notice
I2S-7688-MP-74.D.W.37.2 | CCB Gate 4 - D5 | I.DE.CCB.6750 | DSN - D5 - CCB G4 - Rail Sys - Circuit Book - Meeting - Presentation of CCR Submission to SM Sub CCB
I2S-7688-MP-74.D.W.37.2 | CCB Gate 4 - D5 | I.DE.CCB.6760 | DSN - D5 - CCB G4 - Rail Sys - Circuit Book - Prepare & Submit CCR Checklist to IRPL
Design Stage 4 - IFC
I2S-7688-MP-74.D.W.37.5 | Design Stage 4 - IFC | I.DE.CCB.7390 | DSN - D5 - IFC - Rail Sys - Circuit Book - Close Out CCB Comments
I2S-7688-MP-74.D.W.37.5 | Design Stage 4 - IFC | I.DE.00.11730 | DSN - D5 - IFC - Rail Sys - Circuit Book - Prepare IFC Documentation
I2S-7688-MP-74.D.W.37.5 | Design Stage 4 - IFC | I.DE.00.11740 | DSN - D5 - IFC - Rail Sys - Circuit Book - Submission to IRPL
I2S-7688-MP-74.D.W.37.5 | Design Stage 4 - IFC | I.DE.00.11750 | DSN - D5 - IFC - Rail Sys - Circuit Book - IRPL Review (5 B.days)
I2S-7688-MP-74.D.W.37.5 | Design Stage 4 - IFC | I.DE.00.11760 | DSN - D5 - IFC - Rail Sys - Circuit Book - IFC Package Complete
I2S-7688-MP-74.D.W.37.5 | Design Stage 4 - IFC | Cost-IFC-D5 | DSN - D5 - IFC - Rail Sys - Circuit Book - Cost
Design Stage - A1 - IFC
I2S-7688-MP-74.D.W.37.5.1 | Design Stage - A1 - IFC | I.DE.CCB.7900 | DSN - D5-A1 - IFC - Rail Sys - Circuit Book - Close Out CCB Comments
I2S-7688-MP-74.D.W.37.5.1 | Design Stage - A1 - IFC | I.DE.00.12230 | DSN - D5-A1 - IFC - Rail Sys - Circuit Book - Prepare IFC Documentation
I2S-7688-MP-74.D.W.37.5.1 | Design Stage - A1 - IFC | I.DE.00.12240 | DSN - D5-A1 - IFC - Rail Sys - Circuit Book - Submission to IRPL
I2S-7688-MP-74.D.W.37.5.1 | Design Stage - A1 - IFC | I.DE.00.12250 | DSN - D5-A1 - IFC - Rail Sys - Circuit Book - IRPL Review (5 B.days)
I2S-7688-MP-74.D.W.37.5.1 | Design Stage - A1 - IFC | I.DE.00.12260 | DSN - D5-A1 - IFC - Rail Sys - Circuit Book - IFC Package Complete
Design Stage - A2 - IFC
I2S-7688-MP-74.D.W.37.5.3 | Design Stage - A2 - IFC | I.DE.00.12270 | DSN - D5-A2 - IFC - Rail Sys - Circuit Book - Prepare IFC Documentation
I2S-7688-MP-74.D.W.37.5.3 | Design Stage - A2 - IFC | I.DE.00.12280 | DSN - D5-A2 - IFC - Rail Sys - Circuit Book - Submission to IRPL
I2S-7688-MP-74.D.W.37.5.3 | Design Stage - A2 - IFC | I.DE.00.12290 | DSN - D5-A2 - IFC - Rail Sys - Circuit Book - IRPL Review (5 B.days)
I2S-7688-MP-74.D.W.37.5.3 | Design Stage - A2 - IFC | I.DE.00.12300 | DSN - D5-A2 - IFC - Rail Sys - Circuit Book - IFC Package Complete
I2S-7688-MP-74.D.W.37.5.3 | Design Stage - A2 - IFC | I.DE.CCB.7910 | DSN - D5-A2 - IFC - Rail Sys - Circuit Book - Close Out CCB Comments
Design Stage - A3 - IFC - Stockinbingal
I2S-7688-MP-74.D.W.37.5.2 | Design Stage - A3 - IFC - Stockinbingal | I.DE.CCB.7980 | DSN - D5-A3 - IFC - Rail Sys - Circuit Book - Close Out CCB Comments
I2S-7688-MP-74.D.W.37.5.2 | Design Stage - A3 - IFC - Stockinbingal | I.DE.00.12330 | DSN - D5-A3 - IFC - Rail Sys - Circuit Book - Prepare IFC Documentation
I2S-7688-MP-74.D.W.37.5.2 | Design Stage - A3 - IFC - Stockinbingal | I.DE.00.12340 | DSN - D5-A3 - IFC - Rail Sys - Circuit Book - Submission to IRPL
I2S-7688-MP-74.D.W.37.5.2 | Design Stage - A3 - IFC - Stockinbingal | I.DE.00.12350 | DSN - D5-A3 - IFC - Rail Sys - Circuit Book - IRPL Review (5 B.days)
I2S-7688-MP-74.D.W.37.5.2 | Design Stage - A3 - IFC - Stockinbingal | I.DE.00.12360 | DSN - D5-A3 - IFC - Rail Sys - Circuit Book - IFC Package Complete
Design Package D6 - RS-01- Rail Systems Microlok Data (Was W.01)
Design Stage 3 - Detailed Design - DDD
I2S-7688-MP-74.D.W.38.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11770 | DSN - D6 - DDD - Rail Sys - Microlok Data - Safety Assurance / SiD
I2S-7688-MP-74.D.W.38.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11780 | DSN - D6 - DDD - Rail Sys - Microlok Data - Design Development
I2S-7688-MP-74.D.W.38.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11790 | DSN - D6 - DDD - Rail Sys - Microlok Data - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.38.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11800 | DSN - D6 - DDD - Rail Sys - Microlok Data - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.38.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11810 | DSN - D6 - DDD - Rail Sys - Microlok Data - Incorporate IDR comments
I2S-7688-MP-74.D.W.38.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11820 | DSN - D6 - DDD - Rail Sys - Microlok Data - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.38.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11830 | DSN - D6 - DDD - Rail Sys - Microlok Data - Final Submission to IRPL
I2S-7688-MP-74.D.W.38.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11840 | DSN - D6 - DDD - Rail Sys - Microlok Data - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.38.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11950 | DSN - D6 - DDD - Rail Sys - Microlok Data - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.38.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11960 | DSN - D6 - DDD - Rail Sys - Microlok Data - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.38.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-D6 | DSN - D6 - DDD - Rail Sys - Microlok Data - Cost DDD D6
I2S-7688-MP-74.D.W.38.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.12080 | DSN - D6 - DDD - Rail Sys - Microlok Data - Design upd-Sys and IRPL Submission - Ilabo (1st Set)
I2S-7688-MP-74.D.W.38.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.12090 | DSN - D6 - DDD - Rail Sys - Microlok Data - Design upd-Sys and IRPL Submission - Stockingbingal
I2S-7688-MP-74.D.W.38.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.12100 | DSN - D6 - DDD - Rail Sys - Microlok Data - Design upd-Sys and IRPL Submission - Greenfield
I2S-7688-MP-74.D.W.38.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.12310 | DSN - D6 - DDD - Rail Sys - Microlok Data - Design upd-Sys and IRPL Submission - Ilabo (2nd Set)
CCB Gate 4 - D6
I2S-7688-MP-74.D.W.38.2 | CCB Gate 4 - D6 | I.DE.CCB.7920 | DSN - D6 - CCB G4 - Rail Sys - Circuit Book - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.W.38.2 | CCB Gate 4 - D6 | I.DE.CCB.7930 | DSN - D6 - CCB G4 - Rail Sys - Circuit Book - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.D.W.38.2 | CCB Gate 4 - D6 | I.DE.CCB.7940 | DSN - D6 - CCB G4 - Rail Sys - Circuit Book - Configuration Change Acceptance Notice
I2S-7688-MP-74.D.W.38.2 | CCB Gate 4 - D6 | I.DE.CCB.7950 | DSN - D6 - CCB G4 - Rail Sys - Circuit Book - Meeting - Presentation of CCR Submission to SM Sub CCB
I2S-7688-MP-74.D.W.38.2 | CCB Gate 4 - D6 | I.DE.CCB.7960 | DSN - D6 - CCB G4 - Rail Sys - Circuit Book - Prepare & Submit CCR Checklist to IRPL
Design Stage 4 - IFC
I2S-7688-MP-74.D.W.38.5 | Design Stage 4 - IFC | I.DE.00.11850 | DSN - D6 - IFC - Rail Sys - Microlok Data - Prepare IFC Documentation
I2S-7688-MP-74.D.W.38.5 | Design Stage 4 - IFC | I.DE.00.11860 | DSN - D6 - IFC - Rail Sys - Microlok Data - Submission to IRPL
I2S-7688-MP-74.D.W.38.5 | Design Stage 4 - IFC | I.DE.00.11870 | DSN - D6 - IFC - Rail Sys - Microlok Data - IRPL Review (5 B.days)
I2S-7688-MP-74.D.W.38.5 | Design Stage 4 - IFC | I.DE.00.11880 | DSN - D6 - IFC - Rail Sys - Microlok Data - IFC Package Complete
I2S-7688-MP-74.D.W.38.5 | Design Stage 4 - IFC | Cost-IFC-D6 | DSN - D6 - IFC - Rail Sys - Microlok Data - Cost IFC D6
Design Package D7 -Geotechnical and Hydrogeological Interpretative Report (Was in 3.01,2.01,1.01) |  |  |  | 2024-10-03 | 2025-07-11
Design Stage 1 - Feasibility Design - FDD |  |  |  | 2024-10-03 | 2025-02-03
I2S-7688-MP-74.D.W.13.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.9930 | DSN - D7 - FDD - Geotech Report - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.13.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.7400 | DSN - D7 - FDD - Geotech Report - Design Development | 2024-10-03 | 2024-12-05
I2S-7688-MP-74.D.W.13.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.7410 | DSN - D7 - FDD - Geotech Report - Internal IDR workshop (By BGE) | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.D.W.13.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.7430 | DSN - D7 - FDD - Geotech Report - Review of IDR comment response and final review | 2024-12-06 | 2024-12-12
I2S-7688-MP-74.D.W.13.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.7440 | DSN - D7 - FDD - Geotech Report - Incorporate IDC & CDR comments | 2024-12-13 | 2024-12-19
I2S-7688-MP-74.D.W.13.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.7450 | DSN - D7 - FDD - Geotech Report - Issue Responses & Receive Comment Closeout | 2024-12-13 | 2024-12-19
I2S-7688-MP-74.D.W.13.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.7460 | DSN - D7 - FDD - Geotech Report - Submission to IRPL | 2024-12-20 | 2024-12-20
I2S-7688-MP-74.D.W.13.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.7470 | DSN - D7 - FDD - Geotech Report - IRPL Review (20 B.days) | 2025-01-06 | 2025-02-03
I2S-7688-MP-74.D.W.13.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.04.12260 | DSN - D7 - FDD - Geotech Report - Start Package | 2024-10-03
I2S-7688-MP-74.D.W.13.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-D7 | DSN - D7 - FDD - Geotech Report - Cost
Design Stage 3 - Detailed Design - DDD |  |  |  | 2024-11-29 | 2025-07-03
I2S-7688-MP-74.D.W.13.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.9950 | DSN - D7 - DDD - Geotech Report - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.13.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.7560 | DSN - D7 - DDD - Geotech Report - Design Development | 2025-03-24 | 2025-05-21
I2S-7688-MP-74.D.W.13.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.7570 | DSN - D7 - DDD - Geotech Report - Internal IDR workshop (By BGE) | 2025-05-16 | 2025-05-21
I2S-7688-MP-74.D.W.13.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.7590 | DSN - D7 - DDD - Geotech Report - Review of IDR comment response and final review | 2025-05-22 | 2025-05-28
I2S-7688-MP-74.D.W.13.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.7600 | DSN - D7 - DDD - Geotech Report - Incorporate IDC & CDR comments | 2025-05-29 | 2025-06-04
I2S-7688-MP-74.D.W.13.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.7610 | DSN - D7 - DDD - Geotech Report - Issue Responses & Receive Comment Closeout | 2025-05-29 | 2025-06-04
I2S-7688-MP-74.D.W.13.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.7620 | DSN - D7 - DDD - Geotech Report - Submission to IRPL | 2025-06-05 | 2025-06-05
I2S-7688-MP-74.D.W.13.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.7630 | DSN - D7 - DDD - Geotech Report - IRPL Review (20 B.days) | 2025-06-05 | 2025-07-03
I2S-7688-MP-74.D.W.13.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-D7 | DSN - D7 - DDD - Geotech Report - Cost
I2S-7688-MP-74.D.W.13.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.9960 | DSN - D7 - DDD - Geotech Report - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.13.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.7420 | DSN - D7 - DDD - Geotech Report - Safety Assurance / SiD | 2024-11-29 | 2024-12-05
Design Stage 4 - IFC |  |  |  | 2025-06-06 | 2025-07-11
I2S-7688-MP-74.D.W.13.5 | Design Stage 4 - IFC | I.DE.00.7640 | DSN - D7 - IFC - Geotech Report - Prepare IFC Documentation | 2025-06-06 | 2025-07-11
I2S-7688-MP-74.D.W.13.5 | Design Stage 4 - IFC | I.DE.00.7650 | DSN - D7 - IFC - Geotech Report - Submission to IRPL | 2025-07-07 | 2025-07-11
I2S-7688-MP-74.D.W.13.5 | Design Stage 4 - IFC | I.DE.00.7660 | DSN - D7 - IFC - Geotech Report - IRPL Review (5 B.days) | 2025-07-07 | 2025-07-11
I2S-7688-MP-74.D.W.13.5 | Design Stage 4 - IFC | I.DE.00.7670 | DSN - D7 - IFC - Geotech Report - IFC Package Complete |  | 2025-07-11
I2S-7688-MP-74.D.W.13.5 | Design Stage 4 - IFC | Cost-IFC-D7 | DSN - D7 - IFC - Geotech Report - Cost
Design Package D8 - Geotechnical Monitoring (Was W.05) |  |  |  | 2024-10-03 | 2025-07-16
Design Stage 1 - Feasibility Design - FDD |  |  |  | 2024-10-03 | 2025-02-03
I2S-7688-MP-74.D.W.6.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.9810 | DSN - D8 - FDD - Geotech Monitoring - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.6.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.9820 | DSN - D8 - FDD - Geotech Monitoring - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.6.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.6590 | DSN - D8 - FDD - Geotech Monitoring - Review of IDR comment response and final review | 2024-12-06 | 2024-12-12
I2S-7688-MP-74.D.W.6.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.6600 | DSN - D8 - FDD - Geotech Monitoring - Incorporate IDR comments | 2024-12-13 | 2024-12-19
I2S-7688-MP-74.D.W.6.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.6610 | DSN - D8 - FDD - Geotech Monitoring - Issue Responses & Receive Comment Closeout | 2024-12-13 | 2024-12-19
I2S-7688-MP-74.D.W.6.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.6620 | DSN - D8 - FDD - Geotech Monitoring - Submission to IRPL | 2024-12-20 | 2024-12-20
I2S-7688-MP-74.D.W.6.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.6630 | DSN - D8 - FDD - Geotech Monitoring - IRPL Review (20 B.days) | 2025-01-06 | 2025-02-03
I2S-7688-MP-74.D.W.6.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.04.12190 | DSN - D8 - FDD - Geotech Monitoring - Start Package | 2024-10-03
I2S-7688-MP-74.D.W.6.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.6560 | DSN - D8 - FDD - Geotech Monitoring - Design Development | 2024-10-03 | 2024-12-05
I2S-7688-MP-74.D.W.6.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.6570 | DSN - D8 - FDD - Geotech Monitoring - Internal IDR workshop (By BGE) | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.D.W.6.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-D8 | DSN - D8 - FDD - Geotech Monitoring - Cost
Design Stage 3 - Detailed Design - DDD |  |  |  | 2025-03-12 | 2025-07-01
I2S-7688-MP-74.D.W.6.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.9850 | DSN - D8 - DDD - Geotech Monitoring - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.6.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.9860 | DSN - D8 - DDD - Geotech Monitoring - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.6.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.6660 | DSN - D8 - DDD - Geotech Monitoring - Safety Assurance / SiD | 2025-03-12 | 2025-03-18
I2S-7688-MP-74.D.W.6.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.6720 | DSN - D8 - DDD - Geotech Monitoring - Design Development | 2025-04-10 | 2025-05-19
I2S-7688-MP-74.D.W.6.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.6730 | DSN - D8 - DDD - Geotech Monitoring - Internal IDR workshop (By BGE) | 2025-05-14 | 2025-05-19
I2S-7688-MP-74.D.W.6.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.6750 | DSN - D8 - DDD - Geotech Monitoring - Review of IDR comment response and final review | 2025-05-20 | 2025-05-26
I2S-7688-MP-74.D.W.6.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.6760 | DSN - D8 - DDD - Geotech Monitoring - Incorporate IDR comments | 2025-05-27 | 2025-06-02
I2S-7688-MP-74.D.W.6.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.6770 | DSN - D8 - DDD - Geotech Monitoring - Issue Responses & Receive Comment Closeout | 2025-05-27 | 2025-06-02
I2S-7688-MP-74.D.W.6.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.6780 | DSN - D8 - DDD - Geotech Monitoring - Submission to IRPL | 2025-06-03 | 2025-06-03
I2S-7688-MP-74.D.W.6.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.6790 | DSN - D8 - DDD - Geotech Monitoring - IRPL Review (20 B.days) | 2025-06-03 | 2025-07-01
I2S-7688-MP-74.D.W.6.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-D8 | DSN - D8 - DDD - Geotech Monitoring - Cost
Design Stage 4 - IFC |  |  |  | 2025-06-04 | 2025-07-16
I2S-7688-MP-74.D.W.6.5 | Design Stage 4 - IFC | I.DE.00.6800 | DSN - D8 - IFC - Geotech Monitoring - Prepare IFC Documentation | 2025-06-04 | 2025-07-09
I2S-7688-MP-74.D.W.6.5 | Design Stage 4 - IFC | I.DE.00.6810 | DSN - D8 - IFC - Geotech Monitoring - Submission to IRPL | 2025-07-03 | 2025-07-09
I2S-7688-MP-74.D.W.6.5 | Design Stage 4 - IFC | I.DE.00.6830 | DSN - D8 - IFC - Geotech Monitoring - IFC Package Complete |  | 2025-07-16
I2S-7688-MP-74.D.W.6.5 | Design Stage 4 - IFC | I.DE.00.9650 | DSN - D8 - IFC - Geotech Monitoring - IRPL Review (5 B.days) | 2025-07-10 | 2025-07-16
Design Package D9 - Flood Assessment (Was W.07) |  |  |  | 2024-10-03 | 2025-08-07
Design Stage 1 - Feasibility Design - FDD |  |  |  | 2024-10-03 | 2025-03-06
I2S-7688-MP-74.D.W.7.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.9870 | DSN - D9 - FDD - Flood Assessment - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.7.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.9890 | DSN - D9 - FDD - Flood Assessment - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.7.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.6280 | DSN - D9 - FDD - Flood Assessment - Design Development - 1st Issue /FDVR | 2024-10-03 | 2024-12-05
I2S-7688-MP-74.D.W.7.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.6290 | DSN - D9 - FDD - Flood Assessment - Internal IDR workshop (By BGE) | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.D.W.7.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.6310 | DSN - D9 - FDD - Flood Assessment - Review of IDR comment response and final review | 2025-01-22 | 2025-01-29
I2S-7688-MP-74.D.W.7.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.6320 | DSN - D9 - FDD - Flood Assessment - Incorporate IDR | 2025-01-30 | 2025-02-05
I2S-7688-MP-74.D.W.7.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.6330 | DSN - D9 - FDD - Flood Assessment - Issue Responses & Receive Comment Closeout | 2025-01-30 | 2025-02-05
I2S-7688-MP-74.D.W.7.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.6340 | DSN - D9 - FDD - Flood Assessment - Submission to IRPL | 2025-02-06 | 2025-02-06
I2S-7688-MP-74.D.W.7.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.6350 | DSN - D9 - FDD - Flood Assessment - IRPL Review (20 B.days) | 2025-02-07 | 2025-03-06
I2S-7688-MP-74.D.W.7.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.04.12220 | DSN - D9 - FDD - Flood Assessment - Start Package D9 - Flooding Model / Assessment - 1st Issue /FDVR | 2024-10-03
I2S-7688-MP-74.D.W.7.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-D9 | DSN - D9 - FDD - Flood Assessment - Cost
Design Stage 3 - Detailed Design - DDD
I2S-7688-MP-74.D.W.7.3 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11970 | DSN - D9 - DDD - Flood Assessment - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.7.3 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11980 | DSN - D9 - DDD - Flood Assessment - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.7.3 | Design Stage 3 - Detailed Design - DDD | I.DE.00.11990 | DSN - D9 - DDD - Flood Assessment - Design Development - Final Issue /FDVR
I2S-7688-MP-74.D.W.7.3 | Design Stage 3 - Detailed Design - DDD | I.DE.00.12000 | DSN - D9 - DDD - Flood Assessment - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.7.3 | Design Stage 3 - Detailed Design - DDD | I.DE.00.12010 | DSN - D9 - DDD - Flood Assessment - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.7.3 | Design Stage 3 - Detailed Design - DDD | I.DE.00.12020 | DSN - D9 - DDD - Flood Assessment - Incorporate IDR comments
I2S-7688-MP-74.D.W.7.3 | Design Stage 3 - Detailed Design - DDD | I.DE.00.12030 | DSN - D9 - DDD - Flood Assessment - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.7.3 | Design Stage 3 - Detailed Design - DDD | I.DE.00.12040 | DSN - D9 - DDD - Flood Assessment - Submission to IRPL
I2S-7688-MP-74.D.W.7.3 | Design Stage 3 - Detailed Design - DDD | I.DE.00.12050 | DSN - D9 - DDD - Flood Assessment - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.7.3 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-D9 | DSN - D9 - DDD - Flood Assessment - Cost
Design Stage 4 - IFC |  |  |  | 2025-07-03 | 2025-08-07
I2S-7688-MP-74.D.W.7.5 | Design Stage 4 - IFC | I.DE.00.6520 | DSN - D9 - IFC - Flood Assessment - Prepare IFC Documentation | 2025-07-03 | 2025-08-07
I2S-7688-MP-74.D.W.7.5 | Design Stage 4 - IFC | I.DE.00.6530 | DSN - D9 - IFC - Flood Assessment - Submission to IRPL | 2025-07-31 | 2025-08-07
I2S-7688-MP-74.D.W.7.5 | Design Stage 4 - IFC | I.DE.00.6540 | DSN - D9 - IFC - Flood Assessment - IRPL Review (5 B.days) | 2025-07-31 | 2025-08-07
I2S-7688-MP-74.D.W.7.5 | Design Stage 4 - IFC | I.DE.00.6550 | DSN - D9 - IFC - Flood Assessment - IFC Package Complete |  | 2025-08-07
Design Package E1 - Rail Track, Earthworks and Formation (Was W.08) |  |  |  | 2024-10-03 | 2025-08-19
Design Stage 1 - Feasibility Design - FDD |  |  |  | 2024-10-03 | 2025-01-31
I2S-7688-MP-74.D.W.8.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.8780 | DSN - E1 - FDD - Track, EW and Formation - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.8.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.8460 | DSN - E1 - FDD - Track, EW and Formation - Design Development - Rail (Earthworks and Formation) | 2024-10-17 | 2024-12-04
I2S-7688-MP-74.D.W.8.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.8470 | DSN - E1 - FDD - Track, EW and Formation - Design Development - Rail (Level Crossigs) | 2024-10-17 | 2024-12-04
I2S-7688-MP-74.D.W.8.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.8480 | DSN - E1 - FDD - Track, EW and Formation - Internal IDR workshop (By BGE) | 2024-11-28 | 2024-12-04
I2S-7688-MP-74.D.W.8.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.8500 | DSN - E1 - FDD - Track, EW and Formation - Review of IDR comment response and final review | 2024-12-05 | 2024-12-11
I2S-7688-MP-74.D.W.8.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.8510 | DSN - E1 - FDD - Track, EW and Formation - Incorporate IDR comments | 2024-12-12 | 2024-12-18
I2S-7688-MP-74.D.W.8.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.8520 | DSN - E1 - FDD - Track, EW and Formation - Issue Responses & Receive Comment Closeout | 2024-12-12 | 2024-12-18
I2S-7688-MP-74.D.W.8.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.8530 | DSN - E1 - FDD - Track, EW and Formation - Submission to IRPL | 2024-12-19 | 2024-12-19
I2S-7688-MP-74.D.W.8.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.8540 | DSN - E1 - FDD - Track, EW and Formation - IRPL Review (20 B.days) | 2024-12-19 | 2025-01-31
I2S-7688-MP-74.D.W.8.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.8550 | DSN - E1 - FDD - Track, EW and Formation - Start Package E1 - Rail (Level Crossings+ EW) | 2024-10-03
I2S-7688-MP-74.D.W.8.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-E1 | DSN - E1 - FDD - Track, EW and Formation - Cost
I2S-7688-MP-74.D.W.8.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.10470 | DSN - E1 - FDD - Track, EW and Formation - Design Presentation to IRPL - DPK Presentation (Modified)
CCB Gate 3 |  |  |  | 2024-12-19 | 2025-02-20
I2S-7688-MP-74.D.W.8.6 | CCB Gate 3 | I.DE.CCB.3250 | DSN - E1 - CCB Gate 3 - Track, EW and Formation - Meeting - CCR Submission to SM Sub CCB | 2025-02-03 | 2025-02-19
I2S-7688-MP-74.D.W.8.6 | CCB Gate 3 | I.DE.CCB.3260 | DSN - E1 - CCB Gate 3 - Track, EW and Formation - Prepare & Submit CCR Checklist /Presentation to IRPL | 2024-12-19 | 2025-01-08
I2S-7688-MP-74.D.W.8.6 | CCB Gate 3 | I.DE.CCB.3270 | DSN - E1 - CCB Gate 3 - Track, EW and Formation - IRPL Reviews & Approves CCR Submission | 2025-01-13 | 2025-01-31
I2S-7688-MP-74.D.W.8.6 | CCB Gate 3 | I.DE.CCB.3280 | DSN - E1 - CCB Gate 3 - Track, EW and Formation - IRPL Submits CCB to SM Sub CCB | 2025-01-31 | 2025-02-03
I2S-7688-MP-74.D.W.8.6 | CCB Gate 3 | I.DE.CCB.3290 | DSN - E1 - CCB Gate 3 - Track, EW and Formation - Configuration Change Acceptance Notice | 2025-02-19 | 2025-02-20
Design Stage 2 - Preliminary Design - PDD |  |  |  | 2024-11-28 | 2025-05-02
I2S-7688-MP-74.D.W.8.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.9520 | DSN - E1 - PDD - Track, EW and Formation - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.8.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.8640 | DSN - E1 - PDD - Track, EW and Formation - IRPL Review (20 B.days) | 2025-04-01 | 2025-05-02
I2S-7688-MP-74.D.W.8.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.8490 | DSN - E1 - PDD - Track, EW and Formation - Safety Assurance / SiD | 2024-11-28 | 2024-12-04
I2S-7688-MP-74.D.W.8.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.8560 | DSN - E1 - PDD - Track, EW and Formation - Design Development - Rail (Earthworks and Formation) | 2024-12-19 | 2025-03-10
I2S-7688-MP-74.D.W.8.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.8570 | DSN - E1 - PDD - Track, EW and Formation - Design Development - Rail (Level Crossigs) | 2024-12-19 | 2025-03-10
I2S-7688-MP-74.D.W.8.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.8580 | DSN - E1 - PDD - Track, EW and Formation - Internal IDR workshop (By BGE) | 2025-03-04 | 2025-03-10
I2S-7688-MP-74.D.W.8.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.8600 | DSN - E1 - PDD - Track, EW and Formation - Review of IDR comment response and final review | 2025-03-11 | 2025-03-17
I2S-7688-MP-74.D.W.8.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.8610 | DSN - E1 - PDD - Track, EW and Formation - Incorporate IDR comments | 2025-03-18 | 2025-03-31
I2S-7688-MP-74.D.W.8.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.8620 | DSN - E1 - PDD - Track, EW and Formation - Issue Responses & Receive Comment Closeout | 2025-03-25 | 2025-03-31
I2S-7688-MP-74.D.W.8.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.8630 | DSN - E1 - PDD - Track, EW and Formation - Submission to IRPL | 2025-04-01 | 2025-04-01
I2S-7688-MP-74.D.W.8.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-E1 | DSN - E1 - PDD - Track, EW and Formation - Cost
I2S-7688-MP-74.D.W.8.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.10480 | DSN - E1 - PDD - Track, EW and Formation - Design Presentation to IRPL - (Modified)
Design Stage 3 - Detailed Design - DDD |  |  |  | 2025-03-04 | 2025-07-07
I2S-7688-MP-74.D.W.8.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-E1 | DSN - E1 - DDD - Track, EW and Formation - Cost
I2S-7688-MP-74.D.W.8.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.10490 | DSN - E1 - DDD - Track, EW and Formation - Design Presentation to IRPL - (Modified)
I2S-7688-MP-74.D.W.8.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.9530 | DSN - E1 - DDD - Track, EW and Formation - Internal IDR Review (By JHG)
I2S-7688-MP-74.D.W.8.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.8690 | DSN - E1 - DDD - Track, EW and Formation - Review of IDR comment response and final review | 2025-05-23 | 2025-05-30
I2S-7688-MP-74.D.W.8.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.8700 | DSN - E1 - DDD - Track, EW and Formation - Incorporate IDR comments | 2025-05-30 | 2025-06-06
I2S-7688-MP-74.D.W.8.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.8710 | DSN - E1 - DDD - Track, EW and Formation - Issue Responses & Receive Comment Closeout | 2025-05-30 | 2025-06-06
I2S-7688-MP-74.D.W.8.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.8720 | DSN - E1 - DDD - Track, EW and Formation - Submission to IRPL - E1 - Stage 3 | 2025-06-06 | 2025-06-06
I2S-7688-MP-74.D.W.8.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.8730 | DSN - E1 - DDD - Track, EW and Formation - IRPL Review (20 B.days) | 2025-06-10 | 2025-07-07
I2S-7688-MP-74.D.W.8.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.8650 | DSN - E1 - DDD - Track, EW and Formation - Design Development - Rail (Earthworks and Formation) | 2025-04-08 | 2025-05-23
I2S-7688-MP-74.D.W.8.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.8660 | DSN - E1 - DDD - Track, EW and Formation - Design Development - Rail (Level Crossigs) | 2025-04-08 | 2025-05-23
I2S-7688-MP-74.D.W.8.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.8670 | DSN - E1 - DDD - Track, EW and Formation - Internal IDR workshop (By BGE) | 2025-05-16 | 2025-05-23
I2S-7688-MP-74.D.W.8.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.8590 | DSN - E1 - DDD - Track, EW and Formation - Safety Assurance / SiD | 2025-03-04 | 2025-03-10
CCB Gate 4 |  |  |  | 2025-06-10 | 2025-07-17
I2S-7688-MP-74.D.W.8.1 | CCB Gate 4 | I.DE.CCB.1470 | DSN - E1 - CCB Gate 4 - Track, EW and Formation - IRPL Reviews & Approves CCR Submission | 2025-06-19 | 2025-07-07
I2S-7688-MP-74.D.W.8.1 | CCB Gate 4 | I.DE.CCB.1480 | DSN - E1 - CCB Gate 4 - Track, EW and Formation - IRPL Submits CCB to SM Sub CCB | 2025-07-08 | 2025-07-08
I2S-7688-MP-74.D.W.8.1 | CCB Gate 4 | I.DE.CCB.1490 | DSN - E1 - CCB Gate 4 - Track, EW and Formation - Configuration Change Acceptance Notice | 2025-07-17 | 2025-07-17
I2S-7688-MP-74.D.W.8.1 | CCB Gate 4 | I.DE.CCB.1450 | DSN - E1 - CCB Gate 4 - Track, EW and Formation - Meeting - Presentation of CCR Submission to SM Sub CCB | 2025-07-16 | 2025-07-16
I2S-7688-MP-74.D.W.8.1 | CCB Gate 4 | I.DE.CCB.1460 | DSN - E1 - CCB Gate 4 - Track, EW and Formation - Prepare & Submit CCR Checklist /Presentation to IRPL | 2025-06-10 | 2025-06-16
CRN CCB Gate 2
I2S-7688-MP-74.D.W.8.7 | CRN CCB Gate 2 | I.DE.CCB.7700 | DSN - E1 - CCB Gate 2 - Track, EW and Formation - CCB Gate 2 Meeting - Presentation of CCR Submission
I2S-7688-MP-74.D.W.8.7 | CRN CCB Gate 2 | I.DE.CCB.7710 | DSN - E1 - CCB Gate 2 - Track, EW and Formation - Prepare & Submit CCR Checklist /Presentation Material
I2S-7688-MP-74.D.W.8.7 | CRN CCB Gate 2 | I.DE.CCB.7720 | DSN - E1 - CCB Gate 2 - Track, EW and Formation - UGLRL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.W.8.7 | CRN CCB Gate 2 | I.DE.CCB.7730 | DSN - E1 - CCB Gate 2 - Track, EW and Formation - UGLRL Submits CCB
I2S-7688-MP-74.D.W.8.7 | CRN CCB Gate 2 | I.DE.CCB.7740 | DSN - E1 - CCB Gate 2 - Track, EW and Formation - Configuration Change Acceptance Notice
CRN CCB Gate 3
I2S-7688-MP-74.D.W.8.8 | CRN CCB Gate 3 | I.DE.CCB.7750 | DSN - E1 - CCB Gate 3 - Track, EW and Formation - CCB Gate 3 Meeting - Presentation of CCR Submission
I2S-7688-MP-74.D.W.8.8 | CRN CCB Gate 3 | I.DE.CCB.7760 | DSN - E1 - CCB Gate 3 - Track, EW and Formation - Prepare & Submit CCR Checklist /Presentation Material
I2S-7688-MP-74.D.W.8.8 | CRN CCB Gate 3 | I.DE.CCB.7770 | DSN - E1 - CCB Gate 3 - Track, EW and Formation - UGLRL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.W.8.8 | CRN CCB Gate 3 | I.DE.CCB.7780 | DSN - E1 - CCB Gate 3 - Track, EW and Formation - UGLRL Submits CCB
I2S-7688-MP-74.D.W.8.8 | CRN CCB Gate 3 | I.DE.CCB.7790 | DSN - E1 - CCB Gate 3 - Track, EW and Formation - Configuration Change Acceptance Notice
Design Stage 4 - IFC |  |  |  | 2025-07-01 | 2025-08-19
I2S-7688-MP-74.D.W.8.5 | Design Stage 4 - IFC | Cost-IFC-E1 | DSN - E1 - IFC - Track, EW and Formation - Cost
I2S-7688-MP-74.D.W.8.5 | Design Stage 4 - IFC | I.DE.01.8760 | DSN - E1 - IFC - Track, EW and Formation - IRPL Review (5 B.days) | 2025-08-13 | 2025-08-19
I2S-7688-MP-74.D.W.8.5 | Design Stage 4 - IFC | I.DE.01.8770 | DSN - E1 - IFC - Track, EW and Formation - IFC Package Complete |  | 2025-08-19
I2S-7688-MP-74.D.W.8.5 | Design Stage 4 - IFC | I.DE.01.8740 | DSN - E1 - IFC - Track, EW and Formation - Prepare IFC Documentation - Rail (Level Crossings + EW) | 2025-07-01 | 2025-08-12
I2S-7688-MP-74.D.W.8.5 | Design Stage 4 - IFC | I.DE.01.8750 | DSN - E1 - IFC - Track, EW and Formation - Submission to IRPL | 2025-07-29 | 2025-08-12
Design Package E2 - LXs (Public - Junee Shire Council) (Was 2.04) |  |  |  | 2024-12-05 | 2025-10-23
Design Stage 1 - Feasibility Design - FDD |  |  |  | 2024-12-05 | 2025-03-14
I2S-7688-MP-74.D.W.19.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-E2 | DSN - E2 - FDD - Cost
I2S-7688-MP-74.D.W.19.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17730 | DSN - E2 - FDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.19.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17720 | DSN - E2 - FDD - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.19.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.9270 | DSN - E2 - FDD - Design Development - Level Crossings (Public - Junee Shire Council) | 2024-12-05 | 2025-01-30
I2S-7688-MP-74.D.W.19.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.9280 | DSN - E2 - FDD - Internal IDR workshop (By BGE) | 2025-01-23 | 2025-01-30
I2S-7688-MP-74.D.W.19.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.9300 | DSN - E2 - FDD - Review of IDR comment response and final review | 2025-01-31 | 2025-02-06
I2S-7688-MP-74.D.W.19.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.9310 | DSN - E2 - FDD - Incorporate IDR comments | 2025-02-07 | 2025-02-13
I2S-7688-MP-74.D.W.19.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.9320 | DSN - E2 - FDD - Issue Responses & Receive Comment Closeout | 2025-02-07 | 2025-02-13
I2S-7688-MP-74.D.W.19.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.9330 | DSN - E2 - FDD - Submission to IRPL | 2025-02-14 | 2025-02-14
I2S-7688-MP-74.D.W.19.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.9340 | DSN - E2 - FDD - IRPL Review (20 B.days) | 2025-02-17 | 2025-03-14
I2S-7688-MP-74.D.W.19.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.9380 | DSN - E2 - FDD - Start Package - Level Crossings | 2024-12-05
CCB Gate 3 (Combined for E2 & E6) |  |  |  | 2025-02-17 | 2025-03-20
I2S-7688-MP-74.D.W.19.6 | CCB Gate 3 (Combined for E2 & E6) | I.DE.CCB.3650 | DSN - E2 - CCB Gate 3 - Meeting - Presentation of CCR Submission to SM Sub CCB - LXs (Public - Junee Shire Council) | 2025-03-19 | 2025-03-19
I2S-7688-MP-74.D.W.19.6 | CCB Gate 3 (Combined for E2 & E6) | I.DE.CCB.3660 | DSN - E2 - CCB Gate 3 - Prepare & Submit CCR Checklist /Presentation Material to IRPL (E2 & E6) | 2025-02-17 | 2025-02-21
I2S-7688-MP-74.D.W.19.6 | CCB Gate 3 (Combined for E2 & E6) | I.DE.CCB.3670 | DSN - E2 - CCB Gate 3 - IRPL Reviews & Approves CCR Submission (E2 & E6) | 2025-02-26 | 2025-03-14
I2S-7688-MP-74.D.W.19.6 | CCB Gate 3 (Combined for E2 & E6) | I.DE.CCB.3680 | DSN - E2 - CCB Gate 3 - IRPL Submits CCB to SM Sub CCB (E2 & E6) | 2025-03-17 | 2025-03-17
I2S-7688-MP-74.D.W.19.6 | CCB Gate 3 (Combined for E2 & E6) | I.DE.CCB.3690 | DSN - E2 - CCB Gate 3 - Configuration Change Acceptance Notice | 2025-03-20 | 2025-03-20
Design Stage 2 - Preliminary Design - PDD |  |  |  | 2025-01-23 | 2025-05-28
I2S-7688-MP-74.D.W.19.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.9420 | DSN - E2 - PDD - Review of IDR comment response and final review | 2025-04-04 | 2025-04-10
I2S-7688-MP-74.D.W.19.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.9430 | DSN - E2 - PDD - Incorporate IDR comments | 2025-04-11 | 2025-04-29
I2S-7688-MP-74.D.W.19.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.9440 | DSN - E2 - PDD - Issue Responses & Receive Comment Closeout | 2025-04-22 | 2025-04-29
I2S-7688-MP-74.D.W.19.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.9450 | DSN - E2 - PDD - Submission to IRPL | 2025-04-30 | 2025-04-30
I2S-7688-MP-74.D.W.19.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.9460 | DSN - E2 - PDD - IRPL Review (20 B.days) | 2025-05-01 | 2025-05-28
I2S-7688-MP-74.D.W.19.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-E2 | DSN - E2 - PDD - Cost
I2S-7688-MP-74.D.W.19.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17750 | DSN - E2 - PDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.19.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17740 | DSN - E2 - PDD - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.19.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.9290 | DSN - E2 - PDD - Safety Assurance / SiD | 2025-01-23 | 2025-01-30
I2S-7688-MP-74.D.W.19.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.9390 | DSN - E2 - PDD - Design Development - LXs (Public - Junee Shire Council) | 2025-02-14 | 2025-04-03
I2S-7688-MP-74.D.W.19.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.9400 | DSN - E2 - PDD - Internal IDR workshop (By BGE) | 2025-03-28 | 2025-04-03
Design Stage 3 - Detailed Design - DDD |  |  |  | 2025-03-28 | 2025-08-13
I2S-7688-MP-74.D.W.19.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17770 | DSN - E2 - DDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.19.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.9410 | DSN - E2 - DDD - Safety Assurance / SiD | 2025-03-28 | 2025-04-03
I2S-7688-MP-74.D.W.19.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.9500 | DSN - E2 - DDD - Design Development - LXs (Public - Junee Shire Council) | 2025-05-19 | 2025-06-30
I2S-7688-MP-74.D.W.19.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.9510 | DSN - E2 - DDD - Internal IDR workshop (By BGE) | 2025-06-24 | 2025-06-30
I2S-7688-MP-74.D.W.19.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.9530 | DSN - E2 - DDD - Review of IDR comment response and final review | 2025-07-01 | 2025-07-07
I2S-7688-MP-74.D.W.19.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.9540 | DSN - E2 - DDD - Incorporate IDR comments | 2025-07-08 | 2025-07-14
I2S-7688-MP-74.D.W.19.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.9550 | DSN - E2 - DDD - Issue Responses & Receive Comment Closeout | 2025-07-08 | 2025-07-14
I2S-7688-MP-74.D.W.19.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.9560 | DSN - E2 - DDD - Submission to IRPL | 2025-07-15 | 2025-07-15
I2S-7688-MP-74.D.W.19.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.9570 | DSN - E2 - DDD - IRPL Review (20 B.days) | 2025-07-16 | 2025-08-13
I2S-7688-MP-74.D.W.19.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-E2 | DSN - E2 - DDD - Cost
I2S-7688-MP-74.D.W.19.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17760 | DSN - E2 - DDD - Internal IDR Review (By JHG) - (Modified)
CCB Gate 4 (Combined for E2 & E6) |  |  |  | 2025-07-16 | 2025-08-21
I2S-7688-MP-74.D.W.19.1 | CCB Gate 4 (Combined for E2 & E6) | I.DE.CCB.1880 | DSN - E2 - CCB Gate 4 - IRPL Submits CCB to SM Sub CCB | 2025-08-14 | 2025-08-14
I2S-7688-MP-74.D.W.19.1 | CCB Gate 4 (Combined for E2 & E6) | I.DE.CCB.1890 | DSN - E2 - CCB Gate 4 - Configuration Change Acceptance Notice | 2025-08-21 | 2025-08-21
I2S-7688-MP-74.D.W.19.1 | CCB Gate 4 (Combined for E2 & E6) | I.DE.CCB.1850 | DSN - E2 - CCB Gate 4 - Meeting - Presentation of CCR Submission to SM Sub CCB - LXs (Public - Junee Shire Council) | 2025-08-20 | 2025-08-20
I2S-7688-MP-74.D.W.19.1 | CCB Gate 4 (Combined for E2 & E6) | I.DE.CCB.1860 | DSN - E2 - CCB Gate 4 - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-07-16 | 2025-07-22
I2S-7688-MP-74.D.W.19.1 | CCB Gate 4 (Combined for E2 & E6) | I.DE.CCB.1870 | DSN - E2 - CCB Gate 4 - IRPL Reviews | 2025-07-25 | 2025-08-13
I2S-7688-MP-74.D.W.19.1 | CCB Gate 4 (Combined for E2 & E6) | I.DE.CCB.7970 | DSN - E2 - CCB Gate 4 - IRPL Reviews & Approves CCR Submission
Design Stage 4 - IFC |  |  |  | 2025-07-30 | 2025-10-23
I2S-7688-MP-74.D.W.19.5 | Design Stage 4 - IFC | Cost-IFC-E2 | DSN - E2 - IFC - Cost
I2S-7688-MP-74.D.W.19.5 | Design Stage 4 - IFC | I.DE.02.9610 | DSN - E2 - IFC - Prepare IFC Documentation - LXs (Public - Junee Shire Council) | 2025-07-30 | 2025-09-10
I2S-7688-MP-74.D.W.19.5 | Design Stage 4 - IFC | I.DE.02.9620 | DSN - E2 - IFC - Submission to IRPL - LXs (Public - Junee Shire Council) | 2025-08-28 | 2025-09-10
I2S-7688-MP-74.D.W.19.5 | Design Stage 4 - IFC | I.DE.02.9630 | DSN - E2 - IFC - IRPL Review (5 B.days) | 2025-09-11 | 2025-09-17
I2S-7688-MP-74.D.W.19.5 | Design Stage 4 - IFC | I.DE.02.9640 | DSN - E2 - IFC - Package Complete E2 - Level Crossings |  | 2025-10-23
Design Package E3 - LXs (Public - Cootamundra-Gundagai Regional Council) (2.04) |  |  |  | 2024-12-05 | 2025-10-28
Design Stage 1 - Feasibility Design - FDD |  |  |  | 2024-12-05 | 2025-03-21
I2S-7688-MP-74.D.W.22.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-E3 | DSN - E3 - FDD - Cost
I2S-7688-MP-74.D.W.22.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.12060 | DSN - E3 - FDD - Issue Responses & Receive Comment Closeout | 2025-02-14 | 2025-02-20
I2S-7688-MP-74.D.W.22.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.12070 | DSN - E3 - FDD - Submission to IRPL | 2025-02-21 | 2025-02-21
I2S-7688-MP-74.D.W.22.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.12080 | DSN - E3 - FDD - IRPL Review (20 B.days) | 2025-02-24 | 2025-03-21
I2S-7688-MP-74.D.W.22.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.12090 | DSN - E3 - FDD - Start Package - Level Crossings | 2024-12-05
I2S-7688-MP-74.D.W.22.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.12050 | DSN - E3 - FDD - Incorporate IDR comments | 2025-02-14 | 2025-02-20
I2S-7688-MP-74.D.W.22.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.12010 | DSN - E3 - FDD - Design Development - Level Crossings | 2024-12-05 | 2025-02-06
I2S-7688-MP-74.D.W.22.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.12020 | DSN - E3 - FDD - Internal IDR workshop (By BGE) | 2025-01-31 | 2025-02-06
I2S-7688-MP-74.D.W.22.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.12040 | DSN - E3 - FDD - Review of IDR comment response and final review | 2025-02-07 | 2025-02-13
I2S-7688-MP-74.D.W.22.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17780 | DSN - E3 - FDD - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.22.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17790 | DSN - E3 - FDD - Design Presentation to IRPL - DPK Presentation - (Modified)
CCB Gate 3
I2S-7688-MP-74.D.W.22.6 | CCB Gate 3 | I.DE.CCB.6860 | DSN - E3 - CCB Gate 3 - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.D.W.22.6 | CCB Gate 3 | I.DE.CCB.6870 | DSN - E3 - CCB Gate 3 - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.W.22.6 | CCB Gate 3 | I.DE.CCB.6880 | DSN - E3 - CCB Gate 3 - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.D.W.22.6 | CCB Gate 3 | I.DE.CCB.6890 | DSN - E3 - CCB Gate 3 - Configuration Change Acceptance Notice
I2S-7688-MP-74.D.W.22.6 | CCB Gate 3 | I.DE.CCB.6850 | DSN - E3 - CCB Gate 3 - E3 - CCB Gate 3 - Meeting - Presentation of CCR Submission to SM Sub CCB - LXs (Public - Junee S
Design Stage 2 - Preliminary Design - PDD |  |  |  | 2025-01-31 | 2025-06-04
I2S-7688-MP-74.D.W.22.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.12160 | DSN - E3 - PDD - Submission to IRPL | 2025-05-07 | 2025-05-07
I2S-7688-MP-74.D.W.22.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.12170 | DSN - E3 - PDD - IRPL Review (20 B.days) | 2025-05-08 | 2025-06-04
I2S-7688-MP-74.D.W.22.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.12030 | DSN - E3 - PDD - Safety Assurance / SiD | 2025-01-31 | 2025-02-06
I2S-7688-MP-74.D.W.22.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17800 | DSN - E3 - PDD - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.22.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17810 | DSN - E3 - PDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.22.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-E3 | DSN - E3 - PDD - Cost
I2S-7688-MP-74.D.W.22.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.12100 | DSN - E3 - PDD - Design Development - Level Crossings | 2025-02-21 | 2025-04-10
I2S-7688-MP-74.D.W.22.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.12110 | DSN - E3 - PDD - Internal IDR workshop (By BGE) | 2025-04-04 | 2025-04-10
I2S-7688-MP-74.D.W.22.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.12130 | DSN - E3 - PDD - Review of IDR comment response and final review | 2025-04-11 | 2025-04-17
I2S-7688-MP-74.D.W.22.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.12140 | DSN - E3 - PDD - Incorporate IDR comments | 2025-04-22 | 2025-05-06
I2S-7688-MP-74.D.W.22.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.12150 | DSN - E3 - PDD - Issue Responses & Receive Comment Closeout | 2025-04-30 | 2025-05-06
Design Stage 3 - Detailed Design - DDD |  |  |  | 2025-04-04 | 2025-08-18
I2S-7688-MP-74.D.W.22.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-E3 | DSN - E3 - DDD - Cost DDD E3
I2S-7688-MP-74.D.W.22.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.12120 | DSN - E3 - DDD - Safety Assurance / SiD | 2025-04-04 | 2025-04-10
I2S-7688-MP-74.D.W.22.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.12210 | DSN - E3 - DDD - Review of IDR comment response and final review | 2025-07-04 | 2025-07-10
I2S-7688-MP-74.D.W.22.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.12220 | DSN - E3 - DDD - Incorporate IDR comments | 2025-07-11 | 2025-07-17
I2S-7688-MP-74.D.W.22.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.12230 | DSN - E3 - DDD - Issue Responses & Receive Comment Closeout | 2025-07-11 | 2025-07-17
I2S-7688-MP-74.D.W.22.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.12240 | DSN - E3 - DDD - Submission to IRPL | 2025-07-18 | 2025-07-18
I2S-7688-MP-74.D.W.22.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.12250 | DSN - E3 - DDD - IRPL Review (20 B.days) | 2025-07-21 | 2025-08-18
I2S-7688-MP-74.D.W.22.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.12180 | DSN - E3 - DDD - Design Development - LXs | 2025-05-22 | 2025-07-03
I2S-7688-MP-74.D.W.22.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.12190 | DSN - E3 - DDD - Internal IDR workshop (By BGE) | 2025-06-27 | 2025-07-03
I2S-7688-MP-74.D.W.22.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17820 | DSN - E3 - DDD - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.22.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17830 | DSN - E3 - DDD - Design Presentation to IRPL - DPK Presentation - (Modified)
CCB Gate 4
I2S-7688-MP-74.D.W.22.1 | CCB Gate 4 | I.DE.CCB.6820 | DSN - E3 - CCB Gate 4 - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.W.22.1 | CCB Gate 4 | I.DE.CCB.6830 | DSN - E3 - CCB Gate 4 - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.D.W.22.1 | CCB Gate 4 | I.DE.CCB.6840 | DSN - E3 - CCB Gate 4 - Configuration Change Acceptance Notice
I2S-7688-MP-74.D.W.22.1 | CCB Gate 4 | I.DE.CCB.6800 | DSN - E3 - CCB Gate 4 - Meeting - Presentation of CCR Submission to SM Sub CCB - LXs (Public - Junee Shire Council
I2S-7688-MP-74.D.W.22.1 | CCB Gate 4 | I.DE.CCB.6810 | DSN - E3 - CCB Gate 4 - Prepare & Submit CCR Checklist /Presentation Material to IRPL
Design Stage 4 - IFC |  |  |  | 2025-08-05 | 2025-10-28
I2S-7688-MP-74.D.W.22.5 | Design Stage 4 - IFC | Cost-IFC-E3 | DSN - E3 - IFC - Cost
I2S-7688-MP-74.D.W.22.5 | Design Stage 4 - IFC | I.DE.02.12260 | DSN - E3 - IFC - Prepare IFC Documentation - Level Crossings | 2025-08-05 | 2025-09-08
I2S-7688-MP-74.D.W.22.5 | Design Stage 4 - IFC | I.DE.02.12270 | DSN - E3 - IFC - Submission to IRPL | 2025-09-02 | 2025-09-15
I2S-7688-MP-74.D.W.22.5 | Design Stage 4 - IFC | I.DE.02.12280 | DSN - E3 - IFC - IRPL Review (5 B.days) | 2025-09-16 | 2025-09-22
I2S-7688-MP-74.D.W.22.5 | Design Stage 4 - IFC | I.DE.02.12290 | DSN - E3 - IFC - Package Complete - Level Crossings |  | 2025-10-28
Design Package E4 - LXs General (Was 1.04)
Design Stage 1 - Feasibility Design - FDD
I2S-7688-MP-74.D.W.1.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-E4 | DSN - E4 - FDD - Cost
I2S-7688-MP-74.D.W.1.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.10500 | DSN - E4 - FDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.1.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.9550 | DSN - E4 - FDD - Design Development - LXs General
I2S-7688-MP-74.D.W.1.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.9560 | DSN - E4 - FDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.1.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.9580 | DSN - E4 - FDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.1.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.9590 | DSN - E4 - FDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.1.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.9600 | DSN - E4 - FDD - Issue Responses & Receive Comment Closeout LXs General
I2S-7688-MP-74.D.W.1.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.9610 | DSN - E4 - FDD - Submission to IRPL
I2S-7688-MP-74.D.W.1.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.9620 | DSN - E4 - FDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.1.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.9630 | DSN - E4 - FDD - Start Package - LXs General
I2S-7688-MP-74.D.W.1.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.9840 | DSN - E4 - FDD - Internal IDR Review (By JHG) - (Modified)
Design Stage 2 - Preliminary Design - PDD
I2S-7688-MP-74.D.W.1.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-E4 | DSN - E4 - PDD - Cost
I2S-7688-MP-74.D.W.1.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.10510 | DSN - E4 - PDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.1.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.9570 | DSN - E4 - PDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.1.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.9640 | DSN - E4 - PDD - Design Development - LXs General
I2S-7688-MP-74.D.W.1.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.9660 | DSN - E4 - PDD - Internal IDR workshop (By BGE) - (Modified)
I2S-7688-MP-74.D.W.1.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.9670 | DSN - E4 - PDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.1.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.9680 | DSN - E4 - PDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.1.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.9690 | DSN - E4 - PDD - Issue Responses & Receive Comment Closeout - LXs General
I2S-7688-MP-74.D.W.1.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.9700 | DSN - E4 - PDD - Submission to IRPL
I2S-7688-MP-74.D.W.1.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.9710 | DSN - E4 - PDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.1.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.9850 | DSN - E4 - PDD - Internal IDR Review (By JHG)
Design Stage 3 - Detailed Design - DDD
I2S-7688-MP-74.D.W.1.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-E4 | DSN - E4 - DDD - Cost
I2S-7688-MP-74.D.W.1.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.10520 | DSN - E4 - DDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.1.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.10570 | DSN - E4 - DDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.1.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.9720 | DSN - E4 - DDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.1.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.9730 | DSN - E4 - DDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.1.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.9740 | DSN - E4 - DDD - Issue Responses & Receive Comment Closeout - LXs General
I2S-7688-MP-74.D.W.1.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.9750 | DSN - E4 - DDD - Submission to IRPL
I2S-7688-MP-74.D.W.1.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.9760 | DSN - E4 - DDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.1.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.9770 | DSN - E4 - DDD - Design Development - LXs General
I2S-7688-MP-74.D.W.1.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.9790 | DSN - E4 - DDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.1.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.9860 | DSN - E4 - DDD - Internal IDR Review (By JHG) - (Modified)
Design Stage 4 - IFC
I2S-7688-MP-74.D.W.1.5 | Design Stage 4 - IFC | I.DE.01.9810 | DSN - E4 - IFC - Package Complete - LXs General
I2S-7688-MP-74.D.W.1.5 | Design Stage 4 - IFC | I.DE.01.9820 | DSN - E4 - IFC - Prepare IFC Documentation - LXs General
I2S-7688-MP-74.D.W.1.5 | Design Stage 4 - IFC | I.DE.01.9830 | DSN - E4 - IFC - Submission to IRPL
I2S-7688-MP-74.D.W.1.5 | Design Stage 4 - IFC | Cost-IFC-E4 | DSN - E4 - IFC - Cost
I2S-7688-MP-74.D.W.1.5 | Design Stage 4 - IFC | I.DE.01.9800 | DSN - E4 - IFC - IRPL Review (5 B.days)
Design Package E5 - LXs (Public - Crown) (was Cover in 2.04)
Design Stage 1 - Feasibility Design - FDD
I2S-7688-MP-74.D.W.3.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-E5 | DSN - E5 - FDD - Cost
I2S-7688-MP-74.D.W.3.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.10530 | DSN - E5 - FDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.3.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.9870 | DSN - E5 - FDD - Design Development - LXs (Public - Crown)
I2S-7688-MP-74.D.W.3.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.9880 | DSN - E5 - FDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.3.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.9900 | DSN - E5 - FDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.3.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.9910 | DSN - E5 - FDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.3.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.9920 | DSN - E5 - FDD - Issue Responses & Receive Comment Closeout - LXs (Public - Crown)
I2S-7688-MP-74.D.W.3.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.9930 | DSN - E5 - FDD - Submission to IRPL
I2S-7688-MP-74.D.W.3.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.9940 | DSN - E5 - FDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.3.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.9950 | DSN - E5 - FDD - Start Package - LXs General
I2S-7688-MP-74.D.W.3.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.10140 | DSN - E5 - FDD - Internal IDR Review (By JHG) - (Modified)
CCB Gate 3
I2S-7688-MP-74.D.W.3.6 | CCB Gate 3 | I.DE.CCB.5200 | DSN - E5 - CCB Gate 3 - Meeting - Presentation of CCR Submission to SM Sub CCB
I2S-7688-MP-74.D.W.3.6 | CCB Gate 3 | I.DE.CCB.5210 | DSN - E5 - CCB Gate 3 - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.D.W.3.6 | CCB Gate 3 | I.DE.CCB.5220 | DSN - E5 - CCB Gate 3 - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.W.3.6 | CCB Gate 3 | I.DE.CCB.5230 | DSN - E5 - CCB Gate 3 - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.D.W.3.6 | CCB Gate 3 | I.DE.CCB.5240 | DSN - E5 - CCB Gate 3 - Configuration Change Acceptance Notice
Design Stage 2 - Preliminary Design - PDD
I2S-7688-MP-74.D.W.3.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-E5 | DSN - E5 - PDD - Cost
I2S-7688-MP-74.D.W.3.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.10000 | DSN - E5 - PDD - Issue Responses & Receive Comment Closeout - LXs (Public - Crown)
I2S-7688-MP-74.D.W.3.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.10010 | DSN - E5 - PDD - Submission to IRPL
I2S-7688-MP-74.D.W.3.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.10020 | DSN - E5 - PDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.3.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.10150 | DSN - E5 - PDD - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.3.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.10540 | DSN - E5 - PDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.3.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.9890 | DSN - E5 - PDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.3.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.9960 | DSN - E5 - PDD - Design Development - LXs (Public - Crown)
I2S-7688-MP-74.D.W.3.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.9970 | DSN - E5 - PDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.3.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.9980 | DSN - E5 - PDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.3.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.9990 | DSN - E5 - PDD - Incorporate IDR comments
Design Stage 3 - Detailed Design - DDD
I2S-7688-MP-74.D.W.3.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-E5 | DSN - E5 - DDD - Cost
I2S-7688-MP-74.D.W.3.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.10550 | DSN - E5 - DDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.3.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.10560 | DSN - E5 - DDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.3.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.10030 | DSN - E5 - DDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.3.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.10040 | DSN - E5 - DDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.3.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.10050 | DSN - E5 - DDD - Issue Responses & Receive Comment Closeout- E5 - LXs (Public - Crown)
I2S-7688-MP-74.D.W.3.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.10060 | DSN - E5 - DDD - Submission to IRPL
I2S-7688-MP-74.D.W.3.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.10070 | DSN - E5 - DDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.3.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.10080 | DSN - E5 - DDD - Design Development - LXs (Public - Crown)
I2S-7688-MP-74.D.W.3.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.10090 | DSN - E5 - DDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.3.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.10160 | DSN - E5 - DDD - Internal IDR Review (By JHG)- (Modified)
CCB Gate 4
I2S-7688-MP-74.D.W.3.1 | CCB Gate 4 | I.DE.CCB.5150 | DSN - E5 - CCB Gate 4 - Meeting - Presentation of CCR Submission to SM Sub CCB - LXs (Public - Crown)
I2S-7688-MP-74.D.W.3.1 | CCB Gate 4 | I.DE.CCB.5160 | DSN - E5 - CCB Gate 4 - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.D.W.3.1 | CCB Gate 4 | I.DE.CCB.5170 | DSN - E5 - CCB Gate 4 - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.W.3.1 | CCB Gate 4 | I.DE.CCB.5180 | DSN - E5 - CCB Gate 4 - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.D.W.3.1 | CCB Gate 4 | I.DE.CCB.5190 | DSN - E5 - CCB Gate 4 - Configuration Change Acceptance Notice
Design Stage 4 - IFC
I2S-7688-MP-74.D.W.3.5 | Design Stage 4 - IFC | Cost-IFC-E5 | DSN - E5 - IFC - Cost
I2S-7688-MP-74.D.W.3.5 | Design Stage 4 - IFC | I.DE.01.10110 | DSN - E5 - IFC - Package Complete - LXs (Public - Crown)
I2S-7688-MP-74.D.W.3.5 | Design Stage 4 - IFC | I.DE.01.10120 | DSN - E5 - IFC - Prepare IFC Documentation - LXs (Public - Crown)
I2S-7688-MP-74.D.W.3.5 | Design Stage 4 - IFC | I.DE.01.10130 | DSN - E5 - IFC - Submission to IRPL
I2S-7688-MP-74.D.W.3.5 | Design Stage 4 - IFC | I.DE.01.10100 | DSN - E5 - IFC - IRPL Review (5 B.days)
Design Package E6 - LXs (Private) (was Cover in 1.04, 2.04)
Design Stage 1 - Feasibility Design - FDD
I2S-7688-MP-74.D.W.4.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.10580 | DSN - E6 - FDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.4.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.10170 | DSN - E6 - FDD - Design Development - LXs (Private)
I2S-7688-MP-74.D.W.4.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.10180 | DSN - E6 - FDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.4.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.10200 | DSN - E6 - FDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.4.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.10210 | DSN - E6 - FDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.4.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.10220 | DSN - E6 - FDD - Issue Responses & Receive Comment Closeout - LXs (Private)
I2S-7688-MP-74.D.W.4.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.10230 | DSN - E6 - FDD - Submission to IRPL
I2S-7688-MP-74.D.W.4.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.10240 | DSN - E6 - FDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.4.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.10250 | DSN - E6 - FDD - Start Package - LXs General
I2S-7688-MP-74.D.W.4.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.01.10440 | DSN - E6 - FDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.4.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-E6 | DSN - E6 - FDD - Cost
Design Stage 2 - Preliminary Design - PDD
I2S-7688-MP-74.D.W.4.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-E6 | DSN - E6 - PDD - Cost
I2S-7688-MP-74.D.W.4.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.10590 | DSN - E6 - PDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.4.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.10190 | DSN - E6 - PDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.4.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.10260 | DSN - E6 - PDD - Design Development - LXs (Private)
I2S-7688-MP-74.D.W.4.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.10270 | DSN - E6 - PDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.4.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.10280 | DSN - E6 - PDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.4.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.10290 | DSN - E6 - PDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.4.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.10300 | DSN - E6 - PDD - Issue Responses & Receive Comment Closeout - LXs General
I2S-7688-MP-74.D.W.4.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.10310 | DSN - E6 - PDD - Submission to IRPL
I2S-7688-MP-74.D.W.4.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.10320 | DSN - E6 - PDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.4.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.01.10450 | DSN - E6 - PDD - Internal IDR Review (By JHG)- (Modified)
Design Stage 3 - Detailed Design - DDD
I2S-7688-MP-74.D.W.4.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.10460 | DSN - E6 - DDD - Internal IDR Review (By JHG)
I2S-7688-MP-74.D.W.4.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-E6 | DSN - E6 - DDD - Cost
I2S-7688-MP-74.D.W.4.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.10600 | DSN - E6 - DDD - Design Presentation to IRPL - DPK Presentation - LXs (Private)
I2S-7688-MP-74.D.W.4.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.10330 | DSN - E6 - DDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.4.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.10340 | DSN - E6 - DDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.4.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.10350 | DSN - E6 - DDD - Issue Responses & Receive Comment Closeout - LXs (Private)
I2S-7688-MP-74.D.W.4.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.10360 | DSN - E6 - DDD - Submission to IRPL
I2S-7688-MP-74.D.W.4.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.10370 | DSN - E6 - DDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.4.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.10380 | DSN - E6 - DDD - Design Development - LXs (Private)
I2S-7688-MP-74.D.W.4.4 | Design Stage 3 - Detailed Design - DDD | I.DE.01.10390 | DSN - E6 - DDD - Internal IDR workshop (By BGE)
Design Stage 4 - IFC
I2S-7688-MP-74.D.W.4.5 | Design Stage 4 - IFC | Cost-IFC-E6 | DSN - E6 - IFC - Cost
I2S-7688-MP-74.D.W.4.5 | Design Stage 4 - IFC | I.DE.01.10400 | DSN - E6 - IFC - IRPL Review (5 B.days)
I2S-7688-MP-74.D.W.4.5 | Design Stage 4 - IFC | I.DE.01.10410 | DSN - E6 - IFC - Package Complete - LXs (Private)
I2S-7688-MP-74.D.W.4.5 | Design Stage 4 - IFC | I.DE.01.10420 | DSN - E6 - IFC - Prepare IFC Documentation - LXs (Private)
I2S-7688-MP-74.D.W.4.5 | Design Stage 4 - IFC | I.DE.01.10430 | DSN - E6 - IFC - Submission to IRPL
Design Package E7 - Drainage (Was W10, 3.10,2.10,1.10) |  |  |  | 2024-12-06 | 2025-10-15
Design Stage 1 - Feasibility Design - FDD |  |  |  | 2024-12-06 | 2025-03-31
I2S-7688-MP-74.D.W.10.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-E7 | DSN - E7 - FDD - Cost
I2S-7688-MP-74.D.W.10.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.04.12340 | DSN - E7 - FDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.10.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.04.12350 | DSN - E7 - FDD - Design Presentation to IRPL - DPK Presentation
I2S-7688-MP-74.D.W.10.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.04.2860 | DSN - E7 - FDD - Internal IDR workshop (By BGE) | 2025-02-10 | 2025-02-14
I2S-7688-MP-74.D.W.10.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.04.2880 | DSN - E7 - FDD - Review of IDR comment response and final review | 2025-02-17 | 2025-02-21
I2S-7688-MP-74.D.W.10.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.04.2890 | DSN - E7 - FDD - Incorporate IDR comments | 2025-02-24 | 2025-02-28
I2S-7688-MP-74.D.W.10.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.04.2900 | DSN - E7 - FDD - Issue Responses & Receive Comment Closeout | 2025-02-24 | 2025-02-28
I2S-7688-MP-74.D.W.10.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.04.2920 | DSN - E7 - FDD - Submission to IRPL | 2025-03-03 | 2025-03-03
I2S-7688-MP-74.D.W.10.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.04.2930 | DSN - E7 - FDD - IRPL Review (20 B.days) | 2025-03-04 | 2025-03-31
I2S-7688-MP-74.D.W.10.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.04.11360 | DSN - E7 - FDD - Design Development - Track Drainage | 2024-12-06 | 2025-02-14
I2S-7688-MP-74.D.W.10.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.04.8040 | DSN - E7 - FDD - Start Package - Track Drainage | 2024-12-06
CCB Gate 3 |  |  |  | 2025-03-04 | 2025-04-08
I2S-7688-MP-74.D.W.10.6 | CCB Gate 3 | I.DE.CCB.3350 | DSN - E7 - CCB Gate 3 - Meeting - Presentation of CCR Submission to SM Sub CCB - Track Drainage | 2025-04-07 | 2025-04-07
I2S-7688-MP-74.D.W.10.6 | CCB Gate 3 | I.DE.CCB.3360 | DSN - E7 - CCB Gate 3 - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-03-04 | 2025-03-10
I2S-7688-MP-74.D.W.10.6 | CCB Gate 3 | I.DE.CCB.3370 | DSN - E7 - CCB Gate 3 - IRPL Reviews & Approves CCR Submission | 2025-03-13 | 2025-03-31
I2S-7688-MP-74.D.W.10.6 | CCB Gate 3 | I.DE.CCB.3380 | DSN - E7 - CCB Gate 3 - IRPL Submits CCB to SM Sub CCB | 2025-04-01 | 2025-04-01
I2S-7688-MP-74.D.W.10.6 | CCB Gate 3 | I.DE.CCB.3390 | DSN - E7 - CCB Gate 3 - Configuration Change Acceptance Notice | 2025-04-08 | 2025-04-08
Design Stage 2 - Preliminary Design - PDD |  |  |  | 2025-02-10 | 2025-07-11
I2S-7688-MP-74.D.W.10.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.04.2970 | DSN - E7 - PDD - Internal IDR workshop (By BGE) | 2025-05-15 | 2025-05-21
I2S-7688-MP-74.D.W.10.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.04.2990 | DSN - E7 - PDD - Review of IDR comment response and final review | 2025-05-22 | 2025-05-28
I2S-7688-MP-74.D.W.10.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.04.3000 | DSN - E7 - PDD - Incorporate IDR comments | 2025-05-29 | 2025-06-12
I2S-7688-MP-74.D.W.10.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.04.3010 | DSN - E7 - PDD - Issue Responses & Receive Comment Closeout | 2025-06-05 | 2025-06-12
I2S-7688-MP-74.D.W.10.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.04.3030 | DSN - E7 - PDD - Submission to IRPL | 2025-06-13 | 2025-06-13
I2S-7688-MP-74.D.W.10.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.04.3040 | DSN - E7 - PDD - IRPL Review (20 B.days) | 2025-06-16 | 2025-07-11
I2S-7688-MP-74.D.W.10.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.04I.11470 | DSN - E7 - PDD - Design Development - Track Drainage (including CoA E81 impa | 2025-03-03 | 2025-05-21
I2S-7688-MP-74.D.W.10.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.04.12360 | DSN - E7 - PDD - Internal IDR Review (By JHG)- (Modified)
I2S-7688-MP-74.D.W.10.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.04.12370 | DSN - E7 - PDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.10.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-E7 | DSN - E7 - PDD - Cost
I2S-7688-MP-74.D.W.10.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.04.2870 | DSN - E7 - PDD - Safety Assurance / SiD | 2025-02-10 | 2025-02-14
Design Stage 3 - Detailed Design - DDD |  |  |  | 2025-05-15 | 2025-09-09
I2S-7688-MP-74.D.W.10.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-E7 | DSN - E7 - DDD - Cost
I2S-7688-MP-74.D.W.10.4 | Design Stage 3 - Detailed Design - DDD | I.DE.04.12380 | DSN - E7 - DDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.10.4 | Design Stage 3 - Detailed Design - DDD | I.DE.04.12390 | DSN - E7 - DDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.10.4 | Design Stage 3 - Detailed Design - DDD | I.DE.04.2980 | DSN - E7 - DDD - Safety Assurance / SiD | 2025-05-15 | 2025-05-21
I2S-7688-MP-74.D.W.10.4 | Design Stage 3 - Detailed Design - DDD | I.DE.04.3070 | DSN - E7 - DDD - Internal IDR workshop (By BGE) | 2025-07-21 | 2025-07-25
I2S-7688-MP-74.D.W.10.4 | Design Stage 3 - Detailed Design - DDD | I.DE.04.3090 | DSN - E7 - DDD - Review of IDR comment response and final review | 2025-07-28 | 2025-08-01
I2S-7688-MP-74.D.W.10.4 | Design Stage 3 - Detailed Design - DDD | I.DE.04.3130 | DSN - E7 - DDD - Submission to IRPL | 2025-08-12 | 2025-08-12
I2S-7688-MP-74.D.W.10.4 | Design Stage 3 - Detailed Design - DDD | I.DE.04.3140 | DSN - E7 - DDD - IRPL Review (20 B.days) | 2025-08-13 | 2025-09-09
I2S-7688-MP-74.D.W.10.4 | Design Stage 3 - Detailed Design - DDD | I.DE.04.11570 | DSN - E7 - DDD - Design Development - Track Drainage | 2025-06-16 | 2025-07-25
I2S-7688-MP-74.D.W.10.4 | Design Stage 3 - Detailed Design - DDD | I.DE.04.3100 | DSN - E7 - DDD - Incorporate IDR comments | 2025-08-05 | 2025-08-11
I2S-7688-MP-74.D.W.10.4 | Design Stage 3 - Detailed Design - DDD | I.DE.04.3110 | DSN - E7 - DDD - Issue Responses & Receive Comment Closeout | 2025-08-05 | 2025-08-11
CCB Gate 4 |  |  |  | 2025-08-13 | 2025-09-18
I2S-7688-MP-74.D.W.10.1 | CCB Gate 4 | I.DE.CCB.1550 | DSN - E7 - CCB Gate 4 - Meeting - Presentation of CCR Submission to SM Sub CCB - Track Drainage | 2025-09-17 | 2025-09-17
I2S-7688-MP-74.D.W.10.1 | CCB Gate 4 | I.DE.CCB.1560 | DSN - E7 - CCB Gate 4 - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-08-13 | 2025-08-19
I2S-7688-MP-74.D.W.10.1 | CCB Gate 4 | I.DE.CCB.1570 | DSN - E7 - CCB Gate 4 - IRPL Reviews & Approves CCR Submission | 2025-08-22 | 2025-09-09
I2S-7688-MP-74.D.W.10.1 | CCB Gate 4 | I.DE.CCB.1580 | DSN - E7 - CCB Gate 4 - IRPL Submits CCB to SM Sub CCB | 2025-09-10 | 2025-09-10
I2S-7688-MP-74.D.W.10.1 | CCB Gate 4 | I.DE.CCB.1590 | DSN - E7 - CCB Gate 4 - Configuration Change Acceptance Notice - Track Drainage | 2025-09-18 | 2025-09-18
Design Stage 4 - IFC |  |  |  | 2025-08-20 | 2025-10-15
I2S-7688-MP-74.D.W.10.5 | Design Stage 4 - IFC | I.DE.04.3190 | DSN - E7 - IFC - IRPL Review (5 B.days) | 2025-10-09 | 2025-10-15
I2S-7688-MP-74.D.W.10.5 | Design Stage 4 - IFC | I.DE.04.3210 | DSN - E7 - IFC - Package Complete - Track Drainage |  | 2025-10-15
I2S-7688-MP-74.D.W.10.5 | Design Stage 4 - IFC | I.DE.04.3170 | DSN - E7 - IFC - Submission to IRPL | 2025-09-24 | 2025-10-08
I2S-7688-MP-74.D.W.10.5 | Design Stage 4 - IFC | Cost-IFC-E7 | DSN - E7 - IFC - Cost
I2S-7688-MP-74.D.W.10.5 | Design Stage 4 - IFC | I.DE.04.3180 | DSN - E7 - IFC - Issue Responses & Receive Comment Closeout | 2025-10-01 | 2025-10-08
I2S-7688-MP-74.D.W.10.5 | Design Stage 4 - IFC | I.DE.04.3160 | DSN - E7 - IFC - Prepare IFC Documentation - Track Drainage | 2025-08-20 | 2025-09-23
Design Package E8 - Burley Griffin Way Overbridge (Was 3.06) |  |  |  | 2024-10-03 | 2025-10-13
Design Stage 1 - Feasibility Design - FDD |  |  |  | 2024-10-03 | 2025-01-22
I2S-7688-MP-74.D.W.20.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.8520 | DSN - E8 - FDD - IRPL Review (20 B.days) | 2024-12-12 | 2025-01-22
I2S-7688-MP-74.D.W.20.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.8560 | DSN - E8 - FDD - Start Package - Bridges - Burley Griffin Way Overbridge | 2024-10-03
I2S-7688-MP-74.D.W.20.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-E8 | DSN - E8 - FDD - Cost
I2S-7688-MP-74.D.W.20.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.12700 | DSN - E8 - FDD - Internal IDR Review (By JHG)- (Modified)
I2S-7688-MP-74.D.W.20.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.12710 | DSN - E8 - FDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.20.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.8450 | DSN - E8 - FDD - Design Development - Bridges - Burley Griffin Way Overbridge | 2024-10-03 | 2024-11-28
I2S-7688-MP-74.D.W.20.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.8460 | DSN - E8 - FDD - Internal IDR workshop (By BGE) | 2024-11-22 | 2024-11-28
I2S-7688-MP-74.D.W.20.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.8480 | DSN - E8 - FDD - Review of IDR comment response and final review | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.D.W.20.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.8490 | DSN - E8 - FDD - Incorporate IDR comments - Burley Griffin Way Overbridge | 2024-12-06 | 2024-12-10
I2S-7688-MP-74.D.W.20.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.8500 | DSN - E8 - FDD - Issue Responses & Receive Comment Closeout | 2024-12-04 | 2024-12-10
I2S-7688-MP-74.D.W.20.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.8510 | DSN - E8 - FDD - Submission to IRPL | 2024-12-11 | 2024-12-11
CCB Gate 3 |  |  |  | 2024-12-12 | 2025-02-04
I2S-7688-MP-74.D.W.20.6 | CCB Gate 3 | I.DE.CCB.3750 | DSN - E8 - CCB Gate 3 - Meeting - Presentation of CCR Submission to SM Sub CCB - Bridges - sections 6 (2 off, inc BGW) | 2025-02-03 | 2025-02-03
I2S-7688-MP-74.D.W.20.6 | CCB Gate 3 | I.DE.CCB.3760 | DSN - E8 - CCB Gate 3 - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2024-12-12 | 2024-12-18
I2S-7688-MP-74.D.W.20.6 | CCB Gate 3 | I.DE.CCB.3770 | DSN - E8 - CCB Gate 3 - IRPL Reviews & Approves CCR Submission | 2025-01-06 | 2025-01-22
I2S-7688-MP-74.D.W.20.6 | CCB Gate 3 | I.DE.CCB.3780 | DSN - E8 - CCB Gate 3 - IRPL Submits CCB to SM Sub CCB | 2025-01-23 | 2025-01-23
I2S-7688-MP-74.D.W.20.6 | CCB Gate 3 | I.DE.CCB.3790 | DSN - E8 - CCB Gate 3 - Configuration Change Acceptance Notice | 2025-02-04 | 2025-02-04
Design Stage 2 - Preliminary Design - PDD |  |  |  | 2024-11-22 | 2025-05-20
I2S-7688-MP-74.D.W.20.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-E8 | DSN - E8 - PDD - Cost
I2S-7688-MP-74.D.W.20.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.12720 | DSN - E8 - PDD - Internal IDR Review (By JHG) - bridges (6)
I2S-7688-MP-74.D.W.20.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.12740 | DSN - E8 - PDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.20.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.8470 | DSN - E8 - PDD - Safety Assurance / SiD | 2024-11-22 | 2024-11-28
I2S-7688-MP-74.D.W.20.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.8570 | DSN - E8 - PDD - Design Development - Bridges | 2024-12-11 | 2025-03-12
I2S-7688-MP-74.D.W.20.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.8580 | DSN - E8 - PDD - Internal IDR workshop (By BGE) - bridges (6) | 2025-03-06 | 2025-03-12
I2S-7688-MP-74.D.W.20.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.8600 | DSN - E8 - PDD - Review of IDR comment response and final review | 2025-03-13 | 2025-03-19
I2S-7688-MP-74.D.W.20.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.8610 | DSN - E8 - PDD - Incorporate IDR comments | 2025-03-20 | 2025-04-02
I2S-7688-MP-74.D.W.20.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.8620 | DSN - E8 - PDD - Issue Responses & Receive Comment Closeout | 2025-03-27 | 2025-04-02
I2S-7688-MP-74.D.W.20.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.8630 | DSN - E8 - PDD - Submission to IRPL | 2025-04-03 | 2025-04-03
I2S-7688-MP-74.D.W.20.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.8640 | DSN - E8 - PDD - IRPL Review (20 B.days) | 2025-04-04 | 2025-05-06
I2S-7688-MP-74.D.W.20.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.8850 | DSN - E8 - PDD - TfNSW/ IV Review (30 B.days) - BGW Bridge | 2025-04-04 | 2025-05-20
Design Stage 3 - Detailed Design - DDD |  |  |  | 2025-03-06 | 2025-07-29
I2S-7688-MP-74.D.W.20.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-E8 | DSN - E8 - DDD - Cost
I2S-7688-MP-74.D.W.20.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.8590 | DSN - E8 - DDD - Safety Assurance / SiD | 2025-03-06 | 2025-03-12
I2S-7688-MP-74.D.W.20.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.8680 | DSN - E8 - DDD - Design Development - Bridges - Burley Griffin Way Overbridge | 2025-04-08 | 2025-06-05
I2S-7688-MP-74.D.W.20.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.8690 | DSN - E8 - DDD - Internal IDR workshop (By BGE) | 2025-05-30 | 2025-06-05
I2S-7688-MP-74.D.W.20.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.8710 | DSN - E8 - DDD - Review of IDR comment response and final review - Bridges | 2025-06-06 | 2025-06-06
I2S-7688-MP-74.D.W.20.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.8720 | DSN - E8 - DDD - Incorporate IDR comments | 2025-06-10 | 2025-06-16
I2S-7688-MP-74.D.W.20.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.8730 | DSN - E8 - DDD - Issue Responses & Receive Comment Closeout | 2025-06-10 | 2025-06-16
I2S-7688-MP-74.D.W.20.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.8740 | DSN - E8 - DDD - Submission to IRPL | 2025-06-17 | 2025-06-17
I2S-7688-MP-74.D.W.20.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.8750 | DSN - E8 - DDD - IRPL Review (20 B.days) | 2025-06-18 | 2025-07-15
I2S-7688-MP-74.D.W.20.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.8840 | DSN - E8 - DDD - TfNSW (30 B.days) - Burley Griffin Way Overbridge - Major WAD link | 2025-06-18 | 2025-07-29
I2S-7688-MP-74.D.W.20.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.12730 | DSN - E8 - DDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.20.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.12750 | DSN - E8 - DDD - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.20.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.18340 | DSN - E8 - DDD - Comment closeout and Design approval
I2S-7688-MP-74.D.W.20.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.18350 | DSN - E8 - DDD - IV Review (30 B.days) - Burley Griffin Way Overbridge - Major WAD link
CCB Gate 4 |  |  |  | 2025-06-18 | 2025-08-05
I2S-7688-MP-74.D.W.20.1 | CCB Gate 4 | I.DE.CCB.1950 | DSN - E8 - CCB Gate 4 - Meeting - Presentation of CCR Submission to SM Sub CCB - Bridges - BGW Overbridge | 2025-08-04 | 2025-08-04
I2S-7688-MP-74.D.W.20.1 | CCB Gate 4 | I.DE.CCB.1960 | DSN - E8 - CCB Gate 4 - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-06-18 | 2025-06-24
I2S-7688-MP-74.D.W.20.1 | CCB Gate 4 | I.DE.CCB.1970 | DSN - E8 - CCB Gate 4 - IRPL Reviews & Approves CCR Submission | 2025-06-27 | 2025-07-15
I2S-7688-MP-74.D.W.20.1 | CCB Gate 4 | I.DE.CCB.1980 | DSN - E8 - CCB Gate 4 - IRPL Submits CCB to SM Sub CCB | 2025-07-16 | 2025-07-16
I2S-7688-MP-74.D.W.20.1 | CCB Gate 4 | I.DE.CCB.1990 | DSN - E8 - CCB Gate 4 - Configuration Change Acceptance Notice | 2025-08-05 | 2025-08-05
Design Stage 4 - IFC |  |  |  | 2025-07-11 | 2025-10-13
I2S-7688-MP-74.D.W.20.5 | Design Stage 4 - IFC | Cost-IFC-E8 | DSN - E8 - IFC - Cost
I2S-7688-MP-74.D.W.20.5 | Design Stage 4 - IFC | I.DE.02.8790 | DSN - E8 - IFC - Prepare IFC Documentation - Burley Griffin Way Overbridge | 2025-07-11 | 2025-08-15
I2S-7688-MP-74.D.W.20.5 | Design Stage 4 - IFC | I.DE.02.8800 | DSN - E8 - IFC - Submission to IRPL | 2025-08-18 | 2025-08-29
I2S-7688-MP-74.D.W.20.5 | Design Stage 4 - IFC | I.DE.02.8810 | DSN - E8 - IFC - IRPL Review (5 B.days) | 2025-09-01 | 2025-09-05
I2S-7688-MP-74.D.W.20.5 | Design Stage 4 - IFC | I.DE.02.8820 | DSN - E8 - IFC - Package Complete - Bridges |  | 2025-10-13
Design Package E9 - Bridges Type 2 - Old Cootamundra Road Underbridge
Design Stage 1 - Feasibility Design - FDD
I2S-7688-MP-74.D.W.5.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14200 | DSN - E9 - FDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.5.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14210 | DSN - E9 - FDD - Submission to IRPL
I2S-7688-MP-74.D.W.5.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14220 | DSN - E9 - FDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.5.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14230 | DSN - E9 - FDD - Start Package - Bridges - Old Cootamundra Road Underbridge
I2S-7688-MP-74.D.W.5.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14430 | DSN - E9 - FDD - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.5.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14440 | DSN - E9 - FDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.5.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-E9 | DSN - E9 - FDD - Cost
I2S-7688-MP-74.D.W.5.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14150 | DSN - E9 - FDD - Design Development - Bridges - Old Cootamundra Road Underbridge
I2S-7688-MP-74.D.W.5.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14160 | DSN - E9 - FDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.5.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14180 | DSN - E9 - FDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.5.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14190 | DSN - E9 - FDD - Incorporate IDR comments - Old Cootamundra Road Underbridge
Design Stage 2 - Preliminary Design - PDD
I2S-7688-MP-74.D.W.5.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14450 | DSN - E9 - PDD - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.5.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14470 | DSN - E9 - PDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.5.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-E9 | DSN - E9 - PDD - Cost
I2S-7688-MP-74.D.W.5.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14170 | DSN - E9 - PDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.5.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14240 | DSN - E9 - PDD - Design Development - Bridges
I2S-7688-MP-74.D.W.5.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14250 | DSN - E9 - PDD - Internal IDR workshop (By BGE) - bridges (6)
I2S-7688-MP-74.D.W.5.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14270 | DSN - E9 - PDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.5.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14280 | DSN - E9 - PDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.5.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14290 | DSN - E9 - PDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.5.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14300 | DSN - E9 - PDD - Submission to IRPL
I2S-7688-MP-74.D.W.5.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14310 | DSN - E9 - PDD - IRPL Review (20 B.days)
Design Stage 3 - Detailed Design - DDD
I2S-7688-MP-74.D.W.5.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-E9 | DSN - E9 - DDD - Cost
I2S-7688-MP-74.D.W.5.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14380 | DSN - E9 - DDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.5.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14460 | DSN - E9 - DDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.5.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14480 | DSN - E9 - DDD - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.5.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14260 | DSN - E9 - DDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.5.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14320 | DSN - E9 - DDD - Design Development - Bridges - Old Cootamundra Road Underbridge
I2S-7688-MP-74.D.W.5.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14330 | DSN - E9 - DDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.5.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14340 | DSN - E9 - DDD - Review of IDR comment response and final review - Bridges
I2S-7688-MP-74.D.W.5.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14350 | DSN - E9 - DDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.5.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14360 | DSN - E9 - DDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.5.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14370 | DSN - E9 - DDD - Submission to IRPL
CCB Gate 4
I2S-7688-MP-74.D.W.5.1 | CCB Gate 4 | I.DE.CCB.5750 | DSN - E9 - CCB Gate 4 - Meeting - Presentation of CCR Submission to SM Sub CCB - Bridges
I2S-7688-MP-74.D.W.5.1 | CCB Gate 4 | I.DE.CCB.5760 | DSN - E9 - CCB Gate 4 - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.D.W.5.1 | CCB Gate 4 | I.DE.CCB.5770 | DSN - E9 - CCB Gate 4 - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.W.5.1 | CCB Gate 4 | I.DE.CCB.5780 | DSN - E9 - CCB Gate 4 - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.D.W.5.1 | CCB Gate 4 | I.DE.CCB.5790 | DSN - E9 - CCB Gate 4 - Configuration Change Acceptance Notice
Design Stage 4 - IFC
I2S-7688-MP-74.D.W.5.5 | Design Stage 4 - IFC | Cost-IFC-E9 | DSN - E9 - IFC - Cost
I2S-7688-MP-74.D.W.5.5 | Design Stage 4 - IFC | I.DE.02.14390 | DSN - E9 - IFC - Prepare IFC Documentation - Bridges - Old Cootamundra Road Underbridge
I2S-7688-MP-74.D.W.5.5 | Design Stage 4 - IFC | I.DE.02.14400 | DSN - E9 - IFC - Submission to IRPL
I2S-7688-MP-74.D.W.5.5 | Design Stage 4 - IFC | I.DE.02.14410 | DSN - E9 - IFC - IRPL Review (5 B.days)
I2S-7688-MP-74.D.W.5.5 | Design Stage 4 - IFC | I.DE.02.14420 | DSN - E9 - IFC - Package Complete - Bridges- Old Cootamundra Road Underbridge
Design Package H1 - Bridges Type 1 - Ulandra Creek Underbridge |  |  |  | 2024-10-03 | 2025-09-08
Design Stage 1 - Feasibility Design - FDD |  |  |  | 2024-10-03 | 2025-01-17
I2S-7688-MP-74.D.W.23.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-H1 | DSN - H1 - FDD - Cost
I2S-7688-MP-74.D.W.23.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.18180 | DSN - H1 - FDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.23.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.18190 | DSN - H1 - FDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.23.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.11370 | DSN - H1 - FDD - Design Development - Bridges - Ulandra Creek Underbridge | 2024-10-03 | 2024-11-21
I2S-7688-MP-74.D.W.23.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.11380 | DSN - H1 - FDD - Internal IDR workshop (By BGE) | 2024-11-15 | 2024-11-21
I2S-7688-MP-74.D.W.23.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.11400 | DSN - H1 - FDD - Review of IDR comment response and final review | 2024-11-22 | 2024-11-28
I2S-7688-MP-74.D.W.23.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.11410 | DSN - H1 - FDD - Incorporate IDC & CDR comments | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.D.W.23.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.11420 | DSN - H1 - FDD - Issue Responses & Receive Comment Closeout | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.D.W.23.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.11430 | DSN - H1 - FDD - Submission to IRPL | 2024-12-06 | 2024-12-06
I2S-7688-MP-74.D.W.23.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.11440 | DSN - H1 - FDD - IRPL Review (20 B.days) - Ulandra Creek Underbridge | 2024-12-09 | 2025-01-17
I2S-7688-MP-74.D.W.23.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.11450 | DSN - H1 - FDD - Start Package H1 - Bridges | 2024-10-03
Design Stage 2 - Preliminary Design - PDD |  |  |  | 2024-11-15 | 2025-05-01
I2S-7688-MP-74.D.W.23.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.11500 | DSN - H1 - PDD - Incorporate IDC & CDR comments | 2025-03-17 | 2025-03-28
I2S-7688-MP-74.D.W.23.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.11510 | DSN - H1 - PDD - Issue Responses & Receive Comment Closeout | 2025-03-24 | 2025-03-28
I2S-7688-MP-74.D.W.23.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.11520 | DSN - H1 - PDD - Submission to IRPL | 2025-03-31 | 2025-03-31
I2S-7688-MP-74.D.W.23.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.11530 | DSN - H1 - PDD - IRPL Review (20 B.days) - Ulandra Creek Underbridge | 2025-04-01 | 2025-05-01
I2S-7688-MP-74.D.W.23.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-H1 | DSN - H1 - PDD - Cost
I2S-7688-MP-74.D.W.23.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.18200 | DSN - H1 - PDD - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.23.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.18210 | DSN - H1 - PDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.23.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.11390 | DSN - H1 - PDD - Safety Assurance / SiD | 2024-11-15 | 2024-11-21
I2S-7688-MP-74.D.W.23.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.11460 | DSN - H1 - PDD - Design Development - Ulandra Creek Underbridge | 2024-12-06 | 2025-03-07
I2S-7688-MP-74.D.W.23.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.11470 | DSN - H1 - PDD - Internal IDR workshop (By BGE) | 2025-03-03 | 2025-03-07
I2S-7688-MP-74.D.W.23.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.11490 | DSN - H1 - PDD - Review of IDR comment response and final review | 2025-03-10 | 2025-03-14
Design Stage 3 - Detailed Design - DDD |  |  |  | 2025-03-03 | 2025-07-11
I2S-7688-MP-74.D.W.23.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-H1 | DSN - H1 - DDD - Cost
I2S-7688-MP-74.D.W.23.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.18220 | DSN - H1 - DDD - Internal IDR Review (By JHG)- (Modified)
I2S-7688-MP-74.D.W.23.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.18230 | DSN - H1 - DDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.23.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.11480 | DSN - H1 - DDD - Safety Assurance / SiD | 2025-03-03 | 2025-03-07
I2S-7688-MP-74.D.W.23.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.11540 | DSN - H1 - DDD - Design Development - Bridges - Ulandra Creek Underbridge | 2025-03-31 | 2025-05-28
I2S-7688-MP-74.D.W.23.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.11550 | DSN - H1 - DDD - Internal IDR workshop (By BGE) | 2025-05-22 | 2025-05-28
I2S-7688-MP-74.D.W.23.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.11570 | DSN - H1 - DDD - Review of IDR comment response and final review | 2025-05-29 | 2025-06-04
I2S-7688-MP-74.D.W.23.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.11580 | DSN - H1 - DDD - Incorporate IDC & CDR comments | 2025-06-05 | 2025-06-12
I2S-7688-MP-74.D.W.23.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.11590 | DSN - H1 - DDD - Issue Responses & Receive Comment Closeout - Bridges | 2025-06-05 | 2025-06-12
I2S-7688-MP-74.D.W.23.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.11600 | DSN - H1 - DDD - Submission to IRPL | 2025-06-13 | 2025-06-13
I2S-7688-MP-74.D.W.23.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.11610 | DSN - H1 - DDD - IRPL Review (20 B.days) - Ulandra Creek Underbridge | 2025-06-16 | 2025-07-11
CCB Gate 4 (Combined for H1, H2, H3, H4, & H5) |  |  |  | 2025-06-13 | 2025-08-05
I2S-7688-MP-74.D.W.23.1 | CCB Gate 4 (Combined for H1, H2, H3, H4, & H5) | I.DE.CCB.2450 | DSN - H1 - CCB Gate 4 - Meeting - Presentation of CCR Submission to SM Sub CCB - (H1, H2 , H3, H4 & H5) | 2025-08-04 | 2025-08-04
I2S-7688-MP-74.D.W.23.1 | CCB Gate 4 (Combined for H1, H2, H3, H4, & H5) | I.DE.CCB.2460 | DSN - H1 - CCB Gate 4 - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-06-13 | 2025-07-04
I2S-7688-MP-74.D.W.23.1 | CCB Gate 4 (Combined for H1, H2, H3, H4, & H5) | I.DE.CCB.2470 | DSN - H1 - CCB Gate 4 - IRPL Reviews & Approves CCR Submission - (H1, H2 , H3, H4 & H5) | 2025-07-07 | 2025-07-23
I2S-7688-MP-74.D.W.23.1 | CCB Gate 4 (Combined for H1, H2, H3, H4, & H5) | I.DE.CCB.2480 | DSN - H1 - CCB Gate 4 - IRPL Submits CCB to SM Sub CCB - (H1, H2 , H3, H4 & H5) | 2025-07-24 | 2025-07-24
I2S-7688-MP-74.D.W.23.1 | CCB Gate 4 (Combined for H1, H2, H3, H4, & H5) | I.DE.CCB.2490 | DSN - H1 - CCB Gate 4 - Configuration Change Acceptance Notice - (H1, H2 , H3, H4 & H5) | 2025-08-05 | 2025-08-05
Design Stage 4 - IFC |  |  |  | 2025-07-07 | 2025-09-08
I2S-7688-MP-74.D.W.23.5 | Design Stage 4 - IFC | I.DE.02.11650 | DSN - H1 - IFC - Package Complete - Bridges - Ulandra Creek Underbridge |  | 2025-09-08
I2S-7688-MP-74.D.W.23.5 | Design Stage 4 - IFC | Cost-IFC-H1 | DSN - H1 - IFC - Cost
I2S-7688-MP-74.D.W.23.5 | Design Stage 4 - IFC | I.DE.02.11620 | DSN - H1 - IFC - Prepare IFC Documentation - Bridges - Ulandra Creek Underbridge | 2025-07-07 | 2025-08-18
I2S-7688-MP-74.D.W.23.5 | Design Stage 4 - IFC | I.DE.02.11630 | DSN - H1 - IFC - Submission to IRPL | 2025-08-19 | 2025-09-01
I2S-7688-MP-74.D.W.23.5 | Design Stage 4 - IFC | I.DE.02.11640 | DSN - H1 - IFC - IRPL Review (5 B.days) | 2025-09-02 | 2025-09-08
Design Package H2 - Bridges Type 1 - Run Boundary Creek Underbridge
Design Stage 1 - Feasibility Design - FDD
I2S-7688-MP-74.D.W.9.13 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.12770 | DSN - H2 - FDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.9.13 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-H2 | DSN - H2 - FDD - Cost
I2S-7688-MP-74.D.W.9.13 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.12790 | DSN - H2 - FDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.9.13 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.12800 | DSN - H2 - FDD - Incorporate IDR comments - Run Boundary Creek Underbridge
I2S-7688-MP-74.D.W.9.13 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.12810 | DSN - H2 - FDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.9.13 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.12820 | DSN - H2 - FDD - Submission to IRPL
I2S-7688-MP-74.D.W.9.13 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.12830 | DSN - H2 - FDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.9.13 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.12840 | DSN - H2 - FDD - Start Package - Bridges - Run Boundary Creek Underbridge
I2S-7688-MP-74.D.W.9.13 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13070 | DSN - H2 - FDD - Internal IDR Review (By JHG)- (Modified)
I2S-7688-MP-74.D.W.9.13 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13080 | DSN - H2 - FDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.9.13 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.12760 | DSN - H2 - FDD - Design Development - Bridges - Run Boundary Creek Underbridge
Design Stage 2 - Preliminary Design - PDD
I2S-7688-MP-74.D.W.9.34 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13110 | DSN - H2 - PDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.9.34 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-H2 | DSN - H2 - PDD - Cost
I2S-7688-MP-74.D.W.9.34 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.12780 | DSN - H2 - PDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.9.34 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.12850 | DSN - H2 - PDD - Design Development - Bridges - Run Boundary Creek Underbridge
I2S-7688-MP-74.D.W.9.34 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.12860 | DSN - H2 - PDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.9.34 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.12880 | DSN - H2 - PDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.9.34 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.12890 | DSN - H2 - PDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.9.34 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.12900 | DSN - H2 - PDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.9.34 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.12910 | DSN - H2 - PDD - Submission to IRPL
I2S-7688-MP-74.D.W.9.34 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.12920 | DSN - H2 - PDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.9.34 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13090 | DSN - H2 - PDD - Internal IDR Review (By JHG) - (Modified)
Design Stage 3 - Detailed Design - DDD
I2S-7688-MP-74.D.W.9.35 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-H2 | DSN - H2 - DDD - Cost
I2S-7688-MP-74.D.W.9.35 | Design Stage 3 - Detailed Design - DDD | I.DE.02.12870 | DSN - H2 - DDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.9.35 | Design Stage 3 - Detailed Design - DDD | I.DE.02.12940 | DSN - H2 - DDD - Design Development - Bridges - Run Boundary Creek Underbridge
I2S-7688-MP-74.D.W.9.35 | Design Stage 3 - Detailed Design - DDD | I.DE.02.12950 | DSN - H2 - DDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.9.35 | Design Stage 3 - Detailed Design - DDD | I.DE.02.12960 | DSN - H2 - DDD - Review of IDR comment response and final review - Run Boundary Creek Underbridge
I2S-7688-MP-74.D.W.9.35 | Design Stage 3 - Detailed Design - DDD | I.DE.02.12970 | DSN - H2 - DDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.9.35 | Design Stage 3 - Detailed Design - DDD | I.DE.02.12980 | DSN - H2 - DDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.9.35 | Design Stage 3 - Detailed Design - DDD | I.DE.02.12990 | DSN - H2 - DDD - Submission to IRPL
I2S-7688-MP-74.D.W.9.35 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13000 | DSN - H2 - DDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.9.35 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13100 | DSN - H2 - DDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.9.35 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13120 | DSN - H2 - DDD - Internal IDR Review (By JHG) - (Modified)
Design Stage 4 - IFC
I2S-7688-MP-74.D.W.9.16 | Design Stage 4 - IFC | Cost-IFC-H2 | DSN - H2 - IFC - Cost
I2S-7688-MP-74.D.W.9.16 | Design Stage 4 - IFC | I.DE.02.13020 | DSN - H2 - IFC - Prepare IFC Documentation - Run Boundary Creek Underbridge
I2S-7688-MP-74.D.W.9.16 | Design Stage 4 - IFC | I.DE.02.13030 | DSN - H2 - IFC - Submission to IRPL
I2S-7688-MP-74.D.W.9.16 | Design Stage 4 - IFC | I.DE.02.13040 | DSN - H2 - IFC - IRPL Review (5 B.days)
I2S-7688-MP-74.D.W.9.16 | Design Stage 4 - IFC | I.DE.02.13050 | DSN - H2 - IFC - Package Complete - Run Boundary Creek Underbridge
Design Package H3 - Bridges Type 1 - Dirnaseer Road Underbridge
Design Stage 1 - Feasibility Design - FDD
I2S-7688-MP-74.D.W.36.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-H3 | DSN - H3 - FDD - Cost
I2S-7688-MP-74.D.W.36.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13410 | DSN - H3 - FDD - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.36.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13420 | DSN - H3 - FDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.36.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13140 | DSN - H3 - FDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.36.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13130 | DSN - H3 - FDD - Design Development - Bridges - Dirnaseer Road Underbridge
I2S-7688-MP-74.D.W.36.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13160 | DSN - H3 - FDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.36.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13170 | DSN - H3 - FDD - Incorporate IDR comments - Dirnaseer Road Underbridge
I2S-7688-MP-74.D.W.36.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13180 | DSN - H3 - FDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.36.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13190 | DSN - H3 - FDD - Submission to IRPL
I2S-7688-MP-74.D.W.36.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13200 | DSN - H3 - FDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.36.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13210 | DSN - H3 - FDD - Start Package - Bridges - Dirnaseer Road Underbridge
Design Stage 2 - Preliminary Design - PDD
I2S-7688-MP-74.D.W.36.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13230 | DSN - H3 - PDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.36.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-H3 | DSN - H3 - PDD - Cost
I2S-7688-MP-74.D.W.36.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13430 | DSN - H3 - PDD - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.36.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13450 | DSN - H3 - PDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.36.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13150 | DSN - H3 - PDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.36.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13220 | DSN - H3 - PDD - Design Development - Bridges
I2S-7688-MP-74.D.W.36.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13250 | DSN - H3 - PDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.36.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13260 | DSN - H3 - PDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.36.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13270 | DSN - H3 - PDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.36.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13280 | DSN - H3 - PDD - Submission to IRPL
I2S-7688-MP-74.D.W.36.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13290 | DSN - H3 - PDD - IRPL Review (20 B.days)
Design Stage 3 - Detailed Design - DDD
I2S-7688-MP-74.D.W.36.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-H3 | DSN - H3 - DDD - Cost
I2S-7688-MP-74.D.W.36.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13300 | DSN - H3 - DDD - Bridges - DirnaseerRoad Underbridge
I2S-7688-MP-74.D.W.36.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13310 | DSN - H3 - DDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.36.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13320 | DSN - H3 - DDD - Review of IDR comment response and final review - DirnaseerRoad Underbridge
I2S-7688-MP-74.D.W.36.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13330 | DSN - H3 - DDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.36.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13340 | DSN - H3 - DDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.36.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13350 | DSN - H3 - DDD - Submission to IRPL
I2S-7688-MP-74.D.W.36.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13360 | DSN - H3 - DDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.36.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13440 | DSN - H3 - DDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.36.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13460 | DSN - H3 - DDD - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.36.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13240 | DSN - H3 - DDD - Safety Assurance / SiD
Design Stage 4 - IFC
I2S-7688-MP-74.D.W.36.5 | Design Stage 4 - IFC | Cost-IFC-H3 | DSN - H3 - IFC - Cost
I2S-7688-MP-74.D.W.36.5 | Design Stage 4 - IFC | I.DE.02.13370 | DSN - H3 - IFC - Prepare IFC Documentation - Dirnaseer Road Underbridge
I2S-7688-MP-74.D.W.36.5 | Design Stage 4 - IFC | I.DE.02.13390 | DSN - H3 - IFC - IRPL Review (5 B.days)
I2S-7688-MP-74.D.W.36.5 | Design Stage 4 - IFC | I.DE.02.13400 | DSN - H3 - IFC - IFC Package Complete H3 - Dirnaseer Road Underbridge
I2S-7688-MP-74.D.W.36.5 | Design Stage 4 - IFC | I.DE.02.13380 | DSN - H3 - IFC - Submission to IRPL
Design Package H4 - Bridges Type 1 - Isobel Creek Underbridge
Design Stage 1 - Feasibility Design - FDD
I2S-7688-MP-74.D.W.33.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13540 | DSN - H4 - FDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.33.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13550 | DSN - H4 - FDD - Start Package - Bridges - Isobel Creek Underbridge
I2S-7688-MP-74.D.W.33.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13750 | DSN - H4 - FDD - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.33.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13760 | DSN - H4 - FDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.33.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13480 | DSN - H4 - FDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.33.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13500 | DSN - H4 - FDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.33.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-H4 | DSN - H4 - FDD - Cost
I2S-7688-MP-74.D.W.33.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13470 | DSN - H4 - FDD - Design Development - Bridges - Isobel Creek Underbridge
I2S-7688-MP-74.D.W.33.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13510 | DSN - H4 - FDD - Incorporate IDR comments - Isobel Creek Underbridge
I2S-7688-MP-74.D.W.33.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13520 | DSN - H4 - FDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.33.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13530 | DSN - H4 - FDD - Submission to IRPL
Design Stage 2 - Preliminary Design - PDD
I2S-7688-MP-74.D.W.33.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13630 | DSN - H4 - PDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.33.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13770 | DSN - H4 - PDD - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.33.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13790 | DSN - H4 - PDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.33.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-H4 | DSN - H4 - PDD - Cost
I2S-7688-MP-74.D.W.33.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13490 | DSN - H4 - PDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.33.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13560 | DSN - H4 - PDD - Design Development - Bridges
I2S-7688-MP-74.D.W.33.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13570 | DSN - H4 - PDD - Internal IDR workshop (By BGE) - bridges (6)
I2S-7688-MP-74.D.W.33.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13590 | DSN - H4 - PDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.33.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13600 | DSN - H4 - PDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.33.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13610 | DSN - H4 - PDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.33.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13620 | DSN - H4 - PDD - Submission to IRPL
Design Stage 3 - Detailed Design - DDD
I2S-7688-MP-74.D.W.33.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13800 | DSN - H4 - DDD - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.33.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13640 | DSN - H4 - DDD - Design Development - Bridges - Isobel Creek Underbridge
I2S-7688-MP-74.D.W.33.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-H4 | DSN - H4 - DDD - Cost
I2S-7688-MP-74.D.W.33.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13580 | DSN - H4 - DDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.33.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13650 | DSN - H4 - DDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.33.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13660 | DSN - H4 - DDD - Review of IDR comment response and final review - Bridges
I2S-7688-MP-74.D.W.33.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13670 | DSN - H4 - DDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.33.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13680 | DSN - H4 - DDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.33.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13690 | DSN - H4 - DDD - Submission to IRPL
I2S-7688-MP-74.D.W.33.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13700 | DSN - H4 - DDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.33.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13780 | DSN - H4 - DDD - Design Presentation to IRPL - DPK Presentation - (Modified)
Design Stage 4 - IFC
I2S-7688-MP-74.D.W.33.5 | Design Stage 4 - IFC | I.DE.02.13710 | DSN - H4 - IFC - Prepare IFC Documentation - Isobel Creek Underbridge
I2S-7688-MP-74.D.W.33.5 | Design Stage 4 - IFC | I.DE.02.13720 | DSN - H4 - IFC - Submission to IRPL
I2S-7688-MP-74.D.W.33.5 | Design Stage 4 - IFC | Cost-IFC-H4 | DSN - H4 - IFC - Cost
I2S-7688-MP-74.D.W.33.5 | Design Stage 4 - IFC | I.DE.02.13730 | DSN - H4 - IFC - IRPL Review (5 B.days)
I2S-7688-MP-74.D.W.33.5 | Design Stage 4 - IFC | I.DE.02.13740 | DSN - H4 - IFC - IFC Package Complete H4 - Isobel Creek Underbridge
Design Package H5 - Bridges Type 1 - Isobel Creek Tributary Underbridge
Design Stage 1 - Feasibility Design - FDD
I2S-7688-MP-74.D.W.32.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13890 | DSN - H5 - FDD - Start Package - Bridges - Isobel Creek Underbridge
I2S-7688-MP-74.D.W.32.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14090 | DSN - H5 - FDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.32.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14100 | DSN - H5 - FDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.32.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-H5 | DSN - H5 - FDD - Cost
I2S-7688-MP-74.D.W.32.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13810 | DSN - H5 - FDD - Design Development - Bridges - Isobel Creek Tributary Under
I2S-7688-MP-74.D.W.32.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13820 | DSN - H5 - FDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.32.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13840 | DSN - H5 - FDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.32.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13850 | DSN - H5 - FDD - Incorporate IDR comments - Isobel Creek Tributary Underbridge
I2S-7688-MP-74.D.W.32.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13860 | DSN - H5 - FDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.32.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13870 | DSN - H5 - FDD - Submission to IRPL
I2S-7688-MP-74.D.W.32.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.13880 | DSN - H5 - FDD - IRPL Review (20 B.days)
Design Stage 2 - Preliminary Design - PDD
I2S-7688-MP-74.D.W.32.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-H5 | DSN - H5 - PDD - Cost
I2S-7688-MP-74.D.W.32.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13830 | DSN - H5 - PDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.32.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13900 | DSN - H5 - PDD - Design Development - Isobel Creek Tributary Underbridge
I2S-7688-MP-74.D.W.32.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13910 | DSN - H5 - PDD - Internal IDR workshop (By BGE) (Modified)
I2S-7688-MP-74.D.W.32.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13930 | DSN - H5 - PDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.32.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13940 | DSN - H5 - PDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.32.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13950 | DSN - H5 - PDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.32.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13960 | DSN - H5 - PDD - Submission to IRPL
I2S-7688-MP-74.D.W.32.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.13970 | DSN - H5 - PDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.32.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14110 | DSN - H5 - PDD - Internal IDR Review (By JHG)
I2S-7688-MP-74.D.W.32.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14130 | DSN - H5 - PDD - Design Presentation to IRPL - DPK Presentation (Modified)
Design Stage 3 - Detailed Design - DDD
I2S-7688-MP-74.D.W.32.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14030 | DSN - H5 - DDD - Submission to IRPL
I2S-7688-MP-74.D.W.32.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14040 | DSN - H5 - DDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.32.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14120 | DSN - H5 - DDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.32.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14140 | DSN - H5 - DDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.32.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-H5 | DSN - H5 - DDD - Cost
I2S-7688-MP-74.D.W.32.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13920 | DSN - H5 - DDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.32.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13980 | DSN - H5 - DDD - Design Development - Bridges - Isobel Creek Tributary Underbrid
I2S-7688-MP-74.D.W.32.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.13990 | DSN - H5 - DDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.32.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14000 | DSN - H5 - DDD - Review of IDR comment response and final review - Isobel Creek Tributary Underbridge
I2S-7688-MP-74.D.W.32.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14010 | DSN - H5 - DDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.32.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14020 | DSN - H5 - DDD - Issue Responses & Receive Comment Closeout
Design Stage 4 - IFC
I2S-7688-MP-74.D.W.32.5 | Design Stage 4 - IFC | Cost-IFC-H5 | DSN - H5 - IFC - Cost
I2S-7688-MP-74.D.W.32.5 | Design Stage 4 - IFC | I.DE.02.14050 | DSN - H5 - IFC - Prepare IFC Documentation - Isobel Creek Tributary Underbridge
I2S-7688-MP-74.D.W.32.5 | Design Stage 4 - IFC | I.DE.02.14060 | DSN - H5 - IFC - Submission to IRPL
I2S-7688-MP-74.D.W.32.5 | Design Stage 4 - IFC | I.DE.02.14070 | DSN - H5 - IFC - IRPL Review (5 B.days)
I2S-7688-MP-74.D.W.32.5 | Design Stage 4 - IFC | I.DE.02.14080 | DSN - H5 - IFC - Package Complete - Isobel Creek Tributary Underbridge
Design Package H6 - Bridges Type 3 - Billabong Creek Underbridge
Design Stage 1 - Feasibility Design - FDD
I2S-7688-MP-74.D.W.14.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17890 | DSN - H6 - FDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.14.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17900 | DSN - H6 - FDD - Submission to IRPL
I2S-7688-MP-74.D.W.14.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17910 | DSN - H6 - FDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.14.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17920 | DSN - H6 - FDD - Start Package - Bridges - Billabong Creek Underbridge
I2S-7688-MP-74.D.W.14.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.18120 | DSN - H6 - FDD - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.14.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.18130 | DSN - H6 - FDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.14.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-H6 | DSN - H6 - FDD - Cost
I2S-7688-MP-74.D.W.14.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17840 | DSN - H6 - FDD - Design Development - Bridges - Billabong Creek Underbridge
I2S-7688-MP-74.D.W.14.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17850 | DSN - H6 - FDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.14.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17870 | DSN - H6 - FDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.14.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17880 | DSN - H6 - FDD - Incorporate IDR comments - Billabong Creek Underbridge
Design Stage 2 - Preliminary Design - PDD
I2S-7688-MP-74.D.W.14.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.18160 | DSN - H6 - PDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.14.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-H6 | DSN - H6 - PDD - Cost
I2S-7688-MP-74.D.W.14.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17860 | DSN - H6 - PDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.14.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17930 | DSN - H6 - PDD - Design Development - Bridges
I2S-7688-MP-74.D.W.14.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17940 | DSN - H6 - PDD - Internal IDR workshop (By BGE) - bridges (6)
I2S-7688-MP-74.D.W.14.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17960 | DSN - H6 - PDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.14.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17970 | DSN - H6 - PDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.14.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17980 | DSN - H6 - PDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.14.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17990 | DSN - H6 - PDD - Submission to IRPL
I2S-7688-MP-74.D.W.14.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.18000 | DSN - H6 - PDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.14.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.18140 | DSN - H6 - PDD - Internal IDR Review (By JHG) - (Modified)
Design Stage 3 - Detailed Design - DDD
I2S-7688-MP-74.D.W.14.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-H6 | DSN - H6 - DDD - Cost
I2S-7688-MP-74.D.W.14.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17950 | DSN - H6 - DDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.14.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.18010 | DSN - H6 - DDD - Design Development - Bridges - Billabong Creek Underbridge
I2S-7688-MP-74.D.W.14.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.18020 | DSN - H6 - DDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.14.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.18030 | DSN - H6 - DDD - Review of IDR comment response and final review - Bridges
I2S-7688-MP-74.D.W.14.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.18040 | DSN - H6 - DDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.14.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.18050 | DSN - H6 - DDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.14.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.18060 | DSN - H6 - DDD - Submission to IRPL
I2S-7688-MP-74.D.W.14.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.18070 | DSN - H6 - DDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.14.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.18150 | DSN - H6 - DDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.14.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.18170 | DSN - H6 - DDD - Internal IDR Review (By JHG) (Modified)
CCB Gate 4 (Combined for H6, H7, H8 & H9)
I2S-7688-MP-74.D.W.14.1 | CCB Gate 4 (Combined for H6, H7, H8 & H9) | I.DE.CCB.6660 | DSN - H6 - CCB Gate 4 - Prepare & Submit CCR Checklist /Presentation Material to IRPL (H6, H7, H8, & H9)
I2S-7688-MP-74.D.W.14.1 | CCB Gate 4 (Combined for H6, H7, H8 & H9) | I.DE.CCB.6670 | DSN - H6 - CCB Gate 4 - IRPL Reviews & Approves CCR Submission (H6, H7, H8, & H9)
I2S-7688-MP-74.D.W.14.1 | CCB Gate 4 (Combined for H6, H7, H8 & H9) | I.DE.CCB.6680 | DSN - H6 - CCB Gate 4 - IRPL Submits CCB to SM Sub CCB (H6, H7, H8, & H9)
I2S-7688-MP-74.D.W.14.1 | CCB Gate 4 (Combined for H6, H7, H8 & H9) | I.DE.CCB.6690 | DSN - H6 - CCB Gate 4 - Configuration Change Acceptance Notice (H6, H7, H8, & H9)
I2S-7688-MP-74.D.W.14.1 | CCB Gate 4 (Combined for H6, H7, H8 & H9) | I.DE.CCB.6650 | DSN - H6 - CCB Gate 4 - Meeting - Presentation of CCR Submission to SM Sub CCB - Bridges - (H6, H7, H8, & H9)
Design Stage 4 - IFC
I2S-7688-MP-74.D.W.14.5 | Design Stage 4 - IFC | Cost-IFC-H6 | DSN - H6 - IFC - Cost
I2S-7688-MP-74.D.W.14.5 | Design Stage 4 - IFC | I.DE.02.18080 | DSN - H6 - IFC - Prepare IFC Documentation - Billabong Creek Underbridge
I2S-7688-MP-74.D.W.14.5 | Design Stage 4 - IFC | I.DE.02.18090 | DSN - H6 - IFC - Submission to IRPL
I2S-7688-MP-74.D.W.14.5 | Design Stage 4 - IFC | I.DE.02.18100 | DSN - H6 - IFC - IRPL Review (5 B.days)
I2S-7688-MP-74.D.W.14.5 | Design Stage 4 - IFC | I.DE.02.18110 | DSN - H6 - IFC - Package Complete - Billabong Creek Underbridge
Design Package H7 - Bridges Type 3 - Powder Horn Creek Underbridges
Design Stage 1 - Feasibility Design - FDD
I2S-7688-MP-74.D.W.31.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14550 | DSN - H7 - FDD - Submission to IRPL
I2S-7688-MP-74.D.W.31.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14560 | DSN - H7 - FDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.31.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14570 | DSN - H7 - FDD - Start Package - Bridges - Powder Horn Creek Underbridges
I2S-7688-MP-74.D.W.31.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14770 | DSN - H7 - FDD - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.31.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14780 | DSN - H7 - FDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.31.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-H7 | DSN - H7 - FDD - Cost
I2S-7688-MP-74.D.W.31.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14490 | DSN - H7 - FDD - Design Development - Bridges - Powder Horn Creek Underbridges
I2S-7688-MP-74.D.W.31.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14500 | DSN - H7 - FDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.31.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14520 | DSN - H7 - FDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.31.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14530 | DSN - H7 - FDD - Incorporate IDR comments - Powder Horn Creek Underbridges
I2S-7688-MP-74.D.W.31.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14540 | DSN - H7 - FDD - Issue Responses & Receive Comment Closeout
Design Stage 2 - Preliminary Design - PDD
I2S-7688-MP-74.D.W.31.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-H7 | DSN - H7 - PDD - Cost
I2S-7688-MP-74.D.W.31.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14510 | DSN - H7 - PDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.31.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14580 | DSN - H7 - PDD - Design Development - Bridges
I2S-7688-MP-74.D.W.31.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14590 | DSN - H7 - PDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.31.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14610 | DSN - H7 - PDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.31.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14620 | DSN - H7 - PDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.31.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14630 | DSN - H7 - PDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.31.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14640 | DSN - H7 - PDD - Submission to IRPL
I2S-7688-MP-74.D.W.31.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14650 | DSN - H7 - PDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.31.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14790 | DSN - H7 - PDD - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.31.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14810 | DSN - H7 - PDD - Design Presentation to IRPL - DPK Presentation (Modified)
Design Stage 3 - Detailed Design - DDD
I2S-7688-MP-74.D.W.31.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14800 | DSN - H7 - DDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.31.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14820 | DSN - H7 - DDD - Internal IDR Review (By JHG) - (Modified)
I2S-7688-MP-74.D.W.31.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-H7 | DSN - H7 - DDD - Cost
I2S-7688-MP-74.D.W.31.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14600 | DSN - H7 - DDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.31.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14660 | DSN - H7 - DDD - Design Development - Stage 3 - Bridges - Powder Horn Creek Underbridges
I2S-7688-MP-74.D.W.31.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14670 | DSN - H7 - DDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.31.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14680 | DSN - H7 - DDD - Review of IDR comment response and final review - Powder Horn Creek Underbridges
I2S-7688-MP-74.D.W.31.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14690 | DSN - H7 - DDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.31.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14700 | DSN - H7 - DDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.31.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14710 | DSN - H7 - DDD - Submission to IRPL
I2S-7688-MP-74.D.W.31.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14720 | DSN - H7 - DDD - IRPL Review (20 B.days)
Design Stage 4 - IFC
I2S-7688-MP-74.D.W.31.5 | Design Stage 4 - IFC | Cost-IFC-H7 | DSN - H7 - IFC - Cost
I2S-7688-MP-74.D.W.31.5 | Design Stage 4 - IFC | I.DE.02.14730 | DSN - H7 - IFC - Prepare IFC Documentation - Powder Horn Creek Underbridges
I2S-7688-MP-74.D.W.31.5 | Design Stage 4 - IFC | I.DE.02.14740 | DSN - H7 - IFC - Submission to IRPL
I2S-7688-MP-74.D.W.31.5 | Design Stage 4 - IFC | I.DE.02.14750 | DSN - H7 - IFC - IRPL Review (5 B.days)
I2S-7688-MP-74.D.W.31.5 | Design Stage 4 - IFC | I.DE.02.14760 | DSN - H7 - IFC - Package Complete - BridgesPowder Horn Creek Underbridges
Design Package H9 - Bridges Type 3 - Dudauman Creek Underbridge
Design Stage 1 - Feasibility Design - FDD
I2S-7688-MP-74.D.W.29.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15450 | DSN - H9 - FDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.29.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15460 | DSN - H9 - FDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.29.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-H9 | DSN - H9 - FDD - Cost
I2S-7688-MP-74.D.W.29.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15170 | DSN - H9 - FDD - Design Development - Bridges - Dudauman Creek Underbridge
I2S-7688-MP-74.D.W.29.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15180 | DSN - H9 - FDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.29.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15200 | DSN - H9 - FDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.29.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15210 | DSN - H9 - FDD - Incorporate IDR comments - Dudauman Creek Underbridge
I2S-7688-MP-74.D.W.29.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15220 | DSN - H9 - FDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.29.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15230 | DSN - H9 - FDD - Submission to IRPL
I2S-7688-MP-74.D.W.29.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15240 | DSN - H9 - FDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.29.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15250 | DSN - H9 - FDD - Start Package - Bridges - Dudauman Creek Underbridge
Design Stage 2 - Preliminary Design - PDD
I2S-7688-MP-74.D.W.29.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-H9 | DSN - H9 - PDD - Cost
I2S-7688-MP-74.D.W.29.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.15470 | DSN - H9 - PDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.29.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.15490 | DSN - H9 - PDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.29.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.15190 | DSN - H9 - PDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.29.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.15260 | DSN - H9 - PDD - Design Development - Bridges
I2S-7688-MP-74.D.W.29.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.15270 | DSN - H9 - PDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.29.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.15290 | DSN - H9 - PDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.29.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.15300 | DSN - H9 - PDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.29.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.15310 | DSN - H9 - PDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.29.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.15320 | DSN - H9 - PDD - Submission to IRPL
I2S-7688-MP-74.D.W.29.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.15330 | DSN - H9 - PDD - IRPL Review (20 B.days)
Design Stage 3 - Detailed Design - DDD
I2S-7688-MP-74.D.W.29.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15370 | DSN - H9 - DDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.29.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15380 | DSN - H9 - DDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.29.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15390 | DSN - H9 - DDD - Submission to IRPL
I2S-7688-MP-74.D.W.29.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15400 | DSN - H9 - DDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.29.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15480 | DSN - H9 - DDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.29.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15500 | DSN - H9 - DDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.29.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-H9 | DSN - H9 - DDD - Cost
I2S-7688-MP-74.D.W.29.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15280 | DSN - H9 - DDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.29.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15340 | DSN - H9 - DDD - Design Development - Bridges - Dudauman Creek Underbridge
I2S-7688-MP-74.D.W.29.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15350 | DSN - H9 - DDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.29.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15360 | DSN - H9 - DDD - Review of IDR comment response and final review - Dudauman Creek Underbridge
Design Stage 4 - IFC
I2S-7688-MP-74.D.W.29.5 | Design Stage 4 - IFC | Cost-IFC-H9 | DSN - H9 - IFC - Cost
I2S-7688-MP-74.D.W.29.5 | Design Stage 4 - IFC | I.DE.02.15410 | DSN - H9 - IFC - Prepare IFC Documentation - Dudauman Creek Underbridge
I2S-7688-MP-74.D.W.29.5 | Design Stage 4 - IFC | I.DE.02.15420 | DSN - H9 - IFC - Submission to IRPL
I2S-7688-MP-74.D.W.29.5 | Design Stage 4 - IFC | I.DE.02.15430 | DSN - H9 - IFC - IRPL Review (5 B.days)
I2S-7688-MP-74.D.W.29.5 | Design Stage 4 - IFC | I.DE.02.15440 | DSN - H9 - IFC - Package Complete - Bridges - Dudauman Creek Underbridge
Design Package L1 - Stock Underpasses and Miscellaneous Structures (Was in W.12) |  |  |  | 2024-11-29 | 2025-09-11
Design Stage 1 - Feasibility Design - FDD |  |  |  | 2024-11-29 | 2025-03-24
I2S-7688-MP-74.D.W.12.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-L1 | DSN - L1 - FDD - Cost
I2S-7688-MP-74.D.W.12.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.9750 | DSN - L1 - FDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.12.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.9760 | DSN - L1 - FDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.12.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.8810 | DSN - L1 - FDD - Internal IDR workshop (By BGE) | 2025-02-03 | 2025-02-07
I2S-7688-MP-74.D.W.12.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.8830 | DSN - L1 - FDD - Review of IDR comment response and final review | 2025-02-10 | 2025-02-14
I2S-7688-MP-74.D.W.12.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.8840 | DSN - L1 - FDD - Incorporate IDR comments | 2025-02-17 | 2025-02-21
I2S-7688-MP-74.D.W.12.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.8850 | DSN - L1 - FDD - Issue Responses & Receive Comment Closeout | 2025-02-17 | 2025-02-21
I2S-7688-MP-74.D.W.12.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.8860 | DSN - L1 - FDD - Submission to IRPL | 2025-02-24 | 2025-02-24
I2S-7688-MP-74.D.W.12.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.8870 | DSN - L1 - FDD - IRPL Review (20 B.days) | 2025-02-25 | 2025-03-24
I2S-7688-MP-74.D.W.12.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.04.12310 | DSN - L1 - FDD - Start Package - Stock Underpasses | 2024-11-29
I2S-7688-MP-74.D.W.12.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.00.8800 | DSN - L1 - FDD - Design Development - Stock Underpasses | 2024-11-29 | 2025-02-07
Design Stage 2 - Preliminary Design - PDD |  |  |  | 2025-02-03 | 2025-06-13
I2S-7688-MP-74.D.W.12.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-L1 | DSN - L1 - PDD - Cost
I2S-7688-MP-74.D.W.12.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.00.9770 | DSN - L1 - PDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.12.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.00.9780 | DSN - L1 - PDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.12.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.00.8820 | DSN - L1 - PDD - Safety Assurance / SiD | 2025-02-03 | 2025-02-07
I2S-7688-MP-74.D.W.12.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.00.8880 | DSN - L1 - PDD - Design Development - Stock Underpasses | 2025-02-24 | 2025-04-22
I2S-7688-MP-74.D.W.12.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.00.8890 | DSN - L1 - PDD - Internal IDR workshop (By BGE) | 2025-04-14 | 2025-04-22
I2S-7688-MP-74.D.W.12.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.00.8910 | DSN - L1 - PDD - Review of IDR comment response and final review | 2025-04-23 | 2025-04-30
I2S-7688-MP-74.D.W.12.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.00.8920 | DSN - L1 - PDD - Incorporate IDR comments | 2025-05-01 | 2025-05-14
I2S-7688-MP-74.D.W.12.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.00.8930 | DSN - L1 - PDD - Issue Responses & Receive Comment Closeout | 2025-05-08 | 2025-05-14
I2S-7688-MP-74.D.W.12.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.00.8940 | DSN - L1 - PDD - Submission to IRPL | 2025-05-15 | 2025-05-15
I2S-7688-MP-74.D.W.12.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.00.8950 | DSN - L1 - PDD - IRPL Review (20 B.days) | 2025-05-16 | 2025-06-13
Design Stage 3 - Detailed Design - DDD |  |  |  | 2025-04-14 | 2025-08-11
I2S-7688-MP-74.D.W.12.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-L1 | DSN - L1 - DDD - Cost
I2S-7688-MP-74.D.W.12.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.9790 | DSN - L1 - DDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.12.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.9800 | DSN - L1 - DDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.12.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.8900 | DSN - L1 - DDD - Safety Assurance / SiD | 2025-04-14 | 2025-04-22
I2S-7688-MP-74.D.W.12.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.8960 | DSN - L1 - DDD - Design Development - Stock Underpasses | 2025-05-16 | 2025-06-27
I2S-7688-MP-74.D.W.12.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.8970 | DSN - L1 - DDD - Internal IDR workshop (By BGE) | 2025-06-24 | 2025-06-27
I2S-7688-MP-74.D.W.12.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.8990 | DSN - L1 - DDD - Review of IDR comment response and final review | 2025-06-30 | 2025-07-04
I2S-7688-MP-74.D.W.12.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.9000 | DSN - L1 - DDD - Incorporate IDR comments | 2025-07-07 | 2025-07-11
I2S-7688-MP-74.D.W.12.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.9010 | DSN - L1 - DDD - Issue Responses & Receive Comment Closeout | 2025-07-07 | 2025-07-11
I2S-7688-MP-74.D.W.12.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.9020 | DSN - L1 - DDD - Submission to IRPL | 2025-07-14 | 2025-07-14
I2S-7688-MP-74.D.W.12.4 | Design Stage 3 - Detailed Design - DDD | I.DE.00.9030 | DSN - L1 - DDD - IRPL Review (20 B.days) | 2025-07-14 | 2025-08-11
CCB Combined (Gate 3 & 4) |  |  |  | 2025-07-15 | 2025-08-21
I2S-7688-MP-74.D.W.12.1 | CCB Combined (Gate 3 & 4) | I.DE.CCB.1650 | DSN - L1 - CCB G3 + G4 - Meeting - Presentation of CCR Submission to SM Sub CCB - Stock Underpasses | 2025-08-20 | 2025-08-20
I2S-7688-MP-74.D.W.12.1 | CCB Combined (Gate 3 & 4) | I.DE.CCB.1660 | DSN - L1 - CCB G3 + G4 - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-07-15 | 2025-07-21
I2S-7688-MP-74.D.W.12.1 | CCB Combined (Gate 3 & 4) | I.DE.CCB.1670 | DSN - L1 - CCB G3 + G4 - IRPL Reviews & Approves CCR Submission | 2025-07-23 | 2025-08-11
I2S-7688-MP-74.D.W.12.1 | CCB Combined (Gate 3 & 4) | I.DE.CCB.1680 | DSN - L1 - CCB G3 + G4 - IRPL Submits CCB to SM Sub CCB | 2025-08-12 | 2025-08-12
I2S-7688-MP-74.D.W.12.1 | CCB Combined (Gate 3 & 4) | I.DE.CCB.1690 | DSN - L1 - CCB G3 + G4 - Configuration Change Acceptance Notice | 2025-08-21 | 2025-08-21
Design Stage 4 - IFC |  |  |  | 2025-07-22 | 2025-09-11
I2S-7688-MP-74.D.W.12.5 | Design Stage 4 - IFC | Cost-IFC-L1 | DSN - L1 - IFC - Cost
I2S-7688-MP-74.D.W.12.5 | Design Stage 4 - IFC | I.DE.00.9040 | DSN - L1 - IFC - Prepare IFC Documentation - Stock Underpasses | 2025-07-22 | 2025-08-26
I2S-7688-MP-74.D.W.12.5 | Design Stage 4 - IFC | I.DE.00.9050 | DSN - L1 - IFC - Submission to IRPL | 2025-08-22 | 2025-09-04
I2S-7688-MP-74.D.W.12.5 | Design Stage 4 - IFC | I.DE.00.9060 | DSN - L1 - IFC - Issue Responses & Receive Comment Closeout | 2025-08-29 | 2025-09-04
I2S-7688-MP-74.D.W.12.5 | Design Stage 4 - IFC | I.DE.00.9070 | DSN - L1 - IFC - Package Complete - Stock Underpasses |  | 2025-09-11
I2S-7688-MP-74.D.W.12.5 | Design Stage 4 - IFC | I.DE.00.9680 | DSN - L1 - IFC - IRPL Review (5 B.days) | 2025-09-05 | 2025-09-11
Design Package L2 - Corridor (Maintenance Responsibility Plans) (Was in W.11) |  |  |  | 2024-12-05 | 2025-11-03
Design Stage 1 - Feasibility Design - FDD |  |  |  | 2024-12-05 | 2025-03-28
I2S-7688-MP-74.D.W.11.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15520 | DSN - L2 - FDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.11.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.8050 | DSN - L2 - FDD - Design Development - Maintenance plans & Access | 2024-12-05 | 2025-02-06
I2S-7688-MP-74.D.W.11.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.8060 | DSN - L2 - FDD - Internal IDR workshop (By BGE) | 2025-02-07 | 2025-02-13
I2S-7688-MP-74.D.W.11.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.8080 | DSN - L2 - FDD - Review of IDR comment response and final review | 2025-02-14 | 2025-02-20
I2S-7688-MP-74.D.W.11.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.8090 | DSN - L2 - FDD - Incorporate IDR comments | 2025-02-21 | 2025-02-27
I2S-7688-MP-74.D.W.11.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.8100 | DSN - L2 - FDD - Issue Responses & Receive Comment Closeout L2 - Maintenance plans & Access | 2025-02-21 | 2025-02-27
I2S-7688-MP-74.D.W.11.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.8120 | DSN - L2 - FDD - Submission to IRPL | 2025-02-28 | 2025-02-28
I2S-7688-MP-74.D.W.11.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.8130 | DSN - L2 - FDD - IRPL Review (20 B.days) | 2025-03-03 | 2025-03-28
I2S-7688-MP-74.D.W.11.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.8410 | DSN - L2 - FDD - Start Package - Corridor | 2024-12-05
I2S-7688-MP-74.D.W.11.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-L2 | DSN - L2 - FDD - Cost L2
I2S-7688-MP-74.D.W.11.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15510 | DSN - L2 - FDD - Internal IDR Review (By JHG) (Modified)
Design Stage 1 - Feasibility Design - DDD
I2S-7688-MP-74.D.W.11.1 | Design Stage 1 - Feasibility Design - DDD | I.DE.02.18240 | DSN - L2 - DDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.11.1 | Design Stage 1 - Feasibility Design - DDD | Cost-DDD-L2 | DSN - L2 - DDD - Cost
I2S-7688-MP-74.D.W.11.1 | Design Stage 1 - Feasibility Design - DDD | I.DE.02.18250 | DSN - L2 - DDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.11.1 | Design Stage 1 - Feasibility Design - DDD | I.DE.02.18260 | DSN - L2 - DDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.11.1 | Design Stage 1 - Feasibility Design - DDD | I.DE.02.18270 | DSN - L2 - DDD - Design Development - Maintenance plans & Access
I2S-7688-MP-74.D.W.11.1 | Design Stage 1 - Feasibility Design - DDD | I.DE.02.18280 | DSN - L2 - DDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.11.1 | Design Stage 1 - Feasibility Design - DDD | I.DE.02.18290 | DSN - L2 - DDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.11.1 | Design Stage 1 - Feasibility Design - DDD | I.DE.02.18300 | DSN - L2 - DDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.11.1 | Design Stage 1 - Feasibility Design - DDD | I.DE.02.18310 | DSN - L2 - DDD - Issue Responses & Receive Comment Closeout L2 - Maintenance plans & Access
I2S-7688-MP-74.D.W.11.1 | Design Stage 1 - Feasibility Design - DDD | I.DE.02.18320 | DSN - L2 - DDD - Submission to IRPL
I2S-7688-MP-74.D.W.11.1 | Design Stage 1 - Feasibility Design - DDD | I.DE.02.18330 | DSN - L2 - DDD - IRPL Review (20 B.days)
Design Stage 4 - IFC |  |  |  | 2025-09-01 | 2025-11-03
I2S-7688-MP-74.D.W.11.5 | Design Stage 4 - IFC | Cost-IFC-L2 | DSN - L2 - IFC - Cost
I2S-7688-MP-74.D.W.11.5 | Design Stage 4 - IFC | I.DE.02.8360 | DSN - L2 - IFC - Prepare IFC Documentation - Corridor (Maintenance plans & Access) | 2025-09-01 | 2025-10-13
I2S-7688-MP-74.D.W.11.5 | Design Stage 4 - IFC | I.DE.02.8370 | DSN - L2 - IFC - Submission to IRPL | 2025-10-14 | 2025-10-27
I2S-7688-MP-74.D.W.11.5 | Design Stage 4 - IFC | I.DE.02.8390 | DSN - L2 - IFC - IRPL Review (5 B.days) | 2025-10-28 | 2025-11-03
I2S-7688-MP-74.D.W.11.5 | Design Stage 4 - IFC | I.DE.02.8400 | DSN - L2 - IFC - Package Complete - Corridor (Maintenance plans & Access) |  | 2025-11-03
Design Package L3 - Corridor (Maintenance Access and RMAR) (Was in W.11)
Design Stage 1 - Feasibility Design - FDD
I2S-7688-MP-74.D.W.34.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-L3 | DSN - L3 - FDD - Cost
I2S-7688-MP-74.D.W.34.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15570 | DSN - L3 - FDD - Design Development - Maintenance Access and RMAR
I2S-7688-MP-74.D.W.34.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15580 | DSN - L3 - FDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.34.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15600 | DSN - L3 - FDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.34.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15610 | DSN - L3 - FDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.34.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15620 | DSN - L3 - FDD - Issue Responses & Receive Comment Closeout - Maintenance Access and RMAR
I2S-7688-MP-74.D.W.34.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15630 | DSN - L3 - FDD - Submission to IRPL
I2S-7688-MP-74.D.W.34.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15640 | DSN - L3 - FDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.34.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15680 | DSN - L3 - FDD - Start Package - Corridor
I2S-7688-MP-74.D.W.34.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15940 | DSN - L3 - FDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.34.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15950 | DSN - L3 - FDD - Design Presentation to IRPL - DPK Presentation - Stage 1 (Modified)
Design Stage 2 - Preliminary Design - PDD
I2S-7688-MP-74.D.W.34.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-L3 | DSN - L3 - PDD - Cost
I2S-7688-MP-74.D.W.34.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.15730 | DSN - L3 - PDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.34.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.15740 | DSN - L3 - PDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.34.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.15750 | DSN - L3 - PDD - Submission to IRPL
I2S-7688-MP-74.D.W.34.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.15760 | DSN - L3 - PDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.34.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.15960 | DSN - L3 - PDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.34.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.15970 | DSN - L3 - PDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.34.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.15590 | DSN - L3 - PDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.34.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.15690 | DSN - L3 - PDD - Design Development - Maintenance Access and RMAR
I2S-7688-MP-74.D.W.34.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.15700 | DSN - L3 - PDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.34.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.15720 | DSN - L3 - PDD - Review of IDR comment response and final review
Design Stage 3 - Detailed Design - DDD
I2S-7688-MP-74.D.W.34.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-L3 | DSN - L3 - DDD - Cost
I2S-7688-MP-74.D.W.34.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15710 | DSN - L3 - DDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.34.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15800 | DSN - L3 - DDD - Design Development - Maintenance Access and RMAR
I2S-7688-MP-74.D.W.34.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15810 | DSN - L3 - DDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.34.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15820 | DSN - L3 - DDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.34.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15830 | DSN - L3 - DDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.34.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15840 | DSN - L3 - DDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.34.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15850 | DSN - L3 - DDD - Submission to IRPL2
I2S-7688-MP-74.D.W.34.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15860 | DSN - L3 - DDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.34.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15980 | DSN - L3 - DDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.34.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15990 | DSN - L3 - DDD - Design Presentation to IRPL - DPK Presentation - (Modified)
CCB Combined Gate 3 & 4
I2S-7688-MP-74.D.W.34.1 | CCB Combined Gate 3 & 4 | I.DE.CCB.6170 | DSN - L3 - CCB G3 + G4 - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.W.34.1 | CCB Combined Gate 3 & 4 | I.DE.CCB.6180 | DSN - L3 - CCB G3 + G4 - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.D.W.34.1 | CCB Combined Gate 3 & 4 | I.DE.CCB.6190 | DSN - L3 - CCB G3 + G4 - Configuration Change Acceptance Notice
I2S-7688-MP-74.D.W.34.1 | CCB Combined Gate 3 & 4 | I.DE.CCB.6150 | DSN - L3 - CCB G3 + G4 - Meeting - Presentation of CCR Submission to SM Sub CCB - Corridor
I2S-7688-MP-74.D.W.34.1 | CCB Combined Gate 3 & 4 | I.DE.CCB.6160 | DSN - L3 - CCB G3 + G4 - Prepare & Submit CCR Checklist /Presentation Material to IRPL
Design Stage 4 - IFC
I2S-7688-MP-74.D.W.34.5 | Design Stage 4 - IFC | Cost-IFC-L3 | DSN - L3 - IFC - Cost
I2S-7688-MP-74.D.W.34.5 | Design Stage 4 - IFC | I.DE.02.15900 | DSN - L3 - IFC - Prepare IFC Documentation - Corridor (Maintenance Access and RMAR)
I2S-7688-MP-74.D.W.34.5 | Design Stage 4 - IFC | I.DE.02.15910 | DSN - L3 - IFC - Submission to IRPL
I2S-7688-MP-74.D.W.34.5 | Design Stage 4 - IFC | I.DE.02.15920 | DSN - L3 - IFC - IRPL Review (5 B.days)
I2S-7688-MP-74.D.W.34.5 | Design Stage 4 - IFC | I.DE.02.15930 | DSN - L3 - IFC - Package Complete - Corridor (Maintenance Access and RMAR)
Design Package L4 - Corridor (Rail Systems Civil Works) (Was in W11) |  |  |  | 2024-12-05 | 2025-07-16
Design Stage 1 - Feasibility Design - FDD |  |  |  | 2024-12-05 | 2025-02-13
I2S-7688-MP-74.D.W.28.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD- L4 | DSN - L4 - FDD - Cost
I2S-7688-MP-74.D.W.28.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16010 | DSN - L4 - FDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.28.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16030 | DSN - L4 - FDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.28.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16040 | DSN - L4 - FDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.28.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16050 | DSN - L4 - FDD - Issue Responses & Receive Comment Closeout - Rail Systems Civil Works
I2S-7688-MP-74.D.W.28.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16060 | DSN - L4 - FDD - Submission to IRPL
I2S-7688-MP-74.D.W.28.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16070 | DSN - L4 - FDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.28.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16110 | DSN - L4 - FDD - Start Package - Corridor
I2S-7688-MP-74.D.W.28.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16370 | DSN - L4 - FDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.28.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16380 | DSN - L4 - FDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.28.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.3650 | DSN - L4 - FDD - Design Development - Rail Systems Civil Works | 2024-12-05 | 2025-02-13
CCB Gate 3
I2S-7688-MP-74.D.W.28.6 | CCB Gate 3 | I.DE.CCB.6300 | DSN - L4 - CCB Gate 3 - Meeting - Presentation of CCR Submission to SM Sub CCB - Corridor
I2S-7688-MP-74.D.W.28.6 | CCB Gate 3 | I.DE.CCB.6310 | DSN - L4 - CCB Gate 3 - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.D.W.28.6 | CCB Gate 3 | I.DE.CCB.6320 | DSN - L4 - CCB Gate 3 - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.W.28.6 | CCB Gate 3 | I.DE.CCB.6330 | DSN - L4 - CCB Gate 3 - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.D.W.28.6 | CCB Gate 3 | I.DE.CCB.6340 | DSN - L4 - CCB Gate 3 - Configuration Change Acceptance Notice
Design Stage 2 - Preliminary Design - PDD |  |  |  | 2025-02-28 | 2025-04-29
I2S-7688-MP-74.D.W.28.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.16400 | DSN - L4 - PDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.28.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.3660 | DSN - L4 - PDD - Design Development - Rail Systems Civil Works | 2025-02-28 | 2025-04-29
I2S-7688-MP-74.D.W.28.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-L4 | DSN - L4 - PDD - Cost
I2S-7688-MP-74.D.W.28.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.16020 | DSN - L4 - PDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.28.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.16130 | DSN - L4 - PDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.28.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.16150 | DSN - L4 - PDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.28.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.16160 | DSN - L4 - PDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.28.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.16170 | DSN - L4 - PDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.28.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.16180 | DSN - L4 - PDD - Submission to IRPL
I2S-7688-MP-74.D.W.28.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.16190 | DSN - L4 - PDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.28.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.16390 | DSN - L4 - PDD - Internal IDR Review (By JHG) (Modified)
Design Stage 3 - Detailed Design - DDD |  |  |  | 2025-05-21 | 2025-07-16
I2S-7688-MP-74.D.W.28.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.16250 | DSN - L4 - DDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.28.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.16260 | DSN - L4 - DDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.28.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-L4 | DSN - L4 - DDD - Cost
I2S-7688-MP-74.D.W.28.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.16140 | DSN - L4 - DDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.28.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.16240 | DSN - L4 - DDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.28.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.16270 | DSN - L4 - DDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.28.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.16280 | DSN - L4 - DDD - Submission to IRPL2
I2S-7688-MP-74.D.W.28.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.16290 | DSN - L4 - DDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.28.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.16410 | DSN - L4 - DDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.28.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.16420 | DSN - L4 - DDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.28.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.3670 | DSN - L4 - DDD - Design Development - Rail Systems Civil Works | 2025-05-21 | 2025-07-16
CCB Gate 4
I2S-7688-MP-74.D.W.28.1 | CCB Gate 4 | I.DE.CCB.6250 | DSN - L4 - CCB G4 - Meeting - Presentation of CCR Submission to SM Sub CCB - Corridor
I2S-7688-MP-74.D.W.28.1 | CCB Gate 4 | I.DE.CCB.6260 | DSN - L4 - CCB G4 - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.D.W.28.1 | CCB Gate 4 | I.DE.CCB.6270 | DSN - L4 - CCB G4 - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.W.28.1 | CCB Gate 4 | I.DE.CCB.6280 | DSN - L4 - CCB G4 - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.D.W.28.1 | CCB Gate 4 | I.DE.CCB.6290 | DSN - L4 - CCB G4 - Configuration Change Acceptance Notice
CRN CCB Gate 2
I2S-7688-MP-74.D.W.28.7 | CRN CCB Gate 2 | I.DE.CCB.7800 | DSN - L4 - CCB G2 - CCB Gate 2 Meeting - Presentation of CCR Submission
I2S-7688-MP-74.D.W.28.7 | CRN CCB Gate 2 | I.DE.CCB.7810 | DSN - L4 - CCB G2 - Prepare & Submit CCR Checklist /Presentation Material
I2S-7688-MP-74.D.W.28.7 | CRN CCB Gate 2 | I.DE.CCB.7820 | DSN - L4 - CCB G2 - UGLRL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.W.28.7 | CRN CCB Gate 2 | I.DE.CCB.7830 | DSN - L4 - CCB G2 - UGLRL Submits CCB
I2S-7688-MP-74.D.W.28.7 | CRN CCB Gate 2 | I.DE.CCB.7840 | DSN - L4 - CCB G2 - Configuration Change Acceptance Notice
Design Stage 4 - IFC
I2S-7688-MP-74.D.W.28.5 | Design Stage 4 - IFC | Cost-IFC-L4 | DSN - L4 - IFC - Cost
I2S-7688-MP-74.D.W.28.5 | Design Stage 4 - IFC | I.DE.02.16340 | DSN - L4 - IFC - Submission to IRPL
I2S-7688-MP-74.D.W.28.5 | Design Stage 4 - IFC | I.DE.02.16350 | DSN - L4 - IFC - IRPL Review (5 B.days)
I2S-7688-MP-74.D.W.28.5 | Design Stage 4 - IFC | I.DE.02.16360 | DSN - L4 - IFC - Package Complete - Corridor (Rail Systems Civil Works)
I2S-7688-MP-74.D.W.28.5 | Design Stage 4 - IFC | I.DE.02.16330 | DSN - L4 - IFC - Prepare IFC Documentation - Corridor (Rail Systems Civil Works)
Design Package L5 - Corridor (Landscape) (Was in W11) |  |  |  | 2024-12-05 | 2025-07-07
Design Stage 1 - Feasibility Design - FDD |  |  |  | 2024-12-05 | 2025-02-06
I2S-7688-MP-74.D.W.27.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16440 | DSN - L5 - FDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.27.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16460 | DSN - L5 - FDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.27.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16540 | DSN - L5 - FDD - Start Package - Corridor
I2S-7688-MP-74.D.W.27.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-L5 | DSN - L5 - FDD - Cost
I2S-7688-MP-74.D.W.27.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16470 | DSN - L5 - FDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.27.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16480 | DSN - L5 - FDD - Issue Responses & Receive Comment Closeout L5 - Landscape
I2S-7688-MP-74.D.W.27.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16490 | DSN - L5 - FDD - Submission to IRPL
I2S-7688-MP-74.D.W.27.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16500 | DSN - L5 - FDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.27.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16800 | DSN - L5 - FDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.27.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16810 | DSN - L5 - FDD - Design Presentation to IRPL - DPK Presentation L5 - Stage 1 (Modified)
I2S-7688-MP-74.D.W.27.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.3680 | DSN - L5 - FDD - Design Development - Landscape | 2024-12-05 | 2025-02-06
Design Stage 3 - Detailed Design - DDD |  |  |  | 2025-05-26 | 2025-07-07
I2S-7688-MP-74.D.W.27.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.3700 | DSN - L5 - DDD - Design Development - Landscape | 2025-05-26 | 2025-07-07
I2S-7688-MP-74.D.W.27.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-L5 | DSN - L5 - DDD - Cost
I2S-7688-MP-74.D.W.27.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.16570 | DSN - L5 - DDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.27.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.16670 | DSN - L5 - DDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.27.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.16680 | DSN - L5 - DDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.27.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.16690 | DSN - L5 - DDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.27.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.16700 | DSN - L5 - DDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.27.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.16710 | DSN - L5 - DDD - Submission to IRPL2
I2S-7688-MP-74.D.W.27.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.16720 | DSN - L5 - DDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.27.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.16840 | DSN - L5 - DDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.27.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.16850 | DSN - L5 - DDD - Design Presentation to IRPL - DPK Presentation - (Modified)
Design Stage 4 - IFC
I2S-7688-MP-74.D.W.27.5 | Design Stage 4 - IFC | Cost-IFC-L5 | DSN - L5 - IFC - Cost
I2S-7688-MP-74.D.W.27.5 | Design Stage 4 - IFC | I.DE.02.16760 | DSN - L5 - IFC - Prepare IFC Documentation - Corridor (Landscape)
I2S-7688-MP-74.D.W.27.5 | Design Stage 4 - IFC | I.DE.02.16770 | DSN - L5 - IFC - Submission to IRPL
I2S-7688-MP-74.D.W.27.5 | Design Stage 4 - IFC | I.DE.02.16780 | DSN - L5 - IFC - IRPL Review (5 B.days)
I2S-7688-MP-74.D.W.27.5 | Design Stage 4 - IFC | I.DE.02.16790 | DSN - L5 - IFC - Package Complete - Corridor (Landscape)
Design Package L6 - Corridor (Fencing and Security) (Was in W11) |  |  |  | 2024-12-05 | 2025-07-10
Design Stage 1 - Feasibility Design - FDD |  |  |  | 2024-12-05 | 2025-02-06
I2S-7688-MP-74.D.W.26.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-L6 | DSN - L6 - FDD - Cost
I2S-7688-MP-74.D.W.26.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16870 | DSN - L6 - FDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.26.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16890 | DSN - L6 - FDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.26.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16900 | DSN - L6 - FDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.26.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16910 | DSN - L6 - FDD - Issue Responses & Receive Comment Closeout - Maintenance plans & Access
I2S-7688-MP-74.D.W.26.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16920 | DSN - L6 - FDD - Submission to IRPL
I2S-7688-MP-74.D.W.26.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16930 | DSN - L6 - FDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.26.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.16970 | DSN - L6 - FDD - Start Package - Corridor
I2S-7688-MP-74.D.W.26.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17230 | DSN - L6 - FDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.26.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17240 | DSN - L6 - FDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.26.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.4160 | DSN - L6 - FDD - Design Development - Fencing and Security | 2024-12-05 | 2025-02-06
Design Stage 2 - Preliminary Design - PDD |  |  |  | 2025-03-03 | 2025-04-22
I2S-7688-MP-74.D.W.26.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-L6 | DSN - L6 - PDD - Cost
I2S-7688-MP-74.D.W.26.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.16880 | DSN - L6 - PDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.26.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.16990 | DSN - L6 - PDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.26.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17010 | DSN - L6 - PDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.26.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17020 | DSN - L6 - PDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.26.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17030 | DSN - L6 - PDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.26.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17040 | DSN - L6 - PDD - Submission to IRPL
I2S-7688-MP-74.D.W.26.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17050 | DSN - L6 - PDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.26.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17250 | DSN - L6 - PDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.26.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17260 | DSN - L6 - PDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.26.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.4150 | DSN - L6 - PDD - Design Development - Fencing and Security | 2025-03-03 | 2025-04-22
Design Stage 3 - Detailed Design - DDD |  |  |  | 2025-05-22 | 2025-07-10
I2S-7688-MP-74.D.W.26.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-L6 | DSN - L6 - DDD - Cost
I2S-7688-MP-74.D.W.26.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17000 | DSN - L6 - DDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.26.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17100 | DSN - L6 - DDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.26.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17110 | DSN - L6 - DDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.26.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17120 | DSN - L6 - DDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.26.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17130 | DSN - L6 - DDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.26.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17140 | DSN - L6 - DDD - Submission to IRPL2
I2S-7688-MP-74.D.W.26.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17150 | DSN - L6 - DDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.26.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17270 | DSN - L6 - DDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.26.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17280 | DSN - L6 - DDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.26.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.4140 | DSN - L6 - DDD - Design Development - Fencing and Security | 2025-05-22 | 2025-07-10
Design Stage 4 - IFC
I2S-7688-MP-74.D.W.26.5 | Design Stage 4 - IFC | Cost-IFC-L6 | DSN - L6 - IFC - Cost
I2S-7688-MP-74.D.W.26.5 | Design Stage 4 - IFC | I.DE.02.17190 | DSN - L6 - IFC - Prepare IFC Documentation - Corridor (Fencing and Security
I2S-7688-MP-74.D.W.26.5 | Design Stage 4 - IFC | I.DE.02.17200 | DSN - L6 - IFC - Submission to IRPL
I2S-7688-MP-74.D.W.26.5 | Design Stage 4 - IFC | I.DE.02.17210 | DSN - L6 - IFC - IRPL Review (5 B.days)
I2S-7688-MP-74.D.W.26.5 | Design Stage 4 - IFC | I.DE.02.17220 | DSN - L6 - IFC - Package Complete L6 - Corridor (Fencing and Security)
Design Package L7 - Corridor (Signage) (Was in W11)
Design Stage 1 - Feasibility Design - FDD
I2S-7688-MP-74.D.W.25.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17660 | DSN - L7 - FDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.25.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17670 | DSN - L7 - FDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.25.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17290 | DSN - L7 - FDD - Design Development - Signage
I2S-7688-MP-74.D.W.25.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17300 | DSN - L7 - FDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.25.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17320 | DSN - L7 - FDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.25.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17330 | DSN - L7 - FDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.25.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17340 | DSN - L7 - FDD - Issue Responses & Receive Comment Closeout - Signage
I2S-7688-MP-74.D.W.25.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17350 | DSN - L7 - FDD - Submission to IRPL
I2S-7688-MP-74.D.W.25.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17360 | DSN - L7 - FDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.25.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.17400 | DSN - L7 - FDD - Start Package - Corridor
I2S-7688-MP-74.D.W.25.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-L7 | DSN - L7 - FDD - Cost
Design Stage 2 - Preliminary Design - PDD
I2S-7688-MP-74.D.W.25.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-L7 | DSN - L7 - PDD - Cost
I2S-7688-MP-74.D.W.25.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17680 | DSN - L7 - PDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.25.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17690 | DSN - L7 - PDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.25.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17310 | DSN - L7 - PDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.25.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17410 | DSN - L7 - PDD - Design Development - Signage
I2S-7688-MP-74.D.W.25.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17420 | DSN - L7 - PDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.25.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17440 | DSN - L7 - PDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.25.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17450 | DSN - L7 - PDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.25.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17460 | DSN - L7 - PDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.25.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17470 | DSN - L7 - PDD - Submission to IRPL
I2S-7688-MP-74.D.W.25.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.17480 | DSN - L7 - PDD - IRPL Review (20 B.days)
Design Stage 3 - Detailed Design - DDD
I2S-7688-MP-74.D.W.25.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17570 | DSN - L7 - DDD - Submission to IRPL
I2S-7688-MP-74.D.W.25.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17580 | DSN - L7 - DDD - IRPL Review (20 B.days)
I2S-7688-MP-74.D.W.25.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17700 | DSN - L7 - DDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.25.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17710 | DSN - L7 - DDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.25.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17430 | DSN - L7 - DDD - Safety Assurance / SiD
I2S-7688-MP-74.D.W.25.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17520 | DSN - L7 - DDD - Design Development - Signage
I2S-7688-MP-74.D.W.25.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17530 | DSN - L7 - DDD - Internal IDR workshop (By BGE)
I2S-7688-MP-74.D.W.25.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17540 | DSN - L7 - DDD - Review of IDR comment response and final review
I2S-7688-MP-74.D.W.25.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17550 | DSN - L7 - DDD - Incorporate IDR comments
I2S-7688-MP-74.D.W.25.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.17560 | DSN - L7 - DDD - Issue Responses & Receive Comment Closeout
I2S-7688-MP-74.D.W.25.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-L7 | DSN - L7 - DDD - Cost
Design Stage 4 - IFC
I2S-7688-MP-74.D.W.25.5 | Design Stage 4 - IFC | Cost-IFC-L7 | DSN - L7 - IFC - Cost
I2S-7688-MP-74.D.W.25.5 | Design Stage 4 - IFC | I.DE.02.17620 | DSN - L7 - IFC - Prepare IFC Documentation - Corridor (Signage)
I2S-7688-MP-74.D.W.25.5 | Design Stage 4 - IFC | I.DE.02.17630 | DSN - L7 - IFC - Submission to IRPL
I2S-7688-MP-74.D.W.25.5 | Design Stage 4 - IFC | I.DE.02.17640 | DSN - L7 - IFC - IRPL Review (5 B.days)
I2S-7688-MP-74.D.W.25.5 | Design Stage 4 - IFC | I.DE.02.17650 | DSN - L7 - IFC - Package Complete - Corridor (Signage)
Design Package L8 - Utilities (Was in 3.08, 2.08, 1.08) |  |  |  | 2024-10-24 | 2025-07-18
Design Stage 1 - Feasibility Design - FDD |  |  |  | 2024-10-24 | 2025-01-31
I2S-7688-MP-74.D.W.21.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-L8 | DSN - L8 - FDD - Cost
I2S-7688-MP-74.D.W.21.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.13580 | DSN - L8 - FDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.21.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.13590 | DSN - L8 - FDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.21.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.11860 | DSN - L8 - FDD - Internal IDR workshop (By BGE) | 2024-11-28 | 2024-12-04
I2S-7688-MP-74.D.W.21.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.11880 | DSN - L8 - FDD - Review of IDR comment response and final review | 2024-12-05 | 2024-12-11
I2S-7688-MP-74.D.W.21.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.11890 | DSN - L8 - FDD - Incorporate IDR comments | 2024-12-12 | 2024-12-18
I2S-7688-MP-74.D.W.21.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.11900 | DSN - L8 - FDD - Issue Responses & Receive Comment Closeout | 2024-12-12 | 2024-12-18
I2S-7688-MP-74.D.W.21.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.11910 | DSN - L8 - FDD - Submission to IRPL | 2024-12-19 | 2024-12-19
I2S-7688-MP-74.D.W.21.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.11920 | DSN - L8 - FDD - IRPL Review (20 B.days) | 2024-12-20 | 2025-01-31
I2S-7688-MP-74.D.W.21.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.11930 | DSN - L8 - FDD - Design Development - Utility Coordination Plans | 2024-10-24 | 2024-12-04
I2S-7688-MP-74.D.W.21.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.11940 | DSN - L8 - FDD - Design Development - Utilities Design | 2024-10-24 | 2024-12-04
I2S-7688-MP-74.D.W.21.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.11950 | DSN - L8 - FDD - Start Package - Utility Infrastructure | 2024-10-24
Design Stage 2 - Preliminary Design - PDD |  |  |  | 2024-11-28 | 2025-04-04
I2S-7688-MP-74.D.W.21.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-L8 | DSN - L8 - PDD - Cost
I2S-7688-MP-74.D.W.21.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.13600 | DSN - L8 - PDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.21.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.13620 | DSN - L8 - PDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.21.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.11870 | DSN - L8 - PDD - Safety Assurance / SiD | 2024-11-28 | 2024-12-04
I2S-7688-MP-74.D.W.21.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.11990 | DSN - L8 - PDD - Incorporate IDR comments | 2025-02-28 | 2025-03-06
I2S-7688-MP-74.D.W.21.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.12000 | DSN - L8 - PDD - Issue Responses & Receive Comment Closeout | 2025-02-28 | 2025-03-06
I2S-7688-MP-74.D.W.21.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.12010 | DSN - L8 - PDD - Submission to IRPL | 2025-03-07 | 2025-03-07
I2S-7688-MP-74.D.W.21.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.12020 | DSN - L8 - PDD - IRPL Review (20 B.days) | 2025-03-10 | 2025-04-04
I2S-7688-MP-74.D.W.21.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.12030 | DSN - L8 - PDD - Design Development - Utility Coordination Plans | 2024-12-19 | 2025-02-20
I2S-7688-MP-74.D.W.21.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.12040 | DSN - L8 - PDD - Design Development - Utilities Design | 2024-12-19 | 2025-02-20
I2S-7688-MP-74.D.W.21.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.11960 | DSN - L8 - PDD - Internal IDR workshop (By BGE) - Utilities (6) | 2025-02-14 | 2025-02-20
I2S-7688-MP-74.D.W.21.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.11980 | DSN - L8 - PDD - Review of IDR comment response and final review | 2025-02-21 | 2025-02-27
Design Stage 3 - Detailed Design - DDD |  |  |  | 2025-02-14 | 2025-06-10
I2S-7688-MP-74.D.W.21.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-L8 | DSN - L8 - DDD - Cost
I2S-7688-MP-74.D.W.21.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.13610 | DSN - L8 - DDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.21.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.13630 | DSN - L8 - DDD - Design Presentation to IRPL - DPK Presentation - (Modified)
I2S-7688-MP-74.D.W.21.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.11970 | DSN - L8 - DDD - Safety Assurance / SiD | 2025-02-14 | 2025-02-20
I2S-7688-MP-74.D.W.21.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.12050 | DSN - L8 - DDD - Internal IDR workshop (By BGE) | 2025-04-16 | 2025-04-24
I2S-7688-MP-74.D.W.21.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.12070 | DSN - L8 - DDD - Review of IDR comment response and final review | 2025-04-28 | 2025-05-02
I2S-7688-MP-74.D.W.21.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.12080 | DSN - L8 - DDD - Incorporate IDR comments | 2025-05-05 | 2025-05-09
I2S-7688-MP-74.D.W.21.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.12090 | DSN - L8 - DDD - Issue Responses & Receive Comment Closeout | 2025-05-05 | 2025-05-09
I2S-7688-MP-74.D.W.21.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.12100 | DSN - L8 - DDD - Submission to IRPL | 2025-05-12 | 2025-05-12
I2S-7688-MP-74.D.W.21.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.12110 | DSN - L8 - DDD - IRPL Review (20 B.days) | 2025-05-13 | 2025-06-10
I2S-7688-MP-74.D.W.21.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.12120 | DSN - L8 - DDD - Design Development - Utility Coordination Plans | 2025-03-12 | 2025-04-24
I2S-7688-MP-74.D.W.21.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.12130 | DSN - L8 - DDD - Design Development - Utilities Design | 2025-03-12 | 2025-04-24
Design Stage 4 - IFC |  |  |  | 2025-05-30 | 2025-07-18
I2S-7688-MP-74.D.W.21.5 | Design Stage 4 - IFC | Cost-IFC-L8 | DSN - L8 - IFC - Cost
I2S-7688-MP-74.D.W.21.5 | Design Stage 4 - IFC | I.DE.03.12180 | DSN - L8 - IFC - Package Complete - Utility Infrastructure |  | 2025-07-18
I2S-7688-MP-74.D.W.21.5 | Design Stage 4 - IFC | I.DE.03.12140 | DSN - L8 - IFC - Prepare IFC Documentation - Utility Infrastructure | 2025-05-30 | 2025-07-04
I2S-7688-MP-74.D.W.21.5 | Design Stage 4 - IFC | I.DE.03.12150 | DSN - L8 - IFC - Submission to IRPL | 2025-07-07 | 2025-07-11
I2S-7688-MP-74.D.W.21.5 | Design Stage 4 - IFC | I.DE.03.12160 | DSN - L8 - IFC - Issue Responses & Receive Comment Closeout | 2025-07-07 | 2025-07-11
I2S-7688-MP-74.D.W.21.5 | Design Stage 4 - IFC | I.DE.03.12170 | DSN - L8 - IFC - IRPL Review (5 B.days) | 2025-07-14 | 2025-07-18
Design Package M1 - Roads - Public (Junee Shire Council) (Was in 2.09 1.09) |  |  |  | 2024-10-03 | 2025-09-30
Design Stage 1 - Feasibility Design - FDD |  |  |  | 2024-10-03 | 2025-02-03
I2S-7688-MP-74.D.W.17.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-M1 | DSN - M1 - FDD - Cost
I2S-7688-MP-74.D.W.17.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.13760 | DSN - M1 - FDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.17.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.13770 | DSN - M1 - FDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.17.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.12190 | DSN - M1 - FDD - Internal IDR workshop (By BGE) | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.D.W.17.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.12210 | DSN - M1 - FDD - Review of IDR comment response and final review | 2024-12-06 | 2024-12-12
I2S-7688-MP-74.D.W.17.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.12220 | DSN - M1 - FDD - Incorporate IDR comments | 2024-12-13 | 2024-12-19
I2S-7688-MP-74.D.W.17.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.12230 | DSN - M1 - FDD - Issue Responses & Receive Comment Closeout | 2024-12-13 | 2024-12-19
I2S-7688-MP-74.D.W.17.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.12240 | DSN - M1 - FDD - Submission to IRPL | 2024-12-20 | 2024-12-20
I2S-7688-MP-74.D.W.17.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.12250 | DSN - M1 - FDD - IRPL Review (20 B.days) | 2025-01-06 | 2025-02-03
I2S-7688-MP-74.D.W.17.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.12260 | DSN - M1 - FDD - Design Development - Roads - Public (Junee Shire Council) | 2024-10-03 | 2024-12-05
I2S-7688-MP-74.D.W.17.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.12280 | DSN - M1 - FDD - Start Package - Roads - Public (Junee Shire Council) | 2024-10-03
Design Stage 2 - Preliminary Design - PDD |  |  |  | 2024-11-29 | 2025-05-01
I2S-7688-MP-74.D.W.17.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-M1 | DSN - M1 - PDD - Cost
I2S-7688-MP-74.D.W.17.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.13780 | DSN - M1 - PDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.17.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.13790 | DSN - M1 - PDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.17.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.12200 | DSN - M1 - PDD - Safety Assurance / SiD | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.D.W.17.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.12290 | DSN - M1 - PDD - Internal IDR workshop (By BGE) | 2025-03-10 | 2025-03-14
I2S-7688-MP-74.D.W.17.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.12310 | DSN - M1 - PDD - Review of IDR comment response and final review | 2025-03-17 | 2025-03-21
I2S-7688-MP-74.D.W.17.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.12320 | DSN - M1 - PDD - Incorporate IDR comments | 2025-03-24 | 2025-03-28
I2S-7688-MP-74.D.W.17.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.12330 | DSN - M1 - PDD - Issue Responses & Receive Comment Closeout | 2025-03-24 | 2025-03-28
I2S-7688-MP-74.D.W.17.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.12340 | DSN - M1 - PDD - Submission to IRPL | 2025-03-31 | 2025-03-31
I2S-7688-MP-74.D.W.17.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.12350 | DSN - M1 - PDD - IRPL Review (20 B.days) | 2025-04-01 | 2025-05-01
I2S-7688-MP-74.D.W.17.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.12360 | DSN - M1 - PDD - Design Development - Roads - Public (Junee Shire Council) | 2024-12-20 | 2025-03-14
Design Stage 3 - Detailed Design - DDD |  |  |  | 2025-03-10 | 2025-07-14
I2S-7688-MP-74.D.W.17.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-M1 | DSN - M1 - DDD - Cost
I2S-7688-MP-74.D.W.17.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.13800 | DSN - M1 - DDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.17.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.13810 | DSN - M1 - DDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.17.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.12300 | DSN - M1 - DDD - Safety Assurance / SiD | 2025-03-10 | 2025-03-14
I2S-7688-MP-74.D.W.17.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.12380 | DSN - M1 - DDD - Internal IDR workshop (By BGE) | 2025-05-23 | 2025-05-29
I2S-7688-MP-74.D.W.17.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.12400 | DSN - M1 - DDD - Review of IDR comment response and final review | 2025-05-30 | 2025-06-05
I2S-7688-MP-74.D.W.17.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.12430 | DSN - M1 - DDD - Submission to IRPL | 2025-06-16 | 2025-06-16
I2S-7688-MP-74.D.W.17.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.12440 | DSN - M1 - DDD - IRPL Review (20 B.days) | 2025-06-17 | 2025-07-14
I2S-7688-MP-74.D.W.17.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.12450 | DSN - M1 - DDD - Design Development - Roads - Public (Junee Shire Council) | 2025-04-15 | 2025-05-29
I2S-7688-MP-74.D.W.17.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.12410 | DSN - M1 - DDD - Incorporate IDR comments | 2025-06-06 | 2025-06-13
I2S-7688-MP-74.D.W.17.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.12420 | DSN - M1 - DDD - Issue Responses & Receive Comment Closeout | 2025-06-06 | 2025-06-13
Design Stage 4 - IFC |  |  |  | 2025-07-25 | 2025-09-30
I2S-7688-MP-74.D.W.17.5 | Design Stage 4 - IFC | Cost-IFC-M1 | DSN - M1 - IFC - Cost
I2S-7688-MP-74.D.W.17.5 | Design Stage 4 - IFC | I.DE.03.12470 | DSN - M1 - IFC - Prep IFC Documentation - Roads - Public (Junee Shire Council) | 2025-07-25 | 2025-08-12
I2S-7688-MP-74.D.W.17.5 | Design Stage 4 - IFC | I.DE.03.12480 | DSN - M1 - IFC - Submission to IRPL | 2025-08-13 | 2025-08-19
I2S-7688-MP-74.D.W.17.5 | Design Stage 4 - IFC | I.DE.03.12490 | DSN - M1 - IFC - Issue Responses & Receive Comment Closeout | 2025-08-13 | 2025-08-19
I2S-7688-MP-74.D.W.17.5 | Design Stage 4 - IFC | I.DE.03.12500 | DSN - M1 - IFC - IRPL Review (5 B.days) | 2025-08-20 | 2025-08-26
I2S-7688-MP-74.D.W.17.5 | Design Stage 4 - IFC | I.DE.03.12510 | DSN - M1 - IFC - Package Complete M1- Public (Junee Shire Council) |  | 2025-09-30
I2S-7688-MP-74.D.W.17.5 | Design Stage 4 - IFC | I.DE.03.13820 | DSN - M1 - IFC - Prep IFC Documentation - Roads - Public- Junee Shire Council - Comments Close out
Design Package M2 - Roads - Public (Cootamundra-Gundagai Regional Council) (Was in 2.09) |  |  |  | 2024-10-03 | 2025-08-26
Design Stage 1 - Feasibility Design - FDD |  |  |  | 2024-10-03 | 2025-01-17
I2S-7688-MP-74.D.W.24.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-M2 | DSN - M2 - FDD - Cost
I2S-7688-MP-74.D.W.24.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.13700 | DSN - M2 - FDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.24.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.13710 | DSN - M2 - FDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.24.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.12880 | DSN - M2 - FDD - Internal IDR workshop (By BGE) | 2024-11-15 | 2024-11-21
I2S-7688-MP-74.D.W.24.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.12900 | DSN - M2 - FDD - Review of IDR comment response and final review | 2024-11-22 | 2024-11-28
I2S-7688-MP-74.D.W.24.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.12910 | DSN - M2 - FDD - Incorporate IDR comments | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.D.W.24.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.12920 | DSN - M2 - FDD - Issue Responses & Receive Comment Closeout | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.D.W.24.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.12930 | DSN - M2 - FDD - Submission to IRPL | 2024-12-06 | 2024-12-06
I2S-7688-MP-74.D.W.24.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.12940 | DSN - M2 - FDD - IRPL Review (20 B.days) | 2024-12-09 | 2025-01-17
I2S-7688-MP-74.D.W.24.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.12950 | DSN - M2 - FDD - Design Development - Roads (Public) | 2024-10-03 | 2024-11-21
I2S-7688-MP-74.D.W.24.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.12970 | DSN - M2 - FDD - Start Package - Roads (Public & Private) | 2024-10-03
Design Stage 2 - Preliminary Design - PDD |  |  |  | 2024-11-15 | 2025-03-24
I2S-7688-MP-74.D.W.24.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.13040 | DSN - M2 - PDD - IRPL Review (20 B.days) | 2025-02-25 | 2025-03-24
I2S-7688-MP-74.D.W.24.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.13050 | DSN - M2 - PDD - Design Development - Roads (Public) | 2024-12-06 | 2025-02-07
I2S-7688-MP-74.D.W.24.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.12890 | DSN - M2 - PDD - Safety Assurance / SiD | 2024-11-15 | 2024-11-21
I2S-7688-MP-74.D.W.24.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.12980 | DSN - M2 - PDD - Internal IDR workshop (By BGE) | 2025-02-03 | 2025-02-07
I2S-7688-MP-74.D.W.24.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-M2 | DSN - M2 - PDD - Cost
I2S-7688-MP-74.D.W.24.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.13720 | DSN - M2 - PDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.24.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.13730 | DSN - M2 - PDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.24.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.13000 | DSN - M2 - PDD - Review of IDR comment response and final review | 2025-02-10 | 2025-02-14
I2S-7688-MP-74.D.W.24.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.13010 | DSN - M2 - PDD - Incorporate IDR comments | 2025-02-17 | 2025-02-21
I2S-7688-MP-74.D.W.24.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.13020 | DSN - M2 - PDD - Issue Responses & Receive Comment Closeout | 2025-02-17 | 2025-02-21
I2S-7688-MP-74.D.W.24.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.13030 | DSN - M2 - PDD - Submission to IRPL | 2025-02-24 | 2025-02-24
Design Stage 3 - Detailed Design - DDD |  |  |  | 2025-02-03 | 2025-06-06
I2S-7688-MP-74.D.W.24.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.13120 | DSN - M2 - DDD - Submission to IRPL | 2025-05-09 | 2025-05-09
I2S-7688-MP-74.D.W.24.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.13130 | DSN - M2 - DDD - IRPL Review (20 B.days) | 2025-05-12 | 2025-06-06
I2S-7688-MP-74.D.W.24.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-M2 | DSN - M2 - DDD - Cost
I2S-7688-MP-74.D.W.24.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.13740 | DSN - M2 - DDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.24.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.13750 | DSN - M2 - DDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.24.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.12990 | DSN - M2 - DDD - Safety Assurance / SiD | 2025-02-03 | 2025-02-07
I2S-7688-MP-74.D.W.24.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.13140 | DSN - M2 - DDD - Design Development - Roads (Public) | 2025-03-11 | 2025-04-23
I2S-7688-MP-74.D.W.24.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.13070 | DSN - M2 - DDD - Internal IDR workshop (By BGE) | 2025-04-15 | 2025-04-23
I2S-7688-MP-74.D.W.24.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.13090 | DSN - M2 - DDD - Review of IDR comment response and final review | 2025-04-24 | 2025-05-01
I2S-7688-MP-74.D.W.24.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.13100 | DSN - M2 - DDD - Incorporate IDR comments | 2025-05-02 | 2025-05-08
I2S-7688-MP-74.D.W.24.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.13110 | DSN - M2 - DDD - Issue Responses & Receive Comment Closeout | 2025-05-02 | 2025-05-08
Design Stage 4 - IFC |  |  |  | 2025-06-20 | 2025-08-26
I2S-7688-MP-74.D.W.24.5 | Design Stage 4 - IFC | Cost-IFC-M2 | DSN - M2 - IFC - Cost
I2S-7688-MP-74.D.W.24.5 | Design Stage 4 - IFC | I.DE.03.13160 | DSN - M2 - IFC - Prepare IFC Documentation - Roads (Public & Private) | 2025-06-20 | 2025-07-07
I2S-7688-MP-74.D.W.24.5 | Design Stage 4 - IFC | I.DE.03.13170 | DSN - M2 - IFC - Submission to IRPL | 2025-07-08 | 2025-07-14
I2S-7688-MP-74.D.W.24.5 | Design Stage 4 - IFC | I.DE.03.13180 | DSN - M2 - IFC - Issue Responses & Receive Comment Closeout | 2025-07-08 | 2025-07-14
I2S-7688-MP-74.D.W.24.5 | Design Stage 4 - IFC | I.DE.03.13190 | DSN - M2 - IFC - IRPL Review (5 B.days) | 2025-07-15 | 2025-07-21
I2S-7688-MP-74.D.W.24.5 | Design Stage 4 - IFC | I.DE.03.13200 | DSN - M2 - IFC - Package Complete - Roads (Public) |  | 2025-08-26
Design Package M3 - Roads - Public (TfNSW) (Was in 3.09, 3.07) |  |  |  | 2024-10-03 | 2025-09-30
Design Stage 1 - Feasibility Design - FDD |  |  |  | 2024-10-03 | 2025-02-03
I2S-7688-MP-74.D.W.18.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-M3 | DSN - M3 - FDD - Cost
I2S-7688-MP-74.D.W.18.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.13640 | DSN - M3 - FDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.18.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.13650 | DSN - M3 - FDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.18.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.8050 | DSN - M3 - FDD - Internal IDR workshop (By BGE) | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.D.W.18.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.8070 | DSN - M3 - FDD - Review of IDR comment response and final review | 2024-12-06 | 2024-12-12
I2S-7688-MP-74.D.W.18.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.8080 | DSN - M3 - FDD - Incorporate IDR comments | 2024-12-13 | 2024-12-19
I2S-7688-MP-74.D.W.18.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.8090 | DSN - M3 - FDD - Issue Responses & Receive Comment Closeout | 2024-12-13 | 2024-12-19
I2S-7688-MP-74.D.W.18.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.11580 | DSN - M3 - FDD - Design Development - Roads - Public (TfNSW) | 2024-10-03 | 2024-11-28
I2S-7688-MP-74.D.W.18.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.8380 | DSN - M3 - FDD - Start Package - Roads - Public (TfNSW) | 2024-10-03
I2S-7688-MP-74.D.W.18.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.8110 | DSN - M3 - FDD - Submission to IRPL | 2024-12-20 | 2024-12-20
I2S-7688-MP-74.D.W.18.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.03.8120 | DSN - M3 - FDD - IRPL Review (20 B.days) | 2025-01-06 | 2025-02-03
Design Stage 2 - Preliminary Design - PDD |  |  |  | 2024-11-29 | 2025-05-15
I2S-7688-MP-74.D.W.18.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-M3 | DSN - M3 - PDD - Cost
I2S-7688-MP-74.D.W.18.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.11850 | DSN - M3 - PDD - TfNSW Review (30 B.days) - Roads - Sec.6 | 2025-04-01 | 2025-05-15
I2S-7688-MP-74.D.W.18.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.13660 | DSN - M3 - PDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.18.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.13670 | DSN - M3 - PDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.18.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.8060 | DSN - M3 - PDD - Safety Assurance / SiD | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.D.W.18.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.8150 | DSN - M3 - PDD - Internal IDR workshop (By BGE) | 2025-03-10 | 2025-03-14
I2S-7688-MP-74.D.W.18.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.8170 | DSN - M3 - PDD - Review of IDR comment response and final review | 2025-03-17 | 2025-03-21
I2S-7688-MP-74.D.W.18.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.8180 | DSN - M3 - PDD - Incorporate IDR comments | 2025-03-24 | 2025-03-28
I2S-7688-MP-74.D.W.18.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.8190 | DSN - M3 - PDD - Issue Responses & Receive Comment Closeout | 2025-03-24 | 2025-03-28
I2S-7688-MP-74.D.W.18.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.8210 | DSN - M3 - PDD - Submission to IRPL | 2025-03-31 | 2025-03-31
I2S-7688-MP-74.D.W.18.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.8220 | DSN - M3 - PDD - IRPL Review (20 B.days) | 2025-04-01 | 2025-05-01
I2S-7688-MP-74.D.W.18.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.03.11590 | DSN - M3 - PDD - Design Development - Roads - Public (TfNSW) | 2024-12-20 | 2025-03-14
Design Stage 3 - Detailed Design - DDD |  |  |  | 2025-03-10 | 2025-07-28
I2S-7688-MP-74.D.W.18.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.13830 | DSN - M3 - DDD - Addressing Concessions
I2S-7688-MP-74.D.W.18.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.13840 | DSN - M3 - DDD - Collate documents to comply with WAD
I2S-7688-MP-74.D.W.18.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.8280 | DSN - M3 - DDD - Issue Responses & Receive Comment Closeout | 2025-06-06 | 2025-06-13
I2S-7688-MP-74.D.W.18.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.8300 | DSN - M3 - DDD - Submission to IRPL | 2025-06-16 | 2025-06-16
I2S-7688-MP-74.D.W.18.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.8310 | DSN - M3 - DDD - IRPL Review (20 B.days) | 2025-06-17 | 2025-07-14
I2S-7688-MP-74.D.W.18.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.11600 | DSN - M3 - DDD - Design Development - Roads - Public (TfNSW) | 2025-04-15 | 2025-05-29
I2S-7688-MP-74.D.W.18.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.11840 | DSN - M3 - DDD - TfNSW/ IV Review (30 B.days) - Roads - Public (TfNSW) - Major WAD link | 2025-06-17 | 2025-07-28
I2S-7688-MP-74.D.W.18.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.13680 | DSN - M3 - DDD - Internal IDR Review (By JHG) (Modified)
I2S-7688-MP-74.D.W.18.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.13690 | DSN - M3 - DDD - Design Presentation to IRPL - DPK Presentation (Modified)
I2S-7688-MP-74.D.W.18.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.8160 | DSN - M3 - DDD - Safety Assurance / SiD | 2025-03-10 | 2025-03-14
I2S-7688-MP-74.D.W.18.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.8240 | DSN - M3 - DDD - Internal IDR workshop (By BGE) | 2025-05-23 | 2025-05-29
I2S-7688-MP-74.D.W.18.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.8260 | DSN - M3 - DDD - Review of IDR comment response and final review | 2025-05-30 | 2025-06-05
I2S-7688-MP-74.D.W.18.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-M3 | DSN - M3 - DDD - Cost
I2S-7688-MP-74.D.W.18.4 | Design Stage 3 - Detailed Design - DDD | I.DE.03.8270 | DSN - M3 - DDD - Incorporate IDR comments | 2025-06-06 | 2025-06-13
Design Stage 4 - IFC |  |  |  | 2025-07-25 | 2025-09-30
I2S-7688-MP-74.D.W.18.39 | Design Stage 4 - IFC | Cost-IFC-M3 | DSN - M3 - IFC - Cost
I2S-7688-MP-74.D.W.18.39 | Design Stage 4 - IFC | I.DE.03.8330 | DSN - M3 - IFC - Prepare IFC Documentation - Roads (Public & Private) | 2025-07-25 | 2025-08-12
I2S-7688-MP-74.D.W.18.39 | Design Stage 4 - IFC | I.DE.03.8340 | DSN - M3 - IFC - Submission to IRPL | 2025-08-13 | 2025-08-19
I2S-7688-MP-74.D.W.18.39 | Design Stage 4 - IFC | I.DE.03.8350 | DSN - M3 - IFC - Issue Responses & Receive Comment Closeout | 2025-08-13 | 2025-08-19
I2S-7688-MP-74.D.W.18.39 | Design Stage 4 - IFC | I.DE.03.8360 | DSN - M3 - IFC - IRPL Review (5 B.days) - WAD IFC link | 2025-08-20 | 2025-08-26
I2S-7688-MP-74.D.W.18.39 | Design Stage 4 - IFC | I.DE.03.8370 | DSN - M3 - IFC - Package Complete - Roads (Public) |  | 2025-09-30
Design Package - Reinforced Soil Wall - RSW - GQA - for - E8-BGW
I2S-7688-MP-74.D.W.30 | Design Package - Reinforced Soil Wall - RSW - GQA - for - E8-BGW | I.DE.03.13860 | DSN - RSW design - GQA - E8 BGW - 100 % - TfNSW Accept Design
I2S-7688-MP-74.D.W.30 | Design Package - Reinforced Soil Wall - RSW - GQA - for - E8-BGW | I.DE.03.13850 | DSN - RSW design - GQA - E8 BGW - 85 %
I2S-7688-MP-74.D.W.30 | Design Package - Reinforced Soil Wall - RSW - GQA - for - E8-BGW | I.DE.03.13910 | DSN - RSW design - GQA - E8 BGW - 100 %
I2S-7688-MP-74.D.W.30 | Design Package - Reinforced Soil Wall - RSW - GQA - for - E8-BGW | I.DE.03.13920 | DSN - RSW design - GQA - E8 BGW - 100 % - Submission
I2S-7688-MP-74.D.W.30 | Design Package - Reinforced Soil Wall - RSW - GQA - for - E8-BGW | I.DE.03.13930 | DSN - RSW design - GQA - E8 BGW - 100 % - Requested Design report and submission
I2S-7688-MP-74.D.W.30 | Design Package - Reinforced Soil Wall - RSW - GQA - for - E8-BGW | I.DE.03.13940 | DSN - RSW design - GQA - E8 BGW - 100 % - Review by TfNSW & IV [20 bdays]
I2S-7688-MP-74.D.W.30 | Design Package - Reinforced Soil Wall - RSW - GQA - for - E8-BGW | I.DE.03.13950 | DSN - RSW design - GQA - E8 BGW - 100 % - address comments
Design Package - Reinforced Soil Wall - RSW - GQA - for - E9-Old Coota
I2S-7688-MP-74.D.W.39 | Design Package - Reinforced Soil Wall - RSW - GQA - for - E9-Old Coota | I.DE.03.13870 | DSN - RSW design - GQA - E9 Old Coota - 85 %
I2S-7688-MP-74.D.W.39 | Design Package - Reinforced Soil Wall - RSW - GQA - for - E9-Old Coota | I.DE.03.13880 | DSN - RSW design - GQA - E9 Old Coota - 100 %
Design Package - Reinforced Soil Wall - RSW - GQA - for - H3-Dirnaseer
I2S-7688-MP-74.D.W.40 | Design Package - Reinforced Soil Wall - RSW - GQA - for - H3-Dirnaseer | I.DE.03.13890 | DSN - RSW design - GQA - H3 Dirnaseer - 85 %
I2S-7688-MP-74.D.W.40 | Design Package - Reinforced Soil Wall - RSW - GQA - for - H3-Dirnaseer | I.DE.03.13900 | DSN - RSW design - GQA - H3 Dirnaseer - 100 %
Signalling Design post IFC |  |  |  | 2025-07-22 | 2027-04-08
Stockingbingal |  |  |  | 2025-07-22 | 2027-03-08
Green |  |  |  | 2025-07-22 | 2026-06-29
I2S-7688-MP-74.D.7.1.1 | Green | I.CN.11.5860 | DSN - Sig - STK - Green - Train control system design ( by others) - (up to 6 months) | 2025-08-22 | 2026-02-23
I2S-7688-MP-74.D.7.1.1 | Green | I.CN.11.5870 | DSN - Sig - STK - Green - Return of Green Copies | 2026-06-09 | 2026-06-29
I2S-7688-MP-74.D.7.1.1 | Green | I.CN.11.6000 | DSN - Sig - STK - Green - Start development of Design Integrity Test (DIT) Plan | 2026-03-03 | 2026-05-13
I2S-7688-MP-74.D.7.1.1 | Green | I.CN.11.5830 | DSN - Sig - STK - Green - Issue of signalling bit lists, signalling plan and SFS to train control systems designer | 2025-07-22 | 2025-08-12
I2S-7688-MP-74.D.7.1.1 | Green | I.CN.11.5840 | DSN - Sig - STK - Green - Issue of Green Copies (CDR) | 2025-08-13 | 2025-08-14
Pink |  |  |  | 2026-06-30 | 2027-01-21
I2S-7688-MP-74.D.7.1.2 | Pink | I.CN.11.5910 | DSN - Sig - STK - Pink - Issue of Pink /testing copies | 2026-09-04 | 2026-09-10
I2S-7688-MP-74.D.7.1.2 | Pink | I.CN.11.5920 | DSN - Sig - STK - Pink - Return of Pink copies - post signalling testing - post Sept 26 possession | 2026-09-12 | 2026-09-14
I2S-7688-MP-74.D.7.1.2 | Pink | I.CN.11.15220 | DSN - Sig - STK - Pink - Finish development of Design Integrity Test (DIT) Plan | 2026-07-30 | 2026-09-10
I2S-7688-MP-74.D.7.1.2 | Pink | I.CN.11.15230 | DSN - Sig - STK - Pink - Design Integrity Test (DIT) Testing - 1st Pass | 2026-09-11 | 2026-11-20
I2S-7688-MP-74.D.7.1.2 | Pink | I.CN.11.15250 | DSN - Sig - STK - Pink - Design Integrity Test (DIT) Testing - 3rd Pass | 2027-01-08 | 2027-01-21
I2S-7688-MP-74.D.7.1.2 | Pink | I.CN.11.15240 | DSN - Sig - STK - Pink - Design Integrity Test (DIT) Testing - 2nd Pass | 2026-11-23 | 2027-01-07
I2S-7688-MP-74.D.7.1.2 | Pink | I.CN.11.15420 | DSN - Sig - STK - Pink - Pink Copies for Testing
I2S-7688-MP-74.D.7.1.2 | Pink | I.CN.11.5880 | DSN - Sig - STK - Pink - Updating of signalling design to Pink Copies | 2026-06-30 | 2026-07-27
I2S-7688-MP-74.D.7.1.2 | Pink | I.CN.11.5890 | DSN - Sig - STK - Pink - Issue of updated signalling design to train control systems designer | 2026-07-28 | 2026-07-29
Yellow |  |  |  | 2026-09-14 | 2027-03-08
I2S-7688-MP-74.D.7.1.3 | Yellow | I.CN.11.15430 | DSN - Sig - STK - Yellow - Yellow Copies for Testing
I2S-7688-MP-74.D.7.1.3 | Yellow | I.CN.11.5930 | DSN - Sig - STK - Yellow - Updating of signalling design | 2026-09-14 | 2026-10-12
I2S-7688-MP-74.D.7.1.3 | Yellow | I.CN.11.5940 | DSN - Sig - STK - Yellow - Issue of updated signalling (yellow) design to train control systems designer | 2026-10-13 | 2026-10-19
I2S-7688-MP-74.D.7.1.3 | Yellow | I.CN.11.5950 | DSN - Sig - STK - Yellow - Updates to train control system design (by others) | 2026-10-20 | 2026-11-30
I2S-7688-MP-74.D.7.1.3 | Yellow | I.CN.11.5960 | DSN - Sig - STK - Yellow - Issue of Yellow /Commissioning copies | 2026-12-01 | 2026-12-07
I2S-7688-MP-74.D.7.1.3 | Yellow | I.CN.11.5970 | DSN - Sig - STK - Yellow - Train control commissioning (by others) | 2026-12-08 | 2027-02-01
I2S-7688-MP-74.D.7.1.3 | Yellow | I.CN.11.5980 | DSN - Sig - STK - Yellow - Return of Yellow copies (also known as CC - Certified Commissioning Copies) | 2027-02-02 | 2027-02-08
I2S-7688-MP-74.D.7.1.3 | Yellow | I.CN.11.5990 | DSN - Sig - STK - Yellow - Updating of Signalling as-built records | 2027-02-09 | 2027-03-08
Dirnaseer Loop |  |  |  | 2025-07-22 | 2027-03-08
Green |  |  |  | 2025-07-22 | 2026-05-13
I2S-7688-MP-74.D.7.3.1 | Green | I.CN.11.14900 | DSN - Sig - DRN - Green - Issue of signalling design to train control systems design contractor - CRN | 2025-08-15 | 2025-08-21
I2S-7688-MP-74.D.7.3.1 | Green | I.CN.11.14910 | DSN - Sig - DRN - Green - Train control system design ( by others) - CRN (up to 6 months) | 2025-08-22 | 2026-02-23
I2S-7688-MP-74.D.7.3.1 | Green | I.CN.11.14920 | DSN - Sig - DRN - Green - Return of Green Copies - CRN | 2026-02-24 | 2026-03-16
I2S-7688-MP-74.D.7.3.1 | Green | I.CN.11.15260 | DSN - Sig - DRN - Green - Start development of Design Integrity Test (DIT) Plan - CRN | 2026-03-03 | 2026-05-13
I2S-7688-MP-74.D.7.3.1 | Green | I.CN.11.14880 | DSN - Sig - DRN - Green - Issue of signalling bit lists, concept sig plan and SFS to TCS designer | 2025-07-22 | 2025-08-12
I2S-7688-MP-74.D.7.3.1 | Green | I.CN.11.14890 | DSN - Sig - DRN - Green - Issue of Green Copies (CDR) - CRN | 2025-08-13 | 2025-08-14
CCB Gate 4 Approval to Commission into Operation |  |  |  | 2026-02-24 | 2026-04-07
Possession #4 12/09 to 14/09/2026 |  |  |  | 2026-02-24 | 2026-04-07
I2S-7688-MP-74.D.7.3.4.1 | Possession #4 12/09 to 14/09/2026 | I.DE.CCB.4880 | DSN - Sig - DRN - CCB G4 - SEP -2026 - UGLRL Submits CCB | 2026-03-20 | 2026-03-20
I2S-7688-MP-74.D.7.3.4.1 | Possession #4 12/09 to 14/09/2026 | I.DE.CCB.4890 | DSN - Sig - DRN - CCB G4 - SEP -2026 - Configuration Change Acceptance Notice | 2026-04-07 | 2026-04-07
I2S-7688-MP-74.D.7.3.4.1 | Possession #4 12/09 to 14/09/2026 | I.DE.CCB.4850 | DSN - Sig - DRN - CCB G4 - SEP -2026 - Meeting - Presentation of CCR Submission | 2026-04-06 | 2026-04-06
I2S-7688-MP-74.D.7.3.4.1 | Possession #4 12/09 to 14/09/2026 | I.DE.CCB.4860 | DSN - Sig - DRN - CCB G4 - SEP -2026 - Prepare & Submit CCR Checklist /Presentation Material | 2026-02-24 | 2026-03-02
I2S-7688-MP-74.D.7.3.4.1 | Possession #4 12/09 to 14/09/2026 | I.DE.CCB.4870 | DSN - Sig - DRN - CCB G4 - SEP -2026 - UGLRL Reviews & Approves CCR Submission | 2026-03-03 | 2026-03-19
Possession #5 12/03 to 14/03/2027
I2S-7688-MP-74.D.7.3.4.2 | Possession #5 12/03 to 14/03/2027 | I.DE.CCB.7430 | DSN - Sig - DRN - CCB G4 - MAR-2027 - Meeting - Presentation of CCR Submission
I2S-7688-MP-74.D.7.3.4.2 | Possession #5 12/03 to 14/03/2027 | I.DE.CCB.7400 | DSN - Sig - DRN - CCB G4 - MAR-2027 - Prepare & Submit CCR Checklist /Presentation Material
I2S-7688-MP-74.D.7.3.4.2 | Possession #5 12/03 to 14/03/2027 | I.DE.CCB.7410 | DSN - Sig - DRN - CCB G4 - MAR-2027 - GLRL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.7.3.4.2 | Possession #5 12/03 to 14/03/2027 | I.DE.CCB.7420 | DSN - Sig - DRN - CCB G4 - MAR-2027 - UGLRL Submits CCB
I2S-7688-MP-74.D.7.3.4.2 | Possession #5 12/03 to 14/03/2027 | I.DE.CCB.7440 | DSN - Sig - DRN - CCB G4 - MAR-2027 - Configuration Change Acceptance Notice
Pink |  |  |  | 2026-03-17 | 2026-09-14
I2S-7688-MP-74.D.7.3.2 | Pink | I.CN.11.14930 | DSN - Sig - DRN - Pink - Updating of signalling design to Pink Copies - CRN | 2026-03-17 | 2026-04-15
I2S-7688-MP-74.D.7.3.2 | Pink | I.CN.11.14940 | DSN - Sig - DRN - Pink - Issue of updated signalling (pink) design to train control systems designer - CRN | 2026-04-16 | 2026-04-22
I2S-7688-MP-74.D.7.3.2 | Pink | I.CN.11.14950 | DSN - Sig - DRN - Pink - Updates to train controls system design (by others) - CRN | 2026-04-23 | 2026-06-03
I2S-7688-MP-74.D.7.3.2 | Pink | I.CN.11.14960 | DSN - Sig - DRN - Pink - Issue of Pink /testing copies - CRN | 2026-06-04 | 2026-06-11
I2S-7688-MP-74.D.7.3.2 | Pink | I.CN.11.14970 | DSN - Sig - DRN - Pink - Return of Pink copies - post signalling testing - CRN - post Sept 26 possession | 2026-09-12 | 2026-09-14
I2S-7688-MP-74.D.7.3.2 | Pink | I.CN.11.15270 | DSN - Sig - DRN - Pink - Finish development of Design Integrity Test (DIT) Plan - CRN | 2026-05-14 | 2026-06-25
I2S-7688-MP-74.D.7.3.2 | Pink | I.CN.11.15280 | DSN - Sig - DRN - Pink - Design Integrity Test (DIT) Testing - 1st Pass - CRN | 2026-06-26 | 2026-09-04
CCB Gate 5 Complete Handover to Business Unit |  |  |  | 2026-09-07 | 2026-10-06
Possession #4 12/09 to 14/09/2026 |  |  |  | 2026-09-07 | 2026-10-06
I2S-7688-MP-74.D.7.3.5.1 | Possession #4 12/09 to 14/09/2026 | I.DE.CCB.4920 | DSN - Sig - DRN - CCB G5 - SEP -2026 - IRPL Reviews & Approves CCR Submission | 2026-09-14 | 2026-09-30
I2S-7688-MP-74.D.7.3.5.1 | Possession #4 12/09 to 14/09/2026 | I.DE.CCB.4930 | DSN - Sig - DRN - CCB G5 - SEP -2026 - IRPL Submits CCB to SM Sub CCB | 2026-10-01 | 2026-10-01
I2S-7688-MP-74.D.7.3.5.1 | Possession #4 12/09 to 14/09/2026 | I.DE.CCB.4940 | DSN - Sig - DRN - CCB G5 - SEP -2026 - Configuration Change Acceptance Notice | 2026-10-06 | 2026-10-06
I2S-7688-MP-74.D.7.3.5.1 | Possession #4 12/09 to 14/09/2026 | I.DE.CCB.4900 | DSN - Sig - DRN - CCB G5 - SEP -2026 - Meeting - Presentation of CCR Submission | 2026-10-05 | 2026-10-05
I2S-7688-MP-74.D.7.3.5.1 | Possession #4 12/09 to 14/09/2026 | I.DE.CCB.4910 | DSN - Sig - DRN - CCB G5 - SEP -2026 - Prepare & Submit CCR Checklist /Presentation Material | 2026-09-07 | 2026-09-11
Possession #5 12/03 to 14/03/2027
I2S-7688-MP-74.D.7.3.5.2 | Possession #5 12/03 to 14/03/2027 | I.DE.CCB.7460 | DSN - Sig - DRN - CCB G5 - MAR-2027 - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.7.3.5.2 | Possession #5 12/03 to 14/03/2027 | I.DE.CCB.7470 | DSN - Sig - DRN - CCB G5 - MAR-2027 - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.D.7.3.5.2 | Possession #5 12/03 to 14/03/2027 | I.DE.CCB.7490 | DSN - Sig - DRN - CCB G5 - MAR-2027 - DSN - Sig - Configuration Change Acceptance Notice
I2S-7688-MP-74.D.7.3.5.2 | Possession #5 12/03 to 14/03/2027 | I.DE.CCB.7480 | DSN - Sig - DRN - CCB G5 - MAR-2027 - Meeting - Presentation of CCR Submission
I2S-7688-MP-74.D.7.3.5.2 | Possession #5 12/03 to 14/03/2027 | I.DE.CCB.7450 | DSN - Sig - DRN - CCB G5 - MAR-2027 - Prepare & Submit CCR Checklist /Presentation Material
Yellow |  |  |  | 2026-09-07 | 2027-03-08
I2S-7688-MP-74.D.7.3.3 | Yellow | I.CN.11.15010 | DSN - Sig - DRN - Yellow - Issue of Yellow /Commissioning copies - CRN | 2026-12-01 | 2026-12-07
I2S-7688-MP-74.D.7.3.3 | Yellow | I.CN.11.15020 | DSN - Sig - DRN - Yellow - Train control commissioning (by others) - CRN | 2026-12-08 | 2027-02-01
I2S-7688-MP-74.D.7.3.3 | Yellow | I.CN.11.15030 | DSN - Sig - DRN - Yellow - Return of Yellow copies (also known as CC - Certified Commissioning Copies) - CRN | 2027-02-02 | 2027-02-08
I2S-7688-MP-74.D.7.3.3 | Yellow | I.CN.11.15040 | DSN - Sig - DRN - Yellow - Updating of Signalling as-built records - CRN | 2027-02-09 | 2027-03-08
I2S-7688-MP-74.D.7.3.3 | Yellow | I.CN.11.15290 | DSN - Sig - DRN - Yellow - Design Integrity Test (DIT) Testing - 2nd Pass - CRN | 2026-09-07 | 2026-10-12
I2S-7688-MP-74.D.7.3.3 | Yellow | I.CN.11.15300 | DSN - Sig - DRN - Yellow - Design Integrity Test (DIT) Testing - 3rd Pass - CRN | 2026-10-13 | 2026-10-26
I2S-7688-MP-74.D.7.3.3 | Yellow | I.CN.11.14980 | DSN - Sig - DRN - Yellow - Updating of signalling design to Yellow Copies - CRN | 2026-09-14 | 2026-10-12
I2S-7688-MP-74.D.7.3.3 | Yellow | I.CN.11.14990 | DSN - Sig - DRN - Yellow - Issue of updated signalling (yellow) design to train control systems designer - CRN | 2026-10-13 | 2026-10-19
I2S-7688-MP-74.D.7.3.3 | Yellow | I.CN.11.15000 | DSN - Sig - DRN - Yellow - Updates to train control system design (by others) - CRN | 2026-10-20 | 2026-11-30
Illabo Site |  |  |  | 2025-07-22 | 2027-04-08
Green |  |  |  | 2025-07-22 | 2026-09-07
I2S-7688-MP-74.D.7.2.1 | Green | I.CN.11.15050 | DSN - Sig - ILB - Green - Issue of signalling bit lists, concept sig plan and SFS to TCS designer | 2025-07-22 | 2025-08-12
I2S-7688-MP-74.D.7.2.1 | Green | I.CN.11.15060 | DSN - Sig - ILB - Green - Issue of Green Copies (CDR) | 2025-08-13 | 2025-08-14
I2S-7688-MP-74.D.7.2.1 | Green | I.CN.11.15070 | DSN - Sig - ILB - Green - Issue of signalling design to train control systems design contractor | 2025-08-15 | 2025-08-21
I2S-7688-MP-74.D.7.2.1 | Green | I.CN.11.15080 | DSN - Sig - ILB - Green - Train control system design ( by others) - (up to 6 months) | 2025-08-22 | 2026-02-23
I2S-7688-MP-74.D.7.2.1 | Green | I.CN.11.15090 | DSN - Sig - ILB - Green - Return of Green Copies | 2026-08-31 | 2026-09-07
I2S-7688-MP-74.D.7.2.1 | Green | I.CN.11.15310 | DSN - Sig - ILB - Green - Start development of Design Integrity Test (DIT) Plan | 2026-03-03 | 2026-05-13
CCB Gate 5 Approval to Commission into Operation
Gate 5 - Track/Civil - Possession #2
I2S-7688-MP-74.D.7.2.4.1 | Gate 5 - Track/Civil - Possession #2 | I.DE.CCB.6900 | DSN - Sig - ILB - CCB G5 - POSS-2 - Prepare & Submit CCR checklist
I2S-7688-MP-74.D.7.2.4.1 | Gate 5 - Track/Civil - Possession #2 | I.DE.CCB.6920 | DSN - Sig - ILB - CCB G5 - POSS-2 - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.7.2.4.1 | Gate 5 - Track/Civil - Possession #2 | I.DE.CCB.6930 | DSN - Sig - ILB - CCB G5 - POSS-2 - Meeting - Presentation of CCR Submission to SM Sub CCB
I2S-7688-MP-74.D.7.2.4.1 | Gate 5 - Track/Civil - Possession #2 | I.DE.CCB.6940 | DSN - Sig - ILB - CCB G5 - POSS-2 - Configuration Change Acceptance Notice
I2S-7688-MP-74.D.7.2.4.1 | Gate 5 - Track/Civil - Possession #2 | I.DE.CCB.7220 | DSN - Sig - ILB - CCB G5 - POSS-2 - IRPL Submits CCB to SM Sub CCB
Sub-NAN - Track/Civil - Possession #2
I2S-7688-MP-74.D.7.2.4.9 | Sub-NAN - Track/Civil - Possession #2 | I.DE.CCB.7380 | DSN - Sig - ILB - CCB G5 - POSS-2 - Sub NAN 3752-1 - Closeout
I2S-7688-MP-74.D.7.2.4.9 | Sub-NAN - Track/Civil - Possession #2 | I.DE.CCB.7300 | DSN - Sig - ILB - CCB G5 - POSS-2 - Sub NAN 3752-1 Closeout
Gate 5 - Track/Civil - Possession #3
I2S-7688-MP-74.D.7.2.4.3 | Gate 5 - Track/Civil - Possession #3 | I.DE.CCB.6980 | DSN - Sig - ILB - CCB G5 - Feb-Mar POSS - 3 - Prepare & Submit CCR checklist
I2S-7688-MP-74.D.7.2.4.3 | Gate 5 - Track/Civil - Possession #3 | I.DE.CCB.6990 | DSN - Sig - ILB - CCB G5 - POSS-3 - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.7.2.4.3 | Gate 5 - Track/Civil - Possession #3 | I.DE.CCB.7000 | DSN - Sig - ILB - CCB G5 - POSS-3 - Meeting - Presentation of CCR Submission to SM Sub CCB
I2S-7688-MP-74.D.7.2.4.3 | Gate 5 - Track/Civil - Possession #3 | I.DE.CCB.7010 | DSN - Sig - ILB - CCB G5 - POSS-3 - Configuration Change Acceptance Notice
I2S-7688-MP-74.D.7.2.4.3 | Gate 5 - Track/Civil - Possession #3 | I.DE.CCB.7240 | DSN - Sig - ILB - CCB G5 - POSS-3 - IRPL Submits CCB to SM Sub CCB
Sub-NAN - Track/ Civil - Possession #3
I2S-7688-MP-74.D.7.2.4.10 | Sub-NAN - Track/ Civil - Possession #3 | I.DE.CCB.7320 | DSN - Sig - ILB - CCB G5 - POSS-3 - Sub NAN 3752-2,3 Closeout
I2S-7688-MP-74.D.7.2.4.10 | Sub-NAN - Track/ Civil - Possession #3 | I.DE.CCB.7350 | DSN - Sig - ILB - CCB G5 - POSS-3 - Sub NAN 3752-2,3 - Closeout
Gate 5 - Track/Civil - Possession #4
I2S-7688-MP-74.D.7.2.4.5 | Gate 5 - Track/Civil - Possession #4 | I.DE.CCB.7060 | DSN - Sig - ILB - CCB G5 - POSS-4 - Prepare & Submit CCR checklist
I2S-7688-MP-74.D.7.2.4.5 | Gate 5 - Track/Civil - Possession #4 | I.DE.CCB.7070 | DSN - Sig - ILB - CCB G5 - POSS-4 - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.7.2.4.5 | Gate 5 - Track/Civil - Possession #4 | I.DE.CCB.7080 | DSN - Sig - ILB - CCB G5 - POSS-4 - Meeting - Presentation of CCR Submission to SM Sub CCB
I2S-7688-MP-74.D.7.2.4.5 | Gate 5 - Track/Civil - Possession #4 | I.DE.CCB.7090 | DSN - Sig - ILB - CCB G5 - POSS-4 - Configuration Change Acceptance Notice
I2S-7688-MP-74.D.7.2.4.5 | Gate 5 - Track/Civil - Possession #4 | I.DE.CCB.7260 | DSN - Sig - ILB - CCB G5 - POSS-4 - IRPL Submits CCB to SM Sub CCB
Sub-NAN - Track/Civil - Possession #4
I2S-7688-MP-74.D.7.2.4.11 | Sub-NAN - Track/Civil - Possession #4 | I.DE.CCB.7310 | DSN - Sig - ILB - CCB G5 - POSS-4 - Sub NAN 3752-4 Closeout
I2S-7688-MP-74.D.7.2.4.11 | Sub-NAN - Track/Civil - Possession #4 | I.DE.CCB.7360 | DSN - Sig - ILB - CCB G5 - POSS-4 - Sub NAN 3752-4- Closeout
Gate 5 - Track/Civil - Possession #5
I2S-7688-MP-74.D.7.2.4.6 | Gate 5 - Track/Civil - Possession #5 | I.DE.CCB.7130 | DSN - Sig - ILB - CCB G5 - POSS-5 - Configuration Change Acceptance Notice
I2S-7688-MP-74.D.7.2.4.6 | Gate 5 - Track/Civil - Possession #5 | I.DE.CCB.7110 | DSN - Sig - ILB - CCB G5 - POSS-5 - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.7.2.4.6 | Gate 5 - Track/Civil - Possession #5 | I.DE.CCB.7120 | DSN - Sig - ILB - CCB G5 - POSS-5 - Meeting - Presentation of CCR Submission to SM Sub CCB
I2S-7688-MP-74.D.7.2.4.6 | Gate 5 - Track/Civil - Possession #5 | I.DE.CCB.7280 | DSN - Sig - ILB - CCB G5 - POSS-5 - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.D.7.2.4.6 | Gate 5 - Track/Civil - Possession #5 | I.DE.CCB.7100 | DSN - Sig - ILB - CCB G5 - POSS-5 - Prepare & Submit CCR checklist
Sub-NAN - Track/Civil - Possession #5
I2S-7688-MP-74.D.7.2.4.12 | Sub-NAN - Track/Civil - Possession #5 | I.DE.CCB.7330 | DSN - Sig - ILB - CCB G5 - POSS-5 - Sub NAN 3752-5 Closeout
I2S-7688-MP-74.D.7.2.4.12 | Sub-NAN - Track/Civil - Possession #5 | I.DE.CCB.7370 | DSN - Sig - ILB - CCB G5 - POSS-5 - Sub NAN 3752-5 - Closeout
Pink |  |  |  | 2026-09-07 | 2027-03-14
I2S-7688-MP-74.D.7.2.2 | Pink | I.CN.11.15100 | DSN - Sig - ILB - Pink - Updating of signalling design to Pink Copies | 2026-09-07 | 2026-10-06
I2S-7688-MP-74.D.7.2.2 | Pink | I.CN.11.15110 | DSN - Sig - ILB - Pink - Issue of updated signalling (pink) design to train control systems designer | 2026-10-06 | 2026-10-13
I2S-7688-MP-74.D.7.2.2 | Pink | I.CN.11.15120 | DSN - Sig - ILB - Pink - Updates to train controls system design (by others) | 2026-10-13 | 2026-11-24
I2S-7688-MP-74.D.7.2.2 | Pink | I.CN.11.15130 | DSN - Sig - ILB - Pink - Issue of Pink /testing copies | 2026-11-24 | 2026-12-01
I2S-7688-MP-74.D.7.2.2 | Pink | I.CN.11.15140 | DSN - Sig - ILB - Pink - Return of Pink copies - post signalling testing - post March 27 possession | 2027-03-13 | 2027-03-14
I2S-7688-MP-74.D.7.2.2 | Pink | I.CN.11.15320 | DSN - Sig - ILB - Pink - Finish development of Design Integrity Test (DIT) Plan | 2026-10-20 | 2026-12-01
I2S-7688-MP-74.D.7.2.2 | Pink | I.CN.11.15330 | DSN - Sig - ILB - Pink - Design Integrity Test (DIT) Testing - 1st Pass | 2026-09-07 | 2026-11-17
CCB Gate 6 Complete Handover to Business Unit
Gate 6 - Track/Civil - Possession #4
I2S-7688-MP-74.D.7.2.5.7 | Gate 6 - Track/Civil - Possession #4 | I.DE.CCB.7140 | DSN - Sig - ILB - CCB G6 - POSS-4 - Prepare & Submit CCR checklist
I2S-7688-MP-74.D.7.2.5.7 | Gate 6 - Track/Civil - Possession #4 | I.DE.CCB.7150 | DSN - Sig - ILB - CCB G6 - POSS-4 - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.7.2.5.7 | Gate 6 - Track/Civil - Possession #4 | I.DE.CCB.7160 | DSN - Sig - ILB - CCB G6 - POSS-4 - Meeting - Presentation of CCR Submission to SM Sub CCB
I2S-7688-MP-74.D.7.2.5.7 | Gate 6 - Track/Civil - Possession #4 | I.DE.CCB.7170 | DSN - Sig - ILB - CCB G6 - POSS-4 - Configuration Change Acceptance Notice
I2S-7688-MP-74.D.7.2.5.7 | Gate 6 - Track/Civil - Possession #4 | I.DE.CCB.7270 | DSN - Sig - ILB - CCB G6 - POSS-4 - IRPL Submits CCB to SM Sub CCB
Gate 6 - Track/Civil - Possession #5
I2S-7688-MP-74.D.7.2.5.8 | Gate 6 - Track/Civil - Possession #5 | I.DE.CCB.7180 | DSN - Sig - ILB - CCB G6 - POSS-5 - Prepare & Submit CCR checklist
I2S-7688-MP-74.D.7.2.5.8 | Gate 6 - Track/Civil - Possession #5 | I.DE.CCB.7190 | DSN - Sig - ILB - CCB G6 - POSS-5 - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.D.7.2.5.8 | Gate 6 - Track/Civil - Possession #5 | I.DE.CCB.7200 | DSN - Sig - ILB - CCB G6 - POSS-5 - Meeting - Presentation of CCR Submission to SM Sub CCB
I2S-7688-MP-74.D.7.2.5.8 | Gate 6 - Track/Civil - Possession #5 | I.DE.CCB.7210 | DSN - Sig - ILB - CCB G6 - POSS-5 - Configuration Change Acceptance Notice
I2S-7688-MP-74.D.7.2.5.8 | Gate 6 - Track/Civil - Possession #5 | I.DE.CCB.7290 | DSN - Sig - ILB - CCB G6 - POSS-5 - IRPL Submits CCB to SM Sub CCB
Yellow |  |  |  | 2026-11-17 | 2027-04-08
I2S-7688-MP-74.D.7.2.3 | Yellow | I.CN.11.15340 | DSN - Sig - ILB - Yellow - Design Integrity Test (DIT) Testing - 2nd Pass | 2026-11-17 | 2027-01-04
I2S-7688-MP-74.D.7.2.3 | Yellow | I.CN.11.15350 | DSN - Sig - ILB - Yellow - Design Integrity Test (DIT) Testing - 3rd Pass | 2027-01-04 | 2027-01-18
I2S-7688-MP-74.D.7.2.3 | Yellow | I.CN.11.15150 | DSN - Sig - ILB - Yellow - Updating of signalling design to Yellow Copies | 2027-03-01 | 2027-03-15
I2S-7688-MP-74.D.7.2.3 | Yellow | I.CN.11.15160 | DSN - Sig - ILB - Yellow - Issue of updated signalling (yellow) design to train control systems designer | 2027-03-15 | 2027-03-15
I2S-7688-MP-74.D.7.2.3 | Yellow | I.CN.11.15170 | DSN - Sig - ILB - Yellow - DSN - Sig - Updates to train control system design (by others) | 2027-03-16 | 2027-03-24
I2S-7688-MP-74.D.7.2.3 | Yellow | I.CN.11.15180 | DSN - Sig - ILB - Yellow - Issue of Yellow /Commissioning copies | 2027-03-25 | 2027-03-25
I2S-7688-MP-74.D.7.2.3 | Yellow | I.CN.11.15190 | DSN - Sig - ILB - Yellow - Train control commissioning (by others) | 2027-03-26 | 2027-04-06
I2S-7688-MP-74.D.7.2.3 | Yellow | I.CN.11.15200 | DSN - Sig - ILB - Yellow - Return of Yellow copies (also known as CC - Certified Commissioning Copies) | 2027-04-07 | 2027-04-07
I2S-7688-MP-74.D.7.2.3 | Yellow | I.CN.11.15210 | DSN - Sig - ILB - Yellow - Update of Signalling as-built records | 2027-04-08 | 2027-04-08
Close out design / As-Built documentation |  |  |  | 2026-10-12 | 2027-04-08
I2S-7688-MP-74.D.10 | Close out design / As-Built documentation | I.DE.99.5030 | DSN - Sig - Close out design / As built documentation - Portion 1 - IRPL Stockinbingal to Parkes S2P | 2027-01-18 | 2027-03-08
I2S-7688-MP-74.D.10 | Close out design / As-Built documentation | I.DE.99.5020 | DSN - Sig - Close out design / As built documentation - Returned Works A - CRN Track | 2027-01-18 | 2027-03-08
I2S-7688-MP-74.D.10 | Close out design / As-Built documentation | I.DE.99.5040 | DSN - Sig - Close out design / As built documentation - Returned Works B - BGW Road | 2026-10-12 | 2026-11-20
I2S-7688-MP-74.D.10 | Close out design / As-Built documentation | I.DE.99.5050 | DSN - Sig - Close out design / As built documentation - Portion 2 - I2S Track | 2027-02-26 | 2027-04-08
I2S-7688-MP-74.D.10 | Close out design / As-Built documentation | I.DE.99.5060 | DSN - Sig - Close out design / As built documentation - Portion 3 - All Works | 2027-01-25 | 2027-03-16
Procurement, Manufacturing and Delivery |  |  |  | 2024-09-30 | 2026-09-01
Key Procurement Milestones |  |  |  | 2024-10-03 | 2024-10-25
I2S-7688-MP-74.PR.MS | Key Procurement Milestones | I.GG.P.KM.1000 | PROC - Procurement Team Mobilisation | 2024-10-03 | 2024-10-24
I2S-7688-MP-74.PR.MS | Key Procurement Milestones | I.GG.P.KM.2000 | PROC - Early Procurement Works to Commence to Support enabling and long lead | 2024-10-25
Milestones
I2S-7688-MP-74.PR.MS.1 | Milestones | I.GG.P.KM.2100 | PROC - MIL - Final Material Delivered to Site - STRUCTURES
I2S-7688-MP-74.PR.MS.1 | Milestones | I.GG.P.KM.2110 | PROC - MIL - Final Material Delivered to SIte - TRACK SCOPE
I2S-7688-MP-74.PR.MS.1 | Milestones | I.GG.P.KM.2120 | PROC - MIL - Final Material Delivered to Site - SIGNALLING SCOPE
I2S-7688-MP-74.PR.MS.1 | Milestones | I.GG.P.KM.2130 | PROC - MIL - Final Material Procured - CSR SCOPE
I2S-7688-MP-74.PR.MS.1 | Milestones | I.GG.P.KM.2140 | PROC - MIL - All Material Procured & Delivered - Manufacturing to Site
I2S-7688-MP-74.PR.MS.1 | Milestones | I.GG.P.KM.2010 | PROC - MIL - Final Material Delivered to Site - SITE PRELIMS
I2S-7688-MP-74.PR.MS.1 | Milestones | I.GG.P.KM.2020 | PROC - MIL - Final Material Delivered to SIte - GENERAL PROJECT WIDE
I2S-7688-MP-74.PR.MS.1 | Milestones | I.GG.P.KM.2040 | PROC - MIL - Final Material Procured - CIVIL
I2S-7688-MP-74.PR.MS.1 | Milestones | I.GG.P.KM.2050 | PROC - MIL - Final Material Procured - STRUCTURES
I2S-7688-MP-74.PR.MS.1 | Milestones | I.GG.P.KM.2060 | PROC - MIL - Final Material Procured - TRACK SCOPE
I2S-7688-MP-74.PR.MS.1 | Milestones | I.GG.P.KM.2070 | PROC - MIL - Final Material Procured - SIGNALLING SCOPE
I2S-7688-MP-74.PR.MS.1 | Milestones | I.GG.P.KM.2080 | PROC - MIL - Final Material Delivered to Site - CSR SCOPE
I2S-7688-MP-74.PR.MS.1 | Milestones | I.GG.P.KM.2090 | PROC - MIL - Final Material Delivered to Site - CIVIL
Free Issue Materials (Client Supplied) - IRPL |  |  |  | 2024-12-05 | 2026-09-01
Concrete Sleepers - IRPL - Free Issue |  |  |  | 2025-11-03 | 2026-09-01
I2S-7688-MP-74.PR.FIM.1 | Concrete Sleepers - IRPL - Free Issue | I.GG.P.FI.6650 | PROC - Sec.1 - IRPL Free Issue - Concrete Sleepers (2,473 off) - 100 delivered |  | 2026-03-02
I2S-7688-MP-74.PR.FIM.1 | Concrete Sleepers - IRPL - Free Issue | I.GG.P.FI.6680 | PROC - Sec.3 - IRPL Free Issue - Concrete Sleepers (18,113 off) |  | 2026-05-01
I2S-7688-MP-74.PR.FIM.1 | Concrete Sleepers - IRPL - Free Issue | I.GG.P.FI.6690 | PROC - Sec.4 - IRPL Free Issue - Concrete Sleepers (13,973 off) |  | 2026-07-01
I2S-7688-MP-74.PR.FIM.1 | Concrete Sleepers - IRPL - Free Issue | I.GG.P.FI.6720 | PROC - Sec.5 - IRPL Free Issue - Concrete Sleepers (16,511 off) |  | 2026-09-01
I2S-7688-MP-74.PR.FIM.1 | Concrete Sleepers - IRPL - Free Issue | I.GG.P.FI.6780 | PROC - Sec.6 - IRPL Free Issue - Concrete Sleepers (7,824 off) |  | 2026-02-02
I2S-7688-MP-74.PR.FIM.1 | Concrete Sleepers - IRPL - Free Issue | I.GG.CG.6840 | PROC - IRPL Free Issue - Concrete Sleepers (Standard Gauge) - JH-CONNOTICE-000064 | 2025-11-03 | 2025-11-03
I2S-7688-MP-74.PR.FIM.1 | Concrete Sleepers - IRPL - Free Issue | I.GG.P.FI.6670 | PROC - Sec.2 - IRPL Free Issue - Concrete Sleepers (7,539 off) |  | 2026-04-01
Rail 60kg - IRPL - Free Issue |  |  |  | 2025-11-03 | 2026-09-01
I2S-7688-MP-74.PR.FIM.2 | Rail 60kg - IRPL - Free Issue | I.GG.P.FI.6660 | PROC - Sec.1 - IRPL Free Issue - Rails RT28 60kg tangent profile SC - 992 off (1st 496) |  | 2026-04-01
I2S-7688-MP-74.PR.FIM.2 | Rail 60kg - IRPL - Free Issue | I.GG.P.FI.6840 | PROC - Sec.2 - IRPL Free Issue - Rails RT28 60kg tangent profile SC - 496 off |  | 2026-05-01
I2S-7688-MP-74.PR.FIM.2 | Rail 60kg - IRPL - Free Issue | I.GG.P.FI.6850 | PROC - Sec.3 - IRPL Free Issue - Rails RT28 60kg tangent profile SC - 400 off |  | 2026-06-01
I2S-7688-MP-74.PR.FIM.2 | Rail 60kg - IRPL - Free Issue | I.GG.P.FI.6860 | PROC - Sec.4 - IRPL Free Issue - Rails RT28 60kg tangent profile SC - 714 off |  | 2026-08-04
I2S-7688-MP-74.PR.FIM.2 | Rail 60kg - IRPL - Free Issue | I.GG.P.FI.6870 | PROC - Sec.5 - IRPL Free Issue - Rails RT28 60kg tangent profile SC - 510 off |  | 2026-09-01
I2S-7688-MP-74.PR.FIM.2 | Rail 60kg - IRPL - Free Issue | I.GG.P.FI.6880 | PROC - Sec.6 - IRPL Free Issue - Rails RT28 60kg tangent profile SC - 384 off |  | 2026-02-02
I2S-7688-MP-74.PR.FIM.2 | Rail 60kg - IRPL - Free Issue | I.GG.CG.6890 | PROC - Rail - IRPL Free Issue - Rail SC - RT28 - JH-CONNOTICE-000064 | 2025-11-03 | 2025-11-03
I2S-7688-MP-74.PR.FIM.2 | Rail 60kg - IRPL - Free Issue | I.GG.P.FI.6920 | PROC - Sec.1 - IRPL Free Issue - Rails RT28 60kg tangent profile SC - 992 off (2nd 496)
I2S-7688-MP-74.PR.FIM.2 | Rail 60kg - IRPL - Free Issue | I.GG.CG.7060 | PROC - Rail - IRPL Free Issue - Rail SC - RT28 - rem
Turnouts 10.5 R250 (5 off) - IRPL - Free Issue |  |  |  | 2025-09-08 | 2026-09-01
I2S-7688-MP-74.PR.FIM.3 | Turnouts 10.5 R250 (5 off) - IRPL - Free Issue | I.GG.P.FI.6800 | PROC - IRPL Free Issue - Turnout - 1 in 10.5 R250 (for stabling) - start (SL 122 A) |  | 2026-09-01
I2S-7688-MP-74.PR.FIM.3 | Turnouts 10.5 R250 (5 off) - IRPL - Free Issue | I.GG.P.FI.6900 | PROC - IRPL Free Issue - Turnout - 1 in 10.5 R250 (Sec.3 -loop) - (53Pts B) |  | 2026-08-04
I2S-7688-MP-74.PR.FIM.3 | Turnouts 10.5 R250 (5 off) - IRPL - Free Issue | I.GG.P.FI.6810 | PROC - IRPL Free Issue - Turnout - 1 in 10.5 R250 (for stabling) - finish (SL 122B) |  | 2026-09-01
I2S-7688-MP-74.PR.FIM.3 | Turnouts 10.5 R250 (5 off) - IRPL - Free Issue | I.GG.CG.6850 | PROC - IRPL Free Issue - Turnouts 10.5 - 180 days notification - R250 (stockinbingal - 37521) - (SL130Pts) | 2025-09-08 | 2025-09-08
I2S-7688-MP-74.PR.FIM.3 | Turnouts 10.5 R250 (5 off) - IRPL - Free Issue | I.GG.P.FI.5900 | PROC - IRPL Free Issue - Turnout - 1 in 10.5 R250 (stockinbingal - 37521) - (SL130Pts) |  | 2026-03-02
I2S-7688-MP-74.PR.FIM.3 | Turnouts 10.5 R250 (5 off) - IRPL - Free Issue | I.GG.P.FI.6580 | PROC - IRPL Free Issue - Turnout - 1 in 10.5 R250 (stockinbngal - 37541) - (SL131Pts) |  | 2026-03-02
I2S-7688-MP-74.PR.FIM.3 | Turnouts 10.5 R250 (5 off) - IRPL - Free Issue | I.GG.CG.6970 | PROC - IRPL Free Issue - Turnouts 10.5 - 180 days notification - R250 (stockinbngal - 37541) - (SL131Pts)
I2S-7688-MP-74.PR.FIM.3 | Turnouts 10.5 R250 (5 off) - IRPL - Free Issue | I.GG.CG.6980 | PROC - IRPL Free Issue - Turnouts 10.5 - 180 days notification - R250 (Sec.3 -loop) - (53Pts B)
I2S-7688-MP-74.PR.FIM.3 | Turnouts 10.5 R250 (5 off) - IRPL - Free Issue | I.GG.CG.6990 | PROC - IRPL Free Issue - Turnouts 10.5 - 180 days notification - R250 (for stabling) - start (SL 122A)
I2S-7688-MP-74.PR.FIM.3 | Turnouts 10.5 R250 (5 off) - IRPL - Free Issue | I.GG.CG.7000 | PROC - IRPL Free Issue - Turnouts 10.5 - 180 days notification - R250 (for stabling) - finish (SL 122B)
Turnouts18.5 R1200 (3 off) - IRPL - Free Issue |  |  |  | 2025-07-28 | 2026-03-02
I2S-7688-MP-74.PR.FIM.4 | Turnouts18.5 R1200 (3 off) - IRPL - Free Issue | I.GG.P.FI.6600 | PROC - IRPL Free Issue - Turnout - 1 in 18 R1200 (sidings) (51Pts A/B) |  | 2026-03-02
I2S-7688-MP-74.PR.FIM.4 | Turnouts18.5 R1200 (3 off) - IRPL - Free Issue | I.GG.P.FI.6790 | PROC - IRPL Free Issue - Turnout - 1 in 18 R1200 (Ilabo) - (100pts A/B) |  | 2026-02-20
I2S-7688-MP-74.PR.FIM.4 | Turnouts18.5 R1200 (3 off) - IRPL - Free Issue | I.GG.P.FI.6820 | PROC - IRPL Free Issue - Turnout - 1 in 18 R1200 (loop) (55Pts A/B) |  | 2026-03-02
I2S-7688-MP-74.PR.FIM.4 | Turnouts18.5 R1200 (3 off) - IRPL - Free Issue | I.GG.CG.6870 | PROC - IRPL Free Issue - Turnouts 18.5- 180 days notification - (Ilabo) - JH-CONNOTICE-000040 | 2025-07-28 | 2025-07-28
I2S-7688-MP-74.PR.FIM.4 | Turnouts18.5 R1200 (3 off) - IRPL - Free Issue | I.GG.CG.7010 | PROC - IRPL Free Issue - Turnouts 18.5- 180 days notification - R1200 (sidings) (51Pts A/B)
I2S-7688-MP-74.PR.FIM.4 | Turnouts18.5 R1200 (3 off) - IRPL - Free Issue | I.GG.CG.7020 | PROC - IRPL Free Issue - Turnouts 18.5- 180 days notification - R1200 (loop) (55Pts A/B)
Points Machines, Rodding and Fastening - IRPL - Free Issue |  |  |  | 2025-07-28 | 2026-07-14
I2S-7688-MP-74.PR.FIM.6 | Points Machines, Rodding and Fastening - IRPL - Free Issue | I.GG.P.FI.6640 | PROC - IRPL Free Issue - Point Machines (Sec.3) 4 off (1 in18) |  | 2026-07-14
I2S-7688-MP-74.PR.FIM.6 | Points Machines, Rodding and Fastening - IRPL - Free Issue | I.GG.CG.6860 | PROC - IRPL Free Issue - Points Machine- 180 days notification - (2 each) - JH-CONNOTICE-000056 | 2025-07-28 | 2025-07-28
I2S-7688-MP-74.PR.FIM.6 | Points Machines, Rodding and Fastening - IRPL - Free Issue | I.GG.P.FI.6610 | PROC - IRPL Free Issue - Point Machines (Sec.3) 1 off (1 in10.5) |  | 2026-07-14
I2S-7688-MP-74.PR.FIM.6 | Points Machines, Rodding and Fastening - IRPL - Free Issue | I.GG.P.FI.6620 | PROC - IRPL Free Issue - Point Machines (Sec.1) 6 off (2 each) |  | 2026-03-13
I2S-7688-MP-74.PR.FIM.6 | Points Machines, Rodding and Fastening - IRPL - Free Issue | I.GG.P.FI.6630 | PROC - IRPL Free Issue - Point Machines (Sec.6) 2 off |  | 2026-04-10
I2S-7688-MP-74.PR.FIM.6 | Points Machines, Rodding and Fastening - IRPL - Free Issue | I.GG.CG.7030 | PROC - IRPL Free Issue - Points Machine- 180 days notification
I2S-7688-MP-74.PR.FIM.6 | Points Machines, Rodding and Fastening - IRPL - Free Issue | I.GG.CG.7040 | PROC - IRPL Free Issue - Points Machine- 180 days notification - (1 in18)
I2S-7688-MP-74.PR.FIM.6 | Points Machines, Rodding and Fastening - IRPL - Free Issue | I.GG.CG.7050 | PROC - IRPL Free Issue - Points Machine- 180 days notification - (1 in10.5)
Catchpoints (IRPL Free-Issue) |  |  |  | 2024-12-05 | 2025-09-11
I2S-7688-MP-74.PR.FIM.8 | Catchpoints (IRPL Free-Issue) | I.GG.P.R.10W-637 | PROC - Catchpoints - IRPL Free-Issue - Prepare Tender Documents | 2024-12-05 | 2025-01-15
I2S-7688-MP-74.PR.FIM.8 | Catchpoints (IRPL Free-Issue) | I.GG.P.R.10W-647 | PROC - Catchpoints - IRPL Free-Issue - Pricing by Suppliers / Subcontractors | 2025-01-16 | 2025-02-13
I2S-7688-MP-74.PR.FIM.8 | Catchpoints (IRPL Free-Issue) | I.GG.P.R.10W-657 | PROC - Catchpoints - IRPL Free-Issue - Package Review / Approval | 2025-02-14 | 2025-02-27
I2S-7688-MP-74.PR.FIM.8 | Catchpoints (IRPL Free-Issue) | I.GG.P.R.10W-667 | PROC - Catchpoints - IRPL Free-Issue - Package Placement | 2025-02-28 | 2025-03-13
I2S-7688-MP-74.PR.FIM.8 | Catchpoints (IRPL Free-Issue) | I.GG.P.R.10W-677 | PROC - Catchpoints - IRPL Free-Issue - Manufacturing & Delivery - Dirnaseer Siding (53Pts A) | 2025-03-14 | 2025-09-11
Site Prelims |  |  |  | 2024-09-30 | 2025-10-07
Utilities Locating, Non-destructive Digging & Pothole Truck |  |  |  | 2024-11-05 | 2024-12-13
I2S-7688-MP-74.PR.SP.01 | Utilities Locating, Non-destructive Digging & Pothole Truck | I.GG.P.EW.10C-140 | PROC - Engage Subcontractor - Utility Locating/ NDD/ Potholing | 2024-11-05 | 2024-12-04
I2S-7688-MP-74.PR.SP.01 | Utilities Locating, Non-destructive Digging & Pothole Truck | I.GG.P.EW.10C-150 | PROC - Subcontractor Mob to Site - Utility Locating/ NDD/ Potholing | 2024-12-05 | 2024-12-13
Pkg 17 - Waste Disposal & Skip Bins |  |  |  | 2025-05-02 | 2025-07-11
I2S-7688-MP-74.PR.SP.02 | Pkg 17 - Waste Disposal & Skip Bins | I.GG.P.EW.10909180 | PROC - Pkg 17 - Waste Disposal & Skip Bins - Engage Subcontractor | 2025-05-02 | 2025-06-27
I2S-7688-MP-74.PR.SP.02 | Pkg 17 - Waste Disposal & Skip Bins | I.GG.P.EW.1033190 | PROC - Pkg 17 - Waste Disposal & Skip Bins - Subcontractor Mob to Site | 2025-06-30 | 2025-07-11
Pkg 18 - Dilapidation - Commercial/housing + Roads |  |  |  | 2025-06-18 | 2025-08-27
I2S-7688-MP-74.PR.SP.03 | Pkg 18 - Dilapidation - Commercial/housing + Roads | I.GG.P.C.10C-540 | PROC - Pkg 18 - Dilapidation - Commercial/housing + Roads - Engage Subcontractor | 2025-06-18 | 2025-08-13
I2S-7688-MP-74.PR.SP.03 | Pkg 18 - Dilapidation - Commercial/housing + Roads | I.GG.P.C.10C-550 | PROC - Pkg 18 - Dilapidation - Commercial/housing + Roads - Subcontractor Mob to Site | 2025-08-14 | 2025-08-27
Pkg 19 - Safeworking |  |  |  | 2025-02-24 | 2025-05-07
I2S-7688-MP-74.PR.SP.04 | Pkg 19 - Safeworking | I.GG.P.EW.1090917 | PROC - Pkg 19 - Safeworking - Subcontractor Mob to Site | 2025-04-23 | 2025-05-07
I2S-7688-MP-74.PR.SP.04 | Pkg 19 - Safeworking | I.GG.P.EW.1090160 | PROC - Pkg 19 - Safeworking - Engage Subcontractor | 2025-02-24 | 2025-04-22
Pkg 131 - Surveying - need separate civil + rail Qlaser survey |  |  |  | 2024-09-30 | 2024-10-31
I2S-7688-MP-74.PR.SP.05 | Pkg 131 - Surveying - need separate civil + rail Qlaser survey | I.GG.P.EW.10C-5 | PROC - Pkg 131 - Surveying - need separate civil + rail Qlaser survey - Engage Subcontractor | 2024-09-30 | 2024-10-21
I2S-7688-MP-74.PR.SP.05 | Pkg 131 - Surveying - need separate civil + rail Qlaser survey | I.GG.P.EW.10C-6 | PROC - Pkg 131 - Surveying - need separate civil + rail Qlaser survey - Subcontractor Mob to Site | 2024-10-22 | 2024-10-31
Pkg 20 - Site Offices and Amenities S&I |  |  |  | 2024-10-25 | 2025-02-17
I2S-7688-MP-74.PR.SP.06 | Pkg 20 - Site Offices and Amenities S&I | I.GG.P.EW.103338 | PROC - Pkg 20 - Site Offices and Amenities S&I - Subcontractor Mob to Site | 2024-12-20 | 2025-01-16
I2S-7688-MP-74.PR.SP.06 | Pkg 20 - Site Offices and Amenities S&I | I.GG.P.EW.103080 | PROC - Pkg 20 - Site Offices and Amenities S&I - Set up | 2025-01-17 | 2025-02-17
I2S-7688-MP-74.PR.SP.06 | Pkg 20 - Site Offices and Amenities S&I | I.GG.P.EW.10337 | PROC - Pkg 20 - Site Offices and Amenities S&I - Engage Subcontractor | 2024-10-25 | 2024-12-19
Heritage Consultant |  |  |  | 2025-05-02 | 2025-07-11
I2S-7688-MP-74.PR.SP.09 | Heritage Consultant | I.GG.P.EW.1090120 | PROC - Heritage Consultant - Engage Subcontractor | 2025-05-02 | 2025-06-27
I2S-7688-MP-74.PR.SP.09 | Heritage Consultant | I.GG.P.EW.10C-130 | PROC - Heritage Consultant - Subcontractor Mob to Site | 2025-06-30 | 2025-07-11
Pkg 5/113 - Environment Consultant |  |  |  | 2025-04-10 | 2025-06-24
I2S-7688-MP-74.PR.SP.10 | Pkg 5/113 - Environment Consultant | I.GG.P.EW.1090913 | PROC - Pkg 5/113 - Environment Consultant - Engage Subcontractor | 2025-04-10 | 2025-06-10
I2S-7688-MP-74.PR.SP.10 | Pkg 5/113 - Environment Consultant | I.GG.P.EW.1090914 | PROC - Pkg 5/113 - Environment Consultant - Subcontractor Mob to Site | 2025-06-11 | 2025-06-24
Pkg 25 - Proof Engineer |  |  |  | 2025-02-24 | 2025-05-07
I2S-7688-MP-74.PR.SP.11 | Pkg 25 - Proof Engineer | I.GG.P.EW.10C-80 | PROC - Pkg 25 - Proof Engineer - Engage Subcontractor | 2025-02-24 | 2025-04-22
I2S-7688-MP-74.PR.SP.11 | Pkg 25 - Proof Engineer | I.GG.P.EW.10C-90 | PROC - Pkg 25 - Proof Engineer - Subcontractor Mob to Site | 2025-04-23 | 2025-05-07
Pkg 112 - Geotechnical Services |  |  |  | 2025-04-23 | 2025-05-29
I2S-7688-MP-74.PR.SP.12 | Pkg 112 - Geotechnical Services | I.GG.P.EW.10112 | PROC - Pkg 112 - Geotechnical Services - Engage Subcontractor | 2025-04-23 | 2025-05-21
I2S-7688-MP-74.PR.SP.12 | Pkg 112 - Geotechnical Services | I.GG.P.EW.10111 | PROC - Pkg 112 - Geotechnical Services - Subcontractor Mob to Site | 2025-05-22 | 2025-05-29
Pkg 27/126 - Camp and Misc |  |  |  | 2024-10-25 | 2025-01-16
I2S-7688-MP-74.PR.SP.13 | Pkg 27/126 - Camp and Misc | I.GG.P.EW.10909190 | PROC - Pkg 27/126 - Camp and Misc - Engage Subcontractor | 2024-10-25 | 2024-12-19
I2S-7688-MP-74.PR.SP.13 | Pkg 27/126 - Camp and Misc | I.GG.P.EW.10909200 | PROC - Pkg 27/126 - Camp and Misc - Subcontractor Mob to Site | 2024-12-20 | 2025-01-16
Pkg 29 - Traffic Control Crews Rates including the reports/plans |  |  |  | 2025-05-30 | 2025-08-11
I2S-7688-MP-74.PR.SP.16 | Pkg 29 - Traffic Control Crews Rates including the reports/plans | I.GG.P.EW.10C-9 | PROC - Pkg 29 - Traffic Control - Engage Subcontractor | 2025-05-30 | 2025-07-25
I2S-7688-MP-74.PR.SP.16 | Pkg 29 - Traffic Control Crews Rates including the reports/plans | I.GG.P.EW.1090910 | PROC - Pkg 29 - Traffic Control - Subcontractor Mob to Site | 2025-07-28 | 2025-08-11
Pkg 30 - Freight / logistic |  |  |  | 2025-07-28 | 2025-10-07
I2S-7688-MP-74.PR.SP.17 | Pkg 30 - Freight / logistic | I.GG.P.EW.10909250 | PROC - Pkg 30 - Freight / Logistics - Engage Subcontractor | 2025-07-28 | 2025-09-22
I2S-7688-MP-74.PR.SP.17 | Pkg 30 - Freight / logistic | I.GG.P.EW.10909260 | PROC - Pkg 30 - Freight / Logistics - Subcontractor Mob to Site | 2025-09-23 | 2025-10-07
General Project Wide |  |  |  | 2024-11-29 | 2025-08-08
Pkg 33 - General Labour & Rail Labour Hire (Excluding Signals) |  |  |  | 2025-03-11 | 2025-05-22
I2S-7688-MP-74.PR.GPW.24 | Pkg 33 - General Labour & Rail Labour Hire (Excluding Signals) | I.GG.P.G.101140 | PROC - Pkg 33 - General Labour & Rail Labour Hire (Excluding Signals) - Engage | 2025-03-11 | 2025-05-08
I2S-7688-MP-74.PR.GPW.24 | Pkg 33 - General Labour & Rail Labour Hire (Excluding Signals) | I.GG.P.G.101150 | PROC - Pkg 33 - General Labour & Rail Labour Hire (Excluding Signals) - Mob to Site | 2025-05-09 | 2025-05-22
Pkg 35 - Concrete Supply |  |  |  | 2025-01-15 | 2025-06-10
I2S-7688-MP-74.PR.GPW.18 | Pkg 35 - Concrete Supply | I.GG.P.C.10C-390 | PROC - Pkg 35 - Concrete Supply - Concrete Supply | 2025-03-13 | 2025-06-10
I2S-7688-MP-74.PR.GPW.18 | Pkg 35 - Concrete Supply | I.GG.P.C.10C-380 | PROC - Pkg 35 - Concrete Supply - Engage Subcontractor | 2025-01-15 | 2025-03-12
Pkg 36 - Reinforcing Steel Supply |  |  |  | 2024-11-29 | 2025-07-17
I2S-7688-MP-74.PR.GPW.19 | Pkg 36 - Reinforcing Steel Supply | I.GG.P.C.10TR-11 | PROC - Pkg 36 - Reinforcing Steel (Reo) Supply - Prepare Tender Documents | 2024-11-29 | 2025-01-09
I2S-7688-MP-74.PR.GPW.19 | Pkg 36 - Reinforcing Steel Supply | I.GG.P.C.10TR-12 | PROC - Pkg 36 - Reinforcing Steel (Reo) Supply- Pricing by Suppliers / Subcontractors | 2025-01-10 | 2025-02-07
I2S-7688-MP-74.PR.GPW.19 | Pkg 36 - Reinforcing Steel Supply | I.GG.P.C.10TR-13 | PROC - Pkg 36 - Reinforcing Steel (Reo) Supply - Package Review / Approval | 2025-02-10 | 2025-02-21
I2S-7688-MP-74.PR.GPW.19 | Pkg 36 - Reinforcing Steel Supply | I.GG.P.C.10TR-14 | PROC - Pkg 36 - Reinforcing Steel (Reo) Supply - Package Placement | 2025-02-24 | 2025-03-07
I2S-7688-MP-74.PR.GPW.19 | Pkg 36 - Reinforcing Steel Supply | I.GG.P.C.10TR-15 | PROC - Pkg 36 - Reinforcing Steel (Reo) Supply - Manufacturing & Delivery | 2025-03-10 | 2025-07-17
Pkg 37 - Quarry Materials |  |  |  | 2025-02-24 | 2025-04-23
I2S-7688-MP-74.PR.GPW.20 | Pkg 37 - Quarry Materials | I.GG.P.EW.103335 | PROC - Pkg 37 - Quarry Materials - Engage Subcontractor | 2025-02-24 | 2025-04-22
I2S-7688-MP-74.PR.GPW.20 | Pkg 37 - Quarry Materials | I.GG.P.EW.1033570 | PROC - Pkg 37 - Quarry Materials - Supplies | 2025-04-23 | 2025-04-23
Pkg 38 - Plant Hire |  |  |  | 2025-03-13 | 2025-05-26
I2S-7688-MP-74.PR.GPW.21 | Pkg 38 - Plant Hire | I.GG.P.EW.10C-210 | PROC - Pkg 38 - Plant Hire - Subcontractor Mob to Site | 2025-05-13 | 2025-05-26
I2S-7688-MP-74.PR.GPW.21 | Pkg 38 - Plant Hire | I.GG.P.EW.10C-200 | PROC - Pkg 38 - Plant Hire - Engage Subcontractor | 2025-03-13 | 2025-05-12
Pkg 40 - Crane Hire |  |  |  | 2025-04-23 | 2025-08-08
I2S-7688-MP-74.PR.GPW.23b | Pkg 40 - Crane Hire | I.GG.P.C.10C-400 | PROC - Pkg 40 - Crane Hire - Engage Subcontractor | 2025-04-23 | 2025-06-19
I2S-7688-MP-74.PR.GPW.23b | Pkg 40 - Crane Hire | I.GG.P.C.10C-410 | PROC - Pkg 40 - Crane Hire - Subcontractor Mob to Site | 2025-06-20 | 2025-08-08
Pkg 116 - Temporary Works (Design or Supply) |  |  |  | 2025-03-17 | 2025-05-21
I2S-7688-MP-74.PR.GPW.25 | Pkg 116 - Temporary Works (Design or Supply) | I.GG.P.G.101180 | PROC - Pkg 116 - Temporary Works (Design or Supply) - Engage Temporary Works | 2025-03-17 | 2025-05-14
I2S-7688-MP-74.PR.GPW.25 | Pkg 116 - Temporary Works (Design or Supply) | I.GG.P.G.101190 | PROC - Pkg 116 - Temporary Works (Design or Supply) - Mob to Site | 2025-05-15 | 2025-05-21
Civil |  |  |  | 2024-12-06 | 2026-04-17
Pkg 44 - Bored Piling |  |  |  | 2025-06-13 | 2025-09-05
I2S-7688-MP-74.PR.CV.01 | Pkg 44 - Bored Piling | I.GG.P.C.10C-460 | PROC - Pkg 44 - Bored Piling - Engage Subcontractor | 2025-06-13 | 2025-08-08
I2S-7688-MP-74.PR.CV.01 | Pkg 44 - Bored Piling | I.GG.P.C.10C-470 | PROC - Pkg 44 - Bored Piling - Piling detail design Review & Subcontractor Mob to Site | 2025-08-11 | 2025-09-05
Pkg 46 - Structural/Metalwork S&I (HR/ bridge walkway/protection screens) |  |  |  | 2024-12-06 | 2025-07-10
I2S-7688-MP-74.PR.CV.04 | Pkg 46 - Structural/Metalwork S&I (HR/ bridge walkway/protection screens) | I.GG.P.C.10TR-48 | PROC - Pkg 46 - 01 - Structural/Metalwork S&I - Prepare Tender Documents | 2024-12-06 | 2025-01-16
I2S-7688-MP-74.PR.CV.04 | Pkg 46 - Structural/Metalwork S&I (HR/ bridge walkway/protection screens) | I.GG.P.C.10TR-58 | PROC - Pkg 46 - Structural/Metalwork S&I - Pricing by Suppliers / Subcontractors | 2025-01-17 | 2025-02-14
I2S-7688-MP-74.PR.CV.04 | Pkg 46 - Structural/Metalwork S&I (HR/ bridge walkway/protection screens) | I.GG.P.C.10TR-68 | PROC - Pkg 46 - Structural/Metalwork S&I - Package Review / Approval | 2025-02-17 | 2025-02-28
I2S-7688-MP-74.PR.CV.04 | Pkg 46 - Structural/Metalwork S&I (HR/ bridge walkway/protection screens) | I.GG.P.C.10TR-78 | PROC - Pkg 46 - Struc/Metal S&I - BGW - Package Placement | 2025-03-03 | 2025-03-14
I2S-7688-MP-74.PR.CV.04 | Pkg 46 - Structural/Metalwork S&I (HR/ bridge walkway/protection screens) | I.GG.P.C.10TR-88 | PROC - Pkg 46 - Struc/Metal S&I - BGW - Manufacturing & Delivery - bridge works | 2025-03-17 | 2025-07-10
I2S-7688-MP-74.PR.CV.04 | Pkg 46 - Structural/Metalwork S&I (HR/ bridge walkway/protection screens) | I.GG.P.C.10TR-428 | PROC - Pkg 46 - Struc/Metal S&I - BGW - Re-issue for Tender
Pkg 46-01 - Structural/Metalwork (Hand Rails)
I2S-7688-MP-74.PR.CV.4 | Pkg 46-01 - Structural/Metalwork (Hand Rails) | I.GG.P.C.10TR-368 | PROC - Pkg 46 - 01 - Structural/Metalwork (Handrails) - Prepare Tender Documents
I2S-7688-MP-74.PR.CV.4 | Pkg 46-01 - Structural/Metalwork (Hand Rails) | I.GG.P.C.10TR-378 | PROC - Pkg 46 - 01 - Structural/Metalwork (Handrails) - Pricing by Suppliers / Subcontractors
I2S-7688-MP-74.PR.CV.4 | Pkg 46-01 - Structural/Metalwork (Hand Rails) | I.GG.P.C.10TR-388 | PROC - Pkg 46 - 01 - Structural/Metalwork (Handrails) - Package Review
I2S-7688-MP-74.PR.CV.4 | Pkg 46-01 - Structural/Metalwork (Hand Rails) | I.GG.P.C.10TR-398 | PROC - Pkg 46 - 01 - Structural/Metalwork (Handrails) - Package Placement
I2S-7688-MP-74.PR.CV.4 | Pkg 46-01 - Structural/Metalwork (Hand Rails) | I.GG.P.C.10TR-418 | PROC - Pkg 46 - 01 - Structural/Metalwork (Handrails) - Package Approval
I2S-7688-MP-74.PR.CV.4 | Pkg 46-01 - Structural/Metalwork (Hand Rails) | I.GG.P.C.10TR-438 | PROC - Pkg 46 - 01 - Structural/Metalwork (Handrails) - Manufacturing & Delivery
Pkg 47 - Asphalt & Milling |  |  |  | 2025-06-13 | 2025-09-08
I2S-7688-MP-74.PR.CV.05 | Pkg 47 - Asphalt & Milling | I.GG.P.C.10C-590 | PROC - Pkg 47 - Asphalt & Milling - Engage Subcontractor | 2025-06-13 | 2025-08-11
I2S-7688-MP-74.PR.CV.05 | Pkg 47 - Asphalt & Milling | I.GG.P.C.10C-600 | PROC - Pkg 47 - Asphalt & Milling - Subcontractor Mob to Site | 2025-08-11 | 2025-09-08
Pkg 47-01 - Spray Seal
I2S-7688-MP-74.PR.CV.5 | Pkg 47-01 - Spray Seal | I.GG.P.C.10C-750 | PROC - Pkg 47-01 - Spray Seal - Engage Subcontractor
I2S-7688-MP-74.PR.CV.5 | Pkg 47-01 - Spray Seal | I.GG.P.C.10C-760 | PROC - Pkg 47-01 - Spray Seal - Subcontractor Mob to Site
Pkg 48 - Clearing and Grubbing |  |  |  | 2025-04-17 | 2025-07-15
I2S-7688-MP-74.PR.CV.06 | Pkg 48 - Clearing and Grubbing | I.GG.P.C.10C-610 | PROC - Pkg 48 - Clearing and Grubbing - Engage Subcontractor | 2025-04-17 | 2025-06-17
I2S-7688-MP-74.PR.CV.06 | Pkg 48 - Clearing and Grubbing | I.GG.P.C.10C-620 | PROC - Pkg 48 - Clearing and Grubbing - Subcontractor Mob to Site | 2025-06-18 | 2025-07-15
Pkg 49 - Soft Landscaping |  |  |  | 2025-07-08 | 2025-09-30
I2S-7688-MP-74.PR.CV.07 | Pkg 49 - Soft Landscaping | I.GG.P.C.10C-27 | PROC - Pkg 49 - Soft Landscaping - Engage Subcontractor | 2025-07-08 | 2025-09-02
I2S-7688-MP-74.PR.CV.07 | Pkg 49 - Soft Landscaping | I.GG.P.C.10C-28 | PROC - Pkg 49 - Soft Landscaping - Subcontractor Mob to Site | 2025-09-03 | 2025-09-30
Pkg 51- Form Reo Pour - Bridge |  |  |  | 2025-04-17 | 2025-07-22
I2S-7688-MP-74.PR.CV.09 | Pkg 51- Form Reo Pour - Bridge | I.GG.P.C.1090143 | PROC - Pkg 51 - Form Reo Pour (FRP) - Bridge - Subcontractor Awarded
I2S-7688-MP-74.PR.CV.09 | Pkg 51- Form Reo Pour - Bridge | I.GG.P.C.10917 | PROC - Pkg 51 - Form Reo Pour (FRP) - Bridge - Engage Subcontractor | 2025-04-17 | 2025-06-17
I2S-7688-MP-74.PR.CV.09 | Pkg 51- Form Reo Pour - Bridge | I.GG.P.C.10C-18 | PROC - Pkg 51 - Form Reo Pour (FRP) - Lead time + Mob to Site | 2025-06-18 | 2025-07-22
Pkg 53- Open Channel Drainage |  |  |  | 2024-12-06 | 2025-04-04
I2S-7688-MP-74.PR.CV.11 | Pkg 53- Open Channel Drainage | I.GG.P.C.10C-520 | PROC - Pkg 53 - Open Channel Drainage - Engage Subcontractor | 2024-12-06 | 2025-02-14
I2S-7688-MP-74.PR.CV.11 | Pkg 53- Open Channel Drainage | I.GG.P.C.10C-530 | PROC - Pkg 53 - Open Channel Drainage - Subcontractor Mob to Site | 2025-02-17 | 2025-04-04
Pkg 54- Fencing S&I |  |  |  | 2025-02-07 | 2025-07-03
I2S-7688-MP-74.PR.CV.12 | Pkg 54- Fencing S&I | I.GG.P.R.10W-247 | PROC - Pkg 54 - Fencing S&I - Pricing by Suppliers / Subcontractors | 2025-03-07 | 2025-04-03
I2S-7688-MP-74.PR.CV.12 | Pkg 54- Fencing S&I | I.GG.P.R.10W-257 | PROC - Pkg 54 - Fencing S&I - Package Review / Approval | 2025-04-04 | 2025-04-17
I2S-7688-MP-74.PR.CV.12 | Pkg 54- Fencing S&I | I.GG.P.R.10W-267 | PROC - Pkg 54 - Fencing S&I - Package Placement | 2025-04-23 | 2025-05-07
I2S-7688-MP-74.PR.CV.12 | Pkg 54- Fencing S&I | I.GG.P.R.10W-277 | PROC - Pkg 54 - Fencing S&I - Manufacturing & Delivery | 2025-05-08 | 2025-07-03
I2S-7688-MP-74.PR.CV.12 | Pkg 54- Fencing S&I | I.GG.P.R.10W-237 | PROC - Pkg 54 - Fencing S&I - Prepare Tender Documents | 2025-02-07 | 2025-03-06
Pkg 55- Guardrail |  |  |  | 2025-02-14 | 2025-07-23
I2S-7688-MP-74.PR.CV.13 | Pkg 55- Guardrail | I.GG.P.R.10W-187 | PROC - Pkg 55 - Guardrail - Prepare Tender Documents | 2025-02-14 | 2025-03-13
I2S-7688-MP-74.PR.CV.13 | Pkg 55- Guardrail | I.GG.P.R.10W-197 | PROC - Pkg 55 - Guardrail - Pricing by Suppliers / Subcontractors - Guardrails | 2025-03-14 | 2025-04-10
I2S-7688-MP-74.PR.CV.13 | Pkg 55- Guardrail | I.GG.P.R.10W-207 | PROC - Pkg 55 - Guardrail - Package Review / Approval - Guardrails | 2025-04-11 | 2025-04-29
I2S-7688-MP-74.PR.CV.13 | Pkg 55- Guardrail | I.GG.P.R.10W-217 | PROC - Pkg 55 - Guardrail - Package Placement - Guardrails | 2025-04-30 | 2025-05-13
I2S-7688-MP-74.PR.CV.13 | Pkg 55- Guardrail | I.GG.P.R.10W-227 | PROC - Pkg 55 - Guardrail - Manufacturing & Delivery - Guardrails | 2025-05-14 | 2025-07-23
Pkg 56- Linemarking |  |  |  | 2025-02-07 | 2025-07-03
I2S-7688-MP-74.PR.CV.14 | Pkg 56- Linemarking | I.GG.P.R.10W-137 | PROC - Pkg 56 - Linemarking - Prepare Tender Documents | 2025-02-07 | 2025-03-06
I2S-7688-MP-74.PR.CV.14 | Pkg 56- Linemarking | I.GG.P.R.10W-147 | PROC - Pkg 56 - Linemarking - Pricing by Suppliers / Subcontractors | 2025-03-07 | 2025-04-03
I2S-7688-MP-74.PR.CV.14 | Pkg 56- Linemarking | I.GG.P.R.10W-157 | PROC - Pkg 56 - Linemarking - Package Review / Approval | 2025-04-04 | 2025-04-17
I2S-7688-MP-74.PR.CV.14 | Pkg 56- Linemarking | I.GG.P.R.10W-167 | PROC - Pkg 56 - Linemarking - Package Placement | 2025-04-23 | 2025-05-07
I2S-7688-MP-74.PR.CV.14 | Pkg 56- Linemarking | I.GG.P.R.10W-177 | PROC - Pkg 56 - Linemarking - Manufacturing & Delivery | 2025-05-08 | 2025-07-03
Pkg 57- Signage S&I (Track) |  |  |  | 2025-02-07 | 2025-07-17
I2S-7688-MP-74.PR.CV.15 | Pkg 57- Signage S&I (Track) | I.GG.P.R.10W-87 | PROC - Pkg 57- Signage S&I (Track) - Prepare Tender Documents | 2025-02-07 | 2025-03-06
I2S-7688-MP-74.PR.CV.15 | Pkg 57- Signage S&I (Track) | I.GG.P.R.10W-97 | PROC - Pkg 57- Signage S&I (Track) - Pricing by Suppliers / Subcontractors | 2025-03-07 | 2025-04-03
I2S-7688-MP-74.PR.CV.15 | Pkg 57- Signage S&I (Track) | I.GG.P.R.10W-107 | PROC - Pkg 57- Signage S&I (Track) - Package Review / Approval | 2025-04-04 | 2025-04-17
I2S-7688-MP-74.PR.CV.15 | Pkg 57- Signage S&I (Track) | I.GG.P.R.10W-117 | PROC - Pkg 57- Signage S&I (Track) - Package Placement | 2025-04-23 | 2025-05-07
I2S-7688-MP-74.PR.CV.15 | Pkg 57- Signage S&I (Track) | I.GG.P.R.10W-127 | PROC - Pkg 57- Signage S&I (Track) - Manufacturing & Delivery | 2025-05-08 | 2025-07-17
I2S-7688-MP-74.PR.CV.15 | Pkg 57- Signage S&I (Track) | I.GG.P.R.10W-967 | PROC - Pkg 57- Signage S&I (Track) - Prepare Tender Documents - revised - PO
Pkg 57-02 - Signage S&I - Roads
I2S-7688-MP-74.PR.CV.6 | Pkg 57-02 - Signage S&I - Roads | I.GG.P.R.10W-970 | PROC - Pkg 57-02 - Signage S&I - Roads - Prepare Tender Documents
I2S-7688-MP-74.PR.CV.6 | Pkg 57-02 - Signage S&I - Roads | I.GG.P.R.10W-980 | PROC - Pkg 57-02 - Signage S&I - Roads - Pricing by Suppliers / Subcontractors
I2S-7688-MP-74.PR.CV.6 | Pkg 57-02 - Signage S&I - Roads | I.GG.P.R.10W-990 | PROC - Pkg 57-02 - Signage S&I - Roads - Package Review / Approval
I2S-7688-MP-74.PR.CV.6 | Pkg 57-02 - Signage S&I - Roads | I.GG.P.R.10W-1000 | PROC - Pkg 57-02 - Signage S&I - Roads - Package Placement
I2S-7688-MP-74.PR.CV.6 | Pkg 57-02 - Signage S&I - Roads | I.GG.P.R.10W-1010 | PROC - Pkg 57-02 - Signage S&I - Roads - Manufacturing & Delivery
Pkg 60- Stormwater Drainage - install |  |  |  | 2025-07-18 | 2025-10-20
I2S-7688-MP-74.PR.CV.18 | Pkg 60- Stormwater Drainage - install | I.GG.P.D.10C-260 | PROC - Pkg 60 - Stormwater Drainage - Install - Engage Subcontractor | 2025-07-18 | 2025-09-12
I2S-7688-MP-74.PR.CV.18 | Pkg 60- Stormwater Drainage - install | I.GG.P.D.10C-270 | PROC - Pkg 60 - Stormwater Drainage - Install - Subcontractor Mob to Site | 2025-09-15 | 2025-10-20
Pkg 62- Precast Pipe, Culvert, Pit, Headwall & Kerbs Supply |  |  |  | 2024-12-06 | 2025-11-11
I2S-7688-MP-74.PR.CV.21 | Pkg 62- Precast Pipe, Culvert, Pit, Headwall & Kerbs Supply | I.GG.P.D.10R-585 | PROC - Pkg 62 - Precast Pipe, Culvert, Pit, Headwall & Kerbs - ( RCP + RCBC) - IRPL review (1st of types) - completed
I2S-7688-MP-74.PR.CV.21 | Pkg 62- Precast Pipe, Culvert, Pit, Headwall & Kerbs Supply | I.GG.P.D.1000025 | PROC - Pkg 62 - Precast Pipe, Culvert, Pit, Headwall & Kerbs - ( RCP + RCBC) - Inspection of Pre-cast Fabrication Yard | 2025-04-03 | 2025-06-10
I2S-7688-MP-74.PR.CV.21 | Pkg 62- Precast Pipe, Culvert, Pit, Headwall & Kerbs Supply | I.GG.P.D.10R-265 | PROC - Pkg 62 - Precast Pipe, Culvert, Pit, Headwall & Kerbs - ( RCP + RCBC) - Receive Drawings | 2025-06-11 | 2025-07-08
I2S-7688-MP-74.PR.CV.21 | Pkg 62- Precast Pipe, Culvert, Pit, Headwall & Kerbs Supply | I.GG.P.D.10R-285 | PROC - Pkg 62 - Precast Pipe, Culvert, Pit, Headwall & Kerbs - ( RCP + RCBC) - Manufacturing & Delivery | 2025-09-02 | 2025-11-11
I2S-7688-MP-74.PR.CV.21 | Pkg 62- Precast Pipe, Culvert, Pit, Headwall & Kerbs Supply | I.GG.P.D.1000045 | PROC - Pkg 62 - Precast Pipe, Culvert, Pit, Headwall & Kerbs - ( RCP + RCBC) - Prepare Tender Documents | 2024-12-06 | 2025-01-16
I2S-7688-MP-74.PR.CV.21 | Pkg 62- Precast Pipe, Culvert, Pit, Headwall & Kerbs Supply | I.GG.P.D.10R-525 | PROC - Pkg 62 - Precast Pipe, Culvert, Pit, Headwall & Kerbs - ( RCP + RCBC) - Pricing by Suppliers / Subcontractors | 2025-01-17 | 2025-02-14
I2S-7688-MP-74.PR.CV.21 | Pkg 62- Precast Pipe, Culvert, Pit, Headwall & Kerbs Supply | I.GG.P.D.10R-535 | PROC - Pkg 62 - Precast Pipe, Culvert, Pit, Headwall & Kerbs - ( RCP + RCBC) - Package Review / Approval | 2025-02-17 | 2025-02-28
I2S-7688-MP-74.PR.CV.21 | Pkg 62- Precast Pipe, Culvert, Pit, Headwall & Kerbs Supply | I.GG.P.D.10R-545 | PROC - Pkg 62 - Precast Pipe, Culvert, Pit, Headwall & Kerbs - ( RCP + RCBC) - Package Placement - RCP + RCBC | 2025-03-03 | 2025-03-14
I2S-7688-MP-74.PR.CV.21 | Pkg 62- Precast Pipe, Culvert, Pit, Headwall & Kerbs Supply | I.GG.P.D.10R-575 | PROC - Pkg 62 - Precast Pipe, Culvert, Pit, Headwall & Kerbs - ( RCP + RCBC) - Designer Review & Approve
Pkg 70 - HDPE Supply |  |  |  | 2025-02-17 | 2026-04-17
I2S-7688-MP-74.PR.CV.1 | Pkg 70 - HDPE Supply | I.GG.P.D.10R-375 | PROC - Pkg 70 - HDPE Supply - Manufacturing & Delivery | 2025-05-23 | 2026-04-17
I2S-7688-MP-74.PR.CV.1 | Pkg 70 - HDPE Supply | I.GG.P.D.1000015 | PROC - Pkg 70 - HDPE Supply - Prepare Tender Documents | 2025-02-17 | 2025-03-14
I2S-7688-MP-74.PR.CV.1 | Pkg 70 - HDPE Supply | I.GG.P.D.10R-25 | PROC - Pkg 70 - HDPE Supply - Pricing by Suppliers / Subcontractors | 2025-03-17 | 2025-04-11
I2S-7688-MP-74.PR.CV.1 | Pkg 70 - HDPE Supply | I.GG.P.D.10R-35 | PROC - Pkg 70 - HDPE Supply - Package Review / Approval | 2025-04-14 | 2025-04-22
I2S-7688-MP-74.PR.CV.1 | Pkg 70 - HDPE Supply | I.GG.P.D.10R-45 | PROC - Pkg 70 - HDPE Supply - Package Placement | 2025-05-16 | 2025-05-22
Pkg 63- Geotextile Supply |  |  |  | 2025-02-07 | 2025-06-30
I2S-7688-MP-74.PR.CV.24 | Pkg 63- Geotextile Supply | I.GG.P.C.10TR-188 | PROC - Pkg 63 - Geotextile Supply - Manufacturing & Delivery - of shelf item - readiliy available | 2025-05-08 | 2025-06-30
I2S-7688-MP-74.PR.CV.24 | Pkg 63- Geotextile Supply | I.GG.P.C.10TR-148 | PROC - Pkg 63 - Geotextile Supply - Prepare Tender Documents | 2025-02-07 | 2025-03-06
I2S-7688-MP-74.PR.CV.24 | Pkg 63- Geotextile Supply | I.GG.P.C.10TR-158 | PROC - Pkg 63 - Geotextile Supply - Pricing by Suppliers / Subcontractors | 2025-03-07 | 2025-04-03
I2S-7688-MP-74.PR.CV.24 | Pkg 63- Geotextile Supply | I.GG.P.C.10TR-168 | PROC - Pkg 63 - Geotextile Supply - Package Review / Approval | 2025-04-04 | 2025-04-17
I2S-7688-MP-74.PR.CV.24 | Pkg 63- Geotextile Supply | I.GG.P.C.10TR-178 | PROC - Pkg 63 - Geotextile Supply - Package Placement | 2025-04-23 | 2025-05-07
Pkg 64-02 - Drill and Blast |  |  |  | 2025-01-16 | 2025-04-10
I2S-7688-MP-74.PR.CV.27 | Pkg 64-02 - Drill and Blast | I.GG.P.R.10W-807 | PROC - Pkg 64-02 - Drill and Blast - Prepare Tender Documents | 2025-01-16 | 2025-02-13
I2S-7688-MP-74.PR.CV.27 | Pkg 64-02 - Drill and Blast | I.GG.P.R.10W-817 | PROC - Pkg 64-02 - Drill and Blast - Pricing by Suppliers / Subcontractors | 2025-02-14 | 2025-03-13
I2S-7688-MP-74.PR.CV.27 | Pkg 64-02 - Drill and Blast | I.GG.P.R.10W-827 | PROC - Pkg 64-02 - Drill and Blast - Package Review / Approval | 2025-03-14 | 2025-03-27
I2S-7688-MP-74.PR.CV.27 | Pkg 64-02 - Drill and Blast | I.GG.P.R.10W-837 | PROC - Pkg 64-02 - Drill and Blast - Package Placement | 2025-03-28 | 2025-04-10
Pkg 66 - Crushing and Screening |  |  |  | 2025-01-16 | 2025-07-23
I2S-7688-MP-74.PR.CV.22 | Pkg 66 - Crushing and Screening | I.GG.P.D.10R-215 | PROC - Pkg 66 - Crushing and Screening - Prepare Tender Documents | 2025-01-16 | 2025-02-13
I2S-7688-MP-74.PR.CV.22 | Pkg 66 - Crushing and Screening | I.GG.P.D.10R-225 | PROC - Pkg 66 - Crushing and Screening - Pricing by Suppliers / Subcontractors | 2025-02-14 | 2025-03-13
I2S-7688-MP-74.PR.CV.22 | Pkg 66 - Crushing and Screening | I.GG.P.D.10R-235 | PROC - Pkg 66 - Crushing and Screening - Package Review / Approval | 2025-03-14 | 2025-03-27
I2S-7688-MP-74.PR.CV.22 | Pkg 66 - Crushing and Screening | I.GG.P.D.10R-245 | PROC - Pkg 66 - Crushing and Screening - Package Placement + Contract Award | 2025-03-28 | 2025-04-10
I2S-7688-MP-74.PR.CV.22 | Pkg 66 - Crushing and Screening | I.GG.P.D.10R-255 | PROC - Pkg 66 - Crushing and Screening - Manufacturing & Delivery | 2025-04-11 | 2025-07-23
Pkg 68 - Fauna Crossing S&I |  |  |  | 2025-06-16 | 2025-12-02
I2S-7688-MP-74.PR.CV.25 | Pkg 68 - Fauna Crossing S&I | I.GG.P.D.10R-125 | PROC - Pkg 68 - Fauna Crossing S&I - Pricing by Suppliers / Subcontractors | 2025-07-14 | 2025-08-11
I2S-7688-MP-74.PR.CV.25 | Pkg 68 - Fauna Crossing S&I | I.GG.P.D.10R-135 | PROC - Pkg 68 - Fauna Crossing S&I - Package Review / Approval | 2025-08-12 | 2025-08-25
I2S-7688-MP-74.PR.CV.25 | Pkg 68 - Fauna Crossing S&I | I.GG.P.D.10R-145 | PROC - Pkg 68 - Fauna Crossing S&I - Package Placement | 2025-08-26 | 2025-09-08
I2S-7688-MP-74.PR.CV.25 | Pkg 68 - Fauna Crossing S&I | I.GG.P.D.10R-155 | PROC - Pkg 68 - Fauna Crossing S&I - Manufacturing & Delivery | 2025-09-09 | 2025-12-02
I2S-7688-MP-74.PR.CV.25 | Pkg 68 - Fauna Crossing S&I | I.GG.P.D.10R-115 | PROC - Pkg 68 - Fauna Crossing S&I - Prepare Tender Documents | 2025-06-16 | 2025-07-11
Pkg 142- FRP Drainage Install
I2S-7688-MP-74.PR.CV.3 | Pkg 142- FRP Drainage Install | I.GG.P.D.10C-280 | PROC - Pkg 142 - FRP Drainage install - Engage Subcontractor
I2S-7688-MP-74.PR.CV.3 | Pkg 142- FRP Drainage Install | I.GG.P.D.10C-290 | PROC - Pkg 142 - FRP Drainage install - Subcontractor Mob to Site
Pkg 144 - Pile Trimming
I2S-7688-MP-74.PR.CV.2 | Pkg 144 - Pile Trimming | I.GG.P.C.10C-730 | PROC - Pkg 144 - Pile Trimming - Engage Subcontractor
I2S-7688-MP-74.PR.CV.2 | Pkg 144 - Pile Trimming | I.GG.P.C.10C-740 | PROC - Pkg 144 - Pile Trimming - Subcontractor Mob to Site
Structures |  |  |  | 2024-12-06 | 2026-04-13
Pkg 71 - Bridge Bearing / Expansion Joints |  |  |  | 2024-12-06 | 2025-06-20
I2S-7688-MP-74.PR.ST.01 | Pkg 71 - Bridge Bearing / Expansion Joints | I.GG.P.C.10TR-20 | PROC - Pkg 71 - Bridge Bearing / Expansion Joints - Manufacturing & Delivery | 2025-05-08 | 2025-06-20
I2S-7688-MP-74.PR.ST.01 | Pkg 71 - Bridge Bearing / Expansion Joints | I.GG.P.C.10TR-16 | PROC - Pkg 71 - Bridge Bearing / Expansion Joints - Prepare Tender Documents | 2024-12-06 | 2025-01-16
I2S-7688-MP-74.PR.ST.01 | Pkg 71 - Bridge Bearing / Expansion Joints | I.GG.P.C.10TR-17 | PROC - Pkg 71 - Bridge Bearing / Expansion Joints - Pricing by Suppliers / Subcontractors | 2025-01-17 | 2025-02-14
I2S-7688-MP-74.PR.ST.01 | Pkg 71 - Bridge Bearing / Expansion Joints | I.GG.P.C.10TR-18 | PROC - Pkg 71 - Bridge Bearing / Expansion Joints - Package Review / Approval | 2025-02-17 | 2025-02-28
I2S-7688-MP-74.PR.ST.01 | Pkg 71 - Bridge Bearing / Expansion Joints | I.GG.P.C.10TR-19 | PROC - Pkg 71 - Bridge Bearing / Expansion Joints - Package Placement | 2025-04-23 | 2025-05-07
Pkg 72.1 - Precast Concrete including Parapet Barriers |  |  |  | 2024-12-06 | 2025-04-30
I2S-7688-MP-74.PR.ST.05 | Pkg 72.1 - Precast Concrete including Parapet Barriers | I.GG.P.C.10TR-298 | PROC - Pkg 72.1 - Precast Concrete incl.Parapet Barriers - Prepare Tender Documents | 2024-12-06 | 2025-01-16
I2S-7688-MP-74.PR.ST.05 | Pkg 72.1 - Precast Concrete including Parapet Barriers | I.GG.P.C.10TR-308 | PROC - Pkg 72.1 - Precast Concrete incl.Parapet Barriers - Pricing by Suppliers / Subcontractors | 2025-01-17 | 2025-02-14
I2S-7688-MP-74.PR.ST.05 | Pkg 72.1 - Precast Concrete including Parapet Barriers | I.GG.P.C.10TR-318 | PROC - Pkg 72.1 - Precast Concrete incl.Parapet Barriers - Package Review / Approval | 2025-02-17 | 2025-02-28
I2S-7688-MP-74.PR.ST.05 | Pkg 72.1 - Precast Concrete including Parapet Barriers | I.GG.P.C.10TR-328 | PROC - Pkg 72.1 - Precast Concrete incl.Parapet Barriers - Package Placement | 2025-03-03 | 2025-03-14
I2S-7688-MP-74.PR.ST.05 | Pkg 72.1 - Precast Concrete including Parapet Barriers | I.GG.P.C.10TR-338 | PROC - Pkg 72.1 - Precast Concrete incl.Parapet Barriers - Manufacturing & Delivery | 2025-03-17 | 2025-04-30
Pkg 72 - Super T /Slab |  |  |  | 2024-12-06 | 2026-04-13
I2S-7688-MP-74.PR.ST.03 | Pkg 72 - Super T /Slab | I.GG.P.C.10TR-34 | PROC - Pkg 72 - Super T / Slab - Prepare Tender Documents | 2024-12-06 | 2025-01-16
I2S-7688-MP-74.PR.ST.03 | Pkg 72 - Super T /Slab | I.GG.P.C.10TR-35 | PROC - Pkg 72 - Super T / Slab - Pricing by Suppliers / Subcontractors | 2025-01-17 | 2025-02-14
I2S-7688-MP-74.PR.ST.03 | Pkg 72 - Super T /Slab | I.GG.P.C.10TR-36 | PROC - Pkg 72 - Super T / Slab - Package Review / Approval - Additional Approvals required | 2025-02-17 | 2025-02-28
I2S-7688-MP-74.PR.ST.03 | Pkg 72 - Super T /Slab | I.GG.P.C.10TR-37 | PROC - Pkg 72 - Super T / Slab - Package Placement | 2025-03-10 | 2025-03-21
1500 SUPER-T (ARTC) |  |  |  | 2025-03-24 | 2025-12-15
I2S-7688-MP-74.PR.ST.03.1 | 1500 SUPER-T (ARTC) | I.GG.P.C.107520 | PROC - 1500 SUPER-T (ARTC) - Isobel Creek Tribitary Bridge - fabrication of Bridge span / Super T | 2025-10-28 | 2025-12-15
I2S-7688-MP-74.PR.ST.03.1 | 1500 SUPER-T (ARTC) | I.GG.P.C.105490 | PROC - 1500 SUPER-T (ARTC) - Isobel Creek Bridge - fabrication of Bridge span / Super T | 2025-09-08 | 2025-10-27
I2S-7688-MP-74.PR.ST.03.1 | 1500 SUPER-T (ARTC) | I.GG.P.C.105500 | PROC - 1500 SUPER-T (ARTC) - Dirnaseer Bridge - fabrication of Bridge span / Super T | 2025-05-01 | 2025-06-12
I2S-7688-MP-74.PR.ST.03.1 | 1500 SUPER-T (ARTC) | I.GG.P.C.107100 | PROC - 1500 SUPER-T (ARTC) - Run Boundary Creek Bridge - fabrication of Bridge span / Super T | 2025-07-25 | 2025-09-05
I2S-7688-MP-74.PR.ST.03.1 | 1500 SUPER-T (ARTC) | I.GG.P.C.10TR-348 | PROC - 1500 SUPER-T (ARTC) - Review Drawings - Precast beams - 16 weeks lead time | 2025-03-24 | 2025-04-30
I2S-7688-MP-74.PR.ST.03.1 | 1500 SUPER-T (ARTC) | I.GG.P.C.107380 | PROC - 1500 SUPER-T (ARTC) - Old Cootamundra Rail Bridge - Fabrication of Bridge span | 2025-09-08 | 2025-10-27
Standard PSC Slab Span 14m (ARTC) |  |  |  | 2025-03-24 | 2025-12-15
I2S-7688-MP-74.PR.ST.03.2 | Standard PSC Slab Span 14m (ARTC) | I.GG.P.C.107110 | PROC - Standard PSC Slab Span 14m (ARTC) - Ulandra Bridge - fabrication of Bridge span 14 m long (12 spans) | 2025-06-13 | 2025-07-24
I2S-7688-MP-74.PR.ST.03.2 | Standard PSC Slab Span 14m (ARTC) | I.GG.P.C.104600 | PROC - Standard PSC Slab Span 14m (ARTC) - Dudauman bridge - Fabrication of Bridge span | 2025-05-01 | 2025-07-03
I2S-7688-MP-74.PR.ST.03.2 | Standard PSC Slab Span 14m (ARTC) | I.GG.P.C.107090 | PROC - Standard PSC Slab Span 14m (ARTC) - Powder Horn Creek Bridge - Fabrication of Bridge span | 2025-10-28 | 2025-12-15
I2S-7688-MP-74.PR.ST.03.2 | Standard PSC Slab Span 14m (ARTC) | I.GG.P.C.107540 | PROC - Standard PSC Slab Span 14m (ARTC) - Billabong Creek Bridge - Fabrication of Bridge span | 2025-07-04 | 2025-09-05
I2S-7688-MP-74.PR.ST.03.2 | Standard PSC Slab Span 14m (ARTC) | I.GG.P.C.10TR-358 | PROC - Standard PSC Slab Span 14m (ARTC) - Review Drawings | 2025-03-24 | 2025-04-30
Standard PSC Plank Girder (RMS) |  |  |  | 2025-03-24 | 2026-04-13
I2S-7688-MP-74.PR.ST.03.3 | Standard PSC Plank Girder (RMS) | I.GG.P.C.10TR-38 | PROC - Standard PSC Plank Girder (RMS) - Review Drawings | 2025-03-24 | 2025-04-30
I2S-7688-MP-74.PR.ST.03.3 | Standard PSC Plank Girder (RMS) | I.GG.P.C.105480 | PROC - Standard PSC Plank Girder (RMS) - Burley Griffin Way Bridge - Fabrication of Bridge span | 2025-09-24 | 2026-04-13
Pkg 73 - Reinforced Soil Walls |  |  |  | 2024-12-06 | 2025-07-24
I2S-7688-MP-74.PR.ST.04 | Pkg 73 - Reinforced Soil Walls | I.GG.P.C.10TR-7 | PROC - Pkg 73 - Reinforced Soil Walls - Pricing by Suppliers / Subcontractors | 2025-01-17 | 2025-02-14
I2S-7688-MP-74.PR.ST.04 | Pkg 73 - Reinforced Soil Walls | I.GG.P.C.10TR-8 | PROC - Pkg 73 - Reinforced Soil Walls - Package Review / Approval | 2025-02-17 | 2025-02-28
I2S-7688-MP-74.PR.ST.04 | Pkg 73 - Reinforced Soil Walls | I.GG.P.C.10TR-9 | PROC - Pkg 73 - Reinforced Soil Walls - Package Placement | 2025-03-03 | 2025-03-14
I2S-7688-MP-74.PR.ST.04 | Pkg 73 - Reinforced Soil Walls | I.GG.P.C.10TR-10 | PROC - Pkg 73 - Reinforced Soil Walls - Manufacturing & Delivery (BGW / Old Coot / Dirnaseer) | 2025-03-17 | 2025-07-24
I2S-7688-MP-74.PR.ST.04 | Pkg 73 - Reinforced Soil Walls | I.GG.P.C.1000006 | PROC - Pkg 73 - Reinforced Soil Walls - Prepare Tender Documents | 2024-12-06 | 2025-01-16
Track |  |  |  | 2024-10-25 | 2025-10-13
Pkg: 77 - Rail Sleeper Transportation |  |  |  | 2025-02-14 | 2025-08-22
I2S-7688-MP-74.PR.TR.01 | Pkg: 77 - Rail Sleeper Transportation | I.GG.P.R.10W-1 | PROC - Pkg: 77 - Rail Sleeper Transportation - Prepare Tender Documents & issue to market | 2025-02-14 | 2025-03-13
I2S-7688-MP-74.PR.TR.01 | Pkg: 77 - Rail Sleeper Transportation | I.GG.P.R.10W-2 | PROC - Pkg: 77 - Rail Sleeper Transportation - Pricing by Suppliers / Subcontractors | 2025-03-14 | 2025-04-10
I2S-7688-MP-74.PR.TR.01 | Pkg: 77 - Rail Sleeper Transportation | I.GG.P.R.10W-3 | PROC - Pkg: 77 - Rail Sleeper Transportation - Package Review / Approval | 2025-04-11 | 2025-04-29
I2S-7688-MP-74.PR.TR.01 | Pkg: 77 - Rail Sleeper Transportation | I.GG.P.R.10W-4 | PROC - Pkg: 77 - Rail Sleeper Transportation - Package Placement | 2025-04-30 | 2025-05-13
I2S-7688-MP-74.PR.TR.01 | Pkg: 77 - Rail Sleeper Transportation | I.GG.P.R.10W-5 | PROC - Pkg: 77 - Rail Sleeper Transportation -Manufacturing & Delivery | 2025-05-14 | 2025-08-22
Pkg 78.1 - Rail Supply - Logistics |  |  |  | 2024-12-05 | 2025-06-25
I2S-7688-MP-74.PR.TR.02 | Pkg 78.1 - Rail Supply - Logistics | I.GG.P.R.10W-607 | PROC - Pkg 78.1 - Rail Supply - Package Review / Approval - Free Issue | 2025-02-14 | 2025-02-27
I2S-7688-MP-74.PR.TR.02 | Pkg 78.1 - Rail Supply - Logistics | I.GG.P.R.10W-617 | PROC - Pkg 78.1 - Rail Supply - Package Placement - Free Issue | 2025-02-28 | 2025-03-13
I2S-7688-MP-74.PR.TR.02 | Pkg 78.1 - Rail Supply - Logistics | I.GG.P.R.10W-627 | PROC - Pkg 78.1 - Rail Supply - Manufacturing & Delivery - Free Issue | 2025-03-14 | 2025-06-25
I2S-7688-MP-74.PR.TR.02 | Pkg 78.1 - Rail Supply - Logistics | I.GG.P.R.10W-587 | PROC - Pkg 78.1 - Rail Supply - Prepare Tender Documents | 2024-12-05 | 2025-01-15
I2S-7688-MP-74.PR.TR.02 | Pkg 78.1 - Rail Supply - Logistics | I.GG.P.R.10W-597 | PROC - Pkg 78.1 - Rail Supply - Pricing by Suppliers / Subcontractors | 2025-01-16 | 2025-02-13
Pkg 81 - Crossover Supply |  |  |  | 2024-12-05 | 2025-08-15
I2S-7688-MP-74.PR.TR.05 | Pkg 81 - Crossover Supply | I.GG.P.R.10W-16 | PROC - Pkg 81 - Switches and Crossings - Prepare Tender Documents | 2024-12-05 | 2025-01-15
I2S-7688-MP-74.PR.TR.05 | Pkg 81 - Crossover Supply | I.GG.P.R.10W-17 | PROC - Pkg 81 - Switches and Crossings - Pricing by Suppliers / Subcontractors | 2025-01-16 | 2025-02-13
I2S-7688-MP-74.PR.TR.05 | Pkg 81 - Crossover Supply | I.GG.P.R.10W-18 | PROC - Pkg 81 - Switches and Crossings - Package Review / Approval- Switches and Crossings | 2025-02-14 | 2025-02-27
I2S-7688-MP-74.PR.TR.05 | Pkg 81 - Crossover Supply | I.GG.P.R.10W-19 | PROC - Pkg 81 - Switches and Crossings - Package Placement- Switches and Crossings | 2025-04-23 | 2025-05-07
I2S-7688-MP-74.PR.TR.05 | Pkg 81 - Crossover Supply | I.GG.P.R.10W-20 | PROC - Pkg 81 - Crossover Supply - Manufacturing & Delivery | 2025-05-08 | 2025-08-15
Pkg 82 - Level Crossing Panel Supply |  |  |  | 2024-12-05 | 2025-09-26
I2S-7688-MP-74.PR.TR.06 | Pkg 82 - Level Crossing Panel Supply | I.GG.P.R.10W-787 | PROC - Pkg 82 - Level Crossing Panel Supply - Manufacturing & Delivery - PR38300 (Sec.6) | 2025-05-08 | 2025-09-26
I2S-7688-MP-74.PR.TR.06 | Pkg 82 - Level Crossing Panel Supply | I.GG.P.R.10W-797 | PROC - Pkg 82 - Level Crossing Panel Supply - Manufacturing & Delivery - PR39450 (Sec.6) | 2025-05-08 | 2025-09-26
I2S-7688-MP-74.PR.TR.06 | Pkg 82 - Level Crossing Panel Supply | I.GG.P.R.10W-337 | PROC - Pkg 82 - Level Crossing Panel Supply - Prepare Tender Documents | 2024-12-05 | 2025-01-15
I2S-7688-MP-74.PR.TR.06 | Pkg 82 - Level Crossing Panel Supply | I.GG.P.R.10W-347 | PROC - Pkg 82 - Level Crossing Panel Supply - Pricing by Suppliers / Subcontractors | 2025-01-16 | 2025-02-13
I2S-7688-MP-74.PR.TR.06 | Pkg 82 - Level Crossing Panel Supply | I.GG.P.R.10W-357 | PROC - Pkg 82 - Level Crossing Panel Supply - Package Review / Approval | 2025-02-14 | 2025-02-27
I2S-7688-MP-74.PR.TR.06 | Pkg 82 - Level Crossing Panel Supply | I.GG.P.R.10W-367 | PROC - Pkg 82 - Level Crossing Panel Supply - Package Placement | 2025-04-23 | 2025-05-07
I2S-7688-MP-74.PR.TR.06 | Pkg 82 - Level Crossing Panel Supply | I.GG.P.R.10W-767 | PROC - Pkg 82 - Level Crossing Panel Supply - Manufacturing & Delivery - Ironbong Road (PU8160) (Sec.2) | 2025-05-08 | 2025-09-26
I2S-7688-MP-74.PR.TR.06 | Pkg 82 - Level Crossing Panel Supply | I.GG.P.R.10W-777 | PROC - Pkg 82 - Level Crossing Panel Supply - Manufacturing & Delivery - PU11390 (Sec.3) | 2025-05-08 | 2025-09-26
I2S-7688-MP-74.PR.TR.06 | Pkg 82 - Level Crossing Panel Supply | I.GG.P.R.10W-857 | PROC - Pkg 82 - Level Crossing Panel Supply - Manufacturing & Delivery - PR34950 (Sec.5)
I2S-7688-MP-74.PR.TR.06 | Pkg 82 - Level Crossing Panel Supply | I.GG.P.R.10W-867 | PROC - Pkg 82 - Level Crossing Panel Supply - Manufacturing & Delivery - PU33780 (Sec.5)
I2S-7688-MP-74.PR.TR.06 | Pkg 82 - Level Crossing Panel Supply | I.GG.P.R.10W-877 | PROC - Pkg 82 - Level Crossing Panel Supply - Manufacturing & Delivery - PR32150 (Sec.5)
I2S-7688-MP-74.PR.TR.06 | Pkg 82 - Level Crossing Panel Supply | I.GG.P.R.10W-887 | PROC - Pkg 82 - Level Crossing Panel Supply - Manufacturing & Delivery - PR30850 (Sec.5)
I2S-7688-MP-74.PR.TR.06 | Pkg 82 - Level Crossing Panel Supply | I.GG.P.R.10W-897 | PROC - Pkg 82 - Level Crossing Panel Supply - Manufacturing & Delivery - PR24500 (Sec.4)
I2S-7688-MP-74.PR.TR.06 | Pkg 82 - Level Crossing Panel Supply | I.GG.P.R.10W-907 | PROC - Pkg 82 - Level Crossing Panel Supply - Manufacturing & Delivery - PR22750 (Sec.4)
I2S-7688-MP-74.PR.TR.06 | Pkg 82 - Level Crossing Panel Supply | I.GG.P.R.10W-917 | PROC - Pkg 82 - Level Crossing Panel Supply - Manufacturing & Delivery - PR21200 (Sec.4)
I2S-7688-MP-74.PR.TR.06 | Pkg 82 - Level Crossing Panel Supply | I.GG.P.R.10W-927 | PROC - Pkg 82 - Level Crossing Panel Supply - Manufacturing & Delivery - PR19800 (Sec.4)
I2S-7688-MP-74.PR.TR.06 | Pkg 82 - Level Crossing Panel Supply | I.GG.P.R.10W-937 | PROC - Pkg 82 - Level Crossing Panel Supply - Manufacturing & Delivery - PU15950 (Sec.3)
I2S-7688-MP-74.PR.TR.06 | Pkg 82 - Level Crossing Panel Supply | I.GG.P.R.10W-957 | PROC - Pkg 82 - Level Crossing Panel Supply - Manufacturing & Delivery - PU5600 (Sec.2)
Pkg 83 - Flashbutt Welding |  |  |  | 2025-05-23 | 2025-08-18
I2S-7688-MP-74.PR.TR.07 | Pkg 83 - Flashbutt Welding | I.GG.P.R.10C-300 | PROC - Pkg 83 - Flashbutt Welding - Engage Subcontractor -PO | 2025-05-23 | 2025-07-18
I2S-7688-MP-74.PR.TR.07 | Pkg 83 - Flashbutt Welding | I.GG.P.R.10C-310 | PROC - Pkg 83 - Flashbutt Welding - Subcontractor Mob to Site - PO | 2025-07-21 | 2025-08-18
Pkg 84 - Track Labour and Welder |  |  |  | 2025-06-13 | 2025-09-19
I2S-7688-MP-74.PR.TR.08 | Pkg 84 - Track Labour and Welder | I.GG.P.R.10C-280 | PROC - Pkg 84 - Track Labour and Welder - Engage Subcontractor | 2025-06-13 | 2025-08-22
I2S-7688-MP-74.PR.TR.08 | Pkg 84 - Track Labour and Welder | I.GG.P.R.10C-290 | PROC - Pkg 84 - Track Labour and Welder - Subcontractor Mob to Site - Track Labour and Welder | 2025-08-25 | 2025-09-19
Pkg 85 - Track Plant and Machineries |  |  |  | 2024-12-05 | 2025-05-13
I2S-7688-MP-74.PR.TR.09 | Pkg 85 - Track Plant and Machineries | I.GG.P.R.10W-427 | PROC - Pkg 85 - Track Plant and Machineries - VOC checks | 2025-03-14 | 2025-05-13
I2S-7688-MP-74.PR.TR.09 | Pkg 85 - Track Plant and Machineries | I.GG.P.R.10W-387 | PROC - Pkg 85 - Track Plant and Machineries - Prepare Tender Documents & issue to market | 2024-12-05 | 2025-01-15
I2S-7688-MP-74.PR.TR.09 | Pkg 85 - Track Plant and Machineries | I.GG.P.R.10W-397 | PROC - Pkg 85 - Track Plant and Machineries - Pricing by Suppliers / Subcontractors | 2025-01-16 | 2025-02-13
I2S-7688-MP-74.PR.TR.09 | Pkg 85 - Track Plant and Machineries | I.GG.P.R.10W-407 | PROC - Pkg 85 - Track Plant and Machineries - Package Review / Approval | 2025-02-14 | 2025-02-27
I2S-7688-MP-74.PR.TR.09 | Pkg 85 - Track Plant and Machineries | I.GG.P.R.10W-417 | PROC - Pkg 85 - Track Plant and Machineries - Package Placement | 2025-02-28 | 2025-03-13
Pkg 86 - Weld Kits Supply |  |  |  | 2024-12-05 | 2025-04-10
I2S-7688-MP-74.PR.TR.10 | Pkg 86 - Weld Kits Supply | I.GG.P.R.10W-577 | PROC - Pkg 86 - Weld Kits Supply - Manufacturing & Delivery - PO | 2025-03-14 | 2025-04-10
I2S-7688-MP-74.PR.TR.10 | Pkg 86 - Weld Kits Supply | I.GG.P.R.10W-537 | PROC - Pkg 86 - Weld Kits Supply - Prepare Tender Documents - PO | 2024-12-05 | 2025-01-15
I2S-7688-MP-74.PR.TR.10 | Pkg 86 - Weld Kits Supply | I.GG.P.R.10W-547 | PROC - Pkg 86 - Weld Kits Supply - Pricing by Suppliers / Subcontractors - PO | 2025-01-16 | 2025-02-13
I2S-7688-MP-74.PR.TR.10 | Pkg 86 - Weld Kits Supply | I.GG.P.R.10W-557 | PROC - Pkg 86 - Weld Kits Supply - Package Review / Approval - PO | 2025-02-14 | 2025-02-27
I2S-7688-MP-74.PR.TR.10 | Pkg 86 - Weld Kits Supply | I.GG.P.R.10W-567 | PROC - Pkg 86 - Weld Kits Supply - Package Placement - PO | 2025-02-28 | 2025-03-13
Pkg 87 - Ultrasonic Testing of Rail Welds |  |  |  | 2025-07-18 | 2025-10-13
I2S-7688-MP-74.PR.TR.11 | Pkg 87 - Ultrasonic Testing of Rail Welds | I.GG.P.R.10C-320 | PROC - Pkg 87 - Ultrasonic Testing of Rail Welds - Engage Subcontractor | 2025-07-18 | 2025-09-12
I2S-7688-MP-74.PR.TR.11 | Pkg 87 - Ultrasonic Testing of Rail Welds | I.GG.P.R.10C-330 | PROC - Pkg 87 - Ultrasonic Testing of Rail Welds - Subcontractor Mob to Site | 2025-09-15 | 2025-10-13
Pkg 88 - Locos and Wagons Supply |  |  |  | 2024-12-05 | 2025-05-13
I2S-7688-MP-74.PR.TR.12 | Pkg 88 - Locos and Wagons Supply | I.GG.P.R.10W-437 | PROC - Pkg 88 - Locos and Wagons Supply - Prepare Tender Documents | 2024-12-05 | 2025-01-15
I2S-7688-MP-74.PR.TR.12 | Pkg 88 - Locos and Wagons Supply | I.GG.P.R.10W-447 | PROC - Pkg 88 - Locos and Wagons Supply - Pricing by Suppliers / Subcontractors | 2025-01-16 | 2025-02-13
I2S-7688-MP-74.PR.TR.12 | Pkg 88 - Locos and Wagons Supply | I.GG.P.R.10W-457 | PROC - Pkg 88 - Locos and Wagons Supply - Package Review / Approval | 2025-02-14 | 2025-02-27
I2S-7688-MP-74.PR.TR.12 | Pkg 88 - Locos and Wagons Supply | I.GG.P.R.10W-467 | PROC - Pkg 88 - Locos and Wagons Supply - Package Placement | 2025-02-28 | 2025-03-13
I2S-7688-MP-74.PR.TR.12 | Pkg 88 - Locos and Wagons Supply | I.GG.P.R.10W-477 | PROC - Pkg 88 - Locos and Wagons Supply - Manufacturing & Delivery | 2025-03-14 | 2025-05-13
Pkg 90 - Granular Paver |  |  |  | 2025-05-30 | 2025-08-25
I2S-7688-MP-74.PR.TR.14 | Pkg 90 - Granular Paver | I.GG.P.R.10C-730 | PROC - Pkg 90 - Granular Paver - Engage Subcontractor -PO | 2025-05-30 | 2025-07-25
I2S-7688-MP-74.PR.TR.14 | Pkg 90 - Granular Paver | I.GG.P.R.10C-740 | PROC - Pkg 90 - Granular Paver - Subcontractor Mob to Site | 2025-07-28 | 2025-08-25
Pkg 91 - Rail Grinding |  |  |  | 2024-10-25 | 2025-01-31
I2S-7688-MP-74.PR.TR.16 | Pkg 91 - Rail Grinding | I.GG.P.R.10C-770 | PROC - Pkg 91 - Rail Grinding - Engage Subcontractor - PO | 2024-10-25 | 2024-12-19
I2S-7688-MP-74.PR.TR.16 | Pkg 91 - Rail Grinding | I.GG.P.R.10C-780 | PROC - Pkg 91 - Rail Grinding - Subcontractor Mob to Site - PO | 2024-12-20 | 2025-01-31
Pkg 118 - Rail Distribution |  |  |  | 2024-10-25 | 2025-01-31
I2S-7688-MP-74.PR.TR.15 | Pkg 118 - Rail Distribution | I.GG.P.R.10C-750 | PROC - Pkg 118 - Rail Distribution - Engage Subcontractor | 2024-10-25 | 2024-12-19
I2S-7688-MP-74.PR.TR.15 | Pkg 118 - Rail Distribution | I.GG.P.R.10C-760 | PROC - Pkg 118 - Rail Distribution - Subcontractor Mob to Site | 2024-12-20 | 2025-01-31
Signalling |  |  |  | 2024-11-22 | 2026-02-16
Pkg 92 - Signalling Principal Testing |  |  |  | 2025-06-13 | 2025-09-17
I2S-7688-MP-74.PR.SG.16 | Pkg 92 - Signalling Principal Testing | I.GG.P.S.10C-730 | PROC - Sig - Pkg 92 - Signalling Principal Testing - Engage Subcontractor | 2025-06-13 | 2025-08-22
I2S-7688-MP-74.PR.SG.16 | Pkg 92 - Signalling Principal Testing | I.GG.P.S.10C-740 | PROC - Sig - Pkg 92 - Signalling Principal Testing - Subcontractor Mob to Site | 2025-08-25 | 2025-09-17
Pkg 93 - Signal & Comms Cable Supply Only |  |  |  | 2025-03-17 | 2025-11-03
I2S-7688-MP-74.PR.SG.18 | Pkg 93 - Signal & Comms Cable Supply Only | I.GG.P.S.10IG-19 | PROC - Sig - Pkg 93 - Signal & Comms Cable Supply Only - Package Placement | 2025-05-29 | 2025-06-12
I2S-7688-MP-74.PR.SG.18 | Pkg 93 - Signal & Comms Cable Supply Only | I.GG.P.S.10IG-20 | PROC - Sig - Pkg 93 - Signal & Comms Cable Supply Only - Manufacturing & Delivery | 2025-06-13 | 2025-11-03
I2S-7688-MP-74.PR.SG.18 | Pkg 93 - Signal & Comms Cable Supply Only | I.GG.P.S.1000016 | PROC - Sig - Pkg 93 - Signal & Comms Cable Supply Only - Prepare Tender Documents | 2025-03-17 | 2025-04-11
I2S-7688-MP-74.PR.SG.18 | Pkg 93 - Signal & Comms Cable Supply Only | I.GG.P.S.10IG-17 | PROC - Sig - Pkg 93 - Signal & Comms Cable Supply Only - Pricing by Suppliers / Subcontractors | 2025-04-14 | 2025-05-14
I2S-7688-MP-74.PR.SG.18 | Pkg 93 - Signal & Comms Cable Supply Only | I.GG.P.S.10IG-18 | PROC - Sig - Pkg 93 - Signal & Comms Cable Supply Only - Package Review / Approval | 2025-05-15 | 2025-05-28
Pkg 94 - Signalling and Comms Cable Installation |  |  |  | 2025-06-13 | 2025-09-17
I2S-7688-MP-74.PR.SG.19 | Pkg 94 - Signalling and Comms Cable Installation | I.GG.P.S.10C-670 | PROC - Sig - Pkg 94 - Signalling and Comms Cable Installation - Engage Subcontractor - PO | 2025-06-13 | 2025-08-22
I2S-7688-MP-74.PR.SG.19 | Pkg 94 - Signalling and Comms Cable Installation | I.GG.P.S.10C-680 | PROC - Sig - Pkg 94 - Signalling and Comms Cable Installation - Subcontractor Mob to Site - PO | 2025-08-25 | 2025-09-17
Pkg 95 - Location Cases / Racks & Termination Supply |  |  |  | 2025-03-17 | 2025-11-21
I2S-7688-MP-74.PR.SG.20 | Pkg 95 - Location Cases / Racks & Termination Supply | I.GG.P.S.10IG-11 | PROC - Sig - Pkg 95 - Signalling Equipment Rooms & Loc Cases - Prepare Tender Documents | 2025-03-17 | 2025-04-11
I2S-7688-MP-74.PR.SG.20 | Pkg 95 - Location Cases / Racks & Termination Supply | I.GG.P.S.10IG-12 | PROC - Sig - Pkg 95 - Signalling Equipment Rooms & Loc Cases - Pricing by Suppliers / Subcontractors | 2025-04-14 | 2025-05-14
I2S-7688-MP-74.PR.SG.20 | Pkg 95 - Location Cases / Racks & Termination Supply | I.GG.P.S.10IG-13 | PROC - Sig - Pkg 95 - Loc Cases - Package Review / Approval | 2025-05-15 | 2025-05-28
I2S-7688-MP-74.PR.SG.20 | Pkg 95 - Location Cases / Racks & Termination Supply | I.GG.P.S.10IG-14 | PROC - Sig - Pkg 95 - Loc Cases - Package Placement | 2025-05-29 | 2025-06-12
I2S-7688-MP-74.PR.SG.20 | Pkg 95 - Location Cases / Racks & Termination Supply | I.GG.P.S.10IG-15 | PROC - Sig - Pkg 95 - Loc Cases - Manufacturing | 2025-06-13 | 2025-11-03
I2S-7688-MP-74.PR.SG.20 | Pkg 95 - Location Cases / Racks & Termination Supply | I.GG.P.S.10IG-25 | PROC - Sig - Pkg 95 - Loc Cases - Locations and Track boxes delivery | 2025-11-04 | 2025-11-04
I2S-7688-MP-74.PR.SG.20 | Pkg 95 - Location Cases / Racks & Termination Supply | I.GG.P.S.10IG-35 | PROC - Sig - Pkg 95 - Loc Cases - Internal Fitout | 2025-11-05 | 2025-11-10
I2S-7688-MP-74.PR.SG.20 | Pkg 95 - Location Cases / Racks & Termination Supply | I.GG.P.S.10IG-45 | PROC - Sig - Pkg 95 - Loc Cases - Wiring | 2025-11-11 | 2025-11-17
I2S-7688-MP-74.PR.SG.20 | Pkg 95 - Location Cases / Racks & Termination Supply | I.GG.P.S.10IG-55 | PROC - Sig - Pkg 95 - Loc Cases - Termination and Labeling | 2025-11-18 | 2025-11-19
I2S-7688-MP-74.PR.SG.20 | Pkg 95 - Location Cases / Racks & Termination Supply | I.GG.P.S.10IG-65 | PROC - Sig - Pkg 95 - Loc Cases - FAT | 2025-11-20 | 2025-11-20
I2S-7688-MP-74.PR.SG.20 | Pkg 95 - Location Cases / Racks & Termination Supply | I.GG.P.S.10IG-75 | PROC - Sig - Pkg 95 - Loc Cases - Transport to Site - Manufacturing Location boxes - Illabo | 2025-11-21 | 2025-11-21
I2S-7688-MP-74.PR.SG.20 | Pkg 95 - Location Cases / Racks & Termination Supply | I.GG.P.S.10IG-470 | PROC - Sig - Pkg 95 - Loc Cases - Transport to Site - Manufacturing Location boxes - Stockingbingal
I2S-7688-MP-74.PR.SG.20 | Pkg 95 - Location Cases / Racks & Termination Supply | I.GG.P.S.10IG-480 | PROC - Sig - Pkg 95 - Loc Cases - Transport to Site - Manufacturing Location boxes - Greenfield
Pkg 96 - Sandwich Steel Huts - Signalling Equipment Room - SER |  |  |  | 2025-03-17 | 2026-01-12
I2S-7688-MP-74.PR.SG.21 | Pkg 96 - Sandwich Steel Huts - Signalling Equipment Room - SER | I.GG.P.S.10IG-190 | PROC - Sig - Pkg 96 - Sandwich Steel Huts (SER) - Manufacturing & Delivery - Illabo - 1 delivered | 2025-06-13 | 2026-01-12
I2S-7688-MP-74.PR.SG.21 | Pkg 96 - Sandwich Steel Huts - Signalling Equipment Room - SER | I.GG.P.S.10IG-150 | PROC - Sig - Pkg 96 - Sandwich Steel Huts (SER) - Prepare Tender Documents | 2025-03-17 | 2025-04-11
I2S-7688-MP-74.PR.SG.21 | Pkg 96 - Sandwich Steel Huts - Signalling Equipment Room - SER | I.GG.P.S.10IG-160 | PROC - Sig - Pkg 96 - Sandwich Steel Huts (SER) - Pricing by Suppliers / Subcontractors | 2025-04-14 | 2025-05-14
I2S-7688-MP-74.PR.SG.21 | Pkg 96 - Sandwich Steel Huts - Signalling Equipment Room - SER | I.GG.P.S.10IG-170 | PROC - Sig - Pkg 96 - Sandwich Steel Huts (SER) - Package Review / Approval | 2025-05-15 | 2025-05-28
I2S-7688-MP-74.PR.SG.21 | Pkg 96 - Sandwich Steel Huts - Signalling Equipment Room - SER | I.GG.P.S.10IG-180 | PROC - Sig - Pkg 96 - Sandwich Steel Huts (SER) - Package Placement | 2025-05-29 | 2025-06-12
I2S-7688-MP-74.PR.SG.21 | Pkg 96 - Sandwich Steel Huts - Signalling Equipment Room - SER | I.GG.P.S.10IG-450 | PROC - Sig - Pkg 96 - Sandwich Steel Huts (SER) - Manufacturing & Delivery - Stockingbingal - 2/9 delivered
I2S-7688-MP-74.PR.SG.21 | Pkg 96 - Sandwich Steel Huts - Signalling Equipment Room - SER | I.GG.P.S.10IG-460 | PROC - Sig - Pkg 96 - Sandwich Steel Huts (SER) - Manufacturing & Delivery - Dirnasser - 6 no's
Pkg 97 - Signal Post Aspects & Lxing Assemblies |  |  |  | 2025-03-17 | 2025-10-27
I2S-7688-MP-74.PR.SG.22 | Pkg 97 - Signal Post Aspects & Lxing Assemblies | I.GG.P.S.10IG-1 | PROC - Sig - Pkg 97 - Signal Post Aspects & LXing Assembly - Prepare Tender Documents | 2025-03-17 | 2025-04-11
I2S-7688-MP-74.PR.SG.22 | Pkg 97 - Signal Post Aspects & Lxing Assemblies | I.GG.P.S.10IG-2 | PROC - Sig - Pkg 97 - Signal Post Aspects & LXing Assembly - Pricing by Suppliers / Subcontractors | 2025-04-14 | 2025-05-14
I2S-7688-MP-74.PR.SG.22 | Pkg 97 - Signal Post Aspects & Lxing Assemblies | I.GG.P.S.10IG-3 | PROC - Sig - Pkg 97 - Signal Post Aspects & LXing Assembly - Package Review / Approval | 2025-05-15 | 2025-05-28
I2S-7688-MP-74.PR.SG.22 | Pkg 97 - Signal Post Aspects & Lxing Assemblies | I.GG.P.S.10IG-4 | PROC - Sig - Pkg 97 - Signal Post Aspects & LXing Assembly - Package Placement | 2025-05-29 | 2025-06-12
I2S-7688-MP-74.PR.SG.22 | Pkg 97 - Signal Post Aspects & Lxing Assemblies | I.GG.P.S.10IG-5 | PROC - Sig - Pkg 97 - Signal Post Aspects & LXing Assembly - Manufacturing & Delivery | 2025-06-13 | 2025-10-27
Pkg 98 - LX Electrical Equipment (incl batteries) |  |  |  | 2025-03-17 | 2025-06-12
I2S-7688-MP-74.PR.SG.23 | Pkg 98 - LX Electrical Equipment (incl batteries) | I.GG.P.S.10IG-120 | PROC - Sig - Pkg 98 - LX Electrical Equipment (incl batteries) - Package Review / Approval (Stockingbingal) - PO | 2025-05-15 | 2025-05-28
I2S-7688-MP-74.PR.SG.23 | Pkg 98 - LX Electrical Equipment (incl batteries) | I.GG.P.S.10IG-130 | PROC - Sig - Pkg 98 - LX Electrical Equipment (incl batteries) - Package Placement (Dirnaseer) - PO | 2025-05-29 | 2025-06-12
I2S-7688-MP-74.PR.SG.23 | Pkg 98 - LX Electrical Equipment (incl batteries) | I.GG.P.S.10IG-100 | PROC - Sig - Pkg 98 - LX Electrical Equipment (incl batteries) - Prepare Tender Documents | 2025-03-17 | 2025-04-11
I2S-7688-MP-74.PR.SG.23 | Pkg 98 - LX Electrical Equipment (incl batteries) | I.GG.P.S.10IG-110 | PROC - Sig - Pkg 98 - LX Electrical Equipment (incl batteries) - Material Lead Time (Illabo) - PO | 2025-04-14 | 2025-05-14
Pkg 100 - Signalling Generators |  |  |  | 2025-03-17 | 2026-02-16
I2S-7688-MP-74.PR.SG.25 | Pkg 100 - Signalling Generators | I.GG.P.S.10IG-50 | PROC - Sig - Pkg 100 - Signalling Generators - Prepare Tender Documents | 2025-03-17 | 2025-04-11
I2S-7688-MP-74.PR.SG.25 | Pkg 100 - Signalling Generators | I.GG.P.S.10IG-60 | PROC - Sig - Pkg 100 - Signalling Generators - Pricing by Suppliers / Subcontractors | 2025-04-14 | 2025-05-14
I2S-7688-MP-74.PR.SG.25 | Pkg 100 - Signalling Generators | I.GG.P.S.10IG-70 | PROC - Sig - Pkg 100 - Signalling Generators - Package Review / Approval - PO | 2025-05-15 | 2025-05-28
I2S-7688-MP-74.PR.SG.25 | Pkg 100 - Signalling Generators | I.GG.P.S.10IG-80 | PROC - Sig - Pkg 100 - Signalling Generators - Package Placement -PO Order | 2025-05-29 | 2025-06-12
I2S-7688-MP-74.PR.SG.25 | Pkg 100 - Signalling Generators | I.GG.P.S.10IG-90 | PROC - Sig - Pkg 100 - Signalling Generators - Manufacturing & Delivery - (PO) | 2025-06-13 | 2026-02-16
Pkg 101 - Track Circuits - DC and HVI |  |  |  | 2024-11-22 | 2026-02-16
I2S-7688-MP-74.PR.SG.26 | Pkg 101 - Track Circuits - DC and HVI | I.GG.P.S.10IG-140 | PROC - Sig - Pkg 101 - Track Circuits - DC and HVI - Manufacturing & Delivery - LX Electrical Equipment -PO | 2025-06-13 | 2025-11-17
I2S-7688-MP-74.PR.SG.26 | Pkg 101 - Track Circuits - DC and HVI | I.GG.P.S.10IG-350 | PROC - Sig - Pkg 101 - Track Circuits - DC and HVI - Prepare Tender Documents | 2024-11-22 | 2024-12-19
I2S-7688-MP-74.PR.SG.26 | Pkg 101 - Track Circuits - DC and HVI | I.GG.P.S.10IG-360 | PROC - Sig - Pkg 101 - Track Circuits - DC and HVI - Pricing by Suppliers / Subcontractors | 2024-12-20 | 2025-01-31
I2S-7688-MP-74.PR.SG.26 | Pkg 101 - Track Circuits - DC and HVI | I.GG.P.S.10IG-370 | PROC - Sig - Pkg 101 - Track Circuits - DC and HVI - Package Review / Approval | 2025-02-03 | 2025-02-14
I2S-7688-MP-74.PR.SG.26 | Pkg 101 - Track Circuits - DC and HVI | I.GG.P.S.10IG-380 | PROC - Sig - Pkg 101 - Track Circuits - DC and HVI - Package Placement -PO | 2025-03-07 | 2025-03-20
I2S-7688-MP-74.PR.SG.26 | Pkg 101 - Track Circuits - DC and HVI | I.GG.P.S.10IG-390 | PROC - Sig - Pkg 101 - Track Circuits - DC and HVI - Manufacturing & Delivery - DC and HVI -PO | 2025-03-21 | 2026-02-16
Pkg 102 - Axle Counter |  |  |  | 2025-03-17 | 2025-10-03
I2S-7688-MP-74.PR.SG.27 | Pkg 102 - Axle Counter | I.GG.P.S.10IG-250 | PROC - Sig - Pkg 102 - Axle Counter - Prepare Tender Documents | 2025-03-17 | 2025-04-11
I2S-7688-MP-74.PR.SG.27 | Pkg 102 - Axle Counter | I.GG.P.S.10IG-260 | PROC - Sig - Pkg 102 - Axle Counter - Pricing by Suppliers / Subcontractors | 2025-04-14 | 2025-05-14
I2S-7688-MP-74.PR.SG.27 | Pkg 102 - Axle Counter | I.GG.P.S.10IG-270 | PROC - Sig - Pkg 102 - Axle Counter - Package Review / Approval | 2025-05-15 | 2025-05-28
I2S-7688-MP-74.PR.SG.27 | Pkg 102 - Axle Counter | I.GG.P.S.10IG-280 | PROC - Sig - Pkg 102 - Axle Counter - Package Placement | 2025-05-29 | 2025-06-12
I2S-7688-MP-74.PR.SG.27 | Pkg 102 - Axle Counter | I.GG.P.S.10IG-290 | PROC - Sig - Pkg 102 - Axle Counter - Manufacturing & Delivery - Illabo | 2025-06-13 | 2025-10-03
Pkg 104 - Relays |  |  |  | 2024-12-20 | 2026-02-10
I2S-7688-MP-74.PR.SG.29 | Pkg 104 - Relays | I.GG.P.S.10IG-420 | PROC - Sig - Pkg 104 - Relays - Package Review / Approval | 2025-03-03 | 2025-03-14
I2S-7688-MP-74.PR.SG.29 | Pkg 104 - Relays | I.GG.P.S.10IG-430 | PROC - Sig - Pkg 104 - Relays - Package Placement | 2025-03-17 | 2025-03-28
I2S-7688-MP-74.PR.SG.29 | Pkg 104 - Relays | I.GG.P.S.10IG-440 | PROC - Sig - Pkg 104 - Relays - Manufacturing & Delivery | 2025-03-31 | 2026-02-10
I2S-7688-MP-74.PR.SG.29 | Pkg 104 - Relays | I.GG.P.S.10IG-400 | PROC - Sig - Pkg 104 - Relays - Prepare Tender Documents | 2024-12-20 | 2025-01-31
I2S-7688-MP-74.PR.SG.29 | Pkg 104 - Relays | I.GG.P.S.10IG-410 | PROC - Sig - Pkg 104 - Relays - Pricing by Suppliers / Subcontractors | 2025-02-03 | 2025-02-28
Pkg 106 - Signalling Transformers |  |  |  | 2025-03-17 | 2025-10-03
I2S-7688-MP-74.PR.SG.31 | Pkg 106 - Signalling Transformers | I.GG.P.S.10IG-300 | PROC - Sig - Pkg 106 - Signalling Transformers - Prepare Tender Documents | 2025-03-17 | 2025-04-11
I2S-7688-MP-74.PR.SG.31 | Pkg 106 - Signalling Transformers | I.GG.P.S.10IG-310 | PROC - Sig - Pkg 106 - Signalling Transformers - Pricing by Suppliers / Subcontractors | 2025-04-14 | 2025-05-14
I2S-7688-MP-74.PR.SG.31 | Pkg 106 - Signalling Transformers | I.GG.P.S.10IG-320 | PROC - Sig - Pkg 106 - Signalling Transformers - Package Review / Approval | 2025-05-15 | 2025-05-28
I2S-7688-MP-74.PR.SG.31 | Pkg 106 - Signalling Transformers | I.GG.P.S.10IG-330 | PROC - Sig - Pkg 106 - Signalling Transformers - Package Placement - PO | 2025-05-29 | 2025-06-12
I2S-7688-MP-74.PR.SG.31 | Pkg 106 - Signalling Transformers | I.GG.P.S.10IG-340 | PROC - Sig - Pkg 106 - Signalling Transformers - Manufacturing & Delivery - Illabo | 2025-06-13 | 2025-10-03
Pkg 111 - Interlocking - Hardware |  |  |  | 2024-12-20 | 2026-02-16
I2S-7688-MP-74.PR.SG.28 | Pkg 111 - Interlocking - Hardware | I.GG.P.S.10IG-26 | PROC - Sig - Pkg 111 - Interlocking - Hardware - Prepare Tender Documents | 2024-12-20 | 2025-01-23
I2S-7688-MP-74.PR.SG.28 | Pkg 111 - Interlocking - Hardware | I.GG.P.S.10IG-27 | PROC - Sig - Pkg 111 - Interlocking - Hardware - Pricing by Suppliers / Subcontractors | 2025-01-24 | 2025-02-14
I2S-7688-MP-74.PR.SG.28 | Pkg 111 - Interlocking - Hardware | I.GG.P.S.10IG-28 | PROC - Sig - Pkg 111 - Interlocking - Hardware - Package Review / Approval | 2025-02-17 | 2025-02-28
I2S-7688-MP-74.PR.SG.28 | Pkg 111 - Interlocking - Hardware | I.GG.P.S.10IG-29 | PROC - Sig - Pkg 111 - Interlocking - Hardware - Package Placement | 2025-03-10 | 2025-03-14
I2S-7688-MP-74.PR.SG.28 | Pkg 111 - Interlocking - Hardware | I.GG.P.S.10IG-30 | PROC - Sig - Pkg 111 - Interlocking - Hardware - Manufacturing & Progressive Delivery (Started) | 2025-03-17 | 2026-02-16
Combined Service Route |  |  |  | 2025-02-14 | 2025-08-21
Pkg 108 - Precast Pits: Signalling & Communciation |  |  |  | 2025-02-14 | 2025-08-07
I2S-7688-MP-74.PR.CSR.34 | Pkg 108 - Precast Pits: Signalling & Communciation | I.GG.P.S.10SR-22 | PROC - Pkg 108 - CSR - Precast Pits - Prepare Tender Documents | 2025-02-14 | 2025-03-13
I2S-7688-MP-74.PR.CSR.34 | Pkg 108 - Precast Pits: Signalling & Communciation | I.GG.P.S.10SR-32 | PROC - Pkg 108 - CSR - Precast Pits - Pricing by Suppliers / Subcontractors - Precast Pits | 2025-03-14 | 2025-04-10
I2S-7688-MP-74.PR.CSR.34 | Pkg 108 - Precast Pits: Signalling & Communciation | I.GG.P.S.10SR-42 | PROC - Pkg 108 - CSR - Precast Pits - Package Review / Approval - Precast Pits | 2025-04-11 | 2025-04-17
I2S-7688-MP-74.PR.CSR.34 | Pkg 108 - Precast Pits: Signalling & Communciation | I.GG.P.S.10SR-52 | PROC - Pkg 108 - CSR - Precast Pits - Package Placement - Precast Pits | 2025-04-22 | 2025-04-29
I2S-7688-MP-74.PR.CSR.34 | Pkg 108 - Precast Pits: Signalling & Communciation | I.GG.P.S.10SR-62 | PROC - Pkg 108 - CSR - Precast Pits - Manufacturing & Delivery - Precast Pits | 2025-04-30 | 2025-08-07
Pkg 110 - Conduit Supply |  |  |  | 2025-02-14 | 2025-08-21
I2S-7688-MP-74.PR.CSR.37 | Pkg 110 - Conduit Supply | I.GG.P.S.1000007 | PROC - Pkg 110 - CSR - Conduit Supply - Prepare Tender Documents | 2025-02-14 | 2025-03-13
I2S-7688-MP-74.PR.CSR.37 | Pkg 110 - Conduit Supply | I.GG.P.S.10SR-8 | PROC - Pkg 110 - CSR - Conduit Supply - Pricing by Suppliers / Subcontractors | 2025-03-14 | 2025-04-10
I2S-7688-MP-74.PR.CSR.37 | Pkg 110 - Conduit Supply | I.GG.P.S.10SR-9 | PROC - Pkg 110 - CSR - Conduit Supply - Package Review / Approval | 2025-04-11 | 2025-04-29
I2S-7688-MP-74.PR.CSR.37 | Pkg 110 - Conduit Supply | I.GG.P.S.10SR-10 | PROC - Pkg 110 - CSR - Conduit Supply - Package Placement | 2025-04-30 | 2025-05-13
I2S-7688-MP-74.PR.CSR.37 | Pkg 110 - Conduit Supply | I.GG.P.S.10SR-11 | PROC - Pkg 110 - CSR - Conduit Supply - Manufacturing &Progressive Delivery - PO | 2025-05-14 | 2025-08-21
Utilities
Pkg 42 General Electrical Work (Essential Energy (EE))
I2S-7688-MP-74.PR.1.1 | Pkg 42 General Electrical Work (Essential Energy (EE)) | I.GG.P.G.101161 | PROC - Utilities - Pkg 42 - General Electrical Work (Essential Energy) - Engage Subcontractor
I2S-7688-MP-74.PR.1.1 | Pkg 42 General Electrical Work (Essential Energy (EE)) | I.GG.P.G.101300 | PROC - Utilities - Pkg 42 - General Electrical Work (Essential Energy) - Mob to Site
I2S-7688-MP-74.PR.1.1 | Pkg 42 General Electrical Work (Essential Energy (EE)) | I.GG.P.G.101171 | PROC - Utilities - Pkg 42 - General Electrical Work (Essential Energy) - Contract Award
Pkg 43 Water Relocation (Goldfield Water)
I2S-7688-MP-74.PR.1.2 | Pkg 43 Water Relocation (Goldfield Water) | I.GG.P.G.101310 | PROC - Utilities - Pkg 43 - Water Relocation (Goldfield Water) - Engage Subcontractor
I2S-7688-MP-74.PR.1.2 | Pkg 43 Water Relocation (Goldfield Water) | I.GG.P.G.101320 | PROC - Utilities - Pkg 43 - Water Relocation (Goldfield Water) - Mob to Site
Construction |  |  |  | 2024-11-27 | 2027-04-03
Key Milestone |  |  |  | 2025-07-11 | 2025-07-11
I2S-7688-MP-74.CN.2 | Key Milestone | I.GG.CEMP.14790 | CON - Works Can Commence - Enabling site Works (Post EPL and Site Establishment Management Plans_ | 2025-07-11
I2S-7688-MP-74.CN.2 | Key Milestone | I.GG.CEMP.14800 | CON - Works can Commence - Select Sections - Stage 2 | 2025-07-11
I2S-7688-MP-74.CN.2 | Key Milestone | I.GG.CEMP.17410 | CON - Works can Commence - Compliant FDVR zones - Stage 1
Site Investigations, Survey and Monitoring - Stage 1 |  |  |  | 2024-11-27 | 2027-03-16
Site Investigations |  |  |  | 2024-11-27 | 2025-03-31
I2S-7688-MP-74.CN.EW.1 | Site Investigations | I.CN.11.5370 | CON - Inital Site Investigations / Early works-superseded with ECW | 2024-11-27 | 2025-01-09
I2S-7688-MP-74.CN.EW.1 | Site Investigations | I.CN.11.14330 | CON - Inital Site Surveys / Investigations (potentially in possession Mar 25 with ECW) | 2025-03-29 | 2025-03-31
Survey |  |  |  | 2025-07-14 | 2027-03-16
I2S-7688-MP-74.CN.EW.2 | Survey | I.CN.11.6460 | CON - Site Surveys post CEMP /EPL /Walk over | 2025-07-14 | 2025-08-04
I2S-7688-MP-74.CN.EW.2 | Survey | I.CN.11.12980 | CON - Site Surveys ( in possession) post CEMP | 2025-09-13 | 2025-09-15
I2S-7688-MP-74.CN.EW.2 | Survey | I.CN.11.14380 | CON - Site Surveys post Construction works | 2027-02-28 | 2027-03-16
Site Establishment and Works Housing and Accommodation - Stage 1 |  |  |  | 2025-05-28 | 2027-03-15
Compounds and Laydowns |  |  |  | 2025-07-04 | 2025-08-19
Compounds /Offices |  |  |  | 2025-07-04 | 2025-08-13
Cootamundra |  |  |  | 2025-07-04 | 2025-08-13
I2S-7688-MP-74.CN.SE.3.1.1 | Cootamundra | I.CN.11.14400 | CON - Potable drinking water for the camp facility and site compounds | 2025-07-04 | 2025-07-26
I2S-7688-MP-74.CN.SE.3.1.1 | Cootamundra | I.CN.11.5380 | CON - Set up Site office facilities at Cootamundra (central location) adjacent to Dirnaseer Road | 2025-07-06 | 2025-08-13
satelite |  |  |  | 2025-07-11 | 2025-08-09
I2S-7688-MP-74.CN.SE.3.1.2 | satelite | I.CN.11.14280 | CON - Set up Smaller satellite compounds, cribs and toilet facilities (CH14700 - for Sec.3 | 2025-07-12 | 2025-08-09
I2S-7688-MP-74.CN.SE.3.1.2 | satelite | I.CN.11.14290 | CON - Set up Smaller satellite compounds, cribs and toilets (CH28100 - for Sec.4 & 5 | 2025-07-12 | 2025-08-09
I2S-7688-MP-74.CN.SE.3.1.2 | satelite | I.CN.11.14300 | CON - Set up Smaller satellite compounds, cribs and toilet facilities (CH37300 - for Sec.6 | 2025-07-11 | 2025-08-08
I2S-7688-MP-74.CN.SE.3.1.2 | satelite | I.CN.11.14270 | CON - Set up Smaller satellite compounds, cribs and toilet facilities (CH8600 - for Sec.1 & 2 | 2025-07-11 | 2025-08-08
Laydowns |  |  |  | 2025-07-11 | 2025-08-19
South |  |  |  | 2025-07-11 | 2025-07-21
I2S-7688-MP-74.CN.SE.3.2.1 | South | I.CN.11.14410 | CON - Set up Laydown Area - CH18300 (Dirnaseer Road) | 2025-07-17 | 2025-07-21
I2S-7688-MP-74.CN.SE.3.2.1 | South | I.CN.11.14430 | CON - Set up Laydown Area - CH8600 (Ironbong Road) | 2025-07-11 | 2025-07-16
North |  |  |  | 2025-07-22 | 2025-08-02
I2S-7688-MP-74.CN.SE.3.2.2 | North | I.CN.11.14420 | CON - Set up Laydown Area - CH37300 (BGW / GrainCorp) | 2025-07-28 | 2025-08-02
I2S-7688-MP-74.CN.SE.3.2.2 | North | I.CN.11.14440 | CON - Set up Laydown Area- CH28100 (Old Cootamundra Road) | 2025-07-22 | 2025-07-27
along alignment |  |  |  | 2025-08-03 | 2025-08-19
I2S-7688-MP-74.CN.SE.3.2.3 | along alignment | I.CN.11.14450 | CON - Construct 27 temporary hardstands (dense graded base) along the alignment | 2025-08-03 | 2025-08-19
Camps |  |  |  | 2025-05-28 | 2027-03-15
Grogan road camp |  |  |  | 2025-05-28 | 2027-03-15
I2S-7688-MP-74.CN.SE.2.1 | Grogan road camp | I.CN.11.6470 | CON - Enabling works-Set up CAMP Facility- at Grogan Road in Stockinbingal, 350 pers- 14 weeks to construct (1m after C | 2025-05-28 | 2025-08-13
I2S-7688-MP-74.CN.SE.2.1 | Grogan road camp | I.GG.14690 | CON - Construction period (Main Office /Camp Facility in operation) - LOE | 2025-08-14 | 2027-03-15
Construction Support and Staff |  |  |  | 2025-07-14 | 2027-03-15
PO |  |  |  | 2025-09-13 | 2027-03-15
I2S-7688-MP-74.CN.1.1 | PO | I.CN.50.18310 | CON - Possessions - September 2025 - For Labour only | 2025-09-13 | 2025-09-15
I2S-7688-MP-74.CN.1.1 | PO | I.CN.50.18320 | CON - Possessions - March 2026 - For Labour only | 2026-03-14 | 2026-03-16
I2S-7688-MP-74.CN.1.1 | PO | I.CN.50.18330 | CON - Possessions - September 2026 - For Labour only | 2026-09-12 | 2026-09-14
I2S-7688-MP-74.CN.1.1 | PO | I.CN.50.18340 | CON - Possessions - March 2027 - For Labour only | 2027-03-13 | 2027-03-15
Staff/Supervision |  |  |  | 2025-07-14 | 2027-03-14
I2S-7688-MP-74.CN.1.2 | Staff/Supervision | I.CN.50.18350 | CON - Staff - Early Works - pre camp - LOE | 2025-07-14 | 2025-08-13
I2S-7688-MP-74.CN.1.2 | Staff/Supervision | I.CN.50.18400 | CON - Staff - North - LOE | 2025-08-09 | 2026-12-09
I2S-7688-MP-74.CN.1.2 | Staff/Supervision | I.CN.50.18410 | CON - Staff - Central (with Track) - LOE | 2025-08-14 | 2027-03-14
I2S-7688-MP-74.CN.1.2 | Staff/Supervision | I.CN.50.18420 | CON - Staff - South - LOE | 2025-08-09 | 2026-04-12
Section 6 - Stockinbingal Junction (37301- 42600) |  |  |  | 2025-07-12 | 2027-04-03
Section 6 Key Milestones prior to Final Commissioning
I2S-7688-MP-74.CN.S6.4 | Section 6 Key Milestones prior to Final Commissioning | I.CN.22.13530 | CON - Sec.6 - Construction Completion Milestone (Crossings)
I2S-7688-MP-74.CN.S6.4 | Section 6 Key Milestones prior to Final Commissioning | I.CN.22.13540 | CON - Sec.6 - Construction Completion Milestone (Signalling)
I2S-7688-MP-74.CN.S6.4 | Section 6 Key Milestones prior to Final Commissioning | I.CN.22.13550 | CON - Sec.6 - Construction Completion Milestone (Rail Communications)
I2S-7688-MP-74.CN.S6.4 | Section 6 Key Milestones prior to Final Commissioning | I.CN.22.13560 | CON - Sec.6 - Construction Completion Milestone (Power Supply and Distributions)
I2S-7688-MP-74.CN.S6.4 | Section 6 Key Milestones prior to Final Commissioning | I.CN.22.13570 | CON - Sec.6 - Construction Completion Milestone (Landscaping)
I2S-7688-MP-74.CN.S6.4 | Section 6 Key Milestones prior to Final Commissioning | I.CN.22.13440 | CON - Sec.6 - Construction Completion Milestone (Public Utilities)
I2S-7688-MP-74.CN.S6.4 | Section 6 Key Milestones prior to Final Commissioning | I.CN.22.13450 | CON - Sec.6 - Construction Completion Milestone (Earthworks)
I2S-7688-MP-74.CN.S6.4 | Section 6 Key Milestones prior to Final Commissioning | I.CN.22.13460 | CON - Sec.6 - Construction Completion Milestone (Capping)
I2S-7688-MP-74.CN.S6.4 | Section 6 Key Milestones prior to Final Commissioning | I.CN.22.13470 | CON - Sec.6 - Construction Completion Milestone (Drainage)
I2S-7688-MP-74.CN.S6.4 | Section 6 Key Milestones prior to Final Commissioning | I.CN.22.14460 | CON - Sec.6 - Construction Completion Milestone (Culverts)
I2S-7688-MP-74.CN.S6.4 | Section 6 Key Milestones prior to Final Commissioning | I.CN.22.13480 | CON - Sec.6 - Construction Completion Milestone (Fencing)
I2S-7688-MP-74.CN.S6.4 | Section 6 Key Milestones prior to Final Commissioning | I.CN.22.13490 | CON - Sec.6 - Construction Completion Milestone (Roadworks)
I2S-7688-MP-74.CN.S6.4 | Section 6 Key Milestones prior to Final Commissioning | I.CN.22.13500 | CON - Sec.6 - Construction Completion Milestone (Access Roads)
I2S-7688-MP-74.CN.S6.4 | Section 6 Key Milestones prior to Final Commissioning | I.CN.22.13510 | CON - Sec.6 - Construction Completion Milestone before Final Commissioning (Trackwork)
I2S-7688-MP-74.CN.S6.4 | Section 6 Key Milestones prior to Final Commissioning | I.CN.22.13520 | CON - Sec.6 - Construction Completion Milestone (Bridges)
I2S-7688-MP-74.CN.S6.4 | Section 6 Key Milestones prior to Final Commissioning | I.CN.22.14740 | CON - Sec.6 - Commence Construction Milestone - CEMP approved
I2S-7688-MP-74.CN.S6.4 | Section 6 Key Milestones prior to Final Commissioning | I.CN.22.14730 | CON - Sec.6 - Commence Construction Milestone - FDVR & CEMP approved - 1st A9 submission - approval
I2S-7688-MP-74.CN.S6.4 | Section 6 Key Milestones prior to Final Commissioning | I.CN.50.20710 | CON - Sec.6 - BGW Temp - Road Diversion + Traffic Switch - operational - Milestone
I2S-7688-MP-74.CN.S6.4 | Section 6 Key Milestones prior to Final Commissioning | I.CN.62.22990 | CON - Sec.6 - NEW Burley Griffin Way Bridge Completion - Permanent Traffic Switch - operational - Milestone
I2S-7688-MP-74.CN.S6.4 | Section 6 Key Milestones prior to Final Commissioning | I.CN.74.15980 | CON - Sec.6 - New LX Crossing Commissioned - Possession - BGW road - operational - permanent - Milestone
000 - Site Access |  |  |  | 2025-07-12 | 2025-07-12
BGW |  |  |  | 2025-07-12 | 2025-07-12
I2S-7688-MP-74.CN.S6.00.1 | BGW | I.CN.11.13980 | CON - Sec.6 - Site Gate Access Required by/ Granted - Gate 9 (BGW - West) - TfNSW | 2025-07-12 | 2025-07-12
I2S-7688-MP-74.CN.S6.00.1 | BGW | I.CN.11.13990 | CON - Sec.6 - Site Gate Access Required by/ Granted - Gate 10 (BGW - East) - TfNSW | 2025-07-12 | 2025-07-12
I2S-7688-MP-74.CN.S6.00.1 | BGW | I.CN.11.15820 | CON - Sec.6 - Site Gate Access Required by/ Granted - Gate 8 (BGW - Centre) - TfNSW
I2S |  |  |  | 2025-07-12 | 2025-07-12
I2S-7688-MP-74.CN.S6.00.3 | I2S | I.CN.11.13970 | CON - Sec.6 - Site Gate Access Required by/ Granted - Gate 8A + 8B (37300) - I2S - TfNSW | 2025-07-12 | 2025-07-12
I2S-7688-MP-74.CN.S6.00.3 | I2S | I.CN.11.14000 | CON - Sec.6 - Site Gate Access Required by/ Granted - Gate 11 (40700) - I2S | 2025-07-12 | 2025-07-12
022 - Public Utilities |  |  |  | 2025-07-21 | 2025-08-12
Telstra |  |  |  | 2025-07-21 | 2025-07-24
I2S-7688-MP-74.CN.S6.22.2 | Telstra | I.CN.11.13220 | CON - Util - Sec.6 - TE02-12 Telstra - Reloc - Burley Griffin Way (South) at new rail alignment - Ch37260 (102m) | 2025-07-21 | 2025-07-24
I2S-7688-MP-74.CN.S6.22.2 | Telstra | I.CN.11.13230 | CON - Util - Sec.6 - TE02-13 Telstra - Reloc - BGW leading to residential property (road X) - Ch37292 (255m) | 2025-07-21 | 2025-07-22
I2S-7688-MP-74.CN.S6.22.2 | Telstra | I.CN.11.13240 | CON - Util - Sec.6 - TE02-14 Telstra - Reloc - West St adjacent to Hibernia St, road crossing - Ch37552 (32m) | 2025-07-21 | 2025-07-22
NBN |  |  |  | 2025-07-21 | 2025-07-22
I2S-7688-MP-74.CN.S6.22.3 | NBN | I.CN.22.14860 | CON - Util - Sec.6 - NBN-01 - Commence Work on site
I2S-7688-MP-74.CN.S6.22.3 | NBN | I.CN.22.14870 | CON - Util - Sec.6 - NBN-01 - NBN - Temporary Relocation - Stockinbingal Hill West Side Exist Rail - Ch38192
I2S-7688-MP-74.CN.S6.22.3 | NBN | I.CN.22.14880 | CON - Util - Sec.6 - NBN-01 - NBN - Temporary Relocation - Cutover & Outage
I2S-7688-MP-74.CN.S6.22.3 | NBN | I.CN.22.14890 | CON - Util - Sec.6 - NBN-01 - ECN-113426 Works Complete
I2S-7688-MP-74.CN.S6.22.3 | NBN | I.CN.22.5710 | CON - Util - Sec.6 - NBN-01 - Relocate Stockinbingal Hill West Side Exist Rail - Ch38192 (134m) | 2025-07-21 | 2025-07-22
Essential Energy (EE) |  |  |  | 2025-07-31 | 2025-08-12
ECN-099004 ELO-14
I2S-7688-MP-74.CN.S6.22.4.1 | ECN-099004 ELO-14 | I.CN.22.14310 | CON - Util - Sec.6 - ELO-14 - Essential Energy - Relocate 11kV Across Grogan Road - Ch41292 (42m)
I2S-7688-MP-74.CN.S6.22.4.1 | ECN-099004 ELO-14 | I.CN.22.14670 | CON - Util - Sec.6 - ELO-14 - Commence Work on site
I2S-7688-MP-74.CN.S6.22.4.1 | ECN-099004 ELO-14 | I.CN.22.14680 | CON - Util - Sec.6 - ELO-14 - Outage & Cutover
I2S-7688-MP-74.CN.S6.22.4.1 | ECN-099004 ELO-14 | I.CN.22.14690 | CON - Util - Sec.6 - ELO-14 - ECN-099004 Works Complete
ECN-119227 ELO-12
I2S-7688-MP-74.CN.S6.22.4.2 | ECN-119227 ELO-12 | I.CN.22.14290 | CON - Util - Sec.6 - ELO-12 - Essential Energy - Relocate 11kV BGW near Hibernia & Troy St - Ch37532
I2S-7688-MP-74.CN.S6.22.4.2 | ECN-119227 ELO-12 | I.CN.22.14700 | CON - Util - Sec.6 - ELO-12 - Commence Work on site
I2S-7688-MP-74.CN.S6.22.4.2 | ECN-119227 ELO-12 | I.CN.22.14710 | CON - Util - Sec.6 - ELO-12 - Outage & Cutover
I2S-7688-MP-74.CN.S6.22.4.2 | ECN-119227 ELO-12 | I.CN.22.14720 | CON - Util - Sec.6 - ELO-12 - ECN-119227 Works Complete
ECN-111186 ELO-06/05/07/11 & PS-05 |  |  |  | 2025-07-31 | 2025-08-12
I2S-7688-MP-74.CN.S6.22.4.3 | ECN-111186 ELO-06/05/07/11 & PS-05 | I.CN.22.5670 | CON - Util - Sec.6 - ELO-O5/06/07/11 - Essential Energy - Relocate 11kV West & North Side BGW - Ch37312 / 37342 / 3 | 2025-07-31 | 2025-08-12
I2S-7688-MP-74.CN.S6.22.4.3 | ECN-111186 ELO-06/05/07/11 & PS-05 | I.CN.22.14300 | CON - Util - Sec.6 - PS-05 - Essential Energy - New Signal Equipment Room Power Supply - Ch37642
APA |  |  |  | 2025-07-24 | 2025-07-30
I2S-7688-MP-74.CN.S6.22.5 | APA | I.CN.22.5680 | CON - Util - Sec.6 - NG02-01 - APA - Relocate HP Gas South Side BGW - Ch37254 (91m) | 2025-07-24 | 2025-07-30
Goldenfield Water |  |  |  | 2025-07-22 | 2025-07-28
WA01-02 - Burley Griffin Way |  |  |  | 2025-07-22 | 2025-07-23
I2S-7688-MP-74.CN.S6.22.7.1 | WA01-02 - Burley Griffin Way | I.CN.22.5700 | CON - Util - Sec.6 - WA01-02 Goldenfields Water - Relocate Potable Water South Side BGW - Ch37272 (69m) | 2025-07-22 | 2025-07-23
I2S-7688-MP-74.CN.S6.22.7.1 | WA01-02 - Burley Griffin Way | I.CN.22.14900 | CON - Util - Sec.6 - WA01-02 Goldenfields Water - Commence Work on site
I2S-7688-MP-74.CN.S6.22.7.1 | WA01-02 - Burley Griffin Way | I.CN.22.14920 | CON - Util - Sec.6 - WA01-02 Goldenfields Water - Outage & cutover
I2S-7688-MP-74.CN.S6.22.7.1 | WA01-02 - Burley Griffin Way | I.CN.22.14930 | CON - Util - Sec.6 - WA01-02 Goldenfields Water - Complete Works
WA01-03 - Stockinbingal Hill |  |  |  | 2025-07-24 | 2025-07-28
I2S-7688-MP-74.CN.S6.22.7.2 | WA01-03 - Stockinbingal Hill | I.CN.22.11910 | CON - Util - Sec.6 - WA01-03 Goldenfields Water - Relocate Potable Water Stockinbingal Hill - Ch38022 (318m) | 2025-07-24 | 2025-07-28
I2S-7688-MP-74.CN.S6.22.7.2 | WA01-03 - Stockinbingal Hill | I.CN.22.14940 | CON - Util - Sec.6 - WA01-03 Goldenfields Water - Commence Work on site
I2S-7688-MP-74.CN.S6.22.7.2 | WA01-03 - Stockinbingal Hill | I.CN.22.14950 | CON - Util - Sec.6 - WA01-03 Goldenfields Water - Outage & cutover
I2S-7688-MP-74.CN.S6.22.7.2 | WA01-03 - Stockinbingal Hill | I.CN.22.14960 | CON - Util - Sec.6 - WA01-03 Goldenfields Water - Complete Works
031 - Earthworks
Clearing & Grubbing - Stage 2
Tree Felling and Lopping
I2S-7688-MP-74.CN.S6.31.3.1 | Tree Felling and Lopping | I.CN.11.15760 | CON - Sec.6 - Tree Felling & Lopping
I2S-7688-MP-74.CN.S6.31.3.1 | Tree Felling and Lopping | I.CN.11.15830 | CON - Sec.6 - Tree Felling & Lopping - Possession Works / West St / Gas Relocation
Broad Acre Clearing and Mulching
I2S-7688-MP-74.CN.S6.31.3.2 | Broad Acre Clearing and Mulching | I.CN.11.15770 | CON - Sec.6 - Broad Acre Clearing & Mulching
Grubbing of Stumps
I2S-7688-MP-74.CN.S6.31.3.3 | Grubbing of Stumps | I.CN.11.15780 | CON - Sec.6 - Grubbing of Stumps
Miscellaneous Works
I2S-7688-MP-74.CN.S6.31.3.4 | Miscellaneous Works | I.CN.11.15790 | CON - Sec.6 - Hollow/Habitat Tree Mgmt
I2S-7688-MP-74.CN.S6.31.3.4 | Miscellaneous Works | I.CN.11.15800 | CON - Sec.6 - Habitat Relocations
Cut
Cut Open Drains
I2S-7688-MP-74.CN.S6.31.1.3 | Cut Open Drains | I.CN.31.84070 | CON - Sec.6 - CUT 40 - Cut.OD Soil : Ch38060 to 39472 (3603 bcm - 175 per/d)
I2S-7688-MP-74.CN.S6.31.1.3 | Cut Open Drains | I.CN.31.86870 | CON - Sec.6 - FILL 43 - Cut.OD Soil : Ch37287 to 38060 (1101 bcm - 175 per/d)
Cut Soil to EW
I2S-7688-MP-74.CN.S6.31.1.4 | Cut Soil to EW | I.CN.31.84020 | CON - Sec.6 - CUT 40 - Cut.Soil to EW : Ch38060 to 39472 (89017 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S6.31.1.4 | Cut Soil to EW | I.CN.31.86840 | CON - Sec.6 - FILL 43 - Cut.Soil to EW : Ch37287 to 38060 (131053 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S6.31.1.4 | Cut Soil to EW | I.CN.31.88300 | CON - Sec.6 - FILL 43 - Cut.Soil to EW : Ch37287 to 38060 (131053 bcm - 2500 per/d) - Milestone
Cut Rock
I2S-7688-MP-74.CN.S6.31.1.1 | Cut Rock | I.CN.31.84050 | CON - Sec.6 - CUT 40 - Cut.MW Meta SS : Ch38060 to 39472 (25714 bcm - 2000 per /d)
I2S-7688-MP-74.CN.S6.31.1.1 | Cut Rock | I.CN.31.84060 | CON - Sec.6 - CUT 40 - Cut.HW Meta SS : Ch38060 to 39472 (59994 bcm - 2000 per/d)
I2S-7688-MP-74.CN.S6.31.1.1 | Cut Rock | I.CN.31.86860 | CON - Sec.6 - FILL 43 - Cut.HW Dacite : Ch37287 to 38060 (275 bcm - 2000 per/d)
Fill
Fill Open Drains
I2S-7688-MP-74.CN.S6.31.2.4 | Fill Open Drains | I.CN.31.88210 | CON - Sec.6 - CUT 40 - Fill.OD Fill : Ch38060 to 39472 (1800 bcm - 500 per/d)
Fill Lower
I2S-7688-MP-74.CN.S6.31.2.1 | Fill Lower | I.CN.31.88200 | CON - Sec.6 - CUT 40 - Fill.H2 - Mid : Ch38060 to 39472 (47bcm - 2500 per/d)
I2S-7688-MP-74.CN.S6.31.2.1 | Fill Lower | I.CN.31.88250 | CON - Sec.6 - FILL 43 - Fill.H3 - Lower : Ch Ch37287 to 38060 (4220 bcm - 2500 per/d)
Fill Mid
I2S-7688-MP-74.CN.S6.31.2.2 | Fill Mid | I.CN.31.88230 | CON - Sec.6 - FILL 43 - Fill.H2 - Mid : Ch37287 to 38060 (2478 bcm - 2500 per/d)
Fill Upper
I2S-7688-MP-74.CN.S6.31.2.3 | Fill Upper | I.CN.31.88220 | CON - Sec.6 - CUT 40 - Fill.H1 - Upper I/B : Ch38060 to 39472 (4050 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S6.31.2.3 | Fill Upper | I.CN.31.88240 | CON - Sec.6 - FILL 43 - Fill.H1 - Upper I/B : Ch37287 to 38060 (23205 bcm - 2500 per/d)
033 - Capping |  |  |  | 2025-10-26 | 2026-11-12
Support to u/s Ballast |  |  |  | 2025-10-26 | 2026-11-12
Structural Fill |  |  |  | 2025-10-26 | 2025-10-27
I2S-7688-MP-74.CN.S6.33.3.1 | Structural Fill | I.CN.33.12900 | CON - Sec.6 - Fill Struc fill (21254 TON) 2200 TON/d | 2025-10-26 | 2025-10-27
Capping (Rail) |  |  |  | 2025-10-28 | 2025-10-28
I2S-7688-MP-74.CN.S6.33.3.2 | Capping (Rail) | I.CN.33.12870 | CON - Sec.6 - Capping (11,801 TON) 985 TON/d | 2025-10-28 | 2025-10-28
Capping (RMAR) |  |  |  | 2026-11-12 | 2026-11-12
I2S-7688-MP-74.CN.S6.33.3.21 | Capping (RMAR) | I.CN.45.11600 | CON - Sec.6 - (15,240 TON) - Strip/Grade RMAR with type D Material | 2026-11-12 | 2026-11-12
034 - Drainage |  |  |  | 2025-10-06 | 2026-09-13
I2S-7688-MP-74.CN.S6.34 | 034 - Drainage | I.CN.34.28020 | CON - Sec.6 - Place Enveloper Pipe - DN300 RCP 1.5m past crdr boundary (49m) - (ch. 372 | 2025-10-06 | 2025-10-08
Mainline |  |  |  | 2026-09-08 | 2026-09-13
I2S-7688-MP-74.CN.S6.34.5 | Mainline | I.CN.34.25470 | CON - Sec.6 - Cess Drainage - 37450 - 38144 - Concrete Lining | 2026-09-08 | 2026-09-13
I2S-7688-MP-74.CN.S6.34.5 | Mainline | I.CN.34.25480 | CON - Sec.6 - Cess Drainage - 38624 - 39123 - Rock Lined | 2026-09-08 | 2026-09-10
I2S-7688-MP-74.CN.S6.34.5 | Mainline | I.CN.34.25570 | CON - Sec.6 - Cess Drainage - 39163 to 39545 - Grass lined | 2026-09-11 | 2026-09-13
CRN |  |  |  | 2026-04-07 | 2026-04-26
I2S-7688-MP-74.CN.S6.34.6 | CRN | I.CN.34.25510 | CON - Sec.6 - CRN - Cess Drainage - East | 2026-04-07 | 2026-04-13
I2S-7688-MP-74.CN.S6.34.6 | CRN | I.CN.34.25520 | CON - Sec.6 - CRN - Cess Drainage - West | 2026-04-19 | 2026-04-26
Culverts |  |  |  | 2025-12-23 | 2026-02-20
Culvert ID : E7-RA-454880-1 / Type : 7*900mm HDPE / Ch37432 (28.24m each) |  |  |  | 2025-12-23 | 2026-01-18
I2S-7688-MP-74.CN.S6.34.8.1 | Culvert ID : E7-RA-454880-1 / Type : 7*900mm HDPE / Ch37432 (28.24m each) | I.CN.34.19590 | CON - Sec.6 - Culvert : E7-RA-454880-1 - Site Prep / Detail Excavation | 2025-12-23 | 2026-01-05
I2S-7688-MP-74.CN.S6.34.8.1 | Culvert ID : E7-RA-454880-1 / Type : 7*900mm HDPE / Ch37432 (28.24m each) | I.CN.34.19600 | CON - Sec.6 - Culvert : E7-RA-454880-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-01-06 | 2026-01-07
I2S-7688-MP-74.CN.S6.34.8.1 | Culvert ID : E7-RA-454880-1 / Type : 7*900mm HDPE / Ch37432 (28.24m each) | I.CN.34.19640 | CON - Sec.6 - Culvert : E7-RA-454880-1 - Headwall installation | 2026-01-08 | 2026-01-08
I2S-7688-MP-74.CN.S6.34.8.1 | Culvert ID : E7-RA-454880-1 / Type : 7*900mm HDPE / Ch37432 (28.24m each) | I.CN.34.19650 | CON - Sec.6 - Culvert : E7-RA-454880-1 - HDPE / RCP Pipe Lay & Backfill | 2026-01-09 | 2026-01-10
I2S-7688-MP-74.CN.S6.34.8.1 | Culvert ID : E7-RA-454880-1 / Type : 7*900mm HDPE / Ch37432 (28.24m each) | I.CN.34.19670 | CON - Sec.6 - Culvert : E7-RA-454880-1 - Headwall Stitch Pour | 2026-01-11 | 2026-01-12
I2S-7688-MP-74.CN.S6.34.8.1 | Culvert ID : E7-RA-454880-1 / Type : 7*900mm HDPE / Ch37432 (28.24m each) | I.CN.34.19680 | CON - Sec.6 - Culvert : E7-RA-454880-1 - Headwall Cut-off Wall Installation (FRP) | 2026-01-13 | 2026-01-14
I2S-7688-MP-74.CN.S6.34.8.1 | Culvert ID : E7-RA-454880-1 / Type : 7*900mm HDPE / Ch37432 (28.24m each) | I.CN.34.19700 | CON - Sec.6 - Culvert : E7-RA-454880-1 - Construct Scour Protection | 2026-01-17 | 2026-01-18
Culvert ID : E7-RA-454804-1 / Type : 2*1200x450mm RCBC / Ch37294 (7.2m each)
I2S-7688-MP-74.CN.S6.34.8.5 | Culvert ID : E7-RA-454804-1 / Type : 2*1200x450mm RCBC / Ch37294 (7.2m each) | I.CN.65.19681 | CON - Sec.6 - Culvert : E7-RA-454804-1 - Struc fill Placement (250mm)
I2S-7688-MP-74.CN.S6.34.8.5 | Culvert ID : E7-RA-454804-1 / Type : 2*1200x450mm RCBC / Ch37294 (7.2m each) | I.CN.65.19761 | CON - Sec.6 - Culvert : E7-RA-454804-1 - Construct Scour protection
I2S-7688-MP-74.CN.S6.34.8.5 | Culvert ID : E7-RA-454804-1 / Type : 2*1200x450mm RCBC / Ch37294 (7.2m each) | I.CN.65.19671 | CON - Sec.6 - Culvert : E7-RA-454804-1 - LX Culvert - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S6.34.8.5 | Culvert ID : E7-RA-454804-1 / Type : 2*1200x450mm RCBC / Ch37294 (7.2m each) | I.CN.65.19691 | CON - Sec.6 - Culvert : E7-RA-454804-1 - Blinding placement (50mm)
I2S-7688-MP-74.CN.S6.34.8.5 | Culvert ID : E7-RA-454804-1 / Type : 2*1200x450mm RCBC / Ch37294 (7.2m each) | I.CN.65.19701 | CON - Sec.6 - Culvert : E7-RA-454804-1 - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.CN.S6.34.8.5 | Culvert ID : E7-RA-454804-1 / Type : 2*1200x450mm RCBC / Ch37294 (7.2m each) | I.CN.65.19711 | CON - Sec.6 - Culvert : E7-RA-454804-1 - 7 day Curing
I2S-7688-MP-74.CN.S6.34.8.5 | Culvert ID : E7-RA-454804-1 / Type : 2*1200x450mm RCBC / Ch37294 (7.2m each) | I.CN.65.19721 | CON - Sec.6 - Culvert : E7-RA-454804-1 - Place RCBC crown units
I2S-7688-MP-74.CN.S6.34.8.5 | Culvert ID : E7-RA-454804-1 / Type : 2*1200x450mm RCBC / Ch37294 (7.2m each) | I.CN.65.19731 | CON - Sec.6 - Culvert : E7-RA-454804-1 - Place Precast headwall and precast stich pours
I2S-7688-MP-74.CN.S6.34.8.5 | Culvert ID : E7-RA-454804-1 / Type : 2*1200x450mm RCBC / Ch37294 (7.2m each) | I.CN.65.19741 | CON - Sec.6 - Culvert : E7-RA-454804-1 - Pre-cast RCBC completion (Seal joints)
I2S-7688-MP-74.CN.S6.34.8.5 | Culvert ID : E7-RA-454804-1 / Type : 2*1200x450mm RCBC / Ch37294 (7.2m each) | I.CN.65.19751 | CON - Sec.6 - Culvert : E7-RA-454804-1 - Detail backfill
I2S-7688-MP-74.CN.S6.34.8.5 | Culvert ID : E7-RA-454804-1 / Type : 2*1200x450mm RCBC / Ch37294 (7.2m each) | I.CN.65.19991 | CON - Sec.6 - Culvert : E7-RA-454804-1 - FRP Base Slab / Apron Slab / Cut-off Wall - Milestone
Culvert ID : E7-RD-456911-1 / Type : 4*1200x600mm RCBC / Ch39403 (14.40m each)
I2S-7688-MP-74.CN.S6.34.8.3 | Culvert ID : E7-RD-456911-1 / Type : 4*1200x600mm RCBC / Ch39403 (14.40m each) | I.CN.34.29370 | CON - Sec.6 - Culvert: E7-RD-456911-1 - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.CN.S6.34.8.3 | Culvert ID : E7-RD-456911-1 / Type : 4*1200x600mm RCBC / Ch39403 (14.40m each) | I.CN.34.29360 | CON - Sec.6 - Culvert: E7-RD-456911-1 - Struc fill Placement (250mm)
I2S-7688-MP-74.CN.S6.34.8.3 | Culvert ID : E7-RD-456911-1 / Type : 4*1200x600mm RCBC / Ch39403 (14.40m each) | I.CN.34.29380 | CON - Sec.6 - Culvert: E7-RD-456911-1 - 7 day Curing
I2S-7688-MP-74.CN.S6.34.8.3 | Culvert ID : E7-RD-456911-1 / Type : 4*1200x600mm RCBC / Ch39403 (14.40m each) | I.CN.34.29390 | CON - Sec.6 - Culvert: E7-RD-456911-1 - Place RCBC crown units
I2S-7688-MP-74.CN.S6.34.8.3 | Culvert ID : E7-RD-456911-1 / Type : 4*1200x600mm RCBC / Ch39403 (14.40m each) | I.CN.34.29400 | CON - Sec.6 - Culvert: E7-RD-456911-1 - Place Pre-cast Wingwalls and Stich Pour
I2S-7688-MP-74.CN.S6.34.8.3 | Culvert ID : E7-RD-456911-1 / Type : 4*1200x600mm RCBC / Ch39403 (14.40m each) | I.CN.34.29410 | CON - Sec.6 - Culvert: E7-RD-456911-1 - Pre-cast RCBC completion (Seal joints)
I2S-7688-MP-74.CN.S6.34.8.3 | Culvert ID : E7-RD-456911-1 / Type : 4*1200x600mm RCBC / Ch39403 (14.40m each) | I.CN.34.29420 | CON - Sec.6 - Culvert: E7-RD-456911-1 - Detail backfill
I2S-7688-MP-74.CN.S6.34.8.3 | Culvert ID : E7-RD-456911-1 / Type : 4*1200x600mm RCBC / Ch39403 (14.40m each) | I.CN.34.29430 | CON - Sec.6 - Culvert: E7-RD-456911-1 - Construct Scour protection
I2S-7688-MP-74.CN.S6.34.8.3 | Culvert ID : E7-RD-456911-1 / Type : 4*1200x600mm RCBC / Ch39403 (14.40m each) | I.CN.34.29440 | CON - Sec.6 - Culvert: E7-RD-456911-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S6.34.8.3 | Culvert ID : E7-RD-456911-1 / Type : 4*1200x600mm RCBC / Ch39403 (14.40m each) | I.CN.34.31910 | CON - Sec.6 - Culvert: E7-RD-456911-1 - Blinding placement (50mm)
Culvert ID : E6-RD-456890-1 / Type : 2*1200x450mm RCBC / Ch39392 (8.13m each)
I2S-7688-MP-74.CN.S6.34.8.4 | Culvert ID : E6-RD-456890-1 / Type : 2*1200x450mm RCBC / Ch39392 (8.13m each) | I.CN.34.29450 | CON - Sec.6 - Culvert ID : 6-RD-456890-1 - Struc fill Placement (250mm)
I2S-7688-MP-74.CN.S6.34.8.4 | Culvert ID : E6-RD-456890-1 / Type : 2*1200x450mm RCBC / Ch39392 (8.13m each) | I.CN.34.29460 | CON - Sec.6 - Culvert ID : 6-RD-456890-1 - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.CN.S6.34.8.4 | Culvert ID : E6-RD-456890-1 / Type : 2*1200x450mm RCBC / Ch39392 (8.13m each) | I.CN.34.29470 | CON - Sec.6 - Culvert ID : 6-RD-456890-1 - 7 day Curing
I2S-7688-MP-74.CN.S6.34.8.4 | Culvert ID : E6-RD-456890-1 / Type : 2*1200x450mm RCBC / Ch39392 (8.13m each) | I.CN.34.29480 | CON - Sec.6 - Culvert ID : 6-RD-456890-1 - Place RCBC crown units
I2S-7688-MP-74.CN.S6.34.8.4 | Culvert ID : E6-RD-456890-1 / Type : 2*1200x450mm RCBC / Ch39392 (8.13m each) | I.CN.34.29490 | CON - Sec.6 - Culvert ID : 6-RD-456890-1 - Place Pre-cast Wingwalls and Stich Pour
I2S-7688-MP-74.CN.S6.34.8.4 | Culvert ID : E6-RD-456890-1 / Type : 2*1200x450mm RCBC / Ch39392 (8.13m each) | I.CN.34.29500 | CON - Sec.6 - Culvert ID : 6-RD-456890-1 - Pre-cast RCBC completion (Seal joints)
I2S-7688-MP-74.CN.S6.34.8.4 | Culvert ID : E6-RD-456890-1 / Type : 2*1200x450mm RCBC / Ch39392 (8.13m each) | I.CN.34.29510 | CON - Sec.6 - Culvert ID : 6-RD-456890-1 - Detail backfill
I2S-7688-MP-74.CN.S6.34.8.4 | Culvert ID : E6-RD-456890-1 / Type : 2*1200x450mm RCBC / Ch39392 (8.13m each) | I.CN.34.29520 | CON - Sec.6 - Culvert ID : 6-RD-456890-1 - Construct Scour protection
I2S-7688-MP-74.CN.S6.34.8.4 | Culvert ID : E6-RD-456890-1 / Type : 2*1200x450mm RCBC / Ch39392 (8.13m each) | I.CN.34.29530 | CON - Sec.6 - Culvert ID : 6-RD-456890-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S6.34.8.4 | Culvert ID : E6-RD-456890-1 / Type : 2*1200x450mm RCBC / Ch39392 (8.13m each) | I.CN.34.31920 | CON - Sec.6 - Culvert ID : 6-RD-456890-1 - Blinding placement (50mm)
Culvert ID : E7-RA-456800-1 / Type : 1*900x750mm RCBC / Ch39170 (9.6m) |  |  |  | 2026-01-19 | 2026-02-20
I2S-7688-MP-74.CN.S6.34.8.2 | Culvert ID : E7-RA-456800-1 / Type : 1*900x750mm RCBC / Ch39170 (9.6m) | I.CN.34.19960 | CON - Sec.6 - Culvert : E7-RA-456800-1 - Struc fill Placement (250mm) | 2026-01-21 | 2026-01-22
I2S-7688-MP-74.CN.S6.34.8.2 | Culvert ID : E7-RA-456800-1 / Type : 1*900x750mm RCBC / Ch39170 (9.6m) | I.CN.34.19990 | CON - Sec.6 - Culvert : E7-RA-456800-1 - FRP Base Slab / Apron Slab / Cut-off Wall | 2026-01-23 | 2026-01-24
I2S-7688-MP-74.CN.S6.34.8.2 | Culvert ID : E7-RA-456800-1 / Type : 1*900x750mm RCBC / Ch39170 (9.6m) | I.CN.34.20000 | CON - Sec.6 - Culvert : E7-RA-456800-1 - 7 day Curing | 2026-01-26 | 2026-02-12
I2S-7688-MP-74.CN.S6.34.8.2 | Culvert ID : E7-RA-456800-1 / Type : 1*900x750mm RCBC / Ch39170 (9.6m) | I.CN.34.20010 | CON - Sec.6 - Culvert : E7-RA-456800-1 - Place RCBC crown units | 2026-01-28 | 2026-02-14
I2S-7688-MP-74.CN.S6.34.8.2 | Culvert ID : E7-RA-456800-1 / Type : 1*900x750mm RCBC / Ch39170 (9.6m) | I.CN.34.20030 | CON - Sec.6 - Culvert : E7-RA-456800-1 - Place Pre-cast Wingwalls and Stich Pour | 2026-02-16 | 2026-02-16
I2S-7688-MP-74.CN.S6.34.8.2 | Culvert ID : E7-RA-456800-1 / Type : 1*900x750mm RCBC / Ch39170 (9.6m) | I.CN.34.20040 | CON - Sec.6 - Culvert : E7-RA-456800-1 - Pre-cast RCBC completion (Seal joints) | 2026-02-17 | 2026-02-18
I2S-7688-MP-74.CN.S6.34.8.2 | Culvert ID : E7-RA-456800-1 / Type : 1*900x750mm RCBC / Ch39170 (9.6m) | I.CN.34.20050 | CON - Sec.6 - Culvert : E7-RA-456800-1 - Detail backfill | 2026-02-19 | 2026-02-19
I2S-7688-MP-74.CN.S6.34.8.2 | Culvert ID : E7-RA-456800-1 / Type : 1*900x750mm RCBC / Ch39170 (9.6m) | I.CN.34.20060 | CON - Sec.6 - Culvert : E7-RA-456800-1 - Construct Scour protection | 2026-02-18 | 2026-02-20
I2S-7688-MP-74.CN.S6.34.8.2 | Culvert ID : E7-RA-456800-1 / Type : 1*900x750mm RCBC / Ch39170 (9.6m) | I.CN.34.19950 | CON - Sec.6 - Culvert : E7-RA-456800-1 - Site Prep / Detail Excavation | 2026-01-19 | 2026-01-20
I2S-7688-MP-74.CN.S6.34.8.2 | Culvert ID : E7-RA-456800-1 / Type : 1*900x750mm RCBC / Ch39170 (9.6m) | I.CN.34.31930 | CON - Sec.6 - Culvert : E7-RA-456800-1 - Blinding placement (50mm)
Culvert ID : E7-RD-455105-1 / Type : 3*450mm RCP 4 / Ch37595 (9.76m each)
I2S-7688-MP-74.CN.S6.34.8.6 | Culvert ID : E7-RD-455105-1 / Type : 3*450mm RCP 4 / Ch37595 (9.76m each) | I.CN.34.32230 | CON - Sec.4 - Culvert : E7-RA-439475-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S6.34.8.6 | Culvert ID : E7-RD-455105-1 / Type : 3*450mm RCP 4 / Ch37595 (9.76m each) | I.CN.34.32240 | CON - Sec.4 - Culvert : E7-RA-439475-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S6.34.8.6 | Culvert ID : E7-RD-455105-1 / Type : 3*450mm RCP 4 / Ch37595 (9.76m each) | I.CN.34.32250 | CON - Sec.4 - Culvert : E7-RA-439475-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S6.34.8.6 | Culvert ID : E7-RD-455105-1 / Type : 3*450mm RCP 4 / Ch37595 (9.76m each) | I.CN.34.32260 | CON - Sec.4 - Culvert : E7-RA-439475-1 - Construct Scour Protection
I2S-7688-MP-74.CN.S6.34.8.6 | Culvert ID : E7-RD-455105-1 / Type : 3*450mm RCP 4 / Ch37595 (9.76m each) | I.CN.34.32200 | CON - Sec.4 - Culvert : E7-RA-439475-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S6.34.8.6 | Culvert ID : E7-RD-455105-1 / Type : 3*450mm RCP 4 / Ch37595 (9.76m each) | I.CN.34.32210 | CON - Sec.4 - Culvert : E7-RA-439475-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S6.34.8.6 | Culvert ID : E7-RD-455105-1 / Type : 3*450mm RCP 4 / Ch37595 (9.76m each) | I.CN.34.32220 | CON - Sec.4 - Culvert : E7-RA-439475-1 - Headwall installation
I2S-7688-MP-74.CN.S6.34.8.6 | Culvert ID : E7-RD-455105-1 / Type : 3*450mm RCP 4 / Ch37595 (9.76m each) | I.CN.34.32830 | CON - Sec.4 - Culvert : E7-RA-439475-1 - HDPE / RCP Pipe Lay & Backfill - Milestone
043 - Fencing |  |  |  | 2025-09-13 | 2025-10-27
Eastern Side |  |  |  | 2025-09-13 | 2025-10-27
I2S-7688-MP-74.CN.S6.43.1 | Eastern Side | I.CN.43.13030 | CON - Sec.6 - Fencing East Side - Ch37300-37700 (BGW Field) | 2025-09-13 | 2025-09-20
I2S-7688-MP-74.CN.S6.43.1 | Eastern Side | I.CN.43.14100 | CON - Sec.6 - Fencing East Side - Ch37700-39000 | 2025-09-21 | 2025-10-10
I2S-7688-MP-74.CN.S6.43.1 | Eastern Side | I.CN.43.14120 | CON - Sec.6 - Fencing East Side - Ch39000-40000 | 2025-10-11 | 2025-10-27
Western Side |  |  |  | 2025-09-13 | 2025-10-27
I2S-7688-MP-74.CN.S6.43.2 | Western Side | I.CN.43.14090 | CON - Sec.6 - Fencing West Side - Ch37300-37700 (BGW Field) | 2025-09-13 | 2025-09-20
I2S-7688-MP-74.CN.S6.43.2 | Western Side | I.CN.43.14110 | CON - Sec.6 - Fencing West Side - Ch37700-39000 | 2025-09-21 | 2025-10-10
I2S-7688-MP-74.CN.S6.43.2 | Western Side | I.CN.43.14130 | CON - Sec.6 - Fencing West Side - Ch39000-40000 | 2025-10-11 | 2025-10-27
044 - Roadworks |  |  |  | 2025-08-30 | 2026-11-03
BGW |  |  |  | 2025-08-30 | 2026-11-03
BGW Temporary Diversion |  |  |  | 2025-08-30 | 2025-10-04
I2S-7688-MP-74.CN.S6.44.2.1 | BGW Temporary Diversion | I.CN.50.15180 | CON - Sec.6 - BGW Temp - Road Diversion + Traffic Switch - operational |  | 2025-10-04
I2S-7688-MP-74.CN.S6.44.2.1 | BGW Temporary Diversion | I.CN.62.19470 | CON - Sec.6 - BGW Temp - Road Diversion - Cut/Strip | 2025-08-30 | 2025-10-03
I2S-7688-MP-74.CN.S6.44.2.1 | BGW Temporary Diversion | I.CN.62.22870 | CON - Sec.6 - BGW Temp - Road Diversion - Foundation Test/treatment
I2S-7688-MP-74.CN.S6.44.2.1 | BGW Temporary Diversion | I.CN.62.22880 | CON - Sec.6 - BGW Temp - Road Diversion - Base Course (CMZ1 & CMZ2)
I2S-7688-MP-74.CN.S6.44.2.1 | BGW Temporary Diversion | I.CN.62.22890 | CON - Sec.6 - BGW Temp - Road Diversion - Asphalt
I2S-7688-MP-74.CN.S6.44.2.1 | BGW Temporary Diversion | I.CN.62.22900 | CON - Sec.6 - BGW Temp - Road Diversion - Bulk Embankment Fill
I2S-7688-MP-74.CN.S6.44.2.1 | BGW Temporary Diversion | I.CN.62.22910 | CON - Sec.6 - BGW Temp - Road Diversion - Spray Seal
BGW Permanent Roadworks |  |  |  | 2026-09-13 | 2026-11-03
I2S-7688-MP-74.CN.S6.44.2.2 | BGW Permanent Roadworks | I.CN.62.19480 | CON - Sec.6 - Remove BGW Road Diversion & Finish Basin Works | 2026-09-13 | 2026-10-06
I2S-7688-MP-74.CN.S6.44.2.2 | BGW Permanent Roadworks | I.CN.62.19270 | CON - Sec.6 - NEW Burley Griffin Way Bridge Completion - Permanent Traffic Switch - Operational |  | 2026-11-03
I2S-7688-MP-74.CN.S6.44.2.2 | BGW Permanent Roadworks | I.CN.62.22980 | CON - Sec.6 - Provide TfNSW - confirmation of LX closure date
I2S-7688-MP-74.CN.S6.44.2.2 | BGW Permanent Roadworks | I.CN.74.15970 | CON - Sec.6 - New LX Crossing Commissioned - Possession - BGW road - operational - permanent
NBN |  |  |  | 2025-10-04 | 2025-12-18
I2S-7688-MP-74.CN.S6.44.3 | NBN | I.CN.65.11690 | CON - Sec.6 - Construct Pavement type B sealed - SMZ Placement (2550m2) access road - for LX PR39450 to Grogan Road | 2025-11-11 | 2025-11-24
I2S-7688-MP-74.CN.S6.44.3 | NBN | I.CN.65.12960 | CON - Sec.6 - Construct Pavement type A Unsealed - SMZ Placement (5850m2) access road to NBN/ Goldenfields Water Tower | 2025-10-04 | 2025-11-06
I2S-7688-MP-74.CN.S6.44.3 | NBN | I.CN.65.17950 | CON - Sec.6 - Construct Pavement type B sealed - Primeseal (2550m2) access road - for LX PR39450 to Grogan Road | 2025-11-26 | 2025-11-28
I2S-7688-MP-74.CN.S6.44.3 | NBN | I.CN.65.17960 | CON - Sec.6 - Construct Pavement type A Unsealed - Primeseal (5850m2) access road to NBN & Goldenfields Water | 2025-11-07 | 2025-11-10
I2S-7688-MP-74.CN.S6.44.3 | NBN | I.CN.65.17970 | CON - Sec.6 - Construct Pavement type B sealed - Asphalt (2550m2) access road - for LX PR39450 to Grogan Road | 2025-11-29 | 2025-12-18
045 - Access Roads |  |  |  | 2025-07-12 | 2026-09-12
RMAR |  |  |  | 2025-11-04 | 2026-09-12
I2S-7688-MP-74.CN.S6.45.2 | RMAR | I.CN.65.12820 | CON - Sec.6 - Prep RMAR Road - across CRN track - 37680 - 37720 | 2026-09-10 | 2026-09-12
I2S-7688-MP-74.CN.S6.45.2 | RMAR | I.CN.65.12830 | CON - Sec.6 - Prep RMAR Road - 38045 - 39305 | 2026-04-22 | 2026-04-24
I2S-7688-MP-74.CN.S6.45.2 | RMAR | I.CN.65.12760 | CON - Sec.6 - Prep RMAR Road - across TO - 37400 - 37680 | 2026-04-07 | 2026-04-12
I2S-7688-MP-74.CN.S6.45.2 | RMAR | I.CN.65.12770 | CON - Sec.6 - Prep RMAR Road - across old BGW - 37240 - 37400 | 2025-11-04 | 2025-11-10
I2S-7688-MP-74.CN.S6.45.2 | RMAR | I.CN.65.12780 | CON - Sec.6 - Prep RMAR Road - 39305 - 42480 | 2026-04-19 | 2026-04-21
I2S-7688-MP-74.CN.S6.45.2 | RMAR | I.CN.65.12790 | CON - Sec.6 - Prep RMAR Road - CRN East | 2026-04-02 | 2026-04-06
I2S-7688-MP-74.CN.S6.45.2 | RMAR | I.CN.65.12800 | CON - Sec.6 - Prep RMAR Road - CRN West | 2026-04-16 | 2026-04-18
I2S-7688-MP-74.CN.S6.45.2 | RMAR | I.CN.65.12810 | CON - Sec.6 - Prep RMAR Road - CRN to Bridge - 37720 - 37950 | 2026-04-13 | 2026-04-15
Site Access |  |  |  | 2025-07-12 | 2025-08-11
I2S-7688-MP-74.CN.S6.45.1 | Site Access | I.CN.65.18110 | CON - Sec.6 - Build Temporary Crossing of I2S for access to NBN Tower | 2025-07-20 | 2025-07-24
I2S-7688-MP-74.CN.S6.45.1 | Site Access | I.CN.65.18120 | CON - Sec.6 - Build Temp. Road to access to NBN Tower | 2025-07-26 | 2025-08-11
I2S-7688-MP-74.CN.S6.45.1 | Site Access | I.CN.11.5600 | CON - Sec.6 - Site Access Available - ( CRN37600 to 37800 BF) | 2025-07-12
I2S-7688-MP-74.CN.S6.45.1 | Site Access | I.CN.11.6030 | CON - Sec.6 - Site Access Available - E-W East from N-S to Troy | 2025-07-12
I2S-7688-MP-74.CN.S6.45.1 | Site Access | I.CN.65.12950 | CON - Sec.6 - Construct Temporary Site Access Road for Burley Griffin Road Bridge /Concrete Barriers/ Traffic Manag | 2025-07-26 | 2025-07-31
I2S-7688-MP-74.CN.S6.45.1 | Site Access | I.CN.31.14170 | CON - Sec.6 - Construct Temp Creek Crossing - Dudauman Creek for traffic | 2025-07-18 | 2025-07-19
CRN license
I2S-7688-MP-74.CN.S6.45.1.3 | CRN license | I.CN.65.18865 | CON - Sec.6 - CRN License - JHG legal team review Period of Licences
I2S-7688-MP-74.CN.S6.45.1.3 | CRN license | I.CN.65.18870 | CON - Sec.6 - CRN License - Finalization and approval of CRN Licences
I2S-7688-MP-74.CN.S6.45.1.3 | CRN license | I.CN.65.18871 | CON - Sec.6 - CRN License - JHG Accept and Pay Fees
I2S-7688-MP-74.CN.S6.45.1.3 | CRN license | I.CN.65.18450 | CON - Sec.6 - CRN License - Review of Application By CRN
I2S-7688-MP-74.CN.S6.45.1.3 | CRN license | I.CN.65.18881 | CON - Sec.6 - CRN License - Review of Application Comments Close out by JHG
I2S-7688-MP-74.CN.S6.45.1.3 | CRN license | I.CN.65.18840 | CON - Sec.6 - CRN License - Prepare CRN Construction Access Aplication
I2S-7688-MP-74.CN.S6.45.1.3 | CRN license | I.CN.65.18850 | CON - Sec.6 - CRN License - Submit Application for CRN Access Permission for Construction
I2S-7688-MP-74.CN.S6.45.1.3 | CRN license | I.CN.65.18860 | CON - Sec.6 - CRN License - CRN Provide the draft Licences to JHG
050 - Trackwork |  |  |  | 2026-03-29 | 2026-11-13
Phase 1 - Pre Possession |  |  |  | 2026-03-29 | 2026-05-06
New CRN Track (East to West) - Greenfield build |  |  |  | 2026-03-29 | 2026-04-14
I2S-7688-MP-74.CN.S6.50.4.1 | New CRN Track (East to West) - Greenfield build | I.CN.50.18500 | CON - Sec.6 - Track team Commencing work onsite | 2026-03-29
Place Bottom Ballast |  |  |  | 2026-03-29 | 2026-04-01
I2S-7688-MP-74.CN.S6.50.4.1.15 | Place Bottom Ballast | I.CN.50.14140 | CON - Sec.6 - Place Bottom Ballast - 500m/day - (400m) - CRN - West | 2026-03-29 | 2026-03-29
I2S-7688-MP-74.CN.S6.50.4.1.15 | Place Bottom Ballast | I.CN.50.14150 | CON - Sec.6 - Place Bottom Ballast - 500m/day - (400m) - CRN - start | 2026-03-30 | 2026-03-30
I2S-7688-MP-74.CN.S6.50.4.1.15 | Place Bottom Ballast | I.CN.50.14160 | CON - Sec.6 - Place Bottom Ballast - 500m/day - (400m) - CRN - finish | 2026-03-31 | 2026-03-31
I2S-7688-MP-74.CN.S6.50.4.1.15 | Place Bottom Ballast | I.CN.50.14410 | CON - Sec.6 - Place Bottom Ballast - 500m/day - (400m) - CRN - East | 2026-04-01 | 2026-04-01
Sleeper Distribution |  |  |  | 2026-04-02 | 2026-04-04
I2S-7688-MP-74.CN.S6.50.4.1.1 | Sleeper Distribution | I.CN.50.11890 | CON - Sec.6 - Sleeper Distribution - 860m/day - 44000 to 45000 (850m) - start | 2026-04-03 | 2026-04-03
I2S-7688-MP-74.CN.S6.50.4.1.1 | Sleeper Distribution | I.CN.50.11900 | CON - Sec.6 - Sleeper Distribution - 860m/day - 44000 to 45000 (850m) - finish | 2026-04-04 | 2026-04-04
I2S-7688-MP-74.CN.S6.50.4.1.1 | Sleeper Distribution | I.CN.50.11700 | CON - Sec.6 - Intermediate Sleeper Stockpiles - CRN 36347 - 38070 | 2026-04-02 | 2026-04-02
Rail Distribution |  |  |  | 2026-03-29 | 2026-04-06
I2S-7688-MP-74.CN.S6.50.4.1.2 | Rail Distribution | I.CN.50.11880 | CON - Sec.6 - Rail Distribution - 860m/day - CRN (1700m - 44000 to 45000 | 2026-04-06 | 2026-04-06
I2S-7688-MP-74.CN.S6.50.4.1.2 | Rail Distribution | I.CN.91.14530 | CON - Sec.6 - Hold point for QA Inspection with IRPL - Sec.6 - all tracks - Rail | 2026-03-29 | 2026-04-02
I2S-7688-MP-74.CN.S6.50.4.1.2 | Rail Distribution | I.CN.50.18570 | CON - Sec.6 - Install Barrier close to CRN track to install Turnout | 2026-04-03 | 2026-04-03
Sleeper Laying |  |  |  | 2026-04-06 | 2026-04-09
I2S-7688-MP-74.CN.S6.50.4.1.3 | Sleeper Laying | I.CN.50.11840 | CON - Sec.6 - Sleeper Laying - 800m/day - 36347 to 36778 - CRN - East | 2026-04-06 | 2026-04-06
I2S-7688-MP-74.CN.S6.50.4.1.3 | Sleeper Laying | I.CN.50.11850 | CON - Sec.6 - Sleeper Laying - 800m/day - 36778 to 37209- CRN | 2026-04-07 | 2026-04-07
I2S-7688-MP-74.CN.S6.50.4.1.3 | Sleeper Laying | I.CN.50.11860 | CON - Sec.6 - Sleeper Laying - 800m/day - 37209 to 37639 - CRN /I2S - TO | 2026-04-08 | 2026-04-08
I2S-7688-MP-74.CN.S6.50.4.1.3 | Sleeper Laying | I.CN.50.11870 | CON - Sec.6 - Sleeper Laying - 800m/day - 37639 to 38070 - CRN - West | 2026-04-09 | 2026-04-09
Rail Laying |  |  |  | 2026-04-04 | 2026-04-10
I2S-7688-MP-74.CN.S6.50.4.1.4 | Rail Laying | I.CN.50.11800 | CON - Sec.6 - Rail Laying - 550m/day - (400m) - 36347 to 36778 - CRN - East | 2026-04-07 | 2026-04-07
I2S-7688-MP-74.CN.S6.50.4.1.4 | Rail Laying | I.CN.50.11810 | CON - Sec.6 - Rail Laying - 550m/day - (400m) - crn2 - 44000 to 45000 | 2026-04-08 | 2026-04-08
I2S-7688-MP-74.CN.S6.50.4.1.4 | Rail Laying | I.CN.50.11820 | CON - Sec.6 - Rail Laying - 550m/day - (400m) - crn3 - 44000 to 45000 | 2026-04-09 | 2026-04-09
I2S-7688-MP-74.CN.S6.50.4.1.4 | Rail Laying | I.CN.50.11830 | CON - Sec.6 - Rail Laying - 550m/day - (400m) - 37639 to 38070 - CRN - West | 2026-04-10 | 2026-04-10
I2S-7688-MP-74.CN.S6.50.4.1.4 | Rail Laying | I.CN.50.18560 | CON - Sec.6 - Install New 1:10:5 R250 RH Tangential Turnout | 2026-04-04 | 2026-04-04
Flash Butt Welding and clip up |  |  |  | 2026-04-11 | 2026-04-11
I2S-7688-MP-74.CN.S6.50.4.1.5 | Flash Butt Welding and clip up | I.CN.50.11790 | CON - Sec.6 - Flash Butt Welding and clip up (30 welds/ 412.5 m) -CRN - 44000 to 45000 | 2026-04-11 | 2026-04-11
Top Ballast Finals |  |  |  | 2026-04-11 | 2026-04-12
I2S-7688-MP-74.CN.S6.50.4.1.9 | Top Ballast Finals | I.CN.50.15140 | CON - Sec.6 - Top Ballast Finals - 3000m/day - 37300 to 38070- CRN | 2026-04-12 | 2026-04-12
I2S-7688-MP-74.CN.S6.50.4.1.9 | Top Ballast Finals | I.CN.50.11780 | CON - Sec.6 - Top Ballast Finals - 3000m/day - 36347 to 37300 - CRN | 2026-04-11 | 2026-04-11
Destressing |  |  |  | 2026-04-13 | 2026-04-14
I2S-7688-MP-74.CN.S6.50.4.1.11 | Destressing | I.CN.50.11760 | CON - Sec.6 - Destressing - 1200m/day - 36347 to 37300 - CRN | 2026-04-13 | 2026-04-13
I2S-7688-MP-74.CN.S6.50.4.1.11 | Destressing | I.CN.50.11770 | CON - Sec.6 - Destressing - 1200m/day - 37300 to 38070- CRN | 2026-04-14 | 2026-04-14
I2S Track - 37300 - 37700 - Greenfield build |  |  |  | 2026-04-15 | 2026-04-24
Place Bottom Ballast |  |  |  | 2026-04-15 | 2026-04-15
I2S-7688-MP-74.CN.S6.50.4.2.15 | Place Bottom Ballast | I.CN.50.17820 | CON - Sec.6 - Place Bottom Ballast - 500m/day - (300m) - I2S- 37300 to 37600 | 2026-04-15 | 2026-04-15
Sleeper Distribution |  |  |  | 2026-04-16 | 2026-04-16
I2S-7688-MP-74.CN.S6.50.4.2.1 | Sleeper Distribution | I.CN.50.17830 | CON - Sec.6 - Sleeper Distribution - 860m/day - 37600 to 37600 (300m) | 2026-04-16 | 2026-04-16
Rail Distribution |  |  |  | 2026-04-17 | 2026-04-17
I2S-7688-MP-74.CN.S6.50.4.2.2 | Rail Distribution | I.CN.50.17840 | CON - Sec.6 - Rail Distribution - 860m/day - 37300 to 37600 - | 2026-04-17 | 2026-04-17
Sleeper Laying |  |  |  | 2026-04-18 | 2026-04-18
I2S-7688-MP-74.CN.S6.50.4.2.3 | Sleeper Laying | I.CN.50.4250 | CON - Sec.6 - Sleeper Laying - 800m/day - 37300 to 37450 - upto TOs | 2026-04-18 | 2026-04-18
Rail Laying |  |  |  | 2026-04-19 | 2026-04-22
I2S-7688-MP-74.CN.S6.50.4.2.4 | Rail Laying | I.CN.50.3700 | CON - Sec.6 - Rail Laying - 550m/day - (550m/day) - 37300 to 37450 - upto TOs - | 2026-04-19 | 2026-04-19
I2S-7688-MP-74.CN.S6.50.4.2.4 | Rail Laying | I.CN.50.12940 | CON - Sec.6 - Lift in Turnout - 1 in 10.5 R250 (PEM/LEM or Crane) (37521) | 2026-04-19 | 2026-04-20
I2S-7688-MP-74.CN.S6.50.4.2.4 | Rail Laying | I.CN.50.12950 | CON - Sec.6 - Lift in Turnout - 1 in 10.5 R250 (PEM/LEM or Crane) (37541) | 2026-04-21 | 2026-04-22
Flash Butt Welding and clip up |  |  |  | 2026-04-20 | 2026-04-20
I2S-7688-MP-74.CN.S6.50.4.2.5 | Flash Butt Welding and clip up | I.CN.50.15400 | CON - Sec.6 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 37300 to 37600 | 2026-04-20 | 2026-04-20
Place Top Ballast Initial |  |  |  | 2026-04-21 | 2026-04-21
I2S-7688-MP-74.CN.S6.50.4.2.6 | Place Top Ballast Initial | I.CN.50.17850 | CON - Sec.6 - Place Top Ballast Initial - 1500m/day - 37300 to 37600 | 2026-04-21 | 2026-04-21
Top Ballast Finals |  |  |  | 2026-04-22 | 2026-04-22
I2S-7688-MP-74.CN.S6.50.4.2.9 | Top Ballast Finals | I.CN.50.17860 | CON - Sec.6 - Top Ballast Finals - 3000m/day - 37300 to 37600 | 2026-04-22 | 2026-04-22
Destressing |  |  |  | 2026-04-23 | 2026-04-23
I2S-7688-MP-74.CN.S6.50.4.2.11 | Destressing | I.CN.50.17790 | CON - Sec.6 - Destressing - 1200m/day - 37300 - 37600 | 2026-04-23 | 2026-04-23
Track Joint Inspection |  |  |  | 2026-04-24 | 2026-04-24
I2S-7688-MP-74.CN.S6.50.4.2.13 | Track Joint Inspection | I.CN.50.15370 | CON - Sec.6 - Track Joint Inspection - 5000m/day - 37300 - 37600 | 2026-04-24 | 2026-04-24
I2S Track - 37750 - 42500 - Greenfield build |  |  |  | 2026-04-03 | 2026-05-06
Place Bottom Ballast |  |  |  | 2026-04-16 | 2026-04-20
I2S-7688-MP-74.CN.S6.50.4.3.15 | Place Bottom Ballast | I.CN.50.14070 | CON - Sec.6 - Place Bottom Ballast - 500m/day - 39500 to 40000 (500m) | 2026-04-19 | 2026-04-19
I2S-7688-MP-74.CN.S6.50.4.3.15 | Place Bottom Ballast | I.CN.50.14430 | CON - Sec.6 - Place Bottom Ballast - 500m/day - 40000 to 40540 (540m) | 2026-04-20 | 2026-04-20
I2S-7688-MP-74.CN.S6.50.4.3.15 | Place Bottom Ballast | I.CN.50.14040 | CON - Sec.6 - Place Bottom Ballast - 500m/day - 37800 to 38500 (700m) | 2026-04-16 | 2026-04-16
I2S-7688-MP-74.CN.S6.50.4.3.15 | Place Bottom Ballast | I.CN.50.14050 | CON - Sec.6 - Place Bottom Ballast - 500m/day - 38500 to 39000 (500m) | 2026-04-17 | 2026-04-17
I2S-7688-MP-74.CN.S6.50.4.3.15 | Place Bottom Ballast | I.CN.50.14060 | CON - Sec.6 - Place Bottom Ballast - 500m/day - 39000 to 39500 (500m) | 2026-04-18 | 2026-04-18
Sleeper Distribution |  |  |  | 2026-04-03 | 2026-04-22
I2S-7688-MP-74.CN.S6.50.4.3.1 | Sleeper Distribution | I.CN.50.5210 | CON - Sec.6 - Sleeper Distribution - 860m/day - 38170 to 38860 (860m) - start | 2026-04-21 | 2026-04-21
I2S-7688-MP-74.CN.S6.50.4.3.1 | Sleeper Distribution | I.CN.50.15290 | CON - Sec.6 - Intermediate Sleeper Stockpiles | 2026-04-03 | 2026-04-03
I2S-7688-MP-74.CN.S6.50.4.3.1 | Sleeper Distribution | I.CN.50.17730 | CON - Sec.6 - Sleeper Distribution - 860m/day - 38170 to 38860 (860m) - finish | 2026-04-22 | 2026-04-22
Rail Distribution |  |  |  | 2026-04-22 | 2026-04-24
I2S-7688-MP-74.CN.S6.50.4.3.2 | Rail Distribution | I.CN.50.17740 | CON - Sec.6 - Rail Distribution - 860m/day - 38790 to 39780 - | 2026-04-23 | 2026-04-23
I2S-7688-MP-74.CN.S6.50.4.3.2 | Rail Distribution | I.CN.50.17750 | CON - Sec.6 - Rail Distribution - 860m/day - 39780 to 40540 - | 2026-04-24 | 2026-04-24
I2S-7688-MP-74.CN.S6.50.4.3.2 | Rail Distribution | I.CN.50.15360 | CON - Sec.6 - Rail Distribution - 860m/day - 37800 to 38790 - | 2026-04-22 | 2026-04-22
Sleeper Laying |  |  |  | 2026-04-22 | 2026-04-24
I2S-7688-MP-74.CN.S6.50.4.3.3 | Sleeper Laying | I.CN.50.4260 | CON - Sec.6 - Sleeper Laying - 800m/day - 37750 to 38550 | 2026-04-22 | 2026-04-22
I2S-7688-MP-74.CN.S6.50.4.3.3 | Sleeper Laying | I.CN.50.4270 | CON - Sec.6 - Sleeper Laying - 800m/day - 38550 to 39350 | 2026-04-23 | 2026-04-23
I2S-7688-MP-74.CN.S6.50.4.3.3 | Sleeper Laying | I.CN.50.4280 | CON - Sec.6 - Sleeper Laying - 800m/day - 39350 to TO | 2026-04-24 | 2026-04-24
Rail Laying |  |  |  | 2026-04-23 | 2026-04-27
I2S-7688-MP-74.CN.S6.50.4.3.4 | Rail Laying | I.CN.50.3710 | CON - Sec.6 - Rail Laying - 550m/day - 37800 to 38520 | 2026-04-23 | 2026-04-23
I2S-7688-MP-74.CN.S6.50.4.3.4 | Rail Laying | I.CN.50.3720 | CON - Sec.6 - Rail Laying - 550m/day - 39240 to 39960 | 2026-04-26 | 2026-04-26
I2S-7688-MP-74.CN.S6.50.4.3.4 | Rail Laying | I.CN.50.3730 | CON - Sec.6 - Rail Laying - 550m/day - 39960 to TO | 2026-04-27 | 2026-04-27
I2S-7688-MP-74.CN.S6.50.4.3.4 | Rail Laying | I.CN.50.17720 | CON - Sec.6 - Rail Laying - 550m/day - 38520 to 39240 | 2026-04-24 | 2026-04-24
Flash Butt Welding and clip up |  |  |  | 2026-04-28 | 2026-04-28
I2S-7688-MP-74.CN.S6.50.4.3.5 | Flash Butt Welding and clip up | I.CN.50.15330 | CON - Sec.6 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 37800 to 38830 | 2026-04-28 | 2026-04-28
Place Top Ballast Initial |  |  |  | 2026-04-29 | 2026-04-29
I2S-7688-MP-74.CN.S6.50.4.3.6 | Place Top Ballast Initial | I.CN.50.17700 | CON - Sec.6 - Place Top Ballast Initial - 1500m/day - 37800 to 40220 | 2026-04-29 | 2026-04-29
Surfacing Firsts |  |  |  | 2026-04-30 | 2026-05-01
I2S-7688-MP-74.CN.S6.50.4.3.7 | Surfacing Firsts | I.CN.50.17660 | CON - Sec.6 - Surfacing Firsts - 4000m/day - 37800 to 40220 | 2026-05-01 | 2026-05-01
I2S-7688-MP-74.CN.S6.50.4.3.7 | Surfacing Firsts | I.CN.50.18270 | CON - Sec.6 - Traverse and level Gedo Control - Sec.6- 37800 to 40220 | 2026-04-30 | 2026-04-30
Surfacing Seconds |  |  |  | 2026-05-02 | 2026-05-02
I2S-7688-MP-74.CN.S6.50.4.3.8 | Surfacing Seconds | I.CN.50.17670 | CON - Sec.6 - Surfacing Seconds - 4000m/day - 37800 to 40220 | 2026-05-02 | 2026-05-02
Top Ballast Finals |  |  |  | 2026-05-03 | 2026-05-03
I2S-7688-MP-74.CN.S6.50.4.3.9 | Top Ballast Finals | I.CN.50.17680 | CON - Sec.6 - Top Ballast Finals - 3000m/day - 37800 to 40220 | 2026-05-03 | 2026-05-03
Corrections + Signage + Rubber Xings |  |  |  | 2026-05-04 | 2026-05-05
I2S-7688-MP-74.CN.S6.50.4.3.12 | Corrections + Signage + Rubber Xings | I.CN.50.1890 | CON - Sec.6 - Corrections + Signage - 2000m/day - 37800 to 40000 | 2026-05-05 | 2026-05-05
I2S-7688-MP-74.CN.S6.50.4.3.12 | Corrections + Signage + Rubber Xings | I.CN.50.17880 | CON - Sec.6 - Destressing - 1200m/day - 39200 to 39300 I2S Northern Turnout | 2026-05-04 | 2026-05-04
Track Joint Inspection |  |  |  | 2026-05-06 | 2026-05-06
I2S-7688-MP-74.CN.S6.50.4.3.13 | Track Joint Inspection | I.CN.50.15310 | CON - Sec.6 - Track Joint Inspection - 5000m/day - 37800 - 40000 | 2026-05-06 | 2026-05-06
I2S Track - BGW Infill Works
I2S-7688-MP-74.CN.S6.50.4.14 | I2S Track - BGW Infill Works | I.CN.50.20560 | CON - Sec.6 - Track infill works across Old BGW at Troy St after Traffic Switch
Phase 2 - Possession - Sep 26
I2S-7688-MP-74.CN.S6.50.5 | Phase 2 - Possession - Sep 26 | I.CN.50.20030 | CON - Sec.6 - Target Readiness for Possession - I2S and S2P - Main Line works - 60 hours
I2S-7688-MP-74.CN.S6.50.5 | Phase 2 - Possession - Sep 26 | I.CN.50.20080 | CON - Sec.6 - Possession - 60 hours - I2S and S2P - Main Line works - Contingency - OD 60d reduced to 35d
I2S-7688-MP-74.CN.S6.50.5 | Phase 2 - Possession - Sep 26 | I.CN.50.20090 | CON - Sec.6 - Possession - 60 hours - I2S and S2P - Main Line works - commencement
Rail Safety
take out
I2S-7688-MP-74.CN.S6.50.5.3.1 | take out | I.CN.50.20470 | CON - Sec.6 - Possession - Take out - I2S and S2P - Main Line works - OD 60 hours
Across Old CRN Track - (new I2S Mainline across CRN- 37700 - 37750 )
I2S-7688-MP-74.CN.S6.50.5.6 | Across Old CRN Track - (new I2S Mainline across CRN- 37700 - 37750 ) | I.CN.50.20480 | CON - Sec.6 - Possession - Across Old CRN Track - (New I2S Mainline across CRN 3770-37750) - Summary
New CRN Track (Stockinbingal tie in ) (Eastern End)
I2S-7688-MP-74.CN.S6.50.5.4 | New CRN Track (Stockinbingal tie in ) (Eastern End) | I.CN.50.20490 | CON - Sec.6 - Possession - New CRN Track (Stockinbingal tie in) (Eastern End) - Summary
Parkes Tie in (Northern 39200)
I2S-7688-MP-74.CN.S6.50.5.2 | Parkes Tie in (Northern 39200) | I.CN.50.20500 | CON - Sec.6 - Possession - Parkes Tie in (Northern 39200) - Summary
New CRN Track (CRN Tie in ) (Western end)
I2S-7688-MP-74.CN.S6.50.5.1 | New CRN Track (CRN Tie in ) (Western end) | I.CN.50.20510 | CON - Sec.6 - Possession - New CRN Track (CRN Tie in) (Western end) - Summary
Tamping and Destressing
I2S-7688-MP-74.CN.S6.50.5.7 | Tamping and Destressing | I.CN.50.20520 | CON - Sec.6 - Possession - Tamping and Destressing - Summary
Rail Safety - hand back
I2S-7688-MP-74.CN.S6.50.5.5 | Rail Safety - hand back | I.CN.50.20530 | CON - Sec.6 - Possession - Rail Safety hand back - Summary
Phase 3 - Post Possession |  |  |  | 2026-09-16 | 2026-11-13
I2S Track - 37240 - 37400 Post Road Diversion |  |  |  | 2026-11-10 | 2026-11-13
Place Bottom Ballast |  |  |  | 2026-11-10 | 2026-11-10
I2S-7688-MP-74.CN.S6.50.7.2.15 | Place Bottom Ballast | I.CN.50.18130 | CON - Sec.6 - Place Bottom Ballast - 500m/day - (60m) (across old BGW - 37280 - 37340) | 2026-11-10 | 2026-11-10
Sleeper Distribution |  |  |  | 2026-11-10 | 2026-11-10
I2S-7688-MP-74.CN.S6.50.7.2.1 | Sleeper Distribution | I.CN.50.18120 | CON - Sec.6 - Sleeper Distribution - 860m/day - (across old BGW - 36775 to 36800 (60m) | 2026-11-10 | 2026-11-10
Rail Distribution |  |  |  | 2026-11-10 | 2026-11-10
I2S-7688-MP-74.CN.S6.50.7.2.2 | Rail Distribution | I.CN.50.18110 | CON - Sec.6 - Rail Distribution - 860m/day - (60m) (across old BGW - 37280 - 37340) - | 2026-11-10 | 2026-11-10
Sleeper Laying |  |  |  | 2026-11-10 | 2026-11-10
I2S-7688-MP-74.CN.S6.50.7.2.3 | Sleeper Laying | I.CN.50.18100 | CON - Sec.6 - Sleeper Laying - 800m/day - (across old BGW - 37280 - 37340) | 2026-11-10 | 2026-11-10
Rail Laying |  |  |  | 2026-11-10 | 2026-11-10
I2S-7688-MP-74.CN.S6.50.7.2.4 | Rail Laying | I.CN.50.18090 | CON - Sec.6 - Rail Laying - 550m/day - across old BGW - 37280 - 37340 (60m) | 2026-11-10 | 2026-11-10
Flash Butt Welding and clip up |  |  |  | 2026-11-11 | 2026-11-11
I2S-7688-MP-74.CN.S6.50.7.2.5 | Flash Butt Welding and clip up | I.CN.50.18080 | CON - Sec.6 - Flash Butt Welding and clip up (30 welds/ 412.5 m) (60m) (across old BGW - 37280 - 37340) | 2026-11-11 | 2026-11-11
Top Ballast Finals |  |  |  | 2026-11-11 | 2026-11-11
I2S-7688-MP-74.CN.S6.50.7.2.9 | Top Ballast Finals | I.CN.50.18070 | CON - Sec.6 - Top Ballast Finals - 3000m/day - across old BGW - 37280 - 37340 (60m) | 2026-11-11 | 2026-11-11
Destressing |  |  |  | 2026-11-11 | 2026-11-11
I2S-7688-MP-74.CN.S6.50.7.2.11 | Destressing | I.CN.50.18060 | CON - Sec.6 - Destressing - 1200m/day - across old BGW - 37280 - 37340 (60m) | 2026-11-11 | 2026-11-11
Corrections + Signage + Rubber Xings |  |  |  | 2026-11-11 | 2026-11-13
I2S-7688-MP-74.CN.S6.50.7.2.12 | Corrections + Signage + Rubber Xings | I.CN.50.18010 | CON - Sec.6 - Track Joint Inspection - across old BGW - 37280 - 37340 (60m) | 2026-11-12 | 2026-11-13
I2S-7688-MP-74.CN.S6.50.7.2.12 | Corrections + Signage + Rubber Xings | I.CN.50.18020 | CON - Sec.6 - Corrections + Signage - 2000m/day - across old BGW - 37280 - 37340 (60m) | 2026-11-11 | 2026-11-12
Track Joint Inspection |  |  |  | 2026-11-13 | 2026-11-13
I2S-7688-MP-74.CN.S6.50.7.2.13 | Track Joint Inspection | I.CN.50.18050 | CON - Sec.6 - I2S Route Ready to connect North and South |  | 2026-11-13
Old CRN Track (E-W) |  |  |  | 2026-09-16 | 2026-10-04
Rail Laying |  |  |  | 2026-09-16 | 2026-09-28
I2S-7688-MP-74.CN.S6.50.7.1.4 | Rail Laying | I.CN.50.12910 | CON - Sec.6 - Remove old CRN Track/Signalling (east) where NEW Bridge is going | 2026-09-16 | 2026-09-21
I2S-7688-MP-74.CN.S6.50.7.1.4 | Rail Laying | I.CN.50.18550 | CON - Sec.6 - Install Ballast Buffer Stop East of where NEW Bridge is going | 2026-09-22 | 2026-09-24
I2S-7688-MP-74.CN.S6.50.7.1.4 | Rail Laying | I.CN.50.18590 | CON - Sec.6 - Build / Join new Track to connect the 2 Turnouts | 2026-09-26 | 2026-09-28
I2S-7688-MP-74.CN.S6.50.7.1.4 | Rail Laying | I.CN.50.18600 | CON - Sec.6 - Lift in Turnout - 1 in 10.5 R250 (PEM/LEM or Crane) LH Tgt Turnout - start (SL 122A) | 2026-09-22 | 2026-09-24
I2S-7688-MP-74.CN.S6.50.7.1.4 | Rail Laying | I.CN.50.18660 | CON - Sec.6 - Lift in Turnout - 1 in 10.5 R250 (PEM/LEM or Crane) LH Tgt Turnout - finish (SL 122B) | 2026-09-22 | 2026-09-24
Corrections + Signage + Rubber Xings |  |  |  | 2026-09-29 | 2026-10-04
I2S-7688-MP-74.CN.S6.50.7.1.12 | Corrections + Signage + Rubber Xings | I.CN.50.12900 | CON - Sec.6 - Install New Catchpoints (545560) | 2026-09-29 | 2026-09-30
I2S-7688-MP-74.CN.S6.50.7.1.12 | Corrections + Signage + Rubber Xings | I.CN.50.18610 | CON - Sec.6 - Install New Signal | 2026-10-03 | 2026-10-04
I2S-7688-MP-74.CN.S6.50.7.1.12 | Corrections + Signage + Rubber Xings | I.CN.50.18620 | CON - Sec.6 - Install New Axle Counters x 3 | 2026-10-01 | 2026-10-02
Phase 4 - Possession - Mar 2027
I2S-7688-MP-74.CN.S6.50.1 | Phase 4 - Possession - Mar 2027 | I.CN.50.20100 | CON - Sec.6 - Possession Contingency (March 2027) - 30d
I2S-7688-MP-74.CN.S6.50.1 | Phase 4 - Possession - Mar 2027 | I.CN.50.20110 | CON - Sec.6 - Possession Commencement (March 2027)
I2S-7688-MP-74.CN.S6.50.1 | Phase 4 - Possession - Mar 2027 | I.CN.50.20040 | CON - Sec.6 - Target Readiness for Possession (March 2027)
Rail Safety
I2S-7688-MP-74.CN.S6.50.1.3 | Rail Safety | I.CN.50.20540 | CON - Sec.6 - Possession (March 2027)-Rail Safety
Rail Safety - hand back
I2S-7688-MP-74.CN.S6.50.1.5 | Rail Safety - hand back | I.CN.50.20550 | CON - Sec.6 - Possession (March 2027)- Track -Rail Safety hand back - WBS Summary
Phase 2+3+4 - BGW-Target Readiness for Possession Sep27 - I2S and S2P
I2S-7688-MP-74.CN.S6.50.9 | Phase 2+3+4 - BGW-Target Readiness for Possession Sep27 - I2S and S2P | I.CN.50.20650 | CON - Sec.6 - BGW - Target Readiness for Possession - I2S and S2P - Main Line works
I2S-7688-MP-74.CN.S6.50.9 | Phase 2+3+4 - BGW-Target Readiness for Possession Sep27 - I2S and S2P | I.CN.50.20660 | CON - Sec.6 - BGW - Target Readiness for Possession - I2S and S2P - Main Line works - Contingency
I2S-7688-MP-74.CN.S6.50.9 | Phase 2+3+4 - BGW-Target Readiness for Possession Sep27 - I2S and S2P | I.CN.50.20670 | CON - Sec.6 - BGW - Target Readiness for Possession - I2S and S2P - Main Line works - commencement
Phase 2+3+4 - Pre-Sep-27 works to meet Target Sep27- possession work
I2S-7688-MP-74.CN.S6.50.3 | Phase 2+3+4 - Pre-Sep-27 works to meet Target Sep27- possession work | I.CN.50.20580 | CON - Sec.6 - Track works - BGW-B94 - approx-OD
I2S-7688-MP-74.CN.S6.50.3 | Phase 2+3+4 - Pre-Sep-27 works to meet Target Sep27- possession work | I.CN.50.20590 | CON - Sec.6 - Track works - BGW-new corridor - approx-OD
I2S-7688-MP-74.CN.S6.50.3 | Phase 2+3+4 - Pre-Sep-27 works to meet Target Sep27- possession work | I.CN.50.20600 | CON - Sec.6 - Track works - BGW-CRN - approx-OD
I2S-7688-MP-74.CN.S6.50.3 | Phase 2+3+4 - Pre-Sep-27 works to meet Target Sep27- possession work | I.CN.50.20640 | CON - Sec.6 - Track works - Stockinbingal Yard - Turnout - approx-OD
I2S-7688-MP-74.CN.S6.50.3 | Phase 2+3+4 - Pre-Sep-27 works to meet Target Sep27- possession work | I.CN.50.20680 | CON - Sec.6 - Track works - BGW-CRN - LX works - East end - approx-OD
I2S-7688-MP-74.CN.S6.50.3 | Phase 2+3+4 - Pre-Sep-27 works to meet Target Sep27- possession work | I.CN.50.20690 | CON - Sec.6 - Track works - BGW-CRN - LX works - West end - approx-OD
I2S-7688-MP-74.CN.S6.50.3 | Phase 2+3+4 - Pre-Sep-27 works to meet Target Sep27- possession work | I.CN.50.20700 | CON - Sec.6 - Track works - BGW-CRN - LX works - pre-commissiong checks- approx-OD
062 - Bridges |  |  |  | 2025-09-24 | 2026-11-03
Dudauman Creek Bridge - BR711 - Standard PSC Slab Span 14m (ARTC) |  |  |  | 2025-10-02 | 2026-03-09
Preliminaries |  |  |  | 2025-10-02 | 2025-10-16
I2S-7688-MP-74.CN.S6.62.1.1 | Preliminaries | I.CN.62.17570 | CON - Sec.6 - Dudauman Ck Br - Bridge site prep /Temp Fence/Road Barriers | 2025-10-02 | 2025-10-07
I2S-7688-MP-74.CN.S6.62.1.1 | Preliminaries | I.CN.62.17580 | CON - Sec.6 - Dudauman Ck Br - Construct site access | 2025-10-08 | 2025-10-10
I2S-7688-MP-74.CN.S6.62.1.1 | Preliminaries | I.CN.62.17670 | CON - Sec.6 - Dudauman Ck Br - Construct laydown area /Causeway (inc pipes) | 2025-10-11 | 2025-10-16
Piling |  |  |  | 2025-10-17 | 2025-12-12
Platforms |  |  |  | 2025-10-17 | 2025-11-07
I2S-7688-MP-74.CN.S6.62.1.2.1 | Platforms | I.CN.62.17630 | CON - Sec.6 - Dudauman Ck Br - Excavate platform for piling pad | 2025-10-17 | 2025-10-21
I2S-7688-MP-74.CN.S6.62.1.2.1 | Platforms | I.CN.62.17680 | CON - Sec.6 - Dudauman Ck Br - Place and test platform /Piling Pad | 2025-11-06 | 2025-11-07
Drill Piles |  |  |  | 2025-11-20 | 2025-12-02
I2S-7688-MP-74.CN.S6.62.1.2.3 | Drill Piles | I.CN.62.17700 | CON - Sec.6 - Dudauman Ck Br - Abutment piling consists of 4 x 900mm dia bored concrete piles | 2025-11-21 | 2025-11-24
I2S-7688-MP-74.CN.S6.62.1.2.3 | Drill Piles | I.CN.62.19510 | CON - Sec.6 - Dudauman Ck Br - pier piling consist of 6 x 1200mm dia bored concrete piles | 2025-11-26 | 2025-12-01
I2S-7688-MP-74.CN.S6.62.1.2.3 | Drill Piles | I.CN.62.17640 | CON - Sec.6 - Dudauman Ck Br - Demobilise piling rig | 2025-12-02 | 2025-12-02
I2S-7688-MP-74.CN.S6.62.1.2.3 | Drill Piles | I.CN.62.17690 | CON - Sec.6 - Dudauman Ck Br - Mobilise piling rig | 2025-11-20 | 2025-11-20
I2S-7688-MP-74.CN.S6.62.1.2.3 | Drill Piles | I.CN.62.23000 | CON - Sec.6 - Dudauman Ck Br - Abutment piling - Milestone
Piles Concrete |  |  |  | 2025-12-03 | 2025-12-12
I2S-7688-MP-74.CN.S6.62.1.2.4 | Piles Concrete | I.CN.62.17650 | CON - Sec.6 - Dudauman Ck Br - Pour and finish concrete DN900 Pile x 10 | 2025-12-03 | 2025-12-12
Abutments |  |  |  | 2025-12-13 | 2026-01-31
I2S-7688-MP-74.CN.S6.62.1.7 | Abutments | I.CN.62.19520 | CON - Sec.6 - Dudauman Ck Br - Earthworks / Backfill Abutments | 2026-01-27 | 2026-01-31
I2S-7688-MP-74.CN.S6.62.1.7 | Abutments | I.CN.62.21410 | CON - Sec.6 - Dudauman Ck Br - FRP - Abutment 2 Headstock (Pour 2 - TBC) | 2026-01-13 | 2026-01-19
I2S-7688-MP-74.CN.S6.62.1.7 | Abutments | I.CN.62.21970 | CON - Sec.6 - Dudauman Ck Br - Concrete Curing Pre Backfill (80%)
I2S-7688-MP-74.CN.S6.62.1.7 | Abutments | I.CN.62.17760 | CON - Sec.6 - Dudauman Ck Br - FRP - Abutment 2 | 2026-01-20 | 2026-01-26
I2S-7688-MP-74.CN.S6.62.1.7 | Abutments | I.CN.62.17800 | CON - Sec.6 - Dudauman Ck Br - FRP - Abutment 1 Headstock | 2025-12-13 | 2025-12-19
I2S-7688-MP-74.CN.S6.62.1.7 | Abutments | I.CN.62.17810 | CON - Sec.6 - Dudauman Ck Br - FRP - Abutment 1 | 2025-12-20 | 2026-01-06
I2S-7688-MP-74.CN.S6.62.1.7 | Abutments | I.CN.62.17820 | CON - Sec.6 - Dudauman Ck Br - FRP - Abutment 2 Headstock (Pour 1 - TBC) | 2026-01-07 | 2026-01-12
Superstructure |  |  |  | 2026-02-01 | 2026-03-04
I2S-7688-MP-74.CN.S6.62.1.4 | Superstructure | I.CN.62.17860 | CON - Sec.6 - Dudauman Ck Br - Install handrails - super struc | 2026-02-19 | 2026-02-21
I2S-7688-MP-74.CN.S6.62.1.4 | Superstructure | I.CN.62.22750 | CON - Sec.6 - Dudauman Ck Br - Delivery / QA of Bridge Span
I2S-7688-MP-74.CN.S6.62.1.4 | Superstructure | I.CN.62.17890 | CON - Sec.6 - Dudauman Ck Br - Crane Pads for lift | 2026-02-01 | 2026-02-04
I2S-7688-MP-74.CN.S6.62.1.4 | Superstructure | I.CN.62.17900 | CON - Sec.6 - Dudauman Ck Br - Install Elastomeric bearings & components - 64 off | 2026-02-10 | 2026-02-13
I2S-7688-MP-74.CN.S6.62.1.4 | Superstructure | I.CN.62.17940 | CON - Sec.6 - Dudauman Ck Br - Install/Lift Bridge span (Standard PSC Slab Span 14m (IRPL) (6 per Span/4 Spans - T 24 | 2026-02-14 | 2026-02-18
I2S-7688-MP-74.CN.S6.62.1.4 | Superstructure | I.CN.62.19770 | CON - Sec.6 - Dudauman Ck Br - Scaffold | 2026-02-06 | 2026-02-09
I2S-7688-MP-74.CN.S6.62.1.4 | Superstructure | I.CN.62.17880 | CON - Sec.6 - Dudauman Ck Br - Install access walkways | 2026-03-01 | 2026-03-04
Approach Slab / Deck |  |  |  | 2026-02-01 | 2026-02-20
I2S-7688-MP-74.CN.S6.62.1.3 | Approach Slab / Deck | I.CN.62.17610 | CON - Sec.6 - Dudauman Ck Br - Bridging Strips, compressible fillers and isolation inserts | 2026-02-19 | 2026-02-20
I2S-7688-MP-74.CN.S6.62.1.3 | Approach Slab / Deck | I.CN.62.17830 | CON - Sec.6 - Dudauman Ck Br - Joint sealants | 2026-02-19 | 2026-02-20
I2S-7688-MP-74.CN.S6.62.1.3 | Approach Slab / Deck | I.CN.62.17840 | CON - Sec.6 - Dudauman Ck Br - Expansion joint cover plates | 2026-02-19 | 2026-02-20
I2S-7688-MP-74.CN.S6.62.1.3 | Approach Slab / Deck | I.CN.62.17960 | CON - Sec.6 - Dudauman Ck Br - FRP Approach Slab | 2026-02-01 | 2026-02-07
Bridge Finishing Works |  |  |  | 2026-02-22 | 2026-03-09
I2S-7688-MP-74.CN.S6.62.1.5 | Bridge Finishing Works | I.CN.62.22760 | CON - Sec.6 - Dudauman Ck Br - Scour Protection
I2S-7688-MP-74.CN.S6.62.1.5 | Bridge Finishing Works | I.CN.62.17870 | CON - Sec.6 - Dudauman Ck Br - FRP Footpath/Steps | 2026-02-22 | 2026-02-28
I2S-7688-MP-74.CN.S6.62.1.5 | Bridge Finishing Works | I.CN.62.19250 | CON - Sec.6 - Dudauman Ck Br - Flood protection - stone pitching (not grouted) 88m2 | 2026-03-06 | 2026-03-09
I2S-7688-MP-74.CN.S6.62.1.5 | Bridge Finishing Works | I.CN.62.17620 | CON - Sec.6 - Dudauman Ck Br - Completion |  | 2026-03-09
I2S-7688-MP-74.CN.S6.62.1.5 | Bridge Finishing Works | I.CN.62.22770 | CON - Sec.6 - Dudauman Ck Br - Install CSR Ducting
I2S-7688-MP-74.CN.S6.62.1.5 | Bridge Finishing Works | I.CN.62.22780 | CON - Sec.6 - Dudauman Ck Br - Install Handrails - bridge
Burley Griffin Way (Road over Rail) - BR710 - Standard PSC Plank Girder (RMS) - BGW |  |  |  | 2025-09-24 | 2026-11-03
BGW - Phase 1 - Pre diversion |  |  |  | 2025-09-24 | 2026-10-19
Area Preparation & Preliminaries - BGW - P1 |  |  |  | 2025-09-24 | 2025-10-10
I2S-7688-MP-74.CN.S6.62.2.9.17 | Area Preparation & Preliminaries - BGW - P1 | I.CN.62.11430 | CON - Sec.6 - BGW-P1 - Bridge - Cut - BGW West - 358ccm - S1/S2 | 2025-09-27 | 2025-09-27
I2S-7688-MP-74.CN.S6.62.2.9.17 | Area Preparation & Preliminaries - BGW - P1 | I.CN.62.11440 | CON - Sec.6 - BGW-P1 - Bridge - Cut - BGW East - 492ccm - S1/S2 | 2025-09-28 | 2025-09-28
I2S-7688-MP-74.CN.S6.62.2.9.17 | Area Preparation & Preliminaries - BGW - P1 | I.CN.62.17150 | CON - Sec.6 - BGW-P1 - Bridge - site prep /Temp Fence/Road Barriers | 2025-09-24 | 2025-09-29
I2S-7688-MP-74.CN.S6.62.2.9.17 | Area Preparation & Preliminaries - BGW - P1 | I.CN.62.17160 | CON - Sec.6 - BGW-P1 - Bridge - Construct site access | 2025-09-30 | 2025-10-04
I2S-7688-MP-74.CN.S6.62.2.9.17 | Area Preparation & Preliminaries - BGW - P1 | I.CN.62.17250 | CON - Sec.6 - BGW-P1 - Bridge - Construct laydown area /Causeway (inc pipes) | 2025-10-06 | 2025-10-10
Early Drainage - BGW - P1 |  |  |  | 2025-09-29 | 2025-12-22
I2S-7688-MP-74.CN.S6.62.2.9.19 | Early Drainage - BGW - P1 | I.CN.34.25530 | CON - Sec.6 - BGW-P1 - BGW - Swale Drainage and Piping - East of bridge | 2025-09-30 | 2025-10-30
I2S-7688-MP-74.CN.S6.62.2.9.19 | Early Drainage - BGW - P1 | I.CN.34.25540 | CON - Sec.6 - BGW-P1 - BGW - Swale Drainage and Piping - West of bridge | 2025-09-30 | 2025-11-03
Western Culverts under BGW |  |  |  | 2025-09-29 | 2025-11-02
Culvert - LX-PR37550-06 - Temp BGW - (M3-RD-0280-1 - 1x600 RCP - 17.08m) |  |  |  | 2025-10-28 | 2025-11-02
I2S-7688-MP-74.CN.S6.62.2.9.19.1.3 | Culvert - LX-PR37550-06 - Temp BGW - (M3-RD-0280-1 - 1x600 RCP - 17.08m) | I.CN.65.16960 | CON - Sec.6 - BGW-P1 - Private LX - PR37550 (Temp BGW) - Drainage - LX Culvert - Trench Excavation/ Culvert site prep | 2025-10-28 | 2025-10-29
I2S-7688-MP-74.CN.S6.62.2.9.19.1.3 | Culvert - LX-PR37550-06 - Temp BGW - (M3-RD-0280-1 - 1x600 RCP - 17.08m) | I.CN.65.16970 | CON - Sec.6 - BGW-P1 - Private LX - PR37550 (Temp BGW) - Drainage - Install 1200 RCP (8 off) 18m | 2025-10-30 | 2025-10-30
I2S-7688-MP-74.CN.S6.62.2.9.19.1.3 | Culvert - LX-PR37550-06 - Temp BGW - (M3-RD-0280-1 - 1x600 RCP - 17.08m) | I.CN.65.16980 | CON - Sec.6 - BGW-P1 - Private LX - PR37550 (Temp BGW) - Drainage - Detailed backfill - W | 2025-11-01 | 2025-11-02
I2S-7688-MP-74.CN.S6.62.2.9.19.1.3 | Culvert - LX-PR37550-06 - Temp BGW - (M3-RD-0280-1 - 1x600 RCP - 17.08m) | I.CN.65.18420 | CON - Sec.6 - BGW-P1 - BGW-P1 - Private LX - PR37550 (Temp BGW) - Excavation 1000m2 1m deep - Basin Upstream | 2025-10-30 | 2025-10-31
CULVERT ID: M3-RD-0400-1 C37.695 (10x1200 RCP - 56.12m) |  |  |  | 2025-09-29 | 2025-10-14
I2S-7688-MP-74.CN.S6.62.2.9.19.1.1 | CULVERT ID: M3-RD-0400-1 C37.695 (10x1200 RCP - 56.12m) | I.CN.34.26070 | CON - Sec.6 - BGW-P1 - Culvert : M3-RD-0400-1 - Trench ExcavaOon / Site Prep | 2025-09-29 | 2025-09-30
I2S-7688-MP-74.CN.S6.62.2.9.19.1.1 | CULVERT ID: M3-RD-0400-1 C37.695 (10x1200 RCP - 56.12m) | I.CN.34.26080 | CON - Sec.6 - BGW-P1 - Culvert : M3-RD-0400-1 - FoundaOon Treatment / Bedding | 2025-10-01 | 2025-10-02
I2S-7688-MP-74.CN.S6.62.2.9.19.1.1 | CULVERT ID: M3-RD-0400-1 C37.695 (10x1200 RCP - 56.12m) | I.CN.34.26120 | CON - Sec.6 - BGW-P1 - Culvert : M3-RD-0400-1 - Place Pipe | 2025-10-03 | 2025-10-04
I2S-7688-MP-74.CN.S6.62.2.9.19.1.1 | CULVERT ID: M3-RD-0400-1 C37.695 (10x1200 RCP - 56.12m) | I.CN.34.26140 | CON - Sec.6 - BGW-P1 - Culvert : M3-RD-0400-1 - Backfilll Pipe | 2025-10-04 | 2025-10-07
I2S-7688-MP-74.CN.S6.62.2.9.19.1.1 | CULVERT ID: M3-RD-0400-1 C37.695 (10x1200 RCP - 56.12m) | I.CN.34.26160 | CON - Sec.6 - BGW-P1 - Culvert : M3-RD-0400-1 - Place Precast Wingwall | 2025-10-08 | 2025-10-09
I2S-7688-MP-74.CN.S6.62.2.9.19.1.1 | CULVERT ID: M3-RD-0400-1 C37.695 (10x1200 RCP - 56.12m) | I.CN.34.26170 | CON - Sec.6 - BGW-P1 - Culvert : M3-RD-0400-1 - Precast stich pours for precast headwalls | 2025-10-10 | 2025-10-11
I2S-7688-MP-74.CN.S6.62.2.9.19.1.1 | CULVERT ID: M3-RD-0400-1 C37.695 (10x1200 RCP - 56.12m) | I.CN.34.26180 | CON - Sec.6 - BGW-P1 - Culvert : M3-RD-0400-1 - Detailed backfill | 2025-10-13 | 2025-10-14
I2S-7688-MP-74.CN.S6.62.2.9.19.1.1 | CULVERT ID: M3-RD-0400-1 C37.695 (10x1200 RCP - 56.12m) | I.CN.34.26175 | CON - Sec.6 - BGW-P1 - Culvert : M3-RD-0400-1 - Construct Scour protecOon | 2025-10-12 | 2025-10-12
Eastern Culverts under BGW |  |  |  | 2025-10-16 | 2025-12-22
Temporary Road Drainage Culvert - LX-PR37550-04 - (M4-RD-1450-1 - 1*1200x300 RCBC - 12m) |  |  |  | 2025-10-30 | 2025-11-08
I2S-7688-MP-74.CN.S6.62.2.9.19.18.1 | Temporary Road Drainage Culvert - LX-PR37550-04 - (M4-RD-1450-1 - 1*1200x300 RCBC - 12m) | I.CN.65.16790 | CON - Sec.6 - BGW-P1 - Private LX - PR37550-04 - Drainage - LX Culvert - Trench Excavate/ Culvert site prep | 2025-10-30 | 2025-10-31
I2S-7688-MP-74.CN.S6.62.2.9.19.18.1 | Temporary Road Drainage Culvert - LX-PR37550-04 - (M4-RD-1450-1 - 1*1200x300 RCBC - 12m) | I.CN.65.16800 | CON - Sec.6 - BGW-P1 - Private LX - PR37550-04 - Drainage - Install 1200 RCP (39 off) 95m | 2025-11-01 | 2025-11-06
I2S-7688-MP-74.CN.S6.62.2.9.19.18.1 | Temporary Road Drainage Culvert - LX-PR37550-04 - (M4-RD-1450-1 - 1*1200x300 RCBC - 12m) | I.CN.65.16810 | CON - Sec.6 - BGW-P1 - Private LX - PR37550-04 - Drainage - Detailed backfill | 2025-11-07 | 2025-11-08
I2S-7688-MP-74.CN.S6.62.2.9.19.18.1 | Temporary Road Drainage Culvert - LX-PR37550-04 - (M4-RD-1450-1 - 1*1200x300 RCBC - 12m) | I.CN.65.18410 | CON - Sec.6 - BGW-P1 - Private LX - PR37550-04 - Drainage -Excavate 1000m2 1m deep - Basin Upstream | 2025-11-01 | 2025-11-02
Temporary Road Drainage Culvert - LX-PR37550-07 - (M4-RD-1250-1 - 5*750mm HDPE - 22.03m) |  |  |  | 2025-10-26 | 2025-12-22
I2S-7688-MP-74.CN.S6.62.2.9.19.18.4 | Temporary Road Drainage Culvert - LX-PR37550-07 - (M4-RD-1250-1 - 5*750mm HDPE - 22.03m) | I.CN.31.14140 | CON - Sec.6 - BGW-P1 - Private LX - PR37550-07 - Fill - 57ccm | 2025-12-21 | 2025-12-21
I2S-7688-MP-74.CN.S6.62.2.9.19.18.4 | Temporary Road Drainage Culvert - LX-PR37550-07 - (M4-RD-1250-1 - 5*750mm HDPE - 22.03m) | I.CN.65.18430 | CON - Sec.6 - BGW-P1 - Private LX - PR37550-07 - Excavation 1000m2 1m deep - Basin Upstream | 2025-10-28 | 2025-10-29
I2S-7688-MP-74.CN.S6.62.2.9.19.18.4 | Temporary Road Drainage Culvert - LX-PR37550-07 - (M4-RD-1250-1 - 5*750mm HDPE - 22.03m) | I.CN.65.16990 | CON - Sec.6 - BGW-P1 - Private LX - PR37550-07 - Drainage - LX Culvert - Trench Excavate/ Culvert site prep | 2025-10-26 | 2025-10-27
I2S-7688-MP-74.CN.S6.62.2.9.19.18.4 | Temporary Road Drainage Culvert - LX-PR37550-07 - (M4-RD-1250-1 - 5*750mm HDPE - 22.03m) | I.CN.65.17000 | CON - Sec.6 - BGW-P1 - Private LX - PR37550-07 - Drainage - Install 1200 RCP (388 off) 947m | 2025-10-28 | 2025-12-20
I2S-7688-MP-74.CN.S6.62.2.9.19.18.4 | Temporary Road Drainage Culvert - LX-PR37550-07 - (M4-RD-1250-1 - 5*750mm HDPE - 22.03m) | I.CN.65.17010 | CON - Sec.6 - BGW-P1 - Private LX - PR37550-07- Drainage - Detailed backfill | 2025-12-21 | 2025-12-22
CULVERT ID: M3-RD-1360-1 C37.680 (27x525 RCP - 21.96m) |  |  |  | 2025-10-16 | 2025-10-28
I2S-7688-MP-74.CN.S6.62.2.9.19.18.2 | CULVERT ID: M3-RD-1360-1 C37.680 (27x525 RCP - 21.96m) | I.CN.34.25590 | CON - Sec.6 - BGW-P1 - Culvert : M3-RD-1360-1 - Trench Excavation / Site Prep | 2025-10-16 | 2025-10-17
I2S-7688-MP-74.CN.S6.62.2.9.19.18.2 | CULVERT ID: M3-RD-1360-1 C37.680 (27x525 RCP - 21.96m) | I.CN.34.25600 | CON - Sec.6 - BGW-P1 - Culvert : M3-RD-1360-1 - Foundation Treatment / Bedding | 2025-10-18 | 2025-10-19
I2S-7688-MP-74.CN.S6.62.2.9.19.18.2 | CULVERT ID: M3-RD-1360-1 C37.680 (27x525 RCP - 21.96m) | I.CN.34.25640 | CON - Sec.6 - BGW-P1 - Culvert : M3-RD-1360-1 - Place Pipe | 2025-10-20 | 2025-10-20
I2S-7688-MP-74.CN.S6.62.2.9.19.18.2 | CULVERT ID: M3-RD-1360-1 C37.680 (27x525 RCP - 21.96m) | I.CN.34.25650 | CON - Sec.6 - BGW-P1 - Culvert : M3-RD-1360-1 - Backfill Pipe | 2025-10-21 | 2025-10-21
I2S-7688-MP-74.CN.S6.62.2.9.19.18.2 | CULVERT ID: M3-RD-1360-1 C37.680 (27x525 RCP - 21.96m) | I.CN.34.25670 | CON - Sec.6 - BGW-P1 - Culvert : M3-RD-1360-1 - Place Precast Wingwall | 2025-10-22 | 2025-10-23
I2S-7688-MP-74.CN.S6.62.2.9.19.18.2 | CULVERT ID: M3-RD-1360-1 C37.680 (27x525 RCP - 21.96m) | I.CN.34.25680 | CON - Sec.6 - BGW-P1 - Culvert : M3-RD-1360-1 - Precast stich pours for precast headwalls | 2025-10-24 | 2025-10-26
I2S-7688-MP-74.CN.S6.62.2.9.19.18.2 | CULVERT ID: M3-RD-1360-1 C37.680 (27x525 RCP - 21.96m) | I.CN.34.25690 | CON - Sec.6 - BGW-P1 - Culvert : M3-RD-1360-1 - Construct Scour protection | 2025-10-27 | 2025-10-27
I2S-7688-MP-74.CN.S6.62.2.9.19.18.2 | CULVERT ID: M3-RD-1360-1 C37.680 (27x525 RCP - 21.96m) | I.CN.34.25700 | CON - Sec.6 - BGW-P1 - Culvert : M3-RD-1360-1 - Detailed backfill | 2025-10-27 | 2025-10-28
Earthworks - BGW - P1 |  |  |  | 2025-11-02 | 2026-02-28
I2S-7688-MP-74.CN.S6.62.2.9.1 | Earthworks - BGW - P1 | I.CN.62.11470 | CON - Sec.6 - BGW-P1 - Bridge - Fill - BGW West - 51,447ccm 2000 bcm/d | 2025-12-17 | 2026-02-28
I2S-7688-MP-74.CN.S6.62.2.9.1 | Earthworks - BGW - P1 | I.CN.62.11480 | CON - Sec.6 - BGW-P1 - Bridge - Fill - BGW East - 139,652ccm 2000 bcm/d | 2025-11-02 | 2026-02-03
I2S-7688-MP-74.CN.S6.62.2.9.1 | Earthworks - BGW - P1 | I.CN.62.19430 | CON - Sec.6 - BGW-P1 - Bridge - Fill - BGW North (East) - 9,504ccm 1000 bcm/d | 2026-02-04 | 2026-02-20
I2S-7688-MP-74.CN.S6.62.2.9.1 | Earthworks - BGW - P1 | I.CN.62.22970 | CON - Sec.6 - BGW-P1 - Bridge - Fill - BGW East - SS+30 to start BGW FRP
Piling - BGW - P1 |  |  |  | 2025-10-28 | 2025-12-17
Platforms |  |  |  | 2025-10-28 | 2025-11-08
I2S-7688-MP-74.CN.S6.62.2.9.2.1 | Platforms | I.CN.62.17210 | CON - Sec.6 - BGW-P1 - Bridge - Excavate/site prep for piling pad | 2025-10-28 | 2025-11-04
I2S-7688-MP-74.CN.S6.62.2.9.2.1 | Platforms | I.CN.62.17260 | CON - Sec.6 - BGW-P1 - Bridge - Build Piling Pad - 14m x 16m x 0.4m deep | 2025-11-06 | 2025-11-08
Drill Piles |  |  |  | 2025-11-09 | 2025-11-19
I2S-7688-MP-74.CN.S6.62.2.9.2.4 | Drill Piles | I.CN.62.17220 | CON - Sec.6 - BGW-P1 - Bridge - Demobilise piling rig | 2025-11-19 | 2025-11-19
I2S-7688-MP-74.CN.S6.62.2.9.2.4 | Drill Piles | I.CN.62.17270 | CON - Sec.6 - BGW-P1 - Bridge - Mobilise piling rig | 2025-11-09 | 2025-11-09
I2S-7688-MP-74.CN.S6.62.2.9.2.4 | Drill Piles | I.CN.62.17280 | CON - Sec.6 - BGW-P1 - Bridge - 8 No x 900mm dia bored concrete piles 12m deep | 2025-11-10 | 2025-11-18
I2S-7688-MP-74.CN.S6.62.2.9.2.4 | Drill Piles | I.CN.62.23010 | CON - Sec.6 - BGW-P1 - Bridge - 8 No x 900mm dia bored concrete piles 12m deep - Milestone
Piles Concrete |  |  |  | 2025-11-20 | 2025-12-17
I2S-7688-MP-74.CN.S6.62.2.9.2.5 | Piles Concrete | I.CN.62.21000 | CON - Sec.6 - BGW-P1 - Bridge - Abutment 1 Pile Cap - 15m3 | 2025-11-24 | 2025-11-29
I2S-7688-MP-74.CN.S6.62.2.9.2.5 | Piles Concrete | I.CN.62.21040 | CON - Sec.6 - BGW-P1 - Bridge - Detailed Earthworks Pier Pile Cap Abutment 2 | 2025-12-08 | 2025-12-11
I2S-7688-MP-74.CN.S6.62.2.9.2.5 | Piles Concrete | I.CN.62.21050 | CON - Sec.6 - BGW-P1 - Bridge - Abutment 2 Pile Cap - 15m3 | 2025-12-12 | 2025-12-17
I2S-7688-MP-74.CN.S6.62.2.9.2.5 | Piles Concrete | I.CN.62.20990 | CON - Sec.6 - BGW-P1 - Bridge - Detailed Earthworks Pile Cap Abutment 1 - 55m3 | 2025-11-20 | 2025-11-23
RE Wall Footing - BGW - P1 |  |  |  | 2026-03-01 | 2026-04-20
I2S-7688-MP-74.CN.S6.62.2.9.3 | RE Wall Footing - BGW - P1 | I.CN.62.21150 | CON - Sec.6 - BGW-P1 - Bridge - FRP [40] MPa/20 Retaining Wall Footing base RE Walls East Abut | 2026-03-01 | 2026-03-06
I2S-7688-MP-74.CN.S6.62.2.9.3 | RE Wall Footing - BGW - P1 | I.CN.62.21200 | CON - Sec.6 - BGW-P1 - Bridge - FRP [40] MPa/20 Retaining Wall Footing base RE Walls West Abutment - 25m | 2026-04-09 | 2026-04-13
I2S-7688-MP-74.CN.S6.62.2.9.3 | RE Wall Footing - BGW - P1 | I.CN.62.21430 | CON - Sec.6 - BGW-P1 - Bridge - FRP - Deflection Wall East RE Wall - 32m3 | 2026-03-07 | 2026-03-19
I2S-7688-MP-74.CN.S6.62.2.9.3 | RE Wall Footing - BGW - P1 | I.CN.62.21420 | CON - Sec.6 - BGW-P1 - Bridge - FRP - Deflection Wall West RE Wall- 32m3 | 2026-04-14 | 2026-04-20
Columns - BGW - P1 |  |  |  | 2025-11-30 | 2026-01-05
I2S-7688-MP-74.CN.S6.62.2.9.4 | Columns - BGW - P1 | I.CN.62.21020 | CON - Sec.6 - BGW-P1 - Bridge - FRP - pour, 40 MPa/20 in pier (4no x 0.9m dia cols x 6.6m ht) Abutment 1 | 2025-11-30 | 2025-12-04
I2S-7688-MP-74.CN.S6.62.2.9.4 | Columns - BGW - P1 | I.CN.62.21030 | CON - Sec.6 - BGW-P1 - Bridge - S&I Column sleeves to columns (4off) Abutment 1 | 2025-12-06 | 2025-12-07
I2S-7688-MP-74.CN.S6.62.2.9.4 | Columns - BGW - P1 | I.CN.62.21060 | CON - Sec.6 - BGW-P1 - Bridge - FRP - [40] MPa/20 in abutment 2 (4no x 0.9m dia cols x 6.6m ht) Abutment | 2025-12-18 | 2025-12-22
I2S-7688-MP-74.CN.S6.62.2.9.4 | Columns - BGW - P1 | I.CN.62.21070 | CON - Sec.6 - BGW-P1 - Bridge - S&I Column sleeves to columns (4off) Abutment 2 | 2025-12-23 | 2026-01-05
RE Walls - BGW - P1 |  |  |  | 2026-03-20 | 2026-05-12
I2S-7688-MP-74.CN.S6.62.2.9.5 | RE Walls - BGW - P1 | I.CN.62.21160 | CON - Sec.6 - BGW-P1 - Bridge - Retaining Wall Walls North RE Wall | 2026-03-20 | 2026-03-26
I2S-7688-MP-74.CN.S6.62.2.9.5 | RE Walls - BGW - P1 | I.CN.62.21210 | CON - Sec.6 - BGW-P1 - Bridge - Retaining Wall Walls South RE Wall | 2026-04-21 | 2026-04-27
I2S-7688-MP-74.CN.S6.62.2.9.5 | RE Walls - BGW - P1 | I.CN.62.21250 | CON - Sec.6 - BGW-P1 - Bridge - Install Handrails MSS Retaining Walls | 2026-05-10 | 2026-05-12
Abutment A Headstock - BGW - P1 |  |  |  | 2026-01-06 | 2026-04-08
I2S-7688-MP-74.CN.S6.62.2.9.6 | Abutment A Headstock - BGW - P1 | I.CN.62.21100 | CON - Sec.6 - BGW-P1 - Bridge - Cast inplace headstock - North Abutment - 15m3 | 2026-01-12 | 2026-01-17
I2S-7688-MP-74.CN.S6.62.2.9.6 | Abutment A Headstock - BGW - P1 | I.CN.62.21120 | CON - Sec.6 - BGW-P1 - Bridge - Cast inplace wingwalls North Abutment - 5m3 | 2026-01-23 | 2026-01-28
I2S-7688-MP-74.CN.S6.62.2.9.6 | Abutment A Headstock - BGW - P1 | I.CN.62.21170 | CON - Sec.6 - BGW-P1 - Bridge - Cast inplace back wall - North Abutment | 2026-03-27 | 2026-03-29
I2S-7688-MP-74.CN.S6.62.2.9.6 | Abutment A Headstock - BGW - P1 | I.CN.62.21180 | CON - Sec.6 - BGW-P1 - Bridge - Abutment Precast Panels North Abutment Capping | 2026-03-30 | 2026-04-02
I2S-7688-MP-74.CN.S6.62.2.9.6 | Abutment A Headstock - BGW - P1 | I.CN.62.21190 | CON - Sec.6 - BGW-P1 - Bridge - Mechanically Stabilised Earth Walls (MSE) Walls Construction North Abutment | 2026-04-03 | 2026-04-08
I2S-7688-MP-74.CN.S6.62.2.9.6 | Abutment A Headstock - BGW - P1 | I.CN.62.21080 | CON - Sec.6 - BGW-P1 - Bridge - Site prep Abutment Footings | 2026-01-06 | 2026-01-07
I2S-7688-MP-74.CN.S6.62.2.9.6 | Abutment A Headstock - BGW - P1 | I.CN.62.21090 | CON - Sec.6 - BGW-P1 - Bridge - Detailed Earthworks Abutments (2off) - 34m3 | 2026-01-08 | 2026-01-11
Abutment B Headstock - BGW - P1 |  |  |  | 2026-01-18 | 2026-05-09
I2S-7688-MP-74.CN.S6.62.2.9.7 | Abutment B Headstock - BGW - P1 | I.CN.62.21110 | CON - Sec.6 - BGW-P1 - Bridge - Cast inplace headstock - South Abutment - 15m3 | 2026-01-18 | 2026-01-22
I2S-7688-MP-74.CN.S6.62.2.9.7 | Abutment B Headstock - BGW - P1 | I.CN.62.21130 | CON - Sec.6 - BGW-P1 - Bridge - Cast inplace wingwalls South Abutment - 5m3 | 2026-01-29 | 2026-02-02
I2S-7688-MP-74.CN.S6.62.2.9.7 | Abutment B Headstock - BGW - P1 | I.CN.62.21140 | CON - Sec.6 - BGW-P1 - Bridge - FRP - Form, reinforce, pour, [40] MPa/20 in Restraint Blocks - 8m3 | 2026-02-03 | 2026-02-08
I2S-7688-MP-74.CN.S6.62.2.9.7 | Abutment B Headstock - BGW - P1 | I.CN.62.21220 | CON - Sec.6 - BGW-P1 - Bridge - Cast inplace back wall - South Abutment | 2026-04-28 | 2026-04-30
I2S-7688-MP-74.CN.S6.62.2.9.7 | Abutment B Headstock - BGW - P1 | I.CN.62.21230 | CON - Sec.6 - BGW-P1 - Bridge -Abutment Precast Panels South Abutment Capping | 2026-05-01 | 2026-05-04
I2S-7688-MP-74.CN.S6.62.2.9.7 | Abutment B Headstock - BGW - P1 | I.CN.62.21240 | CON - Sec.6 - BGW-P1 - Bridge - Mechanically Stabilised Earth Walls (MSE) Walls Construction South Abutme | 2026-05-05 | 2026-05-09
Install Bearing and Girders - BGW - P1 |  |  |  | 2026-04-14 | 2026-05-14
I2S-7688-MP-74.CN.S6.62.2.9.8 | Install Bearing and Girders - BGW - P1 | I.CN.62.21260 | CON - Sec.6 - BGW-P1 - Bridge - delivery of concrete deck / super T girder/ I beam unit to site | 2026-04-14 | 2026-04-15
I2S-7688-MP-74.CN.S6.62.2.9.8 | Install Bearing and Girders - BGW - P1 | I.CN.62.21280 | CON - Sec.6 - BGW-P1 - Bridge - Install/Lift Bridge span (Standard PSC Plank Girder (RMS) (15 off (1 per | 2026-05-10 | 2026-05-14
Bridge Slab - BGW - P1 |  |  |  | 2026-05-16 | 2026-05-31
I2S-7688-MP-74.CN.S6.62.2.9.9 | Bridge Slab - BGW - P1 | I.CN.62.22950 | CON - Sec.6 - BGW-P1 - Bridge - Bridge Deck - QDPE waterproofing
I2S-7688-MP-74.CN.S6.62.2.9.9 | Bridge Slab - BGW - P1 | I.CN.62.21290 | CON - Sec.6 - BGW-P1 - Bridge - Infill precast panels between plank beams to deck - 99m2 | 2026-05-16 | 2026-05-21
I2S-7688-MP-74.CN.S6.62.2.9.9 | Bridge Slab - BGW - P1 | I.CN.62.21300 | CON - Sec.6 - BGW-P1 - Bridge - Bridge Deck - 51m3 | 2026-05-22 | 2026-05-31
I2S-7688-MP-74.CN.S6.62.2.9.9 | Bridge Slab - BGW - P1 | I.CN.62.22930 | CON - Sec.6 - BGW-P1 - Bridge - Bridge Deck - 28d curing
Approach Slab & Expansion Joints - BGW - P1 |  |  |  | 2026-06-01 | 2026-10-19
I2S-7688-MP-74.CN.S6.62.2.9.10 | Approach Slab & Expansion Joints - BGW - P1 | I.CN.62.21320 | CON - Sec.6 - BGW-P1 - Bridge - Approach Transition Slab North (West) - 32m3 | 2026-06-01 | 2026-06-08
I2S-7688-MP-74.CN.S6.62.2.9.10 | Approach Slab & Expansion Joints - BGW - P1 | I.CN.62.17540 | CON - Sec.6 - BGW-P1 - Bridge - FRP - Approach Slab - East (final) - m3 | 2026-10-14 | 2026-10-19
I2S-7688-MP-74.CN.S6.62.2.9.10 | Approach Slab & Expansion Joints - BGW - P1 | I.CN.62.22940 | CON - Sec.6 - BGW-P1 - Bridge - FRP - Approach Slab - East (final) - 28d curing
I2S-7688-MP-74.CN.S6.62.2.9.10 | Approach Slab & Expansion Joints - BGW - P1 | I.CN.62.22960 | CON - Sec.6 - BGW-P1 - Bridge - FRP - Approach Slab - East (final) - QDPE waterproofing
Drainage - BGW - P1 |  |  |  | 2026-07-17 | 2026-08-04
I2S-7688-MP-74.CN.S6.62.2.9.11 | Drainage - BGW - P1 | I.CN.62.21380 | CON - Sec.6 - BGW-P1 - Bridge - Batter Slopes Shaping, trimming & compacting -960m2 | 2026-07-17 | 2026-07-23
I2S-7688-MP-74.CN.S6.62.2.9.11 | Drainage - BGW - P1 | I.CN.62.21390 | CON - Sec.6 - BGW-P1 - Bridge - Wing Walls - North side 2 No. - 11m3 | 2026-07-24 | 2026-07-29
I2S-7688-MP-74.CN.S6.62.2.9.11 | Drainage - BGW - P1 | I.CN.62.21400 | CON - Sec.6 - BGW-P1 - Bridge - Wing Walls - South side 2 No. - 11m3 | 2026-07-31 | 2026-08-04
Bridge Barriers - BGW - P1 |  |  |  | 2026-06-17 | 2026-07-19
I2S-7688-MP-74.CN.S6.62.2.9.12 | Bridge Barriers - BGW - P1 | I.CN.62.21340 | CON - Sec.6 - BGW-P1 - Bridge - FRP - Form, reo, pour, MPa/20 Con.Barriers - N/S - 90m | 2026-06-17 | 2026-06-26
I2S-7688-MP-74.CN.S6.62.2.9.12 | Bridge Barriers - BGW - P1 | I.CN.62.21360 | CON - Sec.6 - BGW-P1 - Bridge - Precast Concrete Parapet Panels - 56m | 2026-07-10 | 2026-07-16
I2S-7688-MP-74.CN.S6.62.2.9.12 | Bridge Barriers - BGW - P1 | I.CN.62.21370 | CON - Sec.6 - BGW-P1 - Bridge - Install Twin Rail Barriers- 46m | 2026-07-17 | 2026-07-19
I2S-7688-MP-74.CN.S6.62.2.9.12 | Bridge Barriers - BGW - P1 | I.CN.62.21440 | CON - Sec.6 - BGW-P1 - Bridge - FRP - Form, reo, pour, MPa/20 Con.Barriers - S/S - 90m3 | 2026-06-27 | 2026-07-06
Throw Screens - BGW - P1 |  |  |  | 2026-07-07 | 2026-07-09
I2S-7688-MP-74.CN.S6.62.2.9.13 | Throw Screens - BGW - P1 | I.CN.62.21350 | CON - Sec.6 - BGW-P1 - Bridge - Install Steel anti-throw screen - 112m2 | 2026-07-07 | 2026-07-09
Asphalt - BGW - P1 |  |  |  | 2026-06-17 | 2026-06-26
I2S-7688-MP-74.CN.S6.62.2.9.14 | Asphalt - BGW - P1 | A1030 | CON - Sec.6 - BGW-P1 - Bridge - Asphalt part 1 | 2026-06-17 | 2026-06-26
Line Marking/Signs - BGW - P1 |  |  |  | 2026-06-27 | 2026-07-06
I2S-7688-MP-74.CN.S6.62.2.9.15 | Line Marking/Signs - BGW - P1 | I.CN.62.19440 | CON - Sec.6 - BGW-P1 - Bridge - Linemarking part 1 | 2026-06-27 | 2026-07-02
I2S-7688-MP-74.CN.S6.62.2.9.15 | Line Marking/Signs - BGW - P1 | I.CN.62.19460 | CON - Sec.6 - BGW-P1 - Bridge - Signs | 2026-07-03 | 2026-07-06
Tie-in - New to Old - BGW Bridge - BGW - P1 |  |  |  | 2026-08-04 | 2026-08-10
I2S-7688-MP-74.CN.S6.62.2.9.16 | Tie-in - New to Old - BGW Bridge - BGW - P1 | I.CN.44.13560 | CON - Sec.6 - BGW-P1 - Tie in New BGW to Old BGW - western end - Nightworks | 2026-08-06 | 2026-08-10
I2S-7688-MP-74.CN.S6.62.2.9.16 | Tie-in - New to Old - BGW Bridge - BGW - P1 | I.CN.62.19450 | CON - Sec.6 - BGW-P1 - Completion of Burley Griffin Way Bridge |  | 2026-08-04
I2S-7688-MP-74.CN.S6.62.2.9.16 | Tie-in - New to Old - BGW Bridge - BGW - P1 | I.CN.44.13570 | CON - Sec.6 - BGW-P1 - Tie in Temp BGW diversion to BGW south of exsting LX - Nightworks
I2S-7688-MP-74.CN.S6.62.2.9.16 | Tie-in - New to Old - BGW Bridge - BGW - P1 | I.CN.44.13580 | CON - Sec.6 - BGW-P1 - Traffic Switch onto New BGW temporary diversion - operational
BGW - Phase 2 - Post diversion |  |  |  | 2026-09-22 | 2026-11-03
Demobilisation - BGW - P2 |  |  |  | 2026-10-24 | 2026-11-03
I2S-7688-MP-74.CN.S6.62.2.10.18 | Demobilisation - BGW - P2 | I.CN.44.13550 | CON - Sec.6 - BGW-P2 - New Burley Griffin Way road tie in to Hibernia Street - North of Lx - East Side | 2026-10-24 | 2026-11-03
Earthworks - BGW - P2 |  |  |  | 2026-09-22 | 2026-10-13
I2S-7688-MP-74.CN.S6.62.2.10.8 | Earthworks - BGW - P2 | I.CN.62.11050 | CON - Sec.6 - BGW-P2 - Bridge - Fill - BGW East infill - 22,376ccm (20%) | 2026-09-22 | 2026-10-13
Road - BGW - P2
I2S-7688-MP-74.CN.S6.62.2.10.1 | Road - BGW - P2 | I.CN.62.22920 | CON - Sec.6 - BGW-P2 - Bridge - Pavement Road on Troy Street
Asphalt - BGW - P2 |  |  |  | 2026-10-20 | 2026-10-23
I2S-7688-MP-74.CN.S6.62.2.10.3 | Asphalt - BGW - P2 | I.CN.62.11060 | CON - Sec.6 - BGW-P2 - Bridge - Asphalt part 2 | 2026-10-20 | 2026-10-23
Line Marking/Signs - BGW - P2 |  |  |  | 2026-10-24 | 2026-10-30
I2S-7688-MP-74.CN.S6.62.2.10.4 | Line Marking/Signs - BGW - P2 | I.CN.62.11070 | CON - Sec.6 - BGW-P2 - Bridge - Linemarking part2 | 2026-10-24 | 2026-10-30
065 - Crossings |  |  |  | 2025-09-13 | 2026-10-06
Private LX - Morton (PR39450) - Passive / Private - RX-2 |  |  |  | 2025-09-13 | 2026-03-08
Civils |  |  |  | 2025-12-19 | 2026-03-01
I2S-7688-MP-74.CN.S6.65.1.1 | Civils | I.CN.11.14130 | CON - Sec.6 - Private LX - Morton (PR39450) - Clear and Grub | 2025-12-19 | 2025-12-19
I2S-7688-MP-74.CN.S6.65.1.1 | Civils | I.CN.65.13610 | CON - Sec.6 - Private LX - Morton (PR39450) - Civil Works complete |  | 2026-03-01
Earthworks/Drainage |  |  |  | 2025-09-13 | 2025-09-28
Culvert ID : E7-RD-456912-1 / Type : 1*750mm HDPE / Ch39391 (14.63m each)
I2S-7688-MP-74.CN.S6.65.1.5.2 | Culvert ID : E7-RD-456912-1 / Type : 1*750mm HDPE / Ch39391 (14.63m each) | I.CN.34.29290 | CON - Sec.6 - Culvert : E6-RD-456912-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S6.65.1.5.2 | Culvert ID : E7-RD-456912-1 / Type : 1*750mm HDPE / Ch39391 (14.63m each) | I.CN.34.29300 | CON - Sec.6 - Culvert : E6-RD-456912-1 - Headwall installation
I2S-7688-MP-74.CN.S6.65.1.5.2 | Culvert ID : E7-RD-456912-1 / Type : 1*750mm HDPE / Ch39391 (14.63m each) | I.CN.34.29310 | CON - Sec.6 - Culvert : E6-RD-456912-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S6.65.1.5.2 | Culvert ID : E7-RD-456912-1 / Type : 1*750mm HDPE / Ch39391 (14.63m each) | I.CN.34.29320 | CON - Sec.6 - Culvert : E6-RD-456912-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S6.65.1.5.2 | Culvert ID : E7-RD-456912-1 / Type : 1*750mm HDPE / Ch39391 (14.63m each) | I.CN.34.29330 | CON - Sec.6 - Culvert : E6-RD-456912-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S6.65.1.5.2 | Culvert ID : E7-RD-456912-1 / Type : 1*750mm HDPE / Ch39391 (14.63m each) | I.CN.34.29350 | CON - Sec.6 - Culvert : E6-RD-456912-1 - Construct Scour Protection
I2S-7688-MP-74.CN.S6.65.1.5.2 | Culvert ID : E7-RD-456912-1 / Type : 1*750mm HDPE / Ch39391 (14.63m each) | I.CN.34.29280 | CON - Sec.6 - Culvert : E6-RD-456912-1 - Site Prep / Detail Excavation
Culvert ID : E6-RD-455940-1 / Type : 2*900mm HDPE / Ch38440 (13.48m each) |  |  |  | 2025-09-13 | 2025-09-28
I2S-7688-MP-74.CN.S6.65.1.5.1 | Culvert ID : E6-RD-455940-1 / Type : 2*900mm HDPE / Ch38440 (13.48m each) | I.CN.34.19710 | CON - Sec.6 - Culvert : E6-RD-455940-1 - Site Prep / Detail Excavation | 2025-09-13 | 2025-09-14
I2S-7688-MP-74.CN.S6.65.1.5.1 | Culvert ID : E6-RD-455940-1 / Type : 2*900mm HDPE / Ch38440 (13.48m each) | I.CN.34.19720 | CON - Sec.6 - Culvert : E6-RD-455940-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2025-09-16 | 2025-09-17
I2S-7688-MP-74.CN.S6.65.1.5.1 | Culvert ID : E6-RD-455940-1 / Type : 2*900mm HDPE / Ch38440 (13.48m each) | I.CN.34.19760 | CON - Sec.6 - Culvert : E6-RD-455940-1 - Headwall Installation | 2025-09-18 | 2025-09-19
I2S-7688-MP-74.CN.S6.65.1.5.1 | Culvert ID : E6-RD-455940-1 / Type : 2*900mm HDPE / Ch38440 (13.48m each) | I.CN.34.19800 | CON - Sec.6 - Culvert : E6-RD-455940-1 - Headwall Cut-off Wall Installation (FRP) | 2025-09-24 | 2025-09-26
I2S-7688-MP-74.CN.S6.65.1.5.1 | Culvert ID : E6-RD-455940-1 / Type : 2*900mm HDPE / Ch38440 (13.48m each) | I.CN.34.19820 | CON - Sec.6 - Culvert : E6-RD-455940-1 - Construct Scour Protection | 2025-09-27 | 2025-09-28
I2S-7688-MP-74.CN.S6.65.1.5.1 | Culvert ID : E6-RD-455940-1 / Type : 2*900mm HDPE / Ch38440 (13.48m each) | I.CN.34.19770 | CON - Sec.6 - Culvert : E6-RD-455940-1 - HDPE / RCP Pipe Lay & Backfill | 2025-09-19 | 2025-09-21
I2S-7688-MP-74.CN.S6.65.1.5.1 | Culvert ID : E6-RD-455940-1 / Type : 2*900mm HDPE / Ch38440 (13.48m each) | I.CN.34.19790 | CON - Sec.6 - Culvert : E6-RD-455940-1 - Headwall Stitch Pour | 2025-09-22 | 2025-09-23
Culvert ID : E6-RA-455915-1 / Type : 1*600 HDPE / Ch 38438 (12.58m)
I2S-7688-MP-74.CN.S6.65.1.5.3 | Culvert ID : E6-RA-455915-1 / Type : 1*600 HDPE / Ch 38438 (12.58m) | I.CN.34.32270 | CON - Sec.6 - Culvert : E6-RA-455915-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S6.65.1.5.3 | Culvert ID : E6-RA-455915-1 / Type : 1*600 HDPE / Ch 38438 (12.58m) | I.CN.34.32280 | CON - Sec.6 - Culvert : E6-RA-455915-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S6.65.1.5.3 | Culvert ID : E6-RA-455915-1 / Type : 1*600 HDPE / Ch 38438 (12.58m) | I.CN.34.32290 | CON - Sec.6 - Culvert : E6-RA-455915-1 - Headwall installation
I2S-7688-MP-74.CN.S6.65.1.5.3 | Culvert ID : E6-RA-455915-1 / Type : 1*600 HDPE / Ch 38438 (12.58m) | I.CN.34.32300 | CON - Sec.6 - Culvert : E6-RA-455915-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S6.65.1.5.3 | Culvert ID : E6-RA-455915-1 / Type : 1*600 HDPE / Ch 38438 (12.58m) | I.CN.34.32310 | CON - Sec.6 - Culvert : E6-RA-455915-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S6.65.1.5.3 | Culvert ID : E6-RA-455915-1 / Type : 1*600 HDPE / Ch 38438 (12.58m) | I.CN.34.32320 | CON - Sec.6 - Culvert : E6-RA-455915-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S6.65.1.5.3 | Culvert ID : E6-RA-455915-1 / Type : 1*600 HDPE / Ch 38438 (12.58m) | I.CN.34.32330 | CON - Sec.6 - Culvert : E6-RA-455915-1 - Construct Scour Protection
Culvert ID : E6-RD-456890-1 / Type : 2*1200*450 RCBC / Ch 39390 (12.00m)
I2S-7688-MP-74.CN.S6.65.1.5.4 | Culvert ID : E6-RD-456890-1 / Type : 2*1200*450 RCBC / Ch 39390 (12.00m) | I.CN.65.19771 | CON - Sec.6 - Culvert : E6-RD-456890-1 - LX Culvert - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S6.65.1.5.4 | Culvert ID : E6-RD-456890-1 / Type : 2*1200*450 RCBC / Ch 39390 (12.00m) | I.CN.65.19781 | CON - Sec.6 - Culvert : E6-RD-456890-1 - Struc fill Placement (250mm)
I2S-7688-MP-74.CN.S6.65.1.5.4 | Culvert ID : E6-RD-456890-1 / Type : 2*1200*450 RCBC / Ch 39390 (12.00m) | I.CN.65.19861 | CON - Sec.6 - Culvert : E6-RD-456890-1 - Construct Scour protection
I2S-7688-MP-74.CN.S6.65.1.5.4 | Culvert ID : E6-RD-456890-1 / Type : 2*1200*450 RCBC / Ch 39390 (12.00m) | I.CN.65.19791 | CON - Sec.6 - Culvert : E6-RD-456890-1 - Blinding placement (50mm)
I2S-7688-MP-74.CN.S6.65.1.5.4 | Culvert ID : E6-RD-456890-1 / Type : 2*1200*450 RCBC / Ch 39390 (12.00m) | I.CN.65.19801 | CON - Sec.6 - Culvert : E6-RD-456890-1 - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.CN.S6.65.1.5.4 | Culvert ID : E6-RD-456890-1 / Type : 2*1200*450 RCBC / Ch 39390 (12.00m) | I.CN.65.19811 | CON - Sec.6 - Culvert : E6-RD-456890-1 - 7 day Curing
I2S-7688-MP-74.CN.S6.65.1.5.4 | Culvert ID : E6-RD-456890-1 / Type : 2*1200*450 RCBC / Ch 39390 (12.00m) | I.CN.65.19821 | CON - Sec.6 - Culvert : E6-RD-456890-1 - Place RCBC crown units
I2S-7688-MP-74.CN.S6.65.1.5.4 | Culvert ID : E6-RD-456890-1 / Type : 2*1200*450 RCBC / Ch 39390 (12.00m) | I.CN.65.19831 | CON - Sec.6 - Culvert : E6-RD-456890-1 - Place Precast headwall and precast stich pours
I2S-7688-MP-74.CN.S6.65.1.5.4 | Culvert ID : E6-RD-456890-1 / Type : 2*1200*450 RCBC / Ch 39390 (12.00m) | I.CN.65.19841 | CON - Sec.6 - Culvert : E6-RD-456890-1 - Pre-cast RCBC completion (Seal joints)
I2S-7688-MP-74.CN.S6.65.1.5.4 | Culvert ID : E6-RD-456890-1 / Type : 2*1200*450 RCBC / Ch 39390 (12.00m) | I.CN.65.19851 | CON - Sec.6 - Culvert : E6-RD-456890-1 - Detail backfill
Culvert ID : E6-RD-456911-1 / Type : 4*1200*600 RCBC / Ch 39401 (14.40m)
I2S-7688-MP-74.CN.S6.65.1.5.5 | Culvert ID : E6-RD-456911-1 / Type : 4*1200*600 RCBC / Ch 39401 (14.40m) | I.CN.34.32400 | CON - Sec.6 - Culvert : E6-RD-456911-1 - Place Pre-cast Wingwalls and Stich Pour
I2S-7688-MP-74.CN.S6.65.1.5.5 | Culvert ID : E6-RD-456911-1 / Type : 4*1200*600 RCBC / Ch 39401 (14.40m) | I.CN.34.32410 | CON - Sec.6 - Culvert : E6-RD-456911-1 - Pre-cast RCBC completion (Seal joints)
I2S-7688-MP-74.CN.S6.65.1.5.5 | Culvert ID : E6-RD-456911-1 / Type : 4*1200*600 RCBC / Ch 39401 (14.40m) | I.CN.34.32360 | CON - Sec.6 - Culvert : E6-RD-456911-1 - Blinding placement (50mm)
I2S-7688-MP-74.CN.S6.65.1.5.5 | Culvert ID : E6-RD-456911-1 / Type : 4*1200*600 RCBC / Ch 39401 (14.40m) | I.CN.34.32420 | CON - Sec.6 - Culvert : E6-RD-456911-1 - Detail backfill
I2S-7688-MP-74.CN.S6.65.1.5.5 | Culvert ID : E6-RD-456911-1 / Type : 4*1200*600 RCBC / Ch 39401 (14.40m) | I.CN.34.32430 | CON - Sec.6 - Culvert : E6-RD-456911-1 - Construct Scour protection
I2S-7688-MP-74.CN.S6.65.1.5.5 | Culvert ID : E6-RD-456911-1 / Type : 4*1200*600 RCBC / Ch 39401 (14.40m) | I.CN.34.32340 | CON - Sec.6 - Culvert : E6-RD-456911-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S6.65.1.5.5 | Culvert ID : E6-RD-456911-1 / Type : 4*1200*600 RCBC / Ch 39401 (14.40m) | I.CN.34.32350 | CON - Sec.6 - Culvert : E6-RD-456911-1 - Struc fill Placement (250mm)
I2S-7688-MP-74.CN.S6.65.1.5.5 | Culvert ID : E6-RD-456911-1 / Type : 4*1200*600 RCBC / Ch 39401 (14.40m) | I.CN.34.32370 | CON - Sec.6 - Culvert : E6-RD-456911-1 - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.CN.S6.65.1.5.5 | Culvert ID : E6-RD-456911-1 / Type : 4*1200*600 RCBC / Ch 39401 (14.40m) | I.CN.34.32380 | CON - Sec.6 - Culvert : E6-RD-456911-1 - 7 day Curing
I2S-7688-MP-74.CN.S6.65.1.5.5 | Culvert ID : E6-RD-456911-1 / Type : 4*1200*600 RCBC / Ch 39401 (14.40m) | I.CN.34.32390 | CON - Sec.6 - Culvert : E6-RD-456911-1 - Place RCBC crown units
Roadworks |  |  |  | 2025-12-20 | 2026-01-05
I2S-7688-MP-74.CN.S6.65.1.6 | Roadworks | I.CN.65.13640 | CON - Sec.6 - Private LX - Morton (PR39450) - Prime & Cure - Pavement type B sealed (620m2) | 2025-12-23 | 2025-12-23
I2S-7688-MP-74.CN.S6.65.1.6 | Roadworks | I.CN.65.13650 | CON - Sec.6 - Private LX - Morton (PR39450) - Seal /linemarking | 2026-01-05 | 2026-01-05
I2S-7688-MP-74.CN.S6.65.1.6 | Roadworks | I.CN.65.13540 | CON - Sec.6 - Private LX - Morton (PR39450) - Earthworks | 2025-12-20 | 2025-12-21
I2S-7688-MP-74.CN.S6.65.1.6 | Roadworks | I.CN.65.13550 | CON - Sec.6 - Private LX - Morton (PR39450) - Pavement type A Unsealed (290 m2) | 2025-12-22 | 2025-12-22
I2S-7688-MP-74.CN.S6.65.1.6 | Roadworks | I.CN.65.13630 | CON - Sec.6 - Private LX - Morton (PR39450) - Batter face area (470 m3) | 2025-12-23 | 2025-12-23
Trackworks |  |  |  | 2026-03-02 | 2026-03-04
I2S-7688-MP-74.CN.S6.65.1.7 | Trackworks | I.CN.65.13570 | CON - Sec.6 - Private LX - Morton (PR39450) - Place and compact ballast between foundation block (after road | 2026-03-03 | 2026-03-03
I2S-7688-MP-74.CN.S6.65.1.7 | Trackworks | I.CN.65.13580 | CON - Sec.6 - Private LX - Morton (PR39450) - Tie-in works to foundation block | 2026-03-04 | 2026-03-04
I2S-7688-MP-74.CN.S6.65.1.7 | Trackworks | I.CN.65.13560 | CON - Sec.6 - Private LX - Morton (PR39450) - Place Foundation Block and T-Kerbstone | 2026-03-02 | 2026-03-02
Ancillary |  |  |  | 2026-03-06 | 2026-03-08
I2S-7688-MP-74.CN.S6.65.1.8 | Ancillary | I.CN.65.13590 | CON - Sec.6 - Private LX - Morton (PR39450) - Install Fencing | 2026-03-06 | 2026-03-06
I2S-7688-MP-74.CN.S6.65.1.8 | Ancillary | I.CN.65.13600 | CON - Sec.6 - Private LX - Morton (PR39450) - Install Signage | 2026-03-07 | 2026-03-07
I2S-7688-MP-74.CN.S6.65.1.8 | Ancillary | I.CN.65.13620 | CON - Sec.6 - Private LX - Morton (PR39450) - Install Gates | 2026-03-08 | 2026-03-08
Commissioning |  |  |  | 2026-03-08 | 2026-03-08
I2S-7688-MP-74.CN.S6.65.1.4 | Commissioning | I.CN.65.13680 | CON - Sec.6 - Private LX - Morton (PR39450) - Open |  | 2026-03-08
Private LX - (038300) - LX for CRN works across old BGW road |  |  |  | 2025-10-24 | 2026-10-06
Civils |  |  |  | 2025-10-24 | 2025-10-24
I2S-7688-MP-74.CN.S6.65.4.1 | Civils | I.CN.11.14260 | CON - Sec.6 - Private LX - PR38300 - Clear and Grub | 2025-10-24 | 2025-10-24
Earthworks/Drainage |  |  |  | 2025-10-29 | 2025-11-11
CULVERT ID: C38.3 / 9*1200 RC / M3-RD-0400 (56.12m each) |  |  |  | 2025-10-29 | 2025-11-11
I2S-7688-MP-74.CN.S6.65.4.5.4 | CULVERT ID: C38.3 / 9*1200 RC / M3-RD-0400 (56.12m each) | I.CN.34.26540 | CON - Sec.6 - Culvert : C38.300 - Construct Scour protection | 2025-11-10 | 2025-11-11
I2S-7688-MP-74.CN.S6.65.4.5.4 | CULVERT ID: C38.3 / 9*1200 RC / M3-RD-0400 (56.12m each) | I.CN.34.26430 | CON - Sec.6 - Culvert : C38.300 - Site Prep / Detail Excavation | 2025-10-29 | 2025-10-30
I2S-7688-MP-74.CN.S6.65.4.5.4 | CULVERT ID: C38.3 / 9*1200 RC / M3-RD-0400 (56.12m each) | I.CN.34.26440 | CON - Sec.6 - Culvert : C38.300 - Struc fill (150mm) / Bedding (150mm) Placement | 2025-10-31 | 2025-10-31
I2S-7688-MP-74.CN.S6.65.4.5.4 | CULVERT ID: C38.3 / 9*1200 RC / M3-RD-0400 (56.12m each) | I.CN.34.26480 | CON - Sec.6 - Culvert : C38.300 - Headwall Installation | 2025-11-01 | 2025-11-01
I2S-7688-MP-74.CN.S6.65.4.5.4 | CULVERT ID: C38.3 / 9*1200 RC / M3-RD-0400 (56.12m each) | I.CN.34.26500 | CON - Sec.6 - Culvert : C38.300 - HDPE / RCP pipe lay & backfill | 2025-11-03 | 2025-11-03
I2S-7688-MP-74.CN.S6.65.4.5.4 | CULVERT ID: C38.3 / 9*1200 RC / M3-RD-0400 (56.12m each) | I.CN.34.26510 | CON - Sec.6 - Culvert : C38.300 - Headwall stitch pour | 2025-11-04 | 2025-11-06
I2S-7688-MP-74.CN.S6.65.4.5.4 | CULVERT ID: C38.3 / 9*1200 RC / M3-RD-0400 (56.12m each) | I.CN.34.26520 | CON - Sec.6 - Culvert : C38.300 - Headwall cut-off wall Installation (FRP) | 2025-11-07 | 2025-11-08
Roadworks |  |  |  | 2025-11-12 | 2025-11-19
I2S-7688-MP-74.CN.S6.65.4.6 | Roadworks | I.CN.65.16890 | CON - Sec.6 - Private LX - PR38300 - Civil Works complete |  | 2025-11-14
I2S-7688-MP-74.CN.S6.65.4.6 | Roadworks | I.CN.65.16820 | CON - Sec.6 - Private LX - PR38300 - Road Earthworks | 2025-11-12 | 2025-11-13
I2S-7688-MP-74.CN.S6.65.4.6 | Roadworks | I.CN.65.16830 | CON - Sec.6 - Private LX - PR38300 - Pavement type A Unsealed ( m2) | 2025-11-14 | 2025-11-16
I2S-7688-MP-74.CN.S6.65.4.6 | Roadworks | I.CN.65.16910 | CON - Sec.6 - Private LX - PR38300 - Batter face area ( m3) | 2025-11-14 | 2025-11-16
I2S-7688-MP-74.CN.S6.65.4.6 | Roadworks | I.CN.65.16920 | CON - Sec.6 - Private LX - PR38300 - Prime & Cure - Pavement type B sealed ( m2) | 2025-11-17 | 2025-11-18
I2S-7688-MP-74.CN.S6.65.4.6 | Roadworks | I.CN.65.16930 | CON - Sec.6 - Private LX - PR38300 - Seal /linemarking /signs | 2025-11-17 | 2025-11-19
Trackworks |  |  |  | 2025-11-16 | 2025-11-18
I2S-7688-MP-74.CN.S6.65.4.7 | Trackworks | I.CN.65.16840 | CON - Sec.6 - Private LX - PR38300 - Place Foundation Block and T-Kerbstone | 2025-11-16 | 2025-11-16
I2S-7688-MP-74.CN.S6.65.4.7 | Trackworks | I.CN.65.16850 | CON - Sec.6 - Private LX - PR38300 - Place and compact ballast between foundation block (after road | 2025-11-17 | 2025-11-17
I2S-7688-MP-74.CN.S6.65.4.7 | Trackworks | I.CN.65.16860 | CON - Sec.6 - Private LX - PR38300 - Tie-in works to foundation block | 2025-11-18 | 2025-11-18
Ancillary |  |  |  | 2025-11-19 | 2025-11-21
I2S-7688-MP-74.CN.S6.65.4.8 | Ancillary | I.CN.65.16870 | CON - Sec.6 - Private LX - PR38300 - Install Fencing | 2025-11-19 | 2025-11-19
I2S-7688-MP-74.CN.S6.65.4.8 | Ancillary | I.CN.65.16880 | CON - Sec.6 - Private LX - PR38300 - Install Signage | 2025-11-20 | 2025-11-20
I2S-7688-MP-74.CN.S6.65.4.8 | Ancillary | I.CN.65.16900 | CON - Sec.6 - Private LX - PR38300 - Install Gates /Booms | 2025-11-21 | 2025-11-21
Commissioning |  |  |  | 2025-11-17 | 2026-10-06
I2S-7688-MP-74.CN.S6.65.4.4 | Commissioning | I.CN.74.15130 | CON - Sec.6 - Sig - Decommission old Level Crossing across Hibernia/BGW St | 2026-09-14 | 2026-10-06
I2S-7688-MP-74.CN.S6.65.4.4 | Commissioning | I.CN.74.15140 | CON - Sec.6 - Sig - Transfer booms / put New into operation - POSS | 2026-09-12 | 2026-09-13
I2S-7688-MP-74.CN.S6.65.4.4 | Commissioning | I.CN.74.15150 | CON - Sec.6 - Sig - Leave New LX redundant |  | 2025-11-27
I2S-7688-MP-74.CN.S6.65.4.4 | Commissioning | I.CN.72.15430 | CON - Sec.6 - Sig - Prepare for Cable route/ Axle counter/light /booms | 2025-11-17 | 2025-11-26
I2S-7688-MP-74.CN.S6.65.4.4 | Commissioning | I.CN.65.16950 | CON - Sec.6 - Private LX - PR38300 - Finished but leave redundant (and bagged) |  | 2025-11-21
I2S-7688-MP-74.CN.S6.65.4.4 | Commissioning | I.CN.74.15120 | CON - Sec.6 - Sig - Commission New Level Crossing over exisitng BGW road / then Bag up - POSS | 2026-09-13 | 2026-09-14
I2S-7688-MP-74.CN.S6.65.4.4 | Commissioning | I.CN.74.15960 | CON - Sec.6 - Sig - New Level Crossing Commission - BGW road - operational - permanent
Fauna Crossing |  |  |  | 2026-09-13 | 2026-09-16
I2S-7688-MP-74.CN.S6.65.3 | Fauna Crossing | I.CN.65.12850 | CON - Sec.6 - Install fauna crossing, [2 x pole foundations /cure - CH40150] | 2026-09-13 | 2026-09-14
I2S-7688-MP-74.CN.S6.65.3 | Fauna Crossing | I.CN.65.17850 | CON - Sec.6 - Install fauna crossing, [2 x poles with rope bridge - CH40150] | 2026-09-16 | 2026-09-16
072 - Signalling |  |  |  | 2025-10-22 | 2027-04-03
Signals |  |  |  | 2026-04-24 | 2027-03-14
I2S-7688-MP-74.CN.S6.72.9 | Signals | I.CN.72.16800 | CON - Sec.6 - Sig - IRPL Approval of IWP (Sec.6)
I2S-7688-MP-74.CN.S6.72.9 | Signals | I.CN.72.15500 | CON - Sec.6 - Sig - Install New Main Signals (1 off) 455180 | 2026-04-24 | 2026-04-29
I2S-7688-MP-74.CN.S6.72.9 | Signals | I.CN.72.15510 | CON - Sec.6 - Sig - Install New Main Signals (1 off) 457070 | 2026-05-03 | 2026-05-12
I2S-7688-MP-74.CN.S6.72.9 | Signals | I.CN.72.15520 | CON - Sec.6 - Sig - Install New Main Signals (5 off) 459500 to end | 2026-05-13 | 2026-05-14
I2S-7688-MP-74.CN.S6.72.9 | Signals | I.CN.72.15700 | CON - Sec.6 - Sig - Remove 11 Main Signals | 2027-03-13 | 2027-03-14
I2S-7688-MP-74.CN.S6.72.9 | Signals | I.CN.72.16840 | CON - Sec.6 - Sig - Prepare & Submit of IWP (Sec.6)
Points |  |  |  | 2026-04-30 | 2027-03-14
I2S-7688-MP-74.CN.S6.72.10 | Points | I.CN.72.15380 | CON - Sec.6 - Sig - Install New Points Machine (6 off) (New) 459500 to end | 2026-04-30 | 2026-05-14
I2S-7688-MP-74.CN.S6.72.10 | Points | I.CN.72.15390 | CON - Sec.6 - Sig - Install New Points Machine (2 off) (New) 455050 | 2026-05-24 | 2026-06-03
I2S-7688-MP-74.CN.S6.72.10 | Points | I.CN.72.15710 | CON - Sec.6 - Sig - Remove 1 Ground Frame Point | 2027-03-13 | 2027-03-14
I2S-7688-MP-74.CN.S6.72.10 | Points | I.CN.72.15750 | CON - Sec.6 - Sig - Remove 1 D84M MKIII Point | 2027-03-14 | 2027-03-14
I2S-7688-MP-74.CN.S6.72.10 | Points | I.CN.72.15760 | CON - Sec.6 - Sig - Remove 1 EOL Point | 2027-03-14 | 2027-03-14
Axle |  |  |  | 2026-04-28 | 2027-03-15
I2S-7688-MP-74.CN.S6.72.3 | Axle | I.CN.72.15410 | CON - Sec.6 - Sig - Install New Axle Counter (1 off) 454970 | 2026-04-28 | 2026-05-11
I2S-7688-MP-74.CN.S6.72.3 | Axle | I.CN.72.15780 | CON - Sec.6 - Sig - Remove 8 GAC Axle | 2027-03-13 | 2027-03-15
I2S-7688-MP-74.CN.S6.72.3 | Axle | I.CN.72.16400 | CON - Sec.6 - Sig - Install New Axle Counter (2 off) 455100
I2S-7688-MP-74.CN.S6.72.3 | Axle | I.CN.72.16440 | CON - Sec.6 - Sig - Install New Axle Counter (1 off) 456900
I2S-7688-MP-74.CN.S6.72.3 | Axle | I.CN.72.16450 | CON - Sec.6 - Sig - Install New Axle Counter (23 off) 459500 to end
Track |  |  |  | 2026-05-21 | 2027-03-15
I2S-7688-MP-74.CN.S6.72.4 | Track | I.CN.72.15420 | CON - Sec.6 - Sig - Install New BLR DC Track (3 off) - SL113 - 454.160 (453500 to to 454030) | 2026-05-21 | 2026-05-24
I2S-7688-MP-74.CN.S6.72.4 | Track | I.CN.72.15720 | CON - Sec.6 - Sig - Remove 8 BLR DC Track - SL113 | 2027-03-13 | 2027-03-15
I2S-7688-MP-74.CN.S6.72.4 | Track | I.CN.72.16060 | CON - Sec.6 - Sig - existing JSSR Track (5 off) - SL113 - 454.160 (453500 to to 454030) | 2026-06-01 | 2026-06-06
DW Loc |  |  |  | 2026-05-12 | 2027-03-14
I2S-7688-MP-74.CN.S6.72.6 | DW Loc | I.CN.72.15730 | CON - Sec.6 - Sig - Remove 3 DW Locs | 2027-03-13 | 2027-03-14
I2S-7688-MP-74.CN.S6.72.6 | DW Loc | I.CN.72.15440 | CON - Sec.6 - Sig - Install New DW Locations (5 off) (32840 to 456716) | 2026-05-12 | 2026-05-19
Building |  |  |  | 2027-03-13 | 2027-03-14
I2S-7688-MP-74.CN.S6.72.7 | Building | I.CN.72.16120 | CON - Sec.6 - Sig - Install New SER/Building (1 off) (New) 455000
I2S-7688-MP-74.CN.S6.72.7 | Building | I.CN.72.16130 | CON - Sec.6 - Sig - Install New SER/Building (2 off) (New) 459500 to end
I2S-7688-MP-74.CN.S6.72.7 | Building | I.CN.72.16140 | CON - Sec.6 - Sig - Site terminations and SAT of location cases
I2S-7688-MP-74.CN.S6.72.7 | Building | I.CN.72.15740 | CON - Sec.6 - Sig - Remove 1 Building | 2027-03-13 | 2027-03-14
Cabling |  |  |  | 2025-10-22 | 2027-04-03
I2S-7688-MP-74.CN.S6.72.11 | Cabling | I.CN.72.15960 | CON - Sec.6 - CSR - Main Cable Route - MCR - Pull Cable | 2026-03-20 | 2026-04-08
I2S-7688-MP-74.CN.S6.72.11 | Cabling | I.CN.74.14940 | CON - Sec.6 - CSR - CRN (1200m/70m per day) | 2025-10-22 | 2025-11-10
I2S-7688-MP-74.CN.S6.72.11 | Cabling | I.CN.74.14980 | CON - Sec.6 - CSR- CRN - Pull cable | 2025-11-30 | 2025-12-06
I2S-7688-MP-74.CN.S6.72.11 | Cabling | I.CN.72.15800 | CON - Sec.6 - Sig - Cable Removal | 2027-03-14 | 2027-04-03
Misc Equipment |  |  |  | 2025-11-17 | 2026-03-21
I2S-7688-MP-74.CN.S6.72.1 | Misc Equipment | I.CN.74.1610 | CON - Sec.6 - Sig - Install Track Side Equipment (speed signs/motor generators/notice boards) - 37300 - 38000 | 2026-02-17 | 2026-03-01
I2S-7688-MP-74.CN.S6.72.1 | Misc Equipment | I.CN.74.14960 | CON - Sec.6 - Sig - Install Track Side Equipment (speed signs/motor generators/notice boards) -CRN | 2025-11-17 | 2025-11-29
I2S-7688-MP-74.CN.S6.72.1 | Misc Equipment | I.CN.74.15000 | CON - Sec.6 - Sig - Install Track Side Equipment (speed signs/motor generators/notice boards) - 38000 - 42600 | 2026-03-09 | 2026-03-21
Location Case
I2S-7688-MP-74.CN.S6.72.5 | Location Case | I.CN.72.16780 | CON - Sec.6 - Sig - Install New Location Case (2 off) (New) 459500 to end
I2S-7688-MP-74.CN.S6.72.5 | Location Case | I.CN.72.16420 | CON - Sec.6 - Sig - Install New Location Case (1 off) (New) 457070
074 - Power Supply and Distributions |  |  |  | 2025-11-11 | 2026-04-01
CSR |  |  |  | 2025-11-11 | 2026-04-01
MCR |  |  |  | 2025-11-18 | 2026-03-28
I2S-7688-MP-74.CN.S6.74.2.1 | MCR | I.CN.74.15020 | CON - Sec.6 - CSR - Install Main CSR - Up Across Dudauman Creek Bridge | 2026-03-26 | 2026-03-28
I2S-7688-MP-74.CN.S6.74.2.1 | MCR | I.CN.74.15030 | CON - Sec.6 - CSR - Install Main CSR - Up Main 455500 (Dudauman Br) to 456900 (LX) (1400m) | 2026-01-06 | 2026-02-13
I2S-7688-MP-74.CN.S6.74.2.1 | MCR | I.CN.74.14370 | CON - Sec.6 - CSR - Install Main CSR - Dn Main 455050 to 455250 Across BGW (200m) | 2025-11-18 | 2025-11-22
I2S-7688-MP-74.CN.S6.74.2.1 | MCR | I.CN.74.14400 | CON - Sec.6 - CSR - Install Main CSR - Up Main 456900 to 459500 (Subject to Survey) (2600m) | 2026-03-07 | 2026-03-09
I2S-7688-MP-74.CN.S6.74.2.1 | MCR | I.CN.74.14920 | CON - Sec.6 - CSR - Install Main CSR - Up Main 455250 to 455400 (Dudauman) (150m) | 2026-03-11 | 2026-03-19
LCR |  |  |  | 2026-02-28 | 2026-04-01
I2S-7688-MP-74.CN.S6.74.2.2 | LCR | I.CN.74.14570 | CON - Sec.6 - CSR - Construct Local Cable Route - LCR Up - 455010 | 2026-02-28 | 2026-03-02
I2S-7688-MP-74.CN.S6.74.2.2 | LCR | I.CN.74.14580 | CON - Sec.6 - CSR - Construct Local Cable Route - LCR Dn - 455070 | 2026-03-03 | 2026-03-04
I2S-7688-MP-74.CN.S6.74.2.2 | LCR | I.CN.74.14670 | CON - Sec.6 - CSR - Construct Local Cable Route - LCR Dn - 454850 | 2026-03-29 | 2026-03-31
I2S-7688-MP-74.CN.S6.74.2.2 | LCR | I.CN.74.15010 | CON - Sec.6 - CSR - Construct Local Cable Route - LCR Dn - 454960 | 2026-03-29 | 2026-04-01
I2S-7688-MP-74.CN.S6.74.2.2 | LCR | I.CN.74.15920 | CON - Sec.6 - CSR - Construct Local Cable Route - LCR Dn - 455110
I2S-7688-MP-74.CN.S6.74.2.2 | LCR | I.CN.74.15930 | CON - Sec.6 - CSR - Construct Local Cable Route - LCR Dn - 455200
I2S-7688-MP-74.CN.S6.74.2.2 | LCR | I.CN.74.15940 | CON - Sec.6 - CSR - Construct Local Cable Route - LCR Up - 457070
ULX |  |  |  | 2025-11-11 | 2026-03-22
I2S-7688-MP-74.CN.S6.74.2.3 | ULX | I.CN.74.14640 | CON - Sec.6 - CSR - Main ULX - Across LX Up - 456900 POSS | 2026-03-21 | 2026-03-22
I2S-7688-MP-74.CN.S6.74.2.3 | ULX | I.CN.74.14600 | CON - Sec.6 - CSR - Local ULX Across BGW - 455000 to 455050 POSS | 2026-03-07 | 2026-03-08
I2S-7688-MP-74.CN.S6.74.2.3 | ULX | I.CN.74.14610 | CON - Sec.6 - CSR - Local ULX Across Across Track - 455250 POSS | 2026-03-09 | 2026-03-10
I2S-7688-MP-74.CN.S6.74.2.3 | ULX | I.CN.74.14950 | CON - Sec.6 - CSR - Local ULX Across Creek 455200 to 455250 POSS | 2025-11-11 | 2025-11-17
085 - Landscaping
I2S-7688-MP-74.CN.S6.85 | 085 - Landscaping | I.CN.85.13970 | CON - Sec.6 - Landscaping - Re-spread Topsoil - Ch37300-42600
I2S-7688-MP-74.CN.S6.85 | 085 - Landscaping | I.CN.85.13980 | CON - Sec.6 - Landscaping - Hydroseed Application - Ch37300-42600
Section 5 - GF section (28301 - 37300) |  |  |  | 2025-07-12 | 2026-12-13
Section 5 Key Milestones
I2S-7688-MP-74.CN.S5.1 | Section 5 Key Milestones | I.CN.22.13580 | CON - Sec.5 - Construction Completion Milestone (Public Utilities)
I2S-7688-MP-74.CN.S5.1 | Section 5 Key Milestones | I.CN.22.13670 | CON - Sec.5 - Construction Completion Milestone (Earthworks)
I2S-7688-MP-74.CN.S5.1 | Section 5 Key Milestones | I.CN.22.13680 | CON - Sec.5 - Construction Completion Milestone (Rail Capping)
I2S-7688-MP-74.CN.S5.1 | Section 5 Key Milestones | I.CN.22.13630 | CON - Sec.5 - Construction Completion Milestone (Drainage)
I2S-7688-MP-74.CN.S5.1 | Section 5 Key Milestones | I.CN.22.13590 | CON - Sec.5 - Construction Completion Milestone (Fencing)
I2S-7688-MP-74.CN.S5.1 | Section 5 Key Milestones | I.CN.22.13640 | CON - Sec.5 - Construction Completion Milestone (Access Roads)
I2S-7688-MP-74.CN.S5.1 | Section 5 Key Milestones | I.CN.22.13690 | CON - Sec.5 - Construction Completion Milestone (Trackwork)
I2S-7688-MP-74.CN.S5.1 | Section 5 Key Milestones | I.CN.22.13660 | CON - Sec.5 - Construction Completion Milestone (Bridges)
I2S-7688-MP-74.CN.S5.1 | Section 5 Key Milestones | I.CN.22.13700 | CON - Sec.5 - Construction Completion Milestone (Crossings)
I2S-7688-MP-74.CN.S5.1 | Section 5 Key Milestones | I.CN.22.13620 | CON - Sec.5 - Construction Completion Milestone (Signalling)
I2S-7688-MP-74.CN.S5.1 | Section 5 Key Milestones | I.CN.22.13600 | CON - Sec.5 - Construction Completion Milestone (Rail Communications)
I2S-7688-MP-74.CN.S5.1 | Section 5 Key Milestones | I.CN.22.13610 | CON - Sec.5 - Construction Completion Milestone (Power Supply and Distributions)
I2S-7688-MP-74.CN.S5.1 | Section 5 Key Milestones | I.CN.22.13650 | CON - Sec.5 - Construction Completion Milestone (Landscaping)
I2S-7688-MP-74.CN.S5.1 | Section 5 Key Milestones | I.CN.22.14450 | CON - Sec.5 - Construction Completion Milestone (Culverts)
I2S-7688-MP-74.CN.S5.1 | Section 5 Key Milestones | I.CN.22.14750 | CON - Sec.5 - Commence Construction Milestone - FDVR & CEMP approved - 1st A9 submission - approval
I2S-7688-MP-74.CN.S5.1 | Section 5 Key Milestones | I.CN.22.14760 | CON - Sec.5 - Commence Construction Milestone - CEMP approved
Site Access |  |  |  | 2025-07-12 | 2025-07-12
I2S-7688-MP-74.CN.S5.00 | Site Access | I.CN.11.14010 | CON - Sec.5 - Site Gate Access Required by/ Granted - Gate 7 (30050) | 2025-07-12 | 2025-07-12
I2S-7688-MP-74.CN.S5.00 | Site Access | I.CN.11.14020 | CON - Sec.5 - Site Gate Access Required by/ Granted - Gate 7A (34600) | 2025-07-12 | 2025-07-12
022 - Public Utilities |  |  |  | 2025-08-13 | 2025-09-09
Telstra |  |  |  | 2025-09-03 | 2025-09-09
I2S-7688-MP-74.CN.S5.22.1 | Telstra | I.CN.22.5500 | CON - Util - Sec.5 - TE02-10 Telstra - Relocation West Side Dudauman Road - Ch30860 (136m) | 2025-09-03 | 2025-09-09
I2S-7688-MP-74.CN.S5.22.1 | Telstra | I.CN.22.13380 | CON - Util - Sec.5 - TE02-11 Telstra - Relocation South Side Corbys Lane - Ch33767 (72m) | 2025-09-03 | 2025-09-09
Essential Energy (EE) |  |  |  | 2025-08-13 | 2025-08-26
ECN-099001 ELO-10 |  |  |  | 2025-08-13 | 2025-08-19
I2S-7688-MP-74.CN.S5.22.4.1 | ECN-099001 ELO-10 | I.CN.22.5830 | CON - Util - Sec.5 - ELO-10 - Essential Energy Relocate 11kV West Side Dudauman Road - Ch33042 (167m) | 2025-08-13 | 2025-08-19
I2S-7688-MP-74.CN.S5.22.4.1 | ECN-099001 ELO-10 | I.CN.22.5840 | CON - Util - Sec.5 - ELO-10 - Commence Work on site
I2S-7688-MP-74.CN.S5.22.4.1 | ECN-099001 ELO-10 | I.CN.22.5850 | CON - Util - Sec.5 - ELO-10 - Outage & Cutover
I2S-7688-MP-74.CN.S5.22.4.1 | ECN-099001 ELO-10 | I.CN.22.5860 | CON - Util - Sec.5 - ECN-099001 Works Complete
ECN-099002 ELO-04 |  |  |  | 2025-08-20 | 2025-08-26
I2S-7688-MP-74.CN.S5.22.4.2 | ECN-099002 ELO-04 | I.CN.22.13390 | CON - Util - Sec.5 - ELO-04 - Essential Energy Relocate 11kV East Side Dudauman Road - Ch35642 (124m) | 2025-08-20 | 2025-08-26
I2S-7688-MP-74.CN.S5.22.4.2 | ECN-099002 ELO-04 | I.CN.22.14620 | CON - Util - Sec.5 - ELO-04 - Commence Work on site
I2S-7688-MP-74.CN.S5.22.4.2 | ECN-099002 ELO-04 | I.CN.22.14630 | CON - Util - Sec.5 - ELO-04 - Outage & Cutover
I2S-7688-MP-74.CN.S5.22.4.2 | ECN-099002 ELO-04 | I.CN.22.14640 | CON - Util - Sec.5 - ECN-099002 Works Complete
031 - Earthworks
I2S-7688-MP-74.CN.S5.31 | 031 - Earthworks | I.CN.31.88290 | CON - Sec.5 - Temporary Creek Crossing - Powder Horn Creek for traffic
Clearing & Grubbing -Stage -2
Tree Felling and Lopping
I2S-7688-MP-74.CN.S5.31.3.1 | Tree Felling and Lopping | I.CN.11.15700 | CON - Sec.5 - Tree Felling & Lopping
Broad Acre Clearing and Mulching
I2S-7688-MP-74.CN.S5.31.3.2 | Broad Acre Clearing and Mulching | I.CN.11.15710 | CON - Sec.5 - Broad Acre Clearing & Mulching
Grubbing of Stumps
I2S-7688-MP-74.CN.S5.31.3.3 | Grubbing of Stumps | I.CN.11.15720 | CON - Sec.5 - Grubbing of Stumps
Miscellaneous Works
I2S-7688-MP-74.CN.S5.31.3.4 | Miscellaneous Works | I.CN.11.15730 | CON - Sec.5 - Hollow/Habitat Tree Mgmt
I2S-7688-MP-74.CN.S5.31.3.4 | Miscellaneous Works | I.CN.11.15740 | CON - Sec.5 - Habitat Relocations
Cut
Cut Open Drains
I2S-7688-MP-74.CN.S5.31.1.8 | Cut Open Drains | I.CN.31.86620 | CON - Sec.5 - FILL 36 - Cut.OD Soil : Ch28515 to 29975 (495 bcm - 175 per/d)
I2S-7688-MP-74.CN.S5.31.1.8 | Cut Open Drains | I.CN.31.86650 | CON - Sec.5 - FILL 37 - Cut.OD Soil : Ch30865 to 31702 (1633 bcm - 175 per/d)
I2S-7688-MP-74.CN.S5.31.1.8 | Cut Open Drains | I.CN.31.86710 | CON - Sec.5 - FILL 39 - Cut.OD Soil : Ch33876 to 34635 (663 bcm - 175 per/d)
I2S-7688-MP-74.CN.S5.31.1.8 | Cut Open Drains | I.CN.31.86770 | CON - Sec.5 - FILL 42 - Cut.OD Soil : Ch36255 to 37055 (239 bcm - 175 per/d)
I2S-7688-MP-74.CN.S5.31.1.8 | Cut Open Drains | I.CN.31.86830 | CON - Sec.5 - FILL 40 - Cut.OD Soil : Ch35075 to 35935 (463 bcm - 175 per/d)
I2S-7688-MP-74.CN.S5.31.1.8 | Cut Open Drains | I.CN.31.83820 | CON - Sec.5 - CUT 36 - Cut.OD Soil : Ch33273 to 33642 (884 bcm - 175 per/d)
I2S-7688-MP-74.CN.S5.31.1.8 | Cut Open Drains | I.CN.31.83870 | CON - Sec.5 - CUT 37 - Cut.OD Soil : Ch33642 to 33876 (488 bcm - 175 per/d)
I2S-7688-MP-74.CN.S5.31.1.8 | Cut Open Drains | I.CN.31.83920 | CON - Sec.5 - CUT 38 - Cut.OD Soil : Ch34635 to 35075 (1460 bcm - 175 per/d)
I2S-7688-MP-74.CN.S5.31.1.8 | Cut Open Drains | I.CN.31.83940 | CON - Sec.5 - CUT 38 - Cut.Uns Dam : Ch34635 to 35075 (3200 bcm - 500 per/d)
I2S-7688-MP-74.CN.S5.31.1.8 | Cut Open Drains | I.CN.31.83970 | CON - Sec.5 - CUT 39 - Cut.OD Soil : Ch37055 to 37287 (412 bcm - 175 per/d)
Cut Soil to EW
I2S-7688-MP-74.CN.S5.31.1.3 | Cut Soil to EW | I.CN.31.86610 | CON - Sec.5 - FILL 36 - Cut.Soil to EW : Ch28515 to 29975 (636 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.1.3 | Cut Soil to EW | I.CN.31.86640 | CON - Sec.5 - FILL 37 - Cut.Soil to EW : Ch30865 to 31702 (313 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.1.3 | Cut Soil to EW | I.CN.31.86670 | CON - Sec.5 - FILL 38 - Cut.Soil to EW : Ch32313 to 33273 (1333 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.1.3 | Cut Soil to EW | I.CN.31.86700 | CON - Sec.5 - FILL 39 - Cut.Soil to EW : Ch33876 to 34635 (543 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.1.3 | Cut Soil to EW | I.CN.31.86760 | CON - Sec.5 - FILL 42 - Cut.Soil to EW : Ch36255 to 37055 (185 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.1.3 | Cut Soil to EW | I.CN.31.86790 | CON - Sec.5 - FILL 41 - Cut.Soil to EW : Ch35935 to 36267 (366 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.1.3 | Cut Soil to EW | I.CN.31.86820 | CON - Sec.5 - FILL 40 - Cut.Soil to EW : Ch35075 to 35935 (1871 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.1.3 | Cut Soil to EW | I.CN.31.83860 | CON - Sec.5 - CUT 36 - Cut.Soil to EW : Ch33273 to 33642 (1474 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.1.3 | Cut Soil to EW | I.CN.31.83810 | CON - Sec.5 - CUT 35 - Cut.Soil to EW : Ch31702 to 32313 (9050 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.1.3 | Cut Soil to EW | I.CN.31.83910 | CON - Sec.5 - CUT 37 - Cut.Soil to EW : Ch33642 to 33876 (611 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.1.3 | Cut Soil to EW | I.CN.31.83960 | CON - Sec.5 - CUT 38 - Cut.Soil to EW : Ch34635 to 35075 (4146 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.1.3 | Cut Soil to EW | I.CN.31.84010 | CON - Sec.5 - CUT 39 - Cut.Soil to EW : Ch37055 to 37287 (2292 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.1.3 | Cut Soil to EW | I.CN.31.88310 | CON - Sec.5 - FILL 36 - Cut.Soil to EW : Ch28515 to 29975 (636 bcm - 2500 per/d) - Milestone
Cut Rock
I2S-7688-MP-74.CN.S5.31.1.4 | Cut Rock | I.CN.31.86630 | CON - Sec.5 - FILL 36 - Cut.HW Dacite : Ch28515 to 29975 (855 bcm - 2000 per/d)
Fill
Fill Open Drains
I2S-7688-MP-74.CN.S5.31.2.16 | Fill Open Drains | I.CN.31.85700 | CON - Sec.5 - FILL 42 - Fill.OD Fill : Ch36255 to 37055 (29 bcm - 500 per/d)
I2S-7688-MP-74.CN.S5.31.2.16 | Fill Open Drains | I.CN.31.85740 | CON - Sec.5 - FILL 43 - Fill.OD Fill : Ch37287 to 38060 (382 bcm - 500 per/d)
I2S-7688-MP-74.CN.S5.31.2.16 | Fill Open Drains | I.CN.31.85620 | CON - Sec.5 - FILL 40 - Fill.OD Fill : Ch35075 to 35935 (34 bcm - 500 per/d)
I2S-7688-MP-74.CN.S5.31.2.16 | Fill Open Drains | I.CN.31.88110 | CON - Sec.5 - CUT 37 - Fill.OD Fill : Ch33642 to 33876 (177 bcm - 500 per/d)
I2S-7688-MP-74.CN.S5.31.2.16 | Fill Open Drains | I.CN.31.88150 | CON - Sec.5 - CUT 38 - Fill.OD Fill : Ch34635 to 35075 (225 bcm - 500 per/d)
I2S-7688-MP-74.CN.S5.31.2.16 | Fill Open Drains | I.CN.31.88190 | CON - Sec.5 - CUT 39 - Fill.OD Fill : Ch37055 to 37287 (195 bcm - 500 per/d)
I2S-7688-MP-74.CN.S5.31.2.16 | Fill Open Drains | I.CN.31.88070 | CON - Sec.5 - CUT 36 - Fill.OD Fill : Ch33273 to 33642 (559 bcm - 500 per/d)
Fill Lower
I2S-7688-MP-74.CN.S5.31.2.3 | Fill Lower | I.CN.31.85680 | CON - Sec.5 - FILL 41 - Fill.H3 - Lower : Ch35935 to 36267 (11966 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.3 | Fill Lower | I.CN.31.85760 | CON - Sec.5 - FILL 43 - Fill.H3 - Lower : Ch37287 to 38060 (4220 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.3 | Fill Lower | I.CN.31.85480 | CON - Sec.5 - FILL 36 - Fill.H3 - Lower : Ch28515 to 29975 (120493 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.3 | Fill Lower | I.CN.31.85560 | CON - Sec.5 - FILL 38 - Fill.H3 - Lower : Ch32313 to 33273 (209 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.3 | Fill Lower | I.CN.31.85600 | CON - Sec.5 - FILL 39 - Fill.H3 - Lower : Ch33876 to 34635 (4391 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.3 | Fill Lower | I.CN.31.85640 | CON - Sec.5 - FILL 40 - Fill.H3 - Lower : Ch35075 to 35935 (5337 bcm - 2500 per/d)
Fill Mid
I2S-7688-MP-74.CN.S5.31.2.1 | Fill Mid | I.CN.31.85670 | CON - Sec.5 - FILL 41 - Fill.H2 - Mid : Ch35935 to 36267 (1496 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.1 | Fill Mid | I.CN.31.85710 | CON - Sec.5 - FILL 42 - Fill.H2 - Mid : Ch36255 to 37055 (3942 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.1 | Fill Mid | I.CN.31.85750 | CON - Sec.5 - FILL 43 - Fill.H2 - Mid : Ch37287 to 38060 (2478 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.1 | Fill Mid | I.CN.31.85470 | CON - Sec.5 - FILL 36 - Fill.H2 - Mid : Ch28515 to 29975 (20320 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.1 | Fill Mid | I.CN.31.85510 | CON - Sec.5 - FILL 37 - Fill.H2 - Mid : Ch30865 to 31702 (1681 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.1 | Fill Mid | I.CN.31.85550 | CON - Sec.5 - FILL 38 - Fill.H2 - Mid : Ch32313 to 33273 (4227 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.1 | Fill Mid | I.CN.31.85590 | CON - Sec.5 - FILL 39 - Fill.H2 - Mid : Ch33876 to 34635 (7602 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.1 | Fill Mid | I.CN.31.85630 | CON - Sec.5 - FILL 40 - Fill.H2 - Mid : Ch35075 to 35935 (9018 bcm - 2500 per/d)
Fill Upper
I2S-7688-MP-74.CN.S5.31.2.4 | Fill Upper | I.CN.31.85650 | CON - Sec.5 - FILL 41 - Fill.H1 - Upper : Ch35935 to 36267 (3190 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.4 | Fill Upper | I.CN.31.85690 | CON - Sec.5 - FILL 42 - Fill.H1 - Upper : Ch36255 to 37055 (9897 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.4 | Fill Upper | I.CN.31.85730 | CON - Sec.5 - FILL 43 - Fill.H1 - Upper : Ch37287 to 38060 (23205 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.4 | Fill Upper | I.CN.31.85450 | CON - Sec.5 - FILL 36 - Fill.H1 - Upper : Ch28515 to 29975 (27214 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.4 | Fill Upper | I.CN.31.85490 | CON - Sec.5 - FILL 37 - Fill.H1 - Upper : Ch30865 to 31702 (8175 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.4 | Fill Upper | I.CN.31.85530 | CON - Sec.5 - FILL 38 - Fill.H1 - Upper : Ch32313 to 33273 (9694 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.4 | Fill Upper | I.CN.31.85570 | CON - Sec.5 - FILL 39 - Fill.H1 - Upper : Ch33876 to 34635 (8727 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.4 | Fill Upper | I.CN.31.85610 | CON - Sec.5 - FILL 40 - Fill.H1 - Upper : Ch35075 to 35935 (10116 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.4 | Fill Upper | I.CN.31.88100 | CON - Sec.5 - CUT 37 - Fill.H1 - Upper : Ch33642 to 33876 (229 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.4 | Fill Upper | I.CN.31.88140 | CON - Sec.5 - CUT 38 - Fill.H1 - Upper : Ch34635 to 35075 (326 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.4 | Fill Upper | I.CN.31.88180 | CON - Sec.5 - CUT 39 - Fill.H1 - Upper : Ch37055 to 37287 (243 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.4 | Fill Upper | I.CN.31.88020 | CON - Sec.5 - CUT 35 - Fill.H1 - Upper : Ch31702 to 32313 (294 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S5.31.2.4 | Fill Upper | I.CN.31.88060 | CON - Sec.5 - CUT 36 - Fill.H1 - Upper : Ch33273 to 33642 (492 bcm - 2500 per/d)
033 - Capping |  |  |  | 2026-06-23 | 2026-08-19
Support to u/s Ballast |  |  |  | 2026-06-23 | 2026-08-19
Structural Fill |  |  |  | 2026-06-23 | 2026-06-23
I2S-7688-MP-74.CN.S5.33.3.1 | Structural Fill | I.CN.33.10950 | CON - Sec.5 - Fill Struc fill (75,018 TON) 2200 TON/d | 2026-06-23 | 2026-06-23
Capping (Rail) |  |  |  | 2026-06-30 | 2026-06-30
I2S-7688-MP-74.CN.S5.33.3.2 | Capping (Rail) | I.CN.33.11110 | CON - Sec.5 - Capping (21,687 TON) 985 TON/d | 2026-06-30 | 2026-06-30
Capping (RMAR) |  |  |  | 2026-08-18 | 2026-08-19
I2S-7688-MP-74.CN.S5.33.3.20 | Capping (RMAR) | I.CN.45.11320 | CON - Sec.5 - (15,946 TON) - Strip/Grade RMAR with type D Material (U5 Class) | 2026-08-18 | 2026-08-19
034 - Drainage |  |  |  | 2025-11-12 | 2026-07-01
Mainline |  |  |  | 2026-06-06 | 2026-07-01
I2S-7688-MP-74.CN.S5.34.10 | Mainline | I.CN.34.25450 | CON - Sec.5 - Cess Drainage - 445875 to 454835 - Grass Lining | 2026-06-06 | 2026-06-16
I2S-7688-MP-74.CN.S5.34.10 | Mainline | I.CN.34.25460 | CON - Sec.5 - Cess Drainage - 443866 to 452467 - Grass Lining | 2026-06-17 | 2026-06-24
I2S-7688-MP-74.CN.S5.34.10 | Mainline | I.CN.34.25560 | CON - Sec.5 - Cess Drainage - 446030 to 454718 - Grass Lining | 2026-06-26 | 2026-07-01
Culverts |  |  |  | 2025-11-12 | 2026-04-24
Culvert ID: M3-RD-1360-1 / Type: 30x600mm RCP / Ch37212 (21.96m each)
I2S-7688-MP-74.CN.S5.34.11.4 | Culvert ID: M3-RD-1360-1 / Type: 30x600mm RCP / Ch37212 (21.96m each) | I.CN.34.29540 | CON - Sec.5 - Culvert : M3-RD-1360-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S5.34.11.4 | Culvert ID: M3-RD-1360-1 / Type: 30x600mm RCP / Ch37212 (21.96m each) | I.CN.34.29570 | CON - Sec.5 - Culvert : M3-RD-1360-1 - HDPE / RCP pipe lay & backfill
I2S-7688-MP-74.CN.S5.34.11.4 | Culvert ID: M3-RD-1360-1 / Type: 30x600mm RCP / Ch37212 (21.96m each) | I.CN.34.29580 | CON - Sec.5 - Culvert : M3-RD-1360-1 - Headwall stitch pour
I2S-7688-MP-74.CN.S5.34.11.4 | Culvert ID: M3-RD-1360-1 / Type: 30x600mm RCP / Ch37212 (21.96m each) | I.CN.34.29600 | CON - Sec.5 - Culvert : M3-RD-1360-1 - Construct Scour protection
I2S-7688-MP-74.CN.S5.34.11.4 | Culvert ID: M3-RD-1360-1 / Type: 30x600mm RCP / Ch37212 (21.96m each) | I.CN.34.29610 | CON - Sec.5 - Culvert : M3-RD-1360-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S5.34.11.4 | Culvert ID: M3-RD-1360-1 / Type: 30x600mm RCP / Ch37212 (21.96m each) | I.CN.34.31950 | CON - Sec.5 - Culvert : M3-RD-1360-1 - Headwall Installation
I2S-7688-MP-74.CN.S5.34.11.4 | Culvert ID: M3-RD-1360-1 / Type: 30x600mm RCP / Ch37212 (21.96m each) | I.CN.34.32150 | CON - Sec.5 - Culvert : M3-RD-1360-1 - Headwall cut-off wall Installation (FRP)
Culvert ID : E7-RA-454773-1 / Type : 2*1200x300mm RCBC / Ch37263 (7.2m each)
I2S-7688-MP-74.CN.S5.34.11.16 | Culvert ID : E7-RA-454773-1 / Type : 2*1200x300mm RCBC / Ch37263 (7.2m each) | I.CN.65.19871 | CON - Sec.5 - Culvert : E7-RA-454773-1 - Drainage - LX Culvert - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S5.34.11.16 | Culvert ID : E7-RA-454773-1 / Type : 2*1200x300mm RCBC / Ch37263 (7.2m each) | I.CN.65.19881 | CON - Sec.5 - Culvert : E7-RA-454773-1 - Drainage - Struc fill Placement (250mm)
I2S-7688-MP-74.CN.S5.34.11.16 | Culvert ID : E7-RA-454773-1 / Type : 2*1200x300mm RCBC / Ch37263 (7.2m each) | I.CN.65.19961 | CON - Sec.5 - Culvert : E7-RA-454773-1 - Drainage - Construct Scour protection
I2S-7688-MP-74.CN.S5.34.11.16 | Culvert ID : E7-RA-454773-1 / Type : 2*1200x300mm RCBC / Ch37263 (7.2m each) | I.CN.65.19891 | CON - Sec.5 - Culvert : E7-RA-454773-1- Drainage - Blinding placement (50mm)
I2S-7688-MP-74.CN.S5.34.11.16 | Culvert ID : E7-RA-454773-1 / Type : 2*1200x300mm RCBC / Ch37263 (7.2m each) | I.CN.65.19901 | CON - Sec.5 - Culvert : E7-RA-454773-1 - Drainage - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.CN.S5.34.11.16 | Culvert ID : E7-RA-454773-1 / Type : 2*1200x300mm RCBC / Ch37263 (7.2m each) | I.CN.65.19911 | CON - Sec.5 - Culvert : E7-RA-454773-1 - Drainage - 7 day Curing
I2S-7688-MP-74.CN.S5.34.11.16 | Culvert ID : E7-RA-454773-1 / Type : 2*1200x300mm RCBC / Ch37263 (7.2m each) | I.CN.65.19921 | CON - Sec.5 - Culvert : E7-RA-454773-1 - Drainage - Place RCBC crown units
I2S-7688-MP-74.CN.S5.34.11.16 | Culvert ID : E7-RA-454773-1 / Type : 2*1200x300mm RCBC / Ch37263 (7.2m each) | I.CN.65.19931 | CON - Sec.5 - Culvert : E7-RA-454773-1 - Drainage - Place Precast headwall and precast stich pours
I2S-7688-MP-74.CN.S5.34.11.16 | Culvert ID : E7-RA-454773-1 / Type : 2*1200x300mm RCBC / Ch37263 (7.2m each) | I.CN.65.19941 | CON - Sec.5 - Culvert : E7-RA-454773-1 - Drainage - Pre-cast RCBC completion (Seal joints)
I2S-7688-MP-74.CN.S5.34.11.16 | Culvert ID : E7-RA-454773-1 / Type : 2*1200x300mm RCBC / Ch37263 (7.2m each) | I.CN.65.19951 | CON - Sec.5 - Culvert : E7-RA-454773-1 - Drainage - Detail backfill
I2S-7688-MP-74.CN.S5.34.11.16 | Culvert ID : E7-RA-454773-1 / Type : 2*1200x300mm RCBC / Ch37263 (7.2m each) | I.CN.65.19971 | CON - Sec.5 - Culvert : E7-RA-454773-1 - Drainage - FRP Base Slab - Milestone
Culvert ID : E7-RD-454718-1 / Type : 5*450mm HDPE / Ch37210 (9.76m each)
I2S-7688-MP-74.CN.S5.34.11.13 | Culvert ID : E7-RD-454718-1 / Type : 5*450mm HDPE / Ch37210 (9.76m each) | I.CN.34.29620 | CON - Sec.5 - Culvert : E7-RD-454718-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S5.34.11.13 | Culvert ID : E7-RD-454718-1 / Type : 5*450mm HDPE / Ch37210 (9.76m each) | I.CN.34.29640 | CON - Sec.5 - Culvert : E7-RD-454718-1 - Construct Scour Protection
I2S-7688-MP-74.CN.S5.34.11.13 | Culvert ID : E7-RD-454718-1 / Type : 5*450mm HDPE / Ch37210 (9.76m each) | I.CN.34.29650 | CON - Sec.5 - Culvert : E7-RD-454718-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S5.34.11.13 | Culvert ID : E7-RD-454718-1 / Type : 5*450mm HDPE / Ch37210 (9.76m each) | I.CN.34.29660 | CON - Sec.5 - Culvert : E7-RD-454718-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S5.34.11.13 | Culvert ID : E7-RD-454718-1 / Type : 5*450mm HDPE / Ch37210 (9.76m each) | I.CN.34.29670 | CON - Sec.5 - Culvert : E7-RD-454718-1 - Headwall Installation
I2S-7688-MP-74.CN.S5.34.11.13 | Culvert ID : E7-RD-454718-1 / Type : 5*450mm HDPE / Ch37210 (9.76m each) | I.CN.34.29680 | CON - Sec.5 - Culvert : E7-RD-454718-1 - Backfill
I2S-7688-MP-74.CN.S5.34.11.13 | Culvert ID : E7-RD-454718-1 / Type : 5*450mm HDPE / Ch37210 (9.76m each) | I.CN.34.29690 | CON - Sec.5 - Culvert : E7-RD-454718-1 - Headwall Stitch Pour
Culvert ID : E7-RA-454580-1 / Type : 4*900x450mm RCBC / Ch37094 (9.6m each)
I2S-7688-MP-74.CN.S5.34.11.12 | Culvert ID : E7-RA-454580-1 / Type : 4*900x450mm RCBC / Ch37094 (9.6m each) | I.CN.34.28430 | CON - Sec.5 - Culvert : E7-RA-454580-1 - Struc fill Placement (250mm)
I2S-7688-MP-74.CN.S5.34.11.12 | Culvert ID : E7-RA-454580-1 / Type : 4*900x450mm RCBC / Ch37094 (9.6m each) | I.CN.34.28440 | CON - Sec.5 - Culvert : E7-RA-454580-1 - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.CN.S5.34.11.12 | Culvert ID : E7-RA-454580-1 / Type : 4*900x450mm RCBC / Ch37094 (9.6m each) | I.CN.34.28570 | CON - Sec.5 - Culvert : E7-RA-454580-1 - Place RCBC crown units
I2S-7688-MP-74.CN.S5.34.11.12 | Culvert ID : E7-RA-454580-1 / Type : 4*900x450mm RCBC / Ch37094 (9.6m each) | I.CN.34.28370 | CON - Sec.5 - Culvert : E7-RA-454580-1 - 7 day Curing
I2S-7688-MP-74.CN.S5.34.11.12 | Culvert ID : E7-RA-454580-1 / Type : 4*900x450mm RCBC / Ch37094 (9.6m each) | I.CN.34.28380 | CON - Sec.5 - Culvert : E7-RA-454580-1 - Place Pre-cast Wingwalls and Stich Pour
I2S-7688-MP-74.CN.S5.34.11.12 | Culvert ID : E7-RA-454580-1 / Type : 4*900x450mm RCBC / Ch37094 (9.6m each) | I.CN.34.28390 | CON - Sec.5 - Culvert : E7-RA-454580-1 - Pre-cast RCBC completion (Seal joints)
I2S-7688-MP-74.CN.S5.34.11.12 | Culvert ID : E7-RA-454580-1 / Type : 4*900x450mm RCBC / Ch37094 (9.6m each) | I.CN.34.28400 | CON - Sec.5 - Culvert : E7-RA-454580-1 - Detail backfill
I2S-7688-MP-74.CN.S5.34.11.12 | Culvert ID : E7-RA-454580-1 / Type : 4*900x450mm RCBC / Ch37094 (9.6m each) | I.CN.34.28410 | CON - Sec.5 - Culvert : E7-RA-454580-1 - Construct Scour protection
I2S-7688-MP-74.CN.S5.34.11.12 | Culvert ID : E7-RA-454580-1 / Type : 4*900x450mm RCBC / Ch37094 (9.6m each) | I.CN.34.28420 | CON - Sec.5 - Culvert : E7-RA-454580-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S5.34.11.12 | Culvert ID : E7-RA-454580-1 / Type : 4*900x450mm RCBC / Ch37094 (9.6m each) | I.CN.34.31960 | CON - Sec.5 - Culvert : E7-RA-454580-1 - Blinding placement (50mm)
Culvert ID : E7-RA-454000-1 / Type : 6*600mm HDPE / Ch36721 (10.89m each) |  |  |  | 2026-01-08 | 2026-01-21
I2S-7688-MP-74.CN.S5.34.11.9 | Culvert ID : E7-RA-454000-1 / Type : 6*600mm HDPE / Ch36721 (10.89m each) | I.CN.34.20880 | CON - Sec.5 - Culvert : E7-RA-454000-1 - Headwall Cut-off Wall Installation (FRP) | 2026-01-18 | 2026-01-19
I2S-7688-MP-74.CN.S5.34.11.9 | Culvert ID : E7-RA-454000-1 / Type : 6*600mm HDPE / Ch36721 (10.89m each) | I.CN.34.20900 | CON - Sec.5 - Culvert : E7-RA-454000-1 - Construct Scour Protection | 2026-01-21 | 2026-01-21
I2S-7688-MP-74.CN.S5.34.11.9 | Culvert ID : E7-RA-454000-1 / Type : 6*600mm HDPE / Ch36721 (10.89m each) | I.CN.34.20790 | CON - Sec.5 - Culvert : E7-RA-454000-1 - Site Prep / Detail Excavation | 2026-01-08 | 2026-01-09
I2S-7688-MP-74.CN.S5.34.11.9 | Culvert ID : E7-RA-454000-1 / Type : 6*600mm HDPE / Ch36721 (10.89m each) | I.CN.34.20800 | CON - Sec.5 - Culvert : E7-RA-454000-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-01-10 | 2026-01-10
I2S-7688-MP-74.CN.S5.34.11.9 | Culvert ID : E7-RA-454000-1 / Type : 6*600mm HDPE / Ch36721 (10.89m each) | I.CN.34.20830 | CON - Sec.5 - Culvert : E7-RA-454000-1 - Headwall Installation | 2026-01-11 | 2026-01-11
I2S-7688-MP-74.CN.S5.34.11.9 | Culvert ID : E7-RA-454000-1 / Type : 6*600mm HDPE / Ch36721 (10.89m each) | I.CN.34.20850 | CON - Sec.5 - Culvert : E7-RA-454000-1 - Backfill | 2026-01-14 | 2026-01-16
I2S-7688-MP-74.CN.S5.34.11.9 | Culvert ID : E7-RA-454000-1 / Type : 6*600mm HDPE / Ch36721 (10.89m each) | I.CN.34.20870 | CON - Sec.5 - Culvert : E7-RA-454000-1 - Headwall Stitch Pour | 2026-01-17 | 2026-01-17
Culvert ID : E7-RA-453720-1 / Type : 64*750mm HPDE / Ch36182 (21.11m each)
I2S-7688-MP-74.CN.S5.34.11.11 | Culvert ID : E7-RA-453720-1 / Type : 64*750mm HPDE / Ch36182 (21.11m each) | I.CN.34.28290 | CON - Sec.5 - Culvert : E7-RA-453720-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S5.34.11.11 | Culvert ID : E7-RA-453720-1 / Type : 64*750mm HPDE / Ch36182 (21.11m each) | I.CN.34.28300 | CON - Sec.5 - Culvert : E7-RA-453720-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S5.34.11.11 | Culvert ID : E7-RA-453720-1 / Type : 64*750mm HPDE / Ch36182 (21.11m each) | I.CN.34.28310 | CON - Sec.5 - Culvert : E7-RA-453720-1 - Headwall Installation
I2S-7688-MP-74.CN.S5.34.11.11 | Culvert ID : E7-RA-453720-1 / Type : 64*750mm HPDE / Ch36182 (21.11m each) | I.CN.34.28320 | CON - Sec.5 - Culvert : E7-RA-453720-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S5.34.11.11 | Culvert ID : E7-RA-453720-1 / Type : 64*750mm HPDE / Ch36182 (21.11m each) | I.CN.34.28330 | CON - Sec.5 - Culvert : E7-RA-453720-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S5.34.11.11 | Culvert ID : E7-RA-453720-1 / Type : 64*750mm HPDE / Ch36182 (21.11m each) | I.CN.34.28340 | CON - Sec.5 - Culvert : E7-RA-453720-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S5.34.11.11 | Culvert ID : E7-RA-453720-1 / Type : 64*750mm HPDE / Ch36182 (21.11m each) | I.CN.34.28360 | CON - Sec.5 - Culvert : E7-RA-453720-1 - Construct Scour Protection
Culvert ID : E7-RD-453717-1 / Type: (1x)450mm HDPE / Ch37210 (10.84m each) - RMAR
I2S-7688-MP-74.CN.S5.34.11.15 | Culvert ID : E7-RD-453717-1 / Type: (1x)450mm HDPE / Ch37210 (10.84m each) - RMAR | I.CN.34.31830 | CON - Sec.5 - Culvert : E7-RA-453717-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S5.34.11.15 | Culvert ID : E7-RD-453717-1 / Type: (1x)450mm HDPE / Ch37210 (10.84m each) - RMAR | I.CN.34.31840 | CON - Sec.5 - Culvert : E7-RA-453717-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S5.34.11.15 | Culvert ID : E7-RD-453717-1 / Type: (1x)450mm HDPE / Ch37210 (10.84m each) - RMAR | I.CN.34.31850 | CON - Sec.5 - Culvert : E7-RA-453717-1 - Headwall Installation
I2S-7688-MP-74.CN.S5.34.11.15 | Culvert ID : E7-RD-453717-1 / Type: (1x)450mm HDPE / Ch37210 (10.84m each) - RMAR | I.CN.34.31860 | CON - Sec.5 - Culvert : E7-RA-453717-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S5.34.11.15 | Culvert ID : E7-RD-453717-1 / Type: (1x)450mm HDPE / Ch37210 (10.84m each) - RMAR | I.CN.34.31870 | CON - Sec.5 - Culvert : E7-RA-453717-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S5.34.11.15 | Culvert ID : E7-RD-453717-1 / Type: (1x)450mm HDPE / Ch37210 (10.84m each) - RMAR | I.CN.34.31880 | CON - Sec.5 - Culvert : E7-RA-453717-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S5.34.11.15 | Culvert ID : E7-RD-453717-1 / Type: (1x)450mm HDPE / Ch37210 (10.84m each) - RMAR | I.CN.34.31900 | CON - Sec.5 - Culvert : E7-RA-453717-1 - Construct Scour Protection
Culvert ID : E7-RA-452940-1 / Type : 12*600mm HDPE / Ch35432 (13.13m each) |  |  |  | 2025-11-28 | 2025-12-12
I2S-7688-MP-74.CN.S5.34.11.7 | Culvert ID : E7-RA-452940-1 / Type : 12*600mm HDPE / Ch35432 (13.13m each) | I.CN.34.20610 | CON - Sec.5 - Culvert : E7-RA-452940-1 - HDPE / RCP Pipe Lay & Backfill | 2025-12-04 | 2025-12-04
I2S-7688-MP-74.CN.S5.34.11.7 | Culvert ID : E7-RA-452940-1 / Type : 12*600mm HDPE / Ch35432 (13.13m each) | I.CN.34.20630 | CON - Sec.5 - Culvert : E7-RA-452940-1 - Headwall Stitch Pour | 2025-12-06 | 2025-12-07
I2S-7688-MP-74.CN.S5.34.11.7 | Culvert ID : E7-RA-452940-1 / Type : 12*600mm HDPE / Ch35432 (13.13m each) | I.CN.34.20640 | CON - Sec.5 - Culvert : E7-RA-452940-1 - Headwall Cut-off Wall Installation (FRP) | 2025-12-08 | 2025-12-09
I2S-7688-MP-74.CN.S5.34.11.7 | Culvert ID : E7-RA-452940-1 / Type : 12*600mm HDPE / Ch35432 (13.13m each) | I.CN.34.20660 | CON - Sec.5 - Culvert : E7-RA-452940-1 - Construct Scour Protection | 2025-12-11 | 2025-12-12
I2S-7688-MP-74.CN.S5.34.11.7 | Culvert ID : E7-RA-452940-1 / Type : 12*600mm HDPE / Ch35432 (13.13m each) | I.CN.34.20550 | CON - Sec.5 - Culvert : E7-RA-452940-1 - Site Prep / Detail Excavation | 2025-11-28 | 2025-11-29
I2S-7688-MP-74.CN.S5.34.11.7 | Culvert ID : E7-RA-452940-1 / Type : 12*600mm HDPE / Ch35432 (13.13m each) | I.CN.34.20560 | CON - Sec.5 - Culvert : E7-RA-452940-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2025-11-30 | 2025-12-01
I2S-7688-MP-74.CN.S5.34.11.7 | Culvert ID : E7-RA-452940-1 / Type : 12*600mm HDPE / Ch35432 (13.13m each) | I.CN.34.20600 | CON - Sec.5 - Culvert : E7-RA-452940-1 - Headwall Installation | 2025-12-02 | 2025-12-03
Culvert ID : E7-RA-451960-1 / Type : 14*600mm HDPE / Ch34452 (10.75m each) |  |  |  | 2025-11-12 | 2025-11-27
I2S-7688-MP-74.CN.S5.34.11.6 | Culvert ID : E7-RA-451960-1 / Type : 14*600mm HDPE / Ch34452 (10.75m each) | I.CN.34.20540 | CON - Sec.5 - Culvert : E7-RA-451960-1 - Construct Scour Protection | 2025-11-26 | 2025-11-27
I2S-7688-MP-74.CN.S5.34.11.6 | Culvert ID : E7-RA-451960-1 / Type : 14*600mm HDPE / Ch34452 (10.75m each) | I.CN.34.20430 | CON - Sec.5 - Culvert : E7-RA-451960-1 - Site Prep / Detail Excavation | 2025-11-12 | 2025-11-13
I2S-7688-MP-74.CN.S5.34.11.6 | Culvert ID : E7-RA-451960-1 / Type : 14*600mm HDPE / Ch34452 (10.75m each) | I.CN.34.20440 | CON - Sec.5 - Culvert : E7-RA-451960-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2025-11-14 | 2025-11-16
I2S-7688-MP-74.CN.S5.34.11.6 | Culvert ID : E7-RA-451960-1 / Type : 14*600mm HDPE / Ch34452 (10.75m each) | I.CN.34.20480 | CON - Sec.5 - Culvert : E7-RA-451960-1 - Headwall Installation | 2025-11-17 | 2025-11-18
I2S-7688-MP-74.CN.S5.34.11.6 | Culvert ID : E7-RA-451960-1 / Type : 14*600mm HDPE / Ch34452 (10.75m each) | I.CN.34.20490 | CON - Sec.5 - Culvert : E7-RA-451960-1 - HDPE / RCP Pipe Lay & Backfill | 2025-11-19 | 2025-11-20
I2S-7688-MP-74.CN.S5.34.11.6 | Culvert ID : E7-RA-451960-1 / Type : 14*600mm HDPE / Ch34452 (10.75m each) | I.CN.34.20510 | CON - Sec.5 - Culvert : E7-RA-451960-1 - Headwall Stitch Pour | 2025-11-21 | 2025-11-22
I2S-7688-MP-74.CN.S5.34.11.6 | Culvert ID : E7-RA-451960-1 / Type : 14*600mm HDPE / Ch34452 (10.75m each) | I.CN.34.20520 | CON - Sec.5 - Culvert : E7-RA-451960-1 - Headwall Cut-off Wall Installation (FRP) | 2025-11-23 | 2025-11-24
Culvert ID : E7-RA-450480-1 / Type : 3*900x750mm RCBC / Ch32961 (7.2m each)
I2S-7688-MP-74.CN.S5.34.11.10 | Culvert ID : E7-RA-450480-1 / Type : 3*900x750mm RCBC / Ch32961 (7.2m each) | I.CN.34.28210 | CON - Sec.5 - Culvert : E7-RA-450480-1 - Struc fill Placement (250mm)
I2S-7688-MP-74.CN.S5.34.11.10 | Culvert ID : E7-RA-450480-1 / Type : 3*900x750mm RCBC / Ch32961 (7.2m each) | I.CN.34.28220 | CON - Sec.5 - Culvert : E7-RA-450480-1 - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.CN.S5.34.11.10 | Culvert ID : E7-RA-450480-1 / Type : 3*900x750mm RCBC / Ch32961 (7.2m each) | I.CN.34.28230 | CON - Sec.5 - Culvert : E7-RA-450480-1 - 7 day Curing
I2S-7688-MP-74.CN.S5.34.11.10 | Culvert ID : E7-RA-450480-1 / Type : 3*900x750mm RCBC / Ch32961 (7.2m each) | I.CN.34.28240 | CON - Sec.5 - Culvert : E7-RA-450480-1 - Place Pre-cast Wingwalls and Stich Pour
I2S-7688-MP-74.CN.S5.34.11.10 | Culvert ID : E7-RA-450480-1 / Type : 3*900x750mm RCBC / Ch32961 (7.2m each) | I.CN.34.28250 | CON - Sec.5 - Culvert : E7-RA-450480-1 - Pre-cast RCBC completion (Seal joints)
I2S-7688-MP-74.CN.S5.34.11.10 | Culvert ID : E7-RA-450480-1 / Type : 3*900x750mm RCBC / Ch32961 (7.2m each) | I.CN.34.28260 | CON - Sec.5 - Culvert : E7-RA-450480-1 - Detail backfill
I2S-7688-MP-74.CN.S5.34.11.10 | Culvert ID : E7-RA-450480-1 / Type : 3*900x750mm RCBC / Ch32961 (7.2m each) | I.CN.34.28270 | CON - Sec.5 - Culvert : E7-RA-450480-1 - Construct Scour protection
I2S-7688-MP-74.CN.S5.34.11.10 | Culvert ID : E7-RA-450480-1 / Type : 3*900x750mm RCBC / Ch32961 (7.2m each) | I.CN.34.28280 | CON - Sec.5 - Culvert : E7-RA-450480-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S5.34.11.10 | Culvert ID : E7-RA-450480-1 / Type : 3*900x750mm RCBC / Ch32961 (7.2m each) | I.CN.34.28550 | CON - Sec.5 - Culvert : E7-RA-450480-1 - Place RCBC crown units
I2S-7688-MP-74.CN.S5.34.11.10 | Culvert ID : E7-RA-450480-1 / Type : 3*900x750mm RCBC / Ch32961 (7.2m each) | I.CN.34.31980 | CON - Sec.5 - Culvert : E7-RA-450480-1 - Blinding placement (50mm)
Culvert ID : E7-RA-453560-1 / Type : 15*600mm HDPE / Ch36058 (18.56m each)
I2S-7688-MP-74.CN.S5.34.11.8 | Culvert ID : E7-RA-453560-1 / Type : 15*600mm HDPE / Ch36058 (18.56m each) | I.CN.34.32440 | CON - Sec.5 - Culvert : E7-RA-453560-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S5.34.11.8 | Culvert ID : E7-RA-453560-1 / Type : 15*600mm HDPE / Ch36058 (18.56m each) | I.CN.34.32450 | CON - Sec.5 - Culvert : E7-RA-453560-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S5.34.11.8 | Culvert ID : E7-RA-453560-1 / Type : 15*600mm HDPE / Ch36058 (18.56m each) | I.CN.34.32460 | CON - Sec.5 - Culvert : E7-RA-453560-1 - Headwall installation
I2S-7688-MP-74.CN.S5.34.11.8 | Culvert ID : E7-RA-453560-1 / Type : 15*600mm HDPE / Ch36058 (18.56m each) | I.CN.34.32470 | CON - Sec.5 - Culvert : E7-RA-453560-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S5.34.11.8 | Culvert ID : E7-RA-453560-1 / Type : 15*600mm HDPE / Ch36058 (18.56m each) | I.CN.34.32480 | CON - Sec.5 - Culvert : E7-RA-453560-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S5.34.11.8 | Culvert ID : E7-RA-453560-1 / Type : 15*600mm HDPE / Ch36058 (18.56m each) | I.CN.34.32490 | CON - Sec.5 - Culvert : E7-RA-453560-1- Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S5.34.11.8 | Culvert ID : E7-RA-453560-1 / Type : 15*600mm HDPE / Ch36058 (18.56m each) | I.CN.34.32500 | CON - Sec.5 - Culvert : E7-RA-453560-1 - Construct Scour Protection
I2S-7688-MP-74.CN.S5.34.11.8 | Culvert ID : E7-RA-453560-1 / Type : 15*600mm HDPE / Ch36058 (18.56m each) | I.CN.34.32790 | CON - Sec.5 - Culvert : E7-RA-453560-1 - HDPE / RCP Pipe Lay & Backfill - Milestone
Culvert ID : E7-RA-448900-1 / Type : 30*600mm HDPE / Ch31345 (10.12m each) |  |  |  | 2026-04-12 | 2026-04-24
I2S-7688-MP-74.CN.S5.34.11.5 | Culvert ID : E7-RA-448900-1 / Type : 30*600mm HDPE / Ch31345 (10.12m each) | I.CN.34.20370 | CON - Sec.5 - Culvert : E7-RA-448900-1 - HDPE / RCP Pipe Lay & Backfill | 2026-04-17 | 2026-04-17
I2S-7688-MP-74.CN.S5.34.11.5 | Culvert ID : E7-RA-448900-1 / Type : 30*600mm HDPE / Ch31345 (10.12m each) | I.CN.34.20390 | CON - Sec.5 - Culvert : E7-RA-448900-1 - Headwall Stitch Pour | 2026-04-18 | 2026-04-19
I2S-7688-MP-74.CN.S5.34.11.5 | Culvert ID : E7-RA-448900-1 / Type : 30*600mm HDPE / Ch31345 (10.12m each) | I.CN.34.20400 | CON - Sec.5 - Culvert : E7-RA-448900-1 - Headwall Cut-off Wall Installation (FRP) | 2026-04-20 | 2026-04-21
I2S-7688-MP-74.CN.S5.34.11.5 | Culvert ID : E7-RA-448900-1 / Type : 30*600mm HDPE / Ch31345 (10.12m each) | I.CN.34.20420 | CON - Sec.5 - Culvert : E7-RA-448900-1 - Construct Scour Protection | 2026-04-23 | 2026-04-24
I2S-7688-MP-74.CN.S5.34.11.5 | Culvert ID : E7-RA-448900-1 / Type : 30*600mm HDPE / Ch31345 (10.12m each) | I.CN.34.20310 | CON - Sec.5 - Culvert : E7-RA-448900-1 - Site Prep / Detail Excavation | 2026-04-12 | 2026-04-13
I2S-7688-MP-74.CN.S5.34.11.5 | Culvert ID : E7-RA-448900-1 / Type : 30*600mm HDPE / Ch31345 (10.12m each) | I.CN.34.20320 | CON - Sec.5 - Culvert : E7-RA-448900-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-04-14 | 2026-04-15
I2S-7688-MP-74.CN.S5.34.11.5 | Culvert ID : E7-RA-448900-1 / Type : 30*600mm HDPE / Ch31345 (10.12m each) | I.CN.34.20360 | CON - Sec.5 - Culvert : E7-RA-448900-1 - Headwall Installation | 2026-04-16 | 2026-04-16
Culvert ID : E7-RA-447780-1 / Type : 1*1200x600mm RCBC / Ch30270 (7.2m each) |  |  |  | 2026-03-10 | 2026-03-29
I2S-7688-MP-74.CN.S5.34.11.3 | Culvert ID : E7-RA-447780-1 / Type : 1*1200x600mm RCBC / Ch30270 (7.2m each) | I.CN.34.20070 | CON - Sec.5 - Culvert : E7-RA-447780-1 - Site Prep / Detail Excavation | 2026-03-10 | 2026-03-11
I2S-7688-MP-74.CN.S5.34.11.3 | Culvert ID : E7-RA-447780-1 / Type : 1*1200x600mm RCBC / Ch30270 (7.2m each) | I.CN.34.20080 | CON - Sec.5 - Culvert : E7-RA-447780-1 - Struc fill Placement (250mm) | 2026-03-18 | 2026-03-19
I2S-7688-MP-74.CN.S5.34.11.3 | Culvert ID : E7-RA-447780-1 / Type : 1*1200x600mm RCBC / Ch30270 (7.2m each) | I.CN.34.20120 | CON - Sec.5 - Culvert : E7-RA-447780-1 - FRP Base Slab / Apron Slab / Cut-off Wall | 2026-03-20 | 2026-03-20
I2S-7688-MP-74.CN.S5.34.11.3 | Culvert ID : E7-RA-447780-1 / Type : 1*1200x600mm RCBC / Ch30270 (7.2m each) | I.CN.34.20130 | CON - Sec.5 - Culvert : E7-RA-447780-1 - 7 day Curing | 2026-03-21 | 2026-03-21
I2S-7688-MP-74.CN.S5.34.11.3 | Culvert ID : E7-RA-447780-1 / Type : 1*1200x600mm RCBC / Ch30270 (7.2m each) | I.CN.34.20150 | CON - Sec.5 - Culvert : E7-RA-447780-1 - Place RCBC crown units | 2026-03-22 | 2026-03-23
I2S-7688-MP-74.CN.S5.34.11.3 | Culvert ID : E7-RA-447780-1 / Type : 1*1200x600mm RCBC / Ch30270 (7.2m each) | I.CN.34.20160 | CON - Sec.5 - Culvert : E7-RA-447780-1 - Place Precast headwall and precast stich pours | 2026-03-24 | 2026-03-26
I2S-7688-MP-74.CN.S5.34.11.3 | Culvert ID : E7-RA-447780-1 / Type : 1*1200x600mm RCBC / Ch30270 (7.2m each) | I.CN.34.20170 | CON - Sec.5 - Culvert : E7-RA-447780-1 - Detail backfill | 2026-03-27 | 2026-03-27
I2S-7688-MP-74.CN.S5.34.11.3 | Culvert ID : E7-RA-447780-1 / Type : 1*1200x600mm RCBC / Ch30270 (7.2m each) | I.CN.34.20180 | CON - Sec.5 - Culvert : E7-RA-447780-1 - Construct Scour protection | 2026-03-28 | 2026-03-29
I2S-7688-MP-74.CN.S5.34.11.3 | Culvert ID : E7-RA-447780-1 / Type : 1*1200x600mm RCBC / Ch30270 (7.2m each) | I.CN.34.31990 | CON - Sec.5 - Culvert : E7-RA-447780-1 - Blinding placement (50mm)
I2S-7688-MP-74.CN.S5.34.11.3 | Culvert ID : E7-RA-447780-1 / Type : 1*1200x600mm RCBC / Ch30270 (7.2m each) | I.CN.34.32160 | CON - Sec.5 - Culvert : E7-RA-447780-1 - Pre-cast RCBC completion (Seal joints)
Culvert ID : E7-RA-447210-1 / Type : 22*750mm HDPE / Ch29701 (29.28m each) |  |  |  | 2026-02-22 | 2026-03-09
I2S-7688-MP-74.CN.S5.34.11.2 | Culvert ID : E7-RA-447210-1 / Type : 22*750mm HDPE / Ch29701 (29.28m each) | I.CN.34.19400 | CON - Sec.5 - Culvert : E7-RA-447210-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-02-24 | 2026-02-26
I2S-7688-MP-74.CN.S5.34.11.2 | Culvert ID : E7-RA-447210-1 / Type : 22*750mm HDPE / Ch29701 (29.28m each) | I.CN.34.19440 | CON - Sec.5 - Culvert : E7-RA-447210-1 - Headwall Installation | 2026-02-27 | 2026-03-01
I2S-7688-MP-74.CN.S5.34.11.2 | Culvert ID : E7-RA-447210-1 / Type : 22*750mm HDPE / Ch29701 (29.28m each) | I.CN.34.19470 | CON - Sec.5 - Culvert : E7-RA-447210-1 - Headwall Stitch Pour | 2026-03-03 | 2026-03-04
I2S-7688-MP-74.CN.S5.34.11.2 | Culvert ID : E7-RA-447210-1 / Type : 22*750mm HDPE / Ch29701 (29.28m each) | I.CN.34.19480 | CON - Sec.5 - Culvert : E7-RA-447210-1 - Headwall Cut-off Wall Installation (FRP) | 2026-03-06 | 2026-03-07
I2S-7688-MP-74.CN.S5.34.11.2 | Culvert ID : E7-RA-447210-1 / Type : 22*750mm HDPE / Ch29701 (29.28m each) | I.CN.34.19500 | CON - Sec.5 - Culvert : E7-RA-447210-1 - Construct Scour Protection | 2026-03-08 | 2026-03-09
I2S-7688-MP-74.CN.S5.34.11.2 | Culvert ID : E7-RA-447210-1 / Type : 22*750mm HDPE / Ch29701 (29.28m each) | I.CN.34.19450 | CON - Sec.5 - Culvert : E7-RA-447210-1 - HDPE / RCP Pipe Lay & Backfill | 2026-03-02 | 2026-03-02
I2S-7688-MP-74.CN.S5.34.11.2 | Culvert ID : E7-RA-447210-1 / Type : 22*750mm HDPE / Ch29701 (29.28m each) | I.CN.34.19390 | CON - Sec.5 - Culvert : E7-RA-447210-1 - Site Prep / Detail Excavation | 2026-02-22 | 2026-02-23
Culvert ID : E7-RA-446260-1 / Type : 1*600mm HDPE / Ch28755 (29.43m each) |  |  |  | 2026-02-09 | 2026-02-21
I2S-7688-MP-74.CN.S5.34.11.1 | Culvert ID : E7-RA-446260-1 / Type : 1*600mm HDPE / Ch28755 (29.43m each) | I.CN.34.19380 | CON - Sec.5 - Culvert : E7-RA-446260-1 - Construct Scour Protection | 2026-02-20 | 2026-02-21
I2S-7688-MP-74.CN.S5.34.11.1 | Culvert ID : E7-RA-446260-1 / Type : 1*600mm HDPE / Ch28755 (29.43m each) | I.CN.34.13000 | CON - Sec.5 - Culvert : E7-RA-446260-1 - Site Prep / Detail Excavation | 2026-02-09 | 2026-02-10
I2S-7688-MP-74.CN.S5.34.11.1 | Culvert ID : E7-RA-446260-1 / Type : 1*600mm HDPE / Ch28755 (29.43m each) | I.CN.34.13120 | CON - Sec.5 - Culvert : E7-RA-446260-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-02-11 | 2026-02-12
I2S-7688-MP-74.CN.S5.34.11.1 | Culvert ID : E7-RA-446260-1 / Type : 1*600mm HDPE / Ch28755 (29.43m each) | I.CN.34.13160 | CON - Sec.5 - Culvert : E7-RA-446260-1 - Headwall Installation | 2026-02-13 | 2026-02-13
I2S-7688-MP-74.CN.S5.34.11.1 | Culvert ID : E7-RA-446260-1 / Type : 1*600mm HDPE / Ch28755 (29.43m each) | I.CN.34.13300 | CON - Sec.5 - Culvert : E7-RA-446260-1 - HDPE / RCP Pipe Lay & Backfill | 2026-02-14 | 2026-02-14
I2S-7688-MP-74.CN.S5.34.11.1 | Culvert ID : E7-RA-446260-1 / Type : 1*600mm HDPE / Ch28755 (29.43m each) | I.CN.34.13440 | CON - Sec.5 - Culvert : E7-RA-446260-1 - Headwall Stitch Pour | 2026-02-16 | 2026-02-17
I2S-7688-MP-74.CN.S5.34.11.1 | Culvert ID : E7-RA-446260-1 / Type : 1*600mm HDPE / Ch28755 (29.43m each) | I.CN.34.13700 | CON - Sec.5 - Culvert : E7-RA-446260-1 - Headwall Cut-off Wall Installation (FRP) | 2026-02-18 | 2026-02-19
043 - Fencing |  |  |  | 2026-04-04 | 2026-10-02
Western Side |  |  |  | 2026-04-04 | 2026-10-02
I2S-7688-MP-74.CN.S5.43.1 | Western Side | I.CN.85.1570 | CON - Sec.5 - Fencing Joint Inspection/fix | 2026-09-17 | 2026-10-02
I2S-7688-MP-74.CN.S5.43.1 | Western Side | I.CN.43.14040 | CON - Sec.5 - Fencing West Side - Ch28300-31000 | 2026-04-04 | 2026-05-11
I2S-7688-MP-74.CN.S5.43.1 | Western Side | I.CN.43.14060 | CON - Sec.5 - Fencing West Side - Ch31000-34000 | 2026-05-12 | 2026-06-24
I2S-7688-MP-74.CN.S5.43.1 | Western Side | I.CN.43.14080 | CON - Sec.5 - Fencing West Side - Ch34000-37300 | 2026-06-26 | 2026-08-12
Eastern Side |  |  |  | 2026-04-04 | 2026-08-12
I2S-7688-MP-74.CN.S5.43.2 | Eastern Side | I.CN.43.13890 | CON - Sec.5 - Fencing East Side - Ch28300-31000 | 2026-04-04 | 2026-05-11
I2S-7688-MP-74.CN.S5.43.2 | Eastern Side | I.CN.43.14050 | CON - Sec.5 - Fencing East Side - Ch31000-34000 | 2026-05-12 | 2026-06-24
I2S-7688-MP-74.CN.S5.43.2 | Eastern Side | I.CN.43.14070 | CON - Sec.5 - Fencing East Side - Ch34000-37300 | 2026-06-26 | 2026-08-12
045 - Access Roads |  |  |  | 2025-07-18 | 2026-08-09
I2S-7688-MP-74.CN.S5.45 | 045 - Access Roads | I.CN.45.14270 | CON - Sec.5 - Prep RMAR Road - East - 28300-31000 | 2026-07-13 | 2026-07-21
I2S-7688-MP-74.CN.S5.45 | 045 - Access Roads | I.CN.45.14390 | CON - Sec.5 - Prep RMAR Road - East - 31000-34000 | 2026-07-22 | 2026-07-31
I2S-7688-MP-74.CN.S5.45 | 045 - Access Roads | I.CN.45.14400 | CON - Sec.5 - Prep RMAR Road - East - 34000-37300 | 2026-08-01 | 2026-08-09
I2S-7688-MP-74.CN.S5.45 | 045 - Access Roads | I.CN.45.14450 | CON - Sec.5 - Gate 7A (34600) - Install left hand lane and Portable traffic sign | 2025-07-18 | 2025-07-20
050 - Trackwork |  |  |  | 2026-10-07 | 2026-12-11
Place Bottom Ballast |  |  |  | 2026-10-13 | 2026-11-02
I2S-7688-MP-74.CN.S5.50.15 | Place Bottom Ballast | I.CN.50.13990 | CON - Sec.5 - Place Bottom Ballast - 500m/day - 36000 to 36500 (500m) | 2026-10-31 | 2026-11-01
I2S-7688-MP-74.CN.S5.50.15 | Place Bottom Ballast | I.CN.50.13960 | CON - Sec.5 - Place Bottom Ballast - 500m/day - 34500 to 35000 (500m) | 2026-10-28 | 2026-10-29
I2S-7688-MP-74.CN.S5.50.15 | Place Bottom Ballast | I.CN.50.13970 | CON - Sec.5 - Place Bottom Ballast - 500m/day - 35000 to 35500 (500m) | 2026-10-29 | 2026-10-30
I2S-7688-MP-74.CN.S5.50.15 | Place Bottom Ballast | I.CN.50.14000 | CON - Sec.5 - Place Bottom Ballast - 500m/day - 36500 to 37000 (500m) | 2026-11-01 | 2026-11-02
I2S-7688-MP-74.CN.S5.50.15 | Place Bottom Ballast | I.CN.50.14010 | CON - Sec.5 - Place Bottom Ballast - 500m/day - 37000 to 37300 (300m) | 2026-11-02 | 2026-11-02
I2S-7688-MP-74.CN.S5.50.15 | Place Bottom Ballast | I.CN.50.13830 | CON - Sec.5 - Place Bottom Ballast - 500m/day - 28300 to 28500 (200m) | 2026-10-13 | 2026-10-14
I2S-7688-MP-74.CN.S5.50.15 | Place Bottom Ballast | I.CN.50.13840 | CON - Sec.5 - Place Bottom Ballast - 500m/day - 28500 to 29000 (500m) | 2026-10-14 | 2026-10-16
I2S-7688-MP-74.CN.S5.50.15 | Place Bottom Ballast | I.CN.50.13850 | CON - Sec.5 - Place Bottom Ballast - 500m/day - 29000 to 29500 (500m) | 2026-10-16 | 2026-10-17
I2S-7688-MP-74.CN.S5.50.15 | Place Bottom Ballast | I.CN.50.13860 | CON - Sec.5 - Place Bottom Ballast - 500m/day - 29500 to 30000 (500m) | 2026-10-17 | 2026-10-18
I2S-7688-MP-74.CN.S5.50.15 | Place Bottom Ballast | I.CN.50.13870 | CON - Sec.5 - Place Bottom Ballast - 500m/day - 30000 to 30500 (500m) | 2026-10-18 | 2026-10-19
I2S-7688-MP-74.CN.S5.50.15 | Place Bottom Ballast | I.CN.50.13880 | CON - Sec.5 - Place Bottom Ballast - 500m/day - 30500 to 31000 (500m) - Powder Horn | 2026-10-19 | 2026-10-20
I2S-7688-MP-74.CN.S5.50.15 | Place Bottom Ballast | I.CN.50.13890 | CON - Sec.5 - Place Bottom Ballast - 500m/day - 31000 to 31500 (500m) | 2026-10-20 | 2026-10-21
I2S-7688-MP-74.CN.S5.50.15 | Place Bottom Ballast | I.CN.50.13900 | CON - Sec.5 - Place Bottom Ballast - 500m/day - 31500 to 32000 (500m) | 2026-10-21 | 2026-10-22
I2S-7688-MP-74.CN.S5.50.15 | Place Bottom Ballast | I.CN.50.13910 | CON - Sec.5 - Place Bottom Ballast - 500m/day - 32000 to 32500 (500m) | 2026-10-22 | 2026-10-23
I2S-7688-MP-74.CN.S5.50.15 | Place Bottom Ballast | I.CN.50.13920 | CON - Sec.5 - Place Bottom Ballast - 500m/day - 22500 to 33000 (500m) | 2026-10-23 | 2026-10-24
I2S-7688-MP-74.CN.S5.50.15 | Place Bottom Ballast | I.CN.50.13930 | CON - Sec.5 - Place Bottom Ballast - 500m/day - 33000 to 33500 (500m) | 2026-10-24 | 2026-10-26
I2S-7688-MP-74.CN.S5.50.15 | Place Bottom Ballast | I.CN.50.13940 | CON - Sec.5 - Place Bottom Ballast - 500m/day - 23500 to 34000 (500m) | 2026-10-26 | 2026-10-27
I2S-7688-MP-74.CN.S5.50.15 | Place Bottom Ballast | I.CN.50.13950 | CON - Sec.5 - Place Bottom Ballast - 500m/day - 34000 to 34500 (500m) | 2026-10-27 | 2026-10-28
I2S-7688-MP-74.CN.S5.50.15 | Place Bottom Ballast | I.CN.50.13980 | CON - Sec.5 - Place Bottom Ballast - 500m/day - 35500 to 36000 (500m) | 2026-10-30 | 2026-10-31
Sleeper Distribution |  |  |  | 2026-10-07 | 2026-11-03
I2S-7688-MP-74.CN.S5.50.1 | Sleeper Distribution | I.CN.50.5140 | CON - Sec.5 - Sleeper Distribution - 860m/day - 33340 to 34030 (860m) | 2026-10-26 | 2026-10-27
I2S-7688-MP-74.CN.S5.50.1 | Sleeper Distribution | I.CN.50.5150 | CON - Sec.5 - Sleeper Distribution - 860m/day - 34030 to 34720 (860m) | 2026-10-27 | 2026-10-28
I2S-7688-MP-74.CN.S5.50.1 | Sleeper Distribution | I.CN.50.5160 | CON - Sec.5 - Sleeper Distribution - 860m/day - 34720 to 35410 (860m) | 2026-10-28 | 2026-10-29
I2S-7688-MP-74.CN.S5.50.1 | Sleeper Distribution | I.CN.50.5170 | CON - Sec.5 - Sleeper Distribution - 860m/day - 35410 to 36100 (860m) | 2026-10-29 | 2026-10-30
I2S-7688-MP-74.CN.S5.50.1 | Sleeper Distribution | I.CN.50.14380 | CON - Sec.5 - Intermediate Sleeper Stockpiles | 2026-10-07 | 2026-10-07
I2S-7688-MP-74.CN.S5.50.1 | Sleeper Distribution | I.CN.50.5180 | CON - Sec.5 - Sleeper Distribution - 860m/day - 36100 to 36790 (860m) | 2026-10-30 | 2026-10-31
I2S-7688-MP-74.CN.S5.50.1 | Sleeper Distribution | I.CN.50.5190 | CON - Sec.5 - Sleeper Distribution - 860m/day - 36790 to 37480 (860m) | 2026-11-02 | 2026-11-03
I2S-7688-MP-74.CN.S5.50.1 | Sleeper Distribution | I.CN.50.5070 | CON - Sec.5 - Sleeper Distribution - 860m/day - 28510 to 29200 (860m) | 2026-10-18 | 2026-10-19
I2S-7688-MP-74.CN.S5.50.1 | Sleeper Distribution | I.CN.50.5080 | CON - Sec.5 - Sleeper Distribution - 860m/day - 29200 to 29890 (860m) | 2026-10-19 | 2026-10-20
I2S-7688-MP-74.CN.S5.50.1 | Sleeper Distribution | I.CN.50.5090 | CON - Sec.5 - Sleeper Distribution - 860m/day - 29890 to 30580 (860m) | 2026-10-20 | 2026-10-21
I2S-7688-MP-74.CN.S5.50.1 | Sleeper Distribution | I.CN.50.5100 | CON - Sec.5 - Sleeper Distribution - 860m/day - 30580 to 31270 (860m) - Powder Horn | 2026-10-21 | 2026-10-22
I2S-7688-MP-74.CN.S5.50.1 | Sleeper Distribution | I.CN.50.5110 | CON - Sec.5 - Sleeper Distribution - 860m/day - 31270 to 31960 (860m) | 2026-10-22 | 2026-10-23
I2S-7688-MP-74.CN.S5.50.1 | Sleeper Distribution | I.CN.50.5120 | CON - Sec.5 - Sleeper Distribution - 860m/day - 31960 to 32650 (860m) | 2026-10-23 | 2026-10-24
I2S-7688-MP-74.CN.S5.50.1 | Sleeper Distribution | I.CN.50.5130 | CON - Sec.5 - Sleeper Distribution - 860m/day - 32650 to 33340 (860m) | 2026-10-24 | 2026-10-26
Sleeper Laying |  |  |  | 2026-10-22 | 2026-11-04
I2S-7688-MP-74.CN.S5.50.3 | Sleeper Laying | I.CN.50.4200 | CON - Sec.5 - Sleeper Laying - 800m/day - 33020 to 34780 | 2026-10-29 | 2026-10-30
I2S-7688-MP-74.CN.S5.50.3 | Sleeper Laying | I.CN.50.4210 | CON - Sec.5 - Sleeper Laying - 800m/day - 33820 to 35500 | 2026-10-30 | 2026-10-31
I2S-7688-MP-74.CN.S5.50.3 | Sleeper Laying | I.CN.50.4220 | CON - Sec.5 - Sleeper Laying - 800m/day - 34620 to 36220 | 2026-10-31 | 2026-11-01
I2S-7688-MP-74.CN.S5.50.3 | Sleeper Laying | I.CN.50.4230 | CON - Sec.5 - Sleeper Laying - 800m/day - 35420 to 36940 | 2026-11-01 | 2026-11-02
I2S-7688-MP-74.CN.S5.50.3 | Sleeper Laying | I.CN.50.4240 | CON - Sec.5 - Sleeper Laying - 800m/day - 36940 to 37660 | 2026-11-03 | 2026-11-04
I2S-7688-MP-74.CN.S5.50.3 | Sleeper Laying | I.CN.50.4130 | CON - Sec.5 - Sleeper Laying - 800m/day - 28220 to 29740 | 2026-10-22 | 2026-10-23
I2S-7688-MP-74.CN.S5.50.3 | Sleeper Laying | I.CN.50.4140 | CON - Sec.5 - Sleeper Laying - 800m/day - 29020 to 30460 | 2026-10-23 | 2026-10-24
I2S-7688-MP-74.CN.S5.50.3 | Sleeper Laying | I.CN.50.4150 | CON - Sec.5 - Sleeper Laying - 800m/day - 29820 to 31180 | 2026-10-24 | 2026-10-26
I2S-7688-MP-74.CN.S5.50.3 | Sleeper Laying | I.CN.50.4160 | CON - Sec.5 - Sleeper Laying - 800m/day - 30620 to 31900 - Powder Horn | 2026-10-26 | 2026-10-27
I2S-7688-MP-74.CN.S5.50.3 | Sleeper Laying | I.CN.50.4180 | CON - Sec.5 - Sleeper Laying - 800m/day - 31420 to 33340 | 2026-10-27 | 2026-10-28
I2S-7688-MP-74.CN.S5.50.3 | Sleeper Laying | I.CN.50.4190 | CON - Sec.5 - Sleeper Laying - 800m/day - 32220 to 34060 | 2026-10-28 | 2026-10-29
Rail Distribution |  |  |  | 2026-11-03 | 2026-11-13
I2S-7688-MP-74.CN.S5.50.2 | Rail Distribution | I.CN.50.4580 | CON - Sec.5 - Rail Distribution - 860m/day - 29920 to 30910 - Powder Horn | 2026-11-04 | 2026-11-06
I2S-7688-MP-74.CN.S5.50.2 | Rail Distribution | I.CN.50.4590 | CON - Sec.5 - Rail Distribution - 860m/day - 30910 to 31900 | 2026-11-06 | 2026-11-07
I2S-7688-MP-74.CN.S5.50.2 | Rail Distribution | I.CN.50.4600 | CON - Sec.5 - Rail Distribution - 860m/day - 31900 to 32890 | 2026-11-07 | 2026-11-08
I2S-7688-MP-74.CN.S5.50.2 | Rail Distribution | I.CN.50.4610 | CON - Sec.5 - Rail Distribution - 860m/day - 32890 to 33880 | 2026-11-08 | 2026-11-09
I2S-7688-MP-74.CN.S5.50.2 | Rail Distribution | I.CN.50.4620 | CON - Sec.5 - Rail Distribution - 860m/day - 33880 to 34870 | 2026-11-09 | 2026-11-10
I2S-7688-MP-74.CN.S5.50.2 | Rail Distribution | I.CN.50.4630 | CON - Sec.5 - Rail Distribution - 860m/day - 34870 to 35860 | 2026-11-10 | 2026-11-11
I2S-7688-MP-74.CN.S5.50.2 | Rail Distribution | I.CN.50.4640 | CON - Sec.5 - Rail Distribution - 860m/day - 35860 to 36850 | 2026-11-11 | 2026-11-12
I2S-7688-MP-74.CN.S5.50.2 | Rail Distribution | I.CN.50.4650 | CON - Sec.5 - Rail Distribution - 860m/day - 36850 to 37840 | 2026-11-12 | 2026-11-13
I2S-7688-MP-74.CN.S5.50.2 | Rail Distribution | I.CN.50.4570 | CON - Sec.5 - Rail Distribution - 860m/day - 28930 to 29920 | 2026-11-03 | 2026-11-04
Rail Laying |  |  |  | 2026-11-07 | 2026-11-20
I2S-7688-MP-74.CN.S5.50.4 | Rail Laying | I.CN.50.3580 | CON - Sec.5 - Rail Laying - 550m/day - 29020 to 29740 | 2026-11-07 | 2026-11-08
I2S-7688-MP-74.CN.S5.50.4 | Rail Laying | I.CN.50.3590 | CON - Sec.5 - Rail Laying - 550m/day - 29740 to 30460 | 2026-11-08 | 2026-11-09
I2S-7688-MP-74.CN.S5.50.4 | Rail Laying | I.CN.50.3600 | CON - Sec.5 - Rail Laying - 550m/day - 30460 to 31180 - Powder Horn | 2026-11-09 | 2026-11-10
I2S-7688-MP-74.CN.S5.50.4 | Rail Laying | I.CN.50.3630 | CON - Sec.5 - Rail Laying - 550m/day - 32620 to 33340 | 2026-11-12 | 2026-11-13
I2S-7688-MP-74.CN.S5.50.4 | Rail Laying | I.CN.50.3640 | CON - Sec.5 - Rail Laying - 550m/day - 33340 to 34060 | 2026-11-13 | 2026-11-14
I2S-7688-MP-74.CN.S5.50.4 | Rail Laying | I.CN.50.3650 | CON - Sec.5 - Rail Laying - 550m/day - 34060 to 34780 | 2026-11-14 | 2026-11-16
I2S-7688-MP-74.CN.S5.50.4 | Rail Laying | I.CN.50.3660 | CON - Sec.5 - Rail Laying - 550m/day - 34780 to 35500 | 2026-11-16 | 2026-11-17
I2S-7688-MP-74.CN.S5.50.4 | Rail Laying | I.CN.50.3670 | CON - Sec.5 - Rail Laying - 550m/day - 35500 to 36220 | 2026-11-17 | 2026-11-18
I2S-7688-MP-74.CN.S5.50.4 | Rail Laying | I.CN.50.3680 | CON - Sec.5 - Rail Laying - 550m/day - 36220 to 36940 | 2026-11-18 | 2026-11-19
I2S-7688-MP-74.CN.S5.50.4 | Rail Laying | I.CN.50.3690 | CON - Sec.5 - Rail Laying - 550m/day - 36940 to 37300 | 2026-11-19 | 2026-11-20
I2S-7688-MP-74.CN.S5.50.4 | Rail Laying | I.CN.50.3610 | CON - Sec.5 - Rail Laying - 550m/day - 31180 to 31900 | 2026-11-10 | 2026-11-11
I2S-7688-MP-74.CN.S5.50.4 | Rail Laying | I.CN.50.3620 | CON - Sec.5 - Rail Laying - 550m/day - 31900 to 32620 | 2026-11-11 | 2026-11-12
Flash Butt Welding and clip up |  |  |  | 2026-11-04 | 2026-11-27
I2S-7688-MP-74.CN.S5.50.5 | Flash Butt Welding and clip up | I.CN.50.3090 | CON - Sec.5 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 28930 to 29920 | 2026-11-04 | 2026-11-07
I2S-7688-MP-74.CN.S5.50.5 | Flash Butt Welding and clip up | I.CN.50.3100 | CON - Sec.5 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 29920 to 30910 - Powder Horn | 2026-11-09 | 2026-11-11
I2S-7688-MP-74.CN.S5.50.5 | Flash Butt Welding and clip up | I.CN.50.3110 | CON - Sec.5 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 30910 to 31900 | 2026-11-11 | 2026-11-13
I2S-7688-MP-74.CN.S5.50.5 | Flash Butt Welding and clip up | I.CN.50.3120 | CON - Sec.5 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 31900 to 32890 | 2026-11-13 | 2026-11-16
I2S-7688-MP-74.CN.S5.50.5 | Flash Butt Welding and clip up | I.CN.50.3130 | CON - Sec.5 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 32890 to 33880 | 2026-11-16 | 2026-11-18
I2S-7688-MP-74.CN.S5.50.5 | Flash Butt Welding and clip up | I.CN.50.3140 | CON - Sec.5 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 33880 to 34870 | 2026-11-18 | 2026-11-20
I2S-7688-MP-74.CN.S5.50.5 | Flash Butt Welding and clip up | I.CN.50.3150 | CON - Sec.5 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 34870 to 35860 | 2026-11-20 | 2026-11-22
I2S-7688-MP-74.CN.S5.50.5 | Flash Butt Welding and clip up | I.CN.50.3160 | CON - Sec.5 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 35860 to 36850 | 2026-11-22 | 2026-11-24
I2S-7688-MP-74.CN.S5.50.5 | Flash Butt Welding and clip up | I.CN.50.3170 | CON - Sec.5 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 36850 to 37300 | 2026-11-24 | 2026-11-27
Place Top Ballast Initial |  |  |  | 2026-11-20 | 2026-11-28
I2S-7688-MP-74.CN.S5.50.6 | Place Top Ballast Initial | I.CN.50.2750 | CON - Sec.5 - Place Top Ballast Initial - 1500m/day - 28720 to 30220 | 2026-11-20 | 2026-11-21
I2S-7688-MP-74.CN.S5.50.6 | Place Top Ballast Initial | I.CN.50.2760 | CON - Sec.5 - Place Top Ballast Initial - 1500m/day - 30220 to 31720 | 2026-11-21 | 2026-11-22
I2S-7688-MP-74.CN.S5.50.6 | Place Top Ballast Initial | I.CN.50.2770 | CON - Sec.5 - Place Top Ballast Initial - 1500m/day - 31720 to 33220 | 2026-11-22 | 2026-11-23
I2S-7688-MP-74.CN.S5.50.6 | Place Top Ballast Initial | I.CN.50.2780 | CON - Sec.5 - Place Top Ballast Initial - 1500m/day - 33200 to 34720 | 2026-11-23 | 2026-11-24
I2S-7688-MP-74.CN.S5.50.6 | Place Top Ballast Initial | I.CN.50.2790 | CON - Sec.5 - Place Top Ballast Initial - 1500m/day - 34720 to 36220 | 2026-11-24 | 2026-11-26
I2S-7688-MP-74.CN.S5.50.6 | Place Top Ballast Initial | I.CN.50.2800 | CON - Sec.5 - Place Top Ballast Initial - 1500m/day - 36220 to 37300 | 2026-11-27 | 2026-11-28
Traverse & Level GEDO |  |  |  | 2026-11-26 | 2026-11-29
I2S-7688-MP-74.CN.S5.50.14 | Traverse & Level GEDO | I.CN.50.18250 | CON - Sec.5 - Traverse and level Gedo Control - 32220 to 36220 | 2026-11-26 | 2026-11-27
I2S-7688-MP-74.CN.S5.50.14 | Traverse & Level GEDO | I.CN.50.18260 | CON - Sec.5 - Traverse and level Gedo Control - Sec.5 - 36220 to 37300 | 2026-11-28 | 2026-11-29
Surfacing Firsts |  |  |  | 2026-11-27 | 2026-11-30
I2S-7688-MP-74.CN.S5.50.7 | Surfacing Firsts | I.CN.50.2580 | CON - Sec.5 - Surfacing Firsts - 4000m/day - 32220 to 36220 | 2026-11-27 | 2026-11-28
I2S-7688-MP-74.CN.S5.50.7 | Surfacing Firsts | I.CN.50.2590 | CON - Sec.5 - Surfacing Firsts - 4000m/day - 36220 to 37300 | 2026-11-29 | 2026-11-30
Surfacing Seconds |  |  |  | 2026-11-28 | 2026-12-01
I2S-7688-MP-74.CN.S5.50.8 | Surfacing Seconds | I.CN.50.2490 | CON - Sec.5 - Surfacing Seconds - 4000m/day - 32220 to 36220 | 2026-11-28 | 2026-11-29
I2S-7688-MP-74.CN.S5.50.8 | Surfacing Seconds | I.CN.50.2500 | CON - Sec.5 - Surfacing Seconds - 4000m/day - 36220 to 37300 | 2026-11-30 | 2026-12-01
Top Ballast Finals |  |  |  | 2026-11-29 | 2026-12-02
I2S-7688-MP-74.CN.S5.50.9 | Top Ballast Finals | I.CN.50.2380 | CON - Sec.5 - Top Ballast Finals - 3000m/day - 30000 to 33000 | 2026-11-29 | 2026-11-30
I2S-7688-MP-74.CN.S5.50.9 | Top Ballast Finals | I.CN.50.2390 | CON - Sec.5 - Top Ballast Finals - 3000m/day - 33000 to 36000 | 2026-11-30 | 2026-12-01
I2S-7688-MP-74.CN.S5.50.9 | Top Ballast Finals | I.CN.50.2400 | CON - Sec.5 - Top Ballast Finals - 3000m/day - 36000 to 37300 | 2026-12-01 | 2026-12-02
Surfacing Final |  |  |  | 2026-12-01 | 2026-12-03
I2S-7688-MP-74.CN.S5.50.10 | Surfacing Final | I.CN.50.2270 | CON - Sec.5 - Surfacing Final - 6000m/day - 30000 to 36000 | 2026-12-01 | 2026-12-02
I2S-7688-MP-74.CN.S5.50.10 | Surfacing Final | I.CN.50.2280 | CON - Sec.5 - Surfacing Final - 6000m/day - 36000 to 37300 | 2026-12-02 | 2026-12-03
Destressing |  |  |  | 2026-12-02 | 2026-12-10
I2S-7688-MP-74.CN.S5.50.11 | Destressing | I.CN.50.2180 | CON - Sec.5 - Destressing - 1200m/day - 33600 to 34800 | 2026-12-07 | 2026-12-08
I2S-7688-MP-74.CN.S5.50.11 | Destressing | I.CN.50.2140 | CON - Sec.5 - Destressing - 1200m/day - 28800 to 30000 | 2026-12-02 | 2026-12-03
I2S-7688-MP-74.CN.S5.50.11 | Destressing | I.CN.50.2150 | CON - Sec.5 - Destressing - 1200m/day - 30000 to 31200 | 2026-12-03 | 2026-12-04
I2S-7688-MP-74.CN.S5.50.11 | Destressing | I.CN.50.2160 | CON - Sec.5 - Destressing - 1200m/day - 31200 to 32400 | 2026-12-04 | 2026-12-06
I2S-7688-MP-74.CN.S5.50.11 | Destressing | I.CN.50.2190 | CON - Sec.5 - Destressing - 1200m/day - 34800 to 36000 | 2026-12-08 | 2026-12-09
I2S-7688-MP-74.CN.S5.50.11 | Destressing | I.CN.50.2200 | CON - Sec.5 - Destressing - 1200m/day - 36000 to 37300 | 2026-12-09 | 2026-12-10
I2S-7688-MP-74.CN.S5.50.11 | Destressing | I.CN.50.2170 | CON - Sec.5 - Destressing - 1200m/day - 32400 to 33600 | 2026-12-06 | 2026-12-07
Corrections + Signage + Rubber Xings |  |  |  | 2026-12-06 | 2026-12-11
I2S-7688-MP-74.CN.S5.50.12 | Corrections + Signage + Rubber Xings | I.CN.50.1880 | CON - Sec.5 - Corrections + Signage - 2000m/day - 36000 - 38000 | 2026-12-10 | 2026-12-11
I2S-7688-MP-74.CN.S5.50.12 | Corrections + Signage + Rubber Xings | I.CN.50.1850 | CON - Sec.5 - Corrections + Signage - 2000m/day - 30000 - 32000 | 2026-12-06 | 2026-12-07
I2S-7688-MP-74.CN.S5.50.12 | Corrections + Signage + Rubber Xings | I.CN.50.1860 | CON - Sec.5 - Corrections + Signage - 2000m/day - 32000 - 34000 | 2026-12-07 | 2026-12-08
I2S-7688-MP-74.CN.S5.50.12 | Corrections + Signage + Rubber Xings | I.CN.50.1870 | CON - Sec.5 - Corrections + Signage - 2000m/day - 34000 - 36000 | 2026-12-09 | 2026-12-10
Track Joint Inspection |  |  |  | 2026-12-09 | 2026-12-11
I2S-7688-MP-74.CN.S5.50.13 | Track Joint Inspection | I.CN.50.1680 | CON - Sec.5 - Track Joint Inspection - 5000m/day - 28300 - 32300 | 2026-12-09 | 2026-12-10
I2S-7688-MP-74.CN.S5.50.13 | Track Joint Inspection | I.CN.50.1690 | CON - Sec.5 - Track Joint Inspection - 5000m/day - 32300 - 37300 | 2026-12-10 | 2026-12-11
062 - Bridges |  |  |  | 2025-12-04 | 2026-07-11
Powder Horn Creek Bridge - BR708 - Standard PSC Slab Span 14m (ARTC) |  |  |  | 2025-12-04 | 2026-07-11
Preliminaries |  |  |  | 2025-12-04 | 2025-12-16
I2S-7688-MP-74.CN.S5.62.2.1 | Preliminaries | I.CN.62.16740 | CON - Sec.5 - Powder Horn Ck Br - Construct site access | 2025-12-10 | 2025-12-11
I2S-7688-MP-74.CN.S5.62.2.1 | Preliminaries | I.CN.62.16830 | CON - Sec.5 - Powder Horn Ck Br - Construct laydown area /Causeway (inc pipes) | 2025-12-12 | 2025-12-16
I2S-7688-MP-74.CN.S5.62.2.1 | Preliminaries | I.CN.62.16730 | CON - Sec.5 - Powder Horn Ck Br - Bridge site prep /Temp Fence/Road Barriers | 2025-12-04 | 2025-12-09
Piling |  |  |  | 2025-12-17 | 2026-03-04
Platforms |  |  |  | 2025-12-17 | 2026-01-07
I2S-7688-MP-74.CN.S5.62.2.2.1 | Platforms | I.CN.62.16840 | CON - Sec.5 - Powder Horn Ck Br - Place and test platform | 2026-01-06 | 2026-01-07
I2S-7688-MP-74.CN.S5.62.2.2.1 | Platforms | I.CN.62.16790 | CON - Sec.5 - Powder Horn Ck Br - Excavate platform for piling pad | 2025-12-17 | 2026-01-05
Drill Piles |  |  |  | 2026-02-22 | 2026-03-04
I2S-7688-MP-74.CN.S5.62.2.2.3 | Drill Piles | I.CN.62.22290 | CON - Sec.5 - Powder Horn Ck Br - Pour and Finish Concrete
I2S-7688-MP-74.CN.S5.62.2.2.3 | Drill Piles | I.CN.62.16800 | CON - Sec.5 - Powder Horn Ck Br - Demobilise piling rig | 2026-03-04 | 2026-03-04
I2S-7688-MP-74.CN.S5.62.2.2.3 | Drill Piles | I.CN.62.16850 | CON - Sec.5 - Powder Horn Ck Br - Mobilise piling rig | 2026-02-22 | 2026-02-22
I2S-7688-MP-74.CN.S5.62.2.2.3 | Drill Piles | I.CN.62.16860 | CON - Sec.5 - Powder Horn Ck Br - abutment piling consists of 4 x 900mm dia bored concrete piles | 2026-02-23 | 2026-02-27
I2S-7688-MP-74.CN.S5.62.2.2.3 | Drill Piles | I.CN.62.19640 | CON - Sec.5 - Powder Horn Ck Br - pier piling consist of 2 x 1200mm dia bored concrete piles | 2026-02-28 | 2026-03-03
I2S-7688-MP-74.CN.S5.62.2.2.3 | Drill Piles | I.CN.62.23020 | CON - Sec.5 - Powder Horn Ck Br - abutment piling - Milestone
Piers |  |  |  | 2026-03-06 | 2026-04-12
Pier No 1 |  |  |  | 2026-03-06 | 2026-04-02
I2S-7688-MP-74.CN.S5.62.2.8.1 | Pier No 1 | I.CN.62.22300 | CON - Sec.5 - Powder Horn Ck Br - FRP - Restraint Block - Pier 1
I2S-7688-MP-74.CN.S5.62.2.8.1 | Pier No 1 | I.CN.62.22360 | CON - Sec.5 - Powder Horn Ck Br - FRP - FRP Bearing Mortar Pads - Pier 1
I2S-7688-MP-74.CN.S5.62.2.8.1 | Pier No 1 | I.CN.62.21510 | CON - Sec.5 - Powder Horn Ck Br - FRP - Column Extension - Pier 1 | 2026-03-21 | 2026-03-27
I2S-7688-MP-74.CN.S5.62.2.8.1 | Pier No 1 | I.CN.62.21530 | CON - Sec.5 - Powder Horn Ck Br - FRP - Headstock - Pier 1 | 2026-03-28 | 2026-04-02
I2S-7688-MP-74.CN.S5.62.2.8.1 | Pier No 1 | I.CN.62.16750 | CON - Sec.5 - Powder Horn Ck Br - Detailed Earthworks - Pier 1 | 2026-03-06 | 2026-03-08
Pier No 2 |  |  |  | 2026-03-21 | 2026-04-12
I2S-7688-MP-74.CN.S5.62.2.8.2 | Pier No 2 | I.CN.62.22310 | CON - Sec.5 - Powder Horn Ck Br - FRP - Restraint Block - Pier 2
I2S-7688-MP-74.CN.S5.62.2.8.2 | Pier No 2 | I.CN.62.22370 | CON - Sec.5 - Powder Horn Ck Br - FRP - FRP Bearing Mortar Pads - Pier 2
I2S-7688-MP-74.CN.S5.62.2.8.2 | Pier No 2 | I.CN.62.21520 | CON - Sec.5 - Powder Horn Ck Br - FRP - Column Extension - Pier 2 | 2026-03-31 | 2026-04-06
I2S-7688-MP-74.CN.S5.62.2.8.2 | Pier No 2 | I.CN.62.16900 | CON - Sec.5 - Powder Horn Ck Br - Detailed Earthworks Pier 2 | 2026-03-21 | 2026-03-23
I2S-7688-MP-74.CN.S5.62.2.8.2 | Pier No 2 | I.CN.62.16930 | CON - Sec.5 - Powder Horn Ck Br - FRP - headstock - Pier 2 | 2026-04-07 | 2026-04-12
Abutments |  |  |  | 2026-04-13 | 2026-05-30
South |  |  |  | 2026-04-13 | 2026-05-30
I2S-7688-MP-74.CN.S5.62.2.7.1 | South | I.CN.62.21550 | CON - Sec.5 - Powder Horn Ck Br - FRP Restraint Blocks - South Abutment | 2026-05-24 | 2026-05-30
I2S-7688-MP-74.CN.S5.62.2.7.1 | South | I.CN.62.16950 | CON - Sec.5 - Powder Horn Ck Br - Detailed Earthworks - South Abutment | 2026-04-13 | 2026-04-22
I2S-7688-MP-74.CN.S5.62.2.7.1 | South | I.CN.62.16960 | CON - Sec.5 - Powder Horn Ck Br - FRP Cill Beam - South Abutment | 2026-04-30 | 2026-05-05
I2S-7688-MP-74.CN.S5.62.2.7.1 | South | I.CN.62.22340 | CON - Sec.5 - Powder Horn Ck Br - FRP Wing Walls - South Abutment
I2S-7688-MP-74.CN.S5.62.2.7.1 | South | I.CN.62.22350 | CON - Sec.5 - Powder Horn Ck Br - FRP Bearing Mortar Pads - South Abutment
I2S-7688-MP-74.CN.S5.62.2.7.1 | South | I.CN.62.16980 | CON - Sec.5 - Powder Horn Ck Br - FRP Back Wall - South Abutment | 2026-05-12 | 2026-05-18
North |  |  |  | 2026-04-23 | 2026-05-11
I2S-7688-MP-74.CN.S5.62.2.7.2 | North | I.CN.62.19920 | CON - Sec.5 - Powder Horn Ck Br - FRP Cill Beam - North Abutment | 2026-04-23 | 2026-04-29
I2S-7688-MP-74.CN.S5.62.2.7.2 | North | I.CN.62.16970 | CON - Sec.5 - Powder Horn Ck Br - FRP Back Wall North Abutment | 2026-05-06 | 2026-05-11
I2S-7688-MP-74.CN.S5.62.2.7.2 | North | I.CN.62.22320 | CON - Sec.5 - Powder Horn Ck Br - Detailed Earthworks - North Abutment
I2S-7688-MP-74.CN.S5.62.2.7.2 | North | I.CN.62.22330 | CON - Sec.5 - Powder Horn Ck Br - FRP Restraint Blocks - North Abutment
I2S-7688-MP-74.CN.S5.62.2.7.2 | North | I.CN.62.22380 | CON - Sec.5 - Powder Horn Ck Br - FRP Wing Walls - North Abutment
I2S-7688-MP-74.CN.S5.62.2.7.2 | North | I.CN.62.22390 | CON - Sec.5 - Powder Horn Ck Br - FRP Bearing Mortar Pads - North Abutment
Superstructure |  |  |  | 2026-06-07 | 2026-07-04
I2S-7688-MP-74.CN.S5.62.2.4 | Superstructure | I.CN.62.17050 | CON - Sec.5 - Powder Horn Ck Br - Crane pads for lift | 2026-06-07 | 2026-06-07
I2S-7688-MP-74.CN.S5.62.2.4 | Superstructure | I.CN.62.17060 | CON - Sec.5 - Powder Horn Ck Br - Install bridge bearings | 2026-06-08 | 2026-06-09
I2S-7688-MP-74.CN.S5.62.2.4 | Superstructure | I.CN.62.17100 | CON - Sec.5 - Powder Horn Creek Bridge -Install/Lift Bridge span (PSC Plank x 18) | 2026-06-10 | 2026-06-13
I2S-7688-MP-74.CN.S5.62.2.4 | Superstructure | I.CN.62.17020 | CON - Sec.5 - Powder Horn Ck Br - Install handrail raking/horizontal | 2026-06-29 | 2026-07-01
I2S-7688-MP-74.CN.S5.62.2.4 | Superstructure | I.CN.62.17030 | CON - Sec.5 - Powder Horn Ck Br - Install access walkways | 2026-07-02 | 2026-07-04
I2S-7688-MP-74.CN.S5.62.2.4 | Superstructure | I.CN.62.22400 | CON - Sec.5 - Powder Horn Creek Bridge - Delivery of PSC Planks (x18)
I2S-7688-MP-74.CN.S5.62.2.4 | Superstructure | I.CN.62.22410 | CON - Sec.5 - Powder Horn Ck Br - Install & Stress Tie Bars
Approach Slab / Deck |  |  |  | 2026-05-12 | 2026-06-22
I2S-7688-MP-74.CN.S5.62.2.3 | Approach Slab / Deck | I.CN.62.16920 | CON - Sec.5 - Powder Horn Ck Br - FRP Approach Slab North | 2026-05-12 | 2026-05-18
I2S-7688-MP-74.CN.S5.62.2.3 | Approach Slab / Deck | I.CN.62.17140 | CON - Sec.5 - Powder Horn Ck Br - Install Parapets | 2026-06-19 | 2026-06-22
I2S-7688-MP-74.CN.S5.62.2.3 | Approach Slab / Deck | I.CN.62.19930 | CON - Sec.5 - Powder Horn Ck Br - FRP Approach Slab South | 2026-05-31 | 2026-06-06
I2S-7688-MP-74.CN.S5.62.2.3 | Approach Slab / Deck | I.CN.62.19940 | CON - Sec.5 - Powder Horn Ck Br - FRP Wing Walls - North side 2 No | 2026-05-19 | 2026-05-24
I2S-7688-MP-74.CN.S5.62.2.3 | Approach Slab / Deck | I.CN.62.19950 | CON - Sec.5 - Powder Horn Ck Br - FRP Wing Walls - South side 2 No. | 2026-06-07 | 2026-06-12
Finishing Works |  |  |  | 2026-06-26 | 2026-07-11
I2S-7688-MP-74.CN.S5.62.2.5 | Finishing Works | I.CN.62.17040 | CON - Sec.5 - Powder Horn Ck Br - FRP Footpath/Steps | 2026-07-06 | 2026-07-11
I2S-7688-MP-74.CN.S5.62.2.5 | Finishing Works | I.CN.62.19350 | CON - Sec.5 - Powder Horn Ck Br - Completion |  | 2026-07-11
I2S-7688-MP-74.CN.S5.62.2.5 | Finishing Works | I.CN.62.16780 | CON - Sec.5 - Powder Horn Ck Br - Batter Slopes & Install "Nylex Cordrain" fixed to vertical face of ballast walls | 2026-06-29 | 2026-07-07
I2S-7688-MP-74.CN.S5.62.2.5 | Finishing Works | I.CN.62.17010 | CON - Sec.5 - Powder Horn Ck Br - Install bridge barriers | 2026-06-26 | 2026-06-28
I2S-7688-MP-74.CN.S5.62.2.5 | Finishing Works | I.CN.62.22420 | CON - Sec.5 - Powder Horn Ck Br - Install CSR Ducting
I2S-7688-MP-74.CN.S5.62.2.5 | Finishing Works | I.CN.62.22430 | CON - Sec.5 - Powder Horn Ck Br - Install Handrails
065 - Crossings |  |  |  | 2025-12-13 | 2026-12-13
Fauna Crossing |  |  |  | 2026-12-10 | 2026-12-13
I2S-7688-MP-74.CN.S5.65.5 | Fauna Crossing | I.CN.65.12840 | CON - Sec.5 - Install fauna crossing, [2 x poles foundations /cure - CH36000] | 2026-12-10 | 2026-12-12
I2S-7688-MP-74.CN.S5.65.5 | Fauna Crossing | I.CN.65.17860 | CON - Sec.5 - Install fauna crossing, [2 x poles with rope bridge - CH36000] | 2026-12-12 | 2026-12-13
Stock Crossings |  |  |  | 2025-12-13 | 2026-01-07
Culvert ID : E7-SU-453640-1 / Type : 1*3000x3000mm RCBC / Ch36110 (7.2m) |  |  |  | 2025-12-13 | 2026-01-07
I2S-7688-MP-74.CN.S5.65.6.8 | Culvert ID : E7-SU-453640-1 / Type : 1*3000x3000mm RCBC / Ch36110 (7.2m) | I.CN.34.20770 | CON - Sec.5 - Culvert : E7-SU-453640-1 - Detail backfill | 2026-01-06 | 2026-01-06
I2S-7688-MP-74.CN.S5.65.6.8 | Culvert ID : E7-SU-453640-1 / Type : 1*3000x3000mm RCBC / Ch36110 (7.2m) | I.CN.34.20780 | CON - Sec.5 - Culvert : E7-SU-453640-1 - Construct Scour protection | 2026-01-06 | 2026-01-07
I2S-7688-MP-74.CN.S5.65.6.8 | Culvert ID : E7-SU-453640-1 / Type : 1*3000x3000mm RCBC / Ch36110 (7.2m) | I.CN.34.28560 | CON - Sec.5 - Culvert : E7-SU-453640-1 - Place RCBC crown units
I2S-7688-MP-74.CN.S5.65.6.8 | Culvert ID : E7-SU-453640-1 / Type : 1*3000x3000mm RCBC / Ch36110 (7.2m) | I.CN.34.20670 | CON - Sec.5 - Culvert : E7-SU-453640-1 - Site Prep / Detail Excavation | 2025-12-13 | 2025-12-14
I2S-7688-MP-74.CN.S5.65.6.8 | Culvert ID : E7-SU-453640-1 / Type : 1*3000x3000mm RCBC / Ch36110 (7.2m) | I.CN.34.20680 | CON - Sec.5 - Culvert : E7-SU-453640-1 - Struc fill Placement (250mm) | 2025-12-16 | 2025-12-17
I2S-7688-MP-74.CN.S5.65.6.8 | Culvert ID : E7-SU-453640-1 / Type : 1*3000x3000mm RCBC / Ch36110 (7.2m) | I.CN.34.20720 | CON - Sec.5 - Culvert : E7-SU-453640-1 - FRP Base Slab / Apron Slab / Cut-off Wall | 2025-12-18 | 2025-12-19
I2S-7688-MP-74.CN.S5.65.6.8 | Culvert ID : E7-SU-453640-1 / Type : 1*3000x3000mm RCBC / Ch36110 (7.2m) | I.CN.34.20730 | CON - Sec.5 - Culvert : E7-SU-453640-1 - 7 day Curing | 2025-12-20 | 2025-12-20
I2S-7688-MP-74.CN.S5.65.6.8 | Culvert ID : E7-SU-453640-1 / Type : 1*3000x3000mm RCBC / Ch36110 (7.2m) | I.CN.34.20750 | CON - Sec.5 - Culvert : E7-SU-453640-1 - Place Pre-cast Wingwalls and Stich Pour | 2025-12-21 | 2025-12-22
I2S-7688-MP-74.CN.S5.65.6.8 | Culvert ID : E7-SU-453640-1 / Type : 1*3000x3000mm RCBC / Ch36110 (7.2m) | I.CN.34.20760 | CON - Sec.5 - Culvert : E7-SU-453640-1 - Pre-cast RCBC completion (Seal joints) | 2025-12-23 | 2026-01-05
I2S-7688-MP-74.CN.S5.65.6.8 | Culvert ID : E7-SU-453640-1 / Type : 1*3000x3000mm RCBC / Ch36110 (7.2m) | I.CN.34.31970 | CON - Sec.5 - Culvert : E7-SU-453640-1 - Blinding placement (50mm)
I2S-7688-MP-74.CN.S5.65.6.8 | Culvert ID : E7-SU-453640-1 / Type : 1*3000x3000mm RCBC / Ch36110 (7.2m) | I.CN.34.32810 | CON - Sec.5 - Culvert : E7-SU-453640-1 - FRP Base Slab / Apron Slab / Cut-off Wall - Milestone
Private LX - Kepreotes (PR34950) - Passive / Private - RX-2 |  |  |  | 2026-04-27 | 2026-05-12
Civils |  |  |  | 2026-04-27 | 2026-04-27
I2S-7688-MP-74.CN.S5.65.4.1 | Civils | I.CN.11.14120 | CON - Sec.5 - Private LX - Kepreotes (PR34950) - Clear and Grub | 2026-04-27 | 2026-04-27
Earthworks/Drainage |  |  |  | 2026-04-28 | 2026-05-06
Culvert ID : E7-RD-452450-1 / Type : 1*900mm HDPE / Ch34947 (15.46m each) |  |  |  | 2026-05-02 | 2026-05-06
I2S-7688-MP-74.CN.S5.65.4.5.13 | Culvert ID : E7-RD-452450-1 / Type : 1*900mm HDPE / Ch34947 (15.46m each) | I.CN.34.29270 | CON - Sec.5 - Culvert : E7-RD-452450-1 - Construct Scour Protection
I2S-7688-MP-74.CN.S5.65.4.5.13 | Culvert ID : E7-RD-452450-1 / Type : 1*900mm HDPE / Ch34947 (15.46m each) | I.CN.34.29230 | CON - Sec.5 - Culvert : E7-RD-452450-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S5.65.4.5.13 | Culvert ID : E7-RD-452450-1 / Type : 1*900mm HDPE / Ch34947 (15.46m each) | I.CN.34.29240 | CON - Sec.5 - Culvert : E7-RD-452450-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S5.65.4.5.13 | Culvert ID : E7-RD-452450-1 / Type : 1*900mm HDPE / Ch34947 (15.46m each) | I.CN.34.29250 | CON - Sec.5 - Culvert : E7-RD-452450-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S5.65.4.5.13 | Culvert ID : E7-RD-452450-1 / Type : 1*900mm HDPE / Ch34947 (15.46m each) | I.CN.65.17110 | CON - Sec.5 - Culvert : E7-RD-452450-1 - Site Prep / Detail Excavation | 2026-05-02 | 2026-05-03
I2S-7688-MP-74.CN.S5.65.4.5.13 | Culvert ID : E7-RD-452450-1 / Type : 1*900mm HDPE / Ch34947 (15.46m each) | I.CN.65.17120 | CON - Sec.5 - Culvert : E7-RD-452450-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-05-04 | 2026-05-04
I2S-7688-MP-74.CN.S5.65.4.5.13 | Culvert ID : E7-RD-452450-1 / Type : 1*900mm HDPE / Ch34947 (15.46m each) | I.CN.65.17130 | CON - Sec.5 - Culvert : E7-RD-452450-1 - Headwall installation | 2026-05-05 | 2026-05-06
Culvert ID : E7-RD-452460-1 / Type : 1*900mm HDPE / Ch34947 (15.04m each) |  |  |  | 2026-04-28 | 2026-05-02
I2S-7688-MP-74.CN.S5.65.4.5.1 | Culvert ID : E7-RD-452460-1 / Type : 1*900mm HDPE / Ch34947 (15.04m each) | I.CN.65.13350 | CON - Sec.5 - Private LX - Culvert : E7-RD-452460-1 - Construct Scour Protection | 2026-05-01 | 2026-05-02
I2S-7688-MP-74.CN.S5.65.4.5.1 | Culvert ID : E7-RD-452460-1 / Type : 1*900mm HDPE / Ch34947 (15.04m each) | I.CN.65.13330 | CON - Sec.5 - Private LX - Culvert : E7-RD-452460-1 - Site Prep / Detail Excavation | 2026-04-28 | 2026-04-29
I2S-7688-MP-74.CN.S5.65.4.5.1 | Culvert ID : E7-RD-452460-1 / Type : 1*900mm HDPE / Ch34947 (15.04m each) | I.CN.65.13340 | CON - Sec.5 - Private LX - Culvert : E7-RD-452460-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-04-30 | 2026-04-30
I2S-7688-MP-74.CN.S5.65.4.5.1 | Culvert ID : E7-RD-452460-1 / Type : 1*900mm HDPE / Ch34947 (15.04m each) | I.CN.65.18891 | CON - Sec.5 - Private LX - Culvert : E7-RD-452460-1 - Headwall installation
I2S-7688-MP-74.CN.S5.65.4.5.1 | Culvert ID : E7-RD-452460-1 / Type : 1*900mm HDPE / Ch34947 (15.04m each) | I.CN.65.18901 | CON - Sec.5 - Private LX - Culvert : E7-RD-452460-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S5.65.4.5.1 | Culvert ID : E7-RD-452460-1 / Type : 1*900mm HDPE / Ch34947 (15.04m each) | I.CN.65.18911 | CON - Sec.5 - Private LX - Culvert : E7-RD-452460-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S5.65.4.5.1 | Culvert ID : E7-RD-452460-1 / Type : 1*900mm HDPE / Ch34947 (15.04m each) | I.CN.65.18921 | CON - Sec.5 - Private LX - Culvert : E7-RD-452460-1 - Headwall Cut-off Wall Installation (FRP)
Culvert ID : E7-RD-452440-1 / Type : 1*750mm HDPE / Ch34946 (20.68m each) |  |  |  | 2026-04-30 | 2026-05-04
I2S-7688-MP-74.CN.S5.65.4.5.3 | Culvert ID : E7-RD-452440-1 / Type : 1*750mm HDPE / Ch34946 (20.68m each) | I.CN.65.17090 | CON - Sec.5 - Private LX - Culvert : E7-RD-452440-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-05-02 | 2026-05-02
I2S-7688-MP-74.CN.S5.65.4.5.3 | Culvert ID : E7-RD-452440-1 / Type : 1*750mm HDPE / Ch34946 (20.68m each) | I.CN.65.17100 | CON - Sec.5 - Private LX - Culvert : E7-RD-452440-1 - Construct Scour Protection | 2026-05-03 | 2026-05-04
I2S-7688-MP-74.CN.S5.65.4.5.3 | Culvert ID : E7-RD-452440-1 / Type : 1*750mm HDPE / Ch34946 (20.68m each) | I.CN.65.18931 | CON - Sec.5 - Private LX - Culvert : E7-RD-452440-1 - Headwall installation
I2S-7688-MP-74.CN.S5.65.4.5.3 | Culvert ID : E7-RD-452440-1 / Type : 1*750mm HDPE / Ch34946 (20.68m each) | I.CN.65.18941 | CON - Sec.5 - Private LX - Culvert : E7-RD-452440-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S5.65.4.5.3 | Culvert ID : E7-RD-452440-1 / Type : 1*750mm HDPE / Ch34946 (20.68m each) | I.CN.65.18951 | CON - Sec.5 - Private LX - Culvert : E7-RD-452440-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S5.65.4.5.3 | Culvert ID : E7-RD-452440-1 / Type : 1*750mm HDPE / Ch34946 (20.68m each) | I.CN.65.18961 | CON - Sec.5 - Private LX - Culvert : E7-RD-452440-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S5.65.4.5.3 | Culvert ID : E7-RD-452440-1 / Type : 1*750mm HDPE / Ch34946 (20.68m each) | I.CN.65.17080 | CON - Sec.5 - Private LX - Culvert : E7-RD-452440-1 - Site Prep / Detail Excavation | 2026-04-30 | 2026-05-01
Roadworks |  |  |  | 2026-04-28 | 2026-05-06
I2S-7688-MP-74.CN.S5.65.4.6 | Roadworks | I.CN.65.13430 | CON - Sec.5 - Private LX - Kepreotes (PR34950) - Civil Works complete |  | 2026-05-06
I2S-7688-MP-74.CN.S5.65.4.6 | Roadworks | I.CN.65.13360 | CON - Sec.5 - Private LX - Kepreotes (PR34950) - Earthworks | 2026-04-28 | 2026-04-29
I2S-7688-MP-74.CN.S5.65.4.6 | Roadworks | I.CN.65.13370 | CON - Sec.5 - Private LX - Kepreotes (PR34950) - Pavement type A Unsealed (285m2) | 2026-04-30 | 2026-04-30
I2S-7688-MP-74.CN.S5.65.4.6 | Roadworks | I.CN.65.13450 | CON - Sec.5 - Private LX - Kepreotes (PR34950) - Batter face area (170 m3) | 2026-05-01 | 2026-05-01
I2S-7688-MP-74.CN.S5.65.4.6 | Roadworks | I.CN.65.13460 | CON - Sec.5 - Private LX - Kepreotes (PR34950) - Prime & Cure - Pavement type B sealed (230m2) | 2026-05-01 | 2026-05-01
I2S-7688-MP-74.CN.S5.65.4.6 | Roadworks | I.CN.65.13470 | CON - Sec.5 - Private LX - Kepreotes (PR34950) - Seal /linemarking | 2026-05-05 | 2026-05-05
Trackworks |  |  |  | 2026-05-07 | 2026-05-09
I2S-7688-MP-74.CN.S5.65.4.7 | Trackworks | I.CN.65.13390 | CON - Sec.5 - Private LX - Kepreotes (PR34950) - Place and compact ballast between foundation block (after road | 2026-05-08 | 2026-05-08
I2S-7688-MP-74.CN.S5.65.4.7 | Trackworks | I.CN.65.13400 | CON - Sec.5 - Private LX - Kepreotes (PR34950) - Tie-in works to foundation block | 2026-05-09 | 2026-05-09
I2S-7688-MP-74.CN.S5.65.4.7 | Trackworks | I.CN.65.13380 | CON - Sec.5 - Private LX - Kepreotes (PR34950) - Place Foundation Block and T-Kerbstone | 2026-05-07 | 2026-05-07
Ancillary |  |  |  | 2026-05-10 | 2026-05-12
I2S-7688-MP-74.CN.S5.65.4.8 | Ancillary | I.CN.65.13410 | CON - Sec.5 - Private LX - Kepreotes (PR34950) - Install Fencing | 2026-05-10 | 2026-05-10
I2S-7688-MP-74.CN.S5.65.4.8 | Ancillary | I.CN.65.13420 | CON - Sec.5 - Private LX - Kepreotes (PR34950) - Install Signage | 2026-05-11 | 2026-05-11
I2S-7688-MP-74.CN.S5.65.4.8 | Ancillary | I.CN.65.13440 | CON - Sec.5 - Private LX - Kepreotes (PR34950) - Install Gates | 2026-05-12 | 2026-05-12
Commissioning |  |  |  | 2026-05-12 | 2026-05-12
I2S-7688-MP-74.CN.S5.65.4.4 | Commissioning | I.CN.65.13500 | CON - Sec.5 - Private LX - Kepreotes (PR34950) - Open |  | 2026-05-12
Public LX - Corbys Lane (PU33780) - Passive / Cootamundra LGA - RX-2 |  |  |  | 2026-04-26 | 2026-05-12
Civils |  |  |  | 2026-04-26 | 2026-04-26
I2S-7688-MP-74.CN.S5.65.3.1 | Civils | I.CN.11.14150 | CON - Sec.5 - Public LX - Corbys Lane (PU33780) - Clear and Grub | 2026-04-26 | 2026-04-26
Earthworks/Drainage |  |  |  | 2026-04-27 | 2026-04-30
Culvert ID : E7-RD-451282-1 / Type : 2*1200x600mm RCBC / Ch33774 (36m each) |  |  |  | 2026-04-27 | 2026-04-30
I2S-7688-MP-74.CN.S5.65.3.5.1 | Culvert ID : E7-RD-451282-1 / Type : 2*1200x600mm RCBC / Ch33774 (36m each) | I.CN.65.13870 | CON - Sec.5 - Public LX - PU33766 - Drainage - LX Culvert - Site Prep / Detail Excavation | 2026-04-27 | 2026-04-28
I2S-7688-MP-74.CN.S5.65.3.5.1 | Culvert ID : E7-RD-451282-1 / Type : 2*1200x600mm RCBC / Ch33774 (36m each) | I.CN.65.13880 | CON - Sec.5 - Public LX - PU33766 - Drainage - Struc fill Placement (250mm) | 2026-04-29 | 2026-04-29
I2S-7688-MP-74.CN.S5.65.3.5.1 | Culvert ID : E7-RD-451282-1 / Type : 2*1200x600mm RCBC / Ch33774 (36m each) | I.CN.65.13890 | CON - Sec.5 - Public LX - PU33766 - Drainage - Construct Scour protection | 2026-04-30 | 2026-04-30
I2S-7688-MP-74.CN.S5.65.3.5.1 | Culvert ID : E7-RD-451282-1 / Type : 2*1200x600mm RCBC / Ch33774 (36m each) | I.CN.65.19251 | CON - Sec.5 - Public LX - PU33766 - Drainage - Blinding placement (50mm)
I2S-7688-MP-74.CN.S5.65.3.5.1 | Culvert ID : E7-RD-451282-1 / Type : 2*1200x600mm RCBC / Ch33774 (36m each) | I.CN.65.19261 | CON - Sec.5 - Public LX - PU33766 - Drainage - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.CN.S5.65.3.5.1 | Culvert ID : E7-RD-451282-1 / Type : 2*1200x600mm RCBC / Ch33774 (36m each) | I.CN.65.19271 | CON - Sec.5 - Public LX - PU33766 - Drainage - 7 day Curing
I2S-7688-MP-74.CN.S5.65.3.5.1 | Culvert ID : E7-RD-451282-1 / Type : 2*1200x600mm RCBC / Ch33774 (36m each) | I.CN.65.19281 | CON - Sec.5 - Public LX - PU33766 - Drainage - Place RCBC crown units
I2S-7688-MP-74.CN.S5.65.3.5.1 | Culvert ID : E7-RD-451282-1 / Type : 2*1200x600mm RCBC / Ch33774 (36m each) | I.CN.65.19291 | CON - Sec.5 - Public LX - PU33766 - Drainage - Place Precast headwall and precast stich pours
I2S-7688-MP-74.CN.S5.65.3.5.1 | Culvert ID : E7-RD-451282-1 / Type : 2*1200x600mm RCBC / Ch33774 (36m each) | I.CN.65.19301 | CON - Sec.5 - Public LX - PU33766 - Drainage - Pre-cast RCBC completion (Seal joints)
I2S-7688-MP-74.CN.S5.65.3.5.1 | Culvert ID : E7-RD-451282-1 / Type : 2*1200x600mm RCBC / Ch33774 (36m each) | I.CN.65.19311 | CON - Sec.5 - Public LX - PU33766 - Drainage - Detail backfill
Roadworks |  |  |  | 2026-04-27 | 2026-05-06
I2S-7688-MP-74.CN.S5.65.3.6 | Roadworks | I.CN.65.14000 | CON - Sec.5 - Public LX - Corbys Lane (PU33780) - Prime & Cure - Pavement type B sealed (930m2) | 2026-05-02 | 2026-05-03
I2S-7688-MP-74.CN.S5.65.3.6 | Roadworks | I.CN.65.14010 | CON - Sec.5 - Public LX - Corbys Lane (PU33780) - Seal /linemarking | 2026-05-04 | 2026-05-04
I2S-7688-MP-74.CN.S5.65.3.6 | Roadworks | I.CN.65.13900 | CON - Sec.5 - Public LX - Corbys Lane (PU33780) - Earthworks | 2026-04-27 | 2026-04-28
I2S-7688-MP-74.CN.S5.65.3.6 | Roadworks | I.CN.65.13970 | CON - Sec.5 - Public LX - Corbys Lane (PU33780) - Civil Works complete |  | 2026-05-06
I2S-7688-MP-74.CN.S5.65.3.6 | Roadworks | I.CN.65.13910 | CON - Sec.5 - Public LX - Corbys Lane (PU33780) - Pavement type A Unsealed (5m2) | 2026-04-29 | 2026-04-29
I2S-7688-MP-74.CN.S5.65.3.6 | Roadworks | I.CN.65.13990 | CON - Sec.5 - Public LX - Corbys Lane (PU33780) - Batter face area (460 m3) | 2026-04-30 | 2026-05-01
Trackworks |  |  |  | 2026-05-07 | 2026-05-09
I2S-7688-MP-74.CN.S5.65.3.7 | Trackworks | I.CN.65.13920 | CON - Sec.5 - Public LX - Corbys Lane (PU33780) - Place Foundation Block and T-Kerbstone | 2026-05-07 | 2026-05-07
I2S-7688-MP-74.CN.S5.65.3.7 | Trackworks | I.CN.65.13930 | CON - Sec.5 - Public LX - Corbys Lane (PU33780) - Place and compact ballast between foundation block (after road | 2026-05-08 | 2026-05-08
I2S-7688-MP-74.CN.S5.65.3.7 | Trackworks | I.CN.65.13940 | CON - Sec.5 - Public LX - Corbys Lane (PU33780) - Tie-in works to foundation block | 2026-05-09 | 2026-05-09
Ancillary |  |  |  | 2026-05-10 | 2026-05-12
I2S-7688-MP-74.CN.S5.65.3.8 | Ancillary | I.CN.65.13950 | CON - Sec.5 - Public LX - Corbys Lane (PU33780) - Install Fencing | 2026-05-10 | 2026-05-10
I2S-7688-MP-74.CN.S5.65.3.8 | Ancillary | I.CN.65.13960 | CON - Sec.5 - Public LX - Corbys Lane (PU33780) - Install Signage | 2026-05-11 | 2026-05-11
I2S-7688-MP-74.CN.S5.65.3.8 | Ancillary | I.CN.65.13980 | CON - Sec.5 - Public LX - Corbys Lane (PU33780) - Install Gates | 2026-05-12 | 2026-05-12
Commissioning |  |  |  | 2026-05-12 | 2026-05-12
I2S-7688-MP-74.CN.S5.65.3.4 | Commissioning | I.CN.65.14040 | CON - Sec.5 - Public LX - Corbys Lane (PU33780) - Open |  | 2026-05-12
Private LX - Hill (PR32150) - Passive / Private - RX-2 |  |  |  | 2026-03-31 | 2026-04-17
Civils |  |  |  | 2026-03-31 | 2026-03-31
I2S-7688-MP-74.CN.S5.65.2.1 | Civils | I.CN.11.14140 | CON - Sec.5 - Private LX - Hill (PR32150) - Clear and Grub | 2026-03-31 | 2026-03-31
Earthworks/Drainage |  |  |  | 2026-04-01 | 2026-04-08
Culvert ID : E7-RD-449670-1 / Type : 2*900mm HDPE / Ch32143 (17.22m each) |  |  |  | 2026-04-01 | 2026-04-04
I2S-7688-MP-74.CN.S5.65.2.5.1 | Culvert ID : E7-RD-449670-1 / Type : 2*900mm HDPE / Ch32143 (17.22m each) | I.CN.65.13700 | CON - Sec.5 - Private LX - Culvert : E7-RD-449670-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-04-03 | 2026-04-03
I2S-7688-MP-74.CN.S5.65.2.5.1 | Culvert ID : E7-RD-449670-1 / Type : 2*900mm HDPE / Ch32143 (17.22m each) | I.CN.65.13710 | CON - Sec.5 - Private LX - Culvert : E7-RD-449670-1 - Construct Scour Protection | 2026-04-04 | 2026-04-04
I2S-7688-MP-74.CN.S5.65.2.5.1 | Culvert ID : E7-RD-449670-1 / Type : 2*900mm HDPE / Ch32143 (17.22m each) | I.CN.65.13690 | CON - Sec.5 - Private LX - Culvert : E7-RD-449670-1 - Site Prep / Detail Excavation | 2026-04-01 | 2026-04-02
I2S-7688-MP-74.CN.S5.65.2.5.1 | Culvert ID : E7-RD-449670-1 / Type : 2*900mm HDPE / Ch32143 (17.22m each) | I.CN.65.18971 | CON - Sec.5 - Private LX - Culvert : E7-RD-449670-1 - Headwall installation
I2S-7688-MP-74.CN.S5.65.2.5.1 | Culvert ID : E7-RD-449670-1 / Type : 2*900mm HDPE / Ch32143 (17.22m each) | I.CN.65.18981 | CON - Sec.5 - Private LX - Culvert : E7-RD-449670-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S5.65.2.5.1 | Culvert ID : E7-RD-449670-1 / Type : 2*900mm HDPE / Ch32143 (17.22m each) | I.CN.65.18991 | CON - Sec.5 - Private LX - Culvert : E7-RD-449670-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S5.65.2.5.1 | Culvert ID : E7-RD-449670-1 / Type : 2*900mm HDPE / Ch32143 (17.22m each) | I.CN.65.19001 | CON - Sec.5 - Private LX - Culvert : E7-RD-449670-1 - Headwall Cut-off Wall Installation (FRP)
Culvert ID : E7-RD-449671-1 / Type : 1*900mm HDPE / Ch32144 (17.02m each) |  |  |  | 2026-04-03 | 2026-04-08
I2S-7688-MP-74.CN.S5.65.2.5.2 | Culvert ID : E7-RD-449671-1 / Type : 1*900mm HDPE / Ch32144 (17.02m each) | I.CN.65.17340 | CON - Sec.5 - Private LX - Culvert : E7-RD-449671-1 - Construct Scour Protection | 2026-04-07 | 2026-04-08
I2S-7688-MP-74.CN.S5.65.2.5.2 | Culvert ID : E7-RD-449671-1 / Type : 1*900mm HDPE / Ch32144 (17.02m each) | I.CN.65.19011 | CON - Sec.5 - Private LX - Culvert : E7-RD-449671-1 - Headwall installation
I2S-7688-MP-74.CN.S5.65.2.5.2 | Culvert ID : E7-RD-449671-1 / Type : 1*900mm HDPE / Ch32144 (17.02m each) | I.CN.65.19021 | CON - Sec.5 - Private LX - Culvert : E7-RD-449671-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S5.65.2.5.2 | Culvert ID : E7-RD-449671-1 / Type : 1*900mm HDPE / Ch32144 (17.02m each) | I.CN.65.19031 | CON - Sec.5 - Private LX - Culvert : E7-RD-449671-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S5.65.2.5.2 | Culvert ID : E7-RD-449671-1 / Type : 1*900mm HDPE / Ch32144 (17.02m each) | I.CN.65.19041 | CON - Sec.5 - Private LX - Culvert : E7-RD-449671-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S5.65.2.5.2 | Culvert ID : E7-RD-449671-1 / Type : 1*900mm HDPE / Ch32144 (17.02m each) | I.CN.65.17320 | CON - Sec.5 - Private LX - Culvert : E7-RD-449671-1 - Site Prep / Detail Excavation | 2026-04-03 | 2026-04-04
I2S-7688-MP-74.CN.S5.65.2.5.2 | Culvert ID : E7-RD-449671-1 / Type : 1*900mm HDPE / Ch32144 (17.02m each) | I.CN.65.17330 | CON - Sec.5 - Private LX - Culvert : E7-RD-449671-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-04-06 | 2026-04-06
Roadworks |  |  |  | 2026-04-01 | 2026-04-11
I2S-7688-MP-74.CN.S5.65.2.6 | Roadworks | I.CN.65.13790 | CON - Sec.5 - Private LX - Hill (PR32150) - Civil Works complete |  | 2026-04-11
I2S-7688-MP-74.CN.S5.65.2.6 | Roadworks | I.CN.65.13720 | CON - Sec.5 - Private LX - Hill (PR32150) - Earthworks | 2026-04-01 | 2026-04-02
I2S-7688-MP-74.CN.S5.65.2.6 | Roadworks | I.CN.65.13730 | CON - Sec.5 - Private LX - Hill (PR32150) - Pavement type A Unsealed (120m2) | 2026-04-03 | 2026-04-03
I2S-7688-MP-74.CN.S5.65.2.6 | Roadworks | I.CN.65.13810 | CON - Sec.5 - Private LX - Hill (PR32150) - Batter face area (120 m3) | 2026-04-04 | 2026-04-04
I2S-7688-MP-74.CN.S5.65.2.6 | Roadworks | I.CN.65.13820 | CON - Sec.5 - Private LX - Hill (PR32150) - Prime & Cure - Pavement type B sealed (595m2) | 2026-04-04 | 2026-04-04
I2S-7688-MP-74.CN.S5.65.2.6 | Roadworks | I.CN.65.13830 | CON - Sec.5 - Private LX - Hill (PR32150) - Seal /linemarking | 2026-04-06 | 2026-04-06
Trackworks |  |  |  | 2026-04-12 | 2026-04-14
I2S-7688-MP-74.CN.S5.65.2.7 | Trackworks | I.CN.65.13740 | CON - Sec.5 - Private LX - Hill (PR32150) - Place Foundation Block and T-Kerbstone | 2026-04-12 | 2026-04-12
I2S-7688-MP-74.CN.S5.65.2.7 | Trackworks | I.CN.65.13750 | CON - Sec.5 - Private LX - Hill (PR32150) - Place and compact ballast between foundation block (after road | 2026-04-13 | 2026-04-13
I2S-7688-MP-74.CN.S5.65.2.7 | Trackworks | I.CN.65.13760 | CON - Sec.5 - Private LX - Hill (PR32150) - Tie-in works to foundation block | 2026-04-14 | 2026-04-14
Ancillary |  |  |  | 2026-04-15 | 2026-04-17
I2S-7688-MP-74.CN.S5.65.2.8 | Ancillary | I.CN.65.13770 | CON - Sec.5 - Private LX - Hill (PR32150) - Install Fencing | 2026-04-15 | 2026-04-15
I2S-7688-MP-74.CN.S5.65.2.8 | Ancillary | I.CN.65.13780 | CON - Sec.5 - Private LX - Hill (PR32150) - Install Signage | 2026-04-16 | 2026-04-16
I2S-7688-MP-74.CN.S5.65.2.8 | Ancillary | I.CN.65.13800 | CON - Sec.5 - Private LX - Hill (PR32150) - Install Gates | 2026-04-17 | 2026-04-17
Commissioning |  |  |  | 2026-04-17 | 2026-04-17
I2S-7688-MP-74.CN.S5.65.2.4 | Commissioning | I.CN.65.13860 | CON - Sec.5 - Private LX - Hill (PR32150) - Open |  | 2026-04-17
Private LX - Runnymede Stock Pty Ltd (PR30850) - Passive / Private - RX-2 |  |  |  | 2026-03-30 | 2026-04-16
Civils |  |  |  | 2026-03-30 | 2026-03-30
I2S-7688-MP-74.CN.S5.65.1.1 | Civils | I.CN.11.13920 | CON - Sec.5 - Private LX - PR30855 - Clear and Grub | 2026-03-30 | 2026-03-30
Earthworks/Drainage |  |  |  | 2026-03-31 | 2026-04-06
Culvert ID : E7-RD-448361-1 / Type : 4*900mm HDPE / Ch30854 (19.57m each) |  |  |  | 2026-03-31 | 2026-04-06
I2S-7688-MP-74.CN.S5.65.1.5.1 | Culvert ID : E7-RD-448361-1 / Type : 4*900mm HDPE / Ch30854 (19.57m each) | I.CN.65.12730 | CON - Sec.5 - Private LX - Culvert : E7-RD-448361-1 - Site Prep / Detail Excavation | 2026-03-31 | 2026-04-01
I2S-7688-MP-74.CN.S5.65.1.5.1 | Culvert ID : E7-RD-448361-1 / Type : 4*900mm HDPE / Ch30854 (19.57m each) | I.CN.65.12970 | CON - Sec.5 - Private LX - Culvert : E7-RD-448361-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-04-02 | 2026-04-04
I2S-7688-MP-74.CN.S5.65.1.5.1 | Culvert ID : E7-RD-448361-1 / Type : 4*900mm HDPE / Ch30854 (19.57m each) | I.CN.65.12980 | CON - Sec.5 - Private LX - Culvert : E7-RD-448361-1 - Construct Scour Protection | 2026-04-06 | 2026-04-06
I2S-7688-MP-74.CN.S5.65.1.5.1 | Culvert ID : E7-RD-448361-1 / Type : 4*900mm HDPE / Ch30854 (19.57m each) | I.CN.65.19051 | CON - Sec.5 - Private LX - Culvert : E7-RD-448361-1 - Headwall installation
I2S-7688-MP-74.CN.S5.65.1.5.1 | Culvert ID : E7-RD-448361-1 / Type : 4*900mm HDPE / Ch30854 (19.57m each) | I.CN.65.19061 | CON - Sec.5 - Private LX - Culvert : E7-RD-448361-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S5.65.1.5.1 | Culvert ID : E7-RD-448361-1 / Type : 4*900mm HDPE / Ch30854 (19.57m each) | I.CN.65.19071 | CON - Sec.5 - Private LX - Culvert : E7-RD-448361-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S5.65.1.5.1 | Culvert ID : E7-RD-448361-1 / Type : 4*900mm HDPE / Ch30854 (19.57m each) | I.CN.65.19081 | CON - Sec.5 - Private LX - Culvert : E7-RD-448361-1 - Headwall Cut-off Wall Installation (FRP)
Roadworks |  |  |  | 2026-03-31 | 2026-04-10
I2S-7688-MP-74.CN.S5.65.1.6 | Roadworks | I.CN.65.13060 | CON - Sec.5 - Private LX - PR30850 - Civil Works complete |  | 2026-04-10
I2S-7688-MP-74.CN.S5.65.1.6 | Roadworks | I.CN.65.12990 | CON - Sec.5 - Private LX - Runnymede Stock Pty Ltd (PR30850) - Earthworks | 2026-03-31 | 2026-04-01
I2S-7688-MP-74.CN.S5.65.1.6 | Roadworks | I.CN.65.13000 | CON - Sec.5 - Private LX - PR30850 - Pavement type A Unsealed (630m2) | 2026-04-02 | 2026-04-04
I2S-7688-MP-74.CN.S5.65.1.6 | Roadworks | I.CN.65.13270 | CON - Sec.5 - Private LX - PR30850 - Batter face area (1000 m3) | 2026-04-06 | 2026-04-08
I2S-7688-MP-74.CN.S5.65.1.6 | Roadworks | I.CN.65.13280 | CON - Sec.5 - Private LX - PR30850 - Prime & Cure - Pavement type B sealed (340m2) | 2026-04-06 | 2026-04-07
I2S-7688-MP-74.CN.S5.65.1.6 | Roadworks | I.CN.65.13290 | CON - Sec.5 - Private LX - PR30850 - Seal /linemarking | 2026-04-09 | 2026-04-09
Trackworks |  |  |  | 2026-04-11 | 2026-04-13
I2S-7688-MP-74.CN.S5.65.1.7 | Trackworks | I.CN.65.13010 | CON - Sec.5 - Private LX - PR30850 - Place Foundation Block and T-Kerbstone | 2026-04-11 | 2026-04-11
I2S-7688-MP-74.CN.S5.65.1.7 | Trackworks | I.CN.65.13020 | CON - Sec.5 - Private LX - PR30850 - Place and compact ballast between foundation block (after road | 2026-04-12 | 2026-04-12
I2S-7688-MP-74.CN.S5.65.1.7 | Trackworks | I.CN.65.13030 | CON - Sec.5 - Private LX - PR30850 - Tie-in works to foundation block | 2026-04-13 | 2026-04-13
Ancillary |  |  |  | 2026-04-14 | 2026-04-16
I2S-7688-MP-74.CN.S5.65.1.8 | Ancillary | I.CN.65.13260 | CON - Sec.5 - Private LX - PR30850 - Install Gates | 2026-04-16 | 2026-04-16
I2S-7688-MP-74.CN.S5.65.1.8 | Ancillary | I.CN.65.13040 | CON - Sec.5 - Private LX - PR30850 - Install Fencing | 2026-04-14 | 2026-04-14
I2S-7688-MP-74.CN.S5.65.1.8 | Ancillary | I.CN.65.13050 | CON - Sec.5 - Private LX - PR30850 - Install Signage | 2026-04-15 | 2026-04-15
Commissioning |  |  |  | 2026-04-16 | 2026-04-16
I2S-7688-MP-74.CN.S5.65.1.4 | Commissioning | I.CN.65.13320 | CON - Sec.5 - Private LX - PR30850 - Open |  | 2026-04-16
072 - Signalling |  |  |  | 2026-05-11 | 2026-08-13
Signals |  |  |  | 2026-05-11 | 2026-05-14
I2S-7688-MP-74.CN.S5.72.11 | Signals | I.CN.72.15360 | CON - Sec.5 - Sig - Install New Main Signals (1 off) 449270 | 2026-05-11 | 2026-05-12
I2S-7688-MP-74.CN.S5.72.11 | Signals | I.CN.72.15370 | CON - Sec.5 - Sig - Install New Main Signals (1 off) 454810 | 2026-05-13 | 2026-05-14
Cabling |  |  |  | 2026-07-10 | 2026-07-22
I2S-7688-MP-74.CN.S5.72.8 | Cabling | I.CN.74.14440 | CON - Sec.5 - CSR - Main Cable Route - MCR - Pull Cable -Stockinbingal to SL3 Dist -28300 - 32840 | 2026-07-10 | 2026-07-22
Misc Equipment |  |  |  | 2026-07-24 | 2026-08-13
I2S-7688-MP-74.CN.S5.72.12 | Misc Equipment | I.CN.74.14700 | CON - Sec.5 - Sig - Install Track Side Equipment (speed signs/motor generators/notice boards) | 2026-07-24 | 2026-08-13
Axle
I2S-7688-MP-74.CN.S5.72.1 | Axle | I.CN.72.16470 | CON - Sec.5 - Sig - Install New Axle Counter (1 off) 452050
I2S-7688-MP-74.CN.S5.72.1 | Axle | I.CN.72.16480 | CON - Sec.5 - Sig - Install New Axle Counter (1 off) 452350
I2S-7688-MP-74.CN.S5.72.1 | Axle | I.CN.72.16490 | CON - Sec.5 - Sig - Install New Axle Counter (1 off) 449270
I2S-7688-MP-74.CN.S5.72.1 | Axle | I.CN.72.16500 | CON - Sec.5 - Sig - Install New Axle Counter (1 off) 454810
I2S-7688-MP-74.CN.S5.72.1 | Axle | I.CN.72.16360 | CON - Sec.5 - Sig - Install New Axle Counter (1 off) 448660
Location Case
I2S-7688-MP-74.CN.S5.72.2 | Location Case | I.CN.72.16370 | CON - Sec.5 - Sig - Install New Location Case (1 off) 449270
I2S-7688-MP-74.CN.S5.72.2 | Location Case | I.CN.72.16510 | CON - Sec.5 - Sig - Install New Location Case (1 off) 452050
074 - Power Supply and Distributions |  |  |  | 2025-10-16 | 2026-07-23
CSR |  |  |  | 2025-10-16 | 2026-07-23
MCR |  |  |  | 2025-10-16 | 2026-07-09
I2S-7688-MP-74.CN.S5.74.2.1 | MCR | I.CN.74.15780 | CON - Sec.5 - CSR - Install Main CSR - Up Main 453450 (Powder Horn) to 454750 (1300m)
I2S-7688-MP-74.CN.S5.74.2.1 | MCR | I.CN.74.15790 | CON - Sec.5 - CSR - Install Main CSR - Up Main 454800 to 455000 (200m)
I2S-7688-MP-74.CN.S5.74.2.1 | MCR | I.CN.74.15800 | CON - Sec.5 - CSR - Install Main CSR - Dn Main 454800 to 455000 (200m)
I2S-7688-MP-74.CN.S5.74.2.1 | MCR | I.CN.74.14360 | CON - Sec.5 - CSR - Install Main CSR - Up Main 445800 (Old Coot) TO 452450 (LX) (6650m) | 2026-06-06 | 2026-07-09
I2S-7688-MP-74.CN.S5.74.2.1 | MCR | I.CN.74.14930 | CON - Sec.5 - CSR - Install Main CSR - Up Main 452450 (LX) - 453400 (Powder Horn) (950m) | 2025-10-16 | 2025-11-17
I2S-7688-MP-74.CN.S5.74.2.1 | MCR | I.CN.74.15770 | CON - Sec.5 - CSR - Install Main CSR - Up Main Across Powder Horn Creek Underbridge
LCR |  |  |  | 2026-07-23 | 2026-07-23
I2S-7688-MP-74.CN.S5.74.2.2 | LCR | I.CN.74.14690 | CON - Sec.5 - CSR - Construct Local Cable Route - LCR Up - 448660 | 2026-07-23 | 2026-07-23
I2S-7688-MP-74.CN.S5.74.2.2 | LCR | I.CN.74.15870 | CON - Sec.5 - CSR - Construct Local Cable Route - LCR Up - 449260
I2S-7688-MP-74.CN.S5.74.2.2 | LCR | I.CN.74.15880 | CON - Sec.5 - CSR - Construct Local Cable Route - LCR Up - 452050
I2S-7688-MP-74.CN.S5.74.2.2 | LCR | I.CN.74.15890 | CON - Sec.5 - CSR - Construct Local Cable Route - LCR Up - 452350
I2S-7688-MP-74.CN.S5.74.2.2 | LCR | I.CN.74.15900 | CON - Sec.5 - CSR - Construct Local Cable Route - LCR Dn - 454810
I2S-7688-MP-74.CN.S5.74.2.2 | LCR | I.CN.74.15910 | CON - Sec.5 - CSR - Construct Local Cable Route - LCR Up - 454810
ULX |  |  |  | 2026-03-03 | 2026-03-06
I2S-7688-MP-74.CN.S5.74.2.3 | ULX | I.CN.74.14590 | CON - Sec.5 - CSR - Local ULX Up - 448350 | 2026-03-03 | 2026-03-06
I2S-7688-MP-74.CN.S5.74.2.3 | ULX | I.CN.74.15810 | CON - Sec.5 - CSR - Local ULX Up - 449650
I2S-7688-MP-74.CN.S5.74.2.3 | ULX | I.CN.74.15820 | CON - Sec.5 - CSR - Local ULX Up - 451250
I2S-7688-MP-74.CN.S5.74.2.3 | ULX | I.CN.74.15830 | CON - Sec.5 - CSR - Local ULX Up - 452450
I2S-7688-MP-74.CN.S5.74.2.3 | ULX | I.CN.74.15840 | CON - Sec.5 - CSR - Local ULX Dn - Across BGW - 454750 to 454800
I2S-7688-MP-74.CN.S5.74.2.3 | ULX | I.CN.74.15850 | CON - Sec.5 - CSR - Local ULX Up - Across Track 454800
085 - Landscaping
I2S-7688-MP-74.CN.S5.85 | 085 - Landscaping | I.CN.85.13990 | CON - Sec.5 - Landscaping - Re-spread Topsoil - Ch28300-37300
I2S-7688-MP-74.CN.S5.85 | 085 - Landscaping | I.CN.85.14000 | CON - Sec.5 - Landscaping - Hydroseed Application - Ch28300-37300
Section 4 - GF section (18501 - 28300) |  |  |  | 2025-07-12 | 2026-11-10
Section 4 Key Milestones
I2S-7688-MP-74.CN.S4.1 | Section 4 Key Milestones | I.CN.22.13730 | CON - Sec.4 - Construction Completion Milestone (Earthworks)
I2S-7688-MP-74.CN.S4.1 | Section 4 Key Milestones | I.CN.22.13740 | CON - Sec.4 - Construction Completion Milestone (Rail Capping)
I2S-7688-MP-74.CN.S4.1 | Section 4 Key Milestones | I.CN.22.13750 | CON - Sec.4 - Construction Completion Milestone (Drainage)
I2S-7688-MP-74.CN.S4.1 | Section 4 Key Milestones | I.CN.22.13760 | CON - Sec.4 - Construction Completion Milestone (Fencing)
I2S-7688-MP-74.CN.S4.1 | Section 4 Key Milestones | I.CN.22.13790 | CON - Sec.4 - Construction Completion Milestone (Trackwork)
I2S-7688-MP-74.CN.S4.1 | Section 4 Key Milestones | I.CN.22.13800 | CON - Sec.4 - Construction Completion Milestone (Bridges)
I2S-7688-MP-74.CN.S4.1 | Section 4 Key Milestones | I.CN.22.13810 | CON - Sec.4 - Construction Completion Milestone (Crossings)
I2S-7688-MP-74.CN.S4.1 | Section 4 Key Milestones | I.CN.22.13820 | CON - Sec.4 - Construction Completion Milestone (Signalling)
I2S-7688-MP-74.CN.S4.1 | Section 4 Key Milestones | I.CN.22.13840 | CON - Sec.4 - Construction Completion Milestone (Power Supply and Distributions)
I2S-7688-MP-74.CN.S4.1 | Section 4 Key Milestones | I.CN.22.13850 | CON - Sec.4 - Construction Completion Milestone (Landscaping)
I2S-7688-MP-74.CN.S4.1 | Section 4 Key Milestones | I.CN.22.13720 | CON - Sec.4 - Construction Completion Milestone (Public Utilities)
I2S-7688-MP-74.CN.S4.1 | Section 4 Key Milestones | I.CN.22.14440 | CON - Sec.4 - Construction Completion Milestone (Culverts)
I2S-7688-MP-74.CN.S4.1 | Section 4 Key Milestones | I.CN.22.13780 | CON - Sec.4 - Construction Completion Milestone (Access Roads)
I2S-7688-MP-74.CN.S4.1 | Section 4 Key Milestones | I.CN.22.14780 | CON - Sec.4 - Commence Construction Milestone - FDVR & CEMP approved - 1st A9 submission - approval
I2S-7688-MP-74.CN.S4.1 | Section 4 Key Milestones | I.CN.22.14770 | CON - Sec.4 - Commence Construction Milestone - CEMP approved
Site Access |  |  |  | 2025-07-12 | 2025-07-12
I2S-7688-MP-74.CN.S4.00 | Site Access | I.CN.11.14030 | CON - Sec.4 - Site Gate Access Required by/ Granted - Gate 5A (22100) | 2025-07-12 | 2025-07-12
I2S-7688-MP-74.CN.S4.00 | Site Access | I.CN.11.14040 | CON - Sec.4 - Site Gate Access Required by/ Granted - Gate 6 (28250) | 2025-07-12 | 2025-07-12
022 - Public Utilities |  |  |  | 2025-07-30 | 2025-09-17
Telstra |  |  |  | 2025-07-30 | 2025-09-17
I2S-7688-MP-74.CN.S4.22.2 | Telstra | I.CN.22.6080 | CON - Util - Sec.4 - TEL-02-09 Telstra - Relocation South Side Old Cootamundra Rd - Ch28247 (145m) | 2025-09-10 | 2025-09-17
I2S-7688-MP-74.CN.S4.22.2 | Telstra | I.CN.22.6290 | CON - Util - Sec.4 - TE02-08 Telstra - Relocation East Side Dudaman Road - Ch22242 (137m) | 2025-07-30 | 2025-08-04
Goldenfield Water |  |  |  | 2025-07-30 | 2025-07-31
I2S-7688-MP-74.CN.S4.22.3 | Goldenfield Water | I.CN.22.6060 | CON - Util - Sec.4 - WA01-01 Goldenfields Water - Relocate Potable Water North Side Old Cootamundra Road - Ch28272 | 2025-07-30 | 2025-07-31
I2S-7688-MP-74.CN.S4.22.3 | Goldenfield Water | I.CN.22.14970 | CON - Util - Sec.4 - WA01-01 Goldenfields Water - Commence Work on site
I2S-7688-MP-74.CN.S4.22.3 | Goldenfield Water | I.CN.22.14980 | CON - Util - Sec.4 - WA01-01 Goldenfields Water - Outage & cutover
I2S-7688-MP-74.CN.S4.22.3 | Goldenfield Water | I.CN.22.14990 | CON - Util - Sec.4 - WA01-01 Goldenfields Water - Complete Works
Essential Energy (EE) |  |  |  | 2025-08-11 | 2025-08-12
ECN-098334 ELO-03 |  |  |  | 2025-08-11 | 2025-08-12
I2S-7688-MP-74.CN.S4.22.4.2 | ECN-098334 ELO-03 | I.CN.22.13290 | CON - Util - Sec.4 - ELO-03 - Essential Energy Relocate 11kV South Side Old Cootamundra Road - Ch28092 (105m) | 2025-08-11 | 2025-08-12
I2S-7688-MP-74.CN.S4.22.4.2 | ECN-098334 ELO-03 | I.CN.22.14550 | CON - Util - Sec.4 - ELO-03 - Commence Work on site
I2S-7688-MP-74.CN.S4.22.4.2 | ECN-098334 ELO-03 | I.CN.22.14560 | CON - Util - Sec.4 - ELO-03 - ECN-098334 - Outage & Cutover
I2S-7688-MP-74.CN.S4.22.4.2 | ECN-098334 ELO-03 | I.CN.22.14570 | CON - Util - Sec.4 - ELO-03 - ECN-098334 Works Complete
ECN-098331 ELO-09 |  |  |  | 2025-08-11 | 2025-08-12
I2S-7688-MP-74.CN.S4.22.4.1 | ECN-098331 ELO-09 | I.CN.22.6070 | CON - Util - Sec.4 - ELO-09 - Essential Energy Relocate 11kV East Side Dudauman Road - Ch21922 (134m) | 2025-08-11 | 2025-08-12
I2S-7688-MP-74.CN.S4.22.4.1 | ECN-098331 ELO-09 | I.CN.22.6090 | CON - Util - Sec.4 - ELO-09 - Commence Work on site
I2S-7688-MP-74.CN.S4.22.4.1 | ECN-098331 ELO-09 | I.CN.22.6100 | CON - Util - Sec.4 - ELO-09 - ECN-098331 - Outage & Cutover
I2S-7688-MP-74.CN.S4.22.4.1 | ECN-098331 ELO-09 | I.CN.22.6110 | CON - Util - Sec.4 - ELO-09 - ECN-098331 Works Complete
031 - Earthworks
I2S-7688-MP-74.CN.S4.31 | 031 - Earthworks | I.CN.31.88260 | CON - Sec.4 - Construct Temp Creek Crossing - Isobel Creek for traffic
I2S-7688-MP-74.CN.S4.31 | 031 - Earthworks | I.CN.31.88270 | CON - Sec.4 - Construct Temp Creek Crossing - Isobel Creek Trib for traffic
Clearing & Grubbing - Stage 2
Tree Felling and Lopping
I2S-7688-MP-74.CN.S4.31.3.1 | Tree Felling and Lopping | I.CN.11.15640 | CON - Sec.4 - Tree Felling & Lopping
Broad Acre Clearing and Mulching
I2S-7688-MP-74.CN.S4.31.3.2 | Broad Acre Clearing and Mulching | I.CN.11.15650 | CON - Sec.4 - Broad Acre Clearing & Mulching
Grubbing of Stumps
I2S-7688-MP-74.CN.S4.31.3.3 | Grubbing of Stumps | I.CN.11.15660 | CON - Sec.4 - Grubbing of Stumps
Miscellaneous Works
I2S-7688-MP-74.CN.S4.31.3.4 | Miscellaneous Works | I.CN.11.15670 | CON - Sec.4 - Hollow/Habitat Tree Mgmt
I2S-7688-MP-74.CN.S4.31.3.4 | Miscellaneous Works | I.CN.11.15680 | CON - Sec.4 - Relocations
Cut
Cut Open Drains
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.86210 | CON - Sec.4 - FILL 22 - Cut.OD Soil : Ch19116 to 19556 (3596 bcm - 175 per/d)
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.86240 | CON - Sec.4 - FILL 23 - Cut.OD Soil : Ch19851 to 20147 (504 bcm - 175 per/d)
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.86270 | CON - Sec.4 - FILL 24 - Cut.OD Soil : Ch20194 TO 20253 (203 bcm - 175 per/d)
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.86300 | CON - Sec.4 - FILL 27 - Cut.OD Soil : Ch21208 to 21343 (143 bcm - 175 per/d)
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.86330 | CON - Sec.4 - FILL 26 - Cut.OD Soil : Ch20494 to 20710 (241 bcm - 175 per/d)
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.86390 | CON - Sec.4 - FILL 28 - Cut.OD Soil : Ch21563 to 22023 (969 bcm - 175 per/d)
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.86420 | CON - Sec.4 - FILL 29 - Cut.OD Soil : Ch22420 to 22814 (51 bcm - 175 per/d)
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.86450 | CON - Sec.4 - FILL 30 - Cut.OD Soil : Ch23134 to 23854 (1117 bcm - 175 per/d)
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.86480 | CON - Sec.4 - FILL 34 - Cut.OD Soil : Ch27548 to 28252 (1044 bcm - 175 per/d)
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.86540 | CON - Sec.4 - FILL 33 - Cut.OD Soil : Ch26748 to 27048 (538 bcm - 175 per/d)
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.86570 | CON - Sec.4 - FILL 32 - Cut.OD Soil : Ch25688 to 26448 (1160 bcm - 175 per/d)
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.86600 | CON - Sec.4 - FILL 31 - Cut.OD Soil : Ch24594 to 25192 (847 bcm - 175 per/d)
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.82650 | CON - Sec.4 - CUT 22 - Cut.OD Soil : Ch19556 to 19851 (2732 bcm - 175 per/d)
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.82740 | CON - Sec.4 - CUT 23 - Cut.OD Soil : Ch20206 to 20405 (170 bcm - 175 per/d)
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.82830 | CON - Sec.4 - CUT 24 - Cut.OD Soil : Ch20710 to 21208 (1150 bcm - 175 per/d)
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.82920 | CON - Sec.4 - CUT 25 - Cut.OD Soil : Ch21343 to 21563 (288 bcm - 175 per/d)
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.83100 | CON - Sec.4 - CUT 27 - Cut.OD Soil : Ch22814 to 23134 (736 bcm - 175 per/d)
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.83190 | CON - Sec.4 - CUT 28 - Cut.OD Soil : Ch23854 to 24594 (4541 bcm - 175 per/d)
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.83280 | CON - Sec.4 - CUT 29 - Cut.OD Soil : Ch25192 to 25688 (609 bcm - 175 per/d)
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.83370 | CON - Sec.4 - CUT 30 - Cut.OD Soil : Ch26448 to 26748 (79 bcm - 175 per/d)
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.83460 | CON - Sec.4 - CUT 31 - Cut.OD Soil : Ch27048 to 27588 (200 bcm - 175 per/d)
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.83640 | CON - Sec.4 - CUT 33 - Cut.OD Soil : Ch28375 to 28515 (287 bcm - 175 per/d)
I2S-7688-MP-74.CN.S4.31.1.16 | Cut Open Drains | I.CN.31.83730 | CON - Sec.4 - CUT 34 - Cut.OD Soil : Ch30234 to 30852 (833 bcm - 175 per/d)
Cut Soil to EW
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.86310 | CON - Sec.4 - FILL 26 - Cut.Soil to EW : Ch20494 to 20710 (37 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.86370 | CON - Sec.4 - FILL 28 - Cut.Soil to EW : Ch21563 to 22023 (534 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.86400 | CON - Sec.4 - FILL 29 - Cut.Soil to EW : Ch22420 to 22814 (580 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.86430 | CON - Sec.4 - FILL 30 - Cut.Soil to EW : Ch23134 to 23854 (442 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.86460 | CON - Sec.4 - FILL 34 - Cut.Soil to EW : Ch27548 to 28252 (280 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.86490 | CON - Sec.4 - FILL 35 - Cut.Soil to EW : Ch28275 to 28375 (58 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.86520 | CON - Sec.4 - FILL 33 - Cut.Soil to EW : Ch26748 to 27048 (310 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.86550 | CON - Sec.4 - FILL 32 - Cut.Soil to EW : Ch25688 to 26448 (322 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.86580 | CON - Sec.4 - FILL 31 - Cut.Soil to EW : Ch24594 to 25192 (1721 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.82680 | CON - Sec.4 - CUT 22 - Cut.Soil to EW : Ch19556 to 19851 (27592 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.82770 | CON - Sec.4 - CUT 23 - Cut.Soil to EW : Ch20206 to 20405 (10802 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.82860 | CON - Sec.4 - CUT 24 - Cut.Soil to EW : Ch20710 to 21208 (35070 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.82950 | CON - Sec.4 - CUT 25 - Cut.Soil to EW : Ch21343 to 21563 (7985 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.83040 | CON - Sec.4 - CUT 26 - Cut.Soil to EW : Ch22023 to 22420 (22083 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.83130 | CON - Sec.4 - CUT 27 - Cut.Soil to EW : Ch22814 to 23134 (9137 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.83220 | CON - Sec.4 - CUT 28 - Cut.Soil to EW : Ch23854 to 24594 (46533 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.83310 | CON - Sec.4 - CUT 29 - Cut.Soil to EW : Ch25192 to 25688 (26933 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.83400 | CON - Sec.4 - CUT 30 - Cut.Soil to EW : Ch26448 to 26748 (12379 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.83490 | CON - Sec.4 - CUT 31 - Cut.Soil to EW : Ch27048 to 27588 (25155 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.83580 | CON - Sec.4 - CUT 32 - Cut.Soil to EW : Ch28375 to 28515 (2798 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.83670 | CON - Sec.4 - CUT 33 - Cut.Soil to EW : Ch29975 to 30234 (3383 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.83760 | CON - Sec.4 - CUT 34 - Cut.Soil to EW : Ch30234 to 30852 (6105 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.86190 | CON - Sec.4 - FILL 22 - Cut.Soil to EW : Ch19116 to 19556 (686 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.86250 | CON - Sec.4 - FILL 24 - Cut.Soil to EW : Ch20194 to 20253 (47 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.86280 | CON - Sec.4 - FILL 27 - Cut.Soil to EW : Ch21208 to 21343 (246 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.3 | Cut Soil to EW | I.CN.31.88320 | CON - Sec.4 - FILL 22 - Cut.Soil to EW : Ch19116 to 19556 (686 bcm - 2500 per/d) - Milestone
Cut Rock
I2S-7688-MP-74.CN.S4.31.1.4 | Cut Rock | I.CN.31.86200 | CON - Sec.4 - FILL 22 - Cut.HW Dacite : Ch19116 to 19556 (28bcm - 2000 per/d)
I2S-7688-MP-74.CN.S4.31.1.4 | Cut Rock | I.CN.31.86260 | CON - Sec.4 - FILL 24 - Cut.HW Dacite : Ch20194 to 20253 (41 bcm - 2000 per/d)
I2S-7688-MP-74.CN.S4.31.1.4 | Cut Rock | I.CN.31.86470 | CON - Sec.4 - FILL 34 - Cut.HW Dacite : Ch27548 to 28252 (43 bcm - 2000 per/d)
I2S-7688-MP-74.CN.S4.31.1.4 | Cut Rock | I.CN.31.82630 | CON - Sec.4 - CUT 22 - Cut.HW Rhyolite : Ch19556 to 19851 (27760 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.4 | Cut Rock | I.CN.31.82720 | CON - Sec.4 - CUT 23 - Cut.HW Rhyolite : Ch20206 to 20405 (7154 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.4 | Cut Rock | I.CN.31.82810 | CON - Sec.4 - CUT 24 - Cut.HW Rhyolite : Ch20710 to 21208 (63164 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.4 | Cut Rock | I.CN.31.82900 | CON - Sec.4 - CUT 25 - Cut.HW Rhyolite : Ch21343 to 21563 (2440 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.1.4 | Cut Rock | I.CN.31.82980 | CON - Sec.4 - CUT 26 - Cut.HW/MW Dacite : Ch22023 to 22420 (15272 bcm - 2000 per/d)
I2S-7688-MP-74.CN.S4.31.1.4 | Cut Rock | I.CN.31.83070 | CON - Sec.4 - CUT 27 - Cut.HW/MW Dacite : Ch22814 to 23134 (3310 bcm - 2000 per/d)
I2S-7688-MP-74.CN.S4.31.1.4 | Cut Rock | I.CN.31.83160 | CON - Sec.4 - CUT 28 - Cut.HW Dacite : Ch23854 to 24594 (14316 bcm - 2000 per/d)
I2S-7688-MP-74.CN.S4.31.1.4 | Cut Rock | I.CN.31.83250 | CON - Sec.4 - CUT 29 - Cut.HW/MW/SW Dacite : Ch25192 to 25688 (57069 bcm - 2000 per/d)
I2S-7688-MP-74.CN.S4.31.1.4 | Cut Rock | I.CN.31.83340 | CON - Sec.4 - CUT 30 - Cut.HW/MW/SW Dacite : Ch26448 to 26748(55025 bcm - 2000 per/d)
I2S-7688-MP-74.CN.S4.31.1.4 | Cut Rock | I.CN.31.83430 | CON - Sec.4 - CUT 31 - Cut.HW/MW Dacite : Ch27048 to 27588 (6642 bcm - 2000 per/d)
I2S-7688-MP-74.CN.S4.31.1.4 | Cut Rock | I.CN.31.83520 | CON - Sec.4 - CUT 32 - Cut.HW Dacite : Ch28375 to 28515 (1299 bcm - 2000 per/d)
Fill
Fill Open Drains
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.84890 | CON - Sec.4 - FILL 22 - Fill.OD Fill : Ch19116 to 19556 (42 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.84930 | CON - Sec.4 - FILL 23 - Fill.OD Fill : Ch19851 to 20147 (98 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.85210 | CON - Sec.4 - FILL 30 - Fill.OD Fill : Ch23134 to 23854 (133 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.85250 | CON - Sec.4 - FILL 31 - Fill.OD Fill : Ch24594 to 25192 (33 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.85290 | CON - Sec.4 - FILL 32 - Fill.OD Fill : Ch25688 to 26448 (106 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.85330 | CON - Sec.4 - FILL 33 - Fill.OD Fill : Ch26748 to 27048 (139 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.85370 | CON - Sec.4 - FILL 34 - Fill.OD Fill : Ch27548 to 28252 (38 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.84970 | CON - Sec.4 - FILL 25 - Fill.OD Fill : Ch20405 to 20482 (16 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.85010 | CON - Sec.4 - FILL 24 - Fill.OD Fill : Ch20194 to 20253 (10 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.85050 | CON - Sec.4 - FILL 29 - Fill.OD Fill : Ch22420 to 22814 (69 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.85090 | CON - Sec.4 - FILL 27 - Fill.OD Fill : Ch21208 to 21343 (10 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.85130 | CON - Sec.4 - FILL 26 - Fill.OD Fill : Ch20494 to 20710 (30 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.85170 | CON - Sec.4 - FILL 28 - Fill.OD Fill : Ch21563 to 22023 (179 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.87560 | CON - Sec.4 - CUT 22 - Fill.OD Fill : Ch19556 to 19851 (669 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.87600 | CON - Sec.4 - CUT 23 - Fill.OD Fill : Ch20206 to 20405 (135 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.87640 | CON - Sec.4 - CUT 25 - Fill.OD Fill : Ch21343 to 21563 (151 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.87680 | CON - Sec.4 - CUT 24 - Fill.OD Fill : Ch20710 to 21208 (325 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.87720 | CON - Sec.4 - CUT 30 - Fill.OD Fill : Ch26448 to 26748 (444 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.87760 | CON - Sec.4 - CUT 29 - Fill.OD Fill : Ch25192 to 25688 (253 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.87800 | CON - Sec.4 - CUT 27 - Fill.OD Fill : Ch22814 to 23134 (659 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.87840 | CON - Sec.4 - CUT 28 - Fill.OD Fill : Ch23854 to 24594 (1997 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.87880 | CON - Sec.4 - CUT 31 - Fill.OD Fill : Ch27048 to 27588 (332 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.87960 | CON - Sec.4 - CUT 34 - Fill.OD Fill : Ch30234 to 30852 (682 bcm - 500 per/d)
I2S-7688-MP-74.CN.S4.31.2.30 | Fill Open Drains | I.CN.31.88000 | CON - Sec.4 - CUT 33 - Fill.OD Fill : Ch29975 to 30234 (37 bcm - 500 per/d)
Fill Lower
I2S-7688-MP-74.CN.S4.31.2.3 | Fill Lower | I.CN.31.84920 | CON - Sec.4 - FILL 22 - Fill.H3 - Lower : Ch19116 to 19556(64418 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.3 | Fill Lower | I.CN.31.84960 | CON - Sec.4 - FILL 23 - Fill.H3 - Lower : Ch19851 to 20147 (27498 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.3 | Fill Lower | I.CN.31.85240 | CON - Sec.4 - FILL 30 - Fill.H3 - Lower : Ch23134 to 23854 (15823 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.3 | Fill Lower | I.CN.31.85280 | CON - Sec.4 - FILL 31 - Fill.H3 - Lower : Ch24594 to 25192 (21859 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.3 | Fill Lower | I.CN.31.85320 | CON - Sec.4 - FILL 32 - Fill.H3 - Lower : Ch25688 to 26448 (66645 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.3 | Fill Lower | I.CN.31.85360 | CON - Sec.4 - FILL 33 - Fill.H3 - Lower : Ch26748 to 27048 (23557 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.3 | Fill Lower | I.CN.31.85400 | CON - Sec.4 - FILL 34 - Fill.H3 - Lower : Ch27548 to 28252 (101522 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.3 | Fill Lower | I.CN.31.85440 | CON - Sec.4 - FILL 35 - Fill.H3 - Lower : Ch28275 to 28375 (3023 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.3 | Fill Lower | I.CN.31.85000 | CON - Sec.4 - FILL 25 - Fill.H3 - Lower : Ch20405 to 20482 (611 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.3 | Fill Lower | I.CN.31.85040 | CON - Sec.4 - FILL 24 - Fill.H3 - Lower : Ch20194 to 20253 (471 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.3 | Fill Lower | I.CN.31.85080 | CON - Sec.4 - FILL 29 - Fill.H3 - Lower : Ch22420 to 22814 (2229 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.3 | Fill Lower | I.CN.31.85120 | CON - Sec.4 - FILL 27 - Fill.H3 - Lower : Ch21208 to 21343 (1166 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.3 | Fill Lower | I.CN.31.85160 | CON - Sec.4 - FILL 26 - Fill.H3 - Lower : Ch20494 to 20710 (10421 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.3 | Fill Lower | I.CN.31.85200 | CON - Sec.4 - FILL 28 - Fill.H3 - Lower : Ch21509 to 21929 (28408 bcm - 2500 per/d)
Fill Mid
I2S-7688-MP-74.CN.S4.31.2.4 | Fill Mid | I.CN.31.84910 | CON - Sec.4 - FILL 22 - Fill.H2 - Mid : Ch19116 to 19556 (2802 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.4 | Fill Mid | I.CN.31.84950 | CON - Sec.4 - FILL 23 - Fill.H2 - Mid : Ch19851 to 20147 (1343 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.4 | Fill Mid | I.CN.31.85230 | CON - Sec.4 - FILL 30 - Fill.H2 - Mid : Ch23134 to 23854 (4009 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.4 | Fill Mid | I.CN.31.85270 | CON - Sec.4 - FILL 31 - Fill.H2 - Mid : Ch24594 to 25192 (3293 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.4 | Fill Mid | I.CN.31.85310 | CON - Sec.4 - FILL 32 - Fill.H2 - Mid : Ch25688 to 26448 (5392 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.4 | Fill Mid | I.CN.31.85350 | CON - Sec.4 - FILL 33 - Fill.H2 - Mid : Ch26748 to 27048 (1949 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.4 | Fill Mid | I.CN.31.85390 | CON - Sec.4 - FILL 34 - Fill.H2 - Mid : Ch27548 to 28252 (4646 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.4 | Fill Mid | I.CN.31.85430 | CON - Sec.4 - FILL 35 - Fill.H2 - Mid : Ch28275 to 28375 (937 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.4 | Fill Mid | I.CN.31.84990 | CON - Sec.4 - FILL 25 - Fill.H2 - Mid : Ch20405 to 20482 (242 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.4 | Fill Mid | I.CN.31.85030 | CON - Sec.4 - FILL 24 - Fill.H2 - Mid : Ch20194 to 20253 (133 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.4 | Fill Mid | I.CN.31.85070 | CON - Sec.4 - FILL 29 - Fill.H2 - Mid : Ch22420 to 22814 (1610 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.4 | Fill Mid | I.CN.31.85110 | CON - Sec.4 - FILL 27 - Fill.H2 - Mid : Ch21208 to 21343(792 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.4 | Fill Mid | I.CN.31.85150 | CON - Sec.4 - FILL 26 - Fill.H2 - Mid : Ch20494 to 20710 (1060 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.4 | Fill Mid | I.CN.31.85190 | CON - Sec.4 - FILL 28 - Fill.H2 - Mid : Ch21563 to 22023 (2484 bcm - 2500 per/d)
Fill Upper
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.84900 | CON - Sec.4 - FILL 22 - Fill.H1 - Upper : Ch19116 to 19556 (5010 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.84940 | CON - Sec.4 - FILL 23 - Fill.H1 - Upper : Ch19851 to 20147 (2425 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.85220 | CON - Sec.4 - FILL 30 - Fill.H1 - Upper : Ch23134 to 23854 (4265 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.85260 | CON - Sec.4 - FILL 31 - Fill.H1 - Upper : Ch24594 to 25192 (3601 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.85300 | CON - Sec.4 - FILL 32 - Fill.H1 - Upper : Ch25688 to 26448 (7386 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.85340 | CON - Sec.4 - FILL 33 - Fill.H1 - Upper : Ch26748 to 27048 (3289 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.85380 | CON - Sec.4 - FILL 34 - Fill.H1 - Upper : Ch27548 to 28252 (6281 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.85420 | CON - Sec.4 - FILL 35 - Fill.H1 - Upper : Ch28275 to 28375 (1020 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.84980 | CON - Sec.4 - FILL 25 - Fill.H1 - Upper : Ch20405 to 20482 (313 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.85020 | CON - Sec.4 - FILL 24 - Fill.H1 - Upper : Ch20194 to 20253 (394 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.85060 | CON - Sec.4 - FILL 29 - Fill.H1 - Upper : Ch22420 to 22814 (1711 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.85100 | CON - Sec.4 - FILL 27 - Fill.H1 - Upper : Ch21208 to 21343 (1098 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.85140 | CON - Sec.4 - FILL 26 - Fill.H1 - Upper : Ch20494 to 20710 (1180 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.85180 | CON - Sec.4 - FILL 28 - Fill.H1 - Upper : Ch21563 to 22023 (3488 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.87570 | CON - Sec.4 - CUT 22 - Fill.H1 - Upper : Ch19556 to 19851 (499 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.87610 | CON - Sec.4 - CUT 23 - Fill.H1 - Upper : Ch20206 to 20405 (104 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.87690 | CON - Sec.4 - CUT 24 - Fill.H1 - Upper : Ch20710 to 21208 (100 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.87730 | CON - Sec.4 - CUT 30 - Fill.H1 - Upper : Ch26448 to 26748 (66 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.87770 | CON - Sec.4 - CUT 29 - Fill.H1 - Upper : Ch25192 to 25688 (15 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.87810 | CON - Sec.4 - CUT 27 - Fill.H1 - Upper : Ch22814 to 23134 (55 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.87850 | CON - Sec.4 - CUT 28 - Fill.H1 - Upper : Ch23854 to 24594 (39 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.87930 | CON - Sec.4 - CUT 32 - Fill.H1 - Upper : Ch28375 to 28515 (369 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.87970 | CON - Sec.4 - CUT 34 - Fill.H1 - Upper : Ch30234 to 30852 (800 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S4.31.2.7 | Fill Upper | I.CN.31.88010 | CON - Sec.4 - CUT 33 - Fill.H1 - Upper : Ch29975 to 30234 (419 bcm - 2500 per/d)
033 - Capping |  |  |  | 2026-05-12 | 2026-07-01
Support to u/s Ballast |  |  |  | 2026-05-12 | 2026-07-01
Structural Fill |  |  |  | 2026-05-12 | 2026-05-13
I2S-7688-MP-74.CN.S4.33.3.1 | Structural Fill | I.CN.33.9740 | CON - Sec.4 - Fill Struc fill (113414 TON) 2200 TON/d | 2026-05-12 | 2026-05-12
I2S-7688-MP-74.CN.S4.33.3.1 | Structural Fill | I.CN.33.9750 | CON - Sec.4 - Fill C5 (23487 TON) 1100 TON/d | 2026-05-13 | 2026-05-13
Capping (Rail) |  |  |  | 2026-05-16 | 2026-05-16
I2S-7688-MP-74.CN.S4.33.3.2 | Capping (Rail) | I.CN.33.10000 | CON - Sec.4 - Capping (33,587 TON) 985 TON/d | 2026-05-16 | 2026-05-16
Capping (RMAR) |  |  |  | 2026-07-01 | 2026-07-01
I2S-7688-MP-74.CN.S4.33.3.22 | Capping (RMAR) | I.CN.45.10340 | CON - Sec.4 - (17,244 TON) - Strip/Grade RMAR with type D Material (U5 Class) | 2026-07-01 | 2026-07-01
034 - Drainage |  |  |  | 2025-08-30 | 2026-06-04
Mainline |  |  |  | 2025-08-30 | 2026-06-04
I2S-7688-MP-74.CN.S4.34.16 | Mainline | I.CN.34.27970 | CON - Sec.4 - Place Enveloper Pipe - DN300 RCP 1.5m past crdr boundary (61m) - (ch. 21255) | 2025-09-08 | 2025-09-11
I2S-7688-MP-74.CN.S4.34.16 | Mainline | I.CN.34.27980 | CON - Sec.4 - Place Enveloper Pipe - DN300 RCP 1.5m past crdr boundary (102m) - (ch. 22100) | 2025-09-12 | 2025-09-19
I2S-7688-MP-74.CN.S4.34.16 | Mainline | I.CN.34.27990 | CON - Sec.4 - Place Enveloper Pipe - DN300 RCP 1.5m past crdr boundary (53m) - (ch. 22500) | 2025-09-20 | 2025-09-24
I2S-7688-MP-74.CN.S4.34.16 | Mainline | I.CN.34.28000 | CON - Sec.4 - Place Enveloper Pipe - DN300 RCP 1.5m past crdr boundary (56m) - (ch. 24675) | 2025-09-25 | 2025-09-29
I2S-7688-MP-74.CN.S4.34.16 | Mainline | I.CN.34.28010 | CON - Sec.4 - Place Enveloper Pipe - DN300 RCP 1.5m past crdr boundary (67m) - (ch. 27600) | 2025-09-30 | 2025-10-04
I2S-7688-MP-74.CN.S4.34.16 | Mainline | I.CN.34.27960 | CON - Sec.4 - Place Enveloper Pipe - DN300 RCP 1.5m past crdr boundary (105m) - (ch. 198785) | 2025-08-30 | 2025-09-06
I2S-7688-MP-74.CN.S4.34.16 | Mainline | I.CN.34.25430 | CON - Sec.4 - Cess Drainage - 21090 to 21840 - Concrete Lining | 2026-05-11 | 2026-05-18
I2S-7688-MP-74.CN.S4.34.16 | Mainline | I.CN.34.25440 | CON - Sec.4 - Cess Drainage - 23321 to 24124 - Rock Lined | 2026-05-19 | 2026-05-24
I2S-7688-MP-74.CN.S4.34.16 | Mainline | I.CN.34.25550 | CON - Sec.4 - Cess Drainage - 24324 to 26010 - Grass Lined | 2026-05-26 | 2026-06-04
Culverts |  |  |  | 2025-09-22 | 2026-05-26
Culvert ID : M2-RD-445782-1 / Type : 1*450mm HDPE / Ch28274 (17.13m each) - Old Coota Road
I2S-7688-MP-74.CN.S4.34.17.13 | Culvert ID : M2-RD-445782-1 / Type : 1*450mm HDPE / Ch28274 (17.13m each) - Old Coota Road | I.CN.34.29780 | CON - Sec.4 - Culvert : M2-RD-445782-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S4.34.17.13 | Culvert ID : M2-RD-445782-1 / Type : 1*450mm HDPE / Ch28274 (17.13m each) - Old Coota Road | I.CN.34.29790 | CON - Sec.4 - Culvert : M2-RD-445782-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S4.34.17.13 | Culvert ID : M2-RD-445782-1 / Type : 1*450mm HDPE / Ch28274 (17.13m each) - Old Coota Road | I.CN.34.29800 | CON - Sec.4 - Culvert : M2-RD-445782-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S4.34.17.13 | Culvert ID : M2-RD-445782-1 / Type : 1*450mm HDPE / Ch28274 (17.13m each) - Old Coota Road | I.CN.34.29820 | CON - Sec.4 - Culvert : M2-RD-445782-1 - Construct Scour Protection
I2S-7688-MP-74.CN.S4.34.17.13 | Culvert ID : M2-RD-445782-1 / Type : 1*450mm HDPE / Ch28274 (17.13m each) - Old Coota Road | I.CN.34.29830 | CON - Sec.4 - Culvert : M2-RD-445782-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S4.34.17.13 | Culvert ID : M2-RD-445782-1 / Type : 1*450mm HDPE / Ch28274 (17.13m each) - Old Coota Road | I.CN.34.29840 | CON - Sec.4 - Culvert : M2-RD-445782-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S4.34.17.13 | Culvert ID : M2-RD-445782-1 / Type : 1*450mm HDPE / Ch28274 (17.13m each) - Old Coota Road | I.CN.34.29850 | CON - Sec.4 - Culvert : M2-RD-445782-1 - Headwall installation
Culvert ID : E7-RA-445700-1 / Type : 10*900mm HDPE / Ch28197 (56.92m each) |  |  |  | 2025-11-26 | 2025-12-08
I2S-7688-MP-74.CN.S4.34.17.12 | Culvert ID : E7-RA-445700-1 / Type : 10*900mm HDPE / Ch28197 (56.92m each) | I.CN.34.21690 | CON - Sec.4 - Culvert : E7-RA-445700-1 - HDPE / RCP Pipe Lay & Backfill | 2025-12-01 | 2025-12-01
I2S-7688-MP-74.CN.S4.34.17.12 | Culvert ID : E7-RA-445700-1 / Type : 10*900mm HDPE / Ch28197 (56.92m each) | I.CN.34.21710 | CON - Sec.4 - Culvert : E7-RA-445700-1 - Headwall Stitch Pour | 2025-12-02 | 2025-12-03
I2S-7688-MP-74.CN.S4.34.17.12 | Culvert ID : E7-RA-445700-1 / Type : 10*900mm HDPE / Ch28197 (56.92m each) | I.CN.34.21720 | CON - Sec.4 - Culvert : E7-RA-445700-1 - Headwall Cut-off Wall Installation (FRP) | 2025-12-04 | 2025-12-06
I2S-7688-MP-74.CN.S4.34.17.12 | Culvert ID : E7-RA-445700-1 / Type : 10*900mm HDPE / Ch28197 (56.92m each) | I.CN.34.21740 | CON - Sec.4 - Culvert : E7-RA-445700-1 - Construct Scour Protection | 2025-12-07 | 2025-12-08
I2S-7688-MP-74.CN.S4.34.17.12 | Culvert ID : E7-RA-445700-1 / Type : 10*900mm HDPE / Ch28197 (56.92m each) | I.CN.34.21630 | CON - Sec.4 - Culvert : E7-RA-445700-1 - Site Prep / Detail Excavation | 2025-11-26 | 2025-11-27
I2S-7688-MP-74.CN.S4.34.17.12 | Culvert ID : E7-RA-445700-1 / Type : 10*900mm HDPE / Ch28197 (56.92m each) | I.CN.34.21640 | CON - Sec.4 - Culvert : E7-RA-445700-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2025-11-28 | 2025-11-29
I2S-7688-MP-74.CN.S4.34.17.12 | Culvert ID : E7-RA-445700-1 / Type : 10*900mm HDPE / Ch28197 (56.92m each) | I.CN.34.21680 | CON - Sec.4 - Culvert : E7-RA-445700-1 - Headwall installation | 2025-11-30 | 2025-11-30
Culvert ID : 7-RA-444350-1 / Type : 4*900mm HDPE / Ch26855 (40.22m each) |  |  |  | 2025-11-13 | 2025-11-24
I2S-7688-MP-74.CN.S4.34.17.11 | Culvert ID : 7-RA-444350-1 / Type : 4*900mm HDPE / Ch26855 (40.22m each) | I.CN.34.21860 | CON - Sec.4 - Culvert : 7-RA-444350-1 - Construct Scour Protection | 2025-11-23 | 2025-11-24
I2S-7688-MP-74.CN.S4.34.17.11 | Culvert ID : 7-RA-444350-1 / Type : 4*900mm HDPE / Ch26855 (40.22m each) | I.CN.34.21750 | CON - Sec.4 - Culvert : 7-RA-444350-1 - Site Prep / Detail Excavation | 2025-11-13 | 2025-11-14
I2S-7688-MP-74.CN.S4.34.17.11 | Culvert ID : 7-RA-444350-1 / Type : 4*900mm HDPE / Ch26855 (40.22m each) | I.CN.34.21760 | CON - Sec.4 - Culvert : 7-RA-444350-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2025-11-16 | 2025-11-17
I2S-7688-MP-74.CN.S4.34.17.11 | Culvert ID : 7-RA-444350-1 / Type : 4*900mm HDPE / Ch26855 (40.22m each) | I.CN.34.21800 | CON - Sec.4 - Culvert : 7-RA-444350-1 - Headwall installation | 2025-11-18 | 2025-11-18
I2S-7688-MP-74.CN.S4.34.17.11 | Culvert ID : 7-RA-444350-1 / Type : 4*900mm HDPE / Ch26855 (40.22m each) | I.CN.34.21810 | CON - Sec.4 - Culvert : 7-RA-444350-1 - HDPE / RCP Pipe Lay & Backfill | 2025-11-19 | 2025-11-19
I2S-7688-MP-74.CN.S4.34.17.11 | Culvert ID : 7-RA-444350-1 / Type : 4*900mm HDPE / Ch26855 (40.22m each) | I.CN.34.21830 | CON - Sec.4 - Culvert : 7-RA-444350-1 - Headwall Stitch Pour | 2025-11-20 | 2025-11-20
I2S-7688-MP-74.CN.S4.34.17.11 | Culvert ID : 7-RA-444350-1 / Type : 4*900mm HDPE / Ch26855 (40.22m each) | I.CN.34.21840 | CON - Sec.4 - Culvert : 7-RA-444350-1 - Headwall Cut-off Wall Installation (FRP) | 2025-11-21 | 2025-11-22
Culvert ID : E7-RA-443720-1 / Type : 1*900mm HDPE / Ch26194 (33.91m each) |  |  |  | 2025-10-29 | 2025-11-12
I2S-7688-MP-74.CN.S4.34.17.10 | Culvert ID : E7-RA-443720-1 / Type : 1*900mm HDPE / Ch26194 (33.91m each) | I.CN.34.21930 | CON - Sec.4 - Culvert : E7-RA-443720-1 - HDPE / RCP Pipe Lay & Backfill | 2025-11-04 | 2025-11-04
I2S-7688-MP-74.CN.S4.34.17.10 | Culvert ID : E7-RA-443720-1 / Type : 1*900mm HDPE / Ch26194 (33.91m each) | I.CN.34.21950 | CON - Sec.4 - Culvert : E7-RA-443720-1 - Headwall Stitch Pour | 2025-11-06 | 2025-11-07
I2S-7688-MP-74.CN.S4.34.17.10 | Culvert ID : E7-RA-443720-1 / Type : 1*900mm HDPE / Ch26194 (33.91m each) | I.CN.34.21960 | CON - Sec.4 - Culvert : E7-RA-443720-1 - Headwall Cut-off Wall Installation (FRP) | 2025-11-08 | 2025-11-09
I2S-7688-MP-74.CN.S4.34.17.10 | Culvert ID : E7-RA-443720-1 / Type : 1*900mm HDPE / Ch26194 (33.91m each) | I.CN.34.21980 | CON - Sec.4 - Culvert : E7-RA-443720-1 - Construct Scour Protection | 2025-11-11 | 2025-11-12
I2S-7688-MP-74.CN.S4.34.17.10 | Culvert ID : E7-RA-443720-1 / Type : 1*900mm HDPE / Ch26194 (33.91m each) | I.CN.34.21880 | CON - Sec.4 - Culvert : E7-RA-443720-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2025-10-31 | 2025-11-01
I2S-7688-MP-74.CN.S4.34.17.10 | Culvert ID : E7-RA-443720-1 / Type : 1*900mm HDPE / Ch26194 (33.91m each) | I.CN.34.21920 | CON - Sec.4 - Culvert : E7-RA-443720-1 - Headwall installation | 2025-11-02 | 2025-11-03
I2S-7688-MP-74.CN.S4.34.17.10 | Culvert ID : E7-RA-443720-1 / Type : 1*900mm HDPE / Ch26194 (33.91m each) | I.CN.34.21870 | CON - Sec.4 - Culvert : E7-RA-443720-1 - Site Prep / Detail Excavation | 2025-10-29 | 2025-10-30
Culvert ID : E7-RA-443560-1 / Type : 4*900mm HDPE / Ch26055 (26.65m each)
I2S-7688-MP-74.CN.S4.34.17.7 | Culvert ID : E7-RA-443560-1 / Type : 4*900mm HDPE / Ch26055 (26.65m each) | I.CN.34.32570 | CON - Sec.4 - Culvert : E7-RA-443560-1 - Construct Scour Protection
I2S-7688-MP-74.CN.S4.34.17.7 | Culvert ID : E7-RA-443560-1 / Type : 4*900mm HDPE / Ch26055 (26.65m each) | I.CN.34.32510 | CON - Sec.4 - Culvert : E7-RA-443560-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S4.34.17.7 | Culvert ID : E7-RA-443560-1 / Type : 4*900mm HDPE / Ch26055 (26.65m each) | I.CN.34.32520 | CON - Sec.4 - Culvert : E7-RA-443560-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S4.34.17.7 | Culvert ID : E7-RA-443560-1 / Type : 4*900mm HDPE / Ch26055 (26.65m each) | I.CN.34.32530 | CON - Sec.4 - Culvert : E7-RA-443560-1 - Headwall installation
I2S-7688-MP-74.CN.S4.34.17.7 | Culvert ID : E7-RA-443560-1 / Type : 4*900mm HDPE / Ch26055 (26.65m each) | I.CN.34.32540 | CON - Sec.4 - Culvert : E7-RA-443560-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S4.34.17.7 | Culvert ID : E7-RA-443560-1 / Type : 4*900mm HDPE / Ch26055 (26.65m each) | I.CN.34.32550 | CON - Sec.4 - Culvert : E7-RA-443560-1- Headwall Stitch Pour
I2S-7688-MP-74.CN.S4.34.17.7 | Culvert ID : E7-RA-443560-1 / Type : 4*900mm HDPE / Ch26055 (26.65m each) | I.CN.34.32560 | CON - Sec.4 - Culvert : E7-RA-443560-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S4.34.17.7 | Culvert ID : E7-RA-443560-1 / Type : 4*900mm HDPE / Ch26055 (26.65m each) | I.CN.34.32840 | CON - Sec.4 - Culvert : E7-RA-443560-1 - HDPE / RCP Pipe Lay & Backfill - Milestone
Culvert ID : E7-RA-443484-1 / Type : 5*900mm HDPE / Ch25979 (29.35m each) |  |  |  | 2025-10-16 | 2025-10-28
I2S-7688-MP-74.CN.S4.34.17.9 | Culvert ID : E7-RA-443484-1 / Type : 5*900mm HDPE / Ch25979 (29.35m each) | I.CN.34.21990 | CON - Sec.4 - Culvert : E7-RA-443484-1 - Site Prep / Detail Excavation | 2025-10-16 | 2025-10-17
I2S-7688-MP-74.CN.S4.34.17.9 | Culvert ID : E7-RA-443484-1 / Type : 5*900mm HDPE / Ch25979 (29.35m each) | I.CN.34.22000 | CON - Sec.4 - Culvert : E7-RA-443484-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2025-10-18 | 2025-10-19
I2S-7688-MP-74.CN.S4.34.17.9 | Culvert ID : E7-RA-443484-1 / Type : 5*900mm HDPE / Ch25979 (29.35m each) | I.CN.34.22040 | CON - Sec.4 - Culvert : E7-RA-443484-1 - Headwall installation | 2025-10-20 | 2025-10-21
I2S-7688-MP-74.CN.S4.34.17.9 | Culvert ID : E7-RA-443484-1 / Type : 5*900mm HDPE / Ch25979 (29.35m each) | I.CN.34.22050 | CON - Sec.4 - Culvert : E7-RA-443484-1 - HDPE / RCP Pipe Lay & Backfill | 2025-10-22 | 2025-10-22
I2S-7688-MP-74.CN.S4.34.17.9 | Culvert ID : E7-RA-443484-1 / Type : 5*900mm HDPE / Ch25979 (29.35m each) | I.CN.34.22070 | CON - Sec.4 - Culvert : E7-RA-443484-1 - Headwall Stitch Pour | 2025-10-23 | 2025-10-23
I2S-7688-MP-74.CN.S4.34.17.9 | Culvert ID : E7-RA-443484-1 / Type : 5*900mm HDPE / Ch25979 (29.35m each) | I.CN.34.22080 | CON - Sec.4 - Culvert : E7-RA-443484-1 - Headwall Cut-off Wall Installation (FRP) | 2025-10-24 | 2025-10-26
I2S-7688-MP-74.CN.S4.34.17.9 | Culvert ID : E7-RA-443484-1 / Type : 5*900mm HDPE / Ch25979 (29.35m each) | I.CN.34.22100 | CON - Sec.4 - Culvert : E7-RA-443484-1 - Construct Scour Protection | 2025-10-27 | 2025-10-28
Culvert ID : E7-RA-443320-1 / Type : 8*900mm HDPE / Ch25819 (28.28m each) |  |  |  | 2025-09-22 | 2025-10-04
I2S-7688-MP-74.CN.S4.34.17.8 | Culvert ID : E7-RA-443320-1 / Type : 8*900mm HDPE / Ch25819 (28.28m each) | I.CN.34.22220 | CON - Sec.4 - Culvert : E7-RA-443320-1 - Construct Scour Protection | 2025-10-03 | 2025-10-04
I2S-7688-MP-74.CN.S4.34.17.8 | Culvert ID : E7-RA-443320-1 / Type : 8*900mm HDPE / Ch25819 (28.28m each) | I.CN.34.22110 | CON - Sec.4 - Culvert : E7-RA-443320-1 - Site Prep / Detail Excavation | 2025-09-22 | 2025-09-23
I2S-7688-MP-74.CN.S4.34.17.8 | Culvert ID : E7-RA-443320-1 / Type : 8*900mm HDPE / Ch25819 (28.28m each) | I.CN.34.22120 | CON - Sec.4 - Culvert : E7-RA-443320-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2025-09-24 | 2025-09-26
I2S-7688-MP-74.CN.S4.34.17.8 | Culvert ID : E7-RA-443320-1 / Type : 8*900mm HDPE / Ch25819 (28.28m each) | I.CN.34.22160 | CON - Sec.4 - Culvert : E7-RA-443320-1 - Headwall installation | 2025-09-27 | 2025-09-27
I2S-7688-MP-74.CN.S4.34.17.8 | Culvert ID : E7-RA-443320-1 / Type : 8*900mm HDPE / Ch25819 (28.28m each) | I.CN.34.22170 | CON - Sec.4 - Culvert : E7-RA-443320-1 - HDPE / RCP Pipe Lay & Backfill | 2025-09-28 | 2025-09-28
I2S-7688-MP-74.CN.S4.34.17.8 | Culvert ID : E7-RA-443320-1 / Type : 8*900mm HDPE / Ch25819 (28.28m each) | I.CN.34.22190 | CON - Sec.4 - Culvert : E7-RA-443320-1 - Headwall Stitch Pour | 2025-09-29 | 2025-09-30
I2S-7688-MP-74.CN.S4.34.17.8 | Culvert ID : E7-RA-443320-1 / Type : 8*900mm HDPE / Ch25819 (28.28m each) | I.CN.34.22200 | CON - Sec.4 - Culvert : E7-RA-443320-1 - Headwall Cut-off Wall Installation (FRP) | 2025-10-01 | 2025-10-02
Culvert ID : E7-RA-442560-1 / Type : 6*900mm HDPE / Ch25052 (24.40m each)
I2S-7688-MP-74.CN.S4.34.17.20 | Culvert ID : E7-RA-442560-1 / Type : 6*900mm HDPE / Ch25052 (24.40m each) | I.CN.34.30130 | CON - Sec.4 - Culvert : E7-RA-442560-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S4.34.17.20 | Culvert ID : E7-RA-442560-1 / Type : 6*900mm HDPE / Ch25052 (24.40m each) | I.CN.34.30140 | CON - Sec.4 - Culvert : E7-RA-442560-1 - Headwall installation
I2S-7688-MP-74.CN.S4.34.17.20 | Culvert ID : E7-RA-442560-1 / Type : 6*900mm HDPE / Ch25052 (24.40m each) | I.CN.34.30150 | CON - Sec.4 - Culvert : E7-RA-442560-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S4.34.17.20 | Culvert ID : E7-RA-442560-1 / Type : 6*900mm HDPE / Ch25052 (24.40m each) | I.CN.34.30160 | CON - Sec.4 - Culvert : E7-RA-442560-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S4.34.17.20 | Culvert ID : E7-RA-442560-1 / Type : 6*900mm HDPE / Ch25052 (24.40m each) | I.CN.34.30170 | CON - Sec.4 - Culvert : E7-RA-442560-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S4.34.17.20 | Culvert ID : E7-RA-442560-1 / Type : 6*900mm HDPE / Ch25052 (24.40m each) | I.CN.34.30190 | CON - Sec.4 - Culvert : E7-RA-442560-1 - Construct Scour Protection
I2S-7688-MP-74.CN.S4.34.17.20 | Culvert ID : E7-RA-442560-1 / Type : 6*900mm HDPE / Ch25052 (24.40m each) | I.CN.34.30120 | CON - Sec.4 - Culvert : E7-RA-442560-1 - Site Prep / Detail Excavation
Culvert ID : E7-RA-441210-1 / Type : 6*900mm HDPE / Ch23706 (15.32m each)
I2S-7688-MP-74.CN.S4.34.17.14 | Culvert ID : E7-RA-441210-1 / Type : 6*900mm HDPE / Ch23706 (15.32m each) | I.CN.34.32580 | CON - Sec.4 - Culvert : E7-RA-441210-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S4.34.17.14 | Culvert ID : E7-RA-441210-1 / Type : 6*900mm HDPE / Ch23706 (15.32m each) | I.CN.34.32590 | CON - Sec.4 - Culvert : E7-RA-441210-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S4.34.17.14 | Culvert ID : E7-RA-441210-1 / Type : 6*900mm HDPE / Ch23706 (15.32m each) | I.CN.34.32600 | CON - Sec.4 - Culvert : E7-RA-441210-1 - Headwall installation
I2S-7688-MP-74.CN.S4.34.17.14 | Culvert ID : E7-RA-441210-1 / Type : 6*900mm HDPE / Ch23706 (15.32m each) | I.CN.34.32610 | CON - Sec.4 - Culvert : E7-RA-441210-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S4.34.17.14 | Culvert ID : E7-RA-441210-1 / Type : 6*900mm HDPE / Ch23706 (15.32m each) | I.CN.34.32620 | CON - Sec.4 - Culvert : E7-RA-441210-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S4.34.17.14 | Culvert ID : E7-RA-441210-1 / Type : 6*900mm HDPE / Ch23706 (15.32m each) | I.CN.34.32630 | CON - Sec.4 - Culvert : E7-RA-441210-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S4.34.17.14 | Culvert ID : E7-RA-441210-1 / Type : 6*900mm HDPE / Ch23706 (15.32m each) | I.CN.34.32640 | CON - Sec.4 - Culvert : E7-RA-441210-1 - Construct Scour Protection
Culvert ID : E7-RA-441160-1 / Type : 12*900mm HDPE / Ch23639 (15.77m each)
I2S-7688-MP-74.CN.S4.34.17.17 | Culvert ID : E7-RA-441160-1 / Type : 12*900mm HDPE / Ch23639 (15.77m each) | I.CN.34.32680 | CON - Sec.4 - Culvert : E7-RA-441160-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S4.34.17.17 | Culvert ID : E7-RA-441160-1 / Type : 12*900mm HDPE / Ch23639 (15.77m each) | I.CN.34.32690 | CON - Sec.4 - Culvert : E7-RA-441160-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S4.34.17.17 | Culvert ID : E7-RA-441160-1 / Type : 12*900mm HDPE / Ch23639 (15.77m each) | I.CN.34.32700 | CON - Sec.4 - Culvert : E7-RA-441160-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S4.34.17.17 | Culvert ID : E7-RA-441160-1 / Type : 12*900mm HDPE / Ch23639 (15.77m each) | I.CN.34.32710 | CON - Sec.4 - Culvert : E7-RA-441160-1 - Construct Scour Protection
I2S-7688-MP-74.CN.S4.34.17.17 | Culvert ID : E7-RA-441160-1 / Type : 12*900mm HDPE / Ch23639 (15.77m each) | I.CN.34.32650 | CON - Sec.4 - Culvert : E7-RA-441160-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S4.34.17.17 | Culvert ID : E7-RA-441160-1 / Type : 12*900mm HDPE / Ch23639 (15.77m each) | I.CN.34.32660 | CON - Sec.4 - Culvert : E7-RA-441160-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S4.34.17.17 | Culvert ID : E7-RA-441160-1 / Type : 12*900mm HDPE / Ch23639 (15.77m each) | I.CN.34.32670 | CON - Sec.4 - Culvert : E7-RA-441160-1 - Headwall installation
Culvert ID : E7-RA-440830-1 / Type : 10*900mm HDPE / Ch23316 (17.08m each) |  |  |  | 2025-12-22 | 2026-01-17
I2S-7688-MP-74.CN.S4.34.17.6 | Culvert ID : E7-RA-440830-1 / Type : 10*900mm HDPE / Ch23316 (17.08m each) | I.CN.34.22410 | CON - Sec.4 - Culvert : E7-RA-440830-1 - HDPE / RCP Pipe Lay & Backfill | 2026-01-07 | 2026-01-09
I2S-7688-MP-74.CN.S4.34.17.6 | Culvert ID : E7-RA-440830-1 / Type : 10*900mm HDPE / Ch23316 (17.08m each) | I.CN.34.22430 | CON - Sec.4 - Culvert : E7-RA-440830-1 - Headwall Stitch Pour | 2026-01-10 | 2026-01-11
I2S-7688-MP-74.CN.S4.34.17.6 | Culvert ID : E7-RA-440830-1 / Type : 10*900mm HDPE / Ch23316 (17.08m each) | I.CN.34.22440 | CON - Sec.4 - Culvert : E7-RA-440830-1 - Headwall Cut-off Wall Installation (FRP) | 2026-01-12 | 2026-01-13
I2S-7688-MP-74.CN.S4.34.17.6 | Culvert ID : E7-RA-440830-1 / Type : 10*900mm HDPE / Ch23316 (17.08m each) | I.CN.34.22460 | CON - Sec.4 - Culvert : E7-RA-440830-1 - Construct Scour Protection | 2026-01-16 | 2026-01-17
I2S-7688-MP-74.CN.S4.34.17.6 | Culvert ID : E7-RA-440830-1 / Type : 10*900mm HDPE / Ch23316 (17.08m each) | I.CN.34.22350 | CON - Sec.4 - Culvert : E7-RA-440830-1 - Site Prep / Detail Excavation | 2025-12-22 | 2025-12-23
I2S-7688-MP-74.CN.S4.34.17.6 | Culvert ID : E7-RA-440830-1 / Type : 10*900mm HDPE / Ch23316 (17.08m each) | I.CN.34.22360 | CON - Sec.4 - Culvert : E7-RA-440830-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-01-05 | 2026-01-06
I2S-7688-MP-74.CN.S4.34.17.6 | Culvert ID : E7-RA-440830-1 / Type : 10*900mm HDPE / Ch23316 (17.08m each) | I.CN.34.22400 | CON - Sec.4 - Culvert : E7-RA-440830-1 - Headwall installation | 2026-01-07 | 2026-01-08
Culvert ID : E7-RA-440720-1 / Type : 10*900mm HDPE / Ch23225 (14.20m each) |  |  |  | 2025-12-08 | 2025-12-21
I2S-7688-MP-74.CN.S4.34.17.5 | Culvert ID : E7-RA-440720-1 / Type : 10*900mm HDPE / Ch23225 (14.20m each) | I.CN.34.22480 | CON - Sec.4 - Culvert : E7-RA-440720-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2025-12-10 | 2025-12-11
I2S-7688-MP-74.CN.S4.34.17.5 | Culvert ID : E7-RA-440720-1 / Type : 10*900mm HDPE / Ch23225 (14.20m each) | I.CN.34.22520 | CON - Sec.4 - Culvert : E7-RA-440720-1 - Place HDPE Pipe | 2025-12-12 | 2025-12-13
I2S-7688-MP-74.CN.S4.34.17.5 | Culvert ID : E7-RA-440720-1 / Type : 10*900mm HDPE / Ch23225 (14.20m each) | I.CN.34.22530 | CON - Sec.4 - Culvert : E7-RA-440720-1 - HDPE / RCP Pipe Lay & Backfill | 2025-12-14 | 2025-12-14
I2S-7688-MP-74.CN.S4.34.17.5 | Culvert ID : E7-RA-440720-1 / Type : 10*900mm HDPE / Ch23225 (14.20m each) | I.CN.34.22550 | CON - Sec.4 - Culvert : E7-RA-440720-1 - Headwall Stitch Pour | 2025-12-16 | 2025-12-17
I2S-7688-MP-74.CN.S4.34.17.5 | Culvert ID : E7-RA-440720-1 / Type : 10*900mm HDPE / Ch23225 (14.20m each) | I.CN.34.22560 | CON - Sec.4 - Culvert : E7-RA-440720-1 - Headwall Cut-off Wall Installation (FRP) | 2025-12-18 | 2025-12-19
I2S-7688-MP-74.CN.S4.34.17.5 | Culvert ID : E7-RA-440720-1 / Type : 10*900mm HDPE / Ch23225 (14.20m each) | I.CN.34.22580 | CON - Sec.4 - Culvert : E7-RA-440720-1 - Construct Scour Protection | 2025-12-20 | 2025-12-21
I2S-7688-MP-74.CN.S4.34.17.5 | Culvert ID : E7-RA-440720-1 / Type : 10*900mm HDPE / Ch23225 (14.20m each) | I.CN.34.22470 | CON - Sec.4 - Culvert : E7-RA-440720-1 - Site Prep / Detail Excavation | 2025-12-08 | 2025-12-09
Culvert ID : E7-RA-440130-1 / Type : 5*900mm HDPE / Ch22624 (12.90m each) |  |  |  | 2026-04-01 | 2026-04-14
I2S-7688-MP-74.CN.S4.34.17.15 | Culvert ID : E7-RA-440130-1 / Type : 5*900mm HDPE / Ch22624 (12.90m each) | I.CN.34.22590 | CON - Sec.4 - Culvert : E7-RA-440130-1 - Site Prep / Detail Excavation | 2026-04-01 | 2026-04-02
I2S-7688-MP-74.CN.S4.34.17.15 | Culvert ID : E7-RA-440130-1 / Type : 5*900mm HDPE / Ch22624 (12.90m each) | I.CN.34.22600 | CON - Sec.4 - Culvert : E7-RA-440130-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-04-03 | 2026-04-04
I2S-7688-MP-74.CN.S4.34.17.15 | Culvert ID : E7-RA-440130-1 / Type : 5*900mm HDPE / Ch22624 (12.90m each) | I.CN.34.22640 | CON - Sec.4 - Culvert : E7-RA-440130-1 - Headwall installation | 2026-04-06 | 2026-04-07
I2S-7688-MP-74.CN.S4.34.17.15 | Culvert ID : E7-RA-440130-1 / Type : 5*900mm HDPE / Ch22624 (12.90m each) | I.CN.34.22650 | CON - Sec.4 - Culvert : E7-RA-440130-1 - HDPE / RCP Pipe Lay & Backfill | 2026-04-09 | 2026-04-09
I2S-7688-MP-74.CN.S4.34.17.15 | Culvert ID : E7-RA-440130-1 / Type : 5*900mm HDPE / Ch22624 (12.90m each) | I.CN.34.22670 | CON - Sec.4 - Culvert : E7-RA-440130-1 - Headwall Stitch Pour | 2026-04-10 | 2026-04-11
I2S-7688-MP-74.CN.S4.34.17.15 | Culvert ID : E7-RA-440130-1 / Type : 5*900mm HDPE / Ch22624 (12.90m each) | I.CN.34.22680 | CON - Sec.4 - Culvert : E7-RA-440130-1 - Headwall Cut-off Wall Installation (FRP) | 2026-04-12 | 2026-04-13
I2S-7688-MP-74.CN.S4.34.17.15 | Culvert ID : E7-RA-440130-1 / Type : 5*900mm HDPE / Ch22624 (12.90m each) | I.CN.34.22700 | CON - Sec.4 - Culvert : E7-RA-440130-1 - Construct Scour Protection | 2026-04-14 | 2026-04-14
Culvert ID : E7-RA-439980-1 / Type : 20*1200x600mm RCBC / Ch22492 (7.20m each) |  |  |  | 2026-03-09 | 2026-03-31
I2S-7688-MP-74.CN.S4.34.17.4 | Culvert ID : E7-RA-439980-1 / Type : 20*1200x600mm RCBC / Ch22492 (7.20m each) | I.CN.34.28030 | CON - Sec.4 - Culvert : E7-RA-439980-1 - Blinding placement (50mm)
I2S-7688-MP-74.CN.S4.34.17.4 | Culvert ID : E7-RA-439980-1 / Type : 20*1200x600mm RCBC / Ch22492 (7.20m each) | I.CN.34.28040 | CON - Sec.4 - Culvert : E7-RA-439980-1 - 7 day Curing
I2S-7688-MP-74.CN.S4.34.17.4 | Culvert ID : E7-RA-439980-1 / Type : 20*1200x600mm RCBC / Ch22492 (7.20m each) | I.CN.34.21030 | CON - Sec.4 - Culvert : E7-RA-439980-1 - Site Prep / Detail Excavation | 2026-03-09 | 2026-03-10
I2S-7688-MP-74.CN.S4.34.17.4 | Culvert ID : E7-RA-439980-1 / Type : 20*1200x600mm RCBC / Ch22492 (7.20m each) | I.CN.34.21040 | CON - Sec.4 - Culvert : E7-RA-439980-1 - Struc fill Placement (250mm) | 2026-03-11 | 2026-03-18
I2S-7688-MP-74.CN.S4.34.17.4 | Culvert ID : E7-RA-439980-1 / Type : 20*1200x600mm RCBC / Ch22492 (7.20m each) | I.CN.34.21080 | CON - Sec.4 - Culvert : E7-RA-439980-1 - Place RCBC crown units | 2026-03-19 | 2026-03-22
I2S-7688-MP-74.CN.S4.34.17.4 | Culvert ID : E7-RA-439980-1 / Type : 20*1200x600mm RCBC / Ch22492 (7.20m each) | I.CN.34.21110 | CON - Sec.4 - Culvert : E7-RA-439980-1 - Place Pre-cast Wingwalls and Stich Pour | 2026-03-26 | 2026-03-27
I2S-7688-MP-74.CN.S4.34.17.4 | Culvert ID : E7-RA-439980-1 / Type : 20*1200x600mm RCBC / Ch22492 (7.20m each) | I.CN.34.21120 | CON - Sec.4 - Culvert : E7-RA-439980-1 - Pre-cast RCBC completion (Seal joints) | 2026-03-28 | 2026-03-29
I2S-7688-MP-74.CN.S4.34.17.4 | Culvert ID : E7-RA-439980-1 / Type : 20*1200x600mm RCBC / Ch22492 (7.20m each) | I.CN.34.21130 | CON - Sec.4 - Culvert : E7-RA-439980-1 - Detail backfill | 2026-03-30 | 2026-03-30
I2S-7688-MP-74.CN.S4.34.17.4 | Culvert ID : E7-RA-439980-1 / Type : 20*1200x600mm RCBC / Ch22492 (7.20m each) | I.CN.34.21140 | CON - Sec.4 - Culvert : E7-RA-439980-1 - Construct Scour protection | 2026-03-30 | 2026-03-31
I2S-7688-MP-74.CN.S4.34.17.4 | Culvert ID : E7-RA-439980-1 / Type : 20*1200x600mm RCBC / Ch22492 (7.20m each) | I.CN.34.32010 | CON - Sec.4 - Culvert : E7-RA-439980-1 - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.CN.S4.34.17.4 | Culvert ID : E7-RA-439980-1 / Type : 20*1200x600mm RCBC / Ch22492 (7.20m each) | I.CN.34.32850 | CON - Sec.4 - Culvert : E7-RA-439980-1 - FRP Base Slab / Apron Slab / Cut-off Wall - Milestone
Culvert ID : E7-RA-439475-1 / Type : 3*900mm HDPE / Ch21970 (15.28m each)
I2S-7688-MP-74.CN.S4.34.17.22 | Culvert ID : E7-RA-439475-1 / Type : 3*900mm HDPE / Ch21970 (15.28m each) | I.CN.34.30340 | CON - Sec.4 - Culvert : E7-RA-439475-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S4.34.17.22 | Culvert ID : E7-RA-439475-1 / Type : 3*900mm HDPE / Ch21970 (15.28m each) | I.CN.34.30350 | CON - Sec.4 - Culvert : E7-RA-439475-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S4.34.17.22 | Culvert ID : E7-RA-439475-1 / Type : 3*900mm HDPE / Ch21970 (15.28m each) | I.CN.34.30360 | CON - Sec.4 - Culvert : E7-RA-439475-1 - Headwall installation
I2S-7688-MP-74.CN.S4.34.17.22 | Culvert ID : E7-RA-439475-1 / Type : 3*900mm HDPE / Ch21970 (15.28m each) | I.CN.34.30290 | CON - Sec.4 - Culvert : E7-RA-439475-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S4.34.17.22 | Culvert ID : E7-RA-439475-1 / Type : 3*900mm HDPE / Ch21970 (15.28m each) | I.CN.34.30300 | CON - Sec.4 - Culvert : E7-RA-439475-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S4.34.17.22 | Culvert ID : E7-RA-439475-1 / Type : 3*900mm HDPE / Ch21970 (15.28m each) | I.CN.34.30310 | CON - Sec.4 - Culvert : E7-RA-439475-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S4.34.17.22 | Culvert ID : E7-RA-439475-1 / Type : 3*900mm HDPE / Ch21970 (15.28m each) | I.CN.34.30330 | CON - Sec.4 - Culvert : E7-RA-439475-1 - Construct Scour Protection
Culvert ID : E7-RA-439300-1 / Type : 18*900mm HDPE / Ch21763 (30.81m each) |  |  |  | 2026-02-10 | 2026-03-08
I2S-7688-MP-74.CN.S4.34.17.3 | Culvert ID : E7-RA-439300-1 / Type : 18*900mm HDPE / Ch21763 (30.81m each) | I.CN.34.21210 | CON - Sec.4 - Culvert : E7-RA-439300-1 - HDPE / RCP Pipe Lay & Backfill | 2026-02-28 | 2026-03-01
I2S-7688-MP-74.CN.S4.34.17.3 | Culvert ID : E7-RA-439300-1 / Type : 18*900mm HDPE / Ch21763 (30.81m each) | I.CN.34.21230 | CON - Sec.4 - Culvert : E7-RA-439300-1 - Headwall Stitch Pour | 2026-03-02 | 2026-03-03
I2S-7688-MP-74.CN.S4.34.17.3 | Culvert ID : E7-RA-439300-1 / Type : 18*900mm HDPE / Ch21763 (30.81m each) | I.CN.34.21240 | CON - Sec.4 - Culvert : E7-RA-439300-1 - Headwall Cut-off Wall Installation (FRP) | 2026-03-04 | 2026-03-06
I2S-7688-MP-74.CN.S4.34.17.3 | Culvert ID : E7-RA-439300-1 / Type : 18*900mm HDPE / Ch21763 (30.81m each) | I.CN.34.21260 | CON - Sec.4 - Culvert : E7-RA-439300-1 - Construct Scour Protection | 2026-03-07 | 2026-03-08
I2S-7688-MP-74.CN.S4.34.17.3 | Culvert ID : E7-RA-439300-1 / Type : 18*900mm HDPE / Ch21763 (30.81m each) | I.CN.34.21150 | CON - Sec.4 - Culvert : E7-RA-439300-1 - Site Prep / Detail Excavation | 2026-02-10 | 2026-02-11
I2S-7688-MP-74.CN.S4.34.17.3 | Culvert ID : E7-RA-439300-1 / Type : 18*900mm HDPE / Ch21763 (30.81m each) | I.CN.34.21160 | CON - Sec.4 - Culvert : E7-RA-439300-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-02-12 | 2026-02-13
I2S-7688-MP-74.CN.S4.34.17.3 | Culvert ID : E7-RA-439300-1 / Type : 18*900mm HDPE / Ch21763 (30.81m each) | I.CN.34.21200 | CON - Sec.4 - Culvert : E7-RA-439300-1 - Headwall installation | 2026-02-14 | 2026-02-27
Culvert ID : E7-RA-438810-1 / Type : 3*900mm HDPE / Ch21304 (18.49m each) |  |  |  | 2026-04-15 | 2026-05-01
I2S-7688-MP-74.CN.S4.34.17.2 | Culvert ID : E7-RA-438810-1 / Type : 3*900mm HDPE / Ch21304 (18.49m each) | I.CN.34.21270 | CON - Sec.4 - Culvert : E7-RA-438810-1 - Site Prep / Detail Excavation | 2026-04-15 | 2026-04-16
I2S-7688-MP-74.CN.S4.34.17.2 | Culvert ID : E7-RA-438810-1 / Type : 3*900mm HDPE / Ch21304 (18.49m each) | I.CN.34.21280 | CON - Sec.4 - Culvert : E7-RA-438810-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-04-17 | 2026-04-18
I2S-7688-MP-74.CN.S4.34.17.2 | Culvert ID : E7-RA-438810-1 / Type : 3*900mm HDPE / Ch21304 (18.49m each) | I.CN.34.21320 | CON - Sec.4 - Culvert : E7-RA-438810-1 - Headwall installation | 2026-04-19 | 2026-04-21
I2S-7688-MP-74.CN.S4.34.17.2 | Culvert ID : E7-RA-438810-1 / Type : 3*900mm HDPE / Ch21304 (18.49m each) | I.CN.34.21330 | CON - Sec.4 - Culvert : E7-RA-438810-1 - HDPE / RCP Pipe Lay & Backfill | 2026-04-23 | 2026-04-23
I2S-7688-MP-74.CN.S4.34.17.2 | Culvert ID : E7-RA-438810-1 / Type : 3*900mm HDPE / Ch21304 (18.49m each) | I.CN.34.21350 | CON - Sec.4 - Culvert : E7-RA-438810-1 - Headwall Stitch Pour | 2026-04-26 | 2026-04-27
I2S-7688-MP-74.CN.S4.34.17.2 | Culvert ID : E7-RA-438810-1 / Type : 3*900mm HDPE / Ch21304 (18.49m each) | I.CN.34.21380 | CON - Sec.4 - Culvert : E7-RA-438810-1 - Construct Scour Protection | 2026-04-30 | 2026-05-01
I2S-7688-MP-74.CN.S4.34.17.2 | Culvert ID : E7-RA-438810-1 / Type : 3*900mm HDPE / Ch21304 (18.49m each) | I.CN.34.21360 | CON - Sec.4 - Culvert : E7-RA-438810-1 - Headwall Cut-off Wall Installation (FRP) | 2026-04-28 | 2026-04-29
Culvert ID : E7-RA-436880-1 / Type : 3*900mm HDPE / Ch19372 (55.53m each)
I2S-7688-MP-74.CN.S4.34.17.25 | Culvert ID : E7-RA-436880-1 / Type : 3*900mm HDPE / Ch19372 (55.53m each) | I.CN.34.30580 | CON - Sec.4 - Culvert : E7-RA-436880-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S4.34.17.25 | Culvert ID : E7-RA-436880-1 / Type : 3*900mm HDPE / Ch19372 (55.53m each) | I.CN.34.30600 | CON - Sec.4 - Culvert : E7-RA-436880-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S4.34.17.25 | Culvert ID : E7-RA-436880-1 / Type : 3*900mm HDPE / Ch19372 (55.53m each) | I.CN.34.30610 | CON - Sec.4 - Culvert : E7-RA-436880-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S4.34.17.25 | Culvert ID : E7-RA-436880-1 / Type : 3*900mm HDPE / Ch19372 (55.53m each) | I.CN.34.30630 | CON - Sec.4 - Culvert : E7-RA-436880-1 - Construct Scour Protection
I2S-7688-MP-74.CN.S4.34.17.25 | Culvert ID : E7-RA-436880-1 / Type : 3*900mm HDPE / Ch19372 (55.53m each) | I.CN.34.30550 | CON - Sec.4 - Culvert : E7-RA-436880-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S4.34.17.25 | Culvert ID : E7-RA-436880-1 / Type : 3*900mm HDPE / Ch19372 (55.53m each) | I.CN.34.30560 | CON - Sec.4 - Culvert : E7-RA-436880-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S4.34.17.25 | Culvert ID : E7-RA-436880-1 / Type : 3*900mm HDPE / Ch19372 (55.53m each) | I.CN.34.30570 | CON - Sec.4 - Culvert : E7-RA-436880-1 - Headwall installation
Culvert ID : E7-RA-436850-1 / Type : 7*750mm HDPE / Ch19323 (59.54m each) |  |  |  | 2026-05-09 | 2026-05-26
I2S-7688-MP-74.CN.S4.34.17.16 | Culvert ID : E7-RA-436850-1 / Type : 7*750mm HDPE / Ch19323 (59.54m each) | I.CN.34.27270 | CON - Sec.4 - Culvert : E7-RA-436850-1 - Site Prep / Detail Excavation | 2026-05-09 | 2026-05-10
I2S-7688-MP-74.CN.S4.34.17.16 | Culvert ID : E7-RA-436850-1 / Type : 7*750mm HDPE / Ch19323 (59.54m each) | I.CN.34.27280 | CON - Sec.4 - Culvert : E7-RA-436850-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-05-11 | 2026-05-12
I2S-7688-MP-74.CN.S4.34.17.16 | Culvert ID : E7-RA-436850-1 / Type : 7*750mm HDPE / Ch19323 (59.54m each) | I.CN.34.27320 | CON - Sec.4 - Culvert : E7-RA-436850-1 - Headwall installation | 2026-05-13 | 2026-05-16
I2S-7688-MP-74.CN.S4.34.17.16 | Culvert ID : E7-RA-436850-1 / Type : 7*750mm HDPE / Ch19323 (59.54m each) | I.CN.34.27330 | CON - Sec.4 - Culvert : E7-RA-436850-1 - HDPE / RCP Pipe Lay & Backfill | 2026-05-17 | 2026-05-18
I2S-7688-MP-74.CN.S4.34.17.16 | Culvert ID : E7-RA-436850-1 / Type : 7*750mm HDPE / Ch19323 (59.54m each) | I.CN.34.27350 | CON - Sec.4 - Culvert : E7-RA-436850-1 - Headwall Stitch Pour | 2026-05-20 | 2026-05-21
I2S-7688-MP-74.CN.S4.34.17.16 | Culvert ID : E7-RA-436850-1 / Type : 7*750mm HDPE / Ch19323 (59.54m each) | I.CN.34.27360 | CON - Sec.4 - Culvert : E7-RA-436850-1 - Headwall Cut-off Wall Installation (FRP) | 2026-05-22 | 2026-05-23
I2S-7688-MP-74.CN.S4.34.17.16 | Culvert ID : E7-RA-436850-1 / Type : 7*750mm HDPE / Ch19323 (59.54m each) | I.CN.34.27380 | CON - Sec.4 - Culvert : E7-RA-436850-1 - Construct Scour Protection | 2026-05-24 | 2026-05-26
Culvert ID : E7-RA-436105-1 / Type : 1*900mm HDPE / Ch18597 (36.193m each)
I2S-7688-MP-74.CN.S4.34.17.26 | Culvert ID : E7-RA-436105-1 / Type : 1*900mm HDPE / Ch18597 (36.193m each) | I.CN.34.30640 | CON - Sec.4 - Culvert : E7-RA-436105-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S4.34.17.26 | Culvert ID : E7-RA-436105-1 / Type : 1*900mm HDPE / Ch18597 (36.193m each) | I.CN.34.30650 | CON - Sec.4 - Culvert : E7-RA-436105-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S4.34.17.26 | Culvert ID : E7-RA-436105-1 / Type : 1*900mm HDPE / Ch18597 (36.193m each) | I.CN.34.30660 | CON - Sec.4 - Culvert : E7-RA-436105-1 - Headwall installation
I2S-7688-MP-74.CN.S4.34.17.26 | Culvert ID : E7-RA-436105-1 / Type : 1*900mm HDPE / Ch18597 (36.193m each) | I.CN.34.30670 | CON - Sec.4 - Culvert : E7-RA-436105-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S4.34.17.26 | Culvert ID : E7-RA-436105-1 / Type : 1*900mm HDPE / Ch18597 (36.193m each) | I.CN.34.30690 | CON - Sec.4 - Culvert : E7-RA-436105-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S4.34.17.26 | Culvert ID : E7-RA-436105-1 / Type : 1*900mm HDPE / Ch18597 (36.193m each) | I.CN.34.30700 | CON - Sec.4 - Culvert : E7-RA-436105-1 - Construct Scour Protection
I2S-7688-MP-74.CN.S4.34.17.26 | Culvert ID : E7-RA-436105-1 / Type : 1*900mm HDPE / Ch18597 (36.193m each) | I.CN.34.30710 | CON - Sec.4 - Culvert : E7-RA-436105-1 - Headwall Cut-off Wall Installation (FRP)
043 - Fencing |  |  |  | 2025-10-28 | 2026-04-03
Western Side |  |  |  | 2025-10-28 | 2026-04-03
I2S-7688-MP-74.CN.S4.43.1 | Western Side | I.CN.43.13990 | CON - Sec.4 - Fencing West Side - Ch18500-22100 | 2025-10-28 | 2025-12-18
I2S-7688-MP-74.CN.S4.43.1 | Western Side | I.CN.43.14010 | CON - Sec.4 - Fencing West Side - Ch22100-25000 | 2025-12-19 | 2026-02-09
I2S-7688-MP-74.CN.S4.43.1 | Western Side | I.CN.43.14030 | CON - Sec.4 - Fencing West Side - Ch25000-28300 | 2026-02-10 | 2026-04-03
Eastern Side |  |  |  | 2025-10-28 | 2026-04-03
I2S-7688-MP-74.CN.S4.43.2 | Eastern Side | I.CN.43.13750 | CON - Sec.4 - Fencing East Side - Ch18500-22100 | 2025-10-28 | 2025-12-18
I2S-7688-MP-74.CN.S4.43.2 | Eastern Side | I.CN.43.14000 | CON - Sec.4 - Fencing East Side - Ch22100-25000 | 2025-12-19 | 2026-02-09
I2S-7688-MP-74.CN.S4.43.2 | Eastern Side | I.CN.43.14020 | CON - Sec.4 - Fencing East Side - Ch25000-28300 | 2026-02-10 | 2026-04-03
044 - Roads |  |  |  | 2025-07-21 | 2025-10-16
Old Cootamundra Rail Bridge over Road |  |  |  | 2025-09-09 | 2025-10-16
I2S-7688-MP-74.CN.S4.44.1 | Old Cootamundra Rail Bridge over Road | I.CN.65.18000 | CON - Sec.4 - Construct Pavement type B sealed - SMZ Placement (350m2) Temp.Road Diversion - Old Coota Roa | 2025-09-09 | 2025-09-22
I2S-7688-MP-74.CN.S4.44.1 | Old Cootamundra Rail Bridge over Road | I.CN.65.18010 | CON - Sec.4 - Construct Pavement type B sealed - Primeseal (350m2) Temp. Road Diversion - Old Coota Road | 2025-09-23 | 2025-09-26
I2S-7688-MP-74.CN.S4.44.1 | Old Cootamundra Rail Bridge over Road | I.CN.65.18020 | CON - Sec.4 - Construct Pavement type B sealed - Asphalt (350m2) Temp. Road Diversion - Old Coota Road | 2025-09-27 | 2025-10-16
PR22750 to Dudauman Lane |  |  |  | 2025-07-21 | 2025-07-28
I2S-7688-MP-74.CN.S4.44.2 | PR22750 to Dudauman Lane | I.CN.65.17980 | CON - Sec.4 - Construct Pavement type A Unsealed - SMZ Placement (800m2) access road PR22750 to Dudauman Lane | 2025-07-21 | 2025-07-26
I2S-7688-MP-74.CN.S4.44.2 | PR22750 to Dudauman Lane | I.CN.65.17990 | CON - Sec.4 - Construct Pavement type A Unsealed - Primeseal (800m2) access road to PR22750 to Dudauman Lane | 2025-07-27 | 2025-07-28
045 - Access Roads |  |  |  | 2025-07-18 | 2026-07-12
Access/Temp |  |  |  | 2025-07-18 | 2025-07-20
I2S-7688-MP-74.CN.S4.45.1 | Access/Temp | I.CN.45.14440 | CON - Sec.4 - Gate 5A (22100) - Install Portable traffic sign | 2025-07-18 | 2025-07-20
RMAR Culverts |  |  |  | 2026-05-09 | 2026-07-12
I2S-7688-MP-74.CN.S4.45.2 | RMAR Culverts | I.CN.45.14250 | CON - Sec.4 - Prep RMAR Road - East - 18500-22100 | 2026-06-17 | 2026-06-24
I2S-7688-MP-74.CN.S4.45.2 | RMAR Culverts | I.CN.45.14370 | CON - Sec.4 - Prep RMAR Road - East - 22100-25000 | 2026-06-26 | 2026-07-03
I2S-7688-MP-74.CN.S4.45.2 | RMAR Culverts | I.CN.45.14380 | CON - Sec.4 - Prep RMAR Road - East - 25000-28300 | 2026-07-04 | 2026-07-12
RMAR_(019858)-01 |  |  |  | 2026-05-09 | 2026-05-12
I2S-7688-MP-74.CN.S4.45.2.2 | RMAR_(019858)-01 | I.CN.65.18220 | CON - Sec.4 - RMAR - CH19858-01 Culvert - Trench Excavation/ Culvert site prep | 2026-05-09 | 2026-05-10
I2S-7688-MP-74.CN.S4.45.2.2 | RMAR_(019858)-01 | I.CN.65.18230 | CON - Sec.4 - RMAR - CH19858-01 Culvert - Install 1 x 900 RCP - 15 off 35m | 2026-05-11 | 2026-05-11
I2S-7688-MP-74.CN.S4.45.2.2 | RMAR_(019858)-01 | I.CN.65.18240 | CON - Sec.4 - RMAR - CH19858-01 Culvert - Detailed backfill | 2026-05-12 | 2026-05-12
RMAR_(019858)-02 |  |  |  | 2026-05-13 | 2026-05-17
I2S-7688-MP-74.CN.S4.45.2.5 | RMAR_(019858)-02 | I.CN.65.18260 | CON - Sec.4 - RMAR - CH19858-02 Culvert - Trench Excavation/ Culvert site prep | 2026-05-13 | 2026-05-14
I2S-7688-MP-74.CN.S4.45.2.5 | RMAR_(019858)-02 | I.CN.65.18270 | CON - Sec.4 - RMAR - CH19858-02 Culvert - Install 1 x 450 RCP - 16 off 37m | 2026-05-16 | 2026-05-16
I2S-7688-MP-74.CN.S4.45.2.5 | RMAR_(019858)-02 | I.CN.65.18280 | CON - Sec.4 - RMAR - CH19858-02 Culvert - Detailed backfill | 2026-05-17 | 2026-05-17
050 - Trackwork |  |  |  | 2026-08-30 | 2026-11-10
Place Bottom Ballast |  |  |  | 2026-09-14 | 2026-10-06
I2S-7688-MP-74.CN.S4.50.15 | Place Bottom Ballast | I.CN.50.13690 | CON - Sec.4 - Place Bottom Ballast - 500m/day - 21500 to 22000 (500m) | 2026-09-21 | 2026-09-21
I2S-7688-MP-74.CN.S4.50.15 | Place Bottom Ballast | I.CN.50.13700 | CON - Sec.4 - Place Bottom Ballast - 500m/day - 22000 to 22500 (500m) | 2026-09-22 | 2026-09-22
I2S-7688-MP-74.CN.S4.50.15 | Place Bottom Ballast | I.CN.50.13710 | CON - Sec.4 - Place Bottom Ballast - 500m/day - 22500 to 23000 (500m) | 2026-09-23 | 2026-09-23
I2S-7688-MP-74.CN.S4.50.15 | Place Bottom Ballast | I.CN.50.13720 | CON - Sec.4 - Place Bottom Ballast - 500m/day - 23000 to 23500 (500m) | 2026-09-24 | 2026-09-24
I2S-7688-MP-74.CN.S4.50.15 | Place Bottom Ballast | I.CN.50.13730 | CON - Sec.4 - Place Bottom Ballast - 500m/day - 23500 to 24000 (500m) | 2026-09-26 | 2026-09-26
I2S-7688-MP-74.CN.S4.50.15 | Place Bottom Ballast | I.CN.50.13740 | CON - Sec.4 - Place Bottom Ballast - 500m/day - 24000 to 24500 (500m) | 2026-09-27 | 2026-09-27
I2S-7688-MP-74.CN.S4.50.15 | Place Bottom Ballast | I.CN.50.13750 | CON - Sec.4 - Place Bottom Ballast - 500m/day - 24500 to 25000 (500m) | 2026-09-28 | 2026-09-28
I2S-7688-MP-74.CN.S4.50.15 | Place Bottom Ballast | I.CN.50.13760 | CON - Sec.4 - Place Bottom Ballast - 500m/day - 25000 to 25500 (500m) | 2026-09-29 | 2026-09-29
I2S-7688-MP-74.CN.S4.50.15 | Place Bottom Ballast | I.CN.50.13770 | CON - Sec.4 - Place Bottom Ballast - 500m/day - 25500 to 26000 (500m) | 2026-09-30 | 2026-09-30
I2S-7688-MP-74.CN.S4.50.15 | Place Bottom Ballast | I.CN.50.13780 | CON - Sec.4 - Place Bottom Ballast - 500m/day - 26000 to 26500 (500m) | 2026-10-01 | 2026-10-01
I2S-7688-MP-74.CN.S4.50.15 | Place Bottom Ballast | I.CN.50.13790 | CON - Sec.4 - Place Bottom Ballast - 500m/day - 26500 to 27000 (500m) | 2026-10-02 | 2026-10-02
I2S-7688-MP-74.CN.S4.50.15 | Place Bottom Ballast | I.CN.50.13800 | CON - Sec.4 - Place Bottom Ballast - 500m/day - 27000 to 27500 (500m) | 2026-10-03 | 2026-10-03
I2S-7688-MP-74.CN.S4.50.15 | Place Bottom Ballast | I.CN.50.13810 | CON - Sec.4 - Place Bottom Ballast - 500m/day - 27500 to 28000 (500m) | 2026-10-04 | 2026-10-04
I2S-7688-MP-74.CN.S4.50.15 | Place Bottom Ballast | I.CN.50.13820 | CON - Sec.4 - Place Bottom Ballast - 500m/day - 28000 to 28300 (500m) - Old Coot Bridge | 2026-10-06 | 2026-10-06
I2S-7688-MP-74.CN.S4.50.15 | Place Bottom Ballast | I.CN.50.13630 | CON - Sec.4 - Place Bottom Ballast - 500m/day - 18500 to 19000 (500m) | 2026-09-14 | 2026-09-14
I2S-7688-MP-74.CN.S4.50.15 | Place Bottom Ballast | I.CN.50.13640 | CON - Sec.4 - Place Bottom Ballast - 500m/day - 19000 to 19500 (500m) | 2026-09-16 | 2026-09-16
I2S-7688-MP-74.CN.S4.50.15 | Place Bottom Ballast | I.CN.50.13650 | CON - Sec.4 - Place Bottom Ballast - 500m/day - 19500 to 20000 (500m) - Isobel Bridges | 2026-09-17 | 2026-09-17
I2S-7688-MP-74.CN.S4.50.15 | Place Bottom Ballast | I.CN.50.13660 | CON - Sec.4 - Place Bottom Ballast - 500m/day - 20000 to 20500 (500m) - Isobel Bridges | 2026-09-18 | 2026-09-18
I2S-7688-MP-74.CN.S4.50.15 | Place Bottom Ballast | I.CN.50.13670 | CON - Sec.4 - Place Bottom Ballast - 500m/day - 20500 to 21000 (500m) - Isobel Bridges | 2026-09-19 | 2026-09-19
I2S-7688-MP-74.CN.S4.50.15 | Place Bottom Ballast | I.CN.50.13680 | CON - Sec.4 - Place Bottom Ballast - 500m/day - 21000 to 21500 (500m) | 2026-09-20 | 2026-09-20
Sleeper Distribution |  |  |  | 2026-08-30 | 2026-10-07
I2S-7688-MP-74.CN.S4.50.1 | Sleeper Distribution | I.CN.50.4990 | CON - Sec.4 - Sleeper Distribution - 860m/day - 22990 to 23680 (860m) | 2026-09-29 | 2026-09-29
I2S-7688-MP-74.CN.S4.50.1 | Sleeper Distribution | I.CN.50.4920 | CON - Sec.4 - Sleeper Distribution - 860m/day - 18160 to 18850 (860m) | 2026-09-18 | 2026-09-18
I2S-7688-MP-74.CN.S4.50.1 | Sleeper Distribution | I.CN.50.4930 | CON - Sec.4 - Sleeper Distribution - 860m/day - 18850 to 19540 (860m) | 2026-09-22 | 2026-09-22
I2S-7688-MP-74.CN.S4.50.1 | Sleeper Distribution | I.CN.50.4940 | CON - Sec.4 - Sleeper Distribution - 860m/day - 19540 to 20230 (860m) - Isobel Bridges | 2026-09-23 | 2026-09-23
I2S-7688-MP-74.CN.S4.50.1 | Sleeper Distribution | I.CN.50.4950 | CON - Sec.4 - Sleeper Distribution - 860m/day - 20230 to 20920 (860m) - Isobel Bridges | 2026-09-24 | 2026-09-24
I2S-7688-MP-74.CN.S4.50.1 | Sleeper Distribution | I.CN.50.4960 | CON - Sec.4 - Sleeper Distribution - 860m/day - 20920 to 21610 (860m) - Isobel Bridges | 2026-09-26 | 2026-09-26
I2S-7688-MP-74.CN.S4.50.1 | Sleeper Distribution | I.CN.50.4970 | CON - Sec.4 - Sleeper Distribution - 860m/day - 21610 to 22300 (860m) | 2026-09-27 | 2026-09-27
I2S-7688-MP-74.CN.S4.50.1 | Sleeper Distribution | I.CN.50.5000 | CON - Sec.4 - Sleeper Distribution - 860m/day - 23680 to 24370 (860m) | 2026-09-30 | 2026-09-30
I2S-7688-MP-74.CN.S4.50.1 | Sleeper Distribution | I.CN.50.5010 | CON - Sec.4 - Sleeper Distribution - 860m/day - 24370 to 25060 (860m) | 2026-10-01 | 2026-10-01
I2S-7688-MP-74.CN.S4.50.1 | Sleeper Distribution | I.CN.50.5020 | CON - Sec.4 - Sleeper Distribution - 860m/day - 25060 to 25750 (860m) | 2026-10-02 | 2026-10-02
I2S-7688-MP-74.CN.S4.50.1 | Sleeper Distribution | I.CN.50.5030 | CON - Sec.4 - Sleeper Distribution - 860m/day - 25750 to 26440 (860m) | 2026-10-03 | 2026-10-03
I2S-7688-MP-74.CN.S4.50.1 | Sleeper Distribution | I.CN.50.5040 | CON - Sec.4 - Sleeper Distribution - 860m/day - 26440 to 27130 (860m) | 2026-10-04 | 2026-10-04
I2S-7688-MP-74.CN.S4.50.1 | Sleeper Distribution | I.CN.50.5050 | CON - Sec.4 - Sleeper Distribution - 860m/day - 27130 to 27820 (860m) | 2026-10-06 | 2026-10-06
I2S-7688-MP-74.CN.S4.50.1 | Sleeper Distribution | I.CN.50.5060 | CON - Sec.4 - Sleeper Distribution - 860m/day - 27820 to 28510 (860m) - Old Coot Bridge | 2026-10-07 | 2026-10-07
I2S-7688-MP-74.CN.S4.50.1 | Sleeper Distribution | I.CN.50.14350 | CON - Sec.4 - Intermediate Sleeper Stockpiles - Sec.4 | 2026-08-30 | 2026-08-31
I2S-7688-MP-74.CN.S4.50.1 | Sleeper Distribution | I.CN.50.4980 | CON - Sec.4 - Sleeper Distribution - 860m/day - 22300 to 22990 (860m) | 2026-09-28 | 2026-09-28
Sleeper Laying |  |  |  | 2026-09-24 | 2026-10-08
I2S-7688-MP-74.CN.S4.50.3 | Sleeper Laying | I.CN.50.4030 | CON - Sec.4 - Sleeper Laying - 800m/day - 21820 to 22620 | 2026-09-29 | 2026-09-29
I2S-7688-MP-74.CN.S4.50.3 | Sleeper Laying | I.CN.50.4040 | CON - Sec.4 - Sleeper Laying - 800m/day - 22620 to 23420 | 2026-09-30 | 2026-09-30
I2S-7688-MP-74.CN.S4.50.3 | Sleeper Laying | I.CN.50.4050 | CON - Sec.4 - Sleeper Laying - 800m/day - 23420 to 24220 | 2026-10-01 | 2026-10-01
I2S-7688-MP-74.CN.S4.50.3 | Sleeper Laying | I.CN.50.4060 | CON - Sec.4 - Sleeper Laying - 800m/day - 24220 to 25020 | 2026-10-02 | 2026-10-02
I2S-7688-MP-74.CN.S4.50.3 | Sleeper Laying | I.CN.50.4070 | CON - Sec.4 - Sleeper Laying - 800m/day - 25020 to 26620 | 2026-10-06 | 2026-10-06
I2S-7688-MP-74.CN.S4.50.3 | Sleeper Laying | I.CN.50.4080 | CON - Sec.4 - Sleeper Laying - 800m/day - 26620 to 27420 | 2026-10-07 | 2026-10-07
I2S-7688-MP-74.CN.S4.50.3 | Sleeper Laying | I.CN.50.4120 | CON - Sec.4 - Sleeper Laying - 800m/day - 27420 to 28220 - Old Coot Bridge | 2026-10-08 | 2026-10-08
I2S-7688-MP-74.CN.S4.50.3 | Sleeper Laying | I.CN.50.3980 | CON - Sec.4 - Sleeper Laying - 800m/day - 18620 to 19420 | 2026-09-24 | 2026-09-24
I2S-7688-MP-74.CN.S4.50.3 | Sleeper Laying | I.CN.50.3990 | CON - Sec.4 - Sleeper Laying - 800m/day - 19420 to 20220 - Isobel Bridges | 2026-09-26 | 2026-09-26
I2S-7688-MP-74.CN.S4.50.3 | Sleeper Laying | I.CN.50.4000 | CON - Sec.4 - Sleeper Laying - 800m/day - 20220 to 21020 - Isobel Bridges | 2026-09-27 | 2026-09-27
I2S-7688-MP-74.CN.S4.50.3 | Sleeper Laying | I.CN.50.4010 | CON - Sec.4 - Sleeper Laying - 800m/day - 21020 to 21820 | 2026-09-28 | 2026-09-28
Rail Distribution |  |  |  | 2026-09-28 | 2026-10-10
I2S-7688-MP-74.CN.S4.50.2 | Rail Distribution | I.CN.50.4490 | CON - Sec.4 - Rail Distribution - 860m/day - 21010 to 22000 | 2026-10-01 | 2026-10-01
I2S-7688-MP-74.CN.S4.50.2 | Rail Distribution | I.CN.50.4500 | CON - Sec.4 - Rail Distribution - 860m/day - 22000 to 22990 | 2026-10-02 | 2026-10-02
I2S-7688-MP-74.CN.S4.50.2 | Rail Distribution | I.CN.50.4460 | CON - Sec.4 - Rail Distribution - 860m/day - 18040 to 19030 | 2026-09-28 | 2026-09-28
I2S-7688-MP-74.CN.S4.50.2 | Rail Distribution | I.CN.50.4470 | CON - Sec.4 - Rail Distribution - 860m/day - 19030 to 20020 - Isobel Bridges | 2026-09-29 | 2026-09-29
I2S-7688-MP-74.CN.S4.50.2 | Rail Distribution | I.CN.50.4480 | CON - Sec.4 - Rail Distribution - 860m/day - 20020 to 21010 - Isobel Bridges | 2026-09-30 | 2026-09-30
I2S-7688-MP-74.CN.S4.50.2 | Rail Distribution | I.CN.50.4510 | CON - Sec.4 - Rail Distribution - 860m/day - 22990 to 23980 | 2026-10-03 | 2026-10-03
I2S-7688-MP-74.CN.S4.50.2 | Rail Distribution | I.CN.50.4520 | CON - Sec.4 - Rail Distribution - 860m/day - 23980 to 24970 | 2026-10-04 | 2026-10-04
I2S-7688-MP-74.CN.S4.50.2 | Rail Distribution | I.CN.50.4530 | CON - Sec.4 - Rail Distribution - 860m/day - 24970 to 25960 | 2026-10-06 | 2026-10-06
I2S-7688-MP-74.CN.S4.50.2 | Rail Distribution | I.CN.50.4540 | CON - Sec.4 - Rail Distribution - 860m/day - 25960 to 26950 | 2026-10-08 | 2026-10-08
I2S-7688-MP-74.CN.S4.50.2 | Rail Distribution | I.CN.50.4550 | CON - Sec.4 - Rail Distribution - 860m/day - 26950 to 27940 | 2026-10-09 | 2026-10-09
I2S-7688-MP-74.CN.S4.50.2 | Rail Distribution | I.CN.50.4560 | CON - Sec.4 - Rail Distribution - 860m/day - 27940 to 28930 - Old Coot Bridge | 2026-10-10 | 2026-10-10
Rail Laying |  |  |  | 2026-10-03 | 2026-10-19
I2S-7688-MP-74.CN.S4.50.4 | Rail Laying | I.CN.50.3570 | CON - Sec.4 - Rail Laying - 550m/day - 28300 to 29020 - Old Coot Bridge | 2026-10-19 | 2026-10-19
I2S-7688-MP-74.CN.S4.50.4 | Rail Laying | I.CN.50.3430 | CON - Sec.4 - Rail Laying - 550m/day - 18220 to 18940 | 2026-10-03 | 2026-10-03
I2S-7688-MP-74.CN.S4.50.4 | Rail Laying | I.CN.50.3440 | CON - Sec.4 - Rail Laying - 550m/day - 18940 to 19660 - Isobel Bridges | 2026-10-04 | 2026-10-04
I2S-7688-MP-74.CN.S4.50.4 | Rail Laying | I.CN.50.3450 | CON - Sec.4 - Rail Laying - 550m/day - 19660 to 20380 - Isobel Bridges | 2026-10-06 | 2026-10-06
I2S-7688-MP-74.CN.S4.50.4 | Rail Laying | I.CN.50.3460 | CON - Sec.4 - Rail Laying - 550m/day - 20380 to 21100 - Isobel Bridges | 2026-10-07 | 2026-10-07
I2S-7688-MP-74.CN.S4.50.4 | Rail Laying | I.CN.50.3470 | CON - Sec.4 - Rail Laying - 550m/day - 21100 to 21820 | 2026-10-08 | 2026-10-08
I2S-7688-MP-74.CN.S4.50.4 | Rail Laying | I.CN.50.3480 | CON - Sec.4 - Rail Laying - 550m/day - 21820 to 22540 | 2026-10-09 | 2026-10-09
I2S-7688-MP-74.CN.S4.50.4 | Rail Laying | I.CN.50.3490 | CON - Sec.4 - Rail Laying - 550m/day - 22540 to 23260 | 2026-10-10 | 2026-10-10
I2S-7688-MP-74.CN.S4.50.4 | Rail Laying | I.CN.50.3500 | CON - Sec.4 - Rail Laying - 550m/day - 23260 to 23980 | 2026-10-11 | 2026-10-11
I2S-7688-MP-74.CN.S4.50.4 | Rail Laying | I.CN.50.3510 | CON - Sec.4 - Rail Laying - 550m/day - 23980 to 24700 | 2026-10-12 | 2026-10-12
I2S-7688-MP-74.CN.S4.50.4 | Rail Laying | I.CN.50.3520 | CON - Sec.4 - Rail Laying - 550m/day - 24700 to 25420 | 2026-10-13 | 2026-10-13
I2S-7688-MP-74.CN.S4.50.4 | Rail Laying | I.CN.50.3530 | CON - Sec.4 - Rail Laying - 550m/day - 25420 to 26140 | 2026-10-14 | 2026-10-14
I2S-7688-MP-74.CN.S4.50.4 | Rail Laying | I.CN.50.3540 | CON - Sec.4 - Rail Laying - 550m/day - 26140 to 26860 | 2026-10-16 | 2026-10-16
I2S-7688-MP-74.CN.S4.50.4 | Rail Laying | I.CN.50.3550 | CON - Sec.4 - Rail Laying - 550m/day - 26860 to 27580 | 2026-10-17 | 2026-10-17
I2S-7688-MP-74.CN.S4.50.4 | Rail Laying | I.CN.50.3560 | CON - Sec.4 - Rail Laying - 550m/day - 27580 to 28300 | 2026-10-18 | 2026-10-18
Flash Butt Welding and clip up |  |  |  | 2026-10-06 | 2026-10-29
I2S-7688-MP-74.CN.S4.50.5 | Flash Butt Welding and clip up | I.CN.50.3070 | CON - Sec.4 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 26950 to 27940 | 2026-10-26 | 2026-10-27
I2S-7688-MP-74.CN.S4.50.5 | Flash Butt Welding and clip up | I.CN.50.3080 | CON - Sec.4 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 27940 to 28930 - Old Coot Bridge | 2026-10-28 | 2026-10-29
I2S-7688-MP-74.CN.S4.50.5 | Flash Butt Welding and clip up | I.CN.50.3030 | CON - Sec.4 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 22990 to 23980 | 2026-10-17 | 2026-10-18
I2S-7688-MP-74.CN.S4.50.5 | Flash Butt Welding and clip up | I.CN.50.3040 | CON - Sec.4 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 23980 to 24970 | 2026-10-19 | 2026-10-20
I2S-7688-MP-74.CN.S4.50.5 | Flash Butt Welding and clip up | I.CN.50.2980 | CON - Sec.4 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 18040 to 19030 | 2026-10-06 | 2026-10-07
I2S-7688-MP-74.CN.S4.50.5 | Flash Butt Welding and clip up | I.CN.50.2990 | CON - Sec.4 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 19030 to 20020- Isobel Bridges | 2026-10-08 | 2026-10-09
I2S-7688-MP-74.CN.S4.50.5 | Flash Butt Welding and clip up | I.CN.50.3000 | CON - Sec.4 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 20020 to 21010- Isobel Bridges | 2026-10-10 | 2026-10-11
I2S-7688-MP-74.CN.S4.50.5 | Flash Butt Welding and clip up | I.CN.50.3010 | CON - Sec.4 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 21010 to 22000 | 2026-10-12 | 2026-10-13
I2S-7688-MP-74.CN.S4.50.5 | Flash Butt Welding and clip up | I.CN.50.3020 | CON - Sec.4 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 22000 to 22990 | 2026-10-14 | 2026-10-16
I2S-7688-MP-74.CN.S4.50.5 | Flash Butt Welding and clip up | I.CN.50.3050 | CON - Sec.4 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 24970 to 25960 | 2026-10-21 | 2026-10-22
I2S-7688-MP-74.CN.S4.50.5 | Flash Butt Welding and clip up | I.CN.50.3060 | CON - Sec.4 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 25960 to 26950 | 2026-10-23 | 2026-10-24
Place Top Ballast Initial |  |  |  | 2026-10-20 | 2026-10-30
I2S-7688-MP-74.CN.S4.50.6 | Place Top Ballast Initial | I.CN.50.2690 | CON - Sec.4 - Place Top Ballast Initial - 1500m/day - 19720 to 21220 | 2026-10-21 | 2026-10-21
I2S-7688-MP-74.CN.S4.50.6 | Place Top Ballast Initial | I.CN.50.2700 | CON - Sec.4 - Place Top Ballast Initial - 1500m/day - 21220 to 22720 | 2026-10-22 | 2026-10-22
I2S-7688-MP-74.CN.S4.50.6 | Place Top Ballast Initial | I.CN.50.2710 | CON - Sec.4 - Place Top Ballast Initial - 1500m/day - 22720 to 24220 | 2026-10-23 | 2026-10-23
I2S-7688-MP-74.CN.S4.50.6 | Place Top Ballast Initial | I.CN.50.2720 | CON - Sec.4 - Place Top Ballast Initial - 1500m/day - 24220 to 25720 | 2026-10-26 | 2026-10-26
I2S-7688-MP-74.CN.S4.50.6 | Place Top Ballast Initial | I.CN.50.2730 | CON - Sec.4 - Place Top Ballast Initial - 1500m/day - 25720 to 27220 | 2026-10-27 | 2026-10-27
I2S-7688-MP-74.CN.S4.50.6 | Place Top Ballast Initial | I.CN.50.2740 | CON - Sec.4 - Place Top Ballast Initial - 1500m/day - 27220 to 28720 | 2026-10-30 | 2026-10-30
I2S-7688-MP-74.CN.S4.50.6 | Place Top Ballast Initial | I.CN.50.2680 | CON - Sec.4 - Place Top Ballast Initial - 1500m/day - 18220 to 19720 | 2026-10-20 | 2026-10-20
Traverse & Level GEDO |  |  |  | 2026-10-22 | 2026-10-31
I2S-7688-MP-74.CN.S4.50.14 | Traverse & Level GEDO | I.CN.50.18240 | CON - Sec.4 - Traverse and level Gedo Control - 28220 to 32220 | 2026-10-31 | 2026-10-31
I2S-7688-MP-74.CN.S4.50.14 | Traverse & Level GEDO | I.CN.50.18210 | CON - Sec.4 - Traverse and level Gedo Control - 18000 to 20220 | 2026-10-22 | 2026-10-22
I2S-7688-MP-74.CN.S4.50.14 | Traverse & Level GEDO | I.CN.50.18220 | CON - Sec.4 - Traverse and level Gedo Control - 20220 to 24220 | 2026-10-24 | 2026-10-24
I2S-7688-MP-74.CN.S4.50.14 | Traverse & Level GEDO | I.CN.50.18230 | CON - Sec.4 - Traverse and level Gedo Control - 24220 to 28220 | 2026-10-27 | 2026-10-27
Surfacing Firsts |  |  |  | 2026-10-22 | 2026-11-01
I2S-7688-MP-74.CN.S4.50.7 | Surfacing Firsts | I.CN.50.2570 | CON - Sec.4 - Surfacing Firsts - 4000m/day - 28220 to 32220 | 2026-11-01 | 2026-11-01
I2S-7688-MP-74.CN.S4.50.7 | Surfacing Firsts | I.CN.50.15160 | CON - Sec.4 - Surfacing Firsts - 4000m/day - 18000 to 20220 | 2026-10-22 | 2026-10-22
I2S-7688-MP-74.CN.S4.50.7 | Surfacing Firsts | I.CN.50.2550 | CON - Sec.4 - Surfacing Firsts - 4000m/day - 20220 to 24220 | 2026-10-26 | 2026-10-26
I2S-7688-MP-74.CN.S4.50.7 | Surfacing Firsts | I.CN.50.2560 | CON - Sec.4 - Surfacing Firsts - 4000m/day - 24220 to 28220 | 2026-10-28 | 2026-10-28
Surfacing Seconds |  |  |  | 2026-10-23 | 2026-11-02
I2S-7688-MP-74.CN.S4.50.8 | Surfacing Seconds | I.CN.50.2460 | CON - Sec.4 - Surfacing Seconds - 4000m/day - 20220 to 24220 | 2026-10-27 | 2026-10-27
I2S-7688-MP-74.CN.S4.50.8 | Surfacing Seconds | I.CN.50.2470 | CON - Sec.4 - Surfacing Seconds - 4000m/day - 24220 to 28220 | 2026-10-29 | 2026-10-29
I2S-7688-MP-74.CN.S4.50.8 | Surfacing Seconds | I.CN.50.2480 | CON - Sec.4 - Surfacing Seconds - 4000m/day - 28220 to 32220 | 2026-11-02 | 2026-11-02
I2S-7688-MP-74.CN.S4.50.8 | Surfacing Seconds | I.CN.50.15170 | CON - Sec.4 - Surfacing Seconds - 4000m/day - 18000 to 20220 | 2026-10-23 | 2026-10-23
Top Ballast Finals |  |  |  | 2026-10-28 | 2026-11-03
I2S-7688-MP-74.CN.S4.50.9 | Top Ballast Finals | I.CN.50.2340 | CON - Sec.4 - Top Ballast Finals - 3000m/day - 18000 to 21000 | 2026-10-28 | 2026-10-28
I2S-7688-MP-74.CN.S4.50.9 | Top Ballast Finals | I.CN.50.2350 | CON - Sec.4 - Top Ballast Finals - 3000m/day - 21000 to 24000 | 2026-10-29 | 2026-10-29
I2S-7688-MP-74.CN.S4.50.9 | Top Ballast Finals | I.CN.50.2360 | CON - Sec.4 - Top Ballast Finals - 3000m/day - 24000 to 27000 | 2026-10-30 | 2026-10-30
I2S-7688-MP-74.CN.S4.50.9 | Top Ballast Finals | I.CN.50.2370 | CON - Sec.4 - Top Ballast Finals - 3000m/day - 27000 to 30000 | 2026-11-03 | 2026-11-03
Surfacing Final |  |  |  | 2026-10-30 | 2026-11-04
I2S-7688-MP-74.CN.S4.50.10 | Surfacing Final | I.CN.50.2250 | CON - Sec.4 - Surfacing Final - 6000m/day - 18000 to 24000 | 2026-10-30 | 2026-10-30
I2S-7688-MP-74.CN.S4.50.10 | Surfacing Final | I.CN.50.2260 | CON - Sec.4 - Surfacing Final - 6000m/day - 24000 to 30000 | 2026-11-04 | 2026-11-04
Destressing |  |  |  | 2026-10-31 | 2026-11-09
I2S-7688-MP-74.CN.S4.50.11 | Destressing | I.CN.50.2100 | CON - Sec.4 - Destressing - 1200m/day - 24000 to 25200 | 2026-11-06 | 2026-11-06
I2S-7688-MP-74.CN.S4.50.11 | Destressing | I.CN.50.2110 | CON - Sec.4 - Destressing - 1200m/day - 25200 to 26400 | 2026-11-07 | 2026-11-07
I2S-7688-MP-74.CN.S4.50.11 | Destressing | I.CN.50.2120 | CON - Sec.4 - Destressing - 1200m/day - 26400 to 27600 | 2026-11-08 | 2026-11-08
I2S-7688-MP-74.CN.S4.50.11 | Destressing | I.CN.50.2130 | CON - Sec.4 - Destressing - 1200m/day - 27600 to 28800 | 2026-11-09 | 2026-11-09
I2S-7688-MP-74.CN.S4.50.11 | Destressing | I.CN.50.2050 | CON - Sec.4 - Destressing - 1200m/day - 18500 to 19200 | 2026-10-31 | 2026-10-31
I2S-7688-MP-74.CN.S4.50.11 | Destressing | I.CN.50.2060 | CON - Sec.4 - Destressing - 1200m/day - 19200 to 20400 | 2026-11-01 | 2026-11-01
I2S-7688-MP-74.CN.S4.50.11 | Destressing | I.CN.50.2070 | CON - Sec.4 - Destressing - 1200m/day - 20400 to 21600 | 2026-11-02 | 2026-11-02
I2S-7688-MP-74.CN.S4.50.11 | Destressing | I.CN.50.2080 | CON - Sec.4 - Destressing - 1200m/day - 21600 to 22800 | 2026-11-03 | 2026-11-03
I2S-7688-MP-74.CN.S4.50.11 | Destressing | I.CN.50.2090 | CON - Sec.4 - Destressing - 1200m/day - 22800 to 24000 | 2026-11-04 | 2026-11-04
Corrections + Signage + Rubber Xings |  |  |  | 2026-11-02 | 2026-11-09
I2S-7688-MP-74.CN.S4.50.12 | Corrections + Signage + Rubber Xings | I.CN.50.1790 | CON - Sec.4 - Corrections + Signage - 2000m/day - 18000 - 20000 | 2026-11-02 | 2026-11-02
I2S-7688-MP-74.CN.S4.50.12 | Corrections + Signage + Rubber Xings | I.CN.50.1830 | CON - Sec.4 - Corrections + Signage - 2000m/day - 26000 - 28000 | 2026-11-06 | 2026-11-06
I2S-7688-MP-74.CN.S4.50.12 | Corrections + Signage + Rubber Xings | I.CN.50.1840 | CON - Sec.4 - Corrections + Signage - 2000m/day - 28000 - 30000 | 2026-11-09 | 2026-11-09
I2S-7688-MP-74.CN.S4.50.12 | Corrections + Signage + Rubber Xings | I.CN.50.1800 | CON - Sec.4 - Corrections + Signage - 2000m/day - 20000 - 22000 | 2026-11-03 | 2026-11-03
I2S-7688-MP-74.CN.S4.50.12 | Corrections + Signage + Rubber Xings | I.CN.50.1820 | CON - Sec.4 - Corrections + Signage - 2000m/day - 24000 - 26000 | 2026-11-04 | 2026-11-04
Track Joint Inspection |  |  |  | 2026-11-07 | 2026-11-10
I2S-7688-MP-74.CN.S4.50.13 | Track Joint Inspection | I.CN.50.1660 | CON - Sec.4 - Track Joint Inspection - 5000m/day - 18500 - 25000 | 2026-11-07 | 2026-11-07
I2S-7688-MP-74.CN.S4.50.13 | Track Joint Inspection | I.CN.50.1670 | CON - Sec.4 - Track Joint Inspection - 5000m/day - 25000 - 28300 | 2026-11-10 | 2026-11-10
062 - Bridges |  |  |  | 2025-11-13 | 2026-08-04
Old Cootamundra Rail Bridge over Road- BR707 - 1015 SUPER-T (ARTC) |  |  |  | 2025-11-13 | 2026-08-04
Preliminaries |  |  |  | 2025-11-13 | 2025-11-24
I2S-7688-MP-74.CN.S4.62.4.1 | Preliminaries | I.CN.62.18840 | CON - Sec.4 - Old Cootmundra Rail Br - Construct site access | 2025-11-19 | 2025-11-20
I2S-7688-MP-74.CN.S4.62.4.1 | Preliminaries | I.CN.62.18930 | CON - Sec.4 - Old Cootmundra Rail Br - Construct laydown area /Causeway (inc pipes) | 2025-11-21 | 2025-11-24
I2S-7688-MP-74.CN.S4.62.4.1 | Preliminaries | I.CN.62.18830 | CON - Sec.4 - Old Cootmundra Rail Br - Bridge site prep /Temp Fence/Road Barriers | 2025-11-13 | 2025-11-18
Piling |  |  |  | 2025-12-12 | 2026-02-13
Platforms |  |  |  | 2025-12-12 | 2025-12-19
I2S-7688-MP-74.CN.S4.62.4.2.1 | Platforms | I.CN.62.18890 | CON - Sec.4 - Old Cootmundra Rail Br - Excavate platform for piling pad | 2025-12-12 | 2025-12-17
I2S-7688-MP-74.CN.S4.62.4.2.1 | Platforms | I.CN.62.18940 | CON - Sec.4 - Old Cootmundra Rail Br - Place and test platform | 2025-12-18 | 2025-12-19
Drill Piles |  |  |  | 2026-01-27 | 2026-02-08
I2S-7688-MP-74.CN.S4.62.4.2.3 | Drill Piles | I.CN.62.19660 | CON - Sec.4 - Old Cootmundra Rail Br - pier piling consist of 2 x 1500mm dia bored concrete piles | 2026-02-01 | 2026-02-07
I2S-7688-MP-74.CN.S4.62.4.2.3 | Drill Piles | I.CN.62.18900 | CON - Sec.4 - Old Cootmundra Rail Br - Demobilise piling rig | 2026-02-08 | 2026-02-08
I2S-7688-MP-74.CN.S4.62.4.2.3 | Drill Piles | I.CN.62.18950 | CON - Sec.4 - Old Cootmundra Rail Br - Mobilise piling rig | 2026-01-27 | 2026-01-27
I2S-7688-MP-74.CN.S4.62.4.2.3 | Drill Piles | I.CN.62.18960 | CON - Sec.4 - Old Cootmundra Rail Br - abutment piling consists of 4 x 1200mm dia bored concrete piles | 2026-01-28 | 2026-01-31
I2S-7688-MP-74.CN.S4.62.4.2.3 | Drill Piles | I.CN.62.23030 | CON - Sec.4 - Old Cootmundra Rail Br - abutment piling consists of 4 x 1200mm dia bored concrete piles - Milestone
Piles Concrete |  |  |  | 2026-02-09 | 2026-02-13
I2S-7688-MP-74.CN.S4.62.4.2.4 | Piles Concrete | I.CN.62.18910 | CON - Sec.4 - Old Cootmundra Rail Br - Place pile concrete | 2026-02-09 | 2026-02-13
Abutments |  |  |  | 2026-02-14 | 2026-06-20
Site Prep / Earthworks |  |  |  | 2026-04-23 | 2026-04-29
I2S-7688-MP-74.CN.S4.62.4.7.4 | Site Prep / Earthworks | I.CN.62.20060 | CON - Sec.4 - Old Cootmundra Rail Br - Site prep Abutments (North & South) | 2026-04-23 | 2026-04-26
I2S-7688-MP-74.CN.S4.62.4.7.4 | Site Prep / Earthworks | I.CN.62.20070 | CON - Sec.4 - Old Cootmundra Rail Br - Detailed Earthworks Abutments (North & South) | 2026-04-27 | 2026-04-29
South |  |  |  | 2026-03-28 | 2026-06-20
I2S-7688-MP-74.CN.S4.62.4.7.1 | South | I.CN.62.22110 | CON - Sec.4 - Old Cootmundra Rail Br - S&I Column Extension Sleeves & Pour Pile Extension - South Abutment
I2S-7688-MP-74.CN.S4.62.4.7.1 | South | I.CN.62.19070 | CON - Sec.4 - Old Cootmundra Rail Br - Mechanically Stabilised Earth Walls (MSE) - South Abutment | 2026-06-14 | 2026-06-20
I2S-7688-MP-74.CN.S4.62.4.7.1 | South | I.CN.62.20010 | CON - Sec.4 - Old Cootmundra Rail Br - Detailed Earthworks - South Abutment | 2026-03-28 | 2026-03-30
I2S-7688-MP-74.CN.S4.62.4.7.1 | South | I.CN.62.20090 | CON - Sec.4 - Old Cootmundra Rail Br - FRP Cill Beam - South Abutment | 2026-05-06 | 2026-05-11
I2S-7688-MP-74.CN.S4.62.4.7.1 | South | I.CN.62.20110 | CON - Sec.4 - Old Cootmundra Rail Br - FRP Back Wall - South Abutment | 2026-05-18 | 2026-05-22
I2S-7688-MP-74.CN.S4.62.4.7.1 | South | I.CN.62.21590 | CON - Sec.4 - Old Cootmundra Rail Br - FRP Bearing Mortar Pads - South Abutment | 2026-05-23 | 2026-05-27
I2S-7688-MP-74.CN.S4.62.4.7.1 | South | I.CN.62.21600 | CON - Sec.4 - Old Cootmundra Rail Br - FRP Restraint Blocks - South Abutment | 2026-05-28 | 2026-06-02
I2S-7688-MP-74.CN.S4.62.4.7.1 | South | I.CN.62.21610 | CON - Sec.4 - Old Cootmundra Rail Br - FRP Headstock - South Abutment | 2026-04-04 | 2026-04-10
Central Pier |  |  |  | 2026-02-14 | 2026-03-07
I2S-7688-MP-74.CN.S4.62.4.7.2 | Central Pier | I.CN.62.22130 | CON - Sec.4 - Old Cootmundra Rail Br - FRP Restraint Blocks - Central Pier
I2S-7688-MP-74.CN.S4.62.4.7.2 | Central Pier | I.CN.62.22150 | CON - Sec.4 - Old Cootmundra Rail Br - FRP Bearing Mortar Pads - Central Pier
I2S-7688-MP-74.CN.S4.62.4.7.2 | Central Pier | I.CN.62.19000 | CON - Sec.4 - Old Cootmundra Rail Br - Detailed Earthworks - Central Pier | 2026-02-14 | 2026-02-17
I2S-7688-MP-74.CN.S4.62.4.7.2 | Central Pier | I.CN.62.21560 | CON - Sec.4 - Old Cootmundra Rail Br - FRP Columns - Central Pier | 2026-02-22 | 2026-02-28
I2S-7688-MP-74.CN.S4.62.4.7.2 | Central Pier | I.CN.62.21580 | CON - Sec.4 - Old Cootmundra Rail Br - FRP Headstocks - Central Pier | 2026-03-01 | 2026-03-07
North |  |  |  | 2026-04-11 | 2026-06-14
I2S-7688-MP-74.CN.S4.62.4.7.3 | North | I.CN.62.21620 | CON - Sec.4 - Old Cootmundra Rail Br - FRP Headstock - North Abutment | 2026-04-20 | 2026-04-26
I2S-7688-MP-74.CN.S4.62.4.7.3 | North | I.CN.62.22120 | CON - Sec.4 - Old Cootmundra Rail Br - FRP Restraint Blocks - North Abutment
I2S-7688-MP-74.CN.S4.62.4.7.3 | North | I.CN.62.22140 | CON - Sec.4 - Old Cootmundra Rail Br - FRP - Bearing Mortar Pads - North Abutment
I2S-7688-MP-74.CN.S4.62.4.7.3 | North | I.CN.62.19030 | CON - Sec.4 - Old Cootmundra Rail Br - Mechanically Stabilised Earth Walls (MSE) - North Abutment | 2026-06-09 | 2026-06-14
I2S-7688-MP-74.CN.S4.62.4.7.3 | North | I.CN.62.20030 | CON - Sec.4 - Old Cootmundra Rail Br - S&I Column Extension Sleeves & Pour Pile Extension - North Abutment | 2026-04-11 | 2026-04-12
I2S-7688-MP-74.CN.S4.62.4.7.3 | North | I.CN.62.20040 | CON - Sec.4 - Old Cootmundra Rail Br - Detailed Earthworks - North Abutment | 2026-04-13 | 2026-04-15
I2S-7688-MP-74.CN.S4.62.4.7.3 | North | I.CN.62.20080 | CON - Sec.4 - Old Cootmundra Rail Br - FRP Cill Beam - North Abutment | 2026-04-30 | 2026-05-05
I2S-7688-MP-74.CN.S4.62.4.7.3 | North | I.CN.62.20100 | CON - Sec.4 - Old Cootmundra Rail Br - FRP Back Wall - North Abutment | 2026-05-12 | 2026-05-17
Superstructure |  |  |  | 2026-07-01 | 2026-08-04
I2S-7688-MP-74.CN.S4.62.4.4 | Superstructure | I.CN.62.19150 | CON - Sec.4 - Old Cootmundra Rail Br - Crane pads for lift | 2026-07-01 | 2026-07-02
I2S-7688-MP-74.CN.S4.62.4.4 | Superstructure | I.CN.62.19160 | CON - Sec.4 - Old Cootmundra Rail Br - Install bridge bearings | 2026-07-03 | 2026-07-04
I2S-7688-MP-74.CN.S4.62.4.4 | Superstructure | I.CN.62.19200 | CON - Sec.4 - Old Cootmundra Rail Br - Install/Lift Bridge span - 1015 SUPER-T (2ff x 2 spans - T 4) | 2026-07-06 | 2026-07-09
I2S-7688-MP-74.CN.S4.62.4.4 | Superstructure | I.CN.62.19120 | CON - Sec.4 - Old Cootmundra Rail Br - Install handrail raking/horizontal | 2026-07-29 | 2026-08-01
I2S-7688-MP-74.CN.S4.62.4.4 | Superstructure | I.CN.62.19130 | CON - Sec.4 - Old Cootmundra Rail Br - Install access walkways | 2026-08-02 | 2026-08-04
I2S-7688-MP-74.CN.S4.62.4.4 | Superstructure | I.CN.62.22790 | CON - Sec.4 - Old Cootmundra Rail Br - Delivery / QA of Super-T Bridge Span
Approach Slab / Deck |  |  |  | 2026-06-16 | 2026-07-16
I2S-7688-MP-74.CN.S4.62.4.3 | Approach Slab / Deck | I.CN.62.22160 | CON - Sec.4 - Old Cootmundra Rail Br - FRP Cross Girders
I2S-7688-MP-74.CN.S4.62.4.3 | Approach Slab / Deck | I.CN.62.22170 | CON - Sec.4 - Old Cootmundra Rail Br - FRP Deck
I2S-7688-MP-74.CN.S4.62.4.3 | Approach Slab / Deck | I.CN.62.19020 | CON - Sec.4 - Old Cootmundra Rail Br - FRP Approach Slab North Abutment | 2026-06-24 | 2026-06-30
I2S-7688-MP-74.CN.S4.62.4.3 | Approach Slab / Deck | I.CN.62.19080 | CON - Sec.4 - Old Cootmundra Rail Br - Install Handrails MSE Earth Walls | 2026-06-21 | 2026-06-23
I2S-7688-MP-74.CN.S4.62.4.3 | Approach Slab / Deck | I.CN.62.19210 | CON - Sec.4 - Old Cootmundra Rail Br - FRP Derailment kerb | 2026-07-10 | 2026-07-16
I2S-7688-MP-74.CN.S4.62.4.3 | Approach Slab / Deck | I.CN.62.20120 | CON - Sec.4 - Old Cootmundra Rail Br - FRP Approach Slab - South Abutment | 2026-07-01 | 2026-07-07
I2S-7688-MP-74.CN.S4.62.4.3 | Approach Slab / Deck | I.CN.62.20130 | CON - Sec.4 - Old Cootmundra Rail Br - FRP Wing Walls - North side 2 No | 2026-06-16 | 2026-06-21
I2S-7688-MP-74.CN.S4.62.4.3 | Approach Slab / Deck | I.CN.62.20140 | CON - Sec.4 - Old Cootmundra Rail Br - FRP Wing Walls - South side 2 No | 2026-06-22 | 2026-06-28
Finishing Works |  |  |  | 2026-07-17 | 2026-08-04
I2S-7688-MP-74.CN.S4.62.4.5 | Finishing Works | I.CN.62.22180 | CON - Sec.4 - Old Cootmundra Rail Br - Install CSR Ducting
I2S-7688-MP-74.CN.S4.62.4.5 | Finishing Works | I.CN.62.19110 | CON - Sec.4 - Old Cootmundra Rail Br - Install bridge barriers | 2026-07-26 | 2026-07-28
I2S-7688-MP-74.CN.S4.62.4.5 | Finishing Works | I.CN.62.19140 | CON - Sec.4 - Old Cootmundra Rail Br - FRP Footpath/Steps | 2026-07-26 | 2026-08-01
I2S-7688-MP-74.CN.S4.62.4.5 | Finishing Works | I.CN.62.19240 | CON - Sec.4 - Old Cootmundra Rail Br - Batter Slopes & Install "Nylex Cordrain" fixed to vertical face of ballast | 2026-07-17 | 2026-07-24
I2S-7688-MP-74.CN.S4.62.4.5 | Finishing Works | I.CN.62.19320 | CON - Sec.4 - Old Cootmundra Rail Br - Completion |  | 2026-08-04
I2S-7688-MP-74.CN.S4.62.4.5 | Finishing Works | I.CN.62.22800 | CON - Sec.4 - Old Cootmundra Rail Br - Install Scour Protection
I2S-7688-MP-74.CN.S4.62.4.5 | Finishing Works | I.CN.62.22810 | CON - Sec.4 - Old Cootmundra Rail Br - Install Handrails
Isobel Creek Tribitary Bridge- BR706 - 1500 SUPER-T (ARTC) |  |  |  | 2025-11-29 | 2026-07-03
Preliminaries |  |  |  | 2025-11-29 | 2025-12-10
I2S-7688-MP-74.CN.S4.62.3.1 | Preliminaries | I.CN.62.18410 | CON - Sec.4 - Isobel Ck Trib Br - Bridge site prep /Temp Fence/Road Barriers | 2025-11-29 | 2025-12-03
I2S-7688-MP-74.CN.S4.62.3.1 | Preliminaries | I.CN.62.18420 | CON - Sec.4 - Isobel Ck Trib Br - Construct site access | 2025-12-04 | 2025-12-06
I2S-7688-MP-74.CN.S4.62.3.1 | Preliminaries | I.CN.62.18510 | CON - Sec.4 - Isobel Ck Trib Br - Construct laydown area /Causeway (inc pipes) | 2025-12-07 | 2025-12-10
Piling |  |  |  | 2025-12-11 | 2026-03-02
Platforms |  |  |  | 2025-12-11 | 2026-01-14
I2S-7688-MP-74.CN.S4.62.3.2.1 | Platforms | I.CN.62.18470 | CON - Sec.4 - Isobel Ck Trib Br - Excavate platform for piling pad | 2025-12-11 | 2025-12-19
I2S-7688-MP-74.CN.S4.62.3.2.1 | Platforms | I.CN.62.18520 | CON - Sec.4 - Isobel Ck Trib Br - FRP - Pad Footings 2 | 2026-01-13 | 2026-01-14
I2S-7688-MP-74.CN.S4.62.3.2.1 | Platforms | I.CN.62.18430 | CON - Sec.4 - Isobel Ck Trib Br - FRP - Pad Footings 1 | 2025-12-20 | 2026-01-12
Drill Piles |  |  |  | 2026-02-16 | 2026-02-21
I2S-7688-MP-74.CN.S4.62.3.2.3 | Drill Piles | I.CN.62.18480 | CON - Sec.4 - Isobel Ck Trib Br - Demobilise piling rig | 2026-02-21 | 2026-02-21
I2S-7688-MP-74.CN.S4.62.3.2.3 | Drill Piles | I.CN.62.18530 | CON - Sec.4 - Isobel Ck Trib Br - Mobilise piling rig | 2026-02-16 | 2026-02-16
I2S-7688-MP-74.CN.S4.62.3.2.3 | Drill Piles | I.CN.62.18540 | CON - Sec.4 - Isobel Ck Trib Br - abutment piling consists of 4 x 1200mm dia bored concrete piles | 2026-02-17 | 2026-02-20
I2S-7688-MP-74.CN.S4.62.3.2.3 | Drill Piles | I.CN.62.23040 | CON - Sec.4 - Isobel Ck Trib Br - abutment piling consists of 4 x 1200mm dia bored concrete piles - Milestone
Piles Concrete |  |  |  | 2026-02-22 | 2026-03-02
I2S-7688-MP-74.CN.S4.62.3.2.4 | Piles Concrete | I.CN.62.18490 | CON - Sec.4 - Isobel Ck Trib Br - Place pile concrete | 2026-02-22 | 2026-03-02
Piers |  |  |  | 2026-03-03 | 2026-04-13
I2S-7688-MP-74.CN.S4.62.3.3 | Piers | I.CN.62.18570 | CON - Sec.4 - Isobel Ck Trib Br - Detailed Earthworks | 2026-03-03 | 2026-03-06
I2S-7688-MP-74.CN.S4.62.3.3 | Piers | I.CN.62.21930 | CON - Sec.4 - Isobel Ck Trib Br - FRP - Column | 2026-03-19 | 2026-03-24
I2S-7688-MP-74.CN.S4.62.3.3 | Piers | I.CN.62.21940 | CON - Sec.4 - Isobel Ck Trib Br - FRP - Bearing Mortar Pads | 2026-04-01 | 2026-04-07
I2S-7688-MP-74.CN.S4.62.3.3 | Piers | I.CN.62.21950 | CON - Sec.4 - Isobel Ck Trib Br - FRP - Headstock | 2026-03-26 | 2026-03-31
I2S-7688-MP-74.CN.S4.62.3.3 | Piers | I.CN.62.21960 | CON - Sec.4 - Isobel Ck Trib Br - FRP - Restraint Block | 2026-04-08 | 2026-04-13
Abutments |  |  |  | 2026-03-19 | 2026-05-07
Set Up |  |  |  | 2026-03-19 | 2026-03-20
I2S-7688-MP-74.CN.S4.62.3.7.1 | Set Up | I.CN.62.18630 | CON - Sec.4 - Isobel Ck Trib Br - Site prep Abutment Footings / Blinding | 2026-03-19 | 2026-03-20
North |  |  |  | 2026-03-21 | 2026-04-28
I2S-7688-MP-74.CN.S4.62.3.7.2 | North | I.CN.62.18660 | CON - Sec.4 - Isobel Ck Trib Br - FRP - Back Wall - North Abutment | 2026-04-26 | 2026-04-28
I2S-7688-MP-74.CN.S4.62.3.7.2 | North | I.CN.62.20150 | CON - Sec.4 - Isobel Ck Trib Br - Detailed Earthworks - North Abutment | 2026-03-21 | 2026-03-23
I2S-7688-MP-74.CN.S4.62.3.7.2 | North | I.CN.62.20170 | CON - Sec.4 - Isobel Ck Trib Br - FRP - Cill Beam - North Abutment | 2026-03-24 | 2026-03-27
I2S-7688-MP-74.CN.S4.62.3.7.2 | North | I.CN.62.20210 | CON - Sec.4 - Isobel Ck Trib Br - FRP - Restraint Blocks - North Abutment | 2026-04-14 | 2026-04-19
I2S-7688-MP-74.CN.S4.62.3.7.2 | North | I.CN.62.20220 | CON - Sec.4 - Isobel Ck Trib Br - FRP - Wing Walls - North Abutment | 2026-04-20 | 2026-04-22
I2S-7688-MP-74.CN.S4.62.3.7.2 | North | I.CN.62.22700 | CON - Sec.4 - Isobel Ck Trib Br - FRP - Bearing Mortar Pads - North Abutment
South |  |  |  | 2026-03-24 | 2026-05-07
I2S-7688-MP-74.CN.S4.62.3.7.3 | South | I.CN.62.20160 | CON - Sec.4 - Isobel Ck Trib Br - Detailed Earthworks - South Abutment | 2026-03-24 | 2026-03-27
I2S-7688-MP-74.CN.S4.62.3.7.3 | South | I.CN.62.20230 | CON - Sec.4 - Isobel Ck Trib Br - FRP - Wing Walls - South Abutment | 2026-04-29 | 2026-05-01
I2S-7688-MP-74.CN.S4.62.3.7.3 | South | I.CN.62.22710 | CON - Sec.4 - Isobel Ck Trib Br - FRP - Bearing Mortar Pads - South Abutment
I2S-7688-MP-74.CN.S4.62.3.7.3 | South | I.CN.62.18600 | CON - Sec.4 - Isobel Ck Trib Br - FRP - Back Wall - South Abutment | 2026-05-02 | 2026-05-07
I2S-7688-MP-74.CN.S4.62.3.7.3 | South | I.CN.62.18640 | CON - Sec.4 - Isobel Ck Trib Br - FRP - Cill Beam - South Abutment | 2026-03-28 | 2026-03-30
I2S-7688-MP-74.CN.S4.62.3.7.3 | South | I.CN.62.18650 | CON - Sec.4 - Isobel Ck Trib Br - FRP - Restraint Blocks - South Abutment | 2026-04-20 | 2026-04-26
Superstructure |  |  |  | 2026-02-17 | 2026-06-30
I2S-7688-MP-74.CN.S4.62.3.4 | Superstructure | I.CN.62.18740 | CON - Sec.4 - Isobel Ck Trib Br - Install bridge bearings, [length] x [breadth] x [depth] | 2026-05-04 | 2026-05-06
I2S-7688-MP-74.CN.S4.62.3.4 | Superstructure | I.CN.62.18700 | CON - Sec.4 - Isobel Ck Trib Br - Install handrail raking/horizontal | 2026-06-24 | 2026-06-27
I2S-7688-MP-74.CN.S4.62.3.4 | Superstructure | I.CN.62.18710 | CON - Sec.4 - Isobel Ck Trib Br - Install access walkways | 2026-06-28 | 2026-06-30
I2S-7688-MP-74.CN.S4.62.3.4 | Superstructure | I.CN.62.18440 | CON - Sec.4 - Isobel Ck Trib Br - Delivery /QA of super T girders, 23 metres long x6 (3 spans) | 2026-02-17 | 2026-02-18
I2S-7688-MP-74.CN.S4.62.3.4 | Superstructure | I.CN.62.18730 | CON - Sec.4 - Isobel Ck Trib Br - Crane pads for lift | 2026-05-02 | 2026-05-03
I2S-7688-MP-74.CN.S4.62.3.4 | Superstructure | I.CN.62.18750 | CON - Sec.4 - Isobel Ck Trib Br - Install/Lift of super T girders, 23 metres long x6 (3 spans) | 2026-05-26 | 2026-05-29
Approach Slab / Deck |  |  |  | 2026-04-29 | 2026-06-23
I2S-7688-MP-74.CN.S4.62.3.6 | Approach Slab / Deck | I.CN.62.20240 | CON - Sec.4 - Isobel Ck Trib Br - Bridge Deck (inc scaffold) - 72m3 | 2026-05-30 | 2026-06-11
I2S-7688-MP-74.CN.S4.62.3.6 | Approach Slab / Deck | I.CN.62.20180 | CON - Sec.4 - Isobel Ck Trib Br - Approach Slab - North | 2026-06-12 | 2026-06-16
I2S-7688-MP-74.CN.S4.62.3.6 | Approach Slab / Deck | I.CN.62.20190 | CON - Sec.4 - Isobel Ck Trib Br - Approach Slab - South | 2026-06-17 | 2026-06-20
I2S-7688-MP-74.CN.S4.62.3.6 | Approach Slab / Deck | I.CN.62.20250 | CON - Sec.4 - Isobel Ck Trib Br - Wing Walls - North | 2026-04-29 | 2026-05-02
I2S-7688-MP-74.CN.S4.62.3.6 | Approach Slab / Deck | I.CN.62.20260 | CON - Sec.4 - Isobel Ck Trib Br - Wing Walls - South | 2026-05-21 | 2026-05-24
I2S-7688-MP-74.CN.S4.62.3.6 | Approach Slab / Deck | I.CN.62.21650 | CON - Sec.4 - Isobel Ck Trib Br - FRP - Derailment kerb | 2026-06-21 | 2026-06-23
Finishing Works |  |  |  | 2026-06-12 | 2026-07-03
I2S-7688-MP-74.CN.S4.62.3.5 | Finishing Works | I.CN.62.18460 | CON - Sec.4 - Isobel Ck Trib Br - Batter Slopes & Install "Nylex Cordrain" fixed to vertical face of ballast walls | 2026-06-16 | 2026-06-23
I2S-7688-MP-74.CN.S4.62.3.5 | Finishing Works | I.CN.62.18690 | CON - Sec.4 - Isobel Ck Trib Br - Install Handrails | 2026-06-12 | 2026-06-14
I2S-7688-MP-74.CN.S4.62.3.5 | Finishing Works | I.CN.62.18720 | CON - Sec.4 - Isobel Ck Trib Br - FRP Footpath/Steps | 2026-07-01 | 2026-07-03
I2S-7688-MP-74.CN.S4.62.3.5 | Finishing Works | I.CN.62.19330 | CON - Sec.4 - Isobel Ck Trib Br - Completion |  | 2026-07-03
I2S-7688-MP-74.CN.S4.62.3.5 | Finishing Works | I.CN.62.22720 | CON - Sec.4 - Isobel Ck Trib Br - Install Scour Protection
I2S-7688-MP-74.CN.S4.62.3.5 | Finishing Works | I.CN.62.22730 | CON - Sec.4 - Isobel Ck Trib Br - Install CSR Ducting
Isobel Creek Bridge - BR705 - 1500 SUPER-T (ARTC) |  |  |  | 2025-11-19 | 2026-07-08
Preliminaries |  |  |  | 2025-11-19 | 2025-11-28
I2S-7688-MP-74.CN.S4.62.2.1 | Preliminaries | I.CN.62.16310 | CON - Sec.4 - Isobel Ck Br - Bridge site prep /Temp Fence/Road Barriers | 2025-11-19 | 2025-11-21
I2S-7688-MP-74.CN.S4.62.2.1 | Preliminaries | I.CN.62.16320 | CON - Sec.4 - Isobel Ck Br - Construct site access | 2025-11-22 | 2025-11-23
I2S-7688-MP-74.CN.S4.62.2.1 | Preliminaries | I.CN.62.16410 | CON - Sec.4 - Isobel Ck Br - Construct laydown area /Causeway (inc pipes) | 2025-11-24 | 2025-11-28
Piling |  |  |  | 2025-11-29 | 2026-02-17
Platforms |  |  |  | 2025-11-29 | 2025-12-20
I2S-7688-MP-74.CN.S4.62.2.2.1 | Platforms | I.CN.62.16370 | CON - Sec.4 - Isobel Ck Br - Excavate platform for piling pad | 2025-11-29 | 2025-12-04
I2S-7688-MP-74.CN.S4.62.2.2.1 | Platforms | I.CN.62.16420 | CON - Sec.4 - Isobel Ck Br - test platform | 2025-12-19 | 2025-12-20
Drill Piles |  |  |  | 2026-02-09 | 2026-02-14
I2S-7688-MP-74.CN.S4.62.2.2.3 | Drill Piles | I.CN.62.16380 | CON - Sec.4 - Isobel Ck Br - Demobilise piling rig | 2026-02-14 | 2026-02-14
I2S-7688-MP-74.CN.S4.62.2.2.3 | Drill Piles | I.CN.62.16430 | CON - Sec.4 - Isobel Ck Br - Mobilise piling rig | 2026-02-09 | 2026-02-09
I2S-7688-MP-74.CN.S4.62.2.2.3 | Drill Piles | I.CN.62.16440 | CON - Sec.4 - Isobel Creek Bridge - piling consists of 8 x 1200mm dia bored concrete piles | 2026-02-10 | 2026-02-13
I2S-7688-MP-74.CN.S4.62.2.2.3 | Drill Piles | I.CN.62.23050 | CON - Sec.4 - Isobel Creek Bridge - piling consists of 8 x 1200mm dia bored concrete piles - Milestone
Piles Concrete |  |  |  | 2026-02-16 | 2026-02-17
I2S-7688-MP-74.CN.S4.62.2.2.4 | Piles Concrete | I.CN.62.16390 | CON - Sec.4 - Isobel Ck Br - Place pile concrete consists of 8 x 1200mm dia bored concrete piles | 2026-02-16 | 2026-02-17
Piers |  |  |  | 2026-02-18 | 2026-05-18
Pier No 1 |  |  |  | 2026-02-18 | 2026-05-13
I2S-7688-MP-74.CN.S4.62.2.3.1 | Pier No 1 | I.CN.62.19690 | CON - Sec.4 - Isobel Ck Br - Detailed Earthworks - Pier 1 | 2026-02-18 | 2026-02-22
I2S-7688-MP-74.CN.S4.62.2.3.1 | Pier No 1 | I.CN.62.21690 | CON - Sec.4 - Isobel Ck Br - FRP - Column Extensions - Pier 1 | 2026-03-01 | 2026-03-06
I2S-7688-MP-74.CN.S4.62.2.3.1 | Pier No 1 | I.CN.62.21700 | CON - Sec.4 - Isobel Ck Br - FRP - Headstock - Pier 1 | 2026-03-24 | 2026-03-29
I2S-7688-MP-74.CN.S4.62.2.3.1 | Pier No 1 | I.CN.62.21750 | CON - Sec.4 - Isobel Ck Br - FRP - Restraint Block - Pier 1 (1off) - 3m3 | 2026-05-10 | 2026-05-13
Pier No 2 |  |  |  | 2026-03-01 | 2026-05-18
I2S-7688-MP-74.CN.S4.62.2.3.2 | Pier No 2 | I.CN.62.22080 | CON - Sec.4 - Isobel Ck Br - FRP - Headstock - Pier 2
I2S-7688-MP-74.CN.S4.62.2.3.2 | Pier No 2 | I.CN.62.16480 | CON - Sec.4 - Isobel Ck Br - Detailed Earthworks - Pier 2 | 2026-03-01 | 2026-03-06
I2S-7688-MP-74.CN.S4.62.2.3.2 | Pier No 2 | I.CN.62.16510 | CON - Sec.4 - Isobel Ck Br - FRP - Column Extensions - Pier 2 | 2026-03-18 | 2026-03-23
I2S-7688-MP-74.CN.S4.62.2.3.2 | Pier No 2 | I.CN.62.21760 | CON - Sec.4 - Isobel Ck Br - FRP - Restraint Block - Pier 2 (1off) - 3m3 | 2026-05-14 | 2026-05-18
Abutments |  |  |  | 2026-03-24 | 2026-05-09
Site Prep |  |  |  | 2026-03-24 | 2026-03-26
I2S-7688-MP-74.CN.S4.62.2.7.8 | Site Prep | I.CN.62.16520 | CON - Sec.4 - Isobel Ck Br - Site prep Abutment Footings /blinding | 2026-03-24 | 2026-03-26
South |  |  |  | 2026-03-28 | 2026-05-05
I2S-7688-MP-74.CN.S4.62.2.7.1 | South | I.CN.62.22090 | CON - Sec.4 - Isobel Ck Br - FRP - Restraint Block - South Abutment
I2S-7688-MP-74.CN.S4.62.2.7.1 | South | I.CN.62.20270 | CON - Sec.4 - Isobel Ck Br - Detailed Earthworks - South Abutment (1off) | 2026-03-28 | 2026-04-01
I2S-7688-MP-74.CN.S4.62.2.7.1 | South | I.CN.62.20280 | CON - Sec.4 - Isobel Ck Br - Cill Beam - South Abutment - 7m3 | 2026-04-02 | 2026-04-06
I2S-7688-MP-74.CN.S4.62.2.7.1 | South | I.CN.62.20330 | CON - Sec.4 - Isobel Ck Br - Keeper Walls - South Abutment - 2m3 | 2026-04-26 | 2026-04-30
I2S-7688-MP-74.CN.S4.62.2.7.1 | South | I.CN.62.20340 | CON - Sec.4 - Isobel Ck Br - Back Wall - South Abutment - 4m3 | 2026-05-01 | 2026-05-05
North |  |  |  | 2026-03-27 | 2026-05-09
I2S-7688-MP-74.CN.S4.62.2.7.2 | North | I.CN.62.21740 | CON - Sec.4 - Isobel Ck Br - FRP - Restraint Block - North Abutment | 2026-05-06 | 2026-05-09
I2S-7688-MP-74.CN.S4.62.2.7.2 | North | I.CN.62.16530 | CON - Sec.4 - Isobel Ck Br - Detailed Earthworks North Abutment (1off) | 2026-03-27 | 2026-03-31
I2S-7688-MP-74.CN.S4.62.2.7.2 | North | I.CN.62.16540 | CON - Sec.4 - Isobel Ck Br - Cill Beam - North Abutment - 7m3 | 2026-04-04 | 2026-04-08
I2S-7688-MP-74.CN.S4.62.2.7.2 | North | I.CN.62.20310 | CON - Sec.4 - Isobel Ck Br - Keeper Walls - North Abutment - 2m3 | 2026-04-15 | 2026-04-19
I2S-7688-MP-74.CN.S4.62.2.7.2 | North | I.CN.62.20320 | CON - Sec.4 - Isobel Ck Br - Back Wall North Abutment - 4m3 | 2026-04-20 | 2026-04-24
Superstructure |  |  |  | 2026-02-10 | 2026-06-28
I2S-7688-MP-74.CN.S4.62.2.4 | Superstructure | I.CN.62.16630 | CON - Sec.4 - Isobel Ck Br - Crane pads for lift | 2026-05-06 | 2026-05-06
I2S-7688-MP-74.CN.S4.62.2.4 | Superstructure | I.CN.62.16640 | CON - Sec.4 - Isobel Ck Br - Install bridge bearings | 2026-05-07 | 2026-05-08
I2S-7688-MP-74.CN.S4.62.2.4 | Superstructure | I.CN.62.19550 | CON - Sec.4 - Isobel Ck Br - Delivery /QA of super T girders, 23 metres long x6 (3 spans) | 2026-02-10 | 2026-02-11
I2S-7688-MP-74.CN.S4.62.2.4 | Superstructure | I.CN.62.19560 | CON - Sec.4 - Isobel Ck Br - Install/Lift of super T girders, 26 metres long x 6 (3 spans) | 2026-05-16 | 2026-05-18
I2S-7688-MP-74.CN.S4.62.2.4 | Superstructure | I.CN.62.16600 | CON - Sec.4 - Isobel Ck Br - Install handrail raking/horizontal | 2026-06-21 | 2026-06-23
I2S-7688-MP-74.CN.S4.62.2.4 | Superstructure | I.CN.62.16610 | CON - Sec.4 - Isobel Ck Br - Install access walkways | 2026-06-24 | 2026-06-28
Approach Slab / Deck |  |  |  | 2026-05-06 | 2026-06-17
I2S-7688-MP-74.CN.S4.62.2.6 | Approach Slab / Deck | I.CN.62.20440 | CON - Sec.4 - Isobel Ck Br - FRP Wing Walls - North side 2 No | 2026-06-07 | 2026-06-11
I2S-7688-MP-74.CN.S4.62.2.6 | Approach Slab / Deck | I.CN.62.20450 | CON - Sec.4 - Isobel Ck Br - FRP Wing Walls - South side 2 No | 2026-06-12 | 2026-06-17
I2S-7688-MP-74.CN.S4.62.2.6 | Approach Slab / Deck | I.CN.62.21720 | CON - Sec.4 - Isobel Ck Br - FRP pedestals | 2026-05-06 | 2026-05-10
I2S-7688-MP-74.CN.S4.62.2.6 | Approach Slab / Deck | I.CN.62.21730 | CON - Sec.4 - Isobel Ck Br - FRP Cross Girder | 2026-05-11 | 2026-05-16
I2S-7688-MP-74.CN.S4.62.2.6 | Approach Slab / Deck | I.CN.62.21770 | CON - Sec.4 - Isobel Ck Br - FRP Derailment kerb | 2026-06-12 | 2026-06-17
I2S-7688-MP-74.CN.S4.62.2.6 | Approach Slab / Deck | I.CN.62.20400 | CON - Sec.4 - Isobel Ck Br - FRP Bridge Deck | 2026-05-19 | 2026-05-31
I2S-7688-MP-74.CN.S4.62.2.6 | Approach Slab / Deck | I.CN.62.20410 | CON - Sec.4 - Isobel Ck Br - FRP Approach Slab North | 2026-06-01 | 2026-06-06
I2S-7688-MP-74.CN.S4.62.2.6 | Approach Slab / Deck | I.CN.62.20420 | CON - Sec.4 - Isobel Ck Br - FRP Approach Slab South | 2026-06-07 | 2026-06-11
Finishing Works |  |  |  | 2026-06-01 | 2026-07-08
I2S-7688-MP-74.CN.S4.62.2.5 | Finishing Works | I.CN.62.22100 | CON - Sec.4 - Isobel Ck Br - Scour Protection
I2S-7688-MP-74.CN.S4.62.2.5 | Finishing Works | I.CN.62.16590 | CON - Sec.4 - Isobel Ck Br - Install bridge barriers | 2026-06-01 | 2026-06-03
I2S-7688-MP-74.CN.S4.62.2.5 | Finishing Works | I.CN.62.16620 | CON - Sec.4 - Isobel Ck Br - FRP Footpath/Steps | 2026-06-29 | 2026-07-08
I2S-7688-MP-74.CN.S4.62.2.5 | Finishing Works | I.CN.62.19340 | CON - Sec.4 - Isobel Ck Br - Completion |  | 2026-07-08
I2S-7688-MP-74.CN.S4.62.2.5 | Finishing Works | I.CN.62.16360 | CON - Sec.4 - Isobel Ck Br - Batter Slopes & Install "Nylex Cordrain" fixed to vertical face of ballast walls | 2026-06-04 | 2026-06-12
I2S-7688-MP-74.CN.S4.62.2.5 | Finishing Works | I.CN.62.16550 | CON - Sec.4 - Isobel Ck Br - Precast Concrete Parapet Panels | 2026-06-12 | 2026-06-17
I2S-7688-MP-74.CN.S4.62.2.5 | Finishing Works | I.CN.62.22820 | CON - Sec.4 - Isobel Ck Br - Install CSR Ducting
I2S-7688-MP-74.CN.S4.62.2.5 | Finishing Works | I.CN.62.22830 | CON - Sec.4 - Isobel Ck Br - Install Handrails
065 - Crossings |  |  |  | 2025-12-09 | 2026-11-10
Fauna Crossing |  |  |  | 2026-11-03 | 2026-11-10
I2S-7688-MP-74.CN.S4.65.6 | Fauna Crossing | I.CN.65.12860 | CON - Sec.4 - Install fauna crossing, [2 x poles foundations /cure - CH20150] | 2026-11-06 | 2026-11-07
I2S-7688-MP-74.CN.S4.65.6 | Fauna Crossing | I.CN.65.12870 | CON - Sec.4 - Install fauna crossing, [2 x poles foundations /cure - CH18500] | 2026-11-03 | 2026-11-04
I2S-7688-MP-74.CN.S4.65.6 | Fauna Crossing | I.CN.65.12930 | CON - Sec.4 - Install fauna crossing, [2 x poles foundations /cure - CH26300] | 2026-11-08 | 2026-11-09
I2S-7688-MP-74.CN.S4.65.6 | Fauna Crossing | I.CN.65.17880 | CON - Sec.4 - Install fauna crossing, [2 x poles with rope bridge - CH20150] | 2026-11-08 | 2026-11-08
I2S-7688-MP-74.CN.S4.65.6 | Fauna Crossing | I.CN.65.17870 | CON - Sec.4 - Install fauna crossing, [2 x poles with rope bridge - CH18500] | 2026-11-06 | 2026-11-06
I2S-7688-MP-74.CN.S4.65.6 | Fauna Crossing | I.CN.65.17890 | CON - Sec.4 - Install fauna crossing, [2 x poles with rope bridge - CH26300] | 2026-11-10 | 2026-11-10
Private LX - Ryals (PR24500) - Passive / Private - RX-2 |  |  |  | 2025-12-23 | 2026-05-21
Earthworks/Drainage
Culvert ID : E7-RD-442700-1 / Type : 2*900mm HDPE / Ch25213 (21.44m each)
I2S-7688-MP-74.CN.S4.65.4.5.21 | Culvert ID : E7-RD-442700-1 / Type : 2*900mm HDPE / Ch25213 (21.44m each) | I.CN.34.29170 | CON - Sec.4 - Culvert :E7-RD-442700-1 - Headwall installation
I2S-7688-MP-74.CN.S4.65.4.5.21 | Culvert ID : E7-RD-442700-1 / Type : 2*900mm HDPE / Ch25213 (21.44m each) | I.CN.34.29180 | CON - Sec.4 - Culvert :E7-RD-442700-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S4.65.4.5.21 | Culvert ID : E7-RD-442700-1 / Type : 2*900mm HDPE / Ch25213 (21.44m each) | I.CN.34.29190 | CON - Sec.4 - Culvert :E7-RD-442700-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S4.65.4.5.21 | Culvert ID : E7-RD-442700-1 / Type : 2*900mm HDPE / Ch25213 (21.44m each) | I.CN.34.29200 | CON - Sec.4 - Culvert :E7-RD-442700-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S4.65.4.5.21 | Culvert ID : E7-RD-442700-1 / Type : 2*900mm HDPE / Ch25213 (21.44m each) | I.CN.34.29220 | CON - Sec.4 - Culvert :E7-RD-442700-1 - Construct Scour Protection
I2S-7688-MP-74.CN.S4.65.4.5.21 | Culvert ID : E7-RD-442700-1 / Type : 2*900mm HDPE / Ch25213 (21.44m each) | I.CN.34.29150 | CON - Sec.4 - Culvert :E7-RD-442700-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S4.65.4.5.21 | Culvert ID : E7-RD-442700-1 / Type : 2*900mm HDPE / Ch25213 (21.44m each) | I.CN.34.29160 | CON - Sec.4 - Culvert :E7-RD-442700-1 - Struc fill (150mm) / Bedding (150mm) Placement
Culvert ID : E7-RD-442755-1 / Type : 1*450mm RCP 4 / Ch25246 (17.08m each)
I2S-7688-MP-74.CN.S4.65.4.5.19 | Culvert ID : E7-RD-442755-1 / Type : 1*450mm RCP 4 / Ch25246 (17.08m each) | I.CN.34.30040 | CON - Sec.4 - Culvert : E7-RD-442755-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S4.65.4.5.19 | Culvert ID : E7-RD-442755-1 / Type : 1*450mm RCP 4 / Ch25246 (17.08m each) | I.CN.34.30060 | CON - Sec.4 - Culvert : E7-RD-442755-1 - HDPE / RCP pipe lay & backfill
I2S-7688-MP-74.CN.S4.65.4.5.19 | Culvert ID : E7-RD-442755-1 / Type : 1*450mm RCP 4 / Ch25246 (17.08m each) | I.CN.34.30070 | CON - Sec.4 - Culvert : E7-RD-442755-1 - Headwall stitch pour
I2S-7688-MP-74.CN.S4.65.4.5.19 | Culvert ID : E7-RD-442755-1 / Type : 1*450mm RCP 4 / Ch25246 (17.08m each) | I.CN.34.30080 | CON - Sec.4 - Culvert : E7-RD-442755-1 - Headwall cut-off wall installation (FRP)
I2S-7688-MP-74.CN.S4.65.4.5.19 | Culvert ID : E7-RD-442755-1 / Type : 1*450mm RCP 4 / Ch25246 (17.08m each) | I.CN.34.30100 | CON - Sec.4 - Culvert : E7-RD-442755-1 - Construct Scour protection
I2S-7688-MP-74.CN.S4.65.4.5.19 | Culvert ID : E7-RD-442755-1 / Type : 1*450mm RCP 4 / Ch25246 (17.08m each) | I.CN.34.30110 | CON - Sec.4 - Culvert : E7-RD-442755-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S4.65.4.5.19 | Culvert ID : E7-RD-442755-1 / Type : 1*450mm RCP 4 / Ch25246 (17.08m each) | I.CN.34.32000 | CON - Sec.4 - Culvert : E7-RD-442755-1 - Headwall installation
Civils |  |  |  | 2025-12-23 | 2025-12-23
I2S-7688-MP-74.CN.S4.65.4.1 | Civils | I.CN.11.14190 | CON - Sec.4 - Sec.4 - Private LX - Ryals (PR24500) - Clear and Grub | 2025-12-23 | 2025-12-23
Roadworks |  |  |  | 2026-01-05 | 2026-05-18
I2S-7688-MP-74.CN.S4.65.4.6 | Roadworks | I.CN.65.14690 | CON - Sec.4 - Sec.4 - Private LX - Ryals (PR24500) - Civil Works complete |  | 2026-01-07
I2S-7688-MP-74.CN.S4.65.4.6 | Roadworks | I.CN.65.14620 | CON - Sec.4 - Sec.4 - Private LX - Ryals (PR24500) - Earthworks | 2026-01-05 | 2026-01-06
I2S-7688-MP-74.CN.S4.65.4.6 | Roadworks | I.CN.65.14630 | CON - Sec.4 - Sec.4 - Private LX - Ryals (PR24500) - Pavement type A Unsealed (305m2) | 2026-05-13 | 2026-05-14
I2S-7688-MP-74.CN.S4.65.4.6 | Roadworks | I.CN.65.14710 | CON - Sec.4 - Sec.4 - Private LX - Ryals (PR24500) - Batter face area (810 m3) | 2026-05-16 | 2026-05-17
I2S-7688-MP-74.CN.S4.65.4.6 | Roadworks | I.CN.65.14720 | CON - Sec.4 - Sec.4 - Private LX - Ryals (PR24500) - Prime & Cure - Pavement type B sealed (205m2) | 2026-05-16 | 2026-05-16
I2S-7688-MP-74.CN.S4.65.4.6 | Roadworks | I.CN.65.14730 | CON - Sec.4 - Sec.4 - Private LX - Ryals (PR24500) - Seal /linemarking | 2026-05-18 | 2026-05-18
Trackworks |  |  |  | 2026-01-08 | 2026-01-10
I2S-7688-MP-74.CN.S4.65.4.7 | Trackworks | I.CN.65.14660 | CON - Sec.4 - Private LX - Ryals (PR24500) - Tie-in works to foundation block | 2026-01-10 | 2026-01-10
I2S-7688-MP-74.CN.S4.65.4.7 | Trackworks | I.CN.65.14640 | CON - Sec.4 - Private LX - Ryals (PR24500) - Place Foundation Block and T-Kerbstone | 2026-01-08 | 2026-01-08
I2S-7688-MP-74.CN.S4.65.4.7 | Trackworks | I.CN.65.14650 | CON - Sec.4 - Private LX - Ryals (PR24500) - Place and compact ballast between foundation block (after road | 2026-01-09 | 2026-01-09
Ancillary |  |  |  | 2026-05-19 | 2026-05-21
I2S-7688-MP-74.CN.S4.65.4.8 | Ancillary | I.CN.65.14670 | CON - Sec.4 - Private LX - Ryals (PR24500) - Install Fencing | 2026-05-19 | 2026-05-19
I2S-7688-MP-74.CN.S4.65.4.8 | Ancillary | I.CN.65.14680 | CON - Sec.4 - Private LX - Ryals (PR24500) - Install Signage | 2026-05-20 | 2026-05-20
I2S-7688-MP-74.CN.S4.65.4.8 | Ancillary | I.CN.65.14700 | CON - Sec.4 - Private LX - Ryals (PR24500) - Install Gates | 2026-05-21 | 2026-05-21
Commissioning |  |  |  | 2026-05-21 | 2026-05-21
I2S-7688-MP-74.CN.S4.65.4.4 | Commissioning | I.CN.65.14760 | CON - Sec.4 - Sec.4 - Private LX - Ryals (PR24500) - Open |  | 2026-05-21
Private LX - Lagoon Creek Nominees (PR22750) - Passive / Private - RX-2 |  |  |  | 2026-05-07 | 2026-05-26
Civils |  |  |  | 2026-05-07 | 2026-05-19
I2S-7688-MP-74.CN.S4.65.3.1 | Civils | I.CN.11.14180 | CON - Sec.4 - Private LX - Lagoon Creek Nominees (PR22750) - Clear and Grub | 2026-05-07 | 2026-05-07
I2S-7688-MP-74.CN.S4.65.3.1 | Civils | I.CN.65.14510 | CON - Sec.4 - Private LX - Lagoon Creek Nominees (PR22750) - Civil Works complete |  | 2026-05-19
Earthworks/Drainage
Culvert ID : E7-RD-439950-1 / Type : 2*1200x600mm RCBC / Ch22430 (14.40m each)
I2S-7688-MP-74.CN.S4.65.3.5.17 | Culvert ID : E7-RD-439950-1 / Type : 2*1200x600mm RCBC / Ch22430 (14.40m each) | I.CN.34.28580 | CON - Sec.4 - Culvert : E7-RD-439950-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S4.65.3.5.17 | Culvert ID : E7-RD-439950-1 / Type : 2*1200x600mm RCBC / Ch22430 (14.40m each) | I.CN.34.28590 | CON - Sec.4 - Culvert : E7-RD-439950-1 - Struc fill Placement (250mm)
I2S-7688-MP-74.CN.S4.65.3.5.17 | Culvert ID : E7-RD-439950-1 / Type : 2*1200x600mm RCBC / Ch22430 (14.40m each) | I.CN.34.28600 | CON - Sec.4 - Culvert : E7-RD-439950-1 - Place RCBC crown units
I2S-7688-MP-74.CN.S4.65.3.5.17 | Culvert ID : E7-RD-439950-1 / Type : 2*1200x600mm RCBC / Ch22430 (14.40m each) | I.CN.34.28610 | CON - Sec.4 - Culvert : E7-RD-439950-1 - Place Pre-cast Wingwalls and Stich Pour
I2S-7688-MP-74.CN.S4.65.3.5.17 | Culvert ID : E7-RD-439950-1 / Type : 2*1200x600mm RCBC / Ch22430 (14.40m each) | I.CN.34.28620 | CON - Sec.4 - Culvert : E7-RD-439950-1 - Pre-cast RCBC completion (Seal joints)
I2S-7688-MP-74.CN.S4.65.3.5.17 | Culvert ID : E7-RD-439950-1 / Type : 2*1200x600mm RCBC / Ch22430 (14.40m each) | I.CN.34.28630 | CON - Sec.4 - Culvert : E7-RD-439950-1 - Detail backfill
I2S-7688-MP-74.CN.S4.65.3.5.17 | Culvert ID : E7-RD-439950-1 / Type : 2*1200x600mm RCBC / Ch22430 (14.40m each) | I.CN.34.28640 | CON - Sec.4 - Culvert : E7-RD-439950-1 - Construct Scour protection
I2S-7688-MP-74.CN.S4.65.3.5.17 | Culvert ID : E7-RD-439950-1 / Type : 2*1200x600mm RCBC / Ch22430 (14.40m each) | I.CN.34.28650 | CON - Sec.4 - Culvert : E7-RD-439950-1 - Blinding placement (50mm)
I2S-7688-MP-74.CN.S4.65.3.5.17 | Culvert ID : E7-RD-439950-1 / Type : 2*1200x600mm RCBC / Ch22430 (14.40m each) | I.CN.34.28660 | CON - Sec.4 - Culvert : E7-RD-439950-1 - 7 day Curing
I2S-7688-MP-74.CN.S4.65.3.5.17 | Culvert ID : E7-RD-439950-1 / Type : 2*1200x600mm RCBC / Ch22430 (14.40m each) | I.CN.34.32030 | CON - Sec.4 - Culvert : E7-RD-439950-1 - FRP Base Slab / Apron Slab / Cut-off Wall
Culvert ID : E7-RD-439941-1 / Type : 6*1200x450mm RCBC / Ch22421 (16.80m each)
I2S-7688-MP-74.CN.S4.65.3.5.18 | Culvert ID : E7-RD-439941-1 / Type : 6*1200x450mm RCBC / Ch22421 (16.80m each) | I.CN.34.32020 | CON - Sec.4 - Culvert : E7-RD-439941-1 - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.CN.S4.65.3.5.18 | Culvert ID : E7-RD-439941-1 / Type : 6*1200x450mm RCBC / Ch22421 (16.80m each) | I.CN.34.28690 | CON - Sec.4 - Culvert : E7-RD-439941-1 - Place RCBC crown units
I2S-7688-MP-74.CN.S4.65.3.5.18 | Culvert ID : E7-RD-439941-1 / Type : 6*1200x450mm RCBC / Ch22421 (16.80m each) | I.CN.34.28700 | CON - Sec.4 - Culvert : E7-RD-439941-1 - Place Pre-cast Wingwalls and Stich Pour
I2S-7688-MP-74.CN.S4.65.3.5.18 | Culvert ID : E7-RD-439941-1 / Type : 6*1200x450mm RCBC / Ch22421 (16.80m each) | I.CN.34.28710 | CON - Sec.4 - Culvert : E7-RD-439941-1 - Pre-cast RCBC completion (Seal joints)
I2S-7688-MP-74.CN.S4.65.3.5.18 | Culvert ID : E7-RD-439941-1 / Type : 6*1200x450mm RCBC / Ch22421 (16.80m each) | I.CN.34.28720 | CON - Sec.4 - Culvert : E7-RD-439941-1 - Detail backfill
I2S-7688-MP-74.CN.S4.65.3.5.18 | Culvert ID : E7-RD-439941-1 / Type : 6*1200x450mm RCBC / Ch22421 (16.80m each) | I.CN.34.28730 | CON - Sec.4 - Culvert : E7-RD-439941-1 - Construct Scour protection
I2S-7688-MP-74.CN.S4.65.3.5.18 | Culvert ID : E7-RD-439941-1 / Type : 6*1200x450mm RCBC / Ch22421 (16.80m each) | I.CN.34.28740 | CON - Sec.4 - Culvert : E7-RD-439941-1 - Blinding placement (50mm)
I2S-7688-MP-74.CN.S4.65.3.5.18 | Culvert ID : E7-RD-439941-1 / Type : 6*1200x450mm RCBC / Ch22421 (16.80m each) | I.CN.34.28750 | CON - Sec.4 - Culvert : E7-RD-439941-1 - 7 day Curing
I2S-7688-MP-74.CN.S4.65.3.5.18 | Culvert ID : E7-RD-439941-1 / Type : 6*1200x450mm RCBC / Ch22421 (16.80m each) | I.CN.34.28670 | CON - Sec.4 - Culvert : E7-RD-439941-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S4.65.3.5.18 | Culvert ID : E7-RD-439941-1 / Type : 6*1200x450mm RCBC / Ch22421 (16.80m each) | I.CN.34.28680 | CON - Sec.4 - Culvert : E7-RD-439941-1 - Struc fill Placement (250mm)
Roadworks |  |  |  | 2026-05-08 | 2026-05-12
I2S-7688-MP-74.CN.S4.65.3.6 | Roadworks | I.CN.65.14450 | CON - Sec.4 - Private LX - Lagoon Creek Nominees (PR22750) - Pavement type A Unsealed (25m2) | 2026-05-10 | 2026-05-10
I2S-7688-MP-74.CN.S4.65.3.6 | Roadworks | I.CN.65.14530 | CON - Sec.4 - Private LX - Lagoon Creek Nominees (PR22750) - Batter face area (216 m3) | 2026-05-11 | 2026-05-11
I2S-7688-MP-74.CN.S4.65.3.6 | Roadworks | I.CN.65.14540 | CON - Sec.4 - Private LX - Lagoon Creek Nominees (PR22750) - Prime & Cure - Pavement type B sealed (245m2) | 2026-05-11 | 2026-05-11
I2S-7688-MP-74.CN.S4.65.3.6 | Roadworks | I.CN.65.14550 | CON - Sec.4 - Private LX - Lagoon Creek Nominees (PR22750) - Seal /linemarking | 2026-05-12 | 2026-05-12
I2S-7688-MP-74.CN.S4.65.3.6 | Roadworks | I.CN.65.14440 | CON - Sec.4 - Private LX - Lagoon Creek Nominees (PR22750) - Earthworks | 2026-05-08 | 2026-05-09
Trackworks |  |  |  | 2026-05-20 | 2026-05-22
I2S-7688-MP-74.CN.S4.65.3.7 | Trackworks | I.CN.65.14460 | CON - Sec.4 - Private LX - Lagoon Creek Nominees (PR22750) - Place Foundation Block and T-Kerbstone | 2026-05-20 | 2026-05-20
I2S-7688-MP-74.CN.S4.65.3.7 | Trackworks | I.CN.65.14470 | CON - Sec.4 - Private LX - Lagoon Creek Nominees (PR22750) - Place and compact ballast between foundation block (af | 2026-05-21 | 2026-05-21
I2S-7688-MP-74.CN.S4.65.3.7 | Trackworks | I.CN.65.14480 | CON - Sec.4 - Private LX - Lagoon Creek Nominees (PR22750) - Tie-in works to foundation block | 2026-05-22 | 2026-05-22
Ancillary |  |  |  | 2026-05-23 | 2026-05-26
I2S-7688-MP-74.CN.S4.65.3.8 | Ancillary | I.CN.65.14490 | CON - Sec.4 - Private LX - Lagoon Creek Nominees (PR22750) - Install Fencing | 2026-05-23 | 2026-05-23
I2S-7688-MP-74.CN.S4.65.3.8 | Ancillary | I.CN.65.14500 | CON - Sec.4 - Private LX - Lagoon Creek Nominees (PR22750) - Install Signage | 2026-05-24 | 2026-05-24
I2S-7688-MP-74.CN.S4.65.3.8 | Ancillary | I.CN.65.14520 | CON - Sec.4 - Private LX - Lagoon Creek Nominees (PR22750) - Install Gates | 2026-05-26 | 2026-05-26
Commissioning |  |  |  | 2026-05-26 | 2026-05-26
I2S-7688-MP-74.CN.S4.65.3.4 | Commissioning | I.CN.65.14580 | CON - Sec.4 - Private LX - Lagoon Creek Nominees (PR22750) - Open |  | 2026-05-26
Private LX - Friend (Chris) (PR21200) - Passive / Private - RX-2 |  |  |  | 2026-05-02 | 2026-05-12
Civils |  |  |  | 2026-05-02 | 2026-05-06
I2S-7688-MP-74.CN.S4.65.2.1 | Civils | I.CN.11.14170 | CON - Sec.4 - Private LX - Friend (Chris) (PR21200) - Clear and Grub | 2026-05-02 | 2026-05-02
I2S-7688-MP-74.CN.S4.65.2.1 | Civils | I.CN.65.14330 | CON - Sec.4 - Private LX - Friend (Chris) (PR21200)- Civil Works complete |  | 2026-05-06
Earthworks/Drainage
Culvert ID : E7-RD-438730-1 / Type : 3*600mm HPDE / Ch21214 (16.15m each)
I2S-7688-MP-74.CN.S4.65.2.5.20 | Culvert ID : E7-RD-438730-1 / Type : 3*600mm HPDE / Ch21214 (16.15m each) | I.CN.34.28850 | CON - Sec.4 - Culvert : E7-RD-438730-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S4.65.2.5.20 | Culvert ID : E7-RD-438730-1 / Type : 3*600mm HPDE / Ch21214 (16.15m each) | I.CN.34.28860 | CON - Sec.4 - Culvert : E7-RD-438730-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S4.65.2.5.20 | Culvert ID : E7-RD-438730-1 / Type : 3*600mm HPDE / Ch21214 (16.15m each) | I.CN.34.28870 | CON - Sec.4 - Culvert : E7-RD-438730-1 - Headwall installation
I2S-7688-MP-74.CN.S4.65.2.5.20 | Culvert ID : E7-RD-438730-1 / Type : 3*600mm HPDE / Ch21214 (16.15m each) | I.CN.34.28880 | CON - Sec.4 - Culvert : E7-RD-438730-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S4.65.2.5.20 | Culvert ID : E7-RD-438730-1 / Type : 3*600mm HPDE / Ch21214 (16.15m each) | I.CN.34.28900 | CON - Sec.4 - Culvert : E7-RD-438730-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S4.65.2.5.20 | Culvert ID : E7-RD-438730-1 / Type : 3*600mm HPDE / Ch21214 (16.15m each) | I.CN.34.28910 | CON - Sec.4 - Culvert : E7-RD-438730-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S4.65.2.5.20 | Culvert ID : E7-RD-438730-1 / Type : 3*600mm HPDE / Ch21214 (16.15m each) | I.CN.34.28930 | CON - Sec.4 - Culvert : E7-RD-438730-1 - Construct Scour Protection
Roadworks |  |  |  | 2026-05-03 | 2026-05-07
I2S-7688-MP-74.CN.S4.65.2.6 | Roadworks | I.CN.65.14370 | CON - Sec.4 - Private LX - Friend (Chris) (PR21200) - Seal /linemarking | 2026-05-07 | 2026-05-07
I2S-7688-MP-74.CN.S4.65.2.6 | Roadworks | I.CN.65.14260 | CON - Sec.4 - Private LX - Friend (Chris) (PR21200) - Earthworks | 2026-05-03 | 2026-05-04
I2S-7688-MP-74.CN.S4.65.2.6 | Roadworks | I.CN.65.14270 | CON - Sec.4 - Private LX - Friend (Chris) (PR21200) - Pavement type A Unsealed (240m2) | 2026-05-05 | 2026-05-05
I2S-7688-MP-74.CN.S4.65.2.6 | Roadworks | I.CN.65.14350 | CON - Sec.4 - Private LX - Friend (Chris) (PR21200) - Batter face area (840 m3) | 2026-05-06 | 2026-05-06
I2S-7688-MP-74.CN.S4.65.2.6 | Roadworks | I.CN.65.14360 | CON - Sec.4 - Private LX - Friend (Chris) (PR21200) - Prime & Cure - Pavement type B sealed (210 m2) | 2026-05-06 | 2026-05-06
Trackworks |  |  |  | 2026-05-07 | 2026-05-09
I2S-7688-MP-74.CN.S4.65.2.7 | Trackworks | I.CN.65.14290 | CON - Sec.4 - Private LX - Friend (Chris) (PR21200) - Place and compact ballast between foundation block (after roa | 2026-05-08 | 2026-05-08
I2S-7688-MP-74.CN.S4.65.2.7 | Trackworks | I.CN.65.14300 | CON - Sec.4 - Private LX - Friend (Chris) (PR21200) - Tie-in works to foundation block | 2026-05-09 | 2026-05-09
I2S-7688-MP-74.CN.S4.65.2.7 | Trackworks | I.CN.65.14280 | CON - Sec.4 - Private LX - Friend (Chris) (PR21200) - Place Foundation Block and T-Kerbstone | 2026-05-07 | 2026-05-07
Ancillary |  |  |  | 2026-05-10 | 2026-05-12
I2S-7688-MP-74.CN.S4.65.2.8 | Ancillary | I.CN.65.14310 | CON - Sec.4 - Private LX - Friend (Chris) (PR21200) - Install Fencing | 2026-05-10 | 2026-05-10
I2S-7688-MP-74.CN.S4.65.2.8 | Ancillary | I.CN.65.14320 | CON - Sec.4 - Private LX - Friend (Chris) (PR21200) - Install Signage | 2026-05-11 | 2026-05-11
I2S-7688-MP-74.CN.S4.65.2.8 | Ancillary | I.CN.65.14340 | CON - Sec.4 - Private LX - Friend (Chris) (PR21200) - Install Gates | 2026-05-12 | 2026-05-12
Commissioning |  |  |  | 2026-05-12 | 2026-05-12
I2S-7688-MP-74.CN.S4.65.2.4 | Commissioning | I.CN.65.14400 | CON - Sec.4 - Private LX - Friend (Chris) (PR21200) - Open |  | 2026-05-12
Private LX - Friend (Ian) (PR19800) - Passive / Private - RX-2 |  |  |  | 2025-12-09 | 2026-06-08
Civils |  |  |  | 2026-05-13 | 2026-06-01
I2S-7688-MP-74.CN.S4.65.1.1 | Civils | I.CN.11.14160 | CON - Sec.4 - Private LX - Friend (Ian) (PR19800) - Clear and Grub | 2026-05-13 | 2026-05-13
I2S-7688-MP-74.CN.S4.65.1.1 | Civils | I.CN.65.14150 | CON - Sec.4 - Private LX - Friend (Ian) (PR19800) - Civil Works complete |  | 2026-06-01
Earthworks/Drainage |  |  |  | 2025-12-09 | 2025-12-22
Culvert ID : E7-RD-437360-1 / Type : 3*600mm HDPE / Ch19840 (15.24m each)
I2S-7688-MP-74.CN.S4.65.1.5.19 | Culvert ID : E7-RD-437360-1 / Type : 3*600mm HDPE / Ch19840 (15.24m each) | I.CN.34.28760 | CON - Sec.4 - Culvert : E7-RD-437360-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S4.65.1.5.19 | Culvert ID : E7-RD-437360-1 / Type : 3*600mm HDPE / Ch19840 (15.24m each) | I.CN.34.28770 | CON - Sec.4 - Culvert : E7-RD-437360-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S4.65.1.5.19 | Culvert ID : E7-RD-437360-1 / Type : 3*600mm HDPE / Ch19840 (15.24m each) | I.CN.34.28780 | CON - Sec.4 - Culvert : E7-RD-437360-1 - Headwall installation
I2S-7688-MP-74.CN.S4.65.1.5.19 | Culvert ID : E7-RD-437360-1 / Type : 3*600mm HDPE / Ch19840 (15.24m each) | I.CN.34.28790 | CON - Sec.4 - Culvert : E7-RD-437360-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S4.65.1.5.19 | Culvert ID : E7-RD-437360-1 / Type : 3*600mm HDPE / Ch19840 (15.24m each) | I.CN.34.28800 | CON - Sec.4 - Culvert : E7-RD-437360-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S4.65.1.5.19 | Culvert ID : E7-RD-437360-1 / Type : 3*600mm HDPE / Ch19840 (15.24m each) | I.CN.34.28810 | CON - Sec.4 - Culvert : E7-RD-437360-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S4.65.1.5.19 | Culvert ID : E7-RD-437360-1 / Type : 3*600mm HDPE / Ch19840 (15.24m each) | I.CN.34.28830 | CON - Sec.4 - Culvert : E7-RD-437360-1 - Construct Scour Protection
Culvert ID : E7-RD-437359-1 / Type : 2*900mm HDPE / Ch19836 (24.28m each) |  |  |  | 2025-12-09 | 2025-12-22
I2S-7688-MP-74.CN.S4.65.1.5.13 | Culvert ID : E7-RD-437359-1 / Type : 2*900mm HDPE / Ch19836 (24.28m each) | I.CN.34.21570 | CON - Sec.4 - Culvert : E7-RD-437359-1 - Headwall Stitch Pour | 2025-12-14 | 2025-12-16
I2S-7688-MP-74.CN.S4.65.1.5.13 | Culvert ID : E7-RD-437359-1 / Type : 2*900mm HDPE / Ch19836 (24.28m each) | I.CN.34.21590 | CON - Sec.4 - Culvert : E7-RD-437359-1 - Headwall Cut-off Wall Installation (FRP) | 2025-12-17 | 2025-12-18
I2S-7688-MP-74.CN.S4.65.1.5.13 | Culvert ID : E7-RD-437359-1 / Type : 2*900mm HDPE / Ch19836 (24.28m each) | I.CN.34.21620 | CON - Sec.4 - Culvert : E7-RD-437359-1 - Construct Scour Protection | 2025-12-21 | 2025-12-22
I2S-7688-MP-74.CN.S4.65.1.5.13 | Culvert ID : E7-RD-437359-1 / Type : 2*900mm HDPE / Ch19836 (24.28m each) | I.CN.34.27550 | CON - Sec.4 - Culvert : E7-RD-437359-1 - Headwall installation | 2025-12-11 | 2025-12-12
I2S-7688-MP-74.CN.S4.65.1.5.13 | Culvert ID : E7-RD-437359-1 / Type : 2*900mm HDPE / Ch19836 (24.28m each) | I.CN.34.21510 | CON - Sec.4 - Culvert : E7-RD-437359-1 - Site Prep / Detail Excavation | 2025-12-09 | 2025-12-10
I2S-7688-MP-74.CN.S4.65.1.5.13 | Culvert ID : E7-RD-437359-1 / Type : 2*900mm HDPE / Ch19836 (24.28m each) | I.CN.34.21520 | CON - Sec.4 - Culvert : E7-RD-437359-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2025-12-11 | 2025-12-12
I2S-7688-MP-74.CN.S4.65.1.5.13 | Culvert ID : E7-RD-437359-1 / Type : 2*900mm HDPE / Ch19836 (24.28m each) | I.CN.34.21560 | CON - Sec.4 - Culvert : E7-RD-437359-1 - HDPE / RCP Pipe Lay & Backfill | 2025-12-13 | 2025-12-13
Roadworks |  |  |  | 2026-05-14 | 2026-05-22
I2S-7688-MP-74.CN.S4.65.1.6 | Roadworks | I.CN.65.14080 | CON - Sec.4 - Private LX - Friend (Ian) (PR19800) - Earthworks | 2026-05-14 | 2026-05-16
I2S-7688-MP-74.CN.S4.65.1.6 | Roadworks | I.CN.65.14090 | CON - Sec.4 - Private LX - Friend (Ian) (PR19800) - Pavement type A Unsealed (1225m2) | 2026-05-17 | 2026-05-18
I2S-7688-MP-74.CN.S4.65.1.6 | Roadworks | I.CN.65.14170 | CON - Sec.4 - Private LX - Friend (Ian) (PR19800) - Batter face area (2165 m3) | 2026-05-19 | 2026-05-21
I2S-7688-MP-74.CN.S4.65.1.6 | Roadworks | I.CN.65.14180 | CON - Sec.4 - Private LX - Friend (Ian) (PR19800) - Prime & Cure - Pavement type B sealed (305 m2) | 2026-05-19 | 2026-05-19
I2S-7688-MP-74.CN.S4.65.1.6 | Roadworks | I.CN.65.14190 | CON - Sec.4 - Private LX - Friend (Ian) (PR19800) - Seal /linemarking | 2026-05-22 | 2026-05-22
Trackworks |  |  |  | 2026-06-02 | 2026-06-04
I2S-7688-MP-74.CN.S4.65.1.7 | Trackworks | I.CN.65.14100 | CON - Sec.4 - Private LX - Friend (Ian) (PR19800) - Place Foundation Block and T-Kerbstone | 2026-06-02 | 2026-06-02
I2S-7688-MP-74.CN.S4.65.1.7 | Trackworks | I.CN.65.14110 | CON - Sec.4 - Private LX - Friend (Ian) (PR19800) - Place and compact ballast between foundation block (after road | 2026-06-03 | 2026-06-03
I2S-7688-MP-74.CN.S4.65.1.7 | Trackworks | I.CN.65.14120 | CON - Sec.4 - Private LX - Friend (Ian) (PR19800) - Tie-in works to foundation block | 2026-06-04 | 2026-06-04
Ancillary |  |  |  | 2026-06-06 | 2026-06-08
I2S-7688-MP-74.CN.S4.65.1.8 | Ancillary | I.CN.65.14130 | CON - Sec.4 - Private LX - Friend (Ian) (PR19800) - Install Fencing | 2026-06-06 | 2026-06-06
I2S-7688-MP-74.CN.S4.65.1.8 | Ancillary | I.CN.65.14140 | CON - Sec.4 - Private LX - Friend (Ian) (PR19800) - Install Signage | 2026-06-07 | 2026-06-07
I2S-7688-MP-74.CN.S4.65.1.8 | Ancillary | I.CN.65.14160 | CON - Sec.4 - Private LX - Friend (Ian) (PR19800) - Install Gates | 2026-06-08 | 2026-06-08
Commissioning |  |  |  | 2026-06-08 | 2026-06-08
I2S-7688-MP-74.CN.S4.65.1.4 | Commissioning | I.CN.65.14220 | CON - Sec.4 - Private LX - Friend (Ian) (PR19800) - Open |  | 2026-06-08
Stock Crossings |  |  |  | 2026-01-08 | 2026-06-06
Friend (Ian) (SU19900) Culvert ID : E7-SU-437414-1 / Type : 2*3000x3000mm RCBC / Ch19914 (7.2m each) |  |  |  | 2026-06-02 | 2026-06-06
I2S-7688-MP-74.CN.S4.65.5.1 | Friend (Ian) (SU19900) Culvert ID : E7-SU-437414-1 / Type : 2*3000x3000mm RCBC / Ch19914 (7.2m each) | I.CN.65.17830 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-437414-1 - Construct Scour protection | 2026-06-06 | 2026-06-06
I2S-7688-MP-74.CN.S4.65.5.1 | Friend (Ian) (SU19900) Culvert ID : E7-SU-437414-1 / Type : 2*3000x3000mm RCBC / Ch19914 (7.2m each) | I.CN.65.18440 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-437414-1 - Struc fill Placement (250mm)
I2S-7688-MP-74.CN.S4.65.5.1 | Friend (Ian) (SU19900) Culvert ID : E7-SU-437414-1 / Type : 2*3000x3000mm RCBC / Ch19914 (7.2m each) | I.CN.65.18630 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-437414-1 - 7 day Curing
I2S-7688-MP-74.CN.S4.65.5.1 | Friend (Ian) (SU19900) Culvert ID : E7-SU-437414-1 / Type : 2*3000x3000mm RCBC / Ch19914 (7.2m each) | I.CN.65.18640 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-437414-1 - Detail backfill
I2S-7688-MP-74.CN.S4.65.5.1 | Friend (Ian) (SU19900) Culvert ID : E7-SU-437414-1 / Type : 2*3000x3000mm RCBC / Ch19914 (7.2m each) | I.CN.65.16360 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-437414-1 - Site Prep / Detail Excavation | 2026-06-02 | 2026-06-03
I2S-7688-MP-74.CN.S4.65.5.1 | Friend (Ian) (SU19900) Culvert ID : E7-SU-437414-1 / Type : 2*3000x3000mm RCBC / Ch19914 (7.2m each) | I.CN.65.17820 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-437414-1 - Place RCBC crown units | 2026-06-04 | 2026-06-04
I2S-7688-MP-74.CN.S4.65.5.1 | Friend (Ian) (SU19900) Culvert ID : E7-SU-437414-1 / Type : 2*3000x3000mm RCBC / Ch19914 (7.2m each) | I.CN.65.19211 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-437414-1 - Blinding placement (50mm)
I2S-7688-MP-74.CN.S4.65.5.1 | Friend (Ian) (SU19900) Culvert ID : E7-SU-437414-1 / Type : 2*3000x3000mm RCBC / Ch19914 (7.2m each) | I.CN.65.19221 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-437414-1 - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.CN.S4.65.5.1 | Friend (Ian) (SU19900) Culvert ID : E7-SU-437414-1 / Type : 2*3000x3000mm RCBC / Ch19914 (7.2m each) | I.CN.65.19231 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-437414-1 - Place Pre-cast Wingwalls and Stich Pour
I2S-7688-MP-74.CN.S4.65.5.1 | Friend (Ian) (SU19900) Culvert ID : E7-SU-437414-1 / Type : 2*3000x3000mm RCBC / Ch19914 (7.2m each) | I.CN.65.19241 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-437414-1 - Pre-cast RCBC completion (Seal joints)
I2S-7688-MP-74.CN.S4.65.5.1 | Friend (Ian) (SU19900) Culvert ID : E7-SU-437414-1 / Type : 2*3000x3000mm RCBC / Ch19914 (7.2m each) | I.CN.65.20001 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-437414-1 - FRP Base Slab / Apron Slab / Cut-off Wall - Milestone
Friend (Chris) (SU21670) Culvert ID : E7-SU-439180-1 / Type : 1*3000x3000mm RCBC / Ch21679 (14.4m) |  |  |  | 2026-05-07 | 2026-05-09
I2S-7688-MP-74.CN.S4.65.5.5 | Friend (Chris) (SU21670) Culvert ID : E7-SU-439180-1 / Type : 1*3000x3000mm RCBC / Ch21679 (14.4m) | I.CN.65.18200 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-439180-1 - Backfill and Scour Protection | 2026-05-09 | 2026-05-09
I2S-7688-MP-74.CN.S4.65.5.5 | Friend (Chris) (SU21670) Culvert ID : E7-SU-439180-1 / Type : 1*3000x3000mm RCBC / Ch21679 (14.4m) | I.CN.65.18650 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-439180-1 - Struc fill Placement (250mm)
I2S-7688-MP-74.CN.S4.65.5.5 | Friend (Chris) (SU21670) Culvert ID : E7-SU-439180-1 / Type : 1*3000x3000mm RCBC / Ch21679 (14.4m) | I.CN.65.18660 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-439180-1 - 7 day Curing
I2S-7688-MP-74.CN.S4.65.5.5 | Friend (Chris) (SU21670) Culvert ID : E7-SU-439180-1 / Type : 1*3000x3000mm RCBC / Ch21679 (14.4m) | I.CN.65.18670 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-439180-1 - Place Pre-cast Wingwalls and Stich Pour
I2S-7688-MP-74.CN.S4.65.5.5 | Friend (Chris) (SU21670) Culvert ID : E7-SU-439180-1 / Type : 1*3000x3000mm RCBC / Ch21679 (14.4m) | I.CN.65.19321 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-439180-1 - Blinding placement (50mm)
I2S-7688-MP-74.CN.S4.65.5.5 | Friend (Chris) (SU21670) Culvert ID : E7-SU-439180-1 / Type : 1*3000x3000mm RCBC / Ch21679 (14.4m) | I.CN.65.19331 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-439180-1 - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.CN.S4.65.5.5 | Friend (Chris) (SU21670) Culvert ID : E7-SU-439180-1 / Type : 1*3000x3000mm RCBC / Ch21679 (14.4m) | I.CN.65.19341 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-439180-1 - Pre-cast RCBC completion (Seal joints)
I2S-7688-MP-74.CN.S4.65.5.5 | Friend (Chris) (SU21670) Culvert ID : E7-SU-439180-1 / Type : 1*3000x3000mm RCBC / Ch21679 (14.4m) | I.CN.65.19351 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-439180-1 - Detail backfill
I2S-7688-MP-74.CN.S4.65.5.5 | Friend (Chris) (SU21670) Culvert ID : E7-SU-439180-1 / Type : 1*3000x3000mm RCBC / Ch21679 (14.4m) | I.CN.65.18180 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-439180-1 - Site Prep / Detail Excavation | 2026-05-07 | 2026-05-07
I2S-7688-MP-74.CN.S4.65.5.5 | Friend (Chris) (SU21670) Culvert ID : E7-SU-439180-1 / Type : 1*3000x3000mm RCBC / Ch21679 (14.4m) | I.CN.65.18190 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-439180-1 - Place RCBC crown units | 2026-05-08 | 2026-05-08
Ryals (SU23400) Culvert ID : E7-SU-440914-1 / Type : 1*3000x3000mm RCBC / Ch23414 (9.6m) |  |  |  | 2026-05-20 | 2026-05-22
I2S-7688-MP-74.CN.S4.65.5.2 | Ryals (SU23400) Culvert ID : E7-SU-440914-1 / Type : 1*3000x3000mm RCBC / Ch23414 (9.6m) | I.CN.65.17800 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-440914-1 - Place RCBC crown units | 2026-05-21 | 2026-05-21
I2S-7688-MP-74.CN.S4.65.5.2 | Ryals (SU23400) Culvert ID : E7-SU-440914-1 / Type : 1*3000x3000mm RCBC / Ch23414 (9.6m) | I.CN.65.17810 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-440914-1 - Backfill and Scour Protection | 2026-05-22 | 2026-05-22
I2S-7688-MP-74.CN.S4.65.5.2 | Ryals (SU23400) Culvert ID : E7-SU-440914-1 / Type : 1*3000x3000mm RCBC / Ch23414 (9.6m) | I.CN.65.18680 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-440914-1 - Struc fill Placement (250mm)
I2S-7688-MP-74.CN.S4.65.5.2 | Ryals (SU23400) Culvert ID : E7-SU-440914-1 / Type : 1*3000x3000mm RCBC / Ch23414 (9.6m) | I.CN.65.18690 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-440914-1 - 7 day Curing
I2S-7688-MP-74.CN.S4.65.5.2 | Ryals (SU23400) Culvert ID : E7-SU-440914-1 / Type : 1*3000x3000mm RCBC / Ch23414 (9.6m) | I.CN.65.18700 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-440914-1 - Detail backfill
I2S-7688-MP-74.CN.S4.65.5.2 | Ryals (SU23400) Culvert ID : E7-SU-440914-1 / Type : 1*3000x3000mm RCBC / Ch23414 (9.6m) | I.CN.65.19361 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-440914-1 - Blinding placement (50mm)
I2S-7688-MP-74.CN.S4.65.5.2 | Ryals (SU23400) Culvert ID : E7-SU-440914-1 / Type : 1*3000x3000mm RCBC / Ch23414 (9.6m) | I.CN.65.19371 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-440914-1 - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.CN.S4.65.5.2 | Ryals (SU23400) Culvert ID : E7-SU-440914-1 / Type : 1*3000x3000mm RCBC / Ch23414 (9.6m) | I.CN.65.19381 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-440914-1 - Place Pre-cast Wingwalls and Stich Pour
I2S-7688-MP-74.CN.S4.65.5.2 | Ryals (SU23400) Culvert ID : E7-SU-440914-1 / Type : 1*3000x3000mm RCBC / Ch23414 (9.6m) | I.CN.65.19391 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-440914-1 - Pre-cast RCBC completion (Seal joints)
I2S-7688-MP-74.CN.S4.65.5.2 | Ryals (SU23400) Culvert ID : E7-SU-440914-1 / Type : 1*3000x3000mm RCBC / Ch23414 (9.6m) | I.CN.65.16370 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-440914-1 - Site Prep / Detail Excavation | 2026-05-20 | 2026-05-20
Ryals (SU25900) Culvert ID : E7-SU-443400-1 / Type : 1*3000x3000mm RCBC / Ch25899 (16.8m) |  |  |  | 2026-01-08 | 2026-01-11
I2S-7688-MP-74.CN.S4.65.5.3 | Ryals (SU25900) Culvert ID : E7-SU-443400-1 / Type : 1*3000x3000mm RCBC / Ch25899 (16.8m) | I.CN.65.19421 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-443400-1 - Place Pre-cast Wingwalls and Stich Pour
I2S-7688-MP-74.CN.S4.65.5.3 | Ryals (SU25900) Culvert ID : E7-SU-443400-1 / Type : 1*3000x3000mm RCBC / Ch25899 (16.8m) | I.CN.65.19431 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-443400-1 - Pre-cast RCBC completion (Seal joints)
I2S-7688-MP-74.CN.S4.65.5.3 | Ryals (SU25900) Culvert ID : E7-SU-443400-1 / Type : 1*3000x3000mm RCBC / Ch25899 (16.8m) | I.CN.65.17790 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-443400-1 - Backfill and Scour Protection | 2026-01-11 | 2026-01-11
I2S-7688-MP-74.CN.S4.65.5.3 | Ryals (SU25900) Culvert ID : E7-SU-443400-1 / Type : 1*3000x3000mm RCBC / Ch25899 (16.8m) | I.CN.65.16380 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-443400-1 - Site Prep / Detail Excavation | 2026-01-08 | 2026-01-09
I2S-7688-MP-74.CN.S4.65.5.3 | Ryals (SU25900) Culvert ID : E7-SU-443400-1 / Type : 1*3000x3000mm RCBC / Ch25899 (16.8m) | I.CN.65.17780 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-443400-1 - Place RCBC crown units | 2026-01-10 | 2026-01-10
I2S-7688-MP-74.CN.S4.65.5.3 | Ryals (SU25900) Culvert ID : E7-SU-443400-1 / Type : 1*3000x3000mm RCBC / Ch25899 (16.8m) | I.CN.65.18710 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-443400-1 - Struc fill Placement (250mm)
I2S-7688-MP-74.CN.S4.65.5.3 | Ryals (SU25900) Culvert ID : E7-SU-443400-1 / Type : 1*3000x3000mm RCBC / Ch25899 (16.8m) | I.CN.65.18720 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-443400-1 - 7 day Curing
I2S-7688-MP-74.CN.S4.65.5.3 | Ryals (SU25900) Culvert ID : E7-SU-443400-1 / Type : 1*3000x3000mm RCBC / Ch25899 (16.8m) | I.CN.65.18730 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-443400-1 - Detail backfill
I2S-7688-MP-74.CN.S4.65.5.3 | Ryals (SU25900) Culvert ID : E7-SU-443400-1 / Type : 1*3000x3000mm RCBC / Ch25899 (16.8m) | I.CN.65.19401 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-443400-1 - Blinding placement (50mm)
I2S-7688-MP-74.CN.S4.65.5.3 | Ryals (SU25900) Culvert ID : E7-SU-443400-1 / Type : 1*3000x3000mm RCBC / Ch25899 (16.8m) | I.CN.65.19411 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-443400-1 - FRP Base Slab / Apron Slab / Cut-off Wall
Emery(SU26900) Culvert ID : E7-SU-444500-1 / Type : 1*3000x3000mm RCBC / Ch26956 (14.4m) |  |  |  | 2026-01-12 | 2026-01-16
I2S-7688-MP-74.CN.S4.65.5.4 | Emery(SU26900) Culvert ID : E7-SU-444500-1 / Type : 1*3000x3000mm RCBC / Ch26956 (14.4m) | I.CN.65.16390 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-444500-1 - Site Prep / Detail Excavation | 2026-01-12 | 2026-01-13
I2S-7688-MP-74.CN.S4.65.5.4 | Emery(SU26900) Culvert ID : E7-SU-444500-1 / Type : 1*3000x3000mm RCBC / Ch26956 (14.4m) | I.CN.65.17760 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-444500-1 - Place RCBC crown units | 2026-01-14 | 2026-01-14
I2S-7688-MP-74.CN.S4.65.5.4 | Emery(SU26900) Culvert ID : E7-SU-444500-1 / Type : 1*3000x3000mm RCBC / Ch26956 (14.4m) | I.CN.65.17770 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-444500-1 - Backfill and Scour Protection | 2026-01-16 | 2026-01-16
I2S-7688-MP-74.CN.S4.65.5.4 | Emery(SU26900) Culvert ID : E7-SU-444500-1 / Type : 1*3000x3000mm RCBC / Ch26956 (14.4m) | I.CN.65.18740 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-444500-1 - Struc fill Placement (250mm)
I2S-7688-MP-74.CN.S4.65.5.4 | Emery(SU26900) Culvert ID : E7-SU-444500-1 / Type : 1*3000x3000mm RCBC / Ch26956 (14.4m) | I.CN.65.18750 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-444500-1 - 7 day Curing
I2S-7688-MP-74.CN.S4.65.5.4 | Emery(SU26900) Culvert ID : E7-SU-444500-1 / Type : 1*3000x3000mm RCBC / Ch26956 (14.4m) | I.CN.65.18760 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-444500-1 - Detail backfill
I2S-7688-MP-74.CN.S4.65.5.4 | Emery(SU26900) Culvert ID : E7-SU-444500-1 / Type : 1*3000x3000mm RCBC / Ch26956 (14.4m) | I.CN.65.19441 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-444500-1 - Blinding placement (50mm)
I2S-7688-MP-74.CN.S4.65.5.4 | Emery(SU26900) Culvert ID : E7-SU-444500-1 / Type : 1*3000x3000mm RCBC / Ch26956 (14.4m) | I.CN.65.19451 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-444500-1 - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.CN.S4.65.5.4 | Emery(SU26900) Culvert ID : E7-SU-444500-1 / Type : 1*3000x3000mm RCBC / Ch26956 (14.4m) | I.CN.65.19461 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-444500-1 - Place Pre-cast Wingwalls and Stich Pour
I2S-7688-MP-74.CN.S4.65.5.4 | Emery(SU26900) Culvert ID : E7-SU-444500-1 / Type : 1*3000x3000mm RCBC / Ch26956 (14.4m) | I.CN.65.19471 | CON - Sec.4 - Stock Xing - Culvert : E7-SU-444500-1 - Pre-cast RCBC completion (Seal joints)
072 - Signalling |  |  |  | 2026-06-06 | 2026-07-26
Cabling |  |  |  | 2026-06-06 | 2026-06-13
I2S-7688-MP-74.CN.S4.72.8 | Cabling | I.CN.74.14430 | CON - Sec.4 - CSR - Main Cable Route - MCR - Pull Cable - 18600 to 28200 | 2026-06-06 | 2026-06-13
Misc Equipment |  |  |  | 2026-07-13 | 2026-07-26
I2S-7688-MP-74.CN.S4.72.12 | Misc Equipment | I.CN.74.14740 | CON - Sec.4 - Sig - Install Track Side Equipment (speed signs/motor generators/notice boards) | 2026-07-13 | 2026-07-26
074 - Power Supply and Distributions |  |  |  | 2026-03-20 | 2026-06-30
CSR |  |  |  | 2026-03-20 | 2026-06-30
MCR |  |  |  | 2026-03-20 | 2026-06-30
I2S-7688-MP-74.CN.S4.74.2.1 | MCR | I.CN.74.14350 | CON - Sec.4 - CSR - Install Main CSR - Up Main 436050 to 437600 (LX) (1550m) | 2026-03-20 | 2026-06-04
I2S-7688-MP-74.CN.S4.74.2.1 | MCR | I.CN.74.15070 | CON - Sec.4 - CSR - Install Main CSR - Up Main 437600 - 437700 Across Isobel Creek Bridge | 2026-06-06 | 2026-06-30
I2S-7688-MP-74.CN.S4.74.2.1 | MCR | I.CN.74.15640 | CON - Sec.4 - CSR - Install Main CSR - Up Main 437700 to 437950 (Isobel Trib) (100m)
I2S-7688-MP-74.CN.S4.74.2.1 | MCR | I.CN.74.15650 | CON - Sec.4 - CSR - Install Main CSR - Up Main 437950 - 438050 Across Isbel Ckreek Underbridge
I2S-7688-MP-74.CN.S4.74.2.1 | MCR | I.CN.74.15660 | CON - Sec.4 - CSR - Install Main CSR - Up Main 442700 (LX) - 445750 (Old Coot) (3050m)
I2S-7688-MP-74.CN.S4.74.2.1 | MCR | I.CN.74.15670 | CON - Sec.4 - CSR - Install Main CSR - Up Main 438050 to 442700 (4650m)
I2S-7688-MP-74.CN.S4.74.2.1 | MCR | I.CN.74.15680 | CON - Sec.4 - CSR - Install Main CSR - Up Main 445750 to 445800 Across Old Coot Underbridge
ULX
I2S-7688-MP-74.CN.S4.74.2.3 | ULX | I.CN.74.15730 | CON - Sec.4 - CSR - Local ULX - Across Track - 437350
I2S-7688-MP-74.CN.S4.74.2.3 | ULX | I.CN.74.15740 | CON - Sec.4 - CSR - Local ULX - Across Track - 438700
I2S-7688-MP-74.CN.S4.74.2.3 | ULX | I.CN.74.15750 | CON - Sec.4 - CSR - Local ULX - Across Track - 439900
I2S-7688-MP-74.CN.S4.74.2.3 | ULX | I.CN.74.15760 | CON - Sec.4 - CSR - Local ULX - Across Track - 442700
085 - Landscaping
I2S-7688-MP-74.CN.S4.85 | 085 - Landscaping | I.CN.85.14010 | CON - Sec.4 - Landscaping - Re-spread Topsoil - Ch18500-28300
I2S-7688-MP-74.CN.S4.85 | 085 - Landscaping | I.CN.85.14020 | CON - Sec.4 - Landscaping - Hydroseed Application - Ch18500-28300
Section 3 - GF section (08841 - 18500) |  |  |  | 2025-07-12 | 2026-09-27
Section 3 Key Milestones
I2S-7688-MP-74.CN.S3.2 | Section 3 Key Milestones | I.CN.22.13930 | CON - Sec.3 - Construction Completion Milestone (Bridges)
I2S-7688-MP-74.CN.S3.2 | Section 3 Key Milestones | I.CN.22.13940 | CON - Sec.3 - Construction Completion Milestone (Crossings)
I2S-7688-MP-74.CN.S3.2 | Section 3 Key Milestones | I.CN.22.13860 | CON - Sec.3 - Construction Completion Milestone (Public Utilities)
I2S-7688-MP-74.CN.S3.2 | Section 3 Key Milestones | I.CN.22.13870 | CON - Sec.3 - Construction Completion Milestone (Earthworks)
I2S-7688-MP-74.CN.S3.2 | Section 3 Key Milestones | I.CN.22.13880 | CON - Sec.3 - Construction Completion Milestone (Rail Capping)
I2S-7688-MP-74.CN.S3.2 | Section 3 Key Milestones | I.CN.22.13890 | CON - Sec.3 - Construction Completion Milestone (Drainage)
I2S-7688-MP-74.CN.S3.2 | Section 3 Key Milestones | I.CN.22.13900 | CON - Sec.3 - Construction Completion Milestone (Fencing)
I2S-7688-MP-74.CN.S3.2 | Section 3 Key Milestones | I.CN.22.13910 | CON - Sec.3 - Construction Completion Milestone (Access Roads)
I2S-7688-MP-74.CN.S3.2 | Section 3 Key Milestones | I.CN.22.13960 | CON - Sec.3 - Construction Completion Milestone (Power Supply and Distributions)
I2S-7688-MP-74.CN.S3.2 | Section 3 Key Milestones | I.CN.22.13970 | CON - Sec.3 - Construction Completion Milestone (Landscaping)
I2S-7688-MP-74.CN.S3.2 | Section 3 Key Milestones | I.CN.22.13980 | CON - Sec.3 - Construction Completion Milestone (Roads)
I2S-7688-MP-74.CN.S3.2 | Section 3 Key Milestones | I.CN.22.13990 | CON - Sec.3 - Construction Completion Milestone (Rail Communications)
I2S-7688-MP-74.CN.S3.2 | Section 3 Key Milestones | I.CN.22.14430 | CON - Sec.3 - Construction Completion Milestone (Culverts)
I2S-7688-MP-74.CN.S3.2 | Section 3 Key Milestones | I.CN.22.13950 | CON - Sec.3 - Construction Completion Milestone (Signalling)
I2S-7688-MP-74.CN.S3.2 | Section 3 Key Milestones | I.CN.22.13920 | CON - Sec.3 - Construction Completion Milestone (Trackwork)
I2S-7688-MP-74.CN.S3.2 | Section 3 Key Milestones | I.CN.22.14800 | CON - Sec.3 - Commence Construction Milestone - FDVR & CEMP approved - 1st A9 submission - approval
I2S-7688-MP-74.CN.S3.2 | Section 3 Key Milestones | I.CN.22.14790 | CON - Sec.3 - Commence Construction Milestone - CEMP approved
Site Access |  |  |  | 2025-07-12 | 2025-07-12
I2S-7688-MP-74.CN.S3.00 | Site Access | I.CN.11.14050 | CON - Sec.3 - Site Gate Access Required by/ Granted - Gate 4A (11400) | 2025-07-12 | 2025-07-12
I2S-7688-MP-74.CN.S3.00 | Site Access | I.CN.11.14110 | CON - Sec.3 - Site Gate Access Required by/ Granted - Gate 5 (18450) | 2025-07-12 | 2025-07-12
022 - Public Utilities |  |  |  | 2025-08-07 | 2025-09-08
ARTC |  |  |  | 2025-08-11 | 2025-09-08
I2S-7688-MP-74.CN.S3.22.1 | ARTC | I.CN.22.5480 | CON - Util - Sec.3 - PUP - IRPL- Rail Power - 8200 - 9380 - Connection for activated LX PU8160 (CH8160) | 2025-08-11 | 2025-08-13
I2S-7688-MP-74.CN.S3.22.1 | ARTC | I.CN.22.13330 | CON - Util - Sec.3 - PUP - IRPL- Rail Power - 9150 - Connection to Turnout CH9147 | 2025-08-14 | 2025-08-19
I2S-7688-MP-74.CN.S3.22.1 | ARTC | I.CN.22.13340 | CON - Util - Sec.3 - PUP - IRPL- Rail Power - 9380 - 11400 - From POS E to LX PU11390 | 2025-08-20 | 2025-08-22
I2S-7688-MP-74.CN.S3.22.1 | ARTC | I.CN.22.13350 | CON - Util - Sec.3 - PUP - IRPL- Rail Power - 10370 - Connection to Turnout CH10367 | 2025-08-26 | 2025-08-28
I2S-7688-MP-74.CN.S3.22.1 | ARTC | I.CN.22.13360 | CON - Util - Sec.3 - PUP - IRPL- Rail Power - 11340 - Connection to Turnout CH11342 | 2025-08-29 | 2025-09-02
I2S-7688-MP-74.CN.S3.22.1 | ARTC | I.CN.22.13370 | CON - Util - Sec.3 - PUP - IRPL- Rail Power - 11380 - Connection to LX PU11390 | 2025-09-03 | 2025-09-08
Telstra |  |  |  | 2025-08-21 | 2025-08-29
I2S-7688-MP-74.CN.S3.22.2 | Telstra | I.CN.22.6400 | CON - Util - Sec.3 - TE02-07 Telstra - Protect East Side Ironbong Road - Ch17922 (175m) | 2025-08-27 | 2025-08-29
I2S-7688-MP-74.CN.S3.22.2 | Telstra | I.CN.22.6440 | CON - Util - Sec.3 - TE02-06 Telstra - Relocation East Side Ironbong Road - Ch15947 (104m) | 2025-08-21 | 2025-08-26
Essential Energy (EE) |  |  |  | 2025-08-07 | 2025-08-08
I2S-7688-MP-74.CN.S3.22.4 | Essential Energy (EE) | I.CN.22.6420 | CON - Util - Sec.3 - ELO-02 - Essential Energy Relocate 11kV East Side Ironbong Road (near Dirnaseer) - Ch9342 (207 | 2025-08-07 | 2025-08-08
I2S-7688-MP-74.CN.S3.22.4 | Essential Energy (EE) | I.CN.22.14270 | CON - Util - Sec.3 - PS-02 - Essential Energy New Signal Equipment Room Power Supply - Ch9242
I2S-7688-MP-74.CN.S3.22.4 | Essential Energy (EE) | I.CN.22.6430 | CON - Util - Sec.3 - ELO-02 & PS-02 - Commence Work on site
I2S-7688-MP-74.CN.S3.22.4 | Essential Energy (EE) | I.CN.22.6450 | CON - Util - Sec.3 - ELO-02 & PS-02 - Outage & Cutover - ECN-109630
I2S-7688-MP-74.CN.S3.22.4 | Essential Energy (EE) | I.CN.22.6460 | CON - Util - Sec.3 - ECN-109630 Works Complete
031 - Earthworks
I2S-7688-MP-74.CN.S3.31 | 031 - Earthworks | I.CN.31.88280 | CON - Sec.3 - Construct Temp Creek Crossing - Run Boundary Creek for traffic
Clearing & Grubbing - Stage 2
Tree Felling and Lopping
I2S-7688-MP-74.CN.S3.31.3.1 | Tree Felling and Lopping | I.CN.11.15580 | CON - Sec.3 - Tree Felling & Lopping
Broad Acre Clearing and Mulching
I2S-7688-MP-74.CN.S3.31.3.2 | Broad Acre Clearing and Mulching | I.CN.11.15590 | CON - Sec.3 - Broad Acre Clearing & Mulching
Grubbing of Stumps
I2S-7688-MP-74.CN.S3.31.3.3 | Grubbing of Stumps | I.CN.11.15600 | CON - Sec.3 - Grubbing of Stumps
Miscellaneous Works
I2S-7688-MP-74.CN.S3.31.3.4 | Miscellaneous Works | I.CN.11.15610 | CON - Sec.3 - Hollow/Habitat Tree Mgmt
I2S-7688-MP-74.CN.S3.31.3.4 | Miscellaneous Works | I.CN.11.15620 | CON - Sec.3 - Habitat Relocations
Cut
Cut Open Drains
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.85860 | CON - Sec.3 - FILL 09 - Cut.OD Soil : Ch7942 to 9282 (3299 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.86000 | CON - Sec.3 - FILL 10 - Cut.OD Soil : Ch9942 to 10302 (712 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.86010 | CON - Sec.3 - FILL 11 - Cut.OD Soil : Ch10902 to 11142 (81 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.86020 | CON - Sec.3 - FILL 13 - Cut.OD Soil : Ch12322 to 12720 (344 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.86030 | CON - Sec.3 - FILL 15 - Cut.OD Soil : Ch13460 to 13840 (214 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.86050 | CON - Sec.3 - FILL 17 - Cut.OD Soil : Ch14534 to 15514 (112 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.86060 | CON - Sec.3 - FILL 18 - Cut.OD Soil : Ch16214 to 16493 (27 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.86070 | CON - Sec.3 - FILL 19 - Cut.OD Soil : Ch16767 to 16934 (148 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.86080 | CON - Sec.3 - FILL 20 - Cut.OD Soil : Ch17313 to 18453 (3351 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.86090 | CON - Sec.3 - FILL 21 - Cut.OD Soil : Ch18474 to 18696 (498 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.81390 | CON - Sec.3 - CUT 09 - Cut.OD Soil : Ch10302 to 10542 (919 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.81480 | CON - Sec.3 - CUT 10 - Cut.OD Soil : Ch10542 to 10902 (283 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.81570 | CON - Sec.3 - CUT 11 - Cut.OD Soil : Ch11142 to 11342 (245 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.81660 | CON - Sec.3 - CUT 12 - Cut.OD Soil : Ch11342 to 12322 (909 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.81750 | CON - Sec.3 - CUT 13 - Cut.OD Soil : Ch12720 to 12980 (456 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.81840 | CON - Sec.3 - CUT 14 - Cut.OD Soil : Ch13220 to 13460 (655 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.81930 | CON - Sec.3 - CUT 15 - Cut.OD Soil : Ch13840 to 14120 (138 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.82020 | CON - Sec.3 - CUT 16 - Cut.OD Soil : Ch15514 to 15934 (5606 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.82110 | CON - Sec.3 - CUT 17 - Cut.OD Soil : Ch15934 to 16214 (979 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.82200 | CON - Sec.3 - CUT 18 - Cut.OD Soil : Ch16493 to 16774 (76 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.82290 | CON - Sec.3 - CUT 08 - Cut.OD Soil : Ch9282 to 9942 (1864 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.82380 | CON - Sec.3 - CUT 19 - Cut.OD Soil : Ch16934 to 17313 (187 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.82470 | CON - Sec.3 - CUT 20 - Cut.OD Soil : Ch18696 to 19017 (323 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.17 | Cut Open Drains | I.CN.31.82560 | CON - Sec.3 - CUT 21 - Cut.OD Soil : Ch19017 to 19116 (312 bcm - 175 per/d)
Cut Soil to EW
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.85870 | CON - Sec.3 - FILL 10 - Cut.Soil to EW : Ch9942 to 10302 (323 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.85880 | CON - Sec.3 - FILL 11 - Cut.Soil to EW : Ch10902 to 11142 (223 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.85890 | CON - Sec.3 - FILL 13 - Cut.Soil to EW : Ch12322 to 12720 (190 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.85900 | CON - Sec.3 - FILL 14 - Cut.Soil to EW : Ch12980 to 13240 (127 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.85910 | CON - Sec.3 - FILL 15 - Cut.Soil to EW : Ch13460 to 13840 (207 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.85920 | CON - Sec.3 - FILL 16 - Cut.Soil to EW : Ch14120 to 14400 (590 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.85930 | CON - Sec.3 - FILL 17 - Cut.Soil to EW : Ch14534 to 15514 (2185 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.85940 | CON - Sec.3 - FILL 18 - Cut.Soil to EW : Ch16214 to 16493 (164 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.85950 | CON - Sec.3 - FILL 19 - Cut.Soil to EW : Ch16767 to 16934 (68 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.85960 | CON - Sec.3 - FILL 20 - Cut.Soil to EW : Ch17313 to 18453 (2117 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.85970 | CON - Sec.3 - FILL 21 - Cut.Soil to EW : Ch18474 to 18696 (190 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.85980 | CON - Sec.3 - FILL 09 - Cut.Soil to EW : Ch7942 to 9282 (906 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.81400 | CON - Sec.3 - CUT 09 - Cut.Soil to EW : Ch10302 to 10542 (8838 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.81490 | CON - Sec.3 - CUT 10 - Cut.Soil to EW : Ch10542 to 10902 (8600 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.81580 | CON - Sec.3 - CUT 11 - Cut.Soil to EW : Ch11142 to 11342 (4436 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.81670 | CON - Sec.3 - CUT 12 - Cut.Soil to EW : Ch11342 to 12322 (36461 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.81760 | CON - Sec.3 - CUT 13 - Cut.Soil to EW : Ch12720 to 12980 (11782 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.81850 | CON - Sec.3 - CUT 14 - Cut.Soil to EW : Ch13220 to 13460 (9855 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.81940 | CON - Sec.3 - CUT 15 - Cut.Soil to EW : Ch13840 to 14120 (7069 bcm - 175 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.82030 | CON - Sec.3 - CUT 16 - Cut.Soil to EW : Ch15514 to 15934 (11828 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.82120 | CON - Sec.3 - CUT 17 - Cut.Soil to EW : Ch15934 to 16214 (4383 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.82210 | CON - Sec.3 - CUT 18 - Cut.Soil to EW : Ch16493 to 16774 (9947 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.82300 | CON - Sec.3 - CUT 08 - Cut.Soil to EW : Ch9282 to 9942 (34643 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.82390 | CON - Sec.3 - CUT 19 - Cut.Soil to EW : Ch16934 to 17313 (15067 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.82480 | CON - Sec.3 - CUT 20 - Cut.Soil to EW : Ch18696 to 19017(28530 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.82570 | CON - Sec.3 - CUT 21 - Cut.Soil to EW : Ch19017 to 19116 (1746 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.13 | Cut Soil to EW | I.CN.31.88330 | CON - Sec.3 - CUT 18 - Cut.Soil to EW : Ch16493 to 16774 (9947 bcm - 2500 per/d) - Milestone
Cut Rock
I2S-7688-MP-74.CN.S3.31.1.3 | Cut Rock | I.CN.31.85990 | CON - Sec.3 - FILL 09 - Cut.HW to MW SS : Ch7942 to 9282 (297bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.3 | Cut Rock | I.CN.31.86040 | CON - Sec.3 - FILL 15 - Cut.HW to MW SS : Ch13460 to 13840 (374 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.3 | Cut Rock | I.CN.31.81590 | CON - Sec.3 - CUT 12 - Cut.HW/MW/SW Dacite : Ch11342 to 12322 (33108 bcm - 2000 per/d)
I2S-7688-MP-74.CN.S3.31.1.3 | Cut Rock | I.CN.31.81730 | CON - Sec.3 - CUT 13 - Cut.MW/SW Dacite : Ch12720 to 12980 (8491 bcm - 2000 per/d)
I2S-7688-MP-74.CN.S3.31.1.3 | Cut Rock | I.CN.31.81820 | CON - Sec.3 - CUT 14 - Cut.MW/SW Dacite : Ch13220 to 13460 (5374 bcm - 2000 per/d)
I2S-7688-MP-74.CN.S3.31.1.3 | Cut Rock | I.CN.31.81910 | CON - Sec.3 - CUT 15 - Cut.HW/MW/SW Dacite : Ch13840 to 14120 (22239 bcm - 2000 per/d)
I2S-7688-MP-74.CN.S3.31.1.3 | Cut Rock | I.CN.31.82000 | CON - Sec.3 - CUT 16 - Cut.HW/MW Dacite : Ch15514 to 15934 (8023 bcm - 2000 per/d)
I2S-7688-MP-74.CN.S3.31.1.3 | Cut Rock | I.CN.31.82090 | CON - Sec.3 - CUT 17 - Cut.HW Dacite : Ch15934 to 16214 (825 bcm - 2000 per/d)
I2S-7688-MP-74.CN.S3.31.1.3 | Cut Rock | I.CN.31.82180 | CON - Sec.3 - CUT 18 - Cut.HW/MW/SW Dacite : Ch16493 to 16774 (12043 bcm - 2000 per/d)
I2S-7688-MP-74.CN.S3.31.1.3 | Cut Rock | I.CN.31.82220 | CON - Sec.3 - CUT 08 - Cut.HW to MW SS : Ch9282 to 9942 (4326 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.1.3 | Cut Rock | I.CN.31.82360 | CON - Sec.3 - CUT19 - Cut.HW/SW Dacite : Ch16934 to 17313 (25173 bcm - 2000 per/d)
I2S-7688-MP-74.CN.S3.31.1.3 | Cut Rock | I.CN.31.82450 | CON - Sec.3 - CUT 20 - Cut.HW/MW/SW Dacite : Ch18696 to 19017 (40994 bcm - 2000 per/d)
Fill
Fill Open Drain
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.87500 | CON - Sec.3 - CUT 20 - Fill.OD Fill : Ch18696 to 19017 (364 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.87540 | CON - Sec.3 - CUT 21 - Fill.OD Fill : Ch19017 to 19116 (46 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.84730 | CON - Sec.3 - FILL 18 - Fill.OD Fill : Ch16214 to 16493 (24 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.84770 | CON - Sec.3 - FILL 19 - Fill.OD Fill : Ch16767 to 16934 (39 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.84810 | CON - Sec.3 - FILL 20 - Fill.OD Fill : Ch17313 to 18453 (160 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.84850 | CON - Sec.3 - FILL 21 - Fill.OD Fill : Ch18474 to 18696 (13 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.84370 | CON - Sec.3 - FILL 09 - Fill.OD Fill : Ch7942 to 9282 (203 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.84410 | CON - Sec.3 - FILL 10 - Fill.OD Fill : Ch9942 to 10302 (734 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.84450 | CON - Sec.3 - FILL 11 - Fill.OD Fill : Ch10902 to 11142 (92 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.84530 | CON - Sec.3 - FILL 13 - Fill.OD Fill : Ch12322 to 12720 (20 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.84570 | CON - Sec.3 - FILL 14 - Fill.OD Fill : Ch12980 to 13240 (146 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.84610 | CON - Sec.3 - FILL 15 - Fill.OD Fill : Ch13460 to 13840 (23 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.87020 | CON - Sec.3 - CUT 08 - Fill.OD Fill : Ch9282 to 9942 (1037 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.87060 | CON - Sec.3 - CUT 10 - Fill.OD Fill : Ch10542 to 10902 (1418 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.87100 | CON - Sec.3 - CUT 09 - Fill.OD Fill : Ch10302 to 10542 (1158 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.87140 | CON - Sec.3 - CUT 14 - Fill.OD Fill : Ch13220 to 13460 (154 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.87180 | CON - Sec.3 - CUT 13 - Fill.OD Fill : Ch12720 to 12980 (228 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.87220 | CON - Sec.3 - CUT 11 - Fill.OD Fill : Ch11142 to 11342 (394 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.87260 | CON - Sec.3 - CUT 12 - Fill.OD Fill : Ch11342 to 12322 (889 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.87300 | CON - Sec.3 - CUT 19 - Fill.OD Fill : Ch16934 to 17313 (563 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.87340 | CON - Sec.3 - CUT 15 - Fill.OD Fill : Ch13840 to 14120 (274 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.87380 | CON - Sec.3 - CUT 16 - Fill.OD Fill : Ch15514 to 15934 (56 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.87420 | CON - Sec.3 - CUT 18 - Fill.OD Fill : Ch16493 to 16774 (257 bcm - 500 per/d)
I2S-7688-MP-74.CN.S3.31.6.1 | Fill Open Drain | I.CN.31.87460 | CON - Sec.3 - CUT 17 - Fill.OD Fill : Ch15934 to 16214 (193 bcm - 500 per/d)
Fill Lower
I2S-7688-MP-74.CN.S3.31.6.3 | Fill Lower | I.CN.31.84720 | CON - Sec.3 - FILL 17 - Fill.H3 - Lower : Ch14534 to 15514 (10780 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.3 | Fill Lower | I.CN.31.84760 | CON - Sec.3 - FILL 18 - Fill.H3 - Lower : Ch16214 to 16493 (13785 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.3 | Fill Lower | I.CN.31.84800 | CON - Sec.3 - FILL 19 - Fill.H3 - Lower : Ch16767 to 16934 (105 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.3 | Fill Lower | I.CN.31.84840 | CON - Sec.3 - FILL 20 - Fill.H3 - Lower : Ch17313 to 18453 (101382 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.3 | Fill Lower | I.CN.31.84880 | CON - Sec.3 - FILL 21 - Fill.H3 - Lower : Ch18474 to 18696 (20669 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.3 | Fill Lower | I.CN.31.84400 | CON - Sec.3 - FILL 09 - Fill.H3 - Lower : Ch7942 to 9282 (70961 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.3 | Fill Lower | I.CN.31.84560 | CON - Sec.3 - FILL 13 - Fill.H3 - Lower : Ch12322 to 12720 (15242 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.3 | Fill Lower | I.CN.31.84600 | CON - Sec.3 - FILL 14 - Fill.H3 - Lower : Ch12980 to 13240 (213 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.3 | Fill Lower | I.CN.31.84640 | CON - Sec.3 - FILL 15 - Fill.H3 - Lower : Ch13460 to 13840 (19342 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.3 | Fill Lower | I.CN.31.84680 | CON - Sec.3 - FILL 16 - Fill.H3 - Lower : Ch14120 to 14400 (8597 bcm - 2500 per/d)
Fill Mid
I2S-7688-MP-74.CN.S3.31.6.4 | Fill Mid | I.CN.31.84710 | CON - Sec.3 - FILL 17 - Fill.H2 - Mid : Ch14534 to 15514 (5243 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.4 | Fill Mid | I.CN.31.84750 | CON - Sec.3 - FILL 18 - Fill.H2 - Mid : Ch16214 to 16493 (1767 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.4 | Fill Mid | I.CN.31.84790 | CON - Sec.3 - FILL 19 - Fill.H2 - Mid : Ch16767 to 16934 (523 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.4 | Fill Mid | I.CN.31.84830 | CON - Sec.3 - FILL 20 - Fill.H2 - Mid : Ch17313 to 18453 (7157 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.4 | Fill Mid | I.CN.31.84870 | CON - Sec.3 - FILL 21 - Fill.H2 - Mid : Ch18474 to 18696 (1290 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.4 | Fill Mid | I.CN.31.84390 | CON - Sec.3 - FILL 09 - Fill.H2 - Mid : Ch7942 to 9282 (8773 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.4 | Fill Mid | I.CN.31.84430 | CON - Sec.3 - FILL 10 - Fill.H2 - Mid : Ch9942 to 10302 (50 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.4 | Fill Mid | I.CN.31.84470 | CON - Sec.3 - FILL 11 - Fill.H2 - Mid : Ch10902 to 11142 (621 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.4 | Fill Mid | I.CN.31.84550 | CON - Sec.3 - FILL 13 - Fill.H2 - Mid : Ch12322 to 12720 (2488 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.4 | Fill Mid | I.CN.31.84590 | CON - Sec.3 - FILL 14 - Fill.H2 - Mid : Ch12980 to 13240 (700 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.4 | Fill Mid | I.CN.31.84630 | CON - Sec.3 - FILL 15 - Fill.H2 - Mid : Ch13460 to 13840 (2275 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.4 | Fill Mid | I.CN.31.84670 | CON - Sec.3 - FILL 16 - Fill.H2 - Mid : Ch14120 to 14400 (1692 bcm - 2500 per/d)
Fill Upper
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.84700 | CON - Sec.3 - FILL 17 - Fill.H1 - Upper : Ch14534 to 15514 (5131 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.84740 | CON - Sec.3 - FILL 18 - Fill.H1 - Upper : Ch16214 to 16493 (1898 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.84780 | CON - Sec.3 - FILL 19 - Fill.H1 - Upper : Ch16767 to 16934 (1268 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.84820 | CON - Sec.3 - FILL 20 - Fill.H1 - Upper : Ch17313 to 18453 (8479 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.84860 | CON - Sec.3 - FILL 21 - Fill.H1 - Upper : Ch18474 to 18696 (2238 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.84380 | CON - Sec.3 - FILL 09 - Fill.H1 - Upper : Ch7942 to 9282(16083 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.84420 | CON - Sec.3 - FILL 10 - Fill.H1 - Upper : Ch9942 to 10302 (1597 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.84460 | CON - Sec.3 - FILL 11 - Fill.H1 - Upper : Ch10902 to 11142 (1586 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.84540 | CON - Sec.3 - FILL 13 - Fill.H1 - Upper : Ch12322 to 12720 (2408 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.84580 | CON - Sec.3 - FILL 14 - Fill.H1 - Upper : Ch12980 to 13240 (1272 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.84620 | CON - Sec.3 - FILL 15 - Fill.H1 - Upper : Ch13460 to 13840 (2285 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.84660 | CON - Sec.3 - FILL 16 - Fill.H1 - Upper : Ch14120 to 14400 (1671 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.87030 | CON - Sec.3 - CUT 08 - Fill.H1 - Upper : Ch9282 to 9942 (364 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.87070 | CON - Sec.3 - CUT 10 - Fill.H1 - Upper : Ch10542 to 10902 (154 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.87110 | CON - Sec.3 - CUT 09 - Fill.H1 - Upper : Ch10302 to 10542 (70 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.87150 | CON - Sec.3 - CUT 14 - Fill.H1 - Upper : Ch13220 to 13460 (18 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.87190 | CON - Sec.3 - CUT 13 - Fill.H1 - Upper : Ch12720 to 12980 (45 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.87230 | CON - Sec.3 - CUT 11 - Fill.H1 - Upper : Ch11142 to 11342 (236 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.87270 | CON - Sec.3 - CUT 12 - Fill.H1 - Upper : Ch11342 to 12322 (87 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.87310 | CON - Sec.3 - CUT 19 - Fill.H1 - Upper : Ch16934 to 17313 (23 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.87350 | CON - Sec.3 - CUT 15 - Fill.H1 - Upper : Ch13840 to 14120 (22 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.87390 | CON - Sec.3 - CUT 16 - Fill.H1 - Upper : Ch15514 to 15934 (162 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.87430 | CON - Sec.3 - CUT 18 - Fill.H1 - Upper : Ch16493 to 16774 (48 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.87470 | CON - Sec.3 - CUT 17 - Fill.H1 - Upper : Ch15934 to 16214 (96 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.87510 | CON - Sec.3 - CUT 20 - Fill.H1 - Upper : Ch18696 to 19017 (169 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S3.31.6.6 | Fill Upper | I.CN.31.87550 | CON - Sec.3 - CUT 21 - Fill.H1 - Upper : Ch19017 to 19116 (62 bcm - 2500 per/d)
033 - Capping |  |  |  | 2026-03-30 | 2026-05-23
Support to u/s Ballast |  |  |  | 2026-03-30 | 2026-05-23
Structural Fill |  |  |  | 2026-03-30 | 2026-04-03
I2S-7688-MP-74.CN.S3.33.3.1 | Structural Fill | I.CN.33.8190 | CON - Sec.3 - Fill Struc fill (61845 TON) 2200 TON/d | 2026-03-30 | 2026-04-03
Capping (Rail) |  |  |  | 2026-03-30 | 2026-03-31
I2S-7688-MP-74.CN.S3.33.3.2 | Capping (Rail) | I.CN.33.8400 | CON - Sec.3 - Capping (45,071 TON) 985 TON/d | 2026-03-30 | 2026-03-31
Capping (RMAR) |  |  |  | 2026-05-22 | 2026-05-23
I2S-7688-MP-74.CN.S3.33.3.25 | Capping (RMAR) | I.CN.45.8640 | CON - Sec.3 - Fill - Cut 07 - (14,912 TON) - Strip/Grade RMAR with type D Material (U5 Class) | 2026-05-22 | 2026-05-23
034 - Drainage |  |  |  | 2025-08-01 | 2026-06-11
Mainline |  |  |  | 2025-08-01 | 2026-05-04
I2S-7688-MP-74.CN.S3.34.13 | Mainline | I.CN.34.27900 | CON - Sec.3 - Place Enveloper Pipe - DN300 RCP - 1.5m past crdr boundary (75m) - (ch. 9870) | 2025-08-01 | 2025-08-06
I2S-7688-MP-74.CN.S3.34.13 | Mainline | I.CN.34.27910 | CON - Sec.3 - Place Enveloper Pipe - DN300 RCP - 1.5m past crdr boundary (75m) - (ch. 10330) | 2025-08-07 | 2025-08-12
I2S-7688-MP-74.CN.S3.34.13 | Mainline | I.CN.34.27920 | CON - Sec.3 - Place Enveloper Pipe - DN300 RCP - 1.5m past crdr boundary (58m) - (ch. 10965) | 2025-08-13 | 2025-08-16
I2S-7688-MP-74.CN.S3.34.13 | Mainline | I.CN.34.27930 | CON - Sec.3 - Place Enveloper Pipe - DN300 RCP - 1.5m past crdr boundary (51m) - (ch. 14615) | 2025-08-18 | 2025-08-20
I2S-7688-MP-74.CN.S3.34.13 | Mainline | I.CN.34.27940 | CON - Sec.3 - Place Enveloper Pipe - DN300 RCP - 1.5m past crdr boundary (58m) - (ch. 15475) | 2025-08-21 | 2025-08-25
I2S-7688-MP-74.CN.S3.34.13 | Mainline | I.CN.34.27950 | CON - Sec.3 - Place Enveloper Pipe - DN300 RCP - 1.5m past crdr boundary (60m) - (ch. 15960) | 2025-08-26 | 2025-08-29
I2S-7688-MP-74.CN.S3.34.13 | Mainline | I.CN.34.25420 | CON - Sec.3 - Cess Drainage - 13596 to 13885 - Rock Lined | 2026-05-02 | 2026-05-04
Loop and Sidings |  |  |  | 2026-05-05 | 2026-05-10
I2S-7688-MP-74.CN.S3.34.1 | Loop and Sidings | I.CN.34.25500 | CON - Sec.3 - Loop & sidings - Cess Drainage - 11400 to 14450 | 2026-05-05 | 2026-05-10
Culverts |  |  |  | 2025-12-11 | 2026-06-11
Culvert ID : E7-RA-435700-1 / Type : 12*900mm HDPE / Ch18189 (43.00m each) |  |  |  | 2026-03-21 | 2026-04-10
I2S-7688-MP-74.CN.S3.34.14.11 | Culvert ID : E7-RA-435700-1 / Type : 12*900mm HDPE / Ch18189 (43.00m each) | I.CN.34.24120 | CON - Sec.3 - Culvert : E7-RA-435700-1 - Headwall Cut-off Wall Installation (FRP) | 2026-04-07 | 2026-04-08
I2S-7688-MP-74.CN.S3.34.14.11 | Culvert ID : E7-RA-435700-1 / Type : 12*900mm HDPE / Ch18189 (43.00m each) | I.CN.34.24140 | CON - Sec.3 - Culvert : E7-RA-435700-1 - Construct Scour Protection | 2026-04-09 | 2026-04-10
I2S-7688-MP-74.CN.S3.34.14.11 | Culvert ID : E7-RA-435700-1 / Type : 12*900mm HDPE / Ch18189 (43.00m each) | I.CN.34.24030 | CON - Sec.3 - Culvert : E7-RA-435700-1 - Site Prep / Detail Excavation | 2026-03-21 | 2026-03-22
I2S-7688-MP-74.CN.S3.34.14.11 | Culvert ID : E7-RA-435700-1 / Type : 12*900mm HDPE / Ch18189 (43.00m each) | I.CN.34.24040 | CON - Sec.3 - Culvert : E7-RA-435700-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-03-23 | 2026-03-24
I2S-7688-MP-74.CN.S3.34.14.11 | Culvert ID : E7-RA-435700-1 / Type : 12*900mm HDPE / Ch18189 (43.00m each) | I.CN.34.24070 | CON - Sec.3 - Culvert : E7-RA-435700-1 - Headwall installation | 2026-03-26 | 2026-03-26
I2S-7688-MP-74.CN.S3.34.14.11 | Culvert ID : E7-RA-435700-1 / Type : 12*900mm HDPE / Ch18189 (43.00m each) | I.CN.34.24090 | CON - Sec.3 - Culvert : E7-RA-435700-1 - HDPE / RCP Pipe Lay & Backfill | 2026-03-29 | 2026-04-04
I2S-7688-MP-74.CN.S3.34.14.11 | Culvert ID : E7-RA-435700-1 / Type : 12*900mm HDPE / Ch18189 (43.00m each) | I.CN.34.24110 | CON - Sec.3 - Culvert : E7-RA-435700-1 - Headwall Stitch Pour | 2026-04-06 | 2026-04-06
Culvert ID : E7-RA-435150-1 / Type : 2*1050mm HDPE / Ch17755 (16.06m each) |  |  |  | 2026-01-22 | 2026-03-23
I2S-7688-MP-74.CN.S3.34.14.15 | Culvert ID : E7-RA-435150-1 / Type : 2*1050mm HDPE / Ch17755 (16.06m each) | I.CN.34.27610 | CON - Sec.3 - Culvert : E7-RA-435150-1 - HDPE / RCP Pipe Lay & Backfill | 2026-03-09 | 2026-03-09
I2S-7688-MP-74.CN.S3.34.14.15 | Culvert ID : E7-RA-435150-1 / Type : 2*1050mm HDPE / Ch17755 (16.06m each) | I.CN.34.27630 | CON - Sec.3 - Culvert : E7-RA-435150-1 - Headwall Stitch Pour | 2026-03-11 | 2026-03-18
I2S-7688-MP-74.CN.S3.34.14.15 | Culvert ID : E7-RA-435150-1 / Type : 2*1050mm HDPE / Ch17755 (16.06m each) | I.CN.34.27640 | CON - Sec.3 - Culvert : E7-RA-435150-1 - Headwall Cut-off Wall Installation (FRP) | 2026-03-19 | 2026-03-20
I2S-7688-MP-74.CN.S3.34.14.15 | Culvert ID : E7-RA-435150-1 / Type : 2*1050mm HDPE / Ch17755 (16.06m each) | I.CN.34.27660 | CON - Sec.3 - Culvert : E7-RA-435150-1 - Construct Scour Protection | 2026-03-22 | 2026-03-23
I2S-7688-MP-74.CN.S3.34.14.15 | Culvert ID : E7-RA-435150-1 / Type : 2*1050mm HDPE / Ch17755 (16.06m each) | I.CN.34.27580 | CON - Sec.3 - Culvert : E7-RA-435150-1 - Site Prep / Detail Excavation | 2026-01-22 | 2026-01-23
I2S-7688-MP-74.CN.S3.34.14.15 | Culvert ID : E7-RA-435150-1 / Type : 2*1050mm HDPE / Ch17755 (16.06m each) | I.CN.34.27590 | CON - Sec.3 - Culvert : E7-RA-435150-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-01-24 | 2026-01-26
I2S-7688-MP-74.CN.S3.34.14.15 | Culvert ID : E7-RA-435150-1 / Type : 2*1050mm HDPE / Ch17755 (16.06m each) | I.CN.34.27600 | CON - Sec.3 - Culvert : E7-RA-435150-1 - Headwall installation | 2026-01-27 | 2026-03-08
Culvert ID : E7-RA-435195-1 / Type : 2*600mm HDPE / Ch17688 (17.46m each)
I2S-7688-MP-74.CN.S3.34.14.5 | Culvert ID : E7-RA-435195-1 / Type : 2*600mm HDPE / Ch17688 (17.46m each) | I.CN.34.32750 | CON - Sec.3 - Culvert : E7-RA-435195-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S3.34.14.5 | Culvert ID : E7-RA-435195-1 / Type : 2*600mm HDPE / Ch17688 (17.46m each) | I.CN.34.32760 | CON - Sec.3 - Culvert : E7-RA-435195-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S3.34.14.5 | Culvert ID : E7-RA-435195-1 / Type : 2*600mm HDPE / Ch17688 (17.46m each) | I.CN.34.32770 | CON - Sec.3 - Culvert : E7-RA-435195-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S3.34.14.5 | Culvert ID : E7-RA-435195-1 / Type : 2*600mm HDPE / Ch17688 (17.46m each) | I.CN.34.32780 | CON - Sec.3 - Culvert : E7-RA-435195-1 - Construct Scour Protection
I2S-7688-MP-74.CN.S3.34.14.5 | Culvert ID : E7-RA-435195-1 / Type : 2*600mm HDPE / Ch17688 (17.46m each) | I.CN.34.32720 | CON - Sec.3 - Culvert : E7-RA-435195-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S3.34.14.5 | Culvert ID : E7-RA-435195-1 / Type : 2*600mm HDPE / Ch17688 (17.46m each) | I.CN.34.32730 | CON - Sec.3 - Culvert : E7-RA-435195-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S3.34.14.5 | Culvert ID : E7-RA-435195-1 / Type : 2*600mm HDPE / Ch17688 (17.46m each) | I.CN.34.32740 | CON - Sec.3 - Culvert : E7-RA-435195-1 - Headwall installation
I2S-7688-MP-74.CN.S3.34.14.5 | Culvert ID : E7-RA-435195-1 / Type : 2*600mm HDPE / Ch17688 (17.46m each) | I.CN.34.32860 | CON - Sec.3 - Culvert : E7-RA-435195-1 - HDPE / RCP Pipe Lay & Backfill - Milestone
Culvert ID : E7-RA-435050-1 / Type : 4*2400x1500mm RCBC / Ch17533 (31.2m each) |  |  |  | 2026-02-23 | 2026-03-10
I2S-7688-MP-74.CN.S3.34.14.9 | Culvert ID : E7-RA-435050-1 / Type : 4*2400x1500mm RCBC / Ch17533 (31.2m each) | I.CN.34.27430 | CON - Sec.3 - Culvert : E7-RA-435050-1 - FRP Base Slab / Apron Slab / Cut-off Wall | 2026-02-26 | 2026-03-01
I2S-7688-MP-74.CN.S3.34.14.9 | Culvert ID : E7-RA-435050-1 / Type : 4*2400x1500mm RCBC / Ch17533 (31.2m each) | I.CN.34.24270 | CON - Sec.3 - Culvert : E7-RA-435050-1 - Site Prep / Detail Excavation | 2026-02-23 | 2026-02-24
I2S-7688-MP-74.CN.S3.34.14.9 | Culvert ID : E7-RA-435050-1 / Type : 4*2400x1500mm RCBC / Ch17533 (31.2m each) | I.CN.34.24280 | CON - Sec.3 - Culvert : E7-RA-435050-1 - Struc fill Placement (250mm) | 2026-02-26 | 2026-02-27
I2S-7688-MP-74.CN.S3.34.14.9 | Culvert ID : E7-RA-435050-1 / Type : 4*2400x1500mm RCBC / Ch17533 (31.2m each) | I.CN.34.24320 | CON - Sec.3 - Culvert : E7-RA-435050-1 - 7 day Curing | 2026-02-28 | 2026-02-28
I2S-7688-MP-74.CN.S3.34.14.9 | Culvert ID : E7-RA-435050-1 / Type : 4*2400x1500mm RCBC / Ch17533 (31.2m each) | I.CN.34.24330 | CON - Sec.3 - Culvert : E7-RA-435050-1 - Place RCBC crown units | 2026-03-01 | 2026-03-01
I2S-7688-MP-74.CN.S3.34.14.9 | Culvert ID : E7-RA-435050-1 / Type : 4*2400x1500mm RCBC / Ch17533 (31.2m each) | I.CN.34.24350 | CON - Sec.3 - Culvert : E7-RA-435050-1 - Place Pre-cast Wingwalls and Stich Pour | 2026-03-03 | 2026-03-04
I2S-7688-MP-74.CN.S3.34.14.9 | Culvert ID : E7-RA-435050-1 / Type : 4*2400x1500mm RCBC / Ch17533 (31.2m each) | I.CN.34.24360 | CON - Sec.3 - Culvert : E7-RA-435050-1 - Pre-cast RCBC completion (Seal joints) | 2026-03-06 | 2026-03-07
I2S-7688-MP-74.CN.S3.34.14.9 | Culvert ID : E7-RA-435050-1 / Type : 4*2400x1500mm RCBC / Ch17533 (31.2m each) | I.CN.34.24370 | CON - Sec.3 - Culvert : E7-RA-435050-1 - Detail backfill | 2026-03-08 | 2026-03-08
I2S-7688-MP-74.CN.S3.34.14.9 | Culvert ID : E7-RA-435050-1 / Type : 4*2400x1500mm RCBC / Ch17533 (31.2m each) | I.CN.34.24380 | CON - Sec.3 - Culvert : E7-RA-435050-1 - Construct Scour protection | 2026-03-09 | 2026-03-10
I2S-7688-MP-74.CN.S3.34.14.9 | Culvert ID : E7-RA-435050-1 / Type : 4*2400x1500mm RCBC / Ch17533 (31.2m each) | I.CN.34.32040 | CON - Sec.3 - Culvert : E7-RA-435050-1 - Blinding placement (50mm)
Culvert ID : E7-RA-434325-1 / Type : 4*900mm HDPE / Ch16802 (13.24m each) |  |  |  | 2026-02-09 | 2026-02-22
I2S-7688-MP-74.CN.S3.34.14.8 | Culvert ID : E7-RA-434325-1 / Type : 4*900mm HDPE / Ch16802 (13.24m each) | I.CN.34.24500 | CON - Sec.3 - Culvert : E7-RA-434325-1 - Construct Scour Protection | 2026-02-21 | 2026-02-22
I2S-7688-MP-74.CN.S3.34.14.8 | Culvert ID : E7-RA-434325-1 / Type : 4*900mm HDPE / Ch16802 (13.24m each) | I.CN.34.24390 | CON - Sec.3 - Culvert : E7-RA-434325-1 - Site Prep / Detail Excavation | 2026-02-09 | 2026-02-10
I2S-7688-MP-74.CN.S3.34.14.8 | Culvert ID : E7-RA-434325-1 / Type : 4*900mm HDPE / Ch16802 (13.24m each) | I.CN.34.24400 | CON - Sec.3 - Culvert : E7-RA-434325-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-02-11 | 2026-02-12
I2S-7688-MP-74.CN.S3.34.14.8 | Culvert ID : E7-RA-434325-1 / Type : 4*900mm HDPE / Ch16802 (13.24m each) | I.CN.34.24440 | CON - Sec.3 - Culvert : E7-RA-434325-1 - Headwall installation | 2026-02-13 | 2026-02-13
I2S-7688-MP-74.CN.S3.34.14.8 | Culvert ID : E7-RA-434325-1 / Type : 4*900mm HDPE / Ch16802 (13.24m each) | I.CN.34.24450 | CON - Sec.3 - Culvert : E7-RA-434325-1 - HDPE / RCP Pipe Lay & Backfill | 2026-02-14 | 2026-02-14
I2S-7688-MP-74.CN.S3.34.14.8 | Culvert ID : E7-RA-434325-1 / Type : 4*900mm HDPE / Ch16802 (13.24m each) | I.CN.34.24470 | CON - Sec.3 - Culvert : E7-RA-434325-1 - Headwall Stitch Pour | 2026-02-16 | 2026-02-17
I2S-7688-MP-74.CN.S3.34.14.8 | Culvert ID : E7-RA-434325-1 / Type : 4*900mm HDPE / Ch16802 (13.24m each) | I.CN.34.24480 | CON - Sec.3 - Culvert : E7-RA-434325-1 - Headwall Cut-off Wall Installation (FRP) | 2026-02-18 | 2026-02-19
Culvert ID : E7-RA-433860-1 / Type : 9*900mm HDPE / Ch16337 (24.35m each) |  |  |  | 2026-03-24 | 2026-04-09
I2S-7688-MP-74.CN.S3.34.14.17 | Culvert ID : E7-RA-433860-1 / Type : 9*900mm HDPE / Ch16337 (24.35m each) | I.CN.34.27760 | CON - Sec.3 - Culvert : E7-RA-433860-1 - Construct Scour Protection | 2026-04-08 | 2026-04-09
I2S-7688-MP-74.CN.S3.34.14.17 | Culvert ID : E7-RA-433860-1 / Type : 9*900mm HDPE / Ch16337 (24.35m each) | I.CN.34.27680 | CON - Sec.3 - Culvert : E7-RA-433860-1 - Site Prep / Detail Excavation | 2026-03-24 | 2026-03-26
I2S-7688-MP-74.CN.S3.34.14.17 | Culvert ID : E7-RA-433860-1 / Type : 9*900mm HDPE / Ch16337 (24.35m each) | I.CN.34.27690 | CON - Sec.3 - Culvert : E7-RA-433860-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-03-27 | 2026-03-28
I2S-7688-MP-74.CN.S3.34.14.17 | Culvert ID : E7-RA-433860-1 / Type : 9*900mm HDPE / Ch16337 (24.35m each) | I.CN.34.27700 | CON - Sec.3 - Culvert : E7-RA-433860-1 - Headwall installation | 2026-03-29 | 2026-03-30
I2S-7688-MP-74.CN.S3.34.14.17 | Culvert ID : E7-RA-433860-1 / Type : 9*900mm HDPE / Ch16337 (24.35m each) | I.CN.34.27710 | CON - Sec.3 - Culvert : E7-RA-433860-1 - HDPE / RCP Pipe Lay & Backfill | 2026-03-31 | 2026-03-31
I2S-7688-MP-74.CN.S3.34.14.17 | Culvert ID : E7-RA-433860-1 / Type : 9*900mm HDPE / Ch16337 (24.35m each) | I.CN.34.27730 | CON - Sec.3 - Culvert : E7-RA-433860-1 - Headwall Stitch Pour | 2026-04-02 | 2026-04-03
I2S-7688-MP-74.CN.S3.34.14.17 | Culvert ID : E7-RA-433860-1 / Type : 9*900mm HDPE / Ch16337 (24.35m each) | I.CN.34.27740 | CON - Sec.3 - Culvert : E7-RA-433860-1 - Headwall Cut-off Wall Installation (FRP) | 2026-04-04 | 2026-04-06
Culvert ID : E7-RA-431129-1 / Type : 7*900mm HDPE / Ch13636 (26.91m each) |  |  |  | 2026-04-10 | 2026-04-24
I2S-7688-MP-74.CN.S3.34.14.18 | Culvert ID : E7-RA-431129-1 / Type : 7*900mm HDPE / Ch13636 (26.91m each) | I.CN.34.27810 | CON - Sec.3 - Culvert : E7-RA-431160-1 - HDPE / RCP Pipe Lay & Backfill | 2026-04-16 | 2026-04-16
I2S-7688-MP-74.CN.S3.34.14.18 | Culvert ID : E7-RA-431129-1 / Type : 7*900mm HDPE / Ch13636 (26.91m each) | I.CN.34.27830 | CON - Sec.3 - Culvert : E7-RA-431160-1 - Headwall Stitch Pour | 2026-04-18 | 2026-04-19
I2S-7688-MP-74.CN.S3.34.14.18 | Culvert ID : E7-RA-431129-1 / Type : 7*900mm HDPE / Ch13636 (26.91m each) | I.CN.34.27840 | CON - Sec.3 - Culvert : E7-RA-431160-1 - Headwall Cut-off Wall Installation (FRP) | 2026-04-20 | 2026-04-21
I2S-7688-MP-74.CN.S3.34.14.18 | Culvert ID : E7-RA-431129-1 / Type : 7*900mm HDPE / Ch13636 (26.91m each) | I.CN.34.27860 | CON - Sec.3 - Culvert : E7-RA-431160-1 - Construct Scour Protection | 2026-04-23 | 2026-04-24
I2S-7688-MP-74.CN.S3.34.14.18 | Culvert ID : E7-RA-431129-1 / Type : 7*900mm HDPE / Ch13636 (26.91m each) | I.CN.34.27780 | CON - Sec.3 - Culvert : E7-RA-431160-1 - Site Prep / Detail Excavation | 2026-04-10 | 2026-04-11
I2S-7688-MP-74.CN.S3.34.14.18 | Culvert ID : E7-RA-431129-1 / Type : 7*900mm HDPE / Ch13636 (26.91m each) | I.CN.34.27790 | CON - Sec.3 - Culvert : E7-RA-431160-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-04-12 | 2026-04-13
I2S-7688-MP-74.CN.S3.34.14.18 | Culvert ID : E7-RA-431129-1 / Type : 7*900mm HDPE / Ch13636 (26.91m each) | I.CN.34.27800 | CON - Sec.3 - Culvert : E7-RA-431160-1 - Headwall installation | 2026-04-14 | 2026-04-15
Culvert ID : E7-RA-430650-1 / Type : 16*900mm HDPE / Ch13142 (9.11m each)
I2S-7688-MP-74.CN.S3.34.14.7 | Culvert ID : E7-RA-430650-1 / Type : 16*900mm HDPE / Ch13142 (9.11m each) | I.CN.34.30820 | CON - Sec.3 - Culvert : E7-RA-430650-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S3.34.14.7 | Culvert ID : E7-RA-430650-1 / Type : 16*900mm HDPE / Ch13142 (9.11m each) | I.CN.34.30840 | CON - Sec.3 - Culvert : E7-RA-430650-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S3.34.14.7 | Culvert ID : E7-RA-430650-1 / Type : 16*900mm HDPE / Ch13142 (9.11m each) | I.CN.34.30850 | CON - Sec.3 - Culvert : E7-RA-430650-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S3.34.14.7 | Culvert ID : E7-RA-430650-1 / Type : 16*900mm HDPE / Ch13142 (9.11m each) | I.CN.34.30870 | CON - Sec.3 - Culvert : E7-RA-430650-1 - Construct Scour Protection
I2S-7688-MP-74.CN.S3.34.14.7 | Culvert ID : E7-RA-430650-1 / Type : 16*900mm HDPE / Ch13142 (9.11m each) | I.CN.34.30880 | CON - Sec.3 - Culvert : E7-RA-430650-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S3.34.14.7 | Culvert ID : E7-RA-430650-1 / Type : 16*900mm HDPE / Ch13142 (9.11m each) | I.CN.34.30890 | CON - Sec.3 - Culvert : E7-RA-430650-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S3.34.14.7 | Culvert ID : E7-RA-430650-1 / Type : 16*900mm HDPE / Ch13142 (9.11m each) | I.CN.34.30900 | CON - Sec.3 - Culvert : E7-RA-430650-1 - Headwall installation
Culvert ID : E7-RA-430550-1 / Type : 8*900mm HDPE / Ch13041 (9.48m each) |  |  |  | 2026-05-29 | 2026-06-11
I2S-7688-MP-74.CN.S3.34.14.6 | Culvert ID : E7-RA-430550-1 / Type : 8*900mm HDPE / Ch13041 (9.48m each) | I.CN.34.24630 | CON - Sec.3 - Culvert : E7-RA-430550-1 - Site Prep / Detail Excavation | 2026-05-29 | 2026-05-30
I2S-7688-MP-74.CN.S3.34.14.6 | Culvert ID : E7-RA-430550-1 / Type : 8*900mm HDPE / Ch13041 (9.48m each) | I.CN.34.24640 | CON - Sec.3 - Culvert : E7-RA-430550-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-05-31 | 2026-06-01
I2S-7688-MP-74.CN.S3.34.14.6 | Culvert ID : E7-RA-430550-1 / Type : 8*900mm HDPE / Ch13041 (9.48m each) | I.CN.34.24680 | CON - Sec.3 - Culvert : E7-RA-430550-1 - Headwall installation | 2026-06-02 | 2026-06-02
I2S-7688-MP-74.CN.S3.34.14.6 | Culvert ID : E7-RA-430550-1 / Type : 8*900mm HDPE / Ch13041 (9.48m each) | I.CN.34.24690 | CON - Sec.3 - Culvert : E7-RA-430550-1 - HDPE / RCP Pipe Lay & Backfill | 2026-06-03 | 2026-06-03
I2S-7688-MP-74.CN.S3.34.14.6 | Culvert ID : E7-RA-430550-1 / Type : 8*900mm HDPE / Ch13041 (9.48m each) | I.CN.34.24710 | CON - Sec.3 - Culvert : E7-RA-430550-1 - Headwall Stitch Pour | 2026-06-04 | 2026-06-06
I2S-7688-MP-74.CN.S3.34.14.6 | Culvert ID : E7-RA-430550-1 / Type : 8*900mm HDPE / Ch13041 (9.48m each) | I.CN.34.24720 | CON - Sec.3 - Culvert : E7-RA-430550-1 - Headwall Cut-off Wall Installation (FRP) | 2026-06-07 | 2026-06-08
I2S-7688-MP-74.CN.S3.34.14.6 | Culvert ID : E7-RA-430550-1 / Type : 8*900mm HDPE / Ch13041 (9.48m each) | I.CN.34.24740 | CON - Sec.3 - Culvert : E7-RA-430550-1 - Construct Scour Protection | 2026-06-10 | 2026-06-11
Culvert ID : E7-RA-430480-1 / Type : 3*1200x450mm RCBC / Ch12976 (14.40m each)
I2S-7688-MP-74.CN.S3.34.14.10 | Culvert ID : E7-RA-430480-1 / Type : 3*1200x450mm RCBC / Ch12976 (14.40m each) | I.CN.34.30910 | CON - Sec.3 - Culvert : E7-RA-430480-1 - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.CN.S3.34.14.10 | Culvert ID : E7-RA-430480-1 / Type : 3*1200x450mm RCBC / Ch12976 (14.40m each) | I.CN.34.30920 | CON - Sec.3 - Culvert : E7-RA-430480-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S3.34.14.10 | Culvert ID : E7-RA-430480-1 / Type : 3*1200x450mm RCBC / Ch12976 (14.40m each) | I.CN.34.30930 | CON - Sec.3 - Culvert : E7-RA-430480-1 - Struc fill Placement (250mm)
I2S-7688-MP-74.CN.S3.34.14.10 | Culvert ID : E7-RA-430480-1 / Type : 3*1200x450mm RCBC / Ch12976 (14.40m each) | I.CN.34.30940 | CON - Sec.3 - Culvert : E7-RA-430480-1 - 7 day Curing
I2S-7688-MP-74.CN.S3.34.14.10 | Culvert ID : E7-RA-430480-1 / Type : 3*1200x450mm RCBC / Ch12976 (14.40m each) | I.CN.34.30950 | CON - Sec.3 - Culvert : E7-RA-430480-1 - Place RCBC crown units
I2S-7688-MP-74.CN.S3.34.14.10 | Culvert ID : E7-RA-430480-1 / Type : 3*1200x450mm RCBC / Ch12976 (14.40m each) | I.CN.34.30960 | CON - Sec.3 - Culvert : E7-RA-430480-1 - Place Pre-cast Wingwalls and Stich Pour
I2S-7688-MP-74.CN.S3.34.14.10 | Culvert ID : E7-RA-430480-1 / Type : 3*1200x450mm RCBC / Ch12976 (14.40m each) | I.CN.34.30970 | CON - Sec.3 - Culvert : E7-RA-430480-1 - Pre-cast RCBC completion (Seal joints)
I2S-7688-MP-74.CN.S3.34.14.10 | Culvert ID : E7-RA-430480-1 / Type : 3*1200x450mm RCBC / Ch12976 (14.40m each) | I.CN.34.30980 | CON - Sec.3 - Culvert : E7-RA-430480-1 - Detail backfill
I2S-7688-MP-74.CN.S3.34.14.10 | Culvert ID : E7-RA-430480-1 / Type : 3*1200x450mm RCBC / Ch12976 (14.40m each) | I.CN.34.30990 | CON - Sec.3 - Culvert : E7-RA-430480-1 - Construct Scour protection
I2S-7688-MP-74.CN.S3.34.14.10 | Culvert ID : E7-RA-430480-1 / Type : 3*1200x450mm RCBC / Ch12976 (14.40m each) | I.CN.34.32050 | CON - Sec.3 - Culvert : E7-RA-430480-1 - Blinding placement (50mm)
Culvert ID : E7-RA-430050-1 / Type : 53*750mm HDPE / Ch12534 (23.29m each) |  |  |  | 2026-05-10 | 2026-05-23
I2S-7688-MP-74.CN.S3.34.14.16 | Culvert ID : E7-RA-430050-1 / Type : 53*750mm HDPE / Ch12534 (23.29m each) | I.CN.34.27150 | CON - Sec.3 - Culvert : E7-RA-430050-1 - Site Prep / Detail Excavation | 2026-05-10 | 2026-05-11
I2S-7688-MP-74.CN.S3.34.14.16 | Culvert ID : E7-RA-430050-1 / Type : 53*750mm HDPE / Ch12534 (23.29m each) | I.CN.34.27160 | CON - Sec.3 - Culvert : E7-RA-430050-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2026-05-12 | 2026-05-13
I2S-7688-MP-74.CN.S3.34.14.16 | Culvert ID : E7-RA-430050-1 / Type : 53*750mm HDPE / Ch12534 (23.29m each) | I.CN.34.27200 | CON - Sec.3 - Culvert : E7-RA-430050-1 - Headwall installation | 2026-05-14 | 2026-05-14
I2S-7688-MP-74.CN.S3.34.14.16 | Culvert ID : E7-RA-430050-1 / Type : 53*750mm HDPE / Ch12534 (23.29m each) | I.CN.34.27210 | CON - Sec.3 - Culvert : E7-RA-430050-1 - HDPE / RCP Pipe Lay & Backfill | 2026-05-16 | 2026-05-16
I2S-7688-MP-74.CN.S3.34.14.16 | Culvert ID : E7-RA-430050-1 / Type : 53*750mm HDPE / Ch12534 (23.29m each) | I.CN.34.27230 | CON - Sec.3 - Culvert : E7-RA-430050-1 - Headwall Stitch Pour | 2026-05-17 | 2026-05-18
I2S-7688-MP-74.CN.S3.34.14.16 | Culvert ID : E7-RA-430050-1 / Type : 53*750mm HDPE / Ch12534 (23.29m each) | I.CN.34.27240 | CON - Sec.3 - Culvert : E7-RA-430050-1 - Headwall Cut-off Wall Installation (FRP) | 2026-05-19 | 2026-05-20
I2S-7688-MP-74.CN.S3.34.14.16 | Culvert ID : E7-RA-430050-1 / Type : 53*750mm HDPE / Ch12534 (23.29m each) | I.CN.34.27260 | CON - Sec.3 - Culvert : E7-RA-430050-1 - Construct Scour Protection | 2026-05-22 | 2026-05-23
Culvert ID : E7-RA-428920-1 / Type : 6*1200x300mm RCBC / Ch11420 (7.20m each) |  |  |  | 2026-04-06 | 2026-04-20
I2S-7688-MP-74.CN.S3.34.14.4 | Culvert ID : E7-RA-428920-1 / Type : 6*1200x300mm RCBC / Ch11420 (7.20m each) | I.CN.34.27470 | CON - Sec.3 - Culvert : E7-RA-428920-1 - FRP Base Slab / Apron Slab / Cut-off Wall | 2026-04-08 | 2026-04-12
I2S-7688-MP-74.CN.S3.34.14.4 | Culvert ID : E7-RA-428920-1 / Type : 6*1200x300mm RCBC / Ch11420 (7.20m each) | I.CN.34.24870 | CON - Sec.3 - Culvert : E7-RA-428920-1 - Site Prep / Detail Excavation | 2026-04-06 | 2026-04-07
I2S-7688-MP-74.CN.S3.34.14.4 | Culvert ID : E7-RA-428920-1 / Type : 6*1200x300mm RCBC / Ch11420 (7.20m each) | I.CN.34.24880 | CON - Sec.3 - Culvert : E7-RA-428920-1 - Struc fill Placement (250mm) | 2026-04-08 | 2026-04-09
I2S-7688-MP-74.CN.S3.34.14.4 | Culvert ID : E7-RA-428920-1 / Type : 6*1200x300mm RCBC / Ch11420 (7.20m each) | I.CN.34.24920 | CON - Sec.3 - Culvert : E7-RA-428920-1 - 7 day Curing | 2026-04-10 | 2026-04-12
I2S-7688-MP-74.CN.S3.34.14.4 | Culvert ID : E7-RA-428920-1 / Type : 6*1200x300mm RCBC / Ch11420 (7.20m each) | I.CN.34.24930 | CON - Sec.3 - Culvert : E7-RA-428920-1 - Place RCBC crown units | 2026-04-13 | 2026-04-13
I2S-7688-MP-74.CN.S3.34.14.4 | Culvert ID : E7-RA-428920-1 / Type : 6*1200x300mm RCBC / Ch11420 (7.20m each) | I.CN.34.24950 | CON - Sec.3 - Culvert : E7-RA-428920-1 - Place Pre-cast Wingwalls and Stich Pour | 2026-04-14 | 2026-04-15
I2S-7688-MP-74.CN.S3.34.14.4 | Culvert ID : E7-RA-428920-1 / Type : 6*1200x300mm RCBC / Ch11420 (7.20m each) | I.CN.34.24960 | CON - Sec.3 - Culvert : E7-RA-428920-1 - Pre-cast RCBC completion (Seal joints) | 2026-04-16 | 2026-04-17
I2S-7688-MP-74.CN.S3.34.14.4 | Culvert ID : E7-RA-428920-1 / Type : 6*1200x300mm RCBC / Ch11420 (7.20m each) | I.CN.34.24970 | CON - Sec.3 - Culvert : E7-RA-428920-1 - Detail backfill | 2026-04-18 | 2026-04-18
I2S-7688-MP-74.CN.S3.34.14.4 | Culvert ID : E7-RA-428920-1 / Type : 6*1200x300mm RCBC / Ch11420 (7.20m each) | I.CN.34.24980 | CON - Sec.3 - Culvert : E7-RA-428920-1 - Construct Scour protection | 2026-04-19 | 2026-04-20
I2S-7688-MP-74.CN.S3.34.14.4 | Culvert ID : E7-RA-428920-1 / Type : 6*1200x300mm RCBC / Ch11420 (7.20m each) | I.CN.34.32060 | CON - Sec.3 - Culvert : E7-RA-428920-1 - Blinding placement (50mm)
Culvert ID : E7-RA-428505-1 / Type : 11*1500x900mm RCBC / Ch10973 (12m each) |  |  |  | 2026-03-20 | 2026-04-04
I2S-7688-MP-74.CN.S3.34.14.14 | Culvert ID : E7-RA-428505-1 / Type : 11*1500x900mm RCBC / Ch10973 (12m each) | I.CN.34.26910 | CON - Sec.3 - Culvert : E7-RA-428505-1 - Site Prep / Detail Excavation | 2026-03-20 | 2026-03-21
I2S-7688-MP-74.CN.S3.34.14.14 | Culvert ID : E7-RA-428505-1 / Type : 11*1500x900mm RCBC / Ch10973 (12m each) | I.CN.34.26920 | CON - Sec.3 - Culvert : E7-RA-428505-1 - Struc fill Placement (250mm) | 2026-03-22 | 2026-03-23
I2S-7688-MP-74.CN.S3.34.14.14 | Culvert ID : E7-RA-428505-1 / Type : 11*1500x900mm RCBC / Ch10973 (12m each) | I.CN.34.26960 | CON - Sec.3 - Culvert : E7-RA-428505-1 - 7 day Curing | 2026-03-24 | 2026-03-29
I2S-7688-MP-74.CN.S3.34.14.14 | Culvert ID : E7-RA-428505-1 / Type : 11*1500x900mm RCBC / Ch10973 (12m each) | I.CN.34.26970 | CON - Sec.3 - Culvert : E7-RA-428505-1 - Place RCBC crown units | 2026-03-28 | 2026-03-30
I2S-7688-MP-74.CN.S3.34.14.14 | Culvert ID : E7-RA-428505-1 / Type : 11*1500x900mm RCBC / Ch10973 (12m each) | I.CN.34.26990 | CON - Sec.3 - Culvert : E7-RA-428505-1 - Place Pre-cast Wingwalls and Stich Pour | 2026-03-31 | 2026-03-31
I2S-7688-MP-74.CN.S3.34.14.14 | Culvert ID : E7-RA-428505-1 / Type : 11*1500x900mm RCBC / Ch10973 (12m each) | I.CN.34.27000 | CON - Sec.3 - Culvert : E7-RA-428505-1 - Pre-cast RCBC completion (Seal joints) | 2026-04-01 | 2026-04-02
I2S-7688-MP-74.CN.S3.34.14.14 | Culvert ID : E7-RA-428505-1 / Type : 11*1500x900mm RCBC / Ch10973 (12m each) | I.CN.34.27010 | CON - Sec.3 - Culvert : E7-RA-428505-1 - Detail backfill | 2026-04-03 | 2026-04-03
I2S-7688-MP-74.CN.S3.34.14.14 | Culvert ID : E7-RA-428505-1 / Type : 11*1500x900mm RCBC / Ch10973 (12m each) | I.CN.34.27020 | CON - Sec.3 - Culvert : E7-RA-428505-1 - Construct Scour protection | 2026-04-03 | 2026-04-04
I2S-7688-MP-74.CN.S3.34.14.14 | Culvert ID : E7-RA-428505-1 / Type : 11*1500x900mm RCBC / Ch10973 (12m each) | I.CN.34.27480 | CON - Sec.3 - Culvert : E7-RA-428505-1 - FRP Base Slab / Apron Slab / Cut-off Wall | 2026-03-22 | 2026-03-26
I2S-7688-MP-74.CN.S3.34.14.14 | Culvert ID : E7-RA-428505-1 / Type : 11*1500x900mm RCBC / Ch10973 (12m each) | I.CN.34.32070 | CON - Sec.3 - Culvert : E7-RA-428505-1 - Blinding placement (50mm)
Culvert ID : E7-RA-427750-1 / Type : 9*1200x450mm RCBC / Ch10243 (16.80m each)
I2S-7688-MP-74.CN.S3.34.14.12 | Culvert ID : E7-RA-427750-1 / Type : 9*1200x450mm RCBC / Ch10243 (16.80m each) | I.CN.34.31000 | CON - Sec.3 - Culvert : E7-RA-427750-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S3.34.14.12 | Culvert ID : E7-RA-427750-1 / Type : 9*1200x450mm RCBC / Ch10243 (16.80m each) | I.CN.34.31010 | CON - Sec.3 - Culvert : E7-RA-427750-1 - Struc fill Placement (250mm)
I2S-7688-MP-74.CN.S3.34.14.12 | Culvert ID : E7-RA-427750-1 / Type : 9*1200x450mm RCBC / Ch10243 (16.80m each) | I.CN.34.31020 | CON - Sec.3 - Culvert : E7-RA-427750-1 - 7 day Curing
I2S-7688-MP-74.CN.S3.34.14.12 | Culvert ID : E7-RA-427750-1 / Type : 9*1200x450mm RCBC / Ch10243 (16.80m each) | I.CN.34.31030 | CON - Sec.3 - Culvert : E7-RA-427750-1 - Place RCBC crown units
I2S-7688-MP-74.CN.S3.34.14.12 | Culvert ID : E7-RA-427750-1 / Type : 9*1200x450mm RCBC / Ch10243 (16.80m each) | I.CN.34.31040 | CON - Sec.3 - Culvert : E7-RA-427750-1 - Place Pre-cast Wingwalls and Stich Pour
I2S-7688-MP-74.CN.S3.34.14.12 | Culvert ID : E7-RA-427750-1 / Type : 9*1200x450mm RCBC / Ch10243 (16.80m each) | I.CN.34.31050 | CON - Sec.3 - Culvert : E7-RA-427750-1 - Pre-cast RCBC completion (Seal joints)
I2S-7688-MP-74.CN.S3.34.14.12 | Culvert ID : E7-RA-427750-1 / Type : 9*1200x450mm RCBC / Ch10243 (16.80m each) | I.CN.34.31060 | CON - Sec.3 - Culvert : E7-RA-427750-1 - Detail backfill
I2S-7688-MP-74.CN.S3.34.14.12 | Culvert ID : E7-RA-427750-1 / Type : 9*1200x450mm RCBC / Ch10243 (16.80m each) | I.CN.34.31070 | CON - Sec.3 - Culvert : E7-RA-427750-1 - Construct Scour protection
I2S-7688-MP-74.CN.S3.34.14.12 | Culvert ID : E7-RA-427750-1 / Type : 9*1200x450mm RCBC / Ch10243 (16.80m each) | I.CN.34.31080 | CON - Sec.3 - Culvert : E7-RA-427750-1 - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.CN.S3.34.14.12 | Culvert ID : E7-RA-427750-1 / Type : 9*1200x450mm RCBC / Ch10243 (16.80m each) | I.CN.34.32080 | CON - Sec.3 - Culvert : E7-RA-427750-1 - Blinding placement (50mm)
I2S-7688-MP-74.CN.S3.34.14.12 | Culvert ID : E7-RA-427750-1 / Type : 9*1200x450mm RCBC / Ch10243 (16.80m each) | I.CN.34.32870 | CON - Sec.3 - Culvert : E7-RA-427750-1 - FRP Base Slab / Apron Slab / Cut-off Wall - Milestone
Culvert ID : E7-RA-427720-1 / Type : 21*1200x600mm RCBC / Ch10210 (16.8m each) |  |  |  | 2026-03-02 | 2026-03-19
I2S-7688-MP-74.CN.S3.34.14.3 | Culvert ID : E7-RA-427720-1 / Type : 21*1200x600mm RCBC / Ch10210 (16.8m each) | I.CN.34.29140 | CON - Sec.3 - Culvert : E7-RA-427720-1 - 7 day Curing
I2S-7688-MP-74.CN.S3.34.14.3 | Culvert ID : E7-RA-427720-1 / Type : 21*1200x600mm RCBC / Ch10210 (16.8m each) | I.CN.34.25080 | CON - Sec.3 - Culvert : E7-RA-427720-1 - Pre-cast RCBC completion (Seal joints) | 2026-03-11 | 2026-03-11
I2S-7688-MP-74.CN.S3.34.14.3 | Culvert ID : E7-RA-427720-1 / Type : 21*1200x600mm RCBC / Ch10210 (16.8m each) | I.CN.34.25090 | CON - Sec.3 - Culvert : E7-RA-427720-1 - Detail backfill | 2026-03-18 | 2026-03-18
I2S-7688-MP-74.CN.S3.34.14.3 | Culvert ID : E7-RA-427720-1 / Type : 21*1200x600mm RCBC / Ch10210 (16.8m each) | I.CN.34.25100 | CON - Sec.3 - Culvert : E7-RA-427720-1 - Construct Scour protection | 2026-03-19 | 2026-03-19
I2S-7688-MP-74.CN.S3.34.14.3 | Culvert ID : E7-RA-427720-1 / Type : 21*1200x600mm RCBC / Ch10210 (16.8m each) | I.CN.34.24990 | CON - Sec.3 - Culvert : E7-RA-427720-1 - Site Prep / Detail Excavation | 2026-03-02 | 2026-03-03
I2S-7688-MP-74.CN.S3.34.14.3 | Culvert ID : E7-RA-427720-1 / Type : 21*1200x600mm RCBC / Ch10210 (16.8m each) | I.CN.34.25000 | CON - Sec.3 - Culvert : E7-RA-427720-1 - Struc fill Placement (250mm) | 2026-03-04 | 2026-03-04
I2S-7688-MP-74.CN.S3.34.14.3 | Culvert ID : E7-RA-427720-1 / Type : 21*1200x600mm RCBC / Ch10210 (16.8m each) | I.CN.34.25030 | CON - Sec.3 - Culvert : E7-RA-427720-1 - FRP Base Slab / Apron Slab / Cut-off Wall | 2026-03-06 | 2026-03-06
I2S-7688-MP-74.CN.S3.34.14.3 | Culvert ID : E7-RA-427720-1 / Type : 21*1200x600mm RCBC / Ch10210 (16.8m each) | I.CN.34.25040 | CON - Sec.3 - Culvert : E7-RA-427720-1 - Place RCBC crown units | 2026-03-07 | 2026-03-07
I2S-7688-MP-74.CN.S3.34.14.3 | Culvert ID : E7-RA-427720-1 / Type : 21*1200x600mm RCBC / Ch10210 (16.8m each) | I.CN.34.25070 | CON - Sec.3 - Culvert : E7-RA-427720-1 - Place Pre-cast Wingwalls and Stich Pour | 2026-03-10 | 2026-03-10
I2S-7688-MP-74.CN.S3.34.14.3 | Culvert ID : E7-RA-427720-1 / Type : 21*1200x600mm RCBC / Ch10210 (16.8m each) | I.CN.34.32090 | CON - Sec.3 - Culvert : E7-RA-427720-1 - Blinding placement (50mm)
Culvert ID : E7-RA-427685-1 / Type : 9*1200x450mm RCBC / Ch10179 (16.8m each)
I2S-7688-MP-74.CN.S3.34.14.13 | Culvert ID : E7-RA-427685-1 / Type : 9*1200x450mm RCBC / Ch10179 (16.8m each) | I.CN.34.31090 | CON - Sec.3 - Culvert : E7-RA-427685-1 - 7 day Curing
I2S-7688-MP-74.CN.S3.34.14.13 | Culvert ID : E7-RA-427685-1 / Type : 9*1200x450mm RCBC / Ch10179 (16.8m each) | I.CN.34.31100 | CON - Sec.3 - Culvert : E7-RA-427685-1 - Pre-cast RCBC completion (Seal joints)
I2S-7688-MP-74.CN.S3.34.14.13 | Culvert ID : E7-RA-427685-1 / Type : 9*1200x450mm RCBC / Ch10179 (16.8m each) | I.CN.34.31110 | CON - Sec.3 - Culvert : E7-RA-427685-1 - Detail backfill
I2S-7688-MP-74.CN.S3.34.14.13 | Culvert ID : E7-RA-427685-1 / Type : 9*1200x450mm RCBC / Ch10179 (16.8m each) | I.CN.34.31120 | CON - Sec.3 - Culvert : E7-RA-427685-1 - Construct Scour protection
I2S-7688-MP-74.CN.S3.34.14.13 | Culvert ID : E7-RA-427685-1 / Type : 9*1200x450mm RCBC / Ch10179 (16.8m each) | I.CN.34.31130 | CON - Sec.3 - Culvert : E7-RA-427685-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S3.34.14.13 | Culvert ID : E7-RA-427685-1 / Type : 9*1200x450mm RCBC / Ch10179 (16.8m each) | I.CN.34.31140 | CON - Sec.3 - Culvert : E7-RA-427685-1 - Struc fill Placement (250mm)
I2S-7688-MP-74.CN.S3.34.14.13 | Culvert ID : E7-RA-427685-1 / Type : 9*1200x450mm RCBC / Ch10179 (16.8m each) | I.CN.34.31150 | CON - Sec.3 - Culvert : E7-RA-427685-1 - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.CN.S3.34.14.13 | Culvert ID : E7-RA-427685-1 / Type : 9*1200x450mm RCBC / Ch10179 (16.8m each) | I.CN.34.31160 | CON - Sec.3 - Culvert : E7-RA-427685-1 - Place RCBC crown units
I2S-7688-MP-74.CN.S3.34.14.13 | Culvert ID : E7-RA-427685-1 / Type : 9*1200x450mm RCBC / Ch10179 (16.8m each) | I.CN.34.31170 | CON - Sec.3 - Culvert : E7-RA-427685-1 - Place Pre-cast Wingwalls and Stich Pour
I2S-7688-MP-74.CN.S3.34.14.13 | Culvert ID : E7-RA-427685-1 / Type : 9*1200x450mm RCBC / Ch10179 (16.8m each) | I.CN.34.32100 | CON - Sec.3 - Culvert : E7-RA-427685-1 - Blinding placement (50mm)
Culvert ID : E7-RA-427444-1 / Type : 1*1200x450mm RCBC / Ch9947 (15.6m) |  |  |  | 2026-01-29 | 2026-02-14
I2S-7688-MP-74.CN.S3.34.14.2 | Culvert ID : E7-RA-427444-1 / Type : 1*1200x450mm RCBC / Ch9947 (15.6m) | I.CN.34.25110 | CON - Sec.3 - Culvert : E7-RA-427444-1 - Site Prep / Detail Excavation | 2026-01-29 | 2026-01-30
I2S-7688-MP-74.CN.S3.34.14.2 | Culvert ID : E7-RA-427444-1 / Type : 1*1200x450mm RCBC / Ch9947 (15.6m) | I.CN.34.25120 | CON - Sec.3 - Culvert : E7-RA-427444-1 - Struc fill Placement (250mm) | 2026-01-31 | 2026-02-01
I2S-7688-MP-74.CN.S3.34.14.2 | Culvert ID : E7-RA-427444-1 / Type : 1*1200x450mm RCBC / Ch9947 (15.6m) | I.CN.34.25160 | CON - Sec.3 - Culvert : E7-RA-427444-1 - FRP Base Slab / Apron Slab / Cut-off Wall | 2026-02-02 | 2026-02-06
I2S-7688-MP-74.CN.S3.34.14.2 | Culvert ID : E7-RA-427444-1 / Type : 1*1200x450mm RCBC / Ch9947 (15.6m) | I.CN.34.25170 | CON - Sec.3 - Culvert : E7-RA-427444-1 - 7 day Curing | 2026-02-04 | 2026-02-07
I2S-7688-MP-74.CN.S3.34.14.2 | Culvert ID : E7-RA-427444-1 / Type : 1*1200x450mm RCBC / Ch9947 (15.6m) | I.CN.34.25200 | CON - Sec.3 - Culvert : E7-RA-427444-1 - Pre-cast RCBC completion (Seal joints) | 2026-02-10 | 2026-02-11
I2S-7688-MP-74.CN.S3.34.14.2 | Culvert ID : E7-RA-427444-1 / Type : 1*1200x450mm RCBC / Ch9947 (15.6m) | I.CN.34.25210 | CON - Sec.3 - Culvert : E7-RA-427444-1 - Detail backfill | 2026-02-12 | 2026-02-12
I2S-7688-MP-74.CN.S3.34.14.2 | Culvert ID : E7-RA-427444-1 / Type : 1*1200x450mm RCBC / Ch9947 (15.6m) | I.CN.34.25220 | CON - Sec.3 - Culvert : E7-RA-427444-1 - Construct Scour protection | 2026-02-13 | 2026-02-14
I2S-7688-MP-74.CN.S3.34.14.2 | Culvert ID : E7-RA-427444-1 / Type : 1*1200x450mm RCBC / Ch9947 (15.6m) | I.CN.34.27400 | CON - Sec.3 - Culvert : E7-RA-427444-1 - Place Pre-cast Wingwalls and Stich Pour | 2026-02-08 | 2026-02-09
I2S-7688-MP-74.CN.S3.34.14.2 | Culvert ID : E7-RA-427444-1 / Type : 1*1200x450mm RCBC / Ch9947 (15.6m) | I.CN.34.29130 | CON - Sec.3 - Culvert : E7-RA-427444-1 - Place RCBC crown units
I2S-7688-MP-74.CN.S3.34.14.2 | Culvert ID : E7-RA-427444-1 / Type : 1*1200x450mm RCBC / Ch9947 (15.6m) | I.CN.34.32110 | CON - Sec.3 - Culvert : E7-RA-427444-1 - Blinding placement (50mm)
Culvert ID : E7-RA-427435-1 / Type : 13*1200x450mm RCBC / Ch9933 (20.40m each) |  |  |  | 2025-12-11 | 2026-02-03
I2S-7688-MP-74.CN.S3.34.14.1 | Culvert ID : E7-RA-427435-1 / Type : 13*1200x450mm RCBC / Ch9933 (20.40m each) | I.CN.34.25330 | CON - Sec.3 - Culvert : E7-RA-427435-1 - Detail backfill | 2026-01-31 | 2026-02-01
I2S-7688-MP-74.CN.S3.34.14.1 | Culvert ID : E7-RA-427435-1 / Type : 13*1200x450mm RCBC / Ch9933 (20.40m each) | I.CN.34.25340 | CON - Sec.3 - Culvert : E7-RA-427435-1 - Construct Scour protection | 2026-02-02 | 2026-02-03
I2S-7688-MP-74.CN.S3.34.14.1 | Culvert ID : E7-RA-427435-1 / Type : 13*1200x450mm RCBC / Ch9933 (20.40m each) | I.CN.34.27390 | CON - Sec.3 - Culvert : E7-RA-427435-1 - Pre-cast RCBC completion (Seal joints) | 2026-01-29 | 2026-01-30
I2S-7688-MP-74.CN.S3.34.14.1 | Culvert ID : E7-RA-427435-1 / Type : 13*1200x450mm RCBC / Ch9933 (20.40m each) | I.CN.34.25230 | CON - Sec.3 - Culvert : E7-RA-427435-1 - Site Prep / Detail Excavation | 2025-12-11 | 2025-12-12
I2S-7688-MP-74.CN.S3.34.14.1 | Culvert ID : E7-RA-427435-1 / Type : 13*1200x450mm RCBC / Ch9933 (20.40m each) | I.CN.34.29120 | CON - Sec.3 - Culvert : E7-RA-427435-1 - Place RCBC crown units
I2S-7688-MP-74.CN.S3.34.14.1 | Culvert ID : E7-RA-427435-1 / Type : 13*1200x450mm RCBC / Ch9933 (20.40m each) | I.CN.34.25240 | CON - Sec.3 - Culvert : E7-RA-427435-1 - Struc fill Placement (250mm) | 2025-12-13 | 2025-12-14
I2S-7688-MP-74.CN.S3.34.14.1 | Culvert ID : E7-RA-427435-1 / Type : 13*1200x450mm RCBC / Ch9933 (20.40m each) | I.CN.34.25270 | CON - Sec.3 - Culvert : E7-RA-427435-1 - FRP Base Slab / Apron Slab / Cut-off Wall | 2025-12-16 | 2025-12-17
I2S-7688-MP-74.CN.S3.34.14.1 | Culvert ID : E7-RA-427435-1 / Type : 13*1200x450mm RCBC / Ch9933 (20.40m each) | I.CN.34.25280 | CON - Sec.3 - Culvert : E7-RA-427435-1 - 7 day Curing | 2025-12-18 | 2026-01-24
I2S-7688-MP-74.CN.S3.34.14.1 | Culvert ID : E7-RA-427435-1 / Type : 13*1200x450mm RCBC / Ch9933 (20.40m each) | I.CN.34.25320 | CON - Sec.3 - Culvert : E7-RA-427435-1 - Place Pre-cast Wingwalls and Stich Pour | 2026-01-28 | 2026-01-28
I2S-7688-MP-74.CN.S3.34.14.1 | Culvert ID : E7-RA-427435-1 / Type : 13*1200x450mm RCBC / Ch9933 (20.40m each) | I.CN.34.32120 | CON - Sec.3 - Culvert : E7-RA-427435-1 - Blinding placement (50mm)
Culvert ID : E7-RA-425840-1 / Type : 60*1050mm HDPE / Ch8860 (20.95m each) |  |  |  | 2025-12-14 | 2026-01-16
I2S-7688-MP-74.CN.S3.34.14.19 | Culvert ID : E7-RA-425840-1 / Type : 60*1050mm HDPE / Ch8860 (20.95m each) | I.CN.34.23080 | CON - Sec.3 - Culvert : E7-RA-425840-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2025-12-17 | 2025-12-18
I2S-7688-MP-74.CN.S3.34.14.19 | Culvert ID : E7-RA-425840-1 / Type : 60*1050mm HDPE / Ch8860 (20.95m each) | I.CN.34.23120 | CON - Sec.3 - Culvert : E7-RA-425840-1 - Headwall installation | 2025-12-19 | 2026-01-07
I2S-7688-MP-74.CN.S3.34.14.19 | Culvert ID : E7-RA-425840-1 / Type : 60*1050mm HDPE / Ch8860 (20.95m each) | I.CN.34.23130 | CON - Sec.3 - Culvert : E7-RA-425840-1 - HDPE / RCP Pipe Lay & Backfill | 2026-01-07 | 2026-01-09
I2S-7688-MP-74.CN.S3.34.14.19 | Culvert ID : E7-RA-425840-1 / Type : 60*1050mm HDPE / Ch8860 (20.95m each) | I.CN.34.23150 | CON - Sec.3 - Culvert : E7-RA-425840-1 - Headwall Stitch Pour | 2026-01-10 | 2026-01-11
I2S-7688-MP-74.CN.S3.34.14.19 | Culvert ID : E7-RA-425840-1 / Type : 60*1050mm HDPE / Ch8860 (20.95m each) | I.CN.34.23160 | CON - Sec.3 - Culvert : E7-RA-425840-1 - Headwall Cut-off Wall Installation (FRP) | 2026-01-12 | 2026-01-13
I2S-7688-MP-74.CN.S3.34.14.19 | Culvert ID : E7-RA-425840-1 / Type : 60*1050mm HDPE / Ch8860 (20.95m each) | I.CN.34.23180 | CON - Sec.3 - Culvert : E7-RA-425840-1 - Construct Scour Protection | 2026-01-14 | 2026-01-16
I2S-7688-MP-74.CN.S3.34.14.19 | Culvert ID : E7-RA-425840-1 / Type : 60*1050mm HDPE / Ch8860 (20.95m each) | I.CN.34.23070 | CON - Sec.3 - Culvert : E7-RA-425840-1 - Site Prep / Detail Excavation | 2025-12-14 | 2025-12-16
043 - Fencing |  |  |  | 2026-03-24 | 2026-09-21
Western Side |  |  |  | 2026-05-04 | 2026-09-21
I2S-7688-MP-74.CN.S3.43.1 | Western Side | I.CN.43.13940 | CON - Sec.3 - Fencing West Side - Ch8840-11400 | 2026-05-04 | 2026-06-09
I2S-7688-MP-74.CN.S3.43.1 | Western Side | I.CN.43.13960 | CON - Sec.3 - Fencing West Side - Ch11400-14450 | 2026-06-10 | 2026-07-23
I2S-7688-MP-74.CN.S3.43.1 | Western Side | I.CN.43.13980 | CON - Sec.3 - Fencing West Side - Ch14450-18450 | 2026-07-24 | 2026-09-21
Eastern Side |  |  |  | 2026-03-24 | 2026-08-10
I2S-7688-MP-74.CN.S3.43.2 | Eastern Side | I.CN.43.13610 | CON - Sec.3 - Fencing East Side - Ch8840-11400 | 2026-03-24 | 2026-04-29
I2S-7688-MP-74.CN.S3.43.2 | Eastern Side | I.CN.43.13950 | CON - Sec.3 - Fencing East Side - Ch11400-14450 | 2026-04-30 | 2026-06-11
I2S-7688-MP-74.CN.S3.43.2 | Eastern Side | I.CN.43.13970 | CON - Sec.3 - Fencing East Side - Ch14450-18450 | 2026-06-12 | 2026-08-10
044 - Roads |  |  |  | 2025-09-21 | 2025-10-04
Dirnaseer Bridge over Road |  |  |  | 2025-09-21 | 2025-10-04
I2S-7688-MP-74.CN.S3.1.1 | Dirnaseer Bridge over Road | I.CN.65.18030 | CON - Sec.3 - Construct Pavement type B sealed - SMZ Placement (350m2) Temp. Road Diversion - Dirnaseer Road | 2025-09-21 | 2025-09-26
I2S-7688-MP-74.CN.S3.1.1 | Dirnaseer Bridge over Road | I.CN.65.18040 | CON - Sec.3 - Construct Pavement type B sealed - Primeseal (350m2) Temp. Road Diversion - Dirnaseer Road | 2025-09-27 | 2025-09-29
I2S-7688-MP-74.CN.S3.1.1 | Dirnaseer Bridge over Road | I.CN.65.18050 | CON - Sec.3 - Construct Pavement type B sealed - Asphalt (350m2) Temp. Road Diversion - Dirnaseer Road | 2025-09-30 | 2025-10-04
045 - Access Roads |  |  |  | 2025-07-14 | 2026-06-16
Access/Temp |  |  |  | 2025-07-14 | 2025-07-17
I2S-7688-MP-74.CN.S3.45.1 | Access/Temp | I.CN.45.14430 | CON - Sec.3 - Gate 4A (11400) - Install Portable traffic sign | 2025-07-14 | 2025-07-17
RMAR Culverts |  |  |  | 2025-12-01 | 2026-06-16
I2S-7688-MP-74.CN.S3.45.2 | RMAR Culverts | I.CN.45.14340 | CON - Sec.3 - Prep RMAR Road - East - 8840 to 11400 | 2025-12-01 | 2025-12-09
I2S-7688-MP-74.CN.S3.45.2 | RMAR Culverts | I.CN.45.14350 | CON - Sec.3 - Prep RMAR Road - East - 11400 to 14450 | 2025-12-10 | 2025-12-18
I2S-7688-MP-74.CN.S3.45.2 | RMAR Culverts | I.CN.45.14360 | CON - Sec.3 - Prep RMAR Road - East - 14450 to 18450 | 2025-12-19 | 2026-01-07
RMAR_CH-15936-01 |  |  |  | 2026-06-12 | 2026-06-16
I2S-7688-MP-74.CN.S3.45.2.4 | RMAR_CH-15936-01 | I.CN.65.18320 | CON - Sec.3 - RMAR Culvert - 015936-01 - Trench Excavation/ Culvert site prep | 2026-06-12 | 2026-06-13
I2S-7688-MP-74.CN.S3.45.2.4 | RMAR_CH-15936-01 | I.CN.65.18330 | CON - Sec.3 - RMAR Culvert - 015936-01 - Install 1 x 600 Sec.3 - Culvert - RCP - 15 off - 36m | 2026-06-14 | 2026-06-14
I2S-7688-MP-74.CN.S3.45.2.4 | RMAR_CH-15936-01 | I.CN.65.18340 | CON - Sec.3 - RMAR Culvert - 015936-01 - Detailed backfill | 2026-06-16 | 2026-06-16
RMAR_Ch-15928-01 |  |  |  | 2026-02-04 | 2026-02-08
I2S-7688-MP-74.CN.S3.45.2.2 | RMAR_Ch-15928-01 | I.CN.65.18310 | CON - Sec.3 - RMAR Culvert - 015928-01 - Trench Excavation/ Culvert site prep | 2026-02-04 | 2026-02-06
I2S-7688-MP-74.CN.S3.45.2.2 | RMAR_Ch-15928-01 | I.CN.65.18350 | CON - Sec.3 - RMAR Culvert - 015928-01 - Install 1 x 600 Sec.3 - Culvert - RCP -17 off 40.6m long | 2026-02-07 | 2026-02-07
I2S-7688-MP-74.CN.S3.45.2.2 | RMAR_Ch-15928-01 | I.CN.65.18360 | CON - Sec.3 - RMAR Culvert - 015928-01 - Detailed backfill | 2026-02-08 | 2026-02-08
050 - Trackwork |  |  |  | 2026-03-14 | 2026-09-14
Mainline |  |  |  | 2026-06-13 | 2026-08-11
Place Bottom Ballast |  |  |  | 2026-06-19 | 2026-07-10
I2S-7688-MP-74.CN.S3.50.14.15 | Place Bottom Ballast | I.CN.50.13520 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 12500 to 13000 (500m) | 2026-06-27 | 2026-06-28
I2S-7688-MP-74.CN.S3.50.14.15 | Place Bottom Ballast | I.CN.50.13530 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 13000 to 13500 (500m) | 2026-06-28 | 2026-06-29
I2S-7688-MP-74.CN.S3.50.14.15 | Place Bottom Ballast | I.CN.50.13540 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 13500 to 14000 (500m) | 2026-06-29 | 2026-06-30
I2S-7688-MP-74.CN.S3.50.14.15 | Place Bottom Ballast | I.CN.50.13550 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 14000 to 14500 (500m) | 2026-06-30 | 2026-07-01
I2S-7688-MP-74.CN.S3.50.14.15 | Place Bottom Ballast | I.CN.50.13560 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 14500 to 15000 (500m) | 2026-07-01 | 2026-07-02
I2S-7688-MP-74.CN.S3.50.14.15 | Place Bottom Ballast | I.CN.50.13570 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 15000 to 15500 (500m) | 2026-07-02 | 2026-07-03
I2S-7688-MP-74.CN.S3.50.14.15 | Place Bottom Ballast | I.CN.50.13580 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 15500 to 16000 (500m) | 2026-07-03 | 2026-07-04
I2S-7688-MP-74.CN.S3.50.14.15 | Place Bottom Ballast | I.CN.50.13590 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 16000 to 16500 (500m) | 2026-07-04 | 2026-07-06
I2S-7688-MP-74.CN.S3.50.14.15 | Place Bottom Ballast | I.CN.50.13600 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 16500 to 17000 (500m) | 2026-07-06 | 2026-07-07
I2S-7688-MP-74.CN.S3.50.14.15 | Place Bottom Ballast | I.CN.50.13610 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 17000 to 17500 (500m) | 2026-07-07 | 2026-07-08
I2S-7688-MP-74.CN.S3.50.14.15 | Place Bottom Ballast | I.CN.50.13620 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 17500 to 18000 (500m) | 2026-07-08 | 2026-07-09
I2S-7688-MP-74.CN.S3.50.14.15 | Place Bottom Ballast | I.CN.50.14420 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 18000 to 18500 (500m) | 2026-07-09 | 2026-07-10
I2S-7688-MP-74.CN.S3.50.14.15 | Place Bottom Ballast | I.CN.50.13440 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 8841 to 9000 (159m) | 2026-06-19 | 2026-06-19
I2S-7688-MP-74.CN.S3.50.14.15 | Place Bottom Ballast | I.CN.50.13450 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 9000 to 9500 (500m) | 2026-06-19 | 2026-06-20
I2S-7688-MP-74.CN.S3.50.14.15 | Place Bottom Ballast | I.CN.50.13460 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 9500 to 10000 (500m) | 2026-06-20 | 2026-06-21
I2S-7688-MP-74.CN.S3.50.14.15 | Place Bottom Ballast | I.CN.50.13470 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 10000 to 10500 (500m) | 2026-06-21 | 2026-06-22
I2S-7688-MP-74.CN.S3.50.14.15 | Place Bottom Ballast | I.CN.50.13480 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 10500 to 11000 (500m) | 2026-06-22 | 2026-06-23
I2S-7688-MP-74.CN.S3.50.14.15 | Place Bottom Ballast | I.CN.50.13490 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 11000 to 11500 (500m) | 2026-06-23 | 2026-06-24
I2S-7688-MP-74.CN.S3.50.14.15 | Place Bottom Ballast | I.CN.50.13500 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 11500 to 12000 (500m) | 2026-06-24 | 2026-06-26
I2S-7688-MP-74.CN.S3.50.14.15 | Place Bottom Ballast | I.CN.50.13510 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 12000 to 12500 (500m) | 2026-06-26 | 2026-06-27
Sleeper Distribution |  |  |  | 2026-06-13 | 2026-07-11
I2S-7688-MP-74.CN.S3.50.14.1 | Sleeper Distribution | I.CN.50.4880 | CON - Sec.3 - Sleeper Distribution - 860m/day - 15400 to 16090 (860m) | 2026-07-04 | 2026-07-06
I2S-7688-MP-74.CN.S3.50.14.1 | Sleeper Distribution | I.CN.50.4890 | CON - Sec.3 - Sleeper Distribution - 860m/day - 16090 to 16780 (860m) | 2026-07-08 | 2026-07-09
I2S-7688-MP-74.CN.S3.50.14.1 | Sleeper Distribution | I.CN.50.4900 | CON - Sec.3 - Sleeper Distribution - 860m/day - 16780 to 17470 (860m) | 2026-07-09 | 2026-07-10
I2S-7688-MP-74.CN.S3.50.14.1 | Sleeper Distribution | I.CN.50.4910 | CON - Sec.3 - Sleeper Distribution - 860m/day - 17470 to 18160 (860m) | 2026-07-10 | 2026-07-11
I2S-7688-MP-74.CN.S3.50.14.1 | Sleeper Distribution | I.CN.50.14320 | CON - Sec.3 - Intermediate Sleeper Stockpiles - Sec.3 | 2026-06-13 | 2026-06-13
I2S-7688-MP-74.CN.S3.50.14.1 | Sleeper Distribution | I.CN.50.4780 | CON - Sec.3 - Sleeper Distribution - 860m/day - 8500 to 9190 (860m) | 2026-06-22 | 2026-06-23
I2S-7688-MP-74.CN.S3.50.14.1 | Sleeper Distribution | I.CN.50.4790 | CON - Sec.3 - Sleeper Distribution - 860m/day - 9190 to 9880 (860m) | 2026-06-23 | 2026-06-24
I2S-7688-MP-74.CN.S3.50.14.1 | Sleeper Distribution | I.CN.50.4800 | CON - Sec.3 - Sleeper Distribution - 860m/day - 9880 to 10570 (860m) | 2026-06-24 | 2026-06-26
I2S-7688-MP-74.CN.S3.50.14.1 | Sleeper Distribution | I.CN.50.4810 | CON - Sec.3 - Sleeper Distribution - 860m/day - 10570 to 11260 (860m) | 2026-06-26 | 2026-06-27
I2S-7688-MP-74.CN.S3.50.14.1 | Sleeper Distribution | I.CN.50.4840 | CON - Sec.3 - Sleeper Distribution - 860m/day - 12640 to 13330 (860m) | 2026-06-29 | 2026-06-30
I2S-7688-MP-74.CN.S3.50.14.1 | Sleeper Distribution | I.CN.50.4850 | CON - Sec.3 - Sleeper Distribution - 860m/day - 13330 to 14020 (860m) | 2026-06-30 | 2026-07-01
I2S-7688-MP-74.CN.S3.50.14.1 | Sleeper Distribution | I.CN.50.4860 | CON - Sec.3 - Sleeper Distribution - 860m/day - 14020 to 14710 (860m) | 2026-07-01 | 2026-07-02
I2S-7688-MP-74.CN.S3.50.14.1 | Sleeper Distribution | I.CN.50.4870 | CON - Sec.3 - Sleeper Distribution - 860m/day - 14710 to 15400 (860m) | 2026-07-02 | 2026-07-03
I2S-7688-MP-74.CN.S3.50.14.1 | Sleeper Distribution | I.CN.50.4820 | CON - Sec.3 - Sleeper Distribution - 860m/day - 11260 to 11950 (860m) | 2026-06-27 | 2026-06-28
I2S-7688-MP-74.CN.S3.50.14.1 | Sleeper Distribution | I.CN.50.4830 | CON - Sec.3 - Sleeper Distribution - 860m/day - 11950 to 12640 (860m) | 2026-06-28 | 2026-06-29
Sleeper Laying |  |  |  | 2026-06-26 | 2026-07-12
I2S-7688-MP-74.CN.S3.50.14.3 | Sleeper Laying | I.CN.50.3880 | CON - Sec.3 - Sleeper Laying - 800m/day - 11420 to 12220 | 2026-06-29 | 2026-06-30
I2S-7688-MP-74.CN.S3.50.14.3 | Sleeper Laying | I.CN.50.3890 | CON - Sec.3 - Sleeper Laying - 800m/day - 12220 to 13020 | 2026-06-30 | 2026-07-01
I2S-7688-MP-74.CN.S3.50.14.3 | Sleeper Laying | I.CN.50.3900 | CON - Sec.3 - Sleeper Laying - 800m/day - 13020 to 13820 | 2026-07-01 | 2026-07-02
I2S-7688-MP-74.CN.S3.50.14.3 | Sleeper Laying | I.CN.50.3910 | CON - Sec.3 - Sleeper Laying - 800m/day - 13820 to 14620 | 2026-07-02 | 2026-07-03
I2S-7688-MP-74.CN.S3.50.14.3 | Sleeper Laying | I.CN.50.3920 | CON - Sec.3 - Sleeper Laying - 800m/day - 14620 to 15420 | 2026-07-03 | 2026-07-04
I2S-7688-MP-74.CN.S3.50.14.3 | Sleeper Laying | I.CN.50.3930 | CON - Sec.3 - Sleeper Laying - 800m/day - 15420 to 16220 | 2026-07-04 | 2026-07-06
I2S-7688-MP-74.CN.S3.50.14.3 | Sleeper Laying | I.CN.50.3940 | CON - Sec.3 - Sleeper Laying - 800m/day - 16220 to 17020 | 2026-07-06 | 2026-07-07
I2S-7688-MP-74.CN.S3.50.14.3 | Sleeper Laying | I.CN.50.3960 | CON - Sec.3 - Sleeper Laying - 800m/day - 17020 to 17820 | 2026-07-10 | 2026-07-11
I2S-7688-MP-74.CN.S3.50.14.3 | Sleeper Laying | I.CN.50.3970 | CON - Sec.3 - Sleeper Laying - 800m/day - 17820 to 18620 | 2026-07-11 | 2026-07-12
I2S-7688-MP-74.CN.S3.50.14.3 | Sleeper Laying | I.CN.50.3850 | CON - Sec.3 - Sleeper Laying - 800m/day - 9020 to 9820 | 2026-06-26 | 2026-06-27
I2S-7688-MP-74.CN.S3.50.14.3 | Sleeper Laying | I.CN.50.3860 | CON - Sec.3 - Sleeper Laying - 800m/day - 9820 to 10620 | 2026-06-27 | 2026-06-28
I2S-7688-MP-74.CN.S3.50.14.3 | Sleeper Laying | I.CN.50.3870 | CON - Sec.3 - Sleeper Laying - 800m/day - 10620 to 11420 | 2026-06-28 | 2026-06-29
Rail Distribution |  |  |  | 2026-06-28 | 2026-07-13
I2S-7688-MP-74.CN.S3.50.14.2 | Rail Distribution | I.CN.50.4420 | CON - Sec.3 - Rail Distribution - 1000m/day - 14080 to 15070 | 2026-07-06 | 2026-07-07
I2S-7688-MP-74.CN.S3.50.14.2 | Rail Distribution | I.CN.50.4430 | CON - Sec.3 - Rail Distribution - 1000m/day - 15070 to 16060 | 2026-07-07 | 2026-07-08
I2S-7688-MP-74.CN.S3.50.14.2 | Rail Distribution | I.CN.50.4440 | CON - Sec.3 - Rail Distribution - 1000m/day - 16060 to 17050 | 2026-07-09 | 2026-07-10
I2S-7688-MP-74.CN.S3.50.14.2 | Rail Distribution | I.CN.50.4450 | CON - Sec.3 - Rail Distribution - 1000m/day - 17050 to 18040 | 2026-07-12 | 2026-07-13
I2S-7688-MP-74.CN.S3.50.14.2 | Rail Distribution | I.CN.50.4370 | CON - Sec.3 - Rail Distribution - 1000m/day - 9130 to 10120 | 2026-06-28 | 2026-06-29
I2S-7688-MP-74.CN.S3.50.14.2 | Rail Distribution | I.CN.50.4380 | CON - Sec.3 - Rail Distribution - 1000m/day - 10120 to 11110 | 2026-06-29 | 2026-06-30
I2S-7688-MP-74.CN.S3.50.14.2 | Rail Distribution | I.CN.50.4390 | CON - Sec.3 - Rail Distribution - 1000m/day - 11110 to 12100 | 2026-06-30 | 2026-07-01
I2S-7688-MP-74.CN.S3.50.14.2 | Rail Distribution | I.CN.50.4400 | CON - Sec.3 - Rail Distribution - 1000m/day - 12100 to 13090 | 2026-07-01 | 2026-07-02
I2S-7688-MP-74.CN.S3.50.14.2 | Rail Distribution | I.CN.50.4410 | CON - Sec.3 - Rail Distribution - 1000m/day - 13090 to 14080 | 2026-07-04 | 2026-07-06
Rail Laying |  |  |  | 2026-07-01 | 2026-07-16
I2S-7688-MP-74.CN.S3.50.14.4 | Rail Laying | I.CN.50.3340 | CON - Sec.3 - Rail Laying - 550m/day - 11740 to 12460 | 2026-07-06 | 2026-07-07
I2S-7688-MP-74.CN.S3.50.14.4 | Rail Laying | I.CN.50.3350 | CON - Sec.3 - Rail Laying - 550m/day - 12460 to 13180 | 2026-07-07 | 2026-07-08
I2S-7688-MP-74.CN.S3.50.14.4 | Rail Laying | I.CN.50.3360 | CON - Sec.3 - Rail Laying - 550m/day - 13180 to 13900 | 2026-07-08 | 2026-07-09
I2S-7688-MP-74.CN.S3.50.14.4 | Rail Laying | I.CN.50.3370 | CON - Sec.3 - Rail Laying - 550m/day - 13900 to 14620 | 2026-07-09 | 2026-07-10
I2S-7688-MP-74.CN.S3.50.14.4 | Rail Laying | I.CN.50.3380 | CON - Sec.3 - Rail Laying - 550m/day - 14620 to 15430 | 2026-07-10 | 2026-07-11
I2S-7688-MP-74.CN.S3.50.14.4 | Rail Laying | I.CN.50.3390 | CON - Sec.3 - Rail Laying - 550m/day - 15340 to 16060 | 2026-07-11 | 2026-07-12
I2S-7688-MP-74.CN.S3.50.14.4 | Rail Laying | I.CN.50.3400 | CON - Sec.3 - Rail Laying - 550m/day - 16060 to 16780 | 2026-07-12 | 2026-07-13
I2S-7688-MP-74.CN.S3.50.14.4 | Rail Laying | I.CN.50.3410 | CON - Sec.3 - Rail Laying - 550m/day - 16780 to 17500 | 2026-07-13 | 2026-07-14
I2S-7688-MP-74.CN.S3.50.14.4 | Rail Laying | I.CN.50.3420 | CON - Sec.3 - Rail Laying - 550m/day - 17500 to 18220 | 2026-07-14 | 2026-07-16
I2S-7688-MP-74.CN.S3.50.14.4 | Rail Laying | I.CN.50.3300 | CON - Sec.3 - Rail Laying - 550m/day - 8860 to 9580 | 2026-07-01 | 2026-07-02
I2S-7688-MP-74.CN.S3.50.14.4 | Rail Laying | I.CN.50.3310 | CON - Sec.3 - Rail Laying - 550m/day - 9580 to 10300 | 2026-07-02 | 2026-07-03
I2S-7688-MP-74.CN.S3.50.14.4 | Rail Laying | I.CN.50.3320 | CON - Sec.3 - Rail Laying - 550m/day - 10300 to 11020 | 2026-07-03 | 2026-07-04
I2S-7688-MP-74.CN.S3.50.14.4 | Rail Laying | I.CN.50.3330 | CON - Sec.3 - Rail Laying - 550m/day - 11020 to 11740 | 2026-07-04 | 2026-07-06
Flash Butt Welding and clip up |  |  |  | 2026-07-03 | 2026-07-23
I2S-7688-MP-74.CN.S3.50.14.5 | Flash Butt Welding and clip up | I.CN.50.2890 | CON - Sec.3 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 9130 to 10120 | 2026-07-03 | 2026-07-06
I2S-7688-MP-74.CN.S3.50.14.5 | Flash Butt Welding and clip up | I.CN.50.2900 | CON - Sec.3 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 10120 to 11110 | 2026-07-06 | 2026-07-08
I2S-7688-MP-74.CN.S3.50.14.5 | Flash Butt Welding and clip up | I.CN.50.2910 | CON - Sec.3 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 11110 to 12100 | 2026-07-08 | 2026-07-10
I2S-7688-MP-74.CN.S3.50.14.5 | Flash Butt Welding and clip up | I.CN.50.2920 | CON - Sec.3 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 12100 to 13090 | 2026-07-10 | 2026-07-12
I2S-7688-MP-74.CN.S3.50.14.5 | Flash Butt Welding and clip up | I.CN.50.2930 | CON - Sec.3 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 13090 to 14080 | 2026-07-12 | 2026-07-14
I2S-7688-MP-74.CN.S3.50.14.5 | Flash Butt Welding and clip up | I.CN.50.2940 | CON - Sec.3 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 14080 to 15070 | 2026-07-14 | 2026-07-17
I2S-7688-MP-74.CN.S3.50.14.5 | Flash Butt Welding and clip up | I.CN.50.2950 | CON - Sec.3 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 15070 to 16060 | 2026-07-17 | 2026-07-19
I2S-7688-MP-74.CN.S3.50.14.5 | Flash Butt Welding and clip up | I.CN.50.2960 | CON - Sec.3 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 16060 to 17050 | 2026-07-19 | 2026-07-21
I2S-7688-MP-74.CN.S3.50.14.5 | Flash Butt Welding and clip up | I.CN.50.2970 | CON - Sec.3 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 17050 to 18040 | 2026-07-21 | 2026-07-23
Place Top Ballast Initial |  |  |  | 2026-07-16 | 2026-07-24
I2S-7688-MP-74.CN.S3.50.14.6 | Place Top Ballast Initial | I.CN.50.2620 | CON - Sec.3 - Place Top Ballast Initial - 1500m/day - 9220 to 10720 | 2026-07-16 | 2026-07-17
I2S-7688-MP-74.CN.S3.50.14.6 | Place Top Ballast Initial | I.CN.50.2630 | CON - Sec.3 - Place Top Ballast Initial - 1500m/day - 10720 to 12220 | 2026-07-17 | 2026-07-18
I2S-7688-MP-74.CN.S3.50.14.6 | Place Top Ballast Initial | I.CN.50.2640 | CON - Sec.3 - Place Top Ballast Initial - 1500m/day - 12220 to 13720 | 2026-07-18 | 2026-07-19
I2S-7688-MP-74.CN.S3.50.14.6 | Place Top Ballast Initial | I.CN.50.2670 | CON - Sec.3 - Place Top Ballast Initial - 1500m/day - 16720 to 18220 | 2026-07-23 | 2026-07-24
I2S-7688-MP-74.CN.S3.50.14.6 | Place Top Ballast Initial | I.CN.50.2650 | CON - Sec.3 - Place Top Ballast Initial - 1500m/day - 13720 to 15220 | 2026-07-19 | 2026-07-20
I2S-7688-MP-74.CN.S3.50.14.6 | Place Top Ballast Initial | I.CN.50.2660 | CON - Sec.3 - Place Top Ballast Initial - 1500m/day - 15220 to 16720 | 2026-07-20 | 2026-07-21
Traverse & Level GEDO |  |  |  | 2026-06-24 | 2026-06-27
I2S-7688-MP-74.CN.S3.50.14.14 | Traverse & Level GEDO | I.CN.50.18180 | CON - Traverse and level Gedo Control - 8220 to 12220 | 2026-06-24 | 2026-06-24
I2S-7688-MP-74.CN.S3.50.14.14 | Traverse & Level GEDO | I.CN.50.18190 | CON - Traverse and level Gedo Control - 12220 to 16220 | 2026-06-26 | 2026-06-26
I2S-7688-MP-74.CN.S3.50.14.14 | Traverse & Level GEDO | I.CN.50.18200 | CON - Traverse and level Gedo Control - 16220 to 18000 | 2026-06-27 | 2026-06-27
Surfacing Firsts |  |  |  | 2026-07-18 | 2026-07-24
I2S-7688-MP-74.CN.S3.50.14.7 | Surfacing Firsts | I.CN.50.2520 | CON - Sec.3 - Surfacing Firsts - 4000m/day - 8220 to 12220 | 2026-07-18 | 2026-07-19
I2S-7688-MP-74.CN.S3.50.14.7 | Surfacing Firsts | I.CN.50.2530 | CON - Sec.3 - Surfacing Firsts - 4000m/day - 12220 to 16220 | 2026-07-21 | 2026-07-22
I2S-7688-MP-74.CN.S3.50.14.7 | Surfacing Firsts | I.CN.50.2540 | CON - Sec.3 - Surfacing Firsts - 4000m/day - 16220 to 18000 | 2026-07-24 | 2026-07-24
Surfacing Seconds |  |  |  | 2026-07-19 | 2026-07-26
I2S-7688-MP-74.CN.S3.50.14.8 | Surfacing Seconds | I.CN.50.2430 | CON - Sec.3 - Surfacing Seconds - 4000m/day - 8220 to 12220 | 2026-07-19 | 2026-07-20
I2S-7688-MP-74.CN.S3.50.14.8 | Surfacing Seconds | I.CN.50.2440 | CON - Sec.3 - Surfacing Seconds - 4000m/day - 12220 to 16220 | 2026-07-22 | 2026-07-23
I2S-7688-MP-74.CN.S3.50.14.8 | Surfacing Seconds | I.CN.50.2450 | CON - Sec.3 - Surfacing Seconds - 4000m/day - 16220 to 18000 | 2026-07-26 | 2026-07-26
Top Ballast Finals |  |  |  | 2026-07-20 | 2026-07-27
I2S-7688-MP-74.CN.S3.50.14.9 | Top Ballast Finals | I.CN.50.2310 | CON - Sec.3 - Top Ballast Finals - 3000m/day - 9000 to 12000 | 2026-07-20 | 2026-07-21
I2S-7688-MP-74.CN.S3.50.14.9 | Top Ballast Finals | I.CN.50.2320 | CON - Sec.3 - Top Ballast Finals - 3000m/day - 12000 to 15000 | 2026-07-23 | 2026-07-24
I2S-7688-MP-74.CN.S3.50.14.9 | Top Ballast Finals | I.CN.50.2330 | CON - Sec.3 - Top Ballast Finals - 3000m/day - 15000 to 18000 | 2026-07-26 | 2026-07-27
Surfacing Final |  |  |  | 2026-07-21 | 2026-07-28
I2S-7688-MP-74.CN.S3.50.14.10 | Surfacing Final | I.CN.50.2240 | CON - Sec.3 - Surfacing Final - 6000m/day - 12000 to 18000 | 2026-07-27 | 2026-07-28
I2S-7688-MP-74.CN.S3.50.14.10 | Surfacing Final | I.CN.50.15150 | CON - Sec.3 - Surfacing Final - 6000m/day - 9000 to 12000 | 2026-07-21 | 2026-07-22
Destressing |  |  |  | 2026-07-20 | 2026-08-03
I2S-7688-MP-74.CN.S3.50.14.11 | Destressing | I.CN.50.2040 | CON - Sec.3 - Destressing - 1200m/day - 16800 to 18500 | 2026-08-02 | 2026-08-03
I2S-7688-MP-74.CN.S3.50.14.11 | Destressing | I.CN.50.1970 | CON - Sec.3 - Destressing - 1200m/day - 8400 to 9600 | 2026-07-20 | 2026-07-21
I2S-7688-MP-74.CN.S3.50.14.11 | Destressing | I.CN.50.1980 | CON - Sec.3 - Destressing - 1200m/day - 9600 to 10800 | 2026-07-21 | 2026-07-22
I2S-7688-MP-74.CN.S3.50.14.11 | Destressing | I.CN.50.1990 | CON - Sec.3 - Destressing - 1200m/day - 10800 to 12000 | 2026-07-22 | 2026-07-23
I2S-7688-MP-74.CN.S3.50.14.11 | Destressing | I.CN.50.2000 | CON - Sec.3 - Destressing - 1200m/day - 12000 to 13200 | 2026-07-28 | 2026-07-29
I2S-7688-MP-74.CN.S3.50.14.11 | Destressing | I.CN.50.2010 | CON - Sec.3 - Destressing - 1200m/day - 13200 to 14400 | 2026-07-29 | 2026-07-31
I2S-7688-MP-74.CN.S3.50.14.11 | Destressing | I.CN.50.2020 | CON - Sec.3 - Destressing - 1200m/day - 14400 to 15600 | 2026-07-31 | 2026-08-01
I2S-7688-MP-74.CN.S3.50.14.11 | Destressing | I.CN.50.2030 | CON - Sec.3 - Destressing - 1200m/day - 15600 to 16800 | 2026-08-01 | 2026-08-02
Corrections + Signage + Rubber Xings |  |  |  | 2026-07-26 | 2026-08-03
I2S-7688-MP-74.CN.S3.50.14.12 | Corrections + Signage + Rubber Xings | I.CN.50.1750 | CON - Sec.3 - Corrections + Signage - 2000m/day - 10000 - 12000 | 2026-07-26 | 2026-07-27
I2S-7688-MP-74.CN.S3.50.14.12 | Corrections + Signage + Rubber Xings | I.CN.50.1760 | CON - Sec.3 - Corrections + Signage - 2000m/day - 12000 - 14000 | 2026-07-27 | 2026-07-28
I2S-7688-MP-74.CN.S3.50.14.12 | Corrections + Signage + Rubber Xings | I.CN.50.1770 | CON - Sec.3 - Corrections + Signage - 2000m/day - 14000 - 16000 | 2026-08-01 | 2026-08-02
I2S-7688-MP-74.CN.S3.50.14.12 | Corrections + Signage + Rubber Xings | I.CN.50.1780 | CON - Sec.3 - Corrections + Signage - 2000m/day - 16000 - 18000 | 2026-08-02 | 2026-08-03
Track Joint Inspection |  |  |  | 2026-08-01 | 2026-08-11
I2S-7688-MP-74.CN.S3.50.14.13 | Track Joint Inspection | I.CN.50.1650 | CON - Sec.3 - Track Joint Inspection - 5000m/day - 15000 - 18500 | 2026-08-11 | 2026-08-11
I2S-7688-MP-74.CN.S3.50.14.13 | Track Joint Inspection | I.CN.50.1640 | CON - Sec.3 - Track Joint Inspection - 5000m/day - 10000 - 15000 | 2026-08-01 | 2026-08-02
Loop 9151 to 11259 |  |  |  | 2026-03-14 | 2026-09-01
Place Bottom Ballast |  |  |  | 2026-08-02 | 2026-08-08
I2S-7688-MP-74.CN.S3.50.1.15 | Place Bottom Ballast | I.CN.50.16290 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 9151 to 9651 (500m) - Loop | 2026-08-02 | 2026-08-03
I2S-7688-MP-74.CN.S3.50.1.15 | Place Bottom Ballast | I.CN.50.16300 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 9651 to 10000 (500m) - Loop | 2026-08-03 | 2026-08-04
I2S-7688-MP-74.CN.S3.50.1.15 | Place Bottom Ballast | I.CN.50.16310 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 10000 to 10500 (500m) - Loop | 2026-08-04 | 2026-08-06
I2S-7688-MP-74.CN.S3.50.1.15 | Place Bottom Ballast | I.CN.50.16320 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 10500 to 11000 (500m) - Loop | 2026-08-06 | 2026-08-07
I2S-7688-MP-74.CN.S3.50.1.15 | Place Bottom Ballast | I.CN.50.17650 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 11000 to 11260 (260m) - Loop | 2026-08-07 | 2026-08-08
Sleeper Distribution |  |  |  | 2026-08-02 | 2026-08-10
I2S-7688-MP-74.CN.S3.50.1.1 | Sleeper Distribution | I.CN.50.16150 | CON - Sec.3 - Sleeper Distribution - 860m/day - 9151 to 11259 - Loop - Day 1 | 2026-08-07 | 2026-08-08
I2S-7688-MP-74.CN.S3.50.1.1 | Sleeper Distribution | I.CN.50.16160 | CON - Sec.3 - Sleeper Distribution - 860m/day - 9151 to 11259 - Loop - Day 2 | 2026-08-08 | 2026-08-09
I2S-7688-MP-74.CN.S3.50.1.1 | Sleeper Distribution | I.CN.50.16170 | CON - Sec.3 - Sleeper Distribution - 860m/day - 9151 to 11259 - Loop - Day 3 | 2026-08-09 | 2026-08-10
I2S-7688-MP-74.CN.S3.50.1.1 | Sleeper Distribution | I.CN.50.16480 | CON - Sec.3 - Intermediate Sleeper Stockpiles - Loop | 2026-08-02 | 2026-08-03
Sleeper Laying |  |  |  | 2026-08-10 | 2026-08-14
I2S-7688-MP-74.CN.S3.50.1.3 | Sleeper Laying | I.CN.50.15930 | CON - Sec.3 - Sleeper Laying - 800m/day - 9151 to 9951 Loop | 2026-08-10 | 2026-08-11
I2S-7688-MP-74.CN.S3.50.1.3 | Sleeper Laying | I.CN.50.15940 | CON - Sec.3 - Sleeper Laying - 800m/day - 9951 to 10251 - Loop | 2026-08-11 | 2026-08-12
I2S-7688-MP-74.CN.S3.50.1.3 | Sleeper Laying | I.CN.50.15950 | CON - Sec.3 - Sleeper Laying - 800m/day - 10251 to 10801 - Loop | 2026-08-12 | 2026-08-13
I2S-7688-MP-74.CN.S3.50.1.3 | Sleeper Laying | I.CN.50.15970 | CON - Sec.3 - Sleeper Laying - 800m/day - 10801 to 11259 - Loop | 2026-08-13 | 2026-08-14
Rail Distribution |  |  |  | 2026-08-12 | 2026-08-16
I2S-7688-MP-74.CN.S3.50.1.2 | Rail Distribution | I.CN.50.16060 | CON - Sec.3 - Rail Distribution - 1000m/day - 9151 to 9841 - Loop | 2026-08-12 | 2026-08-13
I2S-7688-MP-74.CN.S3.50.1.2 | Rail Distribution | I.CN.50.16070 | CON - Sec.3 - Rail Distribution - 1000m/day - 10120 - 11110 - Loop - start | 2026-08-13 | 2026-08-14
I2S-7688-MP-74.CN.S3.50.1.2 | Rail Distribution | I.CN.50.16080 | CON - Sec.3 - Rail Distribution - 1000m/day - 10120 - 11110 - Loop - finish | 2026-08-14 | 2026-08-16
Rail Laying |  |  |  | 2026-03-14 | 2026-08-20
I2S-7688-MP-74.CN.S3.50.1.4 | Rail Laying | I.CN.50.15800 | CON - Sec.3 - Rail Laying - 550m/day - 9151 to 9871 - Loop | 2026-08-14 | 2026-08-16
I2S-7688-MP-74.CN.S3.50.1.4 | Rail Laying | I.CN.50.15810 | CON - Sec.3 - Rail Laying - 550m/day - 9871 to 10591 - Loop | 2026-08-16 | 2026-08-17
I2S-7688-MP-74.CN.S3.50.1.4 | Rail Laying | I.CN.50.15820 | CON - Sec.3 - Rail Laying - 550m/day - 10300 to 11020 - Loop | 2026-08-17 | 2026-08-18
I2S-7688-MP-74.CN.S3.50.1.4 | Rail Laying | I.CN.50.15830 | CON - Sec.3 - Rail Laying - 550m/day - 11020 to 11740 - Loop | 2026-08-18 | 2026-08-19
I2S-7688-MP-74.CN.S3.50.1.4 | Rail Laying | I.CN.50.18640 | CON - Sec.3 - Lift in Turnout - 1 in 18 R1200 - Loop | 2026-08-18 | 2026-08-19
I2S-7688-MP-74.CN.S3.50.1.4 | Rail Laying | I.CN.50.18650 | CON - Sec.3 - Lift in Turnout - 1 in 10.5 R250 - Loop | 2026-08-18 | 2026-08-20
I2S-7688-MP-74.CN.S3.50.1.4 | Rail Laying | I.CN.50.18670 | CON - Sec.3 - Possession - Deliver Rail / Turnout - 1 in 18 R1200 - Loop | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.CN.S3.50.1.4 | Rail Laying | I.CN.50.18680 | CON - Sec.3 - Possession - Deliver Rail / Turnout - 1 in 10.5 R250 - Loop | 2026-03-14 | 2026-03-14
Flash Butt Welding and clip up |  |  |  | 2026-08-17 | 2026-08-22
I2S-7688-MP-74.CN.S3.50.1.5 | Flash Butt Welding and clip up | I.CN.50.15710 | CON - Sec.3 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 9151 to 10141 - Loop | 2026-08-17 | 2026-08-19
I2S-7688-MP-74.CN.S3.50.1.5 | Flash Butt Welding and clip up | I.CN.50.15720 | CON - Sec.3 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 10141 to 11259 - Loop | 2026-08-20 | 2026-08-22
Place Top Ballast Initial |  |  |  | 2026-08-22 | 2026-08-24
I2S-7688-MP-74.CN.S3.50.1.6 | Place Top Ballast Initial | I.CN.50.15650 | CON - Sec.3 - Place Top Ballast Initial - 1500m/day - 9151 to 10651 - Loop | 2026-08-22 | 2026-08-23
I2S-7688-MP-74.CN.S3.50.1.6 | Place Top Ballast Initial | I.CN.50.15660 | CON - Sec.3 - Place Top Ballast Initial - 1500m/day - 10720 to 12220 - Loop | 2026-08-23 | 2026-08-24
Traverse & Level GEDO |  |  |  | 2026-06-28 | 2026-06-29
I2S-7688-MP-74.CN.S3.50.1.14 | Traverse & Level GEDO | I.CN.50.18170 | CON - Sec.3 - Traverse and level Gedo Control - 9151 to 11259 - Loop | 2026-06-28 | 2026-06-29
Surfacing Firsts |  |  |  | 2026-08-24 | 2026-08-26
I2S-7688-MP-74.CN.S3.50.1.7 | Surfacing Firsts | I.CN.50.15620 | CON - Sec.3 - Surfacing Firsts - 4000m/day - 9151 to 11259 - Loop | 2026-08-24 | 2026-08-26
Surfacing Seconds |  |  |  | 2026-08-26 | 2026-08-27
I2S-7688-MP-74.CN.S3.50.1.8 | Surfacing Seconds | I.CN.50.15590 | CON - Sec.3 - Surfacing Seconds - 4000m/day - 9151 to 11259 - Loop | 2026-08-26 | 2026-08-27
Top Ballast Finals |  |  |  | 2026-08-27 | 2026-08-28
I2S-7688-MP-74.CN.S3.50.1.9 | Top Ballast Finals | I.CN.50.15560 | CON - Sec.3 - Top Ballast Finals - 3000m/day - 9151 to 11259 - Loop | 2026-08-27 | 2026-08-28
Surfacing Final |  |  |  | 2026-08-28 | 2026-08-29
I2S-7688-MP-74.CN.S3.50.1.10 | Surfacing Final | I.CN.50.16520 | CON - Sec.3 - Surfacing Final - 6000m/day - 9151 to 11259 - Loop | 2026-08-28 | 2026-08-29
Destressing |  |  |  | 2026-08-29 | 2026-08-31
I2S-7688-MP-74.CN.S3.50.1.11 | Destressing | I.CN.50.15470 | CON - Sec.3 - Destressing - 1200m/day - 9151 to 10351 - Loop | 2026-08-29 | 2026-08-30
I2S-7688-MP-74.CN.S3.50.1.11 | Destressing | I.CN.50.15480 | CON - Sec.3 - Destressing - 1200m/day - 10351 to 11259 - Loop | 2026-08-30 | 2026-08-31
Corrections + Signage + Rubber Xings |  |  |  | 2026-08-29 | 2026-08-30
I2S-7688-MP-74.CN.S3.50.1.12 | Corrections + Signage + Rubber Xings | I.CN.50.15430 | CON - Sec.3 - Corrections + Signage - 2000m/day - 9151 to 11259 - Loop | 2026-08-29 | 2026-08-30
Track Joint Inspection |  |  |  | 2026-08-31 | 2026-09-01
I2S-7688-MP-74.CN.S3.50.1.13 | Track Joint Inspection | I.CN.50.15410 | CON - Sec.3 - Track Joint Inspection - 5000m/day - 9151 to 11259 - Loop | 2026-08-31 | 2026-09-01
Sidings 10296 to 10989 |  |  |  | 2026-03-16 | 2026-09-14
Place Bottom Ballast |  |  |  | 2026-08-28 | 2026-08-30
I2S-7688-MP-74.CN.S3.50.2.15 | Place Bottom Ballast | I.CN.50.17410 | CON - Sec.3 - Place Bottom Ballast - 500m/day - 10296 to 10646 (350m) - Sidings | 2026-08-28 | 2026-08-29
I2S-7688-MP-74.CN.S3.50.2.15 | Place Bottom Ballast | I.CN.50.17420 | CON - Sec.3 - Place Bottom Ballast - 500m/day- 10646 to 10989 (343m) - Sidings | 2026-08-29 | 2026-08-30
Sleeper Distribution |  |  |  | 2026-08-29 | 2026-08-31
I2S-7688-MP-74.CN.S3.50.2.1 | Sleeper Distribution | I.CN.50.17600 | CON - Sec.3 - Intermediate Sleeper Stockpiles - Sidings | 2026-08-29 | 2026-08-30
I2S-7688-MP-74.CN.S3.50.2.1 | Sleeper Distribution | I.CN.50.17270 | CON - Sec.3 - Sleeper Distribution - 860m/day - 10296 to 10989 (693m) - Sidings | 2026-08-30 | 2026-08-31
Sleeper Laying |  |  |  | 2026-08-31 | 2026-09-01
I2S-7688-MP-74.CN.S3.50.2.3 | Sleeper Laying | I.CN.50.17050 | CON - Sec.3 - Sleeper Laying - 800m/day - 10296 to 10989 - Sidings | 2026-08-31 | 2026-09-01
Rail Distribution |  |  |  | 2026-09-01 | 2026-09-02
I2S-7688-MP-74.CN.S3.50.2.2 | Rail Distribution | I.CN.50.17180 | CON - Sec.3 - Rail Distribution - 1000m/day - 10296 to 10989 Sidings | 2026-09-01 | 2026-09-02
Rail Laying |  |  |  | 2026-03-16 | 2026-09-04
I2S-7688-MP-74.CN.S3.50.2.4 | Rail Laying | I.CN.50.16920 | CON - Sec.3 - Rail Laying - 550m/day - 10296 to 10989 - Sidings | 2026-09-02 | 2026-09-03
I2S-7688-MP-74.CN.S3.50.2.4 | Rail Laying | I.CN.50.18630 | CON - Sec.3 - Lift in Turnout - 1 in 18 R1200 (PEM/LEM or Crane) - Sidings | 2026-09-02 | 2026-09-04
I2S-7688-MP-74.CN.S3.50.2.4 | Rail Laying | I.CN.50.18690 | CON - Sec.3 - Possession - Deliver Rail / Turnout - 1 in 18 R1200 Sidings (PEM/LEM or Crane) | 2026-03-16 | 2026-03-16
Flash Butt Welding and clip up |  |  |  | 2026-09-04 | 2026-09-07
I2S-7688-MP-74.CN.S3.50.2.5 | Flash Butt Welding and clip up | I.CN.50.16830 | CON - Sec.3 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 10296 to 10989 - Sidings | 2026-09-04 | 2026-09-07
Place Top Ballast Initial |  |  |  | 2026-09-07 | 2026-09-08
I2S-7688-MP-74.CN.S3.50.2.6 | Place Top Ballast Initial | I.CN.50.16770 | CON - Sec.3 - Place Top Ballast Initial - 1500m/day - 10296 to 10989 - Sidings | 2026-09-07 | 2026-09-08
Traverse & Level GEDO |  |  |  | 2026-06-29 | 2026-06-30
I2S-7688-MP-74.CN.S3.50.2.14 | Traverse & Level GEDO | I.CN.50.18160 | CON - Traverse and level Gedo Control - 10296 to 10989 - Sidings | 2026-06-29 | 2026-06-30
Surfacing Firsts |  |  |  | 2026-09-08 | 2026-09-09
I2S-7688-MP-74.CN.S3.50.2.7 | Surfacing Firsts | I.CN.50.16740 | CON - Sec.3 - Surfacing Firsts - 4000m/day - 10296 to 10989 - Sidings | 2026-09-08 | 2026-09-09
Surfacing Seconds |  |  |  | 2026-09-09 | 2026-09-10
I2S-7688-MP-74.CN.S3.50.2.8 | Surfacing Seconds | I.CN.50.16710 | CON - Sec.3 - Surfacing Seconds - 4000m/day - 10296 to 10989 - Sidings | 2026-09-09 | 2026-09-10
Top Ballast Finals |  |  |  | 2026-09-10 | 2026-09-11
I2S-7688-MP-74.CN.S3.50.2.9 | Top Ballast Finals | I.CN.50.16680 | CON - Sec.3 - Top Ballast Finals - 3000m/day - 10296 to 10989 - Sidings | 2026-09-10 | 2026-09-11
Surfacing Final |  |  |  | 2026-09-11 | 2026-09-12
I2S-7688-MP-74.CN.S3.50.2.10 | Surfacing Final | I.CN.50.17640 | CON - Sec.3 - Surfacing Final - 6000m/day - 10296 to 10989 - Sidings | 2026-09-11 | 2026-09-12
Destressing |  |  |  | 2026-09-12 | 2026-09-13
I2S-7688-MP-74.CN.S3.50.2.11 | Destressing | I.CN.50.16590 | CON - Sec.3 - Destressing - 1200m/day - 10296 to 10989 - Sidings | 2026-09-12 | 2026-09-13
Corrections + Signage + Rubber Xings |  |  |  | 2026-09-13 | 2026-09-14
I2S-7688-MP-74.CN.S3.50.2.12 | Corrections + Signage + Rubber Xings | I.CN.50.16550 | CON - Sec.3 - Corrections + Signage - 2000m/day - 10296 to 10989 - Sidings | 2026-09-13 | 2026-09-14
Track Joint Inspection |  |  |  | 2026-09-13 | 2026-09-14
I2S-7688-MP-74.CN.S3.50.2.13 | Track Joint Inspection | I.CN.50.16530 | CON - Sec.3 - Track Joint Inspection - 5000m/day - 10296 to 10989 - Sidings | 2026-09-13 | 2026-09-14
062 - Bridges |  |  |  | 2025-07-12 | 2026-05-30
Dirnaseer Bridge over Road - BR704 - 1500 SUPER-T (ARTC) |  |  |  | 2025-07-12 | 2026-05-28
Preliminaries and Establishment |  |  |  | 2025-07-12 | 2025-09-20
I2S-7688-MP-74.CN.S3.62.1.1 | Preliminaries and Establishment | I.CN.62.15890 | CON - Sec.3 - Dirnaseer Rd Br - Bridge site prep /Temp diversion / Fence/Road Barriers | 2025-09-09 | 2025-09-20
I2S-7688-MP-74.CN.S3.62.1.1 | Preliminaries and Establishment | I.CN.62.15900 | CON - Sec.3 - Dirnaseer Rd Br - Construct site access | 2025-09-09 | 2025-09-10
I2S-7688-MP-74.CN.S3.62.1.1 | Preliminaries and Establishment | I.CN.62.15990 | CON - Sec.3 - Dirnaseer Rd Br - Construct laydown area /Causeway (inc pipes) | 2025-09-17 | 2025-09-20
I2S-7688-MP-74.CN.S3.62.1.1 | Preliminaries and Establishment | I.CN.11.13100 | CON - Sec.3 - Dirnaseer Rd Br - Traffic management set up & prep (concrete barriers and demob) | 2025-07-12 | 2025-07-13
Piling |  |  |  | 2025-09-21 | 2025-12-11
Platforms |  |  |  | 2025-09-21 | 2025-09-28
I2S-7688-MP-74.CN.S3.62.1.2.1 | Platforms | I.CN.62.15950 | CON - Sec.3 - Dirnaseer Rd Br - Excavate platform for piling pad | 2025-09-21 | 2025-09-27
I2S-7688-MP-74.CN.S3.62.1.2.1 | Platforms | I.CN.62.16000 | CON - Sec.3 - Dirnaseer Rd Br - Place and test platform | 2025-09-28 | 2025-09-28
Drill Piles |  |  |  | 2025-12-03 | 2025-12-11
I2S-7688-MP-74.CN.S3.62.1.2.3 | Drill Piles | I.CN.62.15960 | CON - Sec.3 - Dirnaseer Rd Br - Demobilise piling rig | 2025-12-11 | 2025-12-11
I2S-7688-MP-74.CN.S3.62.1.2.3 | Drill Piles | I.CN.62.16010 | CON - Sec.3 - Dirnaseer Rd Br - Mobilise piling rig | 2025-12-03 | 2025-12-03
I2S-7688-MP-74.CN.S3.62.1.2.3 | Drill Piles | I.CN.62.16020 | CON - Sec.3 - Dirnaseer Rd Br - abutment piling - of 4 x 1200mm dia bored concrete piles (incl Rig float 1d) | 2025-12-04 | 2025-12-08
I2S-7688-MP-74.CN.S3.62.1.2.3 | Drill Piles | I.CN.62.19570 | CON - Sec.3 - Dirnaseer Rd Br - pier piling consist of 2 x 900mm dia bored concrete piles | 2025-12-09 | 2025-12-10
I2S-7688-MP-74.CN.S3.62.1.2.3 | Drill Piles | I.CN.62.22190 | CON - Sec.3 - Dirnaseer Rd Br - Pour and Finish Concrete
I2S-7688-MP-74.CN.S3.62.1.2.3 | Drill Piles | I.CN.62.23060 | CON - Sec.3 - Dirnaseer Rd Br - abutment piling - of 4 x 1200mm dia bored concrete piles - Milestone
I2S-7688-MP-74.CN.S3.62.1.2.3 | Drill Piles | I.CN.62.23100 | CON - Sec.3 - Dirnaseer Rd Br - Pile extensions + sleeves
Piers |  |  |  | 2025-12-12 | 2026-01-12
I2S-7688-MP-74.CN.S3.62.1.3 | Piers | I.CN.62.16060 | CON - Sec.3 - Dirnaseer Rd Br - Detailed Earthworks - Pier | 2025-12-12 | 2025-12-16
I2S-7688-MP-74.CN.S3.62.1.3 | Piers | I.CN.62.21860 | CON - Sec.3 - Dirnaseer Rd Br - FRP - Pier Columns (x2) | 2025-12-22 | 2026-01-07
I2S-7688-MP-74.CN.S3.62.1.3 | Piers | I.CN.62.21870 | CON - Sec.3 - Dirnaseer Rd Br - FRP - Pier Headstock | 2026-01-08 | 2026-01-12
I2S-7688-MP-74.CN.S3.62.1.3 | Piers | I.CN.62.22200 | CON - Sec.3 - Dirnaseer Rd Br - FRP - Restraint Block
I2S-7688-MP-74.CN.S3.62.1.3 | Piers | I.CN.62.22210 | CON - Sec.3 - Dirnaseer Rd Br - FRP - Bearing Mortar Pad
Abutments |  |  |  | 2025-12-17 | 2026-03-24
Site Prep |  |  |  | 2025-12-17 | 2025-12-18
I2S-7688-MP-74.CN.S3.62.1.7.8 | Site Prep | I.CN.62.19590 | CON - Sec.3 - Dirnaseer Rd Br - Site prep - Re-Wall | 2025-12-17 | 2025-12-18
North |  |  |  | 2025-12-19 | 2026-03-19
I2S-7688-MP-74.CN.S3.62.1.7.1 | North | I.CN.62.22240 | CON - Sec.3 - Dirnaseer Rd Br - FRP - Bearing Mortar Pads - North Abutment
I2S-7688-MP-74.CN.S3.62.1.7.1 | North | I.CN.62.16070 | CON - Sec.3 - Dirnaseer Rd Br - Detailed Earthworks - North Abutment | 2025-12-19 | 2025-12-22
I2S-7688-MP-74.CN.S3.62.1.7.1 | North | I.CN.62.16090 | CON - Sec.3 - Dirnaseer Rd Br - FRP - Cill Beam - North Abutment | 2026-01-20 | 2026-01-24
I2S-7688-MP-74.CN.S3.62.1.7.1 | North | I.CN.62.16120 | CON - Sec.3 - Dirnaseer Rd Br - FRP - Wing Walls - North Abutment | 2026-01-13 | 2026-01-19
I2S-7688-MP-74.CN.S3.62.1.7.1 | North | I.CN.62.20500 | CON - Sec.3 - Dirnaseer Rd Br - FRP - Back Wall - North Abutment | 2026-01-26 | 2026-01-30
I2S-7688-MP-74.CN.S3.62.1.7.1 | North | I.CN.62.20520 | CON - Sec.3 - Dirnaseer Rd Br - RE Wall Construction & EW Fill - North Abutment | 2026-03-09 | 2026-03-19
I2S-7688-MP-74.CN.S3.62.1.7.1 | North | I.CN.62.22230 | CON - Sec.3 - Dirnaseer Rd Br - FRP - Restraint Block - North Abutment
South |  |  |  | 2026-01-26 | 2026-03-24
I2S-7688-MP-74.CN.S3.62.1.7.2 | South | I.CN.62.16130 | CON - Sec.3 - Dirnaseer Rd Br - FRP - Back Wall - South Abutment | 2026-01-31 | 2026-02-04
I2S-7688-MP-74.CN.S3.62.1.7.2 | South | I.CN.62.20460 | CON - Sec.3 - Dirnaseer Rd Br - FRP - Cill Beam - South Abutment | 2026-01-26 | 2026-01-30
I2S-7688-MP-74.CN.S3.62.1.7.2 | South | I.CN.62.20530 | CON - Sec.3 - Dirnaseer Rd Br - RE Wall Construction & EW Fill - South Abutment | 2026-03-20 | 2026-03-24
I2S-7688-MP-74.CN.S3.62.1.7.2 | South | I.CN.62.21830 | CON - Sec.3 - Dirnaseer Rd Br - FRP - Restraint Block - South Abutment | 2026-02-19 | 2026-02-24
I2S-7688-MP-74.CN.S3.62.1.7.2 | South | I.CN.62.22220 | CON - Sec.3 - Dirnaseer Rd Br - Detailed Earthworks - South Abutment
I2S-7688-MP-74.CN.S3.62.1.7.2 | South | I.CN.62.22250 | CON - Sec.3 - Dirnaseer Rd Br - FRP - Wing Walls - South Abutment
I2S-7688-MP-74.CN.S3.62.1.7.2 | South | I.CN.62.22260 | CON - Sec.3 - Dirnaseer Rd Br - FRP - Bearing Mortar Pads - South Abutment
Superstructure |  |  |  | 2025-12-12 | 2026-03-21
I2S-7688-MP-74.CN.S3.62.1.4 | Superstructure | I.CN.62.16210 | CON - Sec.3 - Dirnaseer Rd Br - Crane pads for crane lift | 2026-01-20 | 2026-01-21
I2S-7688-MP-74.CN.S3.62.1.4 | Superstructure | I.CN.62.16220 | CON - Sec.3 - Dirnaseer Rd Br - Install bridge bearings (x8) | 2026-03-11 | 2026-03-18
I2S-7688-MP-74.CN.S3.62.1.4 | Superstructure | I.CN.62.16230 | CON - Sec.3 - Dirnaseer Rd Br - Install/Lift of super T girders, 23 metres long x4 (2 spans) | 2026-03-19 | 2026-03-21
I2S-7688-MP-74.CN.S3.62.1.4 | Superstructure | I.CN.62.22270 | CON - Sec.3 - Dirnaseer Rd Br - Install access walkways
I2S-7688-MP-74.CN.S3.62.1.4 | Superstructure | I.CN.62.21840 | CON - Sec.3 - Dirnaseer Rd Br - FRP - Cross girders (x3) | 2026-02-26 | 2026-03-03
I2S-7688-MP-74.CN.S3.62.1.4 | Superstructure | I.CN.62.15920 | CON - Sec.3 - Dirnaseer Rd Br - Delivery /QA of super T girders, 23 metres long x4 (2 spans) | 2025-12-12 | 2025-12-13
Approach Slab / Deck |  |  |  | 2026-03-22 | 2026-05-01
I2S-7688-MP-74.CN.S3.62.1.6 | Approach Slab / Deck | I.CN.62.21790 | CON - Sec.3 - Dirnaseer Rd Br - FRP - Wing Walls - North side 2 No | 2026-04-21 | 2026-04-26
I2S-7688-MP-74.CN.S3.62.1.6 | Approach Slab / Deck | I.CN.62.21800 | CON - Sec.3 - Dirnaseer Rd Br - FRP - Wing Walls - South side 2 No | 2026-04-27 | 2026-05-01
I2S-7688-MP-74.CN.S3.62.1.6 | Approach Slab / Deck | I.CN.62.21810 | CON - Sec.3 - Dirnaseer Rd Br - FRP - Derailment kerb | 2026-03-29 | 2026-04-01
I2S-7688-MP-74.CN.S3.62.1.6 | Approach Slab / Deck | I.CN.62.20550 | CON - Sec.3 - Dirnaseer Rd Br - FRP - Bridge Deck | 2026-03-22 | 2026-03-26
I2S-7688-MP-74.CN.S3.62.1.6 | Approach Slab / Deck | I.CN.62.20560 | CON - Sec.3 - Dirnaseer Rd Br - FRP - Approach Slab - North side | 2026-04-02 | 2026-04-07
I2S-7688-MP-74.CN.S3.62.1.6 | Approach Slab / Deck | I.CN.62.20570 | CON - Sec.3 - Dirnaseer Rd Br - FRP - Approach Slab - South side | 2026-04-08 | 2026-04-12
Bridge Finishing Works |  |  |  | 2025-07-14 | 2026-05-28
I2S-7688-MP-74.CN.S3.62.1.5 | Bridge Finishing Works | I.CN.62.20690 | CON - Sec.3 - Dirnaseer Rd Br - Install Handrail - North /south | 2026-05-26 | 2026-05-28
I2S-7688-MP-74.CN.S3.62.1.5 | Bridge Finishing Works | I.CN.62.19310 | CON - Sec.3 - Dirnaseer Rd Br - Bridge Completion |  | 2026-05-28
I2S-7688-MP-74.CN.S3.62.1.5 | Bridge Finishing Works | I.CN.62.20540 | CON - Sec.3 - Dirnaseer Rd Br - Install Handrails MSS Retaining Walls | 2026-03-26 | 2026-03-28
I2S-7688-MP-74.CN.S3.62.1.5 | Bridge Finishing Works | I.CN.62.20580 | CON - Sec.3 - Dirnaseer Rd Br - Precast Concrete Parapet Panels | 2026-04-13 | 2026-04-15
I2S-7688-MP-74.CN.S3.62.1.5 | Bridge Finishing Works | I.CN.62.20590 | CON - Sec.3 - Dirnaseer Rd Br - Concrete - Handle, Place, Finish and Cure Footpath / steps - 5m3 | 2026-04-16 | 2026-04-18
I2S-7688-MP-74.CN.S3.62.1.5 | Bridge Finishing Works | I.CN.11.13840 | CON - Sec.3 - Dirnaseer Rd Br - Traffic management Demob | 2025-07-14 | 2025-07-14
I2S-7688-MP-74.CN.S3.62.1.5 | Bridge Finishing Works | I.CN.62.22280 | CON - Sec.3 - Dirnaseer Rd Br - Install CSR Ducting
I2S-7688-MP-74.CN.S3.62.1.5 | Bridge Finishing Works | I.CN.62.22840 | CON - Sec.3 - Dirnaseer Rd Br - Install Scour Protection
I2S-7688-MP-74.CN.S3.62.1.5 | Bridge Finishing Works | I.CN.62.22850 | CON - Sec.3 - Dirnaseer Rd Br - Batter Slopes & Install "Nylex Cordrain" fixed to vertical face of ballast walls
Run Boundary Creek Bridge - BR703 - 1500 SUPER-T (ARTC) |  |  |  | 2025-11-23 | 2026-05-30
Preliminaries and Establishment |  |  |  | 2025-11-23 | 2025-12-06
I2S-7688-MP-74.CN.S3.62.2.1 | Preliminaries and Establishment | I.CN.62.15470 | CON - Sec.3 - Run Boundary Ck Br - Bridge site prep /Temp Fence/Road Barriers | 2025-11-23 | 2025-11-27
I2S-7688-MP-74.CN.S3.62.2.1 | Preliminaries and Establishment | I.CN.62.15480 | CON - Sec.3 - Run Boundary Ck Br - Construct site access | 2025-11-28 | 2025-12-01
I2S-7688-MP-74.CN.S3.62.2.1 | Preliminaries and Establishment | I.CN.62.15570 | CON - Sec.3 - Run Boundary Ck Br - Construct laydown area /Causeway (inc pipes) | 2025-12-02 | 2025-12-06
Piling |  |  |  | 2025-12-07 | 2026-01-31
Platforms |  |  |  | 2025-12-07 | 2025-12-11
I2S-7688-MP-74.CN.S3.62.2.2.1 | Platforms | I.CN.62.15530 | CON - Sec.3 - Run Boundary Ck Br - Excavate platform for piling pad | 2025-12-07 | 2025-12-09
I2S-7688-MP-74.CN.S3.62.2.2.1 | Platforms | I.CN.62.15580 | CON - Sec.3 - Run Boundary Ck Br - Place and test platform | 2025-12-10 | 2025-12-11
Drill Piles |  |  |  | 2026-01-13 | 2026-01-26
I2S-7688-MP-74.CN.S3.62.2.2.3 | Drill Piles | I.CN.62.15600 | CON - Sec.3 - Run Boundary Ck Br - abutment piling consists of 4 x 900mm dia bored concrete piles | 2026-01-14 | 2026-01-18
I2S-7688-MP-74.CN.S3.62.2.2.3 | Drill Piles | I.CN.62.19670 | CON - Sec.3 - Run Boundary Ck Br - pier piling consist of 6 x 1200mm dia bored concrete piles | 2026-01-19 | 2026-01-24
I2S-7688-MP-74.CN.S3.62.2.2.3 | Drill Piles | I.CN.62.15540 | CON - Sec.3 - Run Boundary Ck Br - Demobilise piling rig | 2026-01-26 | 2026-01-26
I2S-7688-MP-74.CN.S3.62.2.2.3 | Drill Piles | I.CN.62.15590 | CON - Sec.3 - Run Boundary Ck Br - Mobilise piling rig | 2026-01-13 | 2026-01-13
I2S-7688-MP-74.CN.S3.62.2.2.3 | Drill Piles | I.CN.62.23070 | CON - Sec.3 - Run Boundary Ck Br - abutment piling consists of 4 x 900mm dia bored concrete piles - Milestone
Piles Concrete |  |  |  | 2026-01-27 | 2026-01-31
I2S-7688-MP-74.CN.S3.62.2.2.4 | Piles Concrete | I.CN.62.15550 | CON - Sec.3 - Run Boundary Ck Br - Place pile concrete | 2026-01-27 | 2026-01-31
Piers |  |  |  | 2026-02-01 | 2026-02-22
I2S-7688-MP-74.CN.S3.62.2.6 | Piers | I.CN.62.15640 | CON - Sec.3 - Run Boundary Ck Br - FRP - Columns (x3) | 2026-02-01 | 2026-02-07
I2S-7688-MP-74.CN.S3.62.2.6 | Piers | I.CN.62.15650 | CON - Sec.3 - Run Boundary Ck Br - FRP - Headstock (x3) | 2026-02-08 | 2026-02-13
I2S-7688-MP-74.CN.S3.62.2.6 | Piers | I.CN.62.15690 | CON - Sec.3 - Run Boundary Ck Br - Cill Beam - North Abutment - 7m3 | 2026-02-18 | 2026-02-22
I2S-7688-MP-74.CN.S3.62.2.6 | Piers | I.CN.62.22560 | CON - Sec.3 - Run Boundary Ck Br - Detailed Earthworks
I2S-7688-MP-74.CN.S3.62.2.6 | Piers | I.CN.62.22570 | CON - Sec.3 - Run Boundary Ck Br - FRP - Retsraint Blocks (x3)
I2S-7688-MP-74.CN.S3.62.2.6 | Piers | I.CN.62.22580 | CON - Sec.3 - Run Boundary Ck Br - FRP - Bearing Mortar Pads (x3)
Abutments |  |  |  | 2026-02-12 | 2026-03-26
Set Up |  |  |  | 2026-02-12 | 2026-02-13
I2S-7688-MP-74.CN.S3.62.2.7.8 | Set Up | I.CN.62.15670 | CON - Sec.3 - Run Boundary Ck Br - Site prep Abutment Footings / Blinding | 2026-02-12 | 2026-02-13
North |  |  |  | 2026-02-14 | 2026-03-26
I2S-7688-MP-74.CN.S3.62.2.7.1 | North | I.CN.62.15680 | CON - Sec.3 - Run Boundary Ck Br - Detailed Earthworks - North Abutment | 2026-02-14 | 2026-02-17
I2S-7688-MP-74.CN.S3.62.2.7.1 | North | I.CN.62.15700 | CON - Sec.3 - Run Boundary Ck Br - FRP - Bearing Mortar Pad - North Abutment | 2026-03-10 | 2026-03-19
I2S-7688-MP-74.CN.S3.62.2.7.1 | North | I.CN.62.20710 | CON - Sec.3 - Run Boundary Ck Br - FRP - Restraint Blocks - North Abutment | 2026-03-20 | 2026-03-26
I2S-7688-MP-74.CN.S3.62.2.7.1 | North | I.CN.62.20740 | CON - Sec.3 - Run Boundary Ck Br - FRP - Back Wall - North Abutment | 2026-03-01 | 2026-03-04
I2S-7688-MP-74.CN.S3.62.2.7.1 | North | I.CN.62.22600 | CON - Sec.3 - Run Boundary Ck Br - FRP - Wing Wall - North Abutment
I2S-7688-MP-74.CN.S3.62.2.7.1 | North | I.CN.62.22620 | CON - Sec.3 - Run Boundary Ck Br - FRP - Cill Beam - North Abutment
South |  |  |  | 2026-02-23 | 2026-03-09
I2S-7688-MP-74.CN.S3.62.2.7.2 | South | I.CN.62.15710 | CON - Sec.3 - Run Boundary Ck Br - FRP - Cill Beam - South Abutment | 2026-02-23 | 2026-02-28
I2S-7688-MP-74.CN.S3.62.2.7.2 | South | I.CN.62.20700 | CON - Sec.3 - Run Boundary Ck Br - FRP - Back Wall - South Abutment | 2026-03-06 | 2026-03-09
I2S-7688-MP-74.CN.S3.62.2.7.2 | South | I.CN.62.22590 | CON - Sec.3 - Run Boundary Ck Br - Detailed Earthworks - South Abutment
I2S-7688-MP-74.CN.S3.62.2.7.2 | South | I.CN.62.22650 | CON - Sec.3 - Run Boundary Ck Br - FRP - Bearing Mortar Pad - South Abutment
I2S-7688-MP-74.CN.S3.62.2.7.2 | South | I.CN.62.22640 | CON - Sec.3 - Run Boundary Ck Br - FRP - Restraint Blocks - South Abutment
I2S-7688-MP-74.CN.S3.62.2.7.2 | South | I.CN.62.22630 | CON - Sec.3 - Run Boundary Ck Br - FRP - Wing Wall - South Abutment
Superstructure |  |  |  | 2026-02-01 | 2026-05-30
I2S-7688-MP-74.CN.S3.62.2.4 | Superstructure | I.CN.62.15760 | CON - Sec.3 - Run Boundary Ck Br - Install handrail raking/horizontal | 2026-05-24 | 2026-05-27
I2S-7688-MP-74.CN.S3.62.2.4 | Superstructure | I.CN.62.15770 | CON - Sec.3 - Run Boundary Ck Br - Install access walkways | 2026-05-28 | 2026-05-30
I2S-7688-MP-74.CN.S3.62.2.4 | Superstructure | I.CN.62.15500 | CON - Sec.3 - Run Boundary Ck Br - Delivery /QA of super T girders, 23 metres long x4 (2 spans) | 2026-02-01 | 2026-02-02
I2S-7688-MP-74.CN.S3.62.2.4 | Superstructure | I.CN.62.15800 | CON - Sec.3 - Run Boundary Ck Br - Install bridge bearings | 2026-04-09 | 2026-04-10
I2S-7688-MP-74.CN.S3.62.2.4 | Superstructure | I.CN.62.15810 | CON - Sec.3 - Run Boundary Ck Br - Install/Lift of super T girders, 23 metres long x4 | 2026-04-17 | 2026-04-19
I2S-7688-MP-74.CN.S3.62.2.4 | Superstructure | I.CN.62.22660 | CON - Sec.3 - Run Boundary Ck Br - Crane Pads for Crane Lift
Approach Slab / Deck |  |  |  | 2026-03-27 | 2026-05-19
I2S-7688-MP-74.CN.S3.62.2.3 | Approach Slab / Deck | I.CN.62.21880 | CON - Sec.3 - Run Boundary Ck Br - FRP - Derailment kerb | 2026-05-05 | 2026-05-11
I2S-7688-MP-74.CN.S3.62.2.3 | Approach Slab / Deck | I.CN.62.21890 | CON - Sec.3 - Run Boundary Ck Br - FRP - Cross girder - South | 2026-04-26 | 2026-04-29
I2S-7688-MP-74.CN.S3.62.2.3 | Approach Slab / Deck | I.CN.62.15660 | CON - Sec.3 - Run Boundary Ck Br - Approach Slab - South | 2026-04-30 | 2026-05-04
I2S-7688-MP-74.CN.S3.62.2.3 | Approach Slab / Deck | I.CN.62.15720 | CON - Sec.3 - Run Boundary Ck Br - Bridge Deck | 2026-03-27 | 2026-04-08
I2S-7688-MP-74.CN.S3.62.2.3 | Approach Slab / Deck | I.CN.62.15860 | CON - Sec.3 - Run Boundary Ck Br - FRP - Cross girder - North | 2026-04-21 | 2026-04-24
I2S-7688-MP-74.CN.S3.62.2.3 | Approach Slab / Deck | I.CN.62.20720 | CON - Sec.3 - Run Boundary Ck Br - Approach Slab - North | 2026-04-09 | 2026-04-12
I2S-7688-MP-74.CN.S3.62.2.3 | Approach Slab / Deck | I.CN.62.20770 | CON - Sec.3 - Run Boundary Ck Br - Wing Walls - North | 2026-04-13 | 2026-04-20
I2S-7688-MP-74.CN.S3.62.2.3 | Approach Slab / Deck | I.CN.62.20780 | CON - Sec.3 - Run Boundary Ck Br - Wing Walls - South | 2026-05-12 | 2026-05-19
Bridge Finishing Works |  |  |  | 2026-05-12 | 2026-05-30
I2S-7688-MP-74.CN.S3.62.2.5 | Bridge Finishing Works | I.CN.62.15520 | CON - Sec.3 - Run Boundary Ck Br - Batter Slopes & Install "Nylex Cordrain" fixed to vertical face of ballast walls | 2026-05-12 | 2026-05-17
I2S-7688-MP-74.CN.S3.62.2.5 | Bridge Finishing Works | I.CN.62.15780 | CON - Sec.3 - Run Boundary Ck Br - FRP Footpath/Steps | 2026-05-20 | 2026-05-27
I2S-7688-MP-74.CN.S3.62.2.5 | Bridge Finishing Works | I.CN.62.19300 | CON - Sec.3 - Run Boundary Ck Br - Completion |  | 2026-05-30
I2S-7688-MP-74.CN.S3.62.2.5 | Bridge Finishing Works | I.CN.62.22670 | CON - Sec.3 - Run Boundary Ck Br - Install Scour Protection
I2S-7688-MP-74.CN.S3.62.2.5 | Bridge Finishing Works | I.CN.62.22680 | CON - Sec.3 - Run Boundary Ck Br - Install CSR Ducting
I2S-7688-MP-74.CN.S3.62.2.5 | Bridge Finishing Works | I.CN.62.22690 | CON - Sec.3 - Run Boundary Ck Br - Install Handrails
065 - Crossings |  |  |  | 2025-11-07 | 2026-09-27
Fauna Crossing |  |  |  | 2026-09-22 | 2026-09-27
I2S-7688-MP-74.CN.S3.65.5 | Fauna Crossing | I.CN.65.12880 | CON - Sec.3 - Install fauna crossing, [2 x poles foundations /cure - CH10200] | 2026-09-22 | 2026-09-23
I2S-7688-MP-74.CN.S3.65.5 | Fauna Crossing | I.CN.65.12890 | CON - Sec.3 - Install fauna crossing, [2 x poles foundations /cure - CH13600] | 2026-09-24 | 2026-09-26
I2S-7688-MP-74.CN.S3.65.5 | Fauna Crossing | I.CN.65.17900 | CON - Sec.3 - Install fauna crossing, [2 x poles with rope bridge - CH10200] | 2026-09-24 | 2026-09-24
I2S-7688-MP-74.CN.S3.65.5 | Fauna Crossing | I.CN.65.17910 | CON - Sec.3 - Install fauna crossing, [2 x poles with rope bridge - CH13600] | 2026-09-27 | 2026-09-27
Public LX - Unnamed Road (PU15950) - Passive / Junee LGA - RX-2 |  |  |  | 2025-11-23 | 2026-01-29
Civils |  |  |  | 2026-01-16 | 2026-01-22
I2S-7688-MP-74.CN.S3.65.3.1 | Civils | I.CN.65.15050 | CON - Sec.3 - Public LX - Unnamed Road (PU15950) - Civil Works complete |  | 2026-01-22
I2S-7688-MP-74.CN.S3.65.3.1 | Civils | I.CN.11.14210 | CON - Sec.3 - Public LX - Unnamed Road (PU15950) - Clear and Grub | 2026-01-16 | 2026-01-16
Earthworks/Drainage |  |  |  | 2025-11-23 | 2026-01-22
Culvert ID : E7-RD-433452-1 / Type : 1*450mm HDPE / Ch15954 (27.52m each)
I2S-7688-MP-74.CN.S3.65.3.5.19 | Culvert ID : E7-RD-433452-1 / Type : 1*450mm HDPE / Ch15954 (27.52m each) | I.CN.34.28200 | CON - Sec.3 - Culvert : E7-RD-433452-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S3.65.3.5.19 | Culvert ID : E7-RD-433452-1 / Type : 1*450mm HDPE / Ch15954 (27.52m each) | I.CN.34.28130 | CON - Sec.3 - Culvert : E7-RD-433452-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S3.65.3.5.19 | Culvert ID : E7-RD-433452-1 / Type : 1*450mm HDPE / Ch15954 (27.52m each) | I.CN.34.28140 | CON - Sec.3 - Culvert : E7-RD-433452-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S3.65.3.5.19 | Culvert ID : E7-RD-433452-1 / Type : 1*450mm HDPE / Ch15954 (27.52m each) | I.CN.34.28160 | CON - Sec.3 - Culvert : E7-RD-433452-1 - Construct Scour Protection
I2S-7688-MP-74.CN.S3.65.3.5.19 | Culvert ID : E7-RD-433452-1 / Type : 1*450mm HDPE / Ch15954 (27.52m each) | I.CN.34.28170 | CON - Sec.3 - Culvert : E7-RD-433452-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S3.65.3.5.19 | Culvert ID : E7-RD-433452-1 / Type : 1*450mm HDPE / Ch15954 (27.52m each) | I.CN.34.28180 | CON - Sec.3 - Culvert : E7-RD-433452-1 - Foundation Treatment
I2S-7688-MP-74.CN.S3.65.3.5.19 | Culvert ID : E7-RD-433452-1 / Type : 1*450mm HDPE / Ch15954 (27.52m each) | I.CN.34.28190 | CON - Sec.3 - Culvert : E7-RD-433452-1 - Headwall installation
Culvert ID : E7-RD-433450-1 / Type : 4*900mm HDPE / Ch15953 (29.72m each) |  |  |  | 2025-11-23 | 2025-12-10
I2S-7688-MP-74.CN.S3.65.3.5.13 | Culvert ID : E7-RD-433450-1 / Type : 4*900mm HDPE / Ch15953 (29.72m each) | I.CN.34.26840 | CON - Sec.3 - Culvert : E7-RD-433450-1 - HDPE / RCP Pipe Lay & Backfill | 2025-11-29 | 2025-11-30
I2S-7688-MP-74.CN.S3.65.3.5.13 | Culvert ID : E7-RD-433450-1 / Type : 4*900mm HDPE / Ch15953 (29.72m each) | I.CN.34.26870 | CON - Sec.3 - Culvert : E7-RD-433450-1 - Headwall Stitch Pour | 2025-12-03 | 2025-12-03
I2S-7688-MP-74.CN.S3.65.3.5.13 | Culvert ID : E7-RD-433450-1 / Type : 4*900mm HDPE / Ch15953 (29.72m each) | I.CN.34.26880 | CON - Sec.3 - Culvert : E7-RD-433450-1 - Headwall Cut-off Wall Installation (FRP) | 2025-12-04 | 2025-12-06
I2S-7688-MP-74.CN.S3.65.3.5.13 | Culvert ID : E7-RD-433450-1 / Type : 4*900mm HDPE / Ch15953 (29.72m each) | I.CN.34.26900 | CON - Sec.3 - Culvert : E7-RD-433450-1 - Construct Scour Protection | 2025-12-09 | 2025-12-10
I2S-7688-MP-74.CN.S3.65.3.5.13 | Culvert ID : E7-RD-433450-1 / Type : 4*900mm HDPE / Ch15953 (29.72m each) | I.CN.34.26790 | CON - Sec.3 - Culvert : E7-RD-433450-1 - Site Prep / Detail Excavation | 2025-11-23 | 2025-11-24
I2S-7688-MP-74.CN.S3.65.3.5.13 | Culvert ID : E7-RD-433450-1 / Type : 4*900mm HDPE / Ch15953 (29.72m each) | I.CN.34.26800 | CON - Sec.3 - Culvert : E7-RD-433450-1 - Foundation Treatment | 2025-11-26 | 2025-11-27
I2S-7688-MP-74.CN.S3.65.3.5.13 | Culvert ID : E7-RD-433450-1 / Type : 4*900mm HDPE / Ch15953 (29.72m each) | I.CN.34.26830 | CON - Sec.3 - Culvert : E7-RD-433450-1 - Headwall installation | 2025-11-28 | 2025-11-28
Culvert ID : E2-RD-433473-1 / Type : 3*450mm RCP4 / Ch15957 (12.26m each) |  |  |  | 2026-01-17 | 2026-01-22
I2S-7688-MP-74.CN.S3.65.3.5.1 | Culvert ID : E2-RD-433473-1 / Type : 3*450mm RCP4 / Ch15957 (12.26m each) | I.CN.65.14950 | CON - Sec.3 - Public LX - Culvert : E2-RD-433473-1 - Site Prep / Detail Excavation | 2026-01-17 | 2026-01-17
I2S-7688-MP-74.CN.S3.65.3.5.1 | Culvert ID : E2-RD-433473-1 / Type : 3*450mm RCP4 / Ch15957 (12.26m each) | I.CN.65.14960 | CON - Sec.3 - Public LX - Culvert : E2-RD-433473-1 - Foundation Treatment | 2026-01-18 | 2026-01-18
I2S-7688-MP-74.CN.S3.65.3.5.1 | Culvert ID : E2-RD-433473-1 / Type : 3*450mm RCP4 / Ch15957 (12.26m each) | I.CN.65.14970 | CON - Sec.3 - Public LX - Culvert : E2-RD-433473-1 - Headwall Cut-off Wall Installation (FRP) | 2026-01-19 | 2026-01-19
I2S-7688-MP-74.CN.S3.65.3.5.1 | Culvert ID : E2-RD-433473-1 / Type : 3*450mm RCP4 / Ch15957 (12.26m each) | I.CN.65.16540 | CON - Sec.3 - Public LX - Culvert : E2-RD-433473-1 - Construct Scour Protection | 2026-01-22 | 2026-01-22
I2S-7688-MP-74.CN.S3.65.3.5.1 | Culvert ID : E2-RD-433473-1 / Type : 3*450mm RCP4 / Ch15957 (12.26m each) | I.CN.65.19091 | CON - Sec.3 - Public LX - Culvert : E2-RD-433473-1 - Headwall installation
I2S-7688-MP-74.CN.S3.65.3.5.1 | Culvert ID : E2-RD-433473-1 / Type : 3*450mm RCP4 / Ch15957 (12.26m each) | I.CN.65.19101 | CON - Sec.3 - Public LX - Culvert : E2-RD-433473-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S3.65.3.5.1 | Culvert ID : E2-RD-433473-1 / Type : 3*450mm RCP4 / Ch15957 (12.26m each) | I.CN.65.19111 | CON - Sec.3 - Public LX - Culvert : E2-RD-433473-1 - Headwall Stitch Pour
Roadworks |  |  |  | 2026-01-17 | 2026-01-23
I2S-7688-MP-74.CN.S3.65.3.6 | Roadworks | I.CN.65.15080 | CON - Sec.3 - Public LX - Unnamed Council Road (PU15950) - Prime & Cure - Pavement type B sealed (790 m2) | 2026-01-21 | 2026-01-22
I2S-7688-MP-74.CN.S3.65.3.6 | Roadworks | I.CN.65.15090 | CON - Sec.3 - Public LX - Unnamed Council Road (PU15950) - Seal /linemarking | 2026-01-23 | 2026-01-23
I2S-7688-MP-74.CN.S3.65.3.6 | Roadworks | I.CN.65.14980 | CON - Sec.3 - Public LX - Unnamed Council Road (PU15950) - Earthworks | 2026-01-17 | 2026-01-18
I2S-7688-MP-74.CN.S3.65.3.6 | Roadworks | I.CN.65.14990 | CON - Sec.3 - Public LX - Unnamed Council Road (PU15950) - Pavement type A Unsealed (1180m2) | 2026-01-19 | 2026-01-20
I2S-7688-MP-74.CN.S3.65.3.6 | Roadworks | I.CN.65.15070 | CON - Sec.3 - Public LX - Unnamed Council Road (PU15950) - Batter face area (290 m3) | 2026-01-21 | 2026-01-21
Trackworks |  |  |  | 2026-01-23 | 2026-01-26
I2S-7688-MP-74.CN.S3.65.3.7 | Trackworks | I.CN.65.15000 | CON - Sec.3 - Public LX - Unnamed Road (PU15950) - Place Foundation Block and T-Kerbstone | 2026-01-23 | 2026-01-23
I2S-7688-MP-74.CN.S3.65.3.7 | Trackworks | I.CN.65.15010 | CON - Sec.3 - Public LX - Unnamed Road (PU15950) - Place and compact ballast between foundation block (after road | 2026-01-24 | 2026-01-24
I2S-7688-MP-74.CN.S3.65.3.7 | Trackworks | I.CN.65.15020 | CON - Sec.3 - Public LX - Unnamed Road (PU15950) - Tie-in works to foundation block | 2026-01-26 | 2026-01-26
Ancillary |  |  |  | 2026-01-27 | 2026-01-29
I2S-7688-MP-74.CN.S3.65.3.8 | Ancillary | I.CN.65.15030 | CON - Sec.3 - Public LX - Unnamed Road (PU15950) - Install Fencing | 2026-01-27 | 2026-01-27
I2S-7688-MP-74.CN.S3.65.3.8 | Ancillary | I.CN.65.15040 | CON - Sec.3 - Public LX - Unnamed Road (PU15950) - Install Signage | 2026-01-28 | 2026-01-28
I2S-7688-MP-74.CN.S3.65.3.8 | Ancillary | I.CN.65.15060 | CON - Sec.3 - Public LX - Unnamed Road (PU15950) - Install Gates | 2026-01-29 | 2026-01-29
Commissioning |  |  |  | 2026-01-29 | 2026-01-29
I2S-7688-MP-74.CN.S3.65.3.4 | Commissioning | I.CN.65.15120 | CON - Sec.3 - Public LX - Unnamed Road (PU15950) - Open |  | 2026-01-29
Public LX - Paper Road (PU11390) - Active / NSW - RX-5 |  |  |  | 2026-02-23 | 2026-05-16
Civils |  |  |  | 2026-02-23 | 2026-03-06
I2S-7688-MP-74.CN.S3.65.1.1 | Civils | I.CN.65.14205 | CON - Sec.3 - Public LX - Paper Road (Paper Road (PU11390)) - Clear and Grub | 2026-02-23 | 2026-02-23
I2S-7688-MP-74.CN.S3.65.1.1 | Civils | I.CN.65.14870 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Civil Works complete | 2026-03-06 | 2026-03-06
I2S-7688-MP-74.CN.S3.65.1.1 | Civils | I.CN.65.15670 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Local Cable Route (CSR) - pit and Pipe | 2026-02-24 | 2026-02-24
I2S-7688-MP-74.CN.S3.65.1.1 | Civils | I.CN.65.15680 | CON - Sec.3 - Public LX - Paper Road (PU11390) - ULX/URX construction - pit and pipe | 2026-02-26 | 2026-02-26
I2S-7688-MP-74.CN.S3.65.1.1 | Civils | I.CN.65.15690 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Installation of LX Hut Foundations | 2026-02-27 | 2026-02-27
I2S-7688-MP-74.CN.S3.65.1.1 | Civils | I.CN.65.15700 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Installation of booms/lights foundations | 2026-02-28 | 2026-02-28
I2S-7688-MP-74.CN.S3.65.1.1 | Civils | I.CN.65.15710 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Installation of SIgnage foundations | 2026-03-01 | 2026-03-01
Roadworks |  |  |  | 2026-02-24 | 2026-03-21
I2S-7688-MP-74.CN.S3.65.1.6 | Roadworks | I.CN.65.18130 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Earthworks - Fill 4,820ccm | 2026-02-27 | 2026-03-04
I2S-7688-MP-74.CN.S3.65.1.6 | Roadworks | I.CN.65.14800 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Earthworks - cut 5ccm | 2026-02-24 | 2026-02-26
I2S-7688-MP-74.CN.S3.65.1.6 | Roadworks | I.CN.65.14810 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Pavement type A Unsealed (2700m2) | 2026-03-06 | 2026-03-08
I2S-7688-MP-74.CN.S3.65.1.6 | Roadworks | I.CN.65.14900 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Batter face area (3795 m3) | 2026-03-09 | 2026-03-19
I2S-7688-MP-74.CN.S3.65.1.6 | Roadworks | I.CN.65.14910 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Seal /linemarking | 2026-03-20 | 2026-03-21
I2S-7688-MP-74.CN.S3.65.1.6 | Roadworks | I.CN.65.18060 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Prime & Cure - Pavement type B sealed (1150 m2) | 2026-03-09 | 2026-03-11
Trackworks |  |  |  | 2026-03-07 | 2026-03-09
I2S-7688-MP-74.CN.S3.65.1.7 | Trackworks | I.CN.65.14820 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Place Foundation Block and T-Kerbstone | 2026-03-07 | 2026-03-07
I2S-7688-MP-74.CN.S3.65.1.7 | Trackworks | I.CN.65.14830 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Place and compact ballast between foundation block (after road | 2026-03-08 | 2026-03-08
I2S-7688-MP-74.CN.S3.65.1.7 | Trackworks | I.CN.65.14840 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Tie-in works to foundation block | 2026-03-09 | 2026-03-09
Ancillary |  |  |  | 2026-03-22 | 2026-04-11
I2S-7688-MP-74.CN.S3.65.1.8 | Ancillary | I.CN.65.14850 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Install Fencing | 2026-03-22 | 2026-03-22
I2S-7688-MP-74.CN.S3.65.1.8 | Ancillary | I.CN.65.14860 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Install Signage | 2026-04-11 | 2026-04-11
Electrical and Mechanical |  |  |  | 2026-02-27 | 2026-04-28
I2S-7688-MP-74.CN.S3.65.1.2 | Electrical and Mechanical | I.CN.65.16160 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Finalise Installation of LX Hut (Axle Counters | 2026-04-28 | 2026-04-28
I2S-7688-MP-74.CN.S3.65.1.2 | Electrical and Mechanical | I.CN.65.14880 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Install Gates | 2026-04-12 | 2026-04-12
I2S-7688-MP-74.CN.S3.65.1.2 | Electrical and Mechanical | I.CN.65.16050 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Installation of local cables | 2026-02-27 | 2026-02-27
I2S-7688-MP-74.CN.S3.65.1.2 | Electrical and Mechanical | I.CN.65.16060 | CON - Sec.3 - Public LX - Paper Road (PU11390)- Installation of RX5s | 2026-02-28 | 2026-02-28
I2S-7688-MP-74.CN.S3.65.1.2 | Electrical and Mechanical | I.CN.65.16070 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Installation of LX Hut | 2026-02-28 | 2026-02-28
I2S-7688-MP-74.CN.S3.65.1.2 | Electrical and Mechanical | I.CN.65.16080 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Installation of Antenna/Comms | 2026-03-01 | 2026-03-01
I2S-7688-MP-74.CN.S3.65.1.2 | Electrical and Mechanical | I.CN.65.16090 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Cable Testing | 2026-03-03 | 2026-03-03
I2S-7688-MP-74.CN.S3.65.1.2 | Electrical and Mechanical | I.CN.65.16100 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Termination of Local Cables | 2026-02-28 | 2026-02-28
I2S-7688-MP-74.CN.S3.65.1.2 | Electrical and Mechanical | I.CN.65.16110 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Termination of Main Cables | 2026-03-02 | 2026-03-02
I2S-7688-MP-74.CN.S3.65.1.2 | Electrical and Mechanical | I.CN.65.16120 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Connection of Power | 2026-03-04 | 2026-03-04
I2S-7688-MP-74.CN.S3.65.1.2 | Electrical and Mechanical | I.CN.65.16130 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Finalise Installation of LX Hut (Relay/Eqyuipment/tidy up/AC) | 2026-03-06 | 2026-03-06
I2S-7688-MP-74.CN.S3.65.1.2 | Electrical and Mechanical | I.CN.65.16140 | CON - Sec.3 - Public LX - Paper Road (PU11390) - LX Electrical and Mechanical Complete | 2026-03-07 | 2026-03-07
I2S-7688-MP-74.CN.S3.65.1.2 | Electrical and Mechanical | I.CN.65.16150 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Installation of Axle Counter GAKs and sensors | 2026-04-27 | 2026-04-27
STW |  |  |  | 2026-03-01 | 2026-05-14
I2S-7688-MP-74.CN.S3.65.1.3 | STW | I.CN.65.16170 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Set to Work RX5s including SAT | 2026-03-01 | 2026-03-26
I2S-7688-MP-74.CN.S3.65.1.3 | STW | I.CN.65.16180 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Set to Work Interlocking including SAT | 2026-05-14 | 2026-05-14
I2S-7688-MP-74.CN.S3.65.1.3 | STW | I.CN.65.16190 | CON - Sec.3 - Public LX - Paper Road (PU11390)- Set to Work Axle Counter System including SAT | 2026-04-29 | 2026-04-29
Commissioning |  |  |  | 2026-05-16 | 2026-05-16
I2S-7688-MP-74.CN.S3.65.1.4 | Commissioning | I.CN.65.16200 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Commissioning | 2026-05-16 | 2026-05-16
I2S-7688-MP-74.CN.S3.65.1.4 | Commissioning | I.CN.65.14940 | CON - Sec.3 - Public LX - Paper Road (PU11390) - Open |  | 2026-05-16
Stock Crossings |  |  |  | 2025-11-07 | 2026-03-20
Lloyd-Jones (Malcom) (SU9000) Culvert ID : E7-SU-426513-1 / Type : 1*3000x3000mm RCBC / Ch9014 (12m) |  |  |  | 2025-11-07 | 2025-11-10
I2S-7688-MP-74.CN.S3.65.4.1 | Lloyd-Jones (Malcom) (SU9000) Culvert ID : E7-SU-426513-1 / Type : 1*3000x3000mm RCBC / Ch9014 (12m) | I.CN.65.18550 | CON - Sec.3 - Stock Xing - Culvert : E7-SU-426513-1 - Struc fill Placement (250mm)
I2S-7688-MP-74.CN.S3.65.4.1 | Lloyd-Jones (Malcom) (SU9000) Culvert ID : E7-SU-426513-1 / Type : 1*3000x3000mm RCBC / Ch9014 (12m) | I.CN.65.18560 | CON - Sec.3 - Stock Xing - Culvert : E7-SU-426513-1 -7 day Curing
I2S-7688-MP-74.CN.S3.65.4.1 | Lloyd-Jones (Malcom) (SU9000) Culvert ID : E7-SU-426513-1 / Type : 1*3000x3000mm RCBC / Ch9014 (12m) | I.CN.65.18570 | CON - Sec.3 - Stock Xing - Culvert : E7-SU-426513-1 - Detail backfill
I2S-7688-MP-74.CN.S3.65.4.1 | Lloyd-Jones (Malcom) (SU9000) Culvert ID : E7-SU-426513-1 / Type : 1*3000x3000mm RCBC / Ch9014 (12m) | I.CN.65.16320 | CON - Sec.3 - Stock Xing - Culvert : E7-SU-426513-1 - Site Prep / Detail Excavation | 2025-11-07 | 2025-11-08
I2S-7688-MP-74.CN.S3.65.4.1 | Lloyd-Jones (Malcom) (SU9000) Culvert ID : E7-SU-426513-1 / Type : 1*3000x3000mm RCBC / Ch9014 (12m) | I.CN.65.17740 | CON - Sec.3 - Stock Xing - Culvert : E7-SU-426513-1 - Place RCBC crown units | 2025-11-09 | 2025-11-09
I2S-7688-MP-74.CN.S3.65.4.1 | Lloyd-Jones (Malcom) (SU9000) Culvert ID : E7-SU-426513-1 / Type : 1*3000x3000mm RCBC / Ch9014 (12m) | I.CN.65.17750 | CON - Sec.3 - Stock Xing - Culvert : E7-SU-426513-1 - Construct Scour protection | 2025-11-10 | 2025-11-10
I2S-7688-MP-74.CN.S3.65.4.1 | Lloyd-Jones (Malcom) (SU9000) Culvert ID : E7-SU-426513-1 / Type : 1*3000x3000mm RCBC / Ch9014 (12m) | I.CN.65.19481 | CON - Sec.3 - Stock Xing - Culvert : E7-SU-426513-1 - Blinding placement (50mm)
I2S-7688-MP-74.CN.S3.65.4.1 | Lloyd-Jones (Malcom) (SU9000) Culvert ID : E7-SU-426513-1 / Type : 1*3000x3000mm RCBC / Ch9014 (12m) | I.CN.65.19491 | CON - Sec.3 - Stock Xing - Culvert : E7-SU-426513-1 - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.CN.S3.65.4.1 | Lloyd-Jones (Malcom) (SU9000) Culvert ID : E7-SU-426513-1 / Type : 1*3000x3000mm RCBC / Ch9014 (12m) | I.CN.65.19501 | CON - Sec.3 - Stock Xing - Culvert : E7-SU-426513-1 - Place Pre-cast Wingwalls and Stich Pour
I2S-7688-MP-74.CN.S3.65.4.1 | Lloyd-Jones (Malcom) (SU9000) Culvert ID : E7-SU-426513-1 / Type : 1*3000x3000mm RCBC / Ch9014 (12m) | I.CN.65.19511 | CON - Sec.3 - Stock Xing - Culvert : E7-SU-426513-1 - Pre-cast RCBC completion (Seal joints)
I2S-7688-MP-74.CN.S3.65.4.1 | Lloyd-Jones (Malcom) (SU9000) Culvert ID : E7-SU-426513-1 / Type : 1*3000x3000mm RCBC / Ch9014 (12m) | I.CN.65.20011 | CON - Sec.3 - Stock Xing - Culvert : E7-SU-426513-1 - FRP Base Slab / Apron Slab / Cut-off Wall - Milestone
McKenzie (SU17500) Culvert ID : E7-SU-434988-1 / Type : 1*3000x3000mm RCBC / Ch17488 (7.2m) |  |  |  | 2026-03-11 | 2026-03-20
I2S-7688-MP-74.CN.S3.65.4.3 | McKenzie (SU17500) Culvert ID : E7-SU-434988-1 / Type : 1*3000x3000mm RCBC / Ch17488 (7.2m) | I.CN.65.17680 | CON - Sec.3 - Stock Xing - Culvert : E7-SU-434988-1 - Place RCBC crown units | 2026-03-19 | 2026-03-19
I2S-7688-MP-74.CN.S3.65.4.3 | McKenzie (SU17500) Culvert ID : E7-SU-434988-1 / Type : 1*3000x3000mm RCBC / Ch17488 (7.2m) | I.CN.65.17710 | CON - Sec.3 - Stock Xing - Culvert : E7-SU-434988-1 - Construct Scour protection | 2026-03-20 | 2026-03-20
I2S-7688-MP-74.CN.S3.65.4.3 | McKenzie (SU17500) Culvert ID : E7-SU-434988-1 / Type : 1*3000x3000mm RCBC / Ch17488 (7.2m) | I.CN.65.18580 | CON - Sec.3 - Stock Xing - Culvert : E7-SU-434988-1 - Struc fill Placement (250mm)
I2S-7688-MP-74.CN.S3.65.4.3 | McKenzie (SU17500) Culvert ID : E7-SU-434988-1 / Type : 1*3000x3000mm RCBC / Ch17488 (7.2m) | I.CN.65.18590 | CON - Sec.3 - Stock Xing - Culvert : E7-SU-434988-1 - 7 day Curing
I2S-7688-MP-74.CN.S3.65.4.3 | McKenzie (SU17500) Culvert ID : E7-SU-434988-1 / Type : 1*3000x3000mm RCBC / Ch17488 (7.2m) | I.CN.65.18600 | CON - Sec.3 - Stock Xing - Culvert : E7-SU-434988-1 - Detail backfill
I2S-7688-MP-74.CN.S3.65.4.3 | McKenzie (SU17500) Culvert ID : E7-SU-434988-1 / Type : 1*3000x3000mm RCBC / Ch17488 (7.2m) | I.CN.65.16350 | CON - Sec.3 - Stock Xing - Culvert : E7-SU-434988-1 - Site Prep / Detail Excavation | 2026-03-11 | 2026-03-18
I2S-7688-MP-74.CN.S3.65.4.3 | McKenzie (SU17500) Culvert ID : E7-SU-434988-1 / Type : 1*3000x3000mm RCBC / Ch17488 (7.2m) | I.CN.65.19521 | CON - Sec.3 - Stock Xing - Culvert : E7-SU-434988-1 - Blinding placement (50mm)
I2S-7688-MP-74.CN.S3.65.4.3 | McKenzie (SU17500) Culvert ID : E7-SU-434988-1 / Type : 1*3000x3000mm RCBC / Ch17488 (7.2m) | I.CN.65.19531 | CON - Sec.3 - Stock Xing - Culvert : E7-SU-434988-1 - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.CN.S3.65.4.3 | McKenzie (SU17500) Culvert ID : E7-SU-434988-1 / Type : 1*3000x3000mm RCBC / Ch17488 (7.2m) | I.CN.65.19541 | CON - Sec.3 - Stock Xing - Culvert : E7-SU-434988-1 - Place Pre-cast Wingwalls and Stich Pour
I2S-7688-MP-74.CN.S3.65.4.3 | McKenzie (SU17500) Culvert ID : E7-SU-434988-1 / Type : 1*3000x3000mm RCBC / Ch17488 (7.2m) | I.CN.65.19551 | CON - Sec.3 - Stock Xing - Culvert : E7-SU-434988-1 - Pre-cast RCBC completion (Seal joints)
072 - Signalling |  |  |  | 2026-03-01 | 2026-08-29
Signals |  |  |  | 2026-04-01 | 2026-05-03
I2S-7688-MP-74.CN.S3.72.10 | Signals | I.CN.72.15270 | CON - Sec.3 - SIG - Install New Main Signals (2 off) 426810 | 2026-04-12 | 2026-04-22
I2S-7688-MP-74.CN.S3.72.10 | Signals | I.CN.72.15460 | CON - Sec.3 - SIG - Install New Main Signals (1 off) 426500 | 2026-04-01 | 2026-04-07
I2S-7688-MP-74.CN.S3.72.10 | Signals | I.CN.72.15470 | CON - Sec.3 - SIG - Install New Main Signals (1 off) 429030 | 2026-04-26 | 2026-05-01
I2S-7688-MP-74.CN.S3.72.10 | Signals | I.CN.72.15480 | CON - Sec.3 - SIG - Install New Main Signals (1 off) 431670 | 2026-05-02 | 2026-05-03
I2S-7688-MP-74.CN.S3.72.10 | Signals | I.CN.72.15490 | CON - Sec.3 - SIG - Install New Main Signals (2 off) 428730 | 2026-04-23 | 2026-04-24
Points |  |  |  | 2026-07-16 | 2026-08-29
I2S-7688-MP-74.CN.S3.72.2 | Points | I.CN.72.15280 | CON - Sec.3 - SIG - Install New Points Machine (2 off) 428100 to 428300 | 2026-07-16 | 2026-08-03
I2S-7688-MP-74.CN.S3.72.2 | Points | I.CN.72.15290 | CON - Sec.3 - SIG - Install New Points Machine (2 off) (New) 426500 to 426700 | 2026-08-14 | 2026-08-29
I2S-7688-MP-74.CN.S3.72.2 | Points | I.CN.72.15300 | CON - Sec.3 - SIG - Install New Points Machine (2 off) (New) 428700 to 428900 | 2026-08-03 | 2026-08-14
Axle |  |  |  | 2026-07-13 | 2026-08-16
I2S-7688-MP-74.CN.S3.72.3 | Axle | I.CN.72.16630 | CON - Sec.3 - SIG - Install New GAC Axles (1 off) 432100 to 432300
I2S-7688-MP-74.CN.S3.72.3 | Axle | I.CN.72.15310 | CON - Sec.3 - SIG - Install New GAC Axles (2 off) 427900 to 428100 | 2026-07-13 | 2026-08-16
I2S-7688-MP-74.CN.S3.72.3 | Axle | I.CN.72.16320 | CON - Sec.3 - SIG - Install New GAC Axles (2 off) 428100 to 428300
I2S-7688-MP-74.CN.S3.72.3 | Axle | I.CN.72.16580 | CON - Sec.3 - SIG - Install New GAC Axles (2 off) 428500 to 428700
I2S-7688-MP-74.CN.S3.72.3 | Axle | I.CN.72.16590 | CON - Sec.3 - SIG - Install New GAC Axles (3 off) 428700 to 428900
I2S-7688-MP-74.CN.S3.72.3 | Axle | I.CN.72.16600 | CON - Sec.3 - SIG - Install New GAC Axles (2 off) 428900 to 429100
I2S-7688-MP-74.CN.S3.72.3 | Axle | I.CN.72.16610 | CON - Sec.3 - SIG - Install New GAC Axles (1 off) 429700 to 429900
I2S-7688-MP-74.CN.S3.72.3 | Axle | I.CN.72.16620 | CON - Sec.3 - SIG - Install New GAC Axles (1 off) 431500 to 431700
DW Loc |  |  |  | 2026-08-03 | 2026-08-08
I2S-7688-MP-74.CN.S3.72.6 | DW Loc | I.CN.72.15340 | CON - Sec.3 - SIG - Install New DW Locations (2 off) (6552 to 14208) | 2026-08-03 | 2026-08-08
Building |  |  |  | 2026-08-08 | 2026-08-24
I2S-7688-MP-74.CN.S3.72.7 | Building | I.CN.72.16170 | CON - Sec.3 - SIG - Install New SER/Buildings (1 off) 428050
I2S-7688-MP-74.CN.S3.72.7 | Building | I.CN.72.16160 | CON - Sec.3 - SIG - Install New SER/Buildings (1 off) 428850
I2S-7688-MP-74.CN.S3.72.7 | Building | I.CN.72.16150 | CON - Sec.3 - SIG - Site terminations and SAT of location cases
I2S-7688-MP-74.CN.S3.72.7 | Building | I.CN.72.15350 | CON - Sec.3 - SIG - Install New SER/Buildings (1 off) 426650 | 2026-08-08 | 2026-08-24
Cabling |  |  |  | 2026-03-01 | 2026-03-01
I2S-7688-MP-74.CN.S3.72.8 | Cabling | I.CN.74.14420 | CON - Sec.3 - SIG -Main Cable Route - MCR - Pull Cable - 8800 to 18400 | 2026-03-01 | 2026-03-01
Misc Equipment |  |  |  | 2026-03-22 | 2026-04-10
I2S-7688-MP-74.CN.S3.72.1 | Misc Equipment | I.CN.74.14780 | CON - Sec.3 - SIG - Install Track Side Equipment (speed signs/motor generators/notice boards) | 2026-03-22 | 2026-04-10
Location Case
I2S-7688-MP-74.CN.S3.72.4 | Location Case | I.CN.72.16340 | CON - Sec.3 - SIG - Install New Location Case (1 off) 431500
074 - Power Supply and Distributions |  |  |  | 2025-12-14 | 2026-03-21
CSR |  |  |  | 2025-12-14 | 2026-03-21
MCR |  |  |  | 2026-01-17 | 2026-03-19
I2S-7688-MP-74.CN.S3.74.2.1 | MCR | I.CN.74.15430 | CON - Sec.3 - CSR - Install Main CSR - Up Main 428950 to 431925 (Run Boundary) (2975m)
I2S-7688-MP-74.CN.S3.74.2.1 | MCR | I.CN.74.15440 | CON - Sec.3 - CSR - Install Main CSR - Main 431925 to 432025 Over Run Boundary Bridge
I2S-7688-MP-74.CN.S3.74.2.1 | MCR | I.CN.74.15450 | CON - Sec.3 - CSR - Install Main CSR - Up Main 432025 (Run Boundary) to 433450 LX (1425)
I2S-7688-MP-74.CN.S3.74.2.1 | MCR | I.CN.74.15460 | CON - Sec.3 - CSR - Install Main CSR - Up Main 433450 LX to 435950 (Dirnaseer) (2500m)
I2S-7688-MP-74.CN.S3.74.2.1 | MCR | I.CN.74.15470 | CON - Sec.3 - CSR - Install Main CSR - Main 435950 to 436050 Across Dirnaseer Bridge
I2S-7688-MP-74.CN.S3.74.2.1 | MCR | I.CN.74.14340 | CON - Sec.3 - CSR - Install Main CSR - Up Main 425650 to 428025 (2375m) | 2026-01-17 | 2026-02-28
I2S-7688-MP-74.CN.S3.74.2.1 | MCR | I.CN.74.15050 | CON - Sec.3 - CSR - Install Main CSR - Dn Main 428025 to 428950 (LX) (925m) | 2026-03-01 | 2026-03-19
LCR |  |  |  | 2025-12-17 | 2026-03-21
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.15620 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Up 431680
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.15630 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Up 432270
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.14770 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR to Pole Tx 426950 | 2026-03-21 | 2026-03-21
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.14550 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Up 427930 | 2026-02-27 | 2026-02-28
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.14470 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Up 426480 | 2025-12-17 | 2025-12-18
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.14480 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Up 426660 | 2026-01-11 | 2026-01-12
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.14490 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Up 426680 | 2026-01-13 | 2026-01-14
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.14500 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Up to signal 426820 | 2026-01-16 | 2026-01-17
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.14510 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Across Track 426850 | 2026-01-18 | 2026-01-19
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.14520 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Up 426920 | 2026-01-20 | 2026-01-21
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.15480 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Dn 428100
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.15490 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Dn 428170
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.15500 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Dn 428180
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.15510 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Dn 428250
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.15520 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Dn 428640
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.15530 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Dn 428730
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.15540 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Dn 428870
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.15550 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Dn 428880
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.15560 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Dn 428890
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.15570 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Up 428900
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.15580 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Dn 428920
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.15590 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Up 428930
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.15600 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Dn 429030
I2S-7688-MP-74.CN.S3.74.2.2 | LCR | I.CN.74.15610 | CON - Sec.3 - CSR - Construct Local Cable Route - LCR Up 429870
ULX |  |  |  | 2025-12-14 | 2026-03-02
I2S-7688-MP-74.CN.S3.74.2.3 | ULX | I.CN.74.14540 | CON - Sec.3 - CSR - Local ULX - Across Track - 428950 | 2026-02-24 | 2026-02-26
I2S-7688-MP-74.CN.S3.74.2.3 | ULX | I.CN.74.14560 | CON - Sec.3 - CSR - Local ULX - Across Track - 433450 | 2026-03-01 | 2026-03-02
I2S-7688-MP-74.CN.S3.74.2.3 | ULX | I.CN.74.14460 | CON - Sec.3 - CSR - Local ULX - Across Track - 428025 | 2025-12-14 | 2025-12-16
I2S-7688-MP-74.CN.S3.74.2.3 | ULX | I.CN.74.14530 | CON - Sec.3 - CSR - Local ULX - Across Track Dn - 428850 to 428925 | 2026-02-22 | 2026-02-23
085 - Landscaping
I2S-7688-MP-74.CN.S3.85 | 085 - Landscaping | I.CN.85.14040 | CON - Sec.3 - Landscaping - Hydroseed Application - CH8840-18500
I2S-7688-MP-74.CN.S3.85 | 085 - Landscaping | I.CN.85.14030 | CON - Sec.3 - Landscaping - Re-spread Topsoil - CH8840-18500
Section 2 - GF section (02901 - 08840) |  |  |  | 2025-07-12 | 2026-09-22
Section 2 Key Milestones
I2S-7688-MP-74.CN.S2.2 | Section 2 Key Milestones | I.CN.22.14040 | CON - Sec.2 - Construction Completion Milestone (Fencing)
I2S-7688-MP-74.CN.S2.2 | Section 2 Key Milestones | I.CN.22.14050 | CON - Sec.2 - Construction Completion Milestone (Access Roads)
I2S-7688-MP-74.CN.S2.2 | Section 2 Key Milestones | I.CN.22.14060 | CON - Sec.2 - Construction Completion Milestone (Trackwork)
I2S-7688-MP-74.CN.S2.2 | Section 2 Key Milestones | I.CN.22.14070 | CON - Sec.2 - Construction Completion Milestone (Bridges)
I2S-7688-MP-74.CN.S2.2 | Section 2 Key Milestones | I.CN.22.14820 | CON - Sec.2 - Commence Construction Milestone - FDVR & CEMP approved - 1st A9 submission - approval
I2S-7688-MP-74.CN.S2.2 | Section 2 Key Milestones | I.CN.22.14810 | CON - Sec.2 - Commence Construction Milestone - CEMP approved
I2S-7688-MP-74.CN.S2.2 | Section 2 Key Milestones | I.CN.22.14080 | CON - Sec.2 - Construction Completion Milestone (Crossings)
I2S-7688-MP-74.CN.S2.2 | Section 2 Key Milestones | I.CN.22.14090 | CON - Sec.2 - Construction Completion Milestone (Signalling)
I2S-7688-MP-74.CN.S2.2 | Section 2 Key Milestones | I.CN.22.14100 | CON - Sec.2 - Construction Completion Milestone (Power Supply and Distributions)
I2S-7688-MP-74.CN.S2.2 | Section 2 Key Milestones | I.CN.22.14110 | CON - Sec.2 - Construction Completion Milestone (Landscaping)
I2S-7688-MP-74.CN.S2.2 | Section 2 Key Milestones | I.CN.22.14420 | CON - Sec.2 - Construction Completion Milestone (Culverts)
I2S-7688-MP-74.CN.S2.2 | Section 2 Key Milestones | I.CN.22.14000 | CON - Sec.2 - Construction Completion Milestone (Public Utilities)
I2S-7688-MP-74.CN.S2.2 | Section 2 Key Milestones | I.CN.22.14010 | CON - Sec.2 - Construction Completion Milestone (Earthworks)
I2S-7688-MP-74.CN.S2.2 | Section 2 Key Milestones | I.CN.22.14020 | CON - Sec.2 - Construction Completion Milestone (Rail Capping)
I2S-7688-MP-74.CN.S2.2 | Section 2 Key Milestones | I.CN.22.14030 | CON - Sec.2 - Construction Completion Milestone (Drainage)
Site Access |  |  |  | 2025-07-12 | 2025-07-12
I2S-7688-MP-74.CN.S2.00 | Site Access | I.CN.11.14070 | CON - Sec.2 - Site Gate Access Required by/ Granted - Gate 4 (8150) | 2025-07-12 | 2025-07-12
I2S-7688-MP-74.CN.S2.00 | Site Access | I.CN.11.14060 | CON - Sec.2 - Site Gate Access Required by/ Granted - Gate 3 (5600) | 2025-07-12 | 2025-07-12
022 - Public Utilities |  |  |  | 2025-07-30 | 2025-08-29
ARTC |  |  |  | 2025-08-04 | 2025-08-08
I2S-7688-MP-74.CN.S2.22.1 | ARTC | I.CN.22.5470 | CON - Util - Sec.2 - PUP - IRPL - Rail Power - 5610 to 5625 | 2025-08-04 | 2025-08-06
I2S-7688-MP-74.CN.S2.22.1 | ARTC | I.CN.22.11980 | CON - Util - Sec.2 - PUP - IRPL - Rail Power - 8200 - | 2025-08-07 | 2025-08-08
Telstra |  |  |  | 2025-08-11 | 2025-08-29
I2S-7688-MP-74.CN.S2.22.2 | Telstra | I.CN.22.11920 | CON - Util - Sec.2 - TE02-02 Telstra - Protect South Side Verge Old Sydney Road - Ch5562 (137m) | 2025-08-11 | 2025-08-18
I2S-7688-MP-74.CN.S2.22.2 | Telstra | I.CN.22.11970 | CON - Util - Sec.2 - TE02-04 Telstra - Relocate West Side Ironbong Road - Ch7992 (624m) | 2025-08-19 | 2025-08-29
I2S-7688-MP-74.CN.S2.22.2 | Telstra | I.CN.22.14400 | CON - Util - Sec.2 - TE02-03 Telstra - Abondoned In-Situ North Side Verge Old Sydney Road - Ch5612 (Not required)
Private Water |  |  |  | 2025-07-30 | 2025-08-15
I2S-7688-MP-74.CN.S2.22.3 | Private Water | I.CN.22.11940 | CON - Util - Sec.2 - PUP - Water - 8790 - Trenched x-ing WA11 for DN300 RCP enveloper pipe for future water | 2025-07-30 | 2025-07-31
I2S-7688-MP-74.CN.S2.22.3 | Private Water | I.CN.22.11960 | CON - Util - Sec.2 - PUP - Water - 5550, 5625 - (2 off) - Trenched x-ing WA13, and WA12 | 2025-08-04 | 2025-08-08
I2S-7688-MP-74.CN.S2.22.3 | Private Water | I.CN.34.27870 | CON - Util - Sec.2 - Place Enveloper Pipe - DN300 RCP 1.5m past crdr boundary (44m) | 2025-08-13 | 2025-08-15
I2S-7688-MP-74.CN.S2.22.3 | Private Water | I.CN.34.27880 | CON - Util - Sec.2 - Place Enveloper Pipe - DN300 RCP 1.5m past crdr boundary (57m) | 2025-08-08 | 2025-08-12
I2S-7688-MP-74.CN.S2.22.3 | Private Water | I.CN.34.27890 | CON - Util - Sec.2 - Place Enveloper Pipe - DN300 RCP 1.5m past crdr boundary (103m) | 2025-08-01 | 2025-08-07
Goldenfield Water |  |  |  | 2025-07-30 | 2025-08-01
I2S-7688-MP-74.CN.S2.22.4 | Goldenfield Water | I.CN.22.11950 | CON - Util - Sec.2 - WA01-04 - Goldenfields Water - Relocate Potable Water North Side Old Sydney Road - Ch5592 (49m | 2025-07-30 | 2025-08-01
031 - Earthworks |  |  |  | 2025-07-23 | 2025-07-23
I2S-7688-MP-74.CN.S2.31 | 031 - Earthworks | I.CN.31.14160 | CON - Sec.2 - Construct Temp Creek Crossing - Ulandra Creek for traffic | 2025-07-23 | 2025-07-23
Clearing & Grubbing - Stage 2
Tree Felling and Lopping
I2S-7688-MP-74.CN.S2.31.3.1 | Tree Felling and Lopping | I.CN.11.15520 | CON - Sec.2 - Tree Felling & Lopping
Broad Acre Clearing and Mulching
I2S-7688-MP-74.CN.S2.31.3.2 | Broad Acre Clearing and Mulching | I.CN.11.15530 | CON - Sec.2 - Broad Acre Clearing & Mulching
Grubbing of Stumps
I2S-7688-MP-74.CN.S2.31.3.3 | Grubbing of Stumps | I.CN.11.15540 | CON - Sec.2 - Grubbing of Stumps
Miscellaneous Works
I2S-7688-MP-74.CN.S2.31.3.4 | Miscellaneous Works | I.CN.11.15550 | CON - Sec.2 - Hollow/Habitat Tree Mgmt
I2S-7688-MP-74.CN.S2.31.3.4 | Miscellaneous Works | I.CN.11.15560 | CON - Sec.2 - Habitat Relocations
Cut
Cut Open Drains
I2S-7688-MP-74.CN.S2.31.1.6 | Cut Open Drains | I.CN.31.85840 | CON - Sec.2 - FILL 07 - Cut.OD Soil : Ch6862 to 7162 (79 bcm - 175 per/d)
I2S-7688-MP-74.CN.S2.31.1.6 | Cut Open Drains | I.CN.31.85850 | CON - Sec.2 - FILL 08 - Cut.OD Soil : Ch7422 to 7922 (1510 bcm - 175 per/d)
I2S-7688-MP-74.CN.S2.31.1.6 | Cut Open Drains | I.CN.31.85810 | CON - Sec.2 - FILL 05 - Cut.OD Soil : Ch4822 to 5582 (2255 bcm - 175 per/d)
I2S-7688-MP-74.CN.S2.31.1.6 | Cut Open Drains | I.CN.31.85820 | CON - Sec.2 - FILL 06 - Cut.OD Soil : Ch5602 to 6182 (573 bcm - 175 per/d)
I2S-7688-MP-74.CN.S2.31.1.6 | Cut Open Drains | I.CN.31.85830 | CON - Sec.2 - FILL 04 - Cut.OD Soil : Ch2802 to 4022 (1311 bcm - 175 per/d)
I2S-7688-MP-74.CN.S2.31.1.6 | Cut Open Drains | I.CN.31.81250 | CON - Sec.2 - CUT 06 - Cut.OD Soil : Ch6182 to 6862 (914 bcm - 175 per/d)
I2S-7688-MP-74.CN.S2.31.1.6 | Cut Open Drains | I.CN.31.81300 | CON - Sec.2 - CUT 07 - Cut.OD Soil : Ch7162 to 7422 (355 bcm - 175 per/d)
I2S-7688-MP-74.CN.S2.31.1.6 | Cut Open Drains | I.CN.31.82580 | CON - Sec.2 - CUT 04 - Cut.OD Soil : Ch4022 to 4822 (2029 bcm - 175 per/d)
Cut Soil to EW
I2S-7688-MP-74.CN.S2.31.1.1 | Cut Soil to EW | I.CN.31.81260 | CON - Sec.2 - CUT 06 - Cut.Soil to EW : Ch6182 to 6862 (60223 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S2.31.1.1 | Cut Soil to EW | I.CN.31.81310 | CON - Sec.2 - CUT 07 - Cut.Soil to EW : Ch7162 to 7422 (10365 bcm - 2500 per /d)
I2S-7688-MP-74.CN.S2.31.1.1 | Cut Soil to EW | I.CN.31.82590 | CON - Sec.2 - CUT 04 - Cut.Soil to EW : Ch4022 to 4822 (16922 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S2.31.1.1 | Cut Soil to EW | I.CN.31.85770 | CON - Sec.2 - FILL 06 - Cut.Soil to EW : Ch5602 to 6182 (115 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S2.31.1.1 | Cut Soil to EW | I.CN.31.85780 | CON - Sec.2 - FILL 05 - Cut.Soil to EW : Ch4822 to 5582 (525 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S2.31.1.1 | Cut Soil to EW | I.CN.31.85790 | CON - Sec.2 - FILL 07 - Cut.Soil to EW : Ch6862 to 7162 (124 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S2.31.1.1 | Cut Soil to EW | I.CN.31.85800 | CON - Sec.2 - FILL 08 - Cut.Soil to EW : Ch7422 to 7922 (477 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S2.31.1.1 | Cut Soil to EW | I.CN.31.88340 | CON - Sec.2 - CUT 04 - Cut.Soil to EW : Ch4022 to 4822 (16922 bcm - 2500 per/d) - Milestone
Cut Rock
I2S-7688-MP-74.CN.S2.31.1.3 | Cut Rock | I.CN.31.81270 | CON - Sec.2 - CUT 06 - Cut.HW to MW SS : Ch6182 to 6862 (18702 bcm - 2500 per/d)
Fill
Fill Open Drains
I2S-7688-MP-74.CN.S2.31.2.8 | Fill Open Drains | I.CN.31.84140 | CON - Sec.2 - FILL 04 - Fill.OD Fill : Ch2802 to 4022 (698 bcm - 500 per/d)
I2S-7688-MP-74.CN.S2.31.2.8 | Fill Open Drains | I.CN.31.84170 | CON - Sec.2 - FILL 05 - Fill.OD Fill : Ch4822 to 5582 (171 bcm - 500 per/d)
I2S-7688-MP-74.CN.S2.31.2.8 | Fill Open Drains | I.CN.31.84190 | CON - Sec.2 - FILL 06 - Fill.OD Fill : Ch5602 to 6182 (109 bcm - 500 per/d)
I2S-7688-MP-74.CN.S2.31.2.8 | Fill Open Drains | I.CN.31.84210 | CON - Sec.2 - FILL 07 - Fill.OD Fill : Ch6862 to 7162 (197 bcm - 500 per/d)
I2S-7688-MP-74.CN.S2.31.2.8 | Fill Open Drains | I.CN.31.84230 | CON - Sec.2 - FILL 08 - Fill.OD Fill : Ch7422 to 7922 (1371 bcm - 500 per/d)
I2S-7688-MP-74.CN.S2.31.2.8 | Fill Open Drains | I.CN.31.86930 | CON - Sec.2 - CUT 04 - Fill.OD Fill : Ch4022 to 4822 (3443 bcm - 500 per/d)
I2S-7688-MP-74.CN.S2.31.2.8 | Fill Open Drains | I.CN.31.86970 | CON - Sec.2 - CUT 06 - Fill.OD Fill : Ch6182 to 6862 (1276 bcm - 500 per/d)
I2S-7688-MP-74.CN.S2.31.2.8 | Fill Open Drains | I.CN.31.87010 | CON - Sec.2 - CUT 07 - Fill.OD Fill : Ch7162 to 7422 (476 bcm - 500 per/d)
Fill Lower
I2S-7688-MP-74.CN.S2.31.2.1 | Fill Lower | I.CN.31.84280 | CON - Sec.2 - FILL 04 - Fill.H3 - Lower : Ch2802 to 4022 (19864 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S2.31.2.1 | Fill Lower | I.CN.31.84310 | CON - Sec.2 - FILL 05 - Fill.H3 - Lower : Ch4822 to 5582 (7646 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S2.31.2.1 | Fill Lower | I.CN.31.84320 | CON - Sec.2 - FILL 06 - Fill.H3 - Lower : Ch5602 to 6182 (7294 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S2.31.2.1 | Fill Lower | I.CN.31.84350 | CON - Sec.2 - FILL 08 - Fill.H3 - Lower : Ch7422 to 7922 (4507 bcm - 2500 per/d)
Fill Mid
I2S-7688-MP-74.CN.S2.31.2.3 | Fill Mid | I.CN.31.84290 | CON - Sec.2 - FILL 04 - Fill.H2 - Mid : Ch2802 to 4022 (6527 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S2.31.2.3 | Fill Mid | I.CN.31.84300 | CON - Sec.2 - FILL 05 - Fill.H2 - Mid : Ch4822 to 5582 (3686 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S2.31.2.3 | Fill Mid | I.CN.31.84330 | CON - Sec.2 - FILL 06 - Fill.H2 - Mid : Ch5602 to 6182 (2899 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S2.31.2.3 | Fill Mid | I.CN.31.84340 | CON - Sec.2 - FILL 07 - Fill.H2 - Mid : Ch6862 to 7162 (454 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S2.31.2.3 | Fill Mid | I.CN.31.84360 | CON - Sec.2 - FILL 08 - Fill.H2 - Mid : Ch7422 to 7922 (2470 bcm - 2500 per/d)
Fill Upper
I2S-7688-MP-74.CN.S2.31.2.4 | Fill Upper | I.CN.31.84150 | CON - Sec.2 - FILL 04 - Fill.H1 - Upper I/B : Ch2802 to 4022 (16008 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S2.31.2.4 | Fill Upper | I.CN.31.84160 | CON - Sec.2 - FILL 05 - Fill.H1 - Upper I/B : Ch4822 to 5582 (8845 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S2.31.2.4 | Fill Upper | I.CN.31.84180 | CON - Sec.2 - FILL 06 - Fill.H1 - Upper I/B : Ch5602 to 6182 (8451 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S2.31.2.4 | Fill Upper | I.CN.31.84200 | CON - Sec.2 - FILL 07 - Fill.H1 - Upper I/B : Ch6862 to 7162 (3129 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S2.31.2.4 | Fill Upper | I.CN.31.84220 | CON - Sec.2 - FILL 08 - Fill.H1 - Upper I/B : Ch7422 to 7922 (5359 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S2.31.2.4 | Fill Upper | I.CN.31.86920 | CON - Sec.2 - CUT 04 - Fill.H1 - Upper I/B : Ch4022 to 4822 (1256 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S2.31.2.4 | Fill Upper | I.CN.31.86960 | CON - Sec.2 - CUT 06 - Fill.H1 - Upper I/B : Ch6182 to 6862 (705 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S2.31.2.4 | Fill Upper | I.CN.31.87000 | CON - Sec.2 - CUT 07 - Fill.H1 - Upper I/B : Ch7162 to 7422 (196 bcm - 2500 per/d)
033 - Capping |  |  |  | 2026-02-01 | 2026-02-10
Support to u/s Ballast |  |  |  | 2026-02-01 | 2026-02-10
Structural Fill |  |  |  | 2026-02-01 | 2026-02-04
I2S-7688-MP-74.CN.S2.33.3.1 | Structural Fill | I.CN.33.7030 | CON - Sec.2 - Fill - Struc fill (24474 TON) 2,200 TON/d | 2026-02-01 | 2026-02-04
Capping (Rail) |  |  |  | 2026-02-06 | 2026-02-07
I2S-7688-MP-74.CN.S2.33.3.2 | Capping (Rail) | I.CN.33.7130 | CON - Sec.2 - Capping (18,128 TON) 1,316 TON/d | 2026-02-06 | 2026-02-07
Capping (RMAR) |  |  |  | 2026-02-08 | 2026-02-10
I2S-7688-MP-74.CN.S2.33.3.24 | Capping (RMAR) | I.CN.45.7230 | CON - Sec.2 - (10,664 TON) - Strip/Grade RMAR with type D Material (U5 Class) | 2026-02-08 | 2026-02-10
034 - Drainage |  |  |  | 2025-09-02 | 2026-05-01
Mainline |  |  |  | 2026-04-08 | 2026-05-01
I2S-7688-MP-74.CN.S2.34.9 | Mainline | I.CN.34.25390 | CON - Sec.2 - Cess Drainage - 421471 - 424930 - Grass Lined | 2026-04-08 | 2026-04-12
I2S-7688-MP-74.CN.S2.34.9 | Mainline | I.CN.34.25400 | CON - Sec.2 - Cess Drainage - 422049 to 425019 - Grass Lined | 2026-04-13 | 2026-04-24
I2S-7688-MP-74.CN.S2.34.9 | Mainline | I.CN.34.25410 | CON - Sec.2 - Cess Drainage - 8232 to 9101 - Grass Lined | 2026-04-26 | 2026-05-01
Culverts |  |  |  | 2025-09-02 | 2025-12-14
Culvert ID : E7-RD-425670-1 / Type : 1*375mm HDPE / Ch8155 (14.01m each) - RMAR
I2S-7688-MP-74.CN.S2.34.10.12 | Culvert ID : E7-RD-425670-1 / Type : 1*375mm HDPE / Ch8155 (14.01m each) - RMAR | I.CN.34.31430 | CON - Sec.2 - Culvert : E7-RD-425670-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S2.34.10.12 | Culvert ID : E7-RD-425670-1 / Type : 1*375mm HDPE / Ch8155 (14.01m each) - RMAR | I.CN.34.31440 | CON - Sec.2 - Culvert : E7-RD-425670-1 - Headwall installation
I2S-7688-MP-74.CN.S2.34.10.12 | Culvert ID : E7-RD-425670-1 / Type : 1*375mm HDPE / Ch8155 (14.01m each) - RMAR | I.CN.34.31450 | CON - Sec.2 - Culvert : E7-RD-425670-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S2.34.10.12 | Culvert ID : E7-RD-425670-1 / Type : 1*375mm HDPE / Ch8155 (14.01m each) - RMAR | I.CN.34.31460 | CON - Sec.2 - Culvert : E7-RD-425670-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S2.34.10.12 | Culvert ID : E7-RD-425670-1 / Type : 1*375mm HDPE / Ch8155 (14.01m each) - RMAR | I.CN.34.31470 | CON - Sec.2 - Culvert : E7-RD-425670-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S2.34.10.12 | Culvert ID : E7-RD-425670-1 / Type : 1*375mm HDPE / Ch8155 (14.01m each) - RMAR | I.CN.34.31490 | CON - Sec.2 - Culvert : E7-RD-425670-1 - Construct Scour Protection
I2S-7688-MP-74.CN.S2.34.10.12 | Culvert ID : E7-RD-425670-1 / Type : 1*375mm HDPE / Ch8155 (14.01m each) - RMAR | I.CN.34.31500 | CON - Sec.2 - Culvert : E7-RD-425670-1 - Site Prep / Detail Excavation
Culvert ID : E7-RA-425540-1 / Type : 29*900mm HDPE / Ch8034 (13.57m each) |  |  |  | 2025-11-16 | 2025-11-30
I2S-7688-MP-74.CN.S2.34.10.6 | Culvert ID : E7-RA-425540-1 / Type : 29*900mm HDPE / Ch8034 (13.57m each) | I.CN.34.23300 | CON - Sec.2 - Culvert : E7-RA-425540-1 - Construct Scour Protection | 2025-11-29 | 2025-11-30
I2S-7688-MP-74.CN.S2.34.10.6 | Culvert ID : E7-RA-425540-1 / Type : 29*900mm HDPE / Ch8034 (13.57m each) | I.CN.34.23190 | CON - Sec.2 - Culvert : E7-RA-425540-1 - Site Prep / Detail Excavation | 2025-11-16 | 2025-11-17
I2S-7688-MP-74.CN.S2.34.10.6 | Culvert ID : E7-RA-425540-1 / Type : 29*900mm HDPE / Ch8034 (13.57m each) | I.CN.34.23200 | CON - Sec.2 - Culvert : E7-RA-425540-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2025-11-18 | 2025-11-19
I2S-7688-MP-74.CN.S2.34.10.6 | Culvert ID : E7-RA-425540-1 / Type : 29*900mm HDPE / Ch8034 (13.57m each) | I.CN.34.23240 | CON - Sec.2 - Culvert : E7-RA-425540-1 - Headwall installation | 2025-11-20 | 2025-11-21
I2S-7688-MP-74.CN.S2.34.10.6 | Culvert ID : E7-RA-425540-1 / Type : 29*900mm HDPE / Ch8034 (13.57m each) | I.CN.34.23250 | CON - Sec.2 - Culvert : E7-RA-425540-1 - HDPE / RCP Pipe Lay & Backfill | 2025-11-21 | 2025-11-23
I2S-7688-MP-74.CN.S2.34.10.6 | Culvert ID : E7-RA-425540-1 / Type : 29*900mm HDPE / Ch8034 (13.57m each) | I.CN.34.23270 | CON - Sec.2 - Culvert : E7-RA-425540-1 - Headwall Stitch Pour | 2025-11-24 | 2025-11-26
I2S-7688-MP-74.CN.S2.34.10.6 | Culvert ID : E7-RA-425540-1 / Type : 29*900mm HDPE / Ch8034 (13.57m each) | I.CN.34.23280 | CON - Sec.2 - Culvert : E7-RA-425540-1 - Headwall Cut-off Wall Installation (FRP) | 2025-11-27 | 2025-11-28
Culvert ID : E7-RA-425131-1 / Type : 35*750mm HDPE / Ch7625 (14m each) |  |  |  | 2025-11-11 | 2025-11-26
I2S-7688-MP-74.CN.S2.34.10.5 | Culvert ID : E7-RA-425131-1 / Type : 35*750mm HDPE / Ch7625 (14m each) | I.CN.34.23420 | CON - Sec.2 - Culvert : E7-RA-425131-1 - Construct Scour Protection | 2025-11-24 | 2025-11-26
I2S-7688-MP-74.CN.S2.34.10.5 | Culvert ID : E7-RA-425131-1 / Type : 35*750mm HDPE / Ch7625 (14m each) | I.CN.34.23310 | CON - Sec.2 - Culvert : E7-RA-425131-1 - Site Prep / Detail Excavation | 2025-11-11 | 2025-11-12
I2S-7688-MP-74.CN.S2.34.10.5 | Culvert ID : E7-RA-425131-1 / Type : 35*750mm HDPE / Ch7625 (14m each) | I.CN.34.23320 | CON - Sec.2 - Culvert : E7-RA-425131-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2025-11-13 | 2025-11-14
I2S-7688-MP-74.CN.S2.34.10.5 | Culvert ID : E7-RA-425131-1 / Type : 35*750mm HDPE / Ch7625 (14m each) | I.CN.34.23360 | CON - Sec.2 - Culvert : E7-RA-425131-1 - Headwall installation | 2025-11-16 | 2025-11-17
I2S-7688-MP-74.CN.S2.34.10.5 | Culvert ID : E7-RA-425131-1 / Type : 35*750mm HDPE / Ch7625 (14m each) | I.CN.34.23370 | CON - Sec.2 - Culvert : E7-RA-425131-1 - HDPE / RCP Pipe Lay & Backfill | 2025-11-17 | 2025-11-19
I2S-7688-MP-74.CN.S2.34.10.5 | Culvert ID : E7-RA-425131-1 / Type : 35*750mm HDPE / Ch7625 (14m each) | I.CN.34.23390 | CON - Sec.2 - Culvert : E7-RA-425131-1 - Headwall Stitch Pour | 2025-11-20 | 2025-11-21
I2S-7688-MP-74.CN.S2.34.10.5 | Culvert ID : E7-RA-425131-1 / Type : 35*750mm HDPE / Ch7625 (14m each) | I.CN.34.23400 | CON - Sec.2 - Culvert : E7-RA-425131-1 - Headwall Cut-off Wall Installation (FRP) | 2025-11-22 | 2025-11-23
Culvert ID : E7-RA-424570-1 / Type : 19*750mm HDPE / Ch7078 (8.49m each) |  |  |  | 2025-09-18 | 2025-10-03
I2S-7688-MP-74.CN.S2.34.10.4 | Culvert ID : E7-RA-424570-1 / Type : 19*750mm HDPE / Ch7078 (8.49m each) | I.CN.34.23510 | CON - Sec.2 - Culvert : E7-RA-424570-1 - Headwall Stitch Pour | 2025-09-29 | 2025-09-29
I2S-7688-MP-74.CN.S2.34.10.4 | Culvert ID : E7-RA-424570-1 / Type : 19*750mm HDPE / Ch7078 (8.49m each) | I.CN.34.23520 | CON - Sec.2 - Culvert : E7-RA-424570-1 - Headwall Cut-off Wall Installation (FRP) | 2025-09-30 | 2025-10-01
I2S-7688-MP-74.CN.S2.34.10.4 | Culvert ID : E7-RA-424570-1 / Type : 19*750mm HDPE / Ch7078 (8.49m each) | I.CN.34.23540 | CON - Sec.2 - Culvert : E7-RA-424570-1 - Construct Scour Protection | 2025-10-02 | 2025-10-03
I2S-7688-MP-74.CN.S2.34.10.4 | Culvert ID : E7-RA-424570-1 / Type : 19*750mm HDPE / Ch7078 (8.49m each) | I.CN.34.23430 | CON - Sec.2 - Culvert : E7-RA-424570-1 - Site Prep / Detail Excavation | 2025-09-18 | 2025-09-19
I2S-7688-MP-74.CN.S2.34.10.4 | Culvert ID : E7-RA-424570-1 / Type : 19*750mm HDPE / Ch7078 (8.49m each) | I.CN.34.23440 | CON - Sec.2 - Culvert : E7-RA-424570-1 - Foundation Treatment | 2025-09-20 | 2025-09-21
I2S-7688-MP-74.CN.S2.34.10.4 | Culvert ID : E7-RA-424570-1 / Type : 19*750mm HDPE / Ch7078 (8.49m each) | I.CN.34.23480 | CON - Sec.2 - Culvert : E7-RA-424570-1 - Headwall installation | 2025-09-22 | 2025-09-27
I2S-7688-MP-74.CN.S2.34.10.4 | Culvert ID : E7-RA-424570-1 / Type : 19*750mm HDPE / Ch7078 (8.49m each) | I.CN.34.23490 | CON - Sec.2 - Culvert : E7-RA-424570-1 - HDPE / RCP Pipe Lay & Backfill | 2025-09-26 | 2025-09-28
Culvert ID : E7-RA-424520-1 / Type : 4*1200x600mm RCBC / Ch7012 (9.6m each) |  |  |  | 2025-09-02 | 2025-09-17
I2S-7688-MP-74.CN.S2.34.10.3 | Culvert ID : E7-RA-424520-1 / Type : 4*1200x600mm RCBC / Ch7012 (9.6m each) | I.CN.34.23640 | CON - Sec.2 - Culvert : E7-RA-424520-1 - Place Pre-cast Wingwalls and Stich Pour | 2025-09-13 | 2025-09-14
I2S-7688-MP-74.CN.S2.34.10.3 | Culvert ID : E7-RA-424520-1 / Type : 4*1200x600mm RCBC / Ch7012 (9.6m each) | I.CN.34.32180 | CON - Sec.2 - Culvert : E7-RA-424520-1 - Pre-cast RCBC completion (Seal joints)
I2S-7688-MP-74.CN.S2.34.10.3 | Culvert ID : E7-RA-424520-1 / Type : 4*1200x600mm RCBC / Ch7012 (9.6m each) | I.CN.34.32130 | CON - Sec.2 - Culvert : E7-RA-424520-1 - Blinding placement (50mm)
I2S-7688-MP-74.CN.S2.34.10.3 | Culvert ID : E7-RA-424520-1 / Type : 4*1200x600mm RCBC / Ch7012 (9.6m each) | I.CN.34.23650 | CON - Sec.2 - Culvert : E7-RA-424520-1 - Detail backfill | 2025-09-16 | 2025-09-16
I2S-7688-MP-74.CN.S2.34.10.3 | Culvert ID : E7-RA-424520-1 / Type : 4*1200x600mm RCBC / Ch7012 (9.6m each) | I.CN.34.23660 | CON - Sec.2 - Culvert : E7-RA-424520-1 - Construct Scour protection | 2025-09-16 | 2025-09-17
I2S-7688-MP-74.CN.S2.34.10.3 | Culvert ID : E7-RA-424520-1 / Type : 4*1200x600mm RCBC / Ch7012 (9.6m each) | I.CN.34.23550 | CON - Sec.2 - Culvert : E7-RA-424520-1 - Site Prep / Detail Excavation | 2025-09-02 | 2025-09-03
I2S-7688-MP-74.CN.S2.34.10.3 | Culvert ID : E7-RA-424520-1 / Type : 4*1200x600mm RCBC / Ch7012 (9.6m each) | I.CN.34.23560 | CON - Sec.2 - Culvert : E7-RA-424520-1 - Struc fill Placement (250mm) | 2025-09-04 | 2025-09-06
I2S-7688-MP-74.CN.S2.34.10.3 | Culvert ID : E7-RA-424520-1 / Type : 4*1200x600mm RCBC / Ch7012 (9.6m each) | I.CN.34.23600 | CON - Sec.2 - Culvert : E7-RA-424520-1 - FRP Base Slab / Apron Slab / Cut-off Wall | 2025-09-07 | 2025-09-08
I2S-7688-MP-74.CN.S2.34.10.3 | Culvert ID : E7-RA-424520-1 / Type : 4*1200x600mm RCBC / Ch7012 (9.6m each) | I.CN.34.23610 | CON - Sec.2 - Culvert : E7-RA-424520-1 - 7 day Curing | 2025-09-08 | 2025-09-10
I2S-7688-MP-74.CN.S2.34.10.3 | Culvert ID : E7-RA-424520-1 / Type : 4*1200x600mm RCBC / Ch7012 (9.6m each) | I.CN.34.23630 | CON - Sec.2 - Culvert : E7-RA-424520-1 - Place RCBC crown units | 2025-09-11 | 2025-09-12
I2S-7688-MP-74.CN.S2.34.10.3 | Culvert ID : E7-RA-424520-1 / Type : 4*1200x600mm RCBC / Ch7012 (9.6m each) | I.CN.34.32880 | CON - Sec.2 - Culvert : E7-RA-424520-1 - FRP Base Slab / Apron Slab / Cut-off Wall - Milestone
Culvert ID : E7-RA-423540-1 / Type : 35*900mm HDPE / Ch6040 (18.56m each) |  |  |  | 2025-12-02 | 2025-12-14
I2S-7688-MP-74.CN.S2.34.10.2 | Culvert ID : E7-RA-423540-1 / Type : 35*900mm HDPE / Ch6040 (18.56m each) | I.CN.34.23730 | CON - Sec.2 - Culvert : E7-RA-423540-1 - HDPE / RCP Pipe Lay & Backfill | 2025-12-08 | 2025-12-08
I2S-7688-MP-74.CN.S2.34.10.2 | Culvert ID : E7-RA-423540-1 / Type : 35*900mm HDPE / Ch6040 (18.56m each) | I.CN.34.23750 | CON - Sec.2 - Culvert : E7-RA-423540-1 - Headwall Stitch Pour | 2025-12-09 | 2025-12-10
I2S-7688-MP-74.CN.S2.34.10.2 | Culvert ID : E7-RA-423540-1 / Type : 35*900mm HDPE / Ch6040 (18.56m each) | I.CN.34.23670 | CON - Sec.2 - Culvert : E7-RA-423540-1 - Site Prep / Detail Excavation | 2025-12-02 | 2025-12-03
I2S-7688-MP-74.CN.S2.34.10.2 | Culvert ID : E7-RA-423540-1 / Type : 35*900mm HDPE / Ch6040 (18.56m each) | I.CN.34.23680 | CON - Sec.2 - Culvert : E7-RA-423540-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2025-12-04 | 2025-12-06
I2S-7688-MP-74.CN.S2.34.10.2 | Culvert ID : E7-RA-423540-1 / Type : 35*900mm HDPE / Ch6040 (18.56m each) | I.CN.34.23720 | CON - Sec.2 - Culvert : E7-RA-423540-1 - Headwall installation | 2025-12-07 | 2025-12-07
I2S-7688-MP-74.CN.S2.34.10.2 | Culvert ID : E7-RA-423540-1 / Type : 35*900mm HDPE / Ch6040 (18.56m each) | I.CN.34.23760 | CON - Sec.2 - Culvert : E7-RA-423540-1 - Headwall Cut-off Wall Installation (FRP) | 2025-12-11 | 2025-12-12
I2S-7688-MP-74.CN.S2.34.10.2 | Culvert ID : E7-RA-423540-1 / Type : 35*900mm HDPE / Ch6040 (18.56m each) | I.CN.34.23780 | CON - Sec.2 - Culvert : E7-RA-423540-1 - Construct Scour Protection | 2025-12-13 | 2025-12-14
Culvert ID : E7-RA-423450-1 / Type : 22*900mm HDPE / Ch5948 (18.73m each) |  |  |  | 2025-11-13 | 2025-11-27
I2S-7688-MP-74.CN.S2.34.10.9 | Culvert ID : E7-RA-423450-1 / Type : 22*900mm HDPE / Ch5948 (18.73m each) | I.CN.34.26550 | CON - Sec.2 - Culvert : E7-RA-423450-1 - Site Prep / Detail Excavation | 2025-11-13 | 2025-11-14
I2S-7688-MP-74.CN.S2.34.10.9 | Culvert ID : E7-RA-423450-1 / Type : 22*900mm HDPE / Ch5948 (18.73m each) | I.CN.34.26560 | CON - Sec.2 - Culvert : E7-RA-423450-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2025-11-16 | 2025-11-16
I2S-7688-MP-74.CN.S2.34.10.9 | Culvert ID : E7-RA-423450-1 / Type : 22*900mm HDPE / Ch5948 (18.73m each) | I.CN.34.26600 | CON - Sec.2 - Culvert : E7-RA-423450-1 - Headwall installation | 2025-11-17 | 2025-11-19
I2S-7688-MP-74.CN.S2.34.10.9 | Culvert ID : E7-RA-423450-1 / Type : 22*900mm HDPE / Ch5948 (18.73m each) | I.CN.34.26610 | CON - Sec.2 - Culvert : E7-RA-423450-1 - HDPE / RCP Pipe Lay & Backfill | 2025-11-18 | 2025-11-20
I2S-7688-MP-74.CN.S2.34.10.9 | Culvert ID : E7-RA-423450-1 / Type : 22*900mm HDPE / Ch5948 (18.73m each) | I.CN.34.26630 | CON - Sec.2 - Culvert : E7-RA-423450-1 - Headwall Stitch Pour | 2025-11-21 | 2025-11-23
I2S-7688-MP-74.CN.S2.34.10.9 | Culvert ID : E7-RA-423450-1 / Type : 22*900mm HDPE / Ch5948 (18.73m each) | I.CN.34.26640 | CON - Sec.2 - Culvert : E7-RA-423450-1 - Headwall Cut-off Wall Installation (FRP) | 2025-11-24 | 2025-11-24
I2S-7688-MP-74.CN.S2.34.10.9 | Culvert ID : E7-RA-423450-1 / Type : 22*900mm HDPE / Ch5948 (18.73m each) | I.CN.34.26660 | CON - Sec.2 - Culvert : E7-RA-423450-1 - Construct Scour Protection | 2025-11-26 | 2025-11-27
Culvert ID : E7-RA-423060-1 / Type : 30*750mm HDPE / Ch5502 (13.63m each) |  |  |  | 2025-10-30 | 2025-11-12
I2S-7688-MP-74.CN.S2.34.10.10 | Culvert ID : E7-RA-423060-1 / Type : 30*750mm HDPE / Ch5502 (13.63m each) | I.CN.34.26750 | CON - Sec.2 - Culvert : E7-RA-423060-1 - Headwall Stitch Pour | 2025-11-06 | 2025-11-07
I2S-7688-MP-74.CN.S2.34.10.10 | Culvert ID : E7-RA-423060-1 / Type : 30*750mm HDPE / Ch5502 (13.63m each) | I.CN.34.26760 | CON - Sec.2 - Culvert : E7-RA-423060-1 - Headwall Cut-off Wall Installation (FRP) | 2025-11-08 | 2025-11-09
I2S-7688-MP-74.CN.S2.34.10.10 | Culvert ID : E7-RA-423060-1 / Type : 30*750mm HDPE / Ch5502 (13.63m each) | I.CN.34.26780 | CON - Sec.2 - Culvert : E7-RA-423060-1 - Construct Scour Protection | 2025-11-11 | 2025-11-12
I2S-7688-MP-74.CN.S2.34.10.10 | Culvert ID : E7-RA-423060-1 / Type : 30*750mm HDPE / Ch5502 (13.63m each) | I.CN.34.26670 | CON - Sec.2 - Culvert : E7-RA-423060-1 - Site Prep / Detail Excavation | 2025-10-30 | 2025-10-31
I2S-7688-MP-74.CN.S2.34.10.10 | Culvert ID : E7-RA-423060-1 / Type : 30*750mm HDPE / Ch5502 (13.63m each) | I.CN.34.26680 | CON - Sec.2 - Culvert : E7-RA-423060-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2025-11-01 | 2025-11-02
I2S-7688-MP-74.CN.S2.34.10.10 | Culvert ID : E7-RA-423060-1 / Type : 30*750mm HDPE / Ch5502 (13.63m each) | I.CN.34.26720 | CON - Sec.2 - Culvert : E7-RA-423060-1 - Headwall installation | 2025-11-03 | 2025-11-03
I2S-7688-MP-74.CN.S2.34.10.10 | Culvert ID : E7-RA-423060-1 / Type : 30*750mm HDPE / Ch5502 (13.63m each) | I.CN.34.26730 | CON - Sec.2 - Culvert : E7-RA-423060-1 - HDPE / RCP Pipe Lay & Backfill | 2025-11-04 | 2025-11-04
Culvert ID : E7-RD-421367-1 / Type : 3*750mm HDPE / Ch3864 (11.795m each) - RMAR
I2S-7688-MP-74.CN.S2.34.10.16 | Culvert ID : E7-RD-421367-1 / Type : 3*750mm HDPE / Ch3864 (11.795m each) - RMAR | I.CN.34.31750 | CON - Sec.2 - Culvert : E7-RD-421367-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S2.34.10.16 | Culvert ID : E7-RD-421367-1 / Type : 3*750mm HDPE / Ch3864 (11.795m each) - RMAR | I.CN.34.31760 | CON - Sec.2 - Culvert : E7-RD-421367-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S2.34.10.16 | Culvert ID : E7-RD-421367-1 / Type : 3*750mm HDPE / Ch3864 (11.795m each) - RMAR | I.CN.34.31770 | CON - Sec.2 - Culvert : E7-RD-421367-1 - Headwall installation
I2S-7688-MP-74.CN.S2.34.10.16 | Culvert ID : E7-RD-421367-1 / Type : 3*750mm HDPE / Ch3864 (11.795m each) - RMAR | I.CN.34.31780 | CON - Sec.2 - Culvert : E7-RD-421367-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S2.34.10.16 | Culvert ID : E7-RD-421367-1 / Type : 3*750mm HDPE / Ch3864 (11.795m each) - RMAR | I.CN.34.31790 | CON - Sec.2 - Culvert : E7-RD-421367-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S2.34.10.16 | Culvert ID : E7-RD-421367-1 / Type : 3*750mm HDPE / Ch3864 (11.795m each) - RMAR | I.CN.34.31800 | CON - Sec.2 - Culvert : E7-RD-421367-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S2.34.10.16 | Culvert ID : E7-RD-421367-1 / Type : 3*750mm HDPE / Ch3864 (11.795m each) - RMAR | I.CN.34.31820 | CON - Sec.2 - Culvert : E7-RD-421367-1 - Construct Scour Protection
Culvert ID : E7-RA-420670-1 / Type : 3*900mm HDPE / Ch3158 (15.22m each) |  |  |  | 2025-10-01 | 2025-10-14
I2S-7688-MP-74.CN.S2.34.10.1 | Culvert ID : E7-RA-420670-1 / Type : 3*900mm HDPE / Ch3158 (15.22m each) | I.CN.34.23790 | CON - Sec.2 - Culvert : E7-RA-420670-1 - Site Prep / Detail Excavation | 2025-10-01 | 2025-10-02
I2S-7688-MP-74.CN.S2.34.10.1 | Culvert ID : E7-RA-420670-1 / Type : 3*900mm HDPE / Ch3158 (15.22m each) | I.CN.34.23800 | CON - Sec.2 - Culvert : E7-RA-420670-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2025-10-03 | 2025-10-04
I2S-7688-MP-74.CN.S2.34.10.1 | Culvert ID : E7-RA-420670-1 / Type : 3*900mm HDPE / Ch3158 (15.22m each) | I.CN.34.23840 | CON - Sec.2 - Culvert : E7-RA-420670-1 - Headwall installation | 2025-10-06 | 2025-10-06
I2S-7688-MP-74.CN.S2.34.10.1 | Culvert ID : E7-RA-420670-1 / Type : 3*900mm HDPE / Ch3158 (15.22m each) | I.CN.34.23850 | CON - Sec.2 - Culvert : E7-RA-420670-1 - HDPE / RCP Pipe Lay & Backfill | 2025-10-07 | 2025-10-07
I2S-7688-MP-74.CN.S2.34.10.1 | Culvert ID : E7-RA-420670-1 / Type : 3*900mm HDPE / Ch3158 (15.22m each) | I.CN.34.23870 | CON - Sec.2 - Culvert : E7-RA-420670-1 - Headwall Stitch Pour | 2025-10-08 | 2025-10-09
I2S-7688-MP-74.CN.S2.34.10.1 | Culvert ID : E7-RA-420670-1 / Type : 3*900mm HDPE / Ch3158 (15.22m each) | I.CN.34.23880 | CON - Sec.2 - Culvert : E7-RA-420670-1 - Headwall Cut-off Wall Installation (FRP) | 2025-10-10 | 2025-10-11
I2S-7688-MP-74.CN.S2.34.10.1 | Culvert ID : E7-RA-420670-1 / Type : 3*900mm HDPE / Ch3158 (15.22m each) | I.CN.34.23900 | CON - Sec.2 - Culvert : E7-RA-420670-1 - Construct Scour Protection | 2025-10-13 | 2025-10-14
I2S-7688-MP-74.CN.S2.34.10.1 | Culvert ID : E7-RA-420670-1 / Type : 3*900mm HDPE / Ch3158 (15.22m each) | I.CN.34.32890 | CON - Sec.2 - Culvert : E7-RA-420670-1 - HDPE / RCP Pipe Lay & Backfill - Milestone
043 - Fencing |  |  |  | 2025-10-26 | 2026-05-03
Western Side |  |  |  | 2025-12-10 | 2026-05-03
I2S-7688-MP-74.CN.S2.43.1 | Western Side | I.CN.43.13910 | CON - Sec.2 - Fencing West Side - Ch2900-6000 | 2025-12-10 | 2026-02-03
I2S-7688-MP-74.CN.S2.43.1 | Western Side | I.CN.43.13930 | CON - Sec.2 - Fencing West Side - Ch6000-8840 | 2026-03-24 | 2026-05-03
Eastern Side |  |  |  | 2025-10-26 | 2026-03-23
I2S-7688-MP-74.CN.S2.43.2 | Eastern Side | I.CN.43.13470 | CON - Sec.2 - Fencing East Side - Ch2900-6000 | 2025-10-26 | 2025-12-09
I2S-7688-MP-74.CN.S2.43.2 | Eastern Side | I.CN.43.13920 | CON - Sec.2 - Fencing East Side - Ch6000-8840 | 2026-02-04 | 2026-03-23
045 - Access Roads |  |  |  | 2025-07-14 | 2025-11-30
Access/Temp |  |  |  | 2025-07-14 | 2025-07-22
I2S-7688-MP-74.CN.S2.45.1 | Access/Temp | I.CN.45.14420 | CON - Sec.2 - Gate 4 (8150) - Install temp pavement /portable traffic sign | 2025-07-14 | 2025-07-22
RMAR |  |  |  | 2025-11-13 | 2025-11-30
I2S-7688-MP-74.CN.S2.45.2 | RMAR | I.CN.45.14220 | CON - Sec.2 - Prep RMAR Road - East - 2900 to 6000 | 2025-11-13 | 2025-11-21
I2S-7688-MP-74.CN.S2.45.2 | RMAR | I.CN.45.14280 | CON - Sec.2 - Prep RMAR Road - East - 6000 to 8840 | 2025-11-22 | 2025-11-30
050 - Trackwork |  |  |  | 2026-05-12 | 2026-07-26
Place Bottom Ballast |  |  |  | 2026-05-17 | 2026-05-29
I2S-7688-MP-74.CN.S2.50.15 | Place Bottom Ballast | I.CN.50.13350 | CON - Sec.2 - Place Bottom Ballast - 500m/day - 5500 to 6000 (500m) | 2026-05-22 | 2026-05-22
I2S-7688-MP-74.CN.S2.50.15 | Place Bottom Ballast | I.CN.50.13360 | CON - Sec.2 - Place Bottom Ballast - 500m/day - 6000 to 6500 (500m) | 2026-05-23 | 2026-05-23
I2S-7688-MP-74.CN.S2.50.15 | Place Bottom Ballast | I.CN.50.13370 | CON - Sec.2 - Place Bottom Ballast - 500m/day - 6500 to 7000 (500m) | 2026-05-24 | 2026-05-24
I2S-7688-MP-74.CN.S2.50.15 | Place Bottom Ballast | I.CN.50.13380 | CON - Sec.2 - Place Bottom Ballast - 500m/day - 7000 to 7500 (500m) | 2026-05-26 | 2026-05-26
I2S-7688-MP-74.CN.S2.50.15 | Place Bottom Ballast | I.CN.50.13390 | CON - Sec.2 - Place Bottom Ballast - 500m/day - 7500 to 8000 (500m) | 2026-05-27 | 2026-05-27
I2S-7688-MP-74.CN.S2.50.15 | Place Bottom Ballast | I.CN.50.13400 | CON - Sec.2 - Place Bottom Ballast - 500m/day - 8000 to 8500 (500m) | 2026-05-28 | 2026-05-28
I2S-7688-MP-74.CN.S2.50.15 | Place Bottom Ballast | I.CN.50.13410 | CON - Sec.2 - Place Bottom Ballast - 500m/day - 8500 to 9000 (500m) | 2026-05-29 | 2026-05-29
I2S-7688-MP-74.CN.S2.50.15 | Place Bottom Ballast | I.CN.50.13300 | CON - Sec.2 - Place Bottom Ballast - 500m/day - 2900 to 3500 (600m) | 2026-05-17 | 2026-05-17
I2S-7688-MP-74.CN.S2.50.15 | Place Bottom Ballast | I.CN.50.13310 | CON - Sec.2 - Place Bottom Ballast - 500m/day - 3500 to 4000 (500m) | 2026-05-18 | 2026-05-18
I2S-7688-MP-74.CN.S2.50.15 | Place Bottom Ballast | I.CN.50.13320 | CON - Sec.2 - Place Bottom Ballast - 500m/day - 4000 to 4500 (500m) | 2026-05-19 | 2026-05-19
I2S-7688-MP-74.CN.S2.50.15 | Place Bottom Ballast | I.CN.50.13330 | CON - Sec.2 - Place Bottom Ballast - 500m/day - 4500 to 5000 (500m) | 2026-05-20 | 2026-05-20
I2S-7688-MP-74.CN.S2.50.15 | Place Bottom Ballast | I.CN.50.13340 | CON - Sec.2 - Place Bottom Ballast - 500m/day - 5000 to 5500 (500m) | 2026-05-21 | 2026-05-21
Sleeper Distribution |  |  |  | 2026-05-12 | 2026-06-07
I2S-7688-MP-74.CN.S2.50.1 | Sleeper Distribution | I.CN.50.4700 | CON - Sec.2 - Sleeper Distribution - 860m/day - 2800 to 3660 (860m) | 2026-05-30 | 2026-05-30
I2S-7688-MP-74.CN.S2.50.1 | Sleeper Distribution | I.CN.50.4710 | CON - Sec.2 - Sleeper Distribution - 860m/day - 3660 to 4520 (860m) | 2026-05-31 | 2026-05-31
I2S-7688-MP-74.CN.S2.50.1 | Sleeper Distribution | I.CN.50.4720 | CON - Sec.2 - Sleeper Distribution - 860m/day - 4360 to 5050 (860m) | 2026-06-01 | 2026-06-01
I2S-7688-MP-74.CN.S2.50.1 | Sleeper Distribution | I.CN.50.4730 | CON - Sec.2 - Sleeper Distribution - 860m/day - 5050 to 5740 (860m) | 2026-06-02 | 2026-06-02
I2S-7688-MP-74.CN.S2.50.1 | Sleeper Distribution | I.CN.50.4740 | CON - Sec.2 - Sleeper Distribution - 860m/day - 5740 to 6430 (860m) | 2026-06-03 | 2026-06-03
I2S-7688-MP-74.CN.S2.50.1 | Sleeper Distribution | I.CN.50.4750 | CON - Sec.2 - Sleeper Distribution - 860m/day - 6430 to 7120 (860m) | 2026-06-04 | 2026-06-04
I2S-7688-MP-74.CN.S2.50.1 | Sleeper Distribution | I.CN.50.4760 | CON - Sec.2 - Sleeper Distribution - 860m/day - 7120 to 7810 (860m) | 2026-06-06 | 2026-06-06
I2S-7688-MP-74.CN.S2.50.1 | Sleeper Distribution | I.CN.50.4770 | CON - Sec.2 - Sleeper Distribution - 860m/day - 7810 to 8500 (860m) | 2026-06-07 | 2026-06-07
I2S-7688-MP-74.CN.S2.50.1 | Sleeper Distribution | I.CN.50.14290 | CON - Sec.2 - Intermediate Sleeper Stockpiles - Sec.2 | 2026-05-12 | 2026-05-12
Sleeper Laying |  |  |  | 2026-06-02 | 2026-06-10
I2S-7688-MP-74.CN.S2.50.3 | Sleeper Laying | I.CN.50.3800 | CON - Sec.2 - Sleeper Laying - 800m/day - 5020 to 5820 | 2026-06-06 | 2026-06-06
I2S-7688-MP-74.CN.S2.50.3 | Sleeper Laying | I.CN.50.3770 | CON - Sec.2 - Sleeper Laying - 800m/day - 2620 to 3420 | 2026-06-02 | 2026-06-02
I2S-7688-MP-74.CN.S2.50.3 | Sleeper Laying | I.CN.50.3780 | CON - Sec.2 - Sleeper Laying - 800m/day - 3420 to 4220 | 2026-06-03 | 2026-06-03
I2S-7688-MP-74.CN.S2.50.3 | Sleeper Laying | I.CN.50.3810 | CON - Sec.2 - Sleeper Laying - 800m/day - 5820 to 6620 | 2026-06-07 | 2026-06-07
I2S-7688-MP-74.CN.S2.50.3 | Sleeper Laying | I.CN.50.3820 | CON - Sec.2 - Sleeper Laying - 800m/day - 6620 to 7420 | 2026-06-08 | 2026-06-08
I2S-7688-MP-74.CN.S2.50.3 | Sleeper Laying | I.CN.50.3830 | CON - Sec.2 - Sleeper Laying - 800m/day - South of Ironbong 7420 to 8220 | 2026-06-09 | 2026-06-09
I2S-7688-MP-74.CN.S2.50.3 | Sleeper Laying | I.CN.50.3840 | CON - Sec.2 - Sleeper Laying - 800m/day - North of Ironbong 8220 to 9020 | 2026-06-10 | 2026-06-10
I2S-7688-MP-74.CN.S2.50.3 | Sleeper Laying | I.CN.50.3790 | CON - Sec.2 - Sleeper Laying - 800m/day - 4220 to 5020 | 2026-06-04 | 2026-06-04
Rail Distribution |  |  |  | 2026-06-04 | 2026-06-11
I2S-7688-MP-74.CN.S2.50.2 | Rail Distribution | I.CN.50.4310 | CON - Sec.2 - Rail Distribution - 1000m/day - 3190 to 4180 | 2026-06-04 | 2026-06-04
I2S-7688-MP-74.CN.S2.50.2 | Rail Distribution | I.CN.50.4320 | CON - Sec.2 - Rail Distribution - 1000m/day - 4180 to 5170 | 2026-06-06 | 2026-06-06
I2S-7688-MP-74.CN.S2.50.2 | Rail Distribution | I.CN.50.4330 | CON - Sec.2 - Rail Distribution - 1000m/day - 5170 to 6160 | 2026-06-07 | 2026-06-07
I2S-7688-MP-74.CN.S2.50.2 | Rail Distribution | I.CN.50.4360 | CON - Sec.2 - Rail Distribution - 1000m/day - North of Ironbong - 8140 to 9130 | 2026-06-11 | 2026-06-11
I2S-7688-MP-74.CN.S2.50.2 | Rail Distribution | I.CN.50.4340 | CON - Sec.2 - Rail Distribution - 1000m/day - 6160 to 7150 | 2026-06-08 | 2026-06-08
I2S-7688-MP-74.CN.S2.50.2 | Rail Distribution | I.CN.50.4350 | CON - Sec.2 - Rail Distribution - 1000m/day - South of Ironbong - 7150 to 8140 | 2026-06-09 | 2026-06-09
Rail Laying |  |  |  | 2026-06-08 | 2026-06-16
I2S-7688-MP-74.CN.S2.50.4 | Rail Laying | I.CN.50.3230 | CON - Sec.2 - Rail Laying - 550m/day - 3820 to 4540 | 2026-06-09 | 2026-06-09
I2S-7688-MP-74.CN.S2.50.4 | Rail Laying | I.CN.50.3240 | CON - Sec.2 - Rail Laying - 550m/day - 4540 to 5260 | 2026-06-10 | 2026-06-10
I2S-7688-MP-74.CN.S2.50.4 | Rail Laying | I.CN.50.3250 | CON - Sec.2 - Rail Laying - 550m/day - 5260 to 5980 | 2026-06-11 | 2026-06-11
I2S-7688-MP-74.CN.S2.50.4 | Rail Laying | I.CN.50.3260 | CON - Sec.2 - Rail Laying - 550m/day - 5980 to 6700 | 2026-06-12 | 2026-06-12
I2S-7688-MP-74.CN.S2.50.4 | Rail Laying | I.CN.50.3270 | CON - Sec.2 - Rail Laying - 550m/day - 6700 to 7420 | 2026-06-13 | 2026-06-13
I2S-7688-MP-74.CN.S2.50.4 | Rail Laying | I.CN.50.3280 | CON - Sec.2 - Rail Laying - 550m/day - South of Ironbong - 7420 to 8140 | 2026-06-14 | 2026-06-14
I2S-7688-MP-74.CN.S2.50.4 | Rail Laying | I.CN.50.3290 | CON - Sec.2 - Rail Laying - 550m/day - North of Ironbong - 8140 to 9130 | 2026-06-16 | 2026-06-16
I2S-7688-MP-74.CN.S2.50.4 | Rail Laying | I.CN.50.3220 | CON - Sec.2 - Rail Laying - 550m/day - 3100 to 3820 | 2026-06-08 | 2026-06-08
Flash Butt Welding and clip up |  |  |  | 2026-06-09 | 2026-06-21
I2S-7688-MP-74.CN.S2.50.5 | Flash Butt Welding and clip up | I.CN.50.2860 | CON - Sec.2 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 6160 to 7150 | 2026-06-16 | 2026-06-17
I2S-7688-MP-74.CN.S2.50.5 | Flash Butt Welding and clip up | I.CN.50.2870 | CON - Sec.2 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - South of Ironbong - 7150 to 8140 | 2026-06-18 | 2026-06-19
I2S-7688-MP-74.CN.S2.50.5 | Flash Butt Welding and clip up | I.CN.50.2880 | CON - Sec.2 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - North of Ironbong - 8140 to 9130 | 2026-06-20 | 2026-06-21
I2S-7688-MP-74.CN.S2.50.5 | Flash Butt Welding and clip up | I.CN.50.2830 | CON - Sec.2 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 2695 to 3520 | 2026-06-09 | 2026-06-10
I2S-7688-MP-74.CN.S2.50.5 | Flash Butt Welding and clip up | I.CN.50.2840 | CON - Sec.2 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 3520 to 5170 | 2026-06-11 | 2026-06-12
I2S-7688-MP-74.CN.S2.50.5 | Flash Butt Welding and clip up | I.CN.50.2850 | CON - Sec.2 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 5170 to 6160 | 2026-06-13 | 2026-06-14
Place Top Ballast Initial |  |  |  | 2026-06-17 | 2026-06-22
I2S-7688-MP-74.CN.S2.50.6 | Place Top Ballast Initial | I.CN.50.1440 | CON - Sec.2 - Place Top Ballast Initial - 1500m/day - 3220 to 4720 | 2026-06-17 | 2026-06-17
I2S-7688-MP-74.CN.S2.50.6 | Place Top Ballast Initial | I.CN.50.1450 | CON - Sec.2 - Place Top Ballast Initial - 1500m/day - 4720 to 6220 | 2026-06-18 | 2026-06-18
I2S-7688-MP-74.CN.S2.50.6 | Place Top Ballast Initial | I.CN.50.2600 | CON - Sec.2 - Place Top Ballast Initial - 1500m/day - 6220 to 7720 | 2026-06-20 | 2026-06-20
I2S-7688-MP-74.CN.S2.50.6 | Place Top Ballast Initial | I.CN.50.2610 | CON - Sec.2 - Place Top Ballast Initial - 1500m/day - 7720 to 9220 | 2026-06-22 | 2026-06-22
Traverse & Level GEDO |  |  |  | 2026-06-23 | 2026-06-23
I2S-7688-MP-74.CN.S2.50.14 | Traverse & Level GEDO | I.CN.50.18150 | CON - Sec.2 - Traverse and level Gedo Control - 4220 to 8220 | 2026-06-23 | 2026-06-23
Surfacing Firsts |  |  |  | 2026-06-24 | 2026-06-24
I2S-7688-MP-74.CN.S2.50.7 | Surfacing Firsts | I.CN.50.2510 | CON - Sec.2 - Surfacing Firsts - 4000m/day - 4220 to 8220 | 2026-06-24 | 2026-06-24
Surfacing Seconds |  |  |  | 2026-06-26 | 2026-06-26
I2S-7688-MP-74.CN.S2.50.8 | Surfacing Seconds | I.CN.50.2420 | CON - Sec.2 - Surfacing Seconds - 4000m/day - 4220 to 8220 | 2026-06-26 | 2026-06-26
Top Ballast Finals |  |  |  | 2026-06-27 | 2026-06-28
I2S-7688-MP-74.CN.S2.50.9 | Top Ballast Finals | I.CN.50.2290 | CON - Sec.2 - Top Ballast Finals - 3000m/day - 3000 to 6000 | 2026-06-27 | 2026-06-27
I2S-7688-MP-74.CN.S2.50.9 | Top Ballast Finals | I.CN.50.2300 | CON - Sec.2 - Top Ballast Finals - 3000m/day - 6000 to 9000 | 2026-06-28 | 2026-06-28
Surfacing Final |  |  |  | 2026-06-29 | 2026-06-29
I2S-7688-MP-74.CN.S2.50.10 | Surfacing Final | I.CN.50.2230 | CON - Sec.2 - Surfacing Final - 6000m/day - 6000 to 9000 | 2026-06-29 | 2026-06-29
Destressing |  |  |  | 2026-06-30 | 2026-07-03
I2S-7688-MP-74.CN.S2.50.11 | Destressing | I.CN.50.1930 | CON - Sec.2 - Destressing - 1200m/day - 3600 to 4800 | 2026-06-30 | 2026-06-30
I2S-7688-MP-74.CN.S2.50.11 | Destressing | I.CN.50.1940 | CON - Sec.2 - Destressing - 1200m/day - 4800 to 6000 | 2026-07-01 | 2026-07-01
I2S-7688-MP-74.CN.S2.50.11 | Destressing | I.CN.50.1950 | CON - Sec.2 - Destressing - 1200m/day - 6000 to 7200 | 2026-07-02 | 2026-07-02
I2S-7688-MP-74.CN.S2.50.11 | Destressing | I.CN.50.1960 | CON - Sec.2 - Destressing - 1200m/day - 7200 to 8400 | 2026-07-03 | 2026-07-03
Corrections + Signage + Rubber Xings |  |  |  | 2026-07-22 | 2026-07-26
I2S-7688-MP-74.CN.S2.50.12 | Corrections + Signage + Rubber Xings | I.CN.50.1720 | CON - Sec.2 - Corrections + Signage - 2000m/day - 4000 - 6000 | 2026-07-22 | 2026-07-23
I2S-7688-MP-74.CN.S2.50.12 | Corrections + Signage + Rubber Xings | I.CN.50.1730 | CON - Sec.2 - Corrections + Signage - 2000m/day - 6000 - 8000 | 2026-07-23 | 2026-07-24
I2S-7688-MP-74.CN.S2.50.12 | Corrections + Signage + Rubber Xings | I.CN.50.1740 | CON - Sec.2 - Corrections + Signage - 2000m/day - 8000 - 10000 | 2026-07-24 | 2026-07-26
Track Joint Inspection |  |  |  | 2026-07-04 | 2026-07-04
I2S-7688-MP-74.CN.S2.50.13 | Track Joint Inspection | I.CN.50.1630 | CON - Sec.2 - Track Joint Inspection - 5000m/day - 5000 - 10000 | 2026-07-04 | 2026-07-04
062 - Bridges |  |  |  | 2025-11-09 | 2026-05-10
Ulandra Creek Bridge (over Creek and Road ) - BR702 - 1500 SUPER-T (ARTC) |  |  |  | 2025-11-09 | 2026-05-10
Preliminaries |  |  |  | 2025-11-09 | 2025-11-17
I2S-7688-MP-74.CN.S2.62.1.1 | Preliminaries | I.CN.62.15050 | CON - Sec.2 - Ulandra Ck Br - Bridge site prep /Temp Fence/Road Barriers | 2025-11-09 | 2025-11-11
I2S-7688-MP-74.CN.S2.62.1.1 | Preliminaries | I.CN.62.15060 | CON - Sec.2 - Ulandra Ck Br - construct site access (300m) from Gate 3 | 2025-11-09 | 2025-11-13
I2S-7688-MP-74.CN.S2.62.1.1 | Preliminaries | I.CN.62.15150 | CON - Sec.2 - Ulandra Ck Br - Construct laydown area /Causeway (inc pipes) | 2025-11-14 | 2025-11-17
Piling |  |  |  | 2025-11-12 | 2025-12-22
Platforms |  |  |  | 2025-11-12 | 2025-11-19
I2S-7688-MP-74.CN.S2.62.1.2.1 | Platforms | I.CN.62.15110 | CON - Sec.2 - Ulandra Ck Br - Excavate platform for piling pad | 2025-11-12 | 2025-11-17
I2S-7688-MP-74.CN.S2.62.1.2.1 | Platforms | I.CN.62.15160 | CON - Sec.2 - Ulandra Ck Br - Place and test platform | 2025-11-18 | 2025-11-19
Drill Piles |  |  |  | 2025-12-12 | 2025-12-18
I2S-7688-MP-74.CN.S2.62.1.2.3 | Drill Piles | I.CN.62.15120 | CON - Sec.2 - Ulandra Ck Br - Demobilise piling rig | 2025-12-18 | 2025-12-18
I2S-7688-MP-74.CN.S2.62.1.2.3 | Drill Piles | I.CN.62.15170 | CON - Sec.2 - Ulandra Ck Br - Mobilise piling rig | 2025-12-12 | 2025-12-12
I2S-7688-MP-74.CN.S2.62.1.2.3 | Drill Piles | I.CN.62.15180 | CON - Sec.2 - Ulandra Ck Br - piling consists of 6 x 1200mm dia bored concrete piles | 2025-12-13 | 2025-12-17
I2S-7688-MP-74.CN.S2.62.1.2.3 | Drill Piles | I.CN.62.23080 | CON - Sec.2 - Ulandra Ck Br - piling consists of 6 x 1200mm dia bored concrete piles - Milestone
Piles Concrete |  |  |  | 2025-12-18 | 2025-12-22
I2S-7688-MP-74.CN.S2.62.1.2.4 | Piles Concrete | I.CN.62.15130 | CON - Sec.2 - Ulandra Ck Br - Place pile concrete | 2025-12-18 | 2025-12-22
Abutments |  |  |  | 2025-12-23 | 2026-01-24
Earthworks |  |  |  | 2025-12-23 | 2026-01-08
I2S-7688-MP-74.CN.S2.62.1.7.8 | Earthworks | I.CN.62.15220 | CON - Sec.2 - Ulandra Ck Br - Site prep Abutment Footings / blinding | 2025-12-23 | 2026-01-05
I2S-7688-MP-74.CN.S2.62.1.7.8 | Earthworks | I.CN.62.15230 | CON - Sec.2 - Ulandra Ck Br - Detailed Earthworks Abutments | 2026-01-06 | 2026-01-08
South |  |  |  | 2026-01-14 | 2026-01-24
I2S-7688-MP-74.CN.S2.62.1.7.3 | South | I.CN.62.15260 | CON - Sec.2 - Ulandra Ck Br - FRP Cill Beam - South Abutment | 2026-01-14 | 2026-01-19
I2S-7688-MP-74.CN.S2.62.1.7.3 | South | I.CN.62.22040 | CON - Sec.2 - Ulandra Ck Br - FRP Restraint Block - South Abutment
I2S-7688-MP-74.CN.S2.62.1.7.3 | South | I.CN.62.15240 | CON - Sec.2 - Ulandra Ck Br - FRP Wing Wall - South Abutment | 2026-01-20 | 2026-01-24
Central Pier
I2S-7688-MP-74.CN.S2.62.1.7.2 | Central Pier | I.CN.62.22050 | CON - Sec.2 - Ulandra Ck Br - FRP Restraint Block - Central Pier
I2S-7688-MP-74.CN.S2.62.1.7.2 | Central Pier | I.CN.62.22020 | CON - Sec.2 - Ulandra Ck Br - FRP Column Extension - Central Pier
I2S-7688-MP-74.CN.S2.62.1.7.2 | Central Pier | I.CN.62.22030 | CON - Sec.2 - Ulandra Ck Br - FRP Headstock - Central Pier
North |  |  |  | 2026-01-09 | 2026-01-19
I2S-7688-MP-74.CN.S2.62.1.7.1 | North | I.CN.62.22060 | CON - Sec.2 - Ulandra Ck Br - FRP Restraint Block - North Abutment
I2S-7688-MP-74.CN.S2.62.1.7.1 | North | I.CN.62.15250 | CON - Sec.2 - Ulandra Ck Br - FRP Cill Beam - North Abutment | 2026-01-09 | 2026-01-13
I2S-7688-MP-74.CN.S2.62.1.7.1 | North | I.CN.62.15270 | CON - Sec.2 - Ulandra Ck Br - FRP Wing Wall - North Abutment | 2026-01-14 | 2026-01-19
Superstructure |  |  |  | 2025-12-23 | 2026-02-08
I2S-7688-MP-74.CN.S2.62.1.4 | Superstructure | I.CN.62.15080 | CON - Sec.2 - Ulandra Ck Br - Delivery /QA of PSC Planks, 14 metres long (x6 -2 spans - T 12) | 2025-12-23 | 2026-01-05
I2S-7688-MP-74.CN.S2.62.1.4 | Superstructure | I.CN.62.15380 | CON - Sec.2 - Ulandra Ck Br - Install bridge bearings | 2026-02-01 | 2026-02-02
I2S-7688-MP-74.CN.S2.62.1.4 | Superstructure | I.CN.62.15390 | CON - Sec.2 - Ulandra Ck Br - Install/Lift of PSC Planks, 14 metres long (x6 -2 spans - T 12) | 2026-02-06 | 2026-02-08
I2S-7688-MP-74.CN.S2.62.1.4 | Superstructure | I.CN.62.22740 | CON - Sec.2 - Ulandra Ck Br - Crane Pads for Crane Lift
Approach Slab / Deck |  |  |  | 2026-02-22 | 2026-04-09
I2S-7688-MP-74.CN.S2.62.1.3 | Approach Slab / Deck | I.CN.62.22070 | CON - Sec.2 - Ulandra Ck Br - Install & Stress Tie Bars
I2S-7688-MP-74.CN.S2.62.1.3 | Approach Slab / Deck | I.CN.62.20790 | CON - Sec.2 - Ulandra Ck Br - FRP Approach Slab South | 2026-03-01 | 2026-03-06
I2S-7688-MP-74.CN.S2.62.1.3 | Approach Slab / Deck | I.CN.62.15300 | CON - Sec.2 - Ulandra Ck Br - FRP Approach Slab North | 2026-02-23 | 2026-02-28
I2S-7688-MP-74.CN.S2.62.1.3 | Approach Slab / Deck | I.CN.62.15320 | CON - Sec.2 - Ulandra Ck Br - Bridging Strips, compressible fillers and isolation inserts | 2026-02-22 | 2026-02-22
I2S-7688-MP-74.CN.S2.62.1.3 | Approach Slab / Deck | I.CN.62.15330 | CON - Sec.2 - Ulandra Ck Br - Install Expansion Joints - Abutments | 2026-04-08 | 2026-04-09
Bridge Finishing Works |  |  |  | 2026-03-07 | 2026-05-10
I2S-7688-MP-74.CN.S2.62.1.5 | Bridge Finishing Works | I.CN.62.15310 | CON - Sec.2 - Ulandra Ck Br - Batter Slopes & Install "Nylex Cordrain" fixed to vertical face of ballast walls | 2026-03-07 | 2026-03-10
I2S-7688-MP-74.CN.S2.62.1.5 | Bridge Finishing Works | I.CN.62.15340 | CON - Sec.2 - Ulandra Ck Br - Install handrail raking/horizontal - stairs /footpath | 2026-04-10 | 2026-04-12
I2S-7688-MP-74.CN.S2.62.1.5 | Bridge Finishing Works | I.CN.62.15350 | CON - Sec.2 - Ulandra Ck Br - Install access walkways | 2026-04-13 | 2026-04-15
I2S-7688-MP-74.CN.S2.62.1.5 | Bridge Finishing Works | I.CN.62.15360 | CON - Sec.2 - Ulandra Ck Br - Install maintenance access stairs / handrails | 2026-04-16 | 2026-04-18
I2S-7688-MP-74.CN.S2.62.1.5 | Bridge Finishing Works | I.CN.62.19290 | CON - Sec.2 - Ulandra Ck Br - Completion |  | 2026-05-10
I2S-7688-MP-74.CN.S2.62.1.5 | Bridge Finishing Works | I.CN.62.20810 | CON - Sec.2 - Ulandra Ck Br - Install Handrail stairs & footpath | 2026-03-18 | 2026-03-20
I2S-7688-MP-74.CN.S2.62.1.5 | Bridge Finishing Works | I.CN.62.20900 | CON - Sec.2 - Ulandra Ck Br - Scour protection 2off | 2026-05-01 | 2026-05-03
I2S-7688-MP-74.CN.S2.62.1.5 | Bridge Finishing Works | I.CN.62.20910 | CON - Sec.2 - Ulandra Ck Br - Install Handrail north/south | 2026-05-04 | 2026-05-06
I2S-7688-MP-74.CN.S2.62.1.5 | Bridge Finishing Works | I.CN.62.22860 | CON - Sec.2 - Ulandra Ck Br - Install CSR Ducting
I2S-7688-MP-74.CN.S2.62.1.5 | Bridge Finishing Works | I.CN.62.15090 | CON - Sec.2 - Ulandra Ck Br - FRP Footpath/Steps | 2026-03-26 | 2026-04-07
065 - Crossings |  |  |  | 2025-10-27 | 2026-09-22
Fauna Crossing |  |  |  | 2026-09-18 | 2026-09-22
I2S-7688-MP-74.CN.S2.65.4 | Fauna Crossing | I.CN.65.17930 | CON - Sec.2 - Install fauna crossing [2 x poles with rope bridge - CH7800] | 2026-09-22 | 2026-09-22
I2S-7688-MP-74.CN.S2.65.4 | Fauna Crossing | I.CN.65.12900 | CON - Sec.2 - Install fauna crossing [2 x poles foundations /cure - CH5500] | 2026-09-18 | 2026-09-19
I2S-7688-MP-74.CN.S2.65.4 | Fauna Crossing | I.CN.65.12910 | CON - Sec.2 - Install fauna crossing [2 x poles foundations /cure - CH7800] | 2026-09-20 | 2026-09-21
I2S-7688-MP-74.CN.S2.65.4 | Fauna Crossing | I.CN.65.17920 | CON - Sec.2 - Install fauna crossing [2 x poles with rope bridge - CH5500] | 2026-09-20 | 2026-09-20
Public LX - Ironbong Road (PU8160) - Active / Junee LGA - RX-5 |  |  |  | 2025-11-07 | 2026-07-02
Earthworks/Drainage |  |  |  | 2025-12-01 | 2025-12-13
Culvert ID : E2-RD-425720-1 / Type : 30*900mm HDPE / Ch8227 (25.99m each) |  |  |  | 2025-12-01 | 2025-12-12
I2S-7688-MP-74.CN.S2.65.1.5.1 | Culvert ID : E2-RD-425720-1 / Type : 30*900mm HDPE / Ch8227 (25.99m each) | I.CN.65.15150 | CON - Sec.2 - Public LX - Culvert : E2-RD-425720-1 - Construct Scour Protection | 2025-12-09 | 2025-12-12
I2S-7688-MP-74.CN.S2.65.1.5.1 | Culvert ID : E2-RD-425720-1 / Type : 30*900mm HDPE / Ch8227 (25.99m each) | I.CN.65.18770 | CON - Sec.2 - Public LX - Culvert : E2-RD-425720-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S2.65.1.5.1 | Culvert ID : E2-RD-425720-1 / Type : 30*900mm HDPE / Ch8227 (25.99m each) | I.CN.65.15130 | CON - Sec.2 - Public LX - Culvert : E2-RD-425720-1 - Site Prep / Detail Excavation | 2025-12-01 | 2025-12-02
I2S-7688-MP-74.CN.S2.65.1.5.1 | Culvert ID : E2-RD-425720-1 / Type : 30*900mm HDPE / Ch8227 (25.99m each) | I.CN.65.19121 | CON - Sec.2 - Public LX - Culvert : E2-RD-425720-1 - Headwall installation
I2S-7688-MP-74.CN.S2.65.1.5.1 | Culvert ID : E2-RD-425720-1 / Type : 30*900mm HDPE / Ch8227 (25.99m each) | I.CN.65.19131 | CON - Sec.2 - Public LX - Culvert : E2-RD-425720-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S2.65.1.5.1 | Culvert ID : E2-RD-425720-1 / Type : 30*900mm HDPE / Ch8227 (25.99m each) | I.CN.65.19141 | CON - Sec.2 - Public LX - Culvert : E2-RD-425720-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S2.65.1.5.1 | Culvert ID : E2-RD-425720-1 / Type : 30*900mm HDPE / Ch8227 (25.99m each) | I.CN.65.15140 | CON - Sec.2 - Public LX - Culvert : E2-RD-425720-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2025-12-03 | 2025-12-11
Culvert ID : E2-RD-425810-1 / Type : 8*900mm RCP4 / Ch8292 (19.56m each) |  |  |  | 2025-12-03 | 2025-12-13
I2S-7688-MP-74.CN.S2.65.1.5.2 | Culvert ID : E2-RD-425810-1 / Type : 8*900mm RCP4 / Ch8292 (19.56m each) | I.CN.65.18780 | CON - Sec.2 - Public LX - Culvert : E2-RD-425810-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S2.65.1.5.2 | Culvert ID : E2-RD-425810-1 / Type : 8*900mm RCP4 / Ch8292 (19.56m each) | I.CN.65.17560 | CON - Sec.2 - Public LX - Culvert : E2-RD-425810-1 - Site Prep / Detail Excavation | 2025-12-03 | 2025-12-03
I2S-7688-MP-74.CN.S2.65.1.5.2 | Culvert ID : E2-RD-425810-1 / Type : 8*900mm RCP4 / Ch8292 (19.56m each) | I.CN.65.17570 | CON - Sec.2 - Public LX - Culvert : E2-RD-425810-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2025-12-12 | 2025-12-12
I2S-7688-MP-74.CN.S2.65.1.5.2 | Culvert ID : E2-RD-425810-1 / Type : 8*900mm RCP4 / Ch8292 (19.56m each) | I.CN.65.17580 | CON - Sec.2 - Public LX - Culvert : E2-RD-425810-1 - Construct Scour protection | 2025-12-13 | 2025-12-13
I2S-7688-MP-74.CN.S2.65.1.5.2 | Culvert ID : E2-RD-425810-1 / Type : 8*900mm RCP4 / Ch8292 (19.56m each) | I.CN.65.19661 | CON - Sec.2 - Public LX - Culvert : E2-RD-425810-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S2.65.1.5.2 | Culvert ID : E2-RD-425810-1 / Type : 8*900mm RCP4 / Ch8292 (19.56m each) | I.CN.65.19641 | CON - Sec.2 - Public LX - Culvert : E2-RD-425810-1 - Headwall installation
I2S-7688-MP-74.CN.S2.65.1.5.2 | Culvert ID : E2-RD-425810-1 / Type : 8*900mm RCP4 / Ch8292 (19.56m each) | I.CN.65.19651 | CON - Sec.2 - Public LX - Culvert : E2-RD-425810-1 - HDPE / RCP Pipe Lay & Backfill
Civils |  |  |  | 2025-11-07 | 2025-12-20
I2S-7688-MP-74.CN.S2.65.1.1 | Civils | I.CN.65.15230 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Civil Works complete |  | 2025-12-20
I2S-7688-MP-74.CN.S2.65.1.1 | Civils | I.CN.65.13200 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Local Cable Route (CSR) construction - pit and pipe | 2025-12-16 | 2025-12-16
I2S-7688-MP-74.CN.S2.65.1.1 | Civils | I.CN.65.13210 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - ULX/URX construction - pit and pipe | 2025-12-17 | 2025-12-17
I2S-7688-MP-74.CN.S2.65.1.1 | Civils | I.CN.65.13220 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Installation of LX Hut Foundations | 2025-12-18 | 2025-12-18
I2S-7688-MP-74.CN.S2.65.1.1 | Civils | I.CN.65.13230 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Installation of booms/lights foundations | 2025-12-19 | 2025-12-19
I2S-7688-MP-74.CN.S2.65.1.1 | Civils | I.CN.65.13240 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Installation of SIgnage foundations | 2025-12-20 | 2025-12-20
I2S-7688-MP-74.CN.S2.65.1.1 | Civils | I.CN.11.14220 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Establish site access & egress with traffic management | 2025-11-07 | 2025-11-07
I2S-7688-MP-74.CN.S2.65.1.1 | Civils | I.CN.11.14370 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Construct Ironbong Road Diversion | 2025-11-07 | 2025-11-19
Roadworks |  |  |  | 2025-12-14 | 2026-02-14
I2S-7688-MP-74.CN.S2.65.1.6 | Roadworks | I.CN.65.15160 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Cut - 320ccm - Soil - Earthworks to Raise Road | 2025-12-14 | 2025-12-14
I2S-7688-MP-74.CN.S2.65.1.6 | Roadworks | I.CN.65.15170 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Pavement type A Unsealed (210m2) | 2025-12-16 | 2025-12-17
I2S-7688-MP-74.CN.S2.65.1.6 | Roadworks | I.CN.65.15260 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Batter face area (8185 m3) | 2025-12-18 | 2025-12-23
I2S-7688-MP-74.CN.S2.65.1.6 | Roadworks | I.CN.65.15270 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Seal / Linemarking | 2026-01-05 | 2026-01-06
I2S-7688-MP-74.CN.S2.65.1.6 | Roadworks | I.CN.65.18070 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Prime & Cure - Pavement type B sealed (6870 m3) | 2025-12-18 | 2025-12-23
I2S-7688-MP-74.CN.S2.65.1.6 | Roadworks | I.CN.31.6850 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Fill - PU8160 - 10,500ccm | 2026-02-01 | 2026-02-14
I2S-7688-MP-74.CN.S2.65.1.6 | Roadworks | I.CN.65.18080 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Reopen Ironbong Road (stage 3) |  | 2026-01-06
Trackworks |  |  |  | 2026-06-16 | 2026-06-18
I2S-7688-MP-74.CN.S2.65.1.7 | Trackworks | I.CN.65.15200 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Tie-in works to foundation block | 2026-06-18 | 2026-06-18
I2S-7688-MP-74.CN.S2.65.1.7 | Trackworks | I.CN.65.15180 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Place Foundation Block and T-Kerbstone | 2026-06-16 | 2026-06-16
I2S-7688-MP-74.CN.S2.65.1.7 | Trackworks | I.CN.65.15190 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Place and compact ballast between foundation block (after road | 2026-06-17 | 2026-06-17
Ancillary |  |  |  | 2026-06-19 | 2026-06-20
I2S-7688-MP-74.CN.S2.65.1.8 | Ancillary | I.CN.65.15210 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Install Fencing /Landscaping | 2026-06-19 | 2026-06-19
I2S-7688-MP-74.CN.S2.65.1.8 | Ancillary | I.CN.65.15220 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Install Signage | 2026-06-20 | 2026-06-20
Electrical and Mechanical |  |  |  | 2026-03-02 | 2026-06-28
I2S-7688-MP-74.CN.S2.65.1.2 | Electrical and Mechanical | I.CN.65.15860 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - LX Electrical and Mechanical Complete | 2026-06-28 | 2026-06-28
I2S-7688-MP-74.CN.S2.65.1.2 | Electrical and Mechanical | I.CN.65.15870 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Installation of Axle Counter GAKs and sensors | 2026-03-19 | 2026-03-19
I2S-7688-MP-74.CN.S2.65.1.2 | Electrical and Mechanical | I.CN.65.15880 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Finalise Installation of LX Hut (Axle Counters | 2026-06-27 | 2026-06-27
I2S-7688-MP-74.CN.S2.65.1.2 | Electrical and Mechanical | I.CN.65.15240 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Install Gates | 2026-06-21 | 2026-06-21
I2S-7688-MP-74.CN.S2.65.1.2 | Electrical and Mechanical | I.CN.65.15250 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Installation of local cables | 2026-06-22 | 2026-06-22
I2S-7688-MP-74.CN.S2.65.1.2 | Electrical and Mechanical | I.CN.65.15720 | CON - Sec.2 - Public LX - Ironbong Road (PU8160)- Installation of RX5s | 2026-03-19 | 2026-03-19
I2S-7688-MP-74.CN.S2.65.1.2 | Electrical and Mechanical | I.CN.65.15730 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Installation of LX Hut | 2026-03-19 | 2026-03-19
I2S-7688-MP-74.CN.S2.65.1.2 | Electrical and Mechanical | I.CN.65.15740 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Installation of Antenna/Comms | 2026-03-19 | 2026-03-19
I2S-7688-MP-74.CN.S2.65.1.2 | Electrical and Mechanical | I.CN.65.15750 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Cable Testing | 2026-06-24 | 2026-06-24
I2S-7688-MP-74.CN.S2.65.1.2 | Electrical and Mechanical | I.CN.65.15760 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Termination of Local Cables | 2026-06-23 | 2026-06-23
I2S-7688-MP-74.CN.S2.65.1.2 | Electrical and Mechanical | I.CN.65.15770 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Termination of Main Cables | 2026-03-02 | 2026-03-02
I2S-7688-MP-74.CN.S2.65.1.2 | Electrical and Mechanical | I.CN.65.15780 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Connection of Power | 2026-06-26 | 2026-06-26
I2S-7688-MP-74.CN.S2.65.1.2 | Electrical and Mechanical | I.CN.65.15790 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Finalise Installation of LX Hut (Relay/Eqyuipment/tidy up/AC) | 2026-06-27 | 2026-06-27
STW |  |  |  | 2026-03-20 | 2026-06-28
I2S-7688-MP-74.CN.S2.65.1.3 | STW | I.CN.65.13250 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Set to Work RX5s including SAT | 2026-03-20 | 2026-04-08
I2S-7688-MP-74.CN.S2.65.1.3 | STW | I.CN.65.15290 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Set to Work Interlocking including SAT | 2026-06-19 | 2026-06-19
I2S-7688-MP-74.CN.S2.65.1.3 | STW | I.CN.65.15800 | CON - Sec.2 - Public LX - Ironbong Road (PU8160)- Set to Work Axle Counter System including SAT | 2026-06-28 | 2026-06-28
Commissioning |  |  |  | 2026-06-29 | 2026-07-02
I2S-7688-MP-74.CN.S2.65.1.4 | Commissioning | I.CN.11.13880 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Clear and Grub Reinstatement - Ironbong Road | 2026-06-30 | 2026-07-02
I2S-7688-MP-74.CN.S2.65.1.4 | Commissioning | I.CN.65.15300 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Open /Handover |  | 2026-06-29
I2S-7688-MP-74.CN.S2.65.1.4 | Commissioning | I.CN.65.15840 | CON - Sec.2 - Public LX - Ironbong Road (PU8160) - Final Testing / Commissioning | 2026-06-29 | 2026-06-29
Public LX - Old Sydney Road (PU5600) - Passive / Junee LGA - RX-2 |  |  |  | 2025-11-06 | 2026-01-14
Earthworks/Drainage
Culvert ID : E2-RD-423080-1 / Type : 4*900mm HDPE / Ch5569 (13.56m each)
I2S-7688-MP-74.CN.S2.65.2.5.2 | Culvert ID : E2-RD-423080-1 / Type : 4*900mm HDPE / Ch5569 (13.56m each) | I.CN.65.18800 | CON - Sec.2 - Public LX - Culvert : E2-RD-423080-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S2.65.2.5.2 | Culvert ID : E2-RD-423080-1 / Type : 4*900mm HDPE / Ch5569 (13.56m each) | I.CN.65.18810 | CON - Sec.2 - Public LX - Culvert : E2-RD-423080-1 - Struc fill (150mm) / Bedding (150mm) Placement
I2S-7688-MP-74.CN.S2.65.2.5.2 | Culvert ID : E2-RD-423080-1 / Type : 4*900mm HDPE / Ch5569 (13.56m each) | I.CN.65.18830 | CON - Sec.2 - Public LX - Culvert : E2-RD-423080-1 - Construct Scour Protection
I2S-7688-MP-74.CN.S2.65.2.5.2 | Culvert ID : E2-RD-423080-1 / Type : 4*900mm HDPE / Ch5569 (13.56m each) | I.CN.65.18820 | CON - Sec.2 - Public LX - Culvert : E2-RD-423080-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S2.65.2.5.2 | Culvert ID : E2-RD-423080-1 / Type : 4*900mm HDPE / Ch5569 (13.56m each) | I.CN.65.19151 | CON - Sec.2 - Public LX - Culvert : E2-RD-423080-1 - Headwall installation
I2S-7688-MP-74.CN.S2.65.2.5.2 | Culvert ID : E2-RD-423080-1 / Type : 4*900mm HDPE / Ch5569 (13.56m each) | I.CN.65.19161 | CON - Sec.2 - Public LX - Culvert : E2-RD-423080-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S2.65.2.5.2 | Culvert ID : E2-RD-423080-1 / Type : 4*900mm HDPE / Ch5569 (13.56m each) | I.CN.65.19171 | CON - Sec.2 - Public LX - Culvert : E2-RD-423080-1 - Headwall Stitch Pour
Civils |  |  |  | 2025-11-06 | 2025-11-06
I2S-7688-MP-74.CN.S2.65.2.1 | Civils | I.CN.11.14230 | CON - Sec.2 - Public LX - Culvert: E2-RD-423080-1 - Clear and Grub | 2025-11-06 | 2025-11-06
Roadworks |  |  |  | 2025-11-07 | 2026-01-11
I2S-7688-MP-74.CN.S2.65.2.6 | Roadworks | I.CN.31.6780 | CON - Sec.2 - Public LX - Old Sydney Road (PU5600) - Cut - 25ccm - Soil | 2025-11-07 | 2025-11-07
I2S-7688-MP-74.CN.S2.65.2.6 | Roadworks | I.CN.31.6840 | CON - Sec.2 - Public LX - Old Sydney Road (PU5600) - Fill - PU5600 - 2450ccm | 2025-11-08 | 2025-11-10
I2S-7688-MP-74.CN.S2.65.2.6 | Roadworks | I.CN.65.15350 | CON - Sec.2 - Public LX - Old Sydney Road (PU5600) - Pavement type A Unsealed (1005m2) | 2026-01-07 | 2026-01-08
I2S-7688-MP-74.CN.S2.65.2.6 | Roadworks | I.CN.65.15430 | CON - Sec.2 - Public LX - Old Sydney Road (PU5600) - Batter face area (1480 m3) | 2026-01-09 | 2026-01-10
I2S-7688-MP-74.CN.S2.65.2.6 | Roadworks | I.CN.65.15440 | CON - Sec.2 - Public LX - Old Sydney Road (PU5600) - Prime & Cure - Pavement type B sealed (550 m2) | 2026-01-09 | 2026-01-10
I2S-7688-MP-74.CN.S2.65.2.6 | Roadworks | I.CN.65.15450 | CON - Sec.2 - Public LX - Old Sydney Road (PU5600) - Seal /linemarking | 2026-01-11 | 2026-01-11
Trackworks |  |  |  | 2025-12-02 | 2025-12-04
I2S-7688-MP-74.CN.S2.65.2.7 | Trackworks | I.CN.65.15370 | CON - Sec.2 - Public LX - Old Sydney Road (PU5600) - Place and compact ballast between foundation block (after road | 2025-12-03 | 2025-12-03
I2S-7688-MP-74.CN.S2.65.2.7 | Trackworks | I.CN.65.15380 | CON - Sec.2 - Public LX - Old Sydney Road (PU5600) - Tie-in works to foundation block | 2025-12-04 | 2025-12-04
I2S-7688-MP-74.CN.S2.65.2.7 | Trackworks | I.CN.65.15360 | CON - Sec.2 - Public LX - Old Sydney Road (PU5600) - Place Foundation Block and T-Kerbstone | 2025-12-02 | 2025-12-02
Ancillary |  |  |  | 2026-01-12 | 2026-01-13
I2S-7688-MP-74.CN.S2.65.2.8 | Ancillary | I.CN.65.15390 | CON - Sec.2 - Public LX - Old Sydney Road (PU5600) - Install Fencing | 2026-01-12 | 2026-01-12
I2S-7688-MP-74.CN.S2.65.2.8 | Ancillary | I.CN.65.15400 | CON - Sec.2 - Public LX - Old Sydney Road (PU5600) - Install Signage | 2026-01-13 | 2026-01-13
Electrical and Mechanical |  |  |  | 2026-01-14 | 2026-01-14
I2S-7688-MP-74.CN.S2.65.2.2 | Electrical and Mechanical | I.CN.65.15420 | CON - Sec.2 - Public LX - Old Sydney Road (PU5600) - Install Gates | 2026-01-14 | 2026-01-14
Commissioning |  |  |  | 2026-01-14 | 2026-01-14
I2S-7688-MP-74.CN.S2.65.2.4 | Commissioning | I.CN.65.15480 | CON - Sec.2 - Public LX - Old Sydney Road (PU5600) - Open |  | 2026-01-14
Stock Crossings |  |  |  | 2025-10-27 | 2025-11-10
Green (SU5900) Culvert ID : E7-SU-423469-1 / Type : 1*3000x3000mm RCBC / Ch5989 (9.6m) |  |  |  | 2025-10-27 | 2025-10-30
I2S-7688-MP-74.CN.S2.65.3.2 | Green (SU5900) Culvert ID : E7-SU-423469-1 / Type : 1*3000x3000mm RCBC / Ch5989 (9.6m) | I.CN.65.19581 | CON - Sec.2 - Stock Xing - Culvert : E7-SU-423469-1 - Place Pre-cast Wingwalls and Stich Pour
I2S-7688-MP-74.CN.S2.65.3.2 | Green (SU5900) Culvert ID : E7-SU-423469-1 / Type : 1*3000x3000mm RCBC / Ch5989 (9.6m) | I.CN.65.19591 | CON - Sec.2 - Stock Xing - Culvert : E7-SU-423469-1 - Pre-cast RCBC completion (Seal joints)
I2S-7688-MP-74.CN.S2.65.3.2 | Green (SU5900) Culvert ID : E7-SU-423469-1 / Type : 1*3000x3000mm RCBC / Ch5989 (9.6m) | I.CN.65.16300 | CON - Sec.2 - Stock Xing - Culvert : E7-SU-423469-1 - Site Prep / Detail Excavation | 2025-10-27 | 2025-10-28
I2S-7688-MP-74.CN.S2.65.3.2 | Green (SU5900) Culvert ID : E7-SU-423469-1 / Type : 1*3000x3000mm RCBC / Ch5989 (9.6m) | I.CN.65.17630 | CON - Sec.2 - Stock Xing - Culvert : E7-SU-423469-1 - Place RCBC crown units | 2025-10-29 | 2025-10-29
I2S-7688-MP-74.CN.S2.65.3.2 | Green (SU5900) Culvert ID : E7-SU-423469-1 / Type : 1*3000x3000mm RCBC / Ch5989 (9.6m) | I.CN.65.17660 | CON - Sec.2 - Stock Xing - Culvert : E7-SU-423469-1 - Construct Scour protection | 2025-10-30 | 2025-10-30
I2S-7688-MP-74.CN.S2.65.3.2 | Green (SU5900) Culvert ID : E7-SU-423469-1 / Type : 1*3000x3000mm RCBC / Ch5989 (9.6m) | I.CN.65.18490 | CON - Sec.2 - Stock Xing - Culvert : E7-SU-423469-1 - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.CN.S2.65.3.2 | Green (SU5900) Culvert ID : E7-SU-423469-1 / Type : 1*3000x3000mm RCBC / Ch5989 (9.6m) | I.CN.65.18500 | CON - Sec.2 - Stock Xing - Culvert : E7-SU-423469-1 - 7 day Curing
I2S-7688-MP-74.CN.S2.65.3.2 | Green (SU5900) Culvert ID : E7-SU-423469-1 / Type : 1*3000x3000mm RCBC / Ch5989 (9.6m) | I.CN.65.18510 | CON - Sec.2 - Stock Xing - Culvert : E7-SU-423469-1 - Detail backfill
I2S-7688-MP-74.CN.S2.65.3.2 | Green (SU5900) Culvert ID : E7-SU-423469-1 / Type : 1*3000x3000mm RCBC / Ch5989 (9.6m) | I.CN.65.19561 | CON - Sec.2 - Stock Xing - Culvert : E7-SU-423469-1 - Struc fill Placement (250mm)
I2S-7688-MP-74.CN.S2.65.3.2 | Green (SU5900) Culvert ID : E7-SU-423469-1 / Type : 1*3000x3000mm RCBC / Ch5989 (9.6m) | I.CN.65.19571 | CON - Sec.2 - Stock Xing - Culvert : E7-SU-423469-1 - Blinding placement (50mm)
I2S-7688-MP-74.CN.S2.65.3.2 | Green (SU5900) Culvert ID : E7-SU-423469-1 / Type : 1*3000x3000mm RCBC / Ch5989 (9.6m) | I.CN.65.20021 | CON - Sec.2 - Stock Xing - Culvert : E7-SU-423469-1 - FRP Base Slab / Apron Slab / Cut-off Wall - Milestone
Lloyd-Jones (Malcom) (SU7500) Culvert ID : E7-SU-425154-1 / Type : 1*3000x3000mm RCBC / Ch7667 (7.2m |  |  |  | 2025-11-07 | 2025-11-10
I2S-7688-MP-74.CN.S2.65.3.3 | Lloyd-Jones (Malcom) (SU7500) Culvert ID : E7-SU-425154-1 / Type : 1*3000x3000mm RCBC / Ch7667 (7.2m | I.CN.65.16310 | CON - Sec.2 - Stock Xing - Culvert : E7-SU-425154-1 - Site Prep / Detail Excavation | 2025-11-07 | 2025-11-08
I2S-7688-MP-74.CN.S2.65.3.3 | Lloyd-Jones (Malcom) (SU7500) Culvert ID : E7-SU-425154-1 / Type : 1*3000x3000mm RCBC / Ch7667 (7.2m | I.CN.65.17640 | CON - Sec.2 - Stock Xing - Culvert : E7-SU-425154-1 - Place RCBC crown units | 2025-11-09 | 2025-11-09
I2S-7688-MP-74.CN.S2.65.3.3 | Lloyd-Jones (Malcom) (SU7500) Culvert ID : E7-SU-425154-1 / Type : 1*3000x3000mm RCBC / Ch7667 (7.2m | I.CN.65.17670 | CON - Sec.2 - Stock Xing - Culvert : E7-SU-425154-1 - Construct Scour protection | 2025-11-10 | 2025-11-10
I2S-7688-MP-74.CN.S2.65.3.3 | Lloyd-Jones (Malcom) (SU7500) Culvert ID : E7-SU-425154-1 / Type : 1*3000x3000mm RCBC / Ch7667 (7.2m | I.CN.65.18520 | CON - Sec.2 - Stock Xing - Culvert : E7-SU-425154-1 - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.CN.S2.65.3.3 | Lloyd-Jones (Malcom) (SU7500) Culvert ID : E7-SU-425154-1 / Type : 1*3000x3000mm RCBC / Ch7667 (7.2m | I.CN.65.18530 | CON - Sec.2 - Stock Xing - Culvert : E7-SU-425154-1 - 7 day Curing
I2S-7688-MP-74.CN.S2.65.3.3 | Lloyd-Jones (Malcom) (SU7500) Culvert ID : E7-SU-425154-1 / Type : 1*3000x3000mm RCBC / Ch7667 (7.2m | I.CN.65.18540 | CON - Sec.2 - Stock Xing - Culvert : E7-SU-425154-1 - Detail backfill
I2S-7688-MP-74.CN.S2.65.3.3 | Lloyd-Jones (Malcom) (SU7500) Culvert ID : E7-SU-425154-1 / Type : 1*3000x3000mm RCBC / Ch7667 (7.2m | I.CN.65.19601 | CON - Sec.2 - Stock Xing - Culvert : E7-SU-425154-1 - Struc fill Placement (250mm)
I2S-7688-MP-74.CN.S2.65.3.3 | Lloyd-Jones (Malcom) (SU7500) Culvert ID : E7-SU-425154-1 / Type : 1*3000x3000mm RCBC / Ch7667 (7.2m | I.CN.65.19611 | CON - Sec.2 - Stock Xing - Culvert : E7-SU-425154-1 - Blinding placement (50mm)
I2S-7688-MP-74.CN.S2.65.3.3 | Lloyd-Jones (Malcom) (SU7500) Culvert ID : E7-SU-425154-1 / Type : 1*3000x3000mm RCBC / Ch7667 (7.2m | I.CN.65.19621 | CON - Sec.2 - Stock Xing - Culvert : E7-SU-425154-1 - Place Pre-cast Wingwalls and Stich Pour
I2S-7688-MP-74.CN.S2.65.3.3 | Lloyd-Jones (Malcom) (SU7500) Culvert ID : E7-SU-425154-1 / Type : 1*3000x3000mm RCBC / Ch7667 (7.2m | I.CN.65.19631 | CON - Sec.2 - Stock Xing - Culvert : E7-SU-425154-1 - Pre-cast RCBC completion (Seal joints)
072 - Signalling |  |  |  | 2026-01-17 | 2026-03-19
Signals |  |  |  | 2026-03-16 | 2026-03-19
I2S-7688-MP-74.CN.S2.72.11 | Signals | I.CN.72.15160 | CON - Sec.2 - Sig - Install New Main Signals (1 off) 423075 | 2026-03-16 | 2026-03-17
I2S-7688-MP-74.CN.S2.72.11 | Signals | I.CN.72.15260 | CON - Sec.2 - Sig - Prepare & Submit of IWP (Sections 2-5) | 2026-03-18 | 2026-03-19
I2S-7688-MP-74.CN.S2.72.11 | Signals | I.CN.72.16830 | CON - Sec.2 - Sig - IRPL Approval of IWP (Sections 2-5)
I2S-7688-MP-74.CN.S2.72.11 | Signals | I.CN.72.16260 | CON - Sec.2 - Sig - Install New Main Signals (1 off) 423960
Cabling |  |  |  | 2026-01-17 | 2026-01-29
I2S-7688-MP-74.CN.S2.72.8 | Cabling | I.CN.74.14410 | CON - Sec.2 - CSR - Main Cable Route - MCR - Pull Cable - 3000 to 8600 | 2026-01-17 | 2026-01-29
Misc Equipment |  |  |  | 2026-02-17 | 2026-03-01
I2S-7688-MP-74.CN.S2.72.9 | Misc Equipment | I.CN.74.14820 | CON - Sec.2 - Sig - Install Track Side Equipment (speed signs/motor generators/notice boards) | 2026-02-17 | 2026-03-01
Axle
I2S-7688-MP-74.CN.S2.72.2 | Axle | I.CN.72.16680 | CON - Sec.2 - Sig - Install New Axles Counter (1 off) 420850
I2S-7688-MP-74.CN.S2.72.2 | Axle | I.CN.72.16690 | CON - Sec.2 - Sig - Install New Axles Counter (1 off) 423075
I2S-7688-MP-74.CN.S2.72.2 | Axle | I.CN.72.16270 | CON - Sec.2 - Sig - Install New Axles Counter (1 off) 420550
Building
I2S-7688-MP-74.CN.S2.72.3 | Building | I.CN.72.16280 | CON - Sec.2 - Sig - Install New SER/Building (1 off) 425580
Location Case
I2S-7688-MP-74.CN.S2.72.4 | Location Case | I.CN.72.16770 | CON - Sec.2 - Sig - Install New Location Case (1 off) 423960
I2S-7688-MP-74.CN.S2.72.4 | Location Case | I.CN.72.16290 | CON - Sec.2 - Sig - Install New Location Case (1 off) 420850
I2S-7688-MP-74.CN.S2.72.4 | Location Case | I.CN.72.16710 | CON - Sec.2 - Sig - Install New Location Case (1 off) 422970
074 - Power Supply and Distributions |  |  |  | 2025-12-12 | 2026-01-30
CSR |  |  |  | 2025-12-12 | 2026-01-30
MCR |  |  |  | 2025-12-12 | 2026-01-30
I2S-7688-MP-74.CN.S2.74.2.1 | MCR | I.CN.74.14020 | CON - Sec.2 - CSR - Install Main CSR - Dn Main 418300 to 423050 (LX) (4750m) | 2025-12-12 | 2026-01-06
I2S-7688-MP-74.CN.S2.74.2.1 | MCR | I.CN.74.14200 | CON - Sec.2 - CSR - Install Main CSR - Dn Main 423050 (LX) to 425400 (Ulandra) (2350m) | 2026-01-07 | 2026-01-16
I2S-7688-MP-74.CN.S2.74.2.1 | MCR | I.CN.74.14810 | CON - Sec.2 - CSR - Install Main CSR - Dn Main 425400 to 425450 Over Ulandra Creek Bridge | 2026-01-30 | 2026-01-30
I2S-7688-MP-74.CN.S2.74.2.1 | MCR | I.CN.74.15330 | CON - Sec.2 - CSR - Install Main CSR - Up Main 425450 (Ulandra) to 425650 (200m)
I2S-7688-MP-74.CN.S2.74.2.1 | MCR | I.CN.74.15340 | CON - Sec.2 - CSR - Install Main CSR - Up Main 425700 to 428025 (2375m)
LCR
I2S-7688-MP-74.CN.S2.74.2.2 | LCR | I.CN.74.15390 | CON - Sec.2 - CSR - Construct Local Cable Route - LCR Up 425650
I2S-7688-MP-74.CN.S2.74.2.2 | LCR | I.CN.74.15400 | CON - Sec.2 - CSR - Construct Local Cable Route - LCR Up 425660
I2S-7688-MP-74.CN.S2.74.2.2 | LCR | I.CN.74.15410 | CON - Sec.2 - CSR - Construct Local Cable Route - LCR Dn 425670
I2S-7688-MP-74.CN.S2.74.2.2 | LCR | I.CN.74.15420 | CON - Sec.2 - CSR - Construct Local Cable Route - LCR Dn 425680
I2S-7688-MP-74.CN.S2.74.2.2 | LCR | I.CN.74.15320 | CON - Sec.2 - CSR - Construct Local Cable Route - LCR Dn 420550
I2S-7688-MP-74.CN.S2.74.2.2 | LCR | I.CN.74.15350 | CON - Sec.2 - CSR - Construct Local Cable Route - LCR Dn 420850
I2S-7688-MP-74.CN.S2.74.2.2 | LCR | I.CN.74.15360 | CON - Sec.2 - CSR - Construct Local Cable Route - LCR Up 423080
I2S-7688-MP-74.CN.S2.74.2.2 | LCR | I.CN.74.15370 | CON - Sec.2 - CSR - Construct Local Cable Route - LCR Dn 423960
I2S-7688-MP-74.CN.S2.74.2.2 | LCR | I.CN.74.15380 | CON - Sec.2 - CSR - Construct Local Cable Route - LCR Dn 424700
ULX
I2S-7688-MP-74.CN.S2.74.2.3 | ULX | I.CN.74.15280 | CON - Sec.2 - CSR - Local ULX - Across Track - 423075
I2S-7688-MP-74.CN.S2.74.2.3 | ULX | I.CN.74.15290 | CON - Sec.2 - CSR - Local ULX - Across Track - 423075 - 423125
I2S-7688-MP-74.CN.S2.74.2.3 | ULX | I.CN.74.15300 | CON - Sec.2 - CSR - Local ULX - Across Track - 425600
I2S-7688-MP-74.CN.S2.74.2.3 | ULX | I.CN.74.15310 | CON - Sec.2 - CSR - Local ULX - Across Track - 425600 - 425700
085 - Landscaping
I2S-7688-MP-74.CN.S2.85 | 085 - Landscaping | I.CN.85.14050 | CON - Sec.2 - Landscaping - Re-spread Topsoil - Ch2901-8400
I2S-7688-MP-74.CN.S2.85 | 085 - Landscaping | I.CN.85.14060 | CON - Sec.2 - Landscaping - Hydroseed Application - Ch2901-8400
Section 1 - Illabo Junction - (00000 - 02900) |  |  |  | 2025-07-11 | 2027-04-03
Section 1 Key Milestones
I2S-7688-MP-74.CN.S1.2 | Section 1 Key Milestones | I.CN.22.14190 | CON - Sec.1 - Construction Completion Milestone (Bridges)
I2S-7688-MP-74.CN.S1.2 | Section 1 Key Milestones | I.CN.22.14200 | CON - Sec.1 - Construction Completion Milestone (Crossings)
I2S-7688-MP-74.CN.S1.2 | Section 1 Key Milestones | I.CN.22.14210 | CON - Sec.1 - Construction Completion Milestone (Signalling)
I2S-7688-MP-74.CN.S1.2 | Section 1 Key Milestones | I.CN.22.14220 | CON - Sec.1 - Construction Completion Milestone (Power Supply and Distributions)
I2S-7688-MP-74.CN.S1.2 | Section 1 Key Milestones | I.CN.22.14230 | CON - Sec.1 - Construction Completion Milestone (Landscaping)
I2S-7688-MP-74.CN.S1.2 | Section 1 Key Milestones | I.CN.22.14240 | CON - Sec.1 - Construction Completion Milestone (Roads)
I2S-7688-MP-74.CN.S1.2 | Section 1 Key Milestones | I.CN.22.14120 | CON - Sec.1 - Construction Completion Milestone (Public Utilities)
I2S-7688-MP-74.CN.S1.2 | Section 1 Key Milestones | I.CN.22.14130 | CON - Sec.1 - Construction Completion Milestone (Earthworks)
I2S-7688-MP-74.CN.S1.2 | Section 1 Key Milestones | I.CN.22.14140 | CON - Sec.1 - Construction Completion Milestone (Rail Capping)
I2S-7688-MP-74.CN.S1.2 | Section 1 Key Milestones | I.CN.22.14150 | CON - Sec.1 - Construction Completion Milestone (Drainage)
I2S-7688-MP-74.CN.S1.2 | Section 1 Key Milestones | I.CN.22.14160 | CON - Sec.1 - Construction Completion Milestone (Fencing)
I2S-7688-MP-74.CN.S1.2 | Section 1 Key Milestones | I.CN.22.14170 | CON - Sec.1 - Construction Completion Milestone (Access Roads)
I2S-7688-MP-74.CN.S1.2 | Section 1 Key Milestones | I.CN.22.14180 | CON - Sec.1 - Construction Completion Milestone (Trackwork)
I2S-7688-MP-74.CN.S1.2 | Section 1 Key Milestones | I.CN.22.14410 | CON - Sec.1 - Construction Completion Milestone (Culverts)
I2S-7688-MP-74.CN.S1.2 | Section 1 Key Milestones | I.CN.22.14840 | CON - Sec.1 - Commence Construction Milestone - FDVR & CEMP approved - 1st A9 submission - approval
I2S-7688-MP-74.CN.S1.2 | Section 1 Key Milestones | I.CN.22.14830 | CON - Sec.1 - Commence Construction Milestone - CEMP approved
Site Access |  |  |  | 2025-07-11 | 2025-07-11
I2S-7688-MP-74.CN.S1.00 | Site Access | I.CN.11.14080 | CON - Sec.1 - Site Gate Access Required by/ Granted - Gate 0 (00000) | 2025-07-11
I2S-7688-MP-74.CN.S1.00 | Site Access | I.CN.11.14090 | CON - Sec.1 - Site Gate Access Required by/ Granted - Gate 1 (00500) | 2025-07-11
I2S-7688-MP-74.CN.S1.00 | Site Access | I.CN.11.14100 | CON - Sec.1 - Site Gate Access Required by/ Granted - Gate 2 (02800) | 2025-07-11
022 - Public Utilities |  |  |  | 2025-07-21 | 2025-10-28
ARTC |  |  |  | 2025-07-22 | 2025-08-11
I2S-7688-MP-74.CN.S1.22.1 | ARTC | I.CN.22.5650 | CON - Util - Sec.1 - PUPIRPL - Rail Power -25, 25-225, 1925-2000, 3000 (5 off) - all New | 2025-07-22 | 2025-08-01
I2S-7688-MP-74.CN.S1.22.1 | ARTC | I.CN.11.13310 | CON - Util - Sec.1 - Electrical underground for signalling power at Olympic Highway, 200m (CH20 - CH220) | 2025-08-04 | 2025-08-07
I2S-7688-MP-74.CN.S1.22.1 | ARTC | I.CN.11.13320 | CON - Util - Sec.1 - Electrical underground for rail power at Olympic Highway, CH1925 | 2025-08-08 | 2025-08-11
Telstra |  |  |  | 2025-07-21 | 2025-08-04
I2S-7688-MP-74.CN.S1.22.2 | Telstra | I.CN.22.5640 | CON - Util - Sec.1 - TE02-01 Telstra - Relocate Comms Cable - Install Trench - Ch1400 to 1450 | 2025-07-21 | 2025-07-22
I2S-7688-MP-74.CN.S1.22.2 | Telstra | I.CN.22.13240 | CON - Util - Sec.1 - TE02-01 Telstra - Relocate Comms Cable - Ch1400-1468 (by Telstra) | 2025-08-01 | 2025-08-04
I2S-7688-MP-74.CN.S1.22.2 | Telstra | I.CN.22.13250 | CON - Util - Sec.1 - TE02-01 Telstra - Relocate Comms Cable - Track Underbore - Ch1450 | 2025-07-23 | 2025-07-24
I2S-7688-MP-74.CN.S1.22.2 | Telstra | I.CN.22.13270 | CON - Util - Sec.1 - TE02-01 Telstra - Relocate Comms Cable - Install Ducts - Ch1450 - 1460 | 2025-07-30 | 2025-07-31
I2S-7688-MP-74.CN.S1.22.2 | Telstra | I.CN.11.13140 | CON - Util - Sec.1 - TE02-01 Telstra - Relocate Comms Cable - Road underbore across Olympic Highway - Ch1400 | 2025-07-21 | 2025-07-22
Optus |  |  |  | 2025-09-13 | 2025-10-28
Stage 1 - East & West ULX / Fibre Install / Decommission |  |  |  | 2025-09-13 | 2025-10-28
I2S-7688-MP-74.CN.S1.22.3.1 | Stage 1 - East & West ULX / Fibre Install / Decommission | I.CN.22.5630 | CON - Util - Sec.1 - OF01-01 Optus - Western End Bore + Pit Works - Ch155 to 180 | 2025-09-13 | 2025-09-14
I2S-7688-MP-74.CN.S1.22.3.1 | Stage 1 - East & West ULX / Fibre Install / Decommission | I.CN.22.13170 | CON - Util - Sec.1 - OF01-01 Optus - Eastern End Bore + Pit Works - Ch2950 | 2025-09-13 | 2025-09-14
I2S-7688-MP-74.CN.S1.22.3.1 | Stage 1 - East & West ULX / Fibre Install / Decommission | I.CN.22.13200 | CON - Util - Sec.1 - OF01-01 Optus - Fibre Installation into Splice Joints Ch0 to 2950 | 2025-10-07 | 2025-10-28
I2S-7688-MP-74.CN.S1.22.3.1 | Stage 1 - East & West ULX / Fibre Install / Decommission | I.CN.22.14510 | CON - Util - Sec.1 - OF01-01 Optus - Completion Audit Walk
I2S-7688-MP-74.CN.S1.22.3.1 | Stage 1 - East & West ULX / Fibre Install / Decommission | I.CN.22.14470 | CON - Util - Sec.1 - OF01-01 Optus - Fibre Hauled End to End - Ch0 to 2950 (4150m)
I2S-7688-MP-74.CN.S1.22.3.1 | Stage 1 - East & West ULX / Fibre Install / Decommission | I.CN.22.14490 | CON - Util - Sec.1 - OF01-01 Optus - Decommissioning Works
I2S-7688-MP-74.CN.S1.22.3.1 | Stage 1 - East & West ULX / Fibre Install / Decommission | I.CN.22.15020 | CON - Util - Sec.1 - OF01-01 Optus - Fibre Installation into Splice Joints Test - Ch0 to 2950
I2S-7688-MP-74.CN.S1.22.3.1 | Stage 1 - East & West ULX / Fibre Install / Decommission | I.CN.22.15010 | CON - Util - Sec.1 - OF01-01 Optus - Commence work onsite
Stage 2 - Bore & Trench Works (Ch0-1900) |  |  |  | 2025-09-14 | 2025-09-20
I2S-7688-MP-74.CN.S1.22.3.2 | Stage 2 - Bore & Trench Works (Ch0-1900) | I.CN.22.11990 | CON - Util - Sec.1 - OF01-01 Optus - Bore Works / Trench Works / Pit Installation - CH 0 to CH 1900 | 2025-09-14 | 2025-09-20
Stage 3 - Bore & Trench Works (Ch1900-2950) |  |  |  | 2025-09-20 | 2025-10-01
I2S-7688-MP-74.CN.S1.22.3.3 | Stage 3 - Bore & Trench Works (Ch1900-2950) | I.CN.22.13210 | CON - Util - Sec.1 - OF01-01 Optus - Bore Works / Trench Works / Pit Installation - CH 1900 to CH 2950 | 2025-09-20 | 2025-10-01
I2S-7688-MP-74.CN.S1.22.3.3 | Stage 3 - Bore & Trench Works (Ch1900-2950) | I.CN.22.14500 | CON - Util - Sec.1 - OF01-01 Optus - Civil Works Completion Audit Walk
Stage 4 - Splice Audit & Cut-Over |  |  |  | 2025-09-13 | 2025-10-06
I2S-7688-MP-74.CN.S1.22.3.4 | Stage 4 - Splice Audit & Cut-Over | I.CN.22.13220 | CON - Util - Sec.1 - OF01-01 Optus - Fibre Splice cable testing | 2025-09-26 | 2025-10-06
I2S-7688-MP-74.CN.S1.22.3.4 | Stage 4 - Splice Audit & Cut-Over | I.CN.22.13190 | CON - Util - Sec.1 - OF01-01 Optus - Cable Cut & Haul Cutover | 2025-09-13 | 2025-09-15
Essential Energy (EE) |  |  |  | 2025-07-31 | 2025-08-06
ECN-111187 ELO-13 & PS-01
I2S-7688-MP-74.CN.S1.22.4.1 | ECN-111187 ELO-13 & PS-01 | I.CN.22.14250 | CON - Util - Sec.1 - ELO-13 - Essential Energy Relocate 11kV North Side Olympic H/Way - Ch642 (326m)
I2S-7688-MP-74.CN.S1.22.4.1 | ECN-111187 ELO-13 & PS-01 | I.CN.22.14260 | CON - Util - Sec.1 - PS-01 - Essential Energy - New Signal Equipment Room Power Supply - Ch642
I2S-7688-MP-74.CN.S1.22.4.1 | ECN-111187 ELO-13 & PS-01 | I.CN.22.14252 | CON - Util - Sec.1 - ELO-13 & PS-01 - Outage & Cutover (ECN-111187)
I2S-7688-MP-74.CN.S1.22.4.1 | ECN-111187 ELO-13 & PS-01 | I.CN.22.14253 | CON - Util - Sec.1 - ECN-111187 Works Complete
I2S-7688-MP-74.CN.S1.22.4.1 | ECN-111187 ELO-13 & PS-01 | I.CN.22.14251 | CON - Util - Sec.1 - ELO-13 & PS-01 - Commence Work on site
ECN-098333 ELO-08 & ELO-01 |  |  |  | 2025-07-31 | 2025-08-06
I2S-7688-MP-74.CN.S1.22.4.2 | ECN-098333 ELO-08 & ELO-01 | I.CN.22.5390 | CON - Util - Sec.1 - ELO-08 - Essential Energy Relocate 11kV Across Olympic H/Way - Ch1702 (89m) | 2025-07-31 | 2025-08-06
I2S-7688-MP-74.CN.S1.22.4.2 | ECN-098333 ELO-08 & ELO-01 | I.CN.22.13280 | CON - Util - Sec.1 - ELO-01 - Essential Energy Relocate 11kV Across Olympic H/Way - Ch1922 (92m) | 2025-07-31 | 2025-08-06
I2S-7688-MP-74.CN.S1.22.4.2 | ECN-098333 ELO-08 & ELO-01 | I.CN.22.14520 | CON - Util - Sec.1 - ELO-08 & ELO-01 - Commence Work on site
I2S-7688-MP-74.CN.S1.22.4.2 | ECN-098333 ELO-08 & ELO-01 | I.CN.22.14530 | CON - Util - Sec.1 - ELO-08 & ELO-01 - Outage & Cutover (ECN-098333)
I2S-7688-MP-74.CN.S1.22.4.2 | ECN-098333 ELO-08 & ELO-01 | I.CN.22.14540 | CON - Util - Sec.1 - ECN-098333 Works Complete
031 - Earthworks |  |  |  | 2025-07-11 | 2025-09-06
I2S-7688-MP-74.CN.S1.31 | 031 - Earthworks | I.CN.31.14150 | CON - Sec.1 - Construct Temp Creek Crossing - Billabong Creek for traffic | 2025-07-11 | 2025-07-11
Clearing & Grubbing - Stage 2
Tree Felling and Lopping
I2S-7688-MP-74.CN.S1.31.2.1 | Tree Felling and Lopping | I.CN.11.15460 | CON - Sec.1 - Tree Felling & Lopping
Broad Acre Clearing and Mulching
I2S-7688-MP-74.CN.S1.31.2.2 | Broad Acre Clearing and Mulching | I.CN.11.15470 | CON - Sec.1 - Broad Acre Clearing & Mulching
Grubbing of Stumps
I2S-7688-MP-74.CN.S1.31.2.3 | Grubbing of Stumps | I.CN.11.15480 | CON - Sec.1 - Grubbing of Stumps
Miscellaneous Works
I2S-7688-MP-74.CN.S1.31.2.4 | Miscellaneous Works | I.CN.11.15490 | CON - Sec.1 - Hollow/Habitat Tree Mgmt
I2S-7688-MP-74.CN.S1.31.2.4 | Miscellaneous Works | I.CN.11.15500 | CON - Sec.1 - Relocations
Cut |  |  |  | 2025-07-22 | 2025-09-06
Cut Open Drains |  |  |  | 2025-07-23 | 2025-07-28
I2S-7688-MP-74.CN.S1.31.1.3 | Cut Open Drains | I.CN.31.86140 | CON - Sec.1 - FILL 02 - Cut.OD Soil : Ch737 to 1342 (403 bcm - 175 per/d)
I2S-7688-MP-74.CN.S1.31.1.3 | Cut Open Drains | I.CN.31.86110 | CON - Sec.1 - FILL 01 - Cut.OD Soil : Ch82 to 737 (860 bcm - 175 per/d)
I2S-7688-MP-74.CN.S1.31.1.3 | Cut Open Drains | I.CN.31.6490 | CON - Sec.1 - CUT 03 - Cut.OD Soil : Ch1642 to 2802 (1021 bcm - 175 per/d) | 2025-07-23 | 2025-07-28
Cut Soil to EW |  |  |  | 2025-07-29 | 2025-09-06
I2S-7688-MP-74.CN.S1.31.1.6 | Cut Soil to EW | I.CN.31.86150 | CON - Sec.1 - FILL 02 - Cut.Soil to EW : Ch737 to 1342 (435 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S1.31.1.6 | Cut Soil to EW | I.CN.31.86120 | CON - Sec.1 - FILL 01 - Cut.Soil to EW : Ch82 to 737 (2236 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S1.31.1.6 | Cut Soil to EW | I.CN.31.86180 | CON - Sec.1 - FILL 03 - Cut.Soil to EW : Ch1342 to 1642 (195 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S1.31.1.6 | Cut Soil to EW | I.CN.31.6500 | CON - Sec.1 - CUT 03 - Cut.Soil to EW : Ch1642 to 2802 (74483 bcm - 2500 per/d) | 2025-07-29 | 2025-09-06
I2S-7688-MP-74.CN.S1.31.1.6 | Cut Soil to EW | I.CN.31.88350 | CON - Sec.1 - FILL 01 - Cut.Soil to EW : Ch82 to 737 (2236 bcm - 2500 per/d) - Milestone
Cut Rock |  |  |  | 2025-07-22 | 2025-07-22
I2S-7688-MP-74.CN.S1.31.1.1 | Cut Rock | I.CN.31.6480 | CON - Sec.1 - CUT 03 - Cut.HW to MW SS : Ch1642 to 2802 (14298 bcm - 2500 per/d) | 2025-07-22 | 2025-07-22
Fill
Fill Open Drains
I2S-7688-MP-74.CN.S1.31.4.6 | Fill Open Drains | I.CN.31.84100 | CON - Sec.1 - FILL 01 - Fill.OD Fill : Ch82 to 737 (36 bcm - 175 per/d)
I2S-7688-MP-74.CN.S1.31.4.6 | Fill Open Drains | I.CN.31.84120 | CON - Sec.1 - FILL 02 - Fill.OD Fill : Ch737 to 1342 (10 bcm - 175 per/d)
I2S-7688-MP-74.CN.S1.31.4.6 | Fill Open Drains | I.CN.31.86900 | CON - Sec.1 - CUT 03 - Fill.OD Fill : Ch1642 to 2802 (898 bcm - 500 per/d)
Fill Lower
I2S-7688-MP-74.CN.S1.31.4.1 | Fill Lower | I.CN.31.84250 | CON - Sec.1 - FILL 02 - Fill.H3 - Lower : Ch737 to 1342 (16513 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S1.31.4.1 | Fill Lower | I.CN.31.84270 | CON - Sec.1 - FILL 03 - Fill.H3 - Lower : Ch1342 to 1642 (983 bcm - 2500 per/d)
Fill Mid
I2S-7688-MP-74.CN.S1.31.4.3 | Fill Mid | I.CN.31.84240 | CON - Sec.1 - FILL 02 - Fill.H2 - Mid : Ch737 to 1342 (3088 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S1.31.4.3 | Fill Mid | I.CN.31.84260 | CON - Sec.1 - FILL 03 - Fill.H2 - Mid : Ch1342 to 1642 (1240 bcm - 2500 per/d)
Fill Upper
I2S-7688-MP-74.CN.S1.31.4.4 | Fill Upper | I.CN.31.84090 | CON - Sec.1 - FILL 01 - Fill.H1 - Upper I/B : Ch82 to 737 (3343 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S1.31.4.4 | Fill Upper | I.CN.31.84110 | CON - Sec.1 - FILL 02 - Fill.H1 - Upper I/B : Ch737 to 1342 (7257 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S1.31.4.4 | Fill Upper | I.CN.31.84130 | CON - Sec.1 - FILL 03 - Fill.H1 - Upper I/B : Ch1342 to 1642 (4151 bcm - 2500 per/d)
I2S-7688-MP-74.CN.S1.31.4.4 | Fill Upper | I.CN.31.86890 | CON - Sec.1 - CUT 03 - Fill.H1 - Upper I/B : Ch1642 to 2802 (1564 bcm - 2500 per/d)
033 - Capping |  |  |  | 2025-10-16 | 2025-11-09
Support to u/s Ballast |  |  |  | 2025-10-16 | 2025-11-09
Structural Fill |  |  |  | 2025-10-16 | 2025-10-19
I2S-7688-MP-74.CN.S1.33.3.1 | Structural Fill | I.CN.33.6660 | CON - Sec.1 - Struc fill (13,086 TONS) 2200 TON /d | 2025-10-16 | 2025-10-19
Capping (Rail) |  |  |  | 2025-10-20 | 2025-10-22
I2S-7688-MP-74.CN.S1.33.3.2 | Capping (Rail) | I.CN.33.6700 | CON - Sec.1 - Capping (9,639TON) 1014 TON/d | 2025-10-20 | 2025-10-22
Capping (RMAR) |  |  |  | 2025-11-08 | 2025-11-09
I2S-7688-MP-74.CN.S1.33.3.23 | Capping (RMAR) | I.CN.45.6710 | CON - Sec.1 - (4,116 TON) - Strip/Grade RMAR with type D Material (U5 Class) | 2025-11-08 | 2025-11-09
034 - Drainage |  |  |  | 2025-09-07 | 2026-04-07
Mainline Cess Drain |  |  |  | 2026-03-14 | 2026-04-07
I2S-7688-MP-74.CN.S1.34.4 | Mainline Cess Drain | I.CN.34.25380 | CON - Sec.1 - Cess Drainage - 02789 to 03147 - Grass lined | 2026-04-03 | 2026-04-07
I2S-7688-MP-74.CN.S1.34.4 | Mainline Cess Drain | I.CN.34.25580 | CON - Sec.1 - Cess Drainage - 00609 to 02709 - Grass lined | 2026-03-18 | 2026-04-02
I2S-7688-MP-74.CN.S1.34.4 | Mainline Cess Drain | I.CN.34.14000 | CON - Sec.1 - Cess Drainage - 00220 to 00549 - concrete lining | 2026-03-14 | 2026-03-15
Culverts |  |  |  | 2025-09-07 | 2025-09-30
Culvert ID : E7-RA-419470-1 / Type : 3*1200x900mm RCBC / Ch1965 (12m each) |  |  |  | 2025-09-07 | 2025-09-20
I2S-7688-MP-74.CN.S1.34.3.2 | Culvert ID : E7-RA-419470-1 / Type : 3*1200x900mm RCBC / Ch1965 (12m each) | I.CN.34.22760 | CON - Sec.1 - Culvert : E7-RA-419470-1 - FRP Base Slab / Apron Slab / Cut-off Wall | 2025-09-11 | 2025-09-11
I2S-7688-MP-74.CN.S1.34.3.2 | Culvert ID : E7-RA-419470-1 / Type : 3*1200x900mm RCBC / Ch1965 (12m each) | I.CN.34.22770 | CON - Sec.1 - Culvert : E7-RA-419470-1 - 7 day Curing | 2025-09-12 | 2025-09-12
I2S-7688-MP-74.CN.S1.34.3.2 | Culvert ID : E7-RA-419470-1 / Type : 3*1200x900mm RCBC / Ch1965 (12m each) | I.CN.34.22790 | CON - Sec.1 - Culvert : E7-RA-419470-1 - Place RCBC crown units - start | 2025-09-13 | 2025-09-14
I2S-7688-MP-74.CN.S1.34.3.2 | Culvert ID : E7-RA-419470-1 / Type : 3*1200x900mm RCBC / Ch1965 (12m each) | I.CN.34.22800 | CON - Sec.1 - Culvert : E7-RA-419470-1 - Place Pre-cast Wingwalls and Stitch Pour | 2025-09-16 | 2025-09-17
I2S-7688-MP-74.CN.S1.34.3.2 | Culvert ID : E7-RA-419470-1 / Type : 3*1200x900mm RCBC / Ch1965 (12m each) | I.CN.34.22810 | CON - Sec.1 - Culvert : E7-RA-419470-1 - Detail backfill | 2025-09-18 | 2025-09-18
I2S-7688-MP-74.CN.S1.34.3.2 | Culvert ID : E7-RA-419470-1 / Type : 3*1200x900mm RCBC / Ch1965 (12m each) | I.CN.34.22820 | CON - Sec.1 - Culvert : E7-RA-419470-1 - Construct Scour protection | 2025-09-19 | 2025-09-20
I2S-7688-MP-74.CN.S1.34.3.2 | Culvert ID : E7-RA-419470-1 / Type : 3*1200x900mm RCBC / Ch1965 (12m each) | I.CN.34.22710 | CON - Sec.1 - Culvert : E7-RA-419470-1 - Site Prep / Detail Excavation | 2025-09-07 | 2025-09-08
I2S-7688-MP-74.CN.S1.34.3.2 | Culvert ID : E7-RA-419470-1 / Type : 3*1200x900mm RCBC / Ch1965 (12m each) | I.CN.34.22720 | CON - Sec.1 - Culvert : E7-RA-419470-1 - Foundation Treatment - finish | 2025-09-09 | 2025-09-10
I2S-7688-MP-74.CN.S1.34.3.2 | Culvert ID : E7-RA-419470-1 / Type : 3*1200x900mm RCBC / Ch1965 (12m each) | I.CN.34.32190 | CON - Sec.1 - Culvert : E7-RA-419470-1 - Place RCBC crown units - finish
I2S-7688-MP-74.CN.S1.34.3.2 | Culvert ID : E7-RA-419470-1 / Type : 3*1200x900mm RCBC / Ch1965 (12m each) | I.CN.34.32140 | CON - Sec.1 - Culvert : E7-RA-419470-1 - Foundation Treatment - start
I2S-7688-MP-74.CN.S1.34.3.2 | Culvert ID : E7-RA-419470-1 / Type : 3*1200x900mm RCBC / Ch1965 (12m each) | I.CN.34.32900 | CON - Sec.1 - Culvert : E7-RA-419470-1 - FRP Base Slab / Apron Slab / Cut-off Wall - Milestone
Culvert ID : E7-RA-419050-1 / Type : 2*600mm HDPE / Ch1542 (12m each) |  |  |  | 2025-09-21 | 2025-09-30
I2S-7688-MP-74.CN.S1.34.3.1 | Culvert ID : E7-RA-419050-1 / Type : 2*600mm HDPE / Ch1542 (12m each) | I.CN.34.22920 | CON - Sec.1 - Culvert : E7-RA-419050-1 - Headwall Cut-off Wall Installation (FRP) | 2025-09-29 | 2025-09-29
I2S-7688-MP-74.CN.S1.34.3.1 | Culvert ID : E7-RA-419050-1 / Type : 2*600mm HDPE / Ch1542 (12m each) | I.CN.34.22940 | CON - Sec.1 - Culvert : E7-RA-419050-1 - Construct Scour Protection | 2025-09-30 | 2025-09-30
I2S-7688-MP-74.CN.S1.34.3.1 | Culvert ID : E7-RA-419050-1 / Type : 2*600mm HDPE / Ch1542 (12m each) | I.CN.34.22830 | CON - Sec.1 - Culvert : E7-RA-419050-1 - Site Prep / Detail Excavation | 2025-09-21 | 2025-09-22
I2S-7688-MP-74.CN.S1.34.3.1 | Culvert ID : E7-RA-419050-1 / Type : 2*600mm HDPE / Ch1542 (12m each) | I.CN.34.22840 | CON - Sec.1 - Culvert : E7-RA-419050-1 - Struc fill (150mm) / Bedding (150mm) Placement | 2025-09-23 | 2025-09-23
I2S-7688-MP-74.CN.S1.34.3.1 | Culvert ID : E7-RA-419050-1 / Type : 2*600mm HDPE / Ch1542 (12m each) | I.CN.34.22880 | CON - Sec.1 - Culvert : E7-RA-419050-1 - Headwall installation | 2025-09-24 | 2025-09-24
I2S-7688-MP-74.CN.S1.34.3.1 | Culvert ID : E7-RA-419050-1 / Type : 2*600mm HDPE / Ch1542 (12m each) | I.CN.34.22890 | CON - Sec.1 - Culvert : E7-RA-419050-1 - HDPE / RCP Pipe Lay & Backfill | 2025-09-26 | 2025-09-26
I2S-7688-MP-74.CN.S1.34.3.1 | Culvert ID : E7-RA-419050-1 / Type : 2*600mm HDPE / Ch1542 (12m each) | I.CN.34.22910 | CON - Sec.1 - Culvert : E7-RA-419050-1 - Headwall Stitch Pour | 2025-09-28 | 2025-09-28
I2S-7688-MP-74.CN.S1.34.3.1 | Culvert ID : E7-RA-419050-1 / Type : 2*600mm HDPE / Ch1542 (12m each) | I.CN.34.32910 | CON - Sec.1 - Culvert : E7-RA-419050-1 - HDPE / RCP Pipe Lay & Backfill - Milestone
Culvert ID : E7-RA-418060-1 / Type : 1*450mm HDPE / Ch552 (12.46m)
I2S-7688-MP-74.CN.S1.34.3.3 | Culvert ID : E7-RA-418060-1 / Type : 1*450mm HDPE / Ch552 (12.46m) | I.CN.34.28080 | CON - Sec.1 - Culvert : E7-RA-418060-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.CN.S1.34.3.3 | Culvert ID : E7-RA-418060-1 / Type : 1*450mm HDPE / Ch552 (12.46m) | I.CN.34.28090 | CON - Sec.1 - Culvert : E7-RA-418060-1 - Headwall Stitch Pour
I2S-7688-MP-74.CN.S1.34.3.3 | Culvert ID : E7-RA-418060-1 / Type : 1*450mm HDPE / Ch552 (12.46m) | I.CN.34.28100 | CON - Sec.1 - Culvert : E7-RA-418060-1 - Headwall Cut-off Wall Installation (FRP)
I2S-7688-MP-74.CN.S1.34.3.3 | Culvert ID : E7-RA-418060-1 / Type : 1*450mm HDPE / Ch552 (12.46m) | I.CN.34.28120 | CON - Sec.1 - Culvert : E7-RA-418060-1 - Construct Scour Protection
I2S-7688-MP-74.CN.S1.34.3.3 | Culvert ID : E7-RA-418060-1 / Type : 1*450mm HDPE / Ch552 (12.46m) | I.CN.34.28050 | CON - Sec.1 - Culvert : E7-RA-418060-1 - Site Prep / Detail Excavation
I2S-7688-MP-74.CN.S1.34.3.3 | Culvert ID : E7-RA-418060-1 / Type : 1*450mm HDPE / Ch552 (12.46m) | I.CN.34.28060 | CON - Sec.1 - Culvert : E7-RA-418060-1 - Foundation Treatment
I2S-7688-MP-74.CN.S1.34.3.3 | Culvert ID : E7-RA-418060-1 / Type : 1*450mm HDPE / Ch552 (12.46m) | I.CN.34.28070 | CON - Sec.1 - Culvert : E7-RA-418060-1 - Headwall installation
043 - Fencing |  |  |  | 2025-07-11 | 2025-12-06
I2S-7688-MP-74.CN.S1.43 | 043 - Fencing | I.CN.43.14140 | CON - Sec.1 - Install Demarkation Fencing 0-2900 West Side to protect from track | 2025-07-11 | 2025-07-23
Eastern Side |  |  |  | 2025-09-13 | 2025-10-24
I2S-7688-MP-74.CN.S1.43.1 | Eastern Side | I.CN.43.13330 | CON - Sec.1 - Fencing East Side - Ch0-2900 | 2025-09-13 | 2025-10-24
Western Side |  |  |  | 2025-10-26 | 2025-12-06
I2S-7688-MP-74.CN.S1.43.2 | Western Side | I.CN.43.13900 | CON - Sec.1 - Fencing West Side - Ch0-2900 | 2025-10-26 | 2025-12-06
045 - Access Roads |  |  |  | 2025-07-11 | 2025-11-12
Access/Temp |  |  |  | 2025-07-11 | 2025-07-13
I2S-7688-MP-74.CN.S1.45.1 | Access/Temp | I.CN.45.14410 | CON - Sec.1 - Install left hand lane Gate 2 (02800) and signs | 2025-07-11 | 2025-07-13
RMAR |  |  |  | 2025-11-04 | 2025-11-12
I2S-7688-MP-74.CN.S1.45.2 | RMAR | I.CN.45.14170 | CON - Sec.1 - Prep RMAR Road - East - 200 to 700 | 2025-11-04 | 2025-11-07
I2S-7688-MP-74.CN.S1.45.2 | RMAR | I.CN.45.14330 | CON - Sec.1 - Prep RMAR Road - East - 800 to 2900 | 2025-11-08 | 2025-11-12
050 - Trackwork |  |  |  | 2025-09-13 | 2026-06-10
Shutdown 1 - Track Levelling - Sept 25 - Stage 1 |  |  |  | 2025-09-13 | 2025-09-15
I2S-7688-MP-74.CN.S1.50.16 | Shutdown 1 - Track Levelling - Sept 25 - Stage 1 | I.CN.50.20120 | CON - Sec.1 - Target Readiness for Possession (Sept 2025)
I2S-7688-MP-74.CN.S1.50.16 | Shutdown 1 - Track Levelling - Sept 25 - Stage 1 | I.CN.50.20130 | CON - Sec.1 - Possession Float (Sept 2025)
I2S-7688-MP-74.CN.S1.50.16 | Shutdown 1 - Track Levelling - Sept 25 - Stage 1 | I.CN.50.20140 | CON - Sec.1 - Possession Commencement (Sept 2025)
Rail Safety - Take out
I2S-7688-MP-74.CN.S1.50.16.1 | Rail Safety - Take out | I.CN.50.20410 | CON - Sec.1 - PO's (Sept 25) Possession - Railsafety Take out - WBS Summary
Track works
I2S-7688-MP-74.CN.S1.50.16.2 | Track works | I.CN.50.20420 | CON - Sec.1 - (Sept 25) Possession - Trackworks - WBS Summary
Track Levelling |  |  |  | 2025-09-13 | 2025-09-14
I2S-7688-MP-74.CN.S1.50.16.3 | Track Levelling | I.CN.50.14440 | CON - Sec.1 - Level Formation | 2025-09-13 | 2025-09-14
Track works-2
I2S-7688-MP-74.CN.S1.50.16.4 | Track works-2 | I.CN.50.20430 | CON - Sec.1 - (Sept 25) Possession - Trackworks-2 - WBS Summary
up
I2S-7688-MP-74.CN.S1.50.16.4.1 | up | I.CN.50.20440 | CON - Sec.1 - (Sept 25) Possession - UP - WBS Summary
dn
I2S-7688-MP-74.CN.S1.50.16.4.2 | dn | I.CN.50.20450 | CON - Sec.1 - (Sept 25) Possession - dn - WBS Summary
Rail Safety - handback and contingency |  |  |  | 2025-09-15 | 2025-09-15
I2S-7688-MP-74.CN.S1.50.16.5 | Rail Safety - handback and contingency | I.CN.50.14500 | CON - Sec.1 - Float - Sept 2025 | 2025-09-15 | 2025-09-15
I2S-7688-MP-74.CN.S1.50.16.5 | Rail Safety - handback and contingency | I.CN.50.18960 | CON - Sec.1 - Handback Sec.1 - Sept 2025 | 2025-09-15 | 2025-09-15
091 - Delivery Regime |  |  |  | 2026-02-23 | 2026-03-11
Cross Over pre-build |  |  |  | 2026-03-04 | 2026-03-11
I2S-7688-MP-74.CN.S1.50.91.3 | Cross Over pre-build | I.CN.91.14300 | CON - Sec.1 - Hold point for QA Inspection with IRPL - Turnouts 1 in 18 R1200 (Ilabo) | 2026-03-11 | 2026-03-11
I2S-7688-MP-74.CN.S1.50.91.3 | Cross Over pre-build | I.CN.91.14370 | CON - Sec.1 - Crossover - Lay bearers | 2026-03-04 | 2026-03-04
I2S-7688-MP-74.CN.S1.50.91.3 | Cross Over pre-build | I.CN.91.14380 | CON - Sec.1 - Crossover - Lay Steel | 2026-03-04 | 2026-03-04
I2S-7688-MP-74.CN.S1.50.91.3 | Cross Over pre-build | I.CN.91.14390 | CON - Sec.1 - Crossover - Weld out and clamp | 2026-03-04 | 2026-03-04
I2S-7688-MP-74.CN.S1.50.91.3 | Cross Over pre-build | I.CN.91.14400 | CON - Sec.1 - Hold point for QA Inspection with IRPL - Sec.1 Crossovers | 2026-03-10 | 2026-03-10
Track materials delivery, |  |  |  | 2026-02-23 | 2026-03-11
I2S-7688-MP-74.CN.S1.50.91.2 | Track materials delivery, | I.CN.34.25360 | CON - Sec.1 - Survey set out for bearers - Material laydown set out | 2026-02-24 | 2026-02-24
I2S-7688-MP-74.CN.S1.50.91.2 | Track materials delivery, | I.CN.34.25370 | CON - Sec.1 - Survey set out for bearers - Individual Bearer set out | 2026-02-26 | 2026-03-03
I2S-7688-MP-74.CN.S1.50.91.2 | Track materials delivery, | I.CN.91.14340 | CON - Sec.1 - Ballast- Truck from Quarry - Sec.1 | 2026-02-23 | 2026-02-23
I2S-7688-MP-74.CN.S1.50.91.2 | Track materials delivery, | I.CN.91.14180 | CON - Sec.1 - Delivery, 1 Crossover and Turnout 1 in 18 R1200 (Ilabo) | 2026-03-11 | 2026-03-11
I2S-7688-MP-74.CN.S1.50.91.2 | Track materials delivery, | I.CN.91.14360 | CON - Sec.1 - Turnout/crossover pre build | 2026-03-04 | 2026-03-04
Turnout pre-build |  |  |  | 2026-03-08 | 2026-03-11
I2S-7688-MP-74.CN.S1.50.91.4 | Turnout pre-build | I.CN.91.14410 | CON - Sec.1 - Turnout - Lay bearers | 2026-03-08 | 2026-03-08
I2S-7688-MP-74.CN.S1.50.91.4 | Turnout pre-build | I.CN.91.14420 | CON - Sec.1 - Turnout - Lay Steel | 2026-03-09 | 2026-03-09
I2S-7688-MP-74.CN.S1.50.91.4 | Turnout pre-build | I.CN.91.14430 | CON - Sec.1 - Turnout - Weld out and clamp | 2026-03-10 | 2026-03-10
I2S-7688-MP-74.CN.S1.50.91.4 | Turnout pre-build | I.CN.91.14440 | CON - Sec.1 - Hold point for QA Inspection with IRPL - Turnout prebuilds 1 in 18 R1200 (Ilabo) | 2026-03-11 | 2026-03-11
Shutdown 2- Rail Delivery - Dec 2025
I2S-7688-MP-74.CN.S1.50.4 | Shutdown 2- Rail Delivery - Dec 2025 | I.CN.50.20240 | CON - Sec.1 - Target Readiness for Possession (Dec 2025)
I2S-7688-MP-74.CN.S1.50.4 | Shutdown 2- Rail Delivery - Dec 2025 | I.CN.50.20260 | CON - Sec.1 - Possession Commencement (Dec 25)
I2S-7688-MP-74.CN.S1.50.4 | Shutdown 2- Rail Delivery - Dec 2025 | I.CN.50.20250 | CON - Sec.1 - Float before Possession (Dec 25)
Possession Works
I2S-7688-MP-74.CN.S1.50.4.1 | Possession Works | I.CN.50.20280 | CON - Sec.1 - Rail Delivery On Site - (Dec 25)
I2S-7688-MP-74.CN.S1.50.4.1 | Possession Works | I.CN.50.20290 | CON - Sec.1 - Unload Rail - (Dec 25)
I2S-7688-MP-74.CN.S1.50.4.1 | Possession Works | I.CN.50.20300 | CON - Sec.1 - Rail Stack On Laydown Area (Dec 25)
I2S-7688-MP-74.CN.S1.50.4.1 | Possession Works | I.CN.50.20310 | CON - Sec.1 - Handback/ Possession Complete - (Dec 25)
I2S-7688-MP-74.CN.S1.50.4.1 | Possession Works | I.CN.50.20270 | CON - Sec.1 - Possession Starts - (Dec 25)
Shutdown 3- Install TO- Feb-Mar 26
I2S-7688-MP-74.CN.S1.50.2 | Shutdown 3- Install TO- Feb-Mar 26 | I.CN.50.20150 | CON - Sec.1 - Target Readiness for Possession (Feb - March 2026)
I2S-7688-MP-74.CN.S1.50.2 | Shutdown 3- Install TO- Feb-Mar 26 | I.CN.50.20170 | CON - Sec.1 - Possession Commencement (Feb - March 2026)
I2S-7688-MP-74.CN.S1.50.2 | Shutdown 3- Install TO- Feb-Mar 26 | I.CN.50.20160 | CON - Sec.1 - Contingency before Possession (Feb - March 2026)
Possession Works
I2S-7688-MP-74.CN.S1.50.2.1 | Possession Works | I.CN.50.20190 | CON - Sec.1 - Install Points 100 A & B Tournout - (Feb - March 2026)
I2S-7688-MP-74.CN.S1.50.2.1 | Possession Works | I.CN.50.20200 | CON - Sec.1 - Install Points 100 A & B Points Machine - (Feb - March 2026)
I2S-7688-MP-74.CN.S1.50.2.1 | Possession Works | I.CN.50.20210 | CON - Sec.1 - Detect 100 A&B turn out and Points macine (Feb - March 2026)
I2S-7688-MP-74.CN.S1.50.2.1 | Possession Works | I.CN.50.20220 | CON - Sec.1 - Temping 100 A&B turn out and Points macine (Feb - March 2026)
I2S-7688-MP-74.CN.S1.50.2.1 | Possession Works | I.CN.50.20230 | CON - Sec.1 - Handback/ Possession Complete - (Feb - March 2026)
I2S-7688-MP-74.CN.S1.50.2.1 | Possession Works | I.CN.50.20180 | CON - Sec.1 - Possession Starts - (Feb - March 2026)
Shutdown 4 - Install XO - May 26 - OD changed to 96h - 16-Feb-2026
I2S-7688-MP-74.CN.S1.50.3 | Shutdown 4 - Install XO - May 26 - OD changed to 96h - 16-Feb-2026 | I.CN.50.20320 | CON - Sec.1 - Target Readiness for Possession (May 26)
I2S-7688-MP-74.CN.S1.50.3 | Shutdown 4 - Install XO - May 26 - OD changed to 96h - 16-Feb-2026 | I.CN.50.20340 | CON - Sec.1 - Possession Commencement (May 26)
I2S-7688-MP-74.CN.S1.50.3 | Shutdown 4 - Install XO - May 26 - OD changed to 96h - 16-Feb-2026 | I.CN.50.20330 | CON - Sec.1 - Contingency before Possession (May 26)
Possession Works
I2S-7688-MP-74.CN.S1.50.3.1 | Possession Works | I.CN.50.20460 | CON - Sec.1 - Possession Works - (May 26) - OD Summary - changed to - 96h - 16-Feb-2026
I2S Track Construction |  |  |  | 2026-04-21 | 2026-06-10
Place Bottom Ballast |  |  |  | 2026-04-21 | 2026-04-26
I2S-7688-MP-74.CN.S1.50.18.15 | Place Bottom Ballast | I.CN.50.13250 | CON - Sec.1 - Place Bottom Ballast - 500m/day - 0374 to 1000 (626m) | 2026-04-21 | 2026-04-21
I2S-7688-MP-74.CN.S1.50.18.15 | Place Bottom Ballast | I.CN.50.13260 | CON - Sec.1 - Place Bottom Ballast - 500m/day - 1000 to 1500 (500m) | 2026-04-22 | 2026-04-22
I2S-7688-MP-74.CN.S1.50.18.15 | Place Bottom Ballast | I.CN.50.13270 | CON - Sec.1 - Place Bottom Ballast - 500m/day - 1500 to 2000 (500m) | 2026-04-23 | 2026-04-23
I2S-7688-MP-74.CN.S1.50.18.15 | Place Bottom Ballast | I.CN.50.13280 | CON - Sec.1 - Place Bottom Ballast - 500m/day - 2000 to 2500 (500m) | 2026-04-24 | 2026-04-24
I2S-7688-MP-74.CN.S1.50.18.15 | Place Bottom Ballast | I.CN.50.13290 | CON - Sec.1 - Place Bottom Ballast - 500m/day - 2500 to 2900 (400m) | 2026-04-26 | 2026-04-26
Sleeper Distribution |  |  |  | 2026-04-23 | 2026-04-29
I2S-7688-MP-74.CN.S1.50.18.1 | Sleeper Distribution | I.CN.50.1370 | CON - Sec.1 - Sleeper Distribution - 860mm/day - 374 to 1080 (860m) | 2026-04-27 | 2026-04-27
I2S-7688-MP-74.CN.S1.50.18.1 | Sleeper Distribution | I.CN.50.4670 | CON - Sec.1 - Sleeper Distribution - 860mm/day - 1080 to 1940 (860m) | 2026-04-28 | 2026-04-28
I2S-7688-MP-74.CN.S1.50.18.1 | Sleeper Distribution | I.CN.50.4690 | CON - Sec.1 - Sleeper Distribution - 860mm/day - 1940 to 2800 (860m) | 2026-04-29 | 2026-04-29
I2S-7688-MP-74.CN.S1.50.18.1 | Sleeper Distribution | I.CN.50.14260 | CON - Sec.1 - Intermediate Sleeper Stockpiles - Sec.1 | 2026-04-23 | 2026-04-23
Sleeper Laying |  |  |  | 2026-04-29 | 2026-05-01
I2S-7688-MP-74.CN.S1.50.18.3 | Sleeper Laying | I.CN.50.3750 | CON - Sec.1 - Sleeper Laying - 800m/day - 1820 to 2620 | 2026-05-01 | 2026-05-01
I2S-7688-MP-74.CN.S1.50.18.3 | Sleeper Laying | I.CN.50.1390 | CON - Sec.1 - Sleeper Laying - 800m/day - 374 to 1020 | 2026-04-29 | 2026-04-29
I2S-7688-MP-74.CN.S1.50.18.3 | Sleeper Laying | I.CN.50.3740 | CON - Sec.1 - Sleeper Laying - 800m/day - 1020 to 1820 | 2026-04-30 | 2026-04-30
Rail Distribution |  |  |  | 2026-05-02 | 2026-05-04
I2S-7688-MP-74.CN.S1.50.18.2 | Rail Distribution | I.CN.50.4290 | CON - Sec.1 - Rail Distribution - 1000m/day - 1210 to 2200 | 2026-05-03 | 2026-05-03
I2S-7688-MP-74.CN.S1.50.18.2 | Rail Distribution | I.CN.50.4300 | CON - Sec.1 - Rail Distribution - 1000m/day - 2200 to 3190 | 2026-05-04 | 2026-05-04
I2S-7688-MP-74.CN.S1.50.18.2 | Rail Distribution | I.CN.50.1380 | CON - Sec.1 - Rail Distribution - 1000m/day - 00374 to 01210 | 2026-05-02 | 2026-05-02
Rail Laying |  |  |  | 2026-05-04 | 2026-05-08
I2S-7688-MP-74.CN.S1.50.18.4 | Rail Laying | I.CN.50.3190 | CON - Sec.1 - Rail Laying - 550m/day - 770 to 1320 | 2026-05-05 | 2026-05-05
I2S-7688-MP-74.CN.S1.50.18.4 | Rail Laying | I.CN.50.3200 | CON - Sec.1 - Rail Laying - 550m/day - 1320 to 1870 | 2026-05-06 | 2026-05-06
I2S-7688-MP-74.CN.S1.50.18.4 | Rail Laying | I.CN.50.3210 | CON - Sec.1 - Rail Laying - 550m/day - 1870 to 2420 | 2026-05-07 | 2026-05-07
I2S-7688-MP-74.CN.S1.50.18.4 | Rail Laying | I.CN.50.18280 | CON - Sec.1 - Rail Laying - 550m/day - 2420 to 2970 | 2026-05-08 | 2026-05-08
I2S-7688-MP-74.CN.S1.50.18.4 | Rail Laying | I.CN.50.1400 | CON - Sec.1 - Rail Laying - 550m/day - 374 to 770 | 2026-05-04 | 2026-05-04
Flash Butt Welding and clip up |  |  |  | 2026-05-09 | 2026-05-14
I2S-7688-MP-74.CN.S1.50.18.5 | Flash Butt Welding and clip up | I.CN.50.1410 | CON - Sec.1 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 220 to 1045 | 2026-05-09 | 2026-05-10
I2S-7688-MP-74.CN.S1.50.18.5 | Flash Butt Welding and clip up | I.CN.50.2810 | CON - Sec.1 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 1045 to 1870 | 2026-05-11 | 2026-05-12
I2S-7688-MP-74.CN.S1.50.18.5 | Flash Butt Welding and clip up | I.CN.50.2820 | CON - Sec.1 - Flash Butt Welding and clip up (30 welds/ 412.5 m) - 1870 to 2695 | 2026-05-13 | 2026-05-14
Place Top Ballast Initial |  |  |  | 2026-05-13 | 2026-05-16
I2S-7688-MP-74.CN.S1.50.18.6 | Place Top Ballast Initial | I.CN.50.1420 | CON - Sec.1 - Place Top Ballast Initial - 1500m/day - 374 to 1720 | 2026-05-13 | 2026-05-13
I2S-7688-MP-74.CN.S1.50.18.6 | Place Top Ballast Initial | I.CN.50.1430 | CON - Sec.1 - Place Top Ballast Initial - 1500m/day - 1720 to 3220 | 2026-05-16 | 2026-05-16
Traverse & Level GEDO |  |  |  | 2026-05-17 | 2026-05-17
I2S-7688-MP-74.CN.S1.50.18.14 | Traverse & Level GEDO | I.CN.50.18140 | CON - Sec.1 - Traverse and level Gedo Control - 374 to 4220 | 2026-05-17 | 2026-05-17
Surfacing Firsts |  |  |  | 2026-05-18 | 2026-05-18
I2S-7688-MP-74.CN.S1.50.18.7 | Surfacing Firsts | I.CN.50.1460 | CON - Sec.1 - Surfacing Firsts - 4000m/day - 374 to 4220 | 2026-05-18 | 2026-05-18
Surfacing Seconds |  |  |  | 2026-05-19 | 2026-05-19
I2S-7688-MP-74.CN.S1.50.18.8 | Surfacing Seconds | I.CN.50.1470 | CON - Sec.1 - Surfacing Seconds - 4000m/day - 374 to 4220 | 2026-05-19 | 2026-05-19
Top Ballast Finals |  |  |  | 2026-05-20 | 2026-05-20
I2S-7688-MP-74.CN.S1.50.18.9 | Top Ballast Finals | I.CN.50.1480 | CON - Sec.1 - Top Ballast Finals - 3000m/day - 0 to 3000 | 2026-05-20 | 2026-05-20
Surfacing Final |  |  |  | 2026-05-21 | 2026-05-21
I2S-7688-MP-74.CN.S1.50.18.10 | Surfacing Final | I.CN.50.1490 | CON - Sec.1 - Surfacing Final - 6000m/day - 0 to 6000 | 2026-05-21 | 2026-05-21
Destressing |  |  |  | 2026-05-22 | 2026-06-09
I2S-7688-MP-74.CN.S1.50.18.11 | Destressing | I.CN.50.1500 | CON - Sec.1 - Destressing - 1200m/day - 0 to 1200 | 2026-05-22 | 2026-05-22
I2S-7688-MP-74.CN.S1.50.18.11 | Destressing | I.CN.50.1910 | CON - Sec.1 - Destressing - 1200 to 2400 | 2026-05-23 | 2026-05-23
I2S-7688-MP-74.CN.S1.50.18.11 | Destressing | I.CN.50.1920 | CON - Sec.1 - Destressing - 1200m/day - 2400 to 3600 | 2026-06-09 | 2026-06-09
Corrections + Signage + Rubber Xings |  |  |  | 2026-05-24 | 2026-05-26
I2S-7688-MP-74.CN.S1.50.18.12 | Corrections + Signage + Rubber Xings | I.CN.50.1510 | CON - Sec.1 - Corrections + Signage - 2000m/day - 0 to 1500 | 2026-05-24 | 2026-05-24
I2S-7688-MP-74.CN.S1.50.18.12 | Corrections + Signage + Rubber Xings | I.CN.50.1710 | CON - Sec.1 - Corrections + Signage - 2000m/day - 1500 to 2900 | 2026-05-26 | 2026-05-26
Track Joint Inspection |  |  |  | 2026-06-10 | 2026-06-10
I2S-7688-MP-74.CN.S1.50.18.13 | Track Joint Inspection | I.CN.50.1520 | CON - Sec.1 - Track Joint Inspection - 5000m/day - Sec.1 - 0000 -2900 | 2026-06-10 | 2026-06-10
062 - Bridges |  |  |  | 2025-11-12 | 2026-04-12
Billabong Creek Bridge - (over creek) - BR701 - Standard PSC Slab Span 14m (ARTC) |  |  |  | 2025-11-12 | 2026-04-12
Preliminaries |  |  |  | 2025-11-12 | 2025-11-22
I2S-7688-MP-74.CN.S1.62.2.1 | Preliminaries | I.CN.62.5520 | CON - Sec.1 - Billabong Ck Br - Bridge site prep /Temp Fence/Road Barriers | 2025-11-12 | 2025-11-17
I2S-7688-MP-74.CN.S1.62.2.1 | Preliminaries | I.CN.62.5530 | CON - Sec.1 - Billabong Ck Br - Construct site access from gate 2 | 2025-11-18 | 2025-11-19
I2S-7688-MP-74.CN.S1.62.2.1 | Preliminaries | I.CN.62.14730 | CON - Sec.1 - Billabong Ck Br - Construct laydown area /Causeway (inc pipes) | 2025-11-20 | 2025-11-22
Piling |  |  |  | 2025-11-23 | 2026-01-18
Platforms |  |  |  | 2025-11-23 | 2025-11-30
I2S-7688-MP-74.CN.S1.62.2.2.1 | Platforms | I.CN.62.5580 | CON - Sec.1 - Billabong Ck Br - Excavate platform for piling pad | 2025-11-23 | 2025-11-28
I2S-7688-MP-74.CN.S1.62.2.2.1 | Platforms | I.CN.62.14740 | CON - Sec.1 - Billabong Ck Br - Place and test platform | 2025-11-29 | 2025-11-30
Drill Piles |  |  |  | 2025-12-19 | 2026-01-12
I2S-7688-MP-74.CN.S1.62.2.2.3 | Drill Piles | I.CN.62.14760 | CON - Sec.1 - Billabong Ck Br - abutment piling consists of 4 x 1200mm dia bored concrete piles | 2025-12-20 | 2025-12-23
I2S-7688-MP-74.CN.S1.62.2.2.3 | Drill Piles | I.CN.62.14780 | CON - Sec.1 - Billabong Ck Br - Demobilise piling rig | 2026-01-12 | 2026-01-12
I2S-7688-MP-74.CN.S1.62.2.2.3 | Drill Piles | I.CN.62.19490 | CON - Sec.1 - Billabong Ck Br - pier pling consist of 6 x 1200mm dia bored concrete piles | 2026-01-06 | 2026-01-11
I2S-7688-MP-74.CN.S1.62.2.2.3 | Drill Piles | I.CN.62.14700 | CON - Sec.1 - Billabong Ck Br - Mobilise piling rig | 2025-12-19 | 2025-12-19
I2S-7688-MP-74.CN.S1.62.2.2.3 | Drill Piles | I.CN.62.23090 | CON - Sec.1 - Billabong Ck Br - abutment piling consists of 4 x 1200mm dia bored concrete piles - Milestone
Piles Concrete |  |  |  | 2026-01-13 | 2026-01-18
I2S-7688-MP-74.CN.S1.62.2.2.4 | Piles Concrete | I.CN.62.19780 | CON - Sec.1 - Billabong Ck Br - Place pile concrete | 2026-01-13 | 2026-01-18
Piers |  |  |  | 2026-01-13 | 2026-03-04
I2S-7688-MP-74.CN.S1.62.2.3 | Piers | I.CN.62.22440 | CON - Sec.1 - Billabong Ck Br - FRP - Bearing Mortar Pads (x3)
I2S-7688-MP-74.CN.S1.62.2.3 | Piers | I.CN.62.14800 | CON - Sec.1 - Billabong Ck Br - FRP - Pier Columns (x3) | 2026-01-19 | 2026-01-27
I2S-7688-MP-74.CN.S1.62.2.3 | Piers | I.CN.62.14810 | CON - Sec.1 - Billabong Ck Br - FRP - Restraint Block (x3) | 2026-01-26 | 2026-02-02
I2S-7688-MP-74.CN.S1.62.2.3 | Piers | I.CN.62.14830 | CON - Sec.1 - Billabong Ck Br - FRP - Headstock (x3) | 2026-03-01 | 2026-03-04
I2S-7688-MP-74.CN.S1.62.2.3 | Piers | I.CN.62.19730 | CON - Sec.1 - Billabong Ck Br - Detailed Earthworks | 2026-01-13 | 2026-01-16
Abutments |  |  |  | 2026-01-28 | 2026-03-07
Site Prep |  |  |  | 2026-01-28 | 2026-01-29
I2S-7688-MP-74.CN.S1.62.2.7.1 | Site Prep | I.CN.62.20960 | CON - Sec.1 - Billabong Ck Br - Site prep Abutment Footings / Blinding | 2026-01-28 | 2026-01-29
North |  |  |  | 2026-01-30 | 2026-02-20
I2S-7688-MP-74.CN.S1.62.2.7.2 | North | I.CN.62.14870 | CON - Sec.1 - Billabong Ck Br - FRP - Back Wall - North Abutment | 2026-02-09 | 2026-02-13
I2S-7688-MP-74.CN.S1.62.2.7.2 | North | I.CN.62.19750 | CON - Sec.1 - Billabong Ck Br - FRP - Wing Walls - North Abutment | 2026-02-14 | 2026-02-20
I2S-7688-MP-74.CN.S1.62.2.7.2 | North | I.CN.62.20970 | CON - Sec.1 - Billabong Ck Br - Detailed Earthworks - North Abutment | 2026-01-30 | 2026-01-31
I2S-7688-MP-74.CN.S1.62.2.7.2 | North | I.CN.62.22450 | CON - Sec.1 - Billabong Ck Br - FRP - Restraint Block - North Abutment
I2S-7688-MP-74.CN.S1.62.2.7.2 | North | I.CN.62.22460 | CON - Sec.1 - Billabong Ck Br - FRP - Bearing Mortar Pads - North Abutment
I2S-7688-MP-74.CN.S1.62.2.7.2 | North | I.CN.62.14860 | CON - Sec.1 - Billabong Ck Br - FRP - Abutment Cill Beam - North Abutment | 2026-02-03 | 2026-02-13
South |  |  |  | 2026-02-18 | 2026-03-07
I2S-7688-MP-74.CN.S1.62.2.7.3 | South | I.CN.62.14820 | CON - Sec.1 - Billabong Ck Br - FRP - Back Wall - South Abutment | 2026-02-23 | 2026-02-28
I2S-7688-MP-74.CN.S1.62.2.7.3 | South | I.CN.62.14880 | CON - Sec.1 - Billabong Ck Br - FRP - Abutment Cill Beam - South Abutment | 2026-02-18 | 2026-02-28
I2S-7688-MP-74.CN.S1.62.2.7.3 | South | I.CN.62.19760 | CON - Sec.1 - Billabong Ck Br - FRP - Wing Walls - South Abutment | 2026-03-01 | 2026-03-07
I2S-7688-MP-74.CN.S1.62.2.7.3 | South | I.CN.62.22470 | CON - Sec.1 - Billabong Ck Br - Detailed Earthworks - South Abutment
I2S-7688-MP-74.CN.S1.62.2.7.3 | South | I.CN.62.22490 | CON - Sec.1 - Billabong Ck Br - FRP - Restraint Block - South Abutment
I2S-7688-MP-74.CN.S1.62.2.7.3 | South | I.CN.62.22500 | CON - Sec.1 - Billabong Ck Br - FRP - Bearing Mortar Pads - South Abutment
Superstructure |  |  |  | 2026-03-01 | 2026-04-07
I2S-7688-MP-74.CN.S1.62.2.4 | Superstructure | I.CN.62.14950 | CON - Sec.1 - Billabong Ck Br - handling /QA of 14m Prestressed Precast Beams | 2026-03-01 | 2026-03-02
I2S-7688-MP-74.CN.S1.62.2.4 | Superstructure | I.CN.62.14960 | CON - Sec.1 - Billabong Ck Br - Install bridge bearings | 2026-03-06 | 2026-03-08
I2S-7688-MP-74.CN.S1.62.2.4 | Superstructure | I.CN.62.15000 | CON - Sec.1 - Billabong Ck Br - Install/Lift Bridge span (Standard PSC Slab Span 14m (IRPL) (8 off (2 per span)) | 2026-03-09 | 2026-03-18
I2S-7688-MP-74.CN.S1.62.2.4 | Superstructure | I.CN.62.14920 | CON - Sec.1 - Billabong Ck Br - Install Handrails (raking/horizontal) | 2026-03-29 | 2026-04-01
I2S-7688-MP-74.CN.S1.62.2.4 | Superstructure | I.CN.62.14930 | CON - Sec.1 - Billabong Ck Br - Install access walkways | 2026-04-03 | 2026-04-07
I2S-7688-MP-74.CN.S1.62.2.4 | Superstructure | I.CN.62.22510 | CON - Sec.1 - Billabong Ck Br - Crane Pads for Crane Lift
I2S-7688-MP-74.CN.S1.62.2.4 | Superstructure | I.CN.62.22520 | CON - Sec.1 - Billabong Ck Br - Install & Stress Tie Bars
Approach Slab / Deck |  |  |  | 2026-03-09 | 2026-03-24
I2S-7688-MP-74.CN.S1.62.2.6 | Approach Slab / Deck | I.CN.62.14900 | CON - Sec.1 - Billabong Ck Br - Approach Slab South | 2026-03-20 | 2026-03-24
I2S-7688-MP-74.CN.S1.62.2.6 | Approach Slab / Deck | I.CN.62.15020 | CON - Sec.1 - Billabong Ck Br - Approach Slab North | 2026-03-09 | 2026-03-19
I2S-7688-MP-74.CN.S1.62.2.6 | Approach Slab / Deck | I.CN.62.22530 | CON - Sec.1 - Billabong Ck Br - Wing Walls North
I2S-7688-MP-74.CN.S1.62.2.6 | Approach Slab / Deck | I.CN.62.22540 | CON - Sec.1 - Billabong Ck Br - Wing Walls South
Bridge Finishing Works |  |  |  | 2026-03-03 | 2026-04-12
I2S-7688-MP-74.CN.S1.62.2.5 | Bridge Finishing Works | I.CN.62.21920 | CON - Sec.1 - Billabong Ck Br - Handle, Place, Finish and Cure Footpath/ Steps - 21m3 | 2026-03-29 | 2026-04-02
I2S-7688-MP-74.CN.S1.62.2.5 | Bridge Finishing Works | I.CN.62.22550 | CON - Sec.1 - Billabong Ck Br - Install CSR Ducting
I2S-7688-MP-74.CN.S1.62.2.5 | Bridge Finishing Works | I.CN.62.5560 | CON - Sec.1 - Billabong Ck Br - Bridging Strips, compressible fillers and isolation inserts | 2026-03-20 | 2026-03-24
I2S-7688-MP-74.CN.S1.62.2.5 | Bridge Finishing Works | I.CN.62.5570 | CON - Sec.1 - Billabong Ck Br - Install groundwater standpipe | 2026-03-29 | 2026-04-06
I2S-7688-MP-74.CN.S1.62.2.5 | Bridge Finishing Works | I.CN.62.14850 | CON - Sec.1 - Billabong Ck Br - Instrumentation & Monitoring | 2026-03-03 | 2026-03-10
I2S-7688-MP-74.CN.S1.62.2.5 | Bridge Finishing Works | I.CN.62.14890 | CON - Sec.1 - Billabong Ck Br - Expansion joint cover plates | 2026-03-26 | 2026-03-30
I2S-7688-MP-74.CN.S1.62.2.5 | Bridge Finishing Works | I.CN.62.14910 | CON - Sec.1 - Billabong Ck Br - Install bridge barriers 56m | 2026-03-26 | 2026-03-28
I2S-7688-MP-74.CN.S1.62.2.5 | Bridge Finishing Works | I.CN.62.14940 | CON - Sec.1 - Billabong Ck Br - Install maintenance access stairs / handrails / platform | 2026-04-08 | 2026-04-12
I2S-7688-MP-74.CN.S1.62.2.5 | Bridge Finishing Works | I.CN.62.15040 | CON - Sec.1 - Billabong Ck Br - Batter Slopes & Install "Nylex Cordrain" fixed to vertical face of ballast walls | 2026-03-20 | 2026-03-24
I2S-7688-MP-74.CN.S1.62.2.5 | Bridge Finishing Works | I.CN.62.19280 | CON - Sec.1 - Billabong Ck Br - Completion - Sec.1 |  | 2026-04-12
065 - Crossings |  |  |  | 2026-03-14 | 2026-09-18
Fauna Crossing |  |  |  | 2026-09-16 | 2026-09-18
I2S-7688-MP-74.CN.S1.65.3 | Fauna Crossing | I.CN.65.12920 | CON - Sec.1 - Install fauna crossing, [2 x poles foundations /cure - CH750] | 2026-09-16 | 2026-09-17
I2S-7688-MP-74.CN.S1.65.3 | Fauna Crossing | I.CN.65.17940 | CON - Sec.1 - Install fauna crossing, [2 x poles with rope bridge - CH750] | 2026-09-18 | 2026-09-18
Public LX - Forest Lodge Road (PU2800) - (2794) - Active / NSW / RX-5 |  |  |  | 2026-03-14 | 2026-03-15
Roadworks |  |  |  | 2026-03-14 | 2026-03-15
I2S-7688-MP-74.CN.S1.65.4.5 | Roadworks | I.CN.65.17840 | CON - Sec.1 - Public LX - Forest Lodge Road (PU2800) - Remove fencing, assembly signs and posts | 2026-03-14 | 2026-03-15
072 - Signalling |  |  |  | 2026-01-06 | 2027-04-03
Signals |  |  |  | 2026-03-14 | 2027-03-14
I2S-7688-MP-74.CN.S1.72.1 | Signals | I.CN.72.16790 | CON - Sec.1 - Sig - Prepare & Submit of IWP (Sec.1)
I2S-7688-MP-74.CN.S1.72.1 | Signals | I.CN.72.15560 | CON - Sec.1 - Sig - Install New Main Signals (1 off) 418010 | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.CN.S1.72.1 | Signals | I.CN.72.15650 | CON - Sec.1 - Sig - Remove 6 Main Signals | 2027-03-13 | 2027-03-14
I2S-7688-MP-74.CN.S1.72.1 | Signals | I.CN.72.15170 | CON - Sec.1 - Sig - Install New Main Signals (1 off) 418080 | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.CN.S1.72.1 | Signals | I.CN.72.15550 | CON - Sec.1 - Sig - Install New Main Signals (1 off) -60 | 2026-03-14 | 2026-03-15
I2S-7688-MP-74.CN.S1.72.1 | Signals | I.CN.72.16810 | CON - Sec.1 - Sig - Approval of MWP (Sec.1)
I2S-7688-MP-74.CN.S1.72.1 | Signals | I.CN.72.16820 | CON - Sec.1 - Sig - IRPL Approval of IWP (Sec.1)
Points |  |  |  | 2026-03-14 | 2027-03-14
I2S-7688-MP-74.CN.S1.72.2 | Points | I.CN.72.15180 | CON - Sec.1 - Sig - Install New Points Machine (3 off)) 417500 to 417700 | 2026-03-14 | 2026-03-16
I2S-7688-MP-74.CN.S1.72.2 | Points | I.CN.72.15190 | CON - Sec.1 - Sig - Install New Points Machine (3 off) 417700 to 417900 | 2026-03-14 | 2026-03-15
I2S-7688-MP-74.CN.S1.72.2 | Points | I.CN.72.15660 | CON - Sec.1 - Sig - Remove 1 Ground Frame Point | 2027-03-14 | 2027-03-14
Axle |  |  |  | 2026-03-14 | 2026-03-16
I2S-7688-MP-74.CN.S1.72.3 | Axle | I.CN.72.16740 | CON - Sec.1 - Sig - Install New Axles Counter (3 off) 417900 to 418100
I2S-7688-MP-74.CN.S1.72.3 | Axle | I.CN.72.16750 | CON - Sec.1 - Sig - Install New Axles Counter (4 off) 418500 to 418700
I2S-7688-MP-74.CN.S1.72.3 | Axle | I.CN.72.15210 | CON - Sec.1 - Sig - Install New Axles Counter (10 off) - 800 to 0 | 2026-03-14 | 2026-03-16
I2S-7688-MP-74.CN.S1.72.3 | Axle | I.CN.72.16240 | CON - Sec.1 - Sig - Install New Axles Counter (1 off) 417600
I2S-7688-MP-74.CN.S1.72.3 | Axle | I.CN.72.16730 | CON - Sec.1 - Sig - Install New Axles Counter (3 off) 417700 to 417900
Track |  |  |  | 2026-03-14 | 2027-03-15
I2S-7688-MP-74.CN.S1.72.4 | Track | I.CN.72.15220 | CON - Sec.1 - Sig - Install New BLR DC Track (6 off) (460416 to 470971) | 2026-03-14 | 2026-03-16
I2S-7688-MP-74.CN.S1.72.4 | Track | I.CN.72.15670 | CON - Sec.1 - Sig - Remove - DC Track | 2027-03-13 | 2027-03-15
Misc Equipment |  |  |  | 2026-03-14 | 2026-03-16
I2S-7688-MP-74.CN.S1.72.9 | Misc Equipment | I.CN.74.14860 | CON - Sec.1 - Sig - Install Track Side Equipment (speed signs/motor generators/notice boards) | 2026-03-14 | 2026-03-16
Building |  |  |  | 2027-03-14 | 2027-03-15
I2S-7688-MP-74.CN.S1.72.7 | Building | I.CN.72.16200 | CON - Sec.1 - Sig - Install New SER/Building (1 off) 417700 to 417900
I2S-7688-MP-74.CN.S1.72.7 | Building | I.CN.72.16190 | CON - Sec.1 - Sig - Verification/Test and FAT of Pre Built Signalling Location Cases
I2S-7688-MP-74.CN.S1.72.7 | Building | I.CN.72.16180 | CON - Sec.1 - Sig - Site terminations and SAT of location cases
I2S-7688-MP-74.CN.S1.72.7 | Building | I.CN.72.15690 | CON - Sec.1 - Sig - Remove 1 Building | 2027-03-14 | 2027-03-15
Cabling |  |  |  | 2026-01-06 | 2027-04-03
I2S-7688-MP-74.CN.S1.72.8 | Cabling | I.CN.72.15810 | CON - Sec.1 - Sig - Cable Removal | 2027-03-16 | 2027-04-03
I2S-7688-MP-74.CN.S1.72.8 | Cabling | I.CN.74.14320 | CON - Sec.1 - CSR - Main Cable Route - MCR - Pull Cable - 5338 to 2800 | 2026-01-06 | 2026-01-06
I2S-7688-MP-74.CN.S1.72.8 | Cabling | I.CN.74.14330 | CON - Sec.1 - CSR - Main Cable Route - MCR - Pull Cable - 5338 - 200 | 2026-03-18 | 2026-03-18
Testing |  |  |  | 2026-02-20 | 2026-02-20
I2S-7688-MP-74.CN.S1.72.10 | Testing | I.CN.74.14900 | CON - Sec.1 - Sig - All pre works for TO commissioning ready | 2026-02-20
I2S-7688-MP-74.CN.S1.72.10 | Testing | I.CN.74.15200 | CON - Sec.1 - Sig - Pre-Testing Prior to Possession
Location Case
I2S-7688-MP-74.CN.S1.72.11 | Location Case | I.CN.72.16760 | CON - Sec.1 - Sig - Install New Location Case (2 off) (New) -800 to 0
074 - Power Supply and Distributions |  |  |  | 2025-08-13 | 2025-12-11
CSR |  |  |  | 2025-08-13 | 2025-12-11
Main Cable Route - MCR |  |  |  | 2025-08-13 | 2025-12-11
I2S-7688-MP-74.CN.S1.74.2.1 | Main Cable Route - MCR | I.CN.74.15950 | CON - Sec.1 - CSR - MCR - Install - Dn Tie with Illabo (4000m) - Part 2
I2S-7688-MP-74.CN.S1.74.2.1 | Main Cable Route - MCR | I.CN.74.15210 | CON - Sec.1 - CSR - MCR - Install - Up Main 418400- 418500 (100m)
I2S-7688-MP-74.CN.S1.74.2.1 | Main Cable Route - MCR | I.CN.74.13970 | CON - Sec.1 - CSR - MCR - Install - Dn Tie with Illabo (4000m) - Part 1 | 2025-08-13 | 2025-08-17
I2S-7688-MP-74.CN.S1.74.2.1 | Main Cable Route - MCR | I.CN.74.13980 | CON - Sec.1 - CSR - MCR - Install - Dn Main Ch0-418200 (Billabong Bridge) (400m) | 2025-08-18 | 2025-08-22
I2S-7688-MP-74.CN.S1.74.2.1 | Main Cable Route - MCR | I.CN.74.13990 | CON - Sec.1 - CSR - MCR - Install - Over Billabong Bridge | 2025-08-23 | 2025-09-30
I2S-7688-MP-74.CN.S1.74.2.1 | Main Cable Route - MCR | I.CN.74.14000 | CON - Sec.1 - CSR - MCR - Install - Up Main Ch0-418100 (600m) | 2025-10-01 | 2025-10-20
I2S-7688-MP-74.CN.S1.74.2.1 | Main Cable Route - MCR | I.CN.74.14010 | CON - Sec.1 - CSR - MCR - Install - Dn Main Ch418200 to 420300 (LX) (2100m) | 2025-10-21 | 2025-12-11
Local Cable Route - LCR |  |  |  | 2025-09-14 | 2025-10-18
I2S-7688-MP-74.CN.S1.74.2.2 | Local Cable Route - LCR | I.CN.74.14140 | CON - Sec.1 - CSR - LCR - Construct - Up - 60 / Dn -60 | 2025-09-28 | 2025-10-01
I2S-7688-MP-74.CN.S1.74.2.2 | Local Cable Route - LCR | I.CN.74.14150 | CON - Sec.1 - CSR - LCR - Construct - 4 No Dn / 60 to 275 | 2025-10-04 | 2025-10-08
I2S-7688-MP-74.CN.S1.74.2.2 | Local Cable Route - LCR | I.CN.74.14160 | CON - Sec.1 - CSR - LCR - Construct - Dn 417810 | 2025-10-14 | 2025-10-18
I2S-7688-MP-74.CN.S1.74.2.2 | Local Cable Route - LCR | I.CN.74.14300 | CON - Sec.1 - CSR - LCR - Construct - Dn 417830 | 2025-09-18 | 2025-09-21
I2S-7688-MP-74.CN.S1.74.2.2 | Local Cable Route - LCR | I.CN.74.14310 | CON - Sec.1 - CSR - LCR - Construct - 2 No Dn 417850 | 2025-10-08 | 2025-10-11
I2S-7688-MP-74.CN.S1.74.2.2 | Local Cable Route - LCR | I.CN.74.14050 | CON - Sec.1 - CSR - LCR - Construct - Up -10 / Up 10 | 2025-10-01 | 2025-10-04
I2S-7688-MP-74.CN.S1.74.2.2 | Local Cable Route - LCR | I.CN.74.14080 | CON - Sec.1 - CSR - LCR - Construct - Dn 417840 | 2025-09-14 | 2025-09-18
I2S-7688-MP-74.CN.S1.74.2.2 | Local Cable Route - LCR | I.CN.74.14100 | CON - Sec.1 - CSR - LCR - Construct - Dn 417800 | 2025-10-11 | 2025-10-14
I2S-7688-MP-74.CN.S1.74.2.2 | Local Cable Route - LCR | I.CN.74.15230 | CON - Sec.1 - CSR - LCR - Construct - Dn 418000
I2S-7688-MP-74.CN.S1.74.2.2 | Local Cable Route - LCR | I.CN.74.15220 | CON - Sec.1 - CSR - LCR - Construct - Up 417880
I2S-7688-MP-74.CN.S1.74.2.2 | Local Cable Route - LCR | I.CN.74.15240 | CON - Sec.1 - CSR - LCR - Construct - Dn 418010
I2S-7688-MP-74.CN.S1.74.2.2 | Local Cable Route - LCR | I.CN.74.15250 | CON - Sec.1 - CSR - LCR - Construct - Up 418100
I2S-7688-MP-74.CN.S1.74.2.2 | Local Cable Route - LCR | I.CN.74.15260 | CON - Sec.1 - CSR - LCR - Construct - Dn 418200
I2S-7688-MP-74.CN.S1.74.2.2 | Local Cable Route - LCR | I.CN.74.15270 | CON - Sec.1 - CSR - LCR - Construct - Up 418500
ULX |  |  |  | 2025-09-13 | 2025-09-14
I2S-7688-MP-74.CN.S1.74.2.3 | ULX | I.CN.74.14060 | CON - Sec.1 - CSR - Local ULX - Across Track - 418400 - POSS | 2025-09-13 | 2025-09-14
I2S-7688-MP-74.CN.S1.74.2.3 | ULX | I.CN.74.14090 | CON - Sec.1 - CSR - Local ULX - Across Track - 418005 - POSS | 2025-09-13 | 2025-09-13
085 - Landscaping
I2S-7688-MP-74.CN.S1.85 | 085 - Landscaping | I.CN.85.14070 | CON - Sec.1 - Landscape - Re-spread Topsoil - Ch000-2900
I2S-7688-MP-74.CN.S1.85 | 085 - Landscaping | I.CN.85.14080 | CON - Sec.1 - Landscape - Hydroseed Application - Ch000-2900
Testing and Commissioning / Operational |  |  |  | 2026-04-24 | 2027-03-15
Burley Griffin Way Realignment Operational |  |  |  | 2026-10-27 | 2026-11-03
I2S-7688-MP-74.TC.6 | Burley Griffin Way Realignment Operational | I.CN.11.5820 | T&C - Burley Griffin Way Road inspection by RMS/TfNSW for Realignment Operational - Returned Works B | 2026-10-27 | 2026-11-03
Track Installation - Testing and Commissioning |  |  |  | 2026-09-13 | 2027-03-14
I2S-7688-MP-74.TC.t | Track Installation - Testing and Commissioning | I.CN.11.5800 | T&C - Mar 2027 Possession - Track - Testing and Commissioning - I2S - Portion 2 | 2027-03-13 | 2027-03-14
I2S-7688-MP-74.TC.t | Track Installation - Testing and Commissioning | I.CN.11.14310 | T&C - Sep 2026 Possession - Track - Testing and Commissioning - CRN - RW-A (Sep 2026) | 2026-09-13 | 2026-09-14
I2S-7688-MP-74.TC.t | Track Installation - Testing and Commissioning | I.CN.11.14320 | T&C - Sep 2026 Possession - Track - Testing and Commissioning - S2P - Portion 1(Sep 2026) | 2026-09-13 | 2026-09-14
I2S-7688-MP-74.TC.t | Track Installation - Testing and Commissioning | I.CN.50.18480 | T&C - Contingency before T&C can commence - Portion 2 | 2026-12-12 | 2027-03-13
Signal Testing and Commissioning |  |  |  | 2026-04-24 | 2027-03-15
I2S-7688-MP-74.TC.s | Signal Testing and Commissioning | I.CN.72.16210 | T&C - Approval of CWP
I2S-7688-MP-74.TC.s | Signal Testing and Commissioning | I.CN.50.12890 | T&C - NEW CRN route operational | 2026-09-14
I2S-7688-MP-74.TC.s | Signal Testing and Commissioning | I.CN.50.15390 | T&C - NEW S2P route operational - ( 37300 - 42500) |  | 2026-09-14
CRN - Testing and Commissioning |  |  |  | 2026-09-14 | 2026-09-14
I2S-7688-MP-74.TC.s.2 | CRN - Testing and Commissioning | I.CN.50.18520 | T&C - Signalling Testing and Commissioning - CRN - RW-A (Sep 2026) - POSS | 2026-09-14 | 2026-09-14
S2P - Testing and Commissioning |  |  |  | 2026-09-14 | 2026-09-14
I2S-7688-MP-74.TC.s.3 | S2P - Testing and Commissioning | I.CN.50.18530 | T&C - Signalling Testing and Commissioning - S2P - Portion 1 (Sep 2026) - POSS | 2026-09-14 | 2026-09-14
I2S - Testing and Commissioning |  |  |  | 2026-04-24 | 2027-03-15
Works ready milestones |  |  |  | 2026-04-24 | 2026-12-12
I2S-7688-MP-74.TC.s.1.5 | Works ready milestones | I.CN.74.1620 | T&C - Signalling STW (Pre-comm ready) - I2S Mainline - Stockinbingal Sec.6 - (37300 - 38000) | 2026-04-24 | 2026-04-26
I2S-7688-MP-74.TC.s.1.5 | Works ready milestones | I.CN.74.5620 | T&C - Signalling STW (Pre-comm ready) - I2S Mainline - Illabo Sec.1 - (0020-2900) | 2026-06-11 | 2026-06-11
I2S-7688-MP-74.TC.s.1.5 | Works ready milestones | I.CN.74.14710 | T&C - Signalling STW (Pre-comm ready) - I2S Mainline - Stockinbingal Sec.5 - (28300 - 37300) | 2026-12-11 | 2026-12-12
I2S-7688-MP-74.TC.s.1.5 | Works ready milestones | I.CN.74.14750 | T&C - Signalling STW (Pre-comm ready) - I2S Mainline - Stockinbingal Sec.4 - (18500 - 28300) | 2026-11-16 | 2026-11-16
I2S-7688-MP-74.TC.s.1.5 | Works ready milestones | I.CN.74.14790 | T&C - Signalling STW (Pre-comm ready) - I2S Mainline - Dirnaseer Sec.2 & Sec.3 - (8840-11000) | 2026-08-31 | 2026-09-01
I2S-7688-MP-74.TC.s.1.5 | Works ready milestones | I.CN.74.14830 | T&C - Signalling STW (Pre-comm ready) - I2S Mainline - Dirnaseer Sec.2 & Sec.3 - (6000-8840) | 2026-07-13 | 2026-07-13
I2S-7688-MP-74.TC.s.1.5 | Works ready milestones | I.CN.74.15040 | T&C - Signalling STW (Pre-comm ready) - I2S Mainline - Stockinbingal Sec.6 - Temp Div (38000 - 42000) | 2026-09-14 | 2026-09-14
I2S-7688-MP-74.TC.s.1.5 | Works ready milestones | I.CN.74.15160 | T&C - Signalling STW (Pre-comm ready) - I2S Mainline - Illabo Sec.2 & Sec.3 - (2900-6000) | 2026-07-13 | 2026-07-13
I2S-7688-MP-74.TC.s.1.5 | Works ready milestones | I.CN.74.15170 | T&C - Signalling STW (Pre-comm ready) - I2S Mainline - Stockinbingal Sec.3 - (11000 - 18500) | 2026-08-31 | 2026-09-01
Pre Shift - Prep |  |  |  | 2027-03-13 | 2027-03-15
I2S-7688-MP-74.TC.s.1.1 | Pre Shift - Prep | I.CN.11.14460 | T&C - March 2027 Possession - Commissioning - Pre-start Briefing Shift 1 | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.TC.s.1.1 | Pre Shift - Prep | I.CN.11.14490 | T&C - March 2027 Possession - Commissioning - Travel to site Shift 1 | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.TC.s.1.1 | Pre Shift - Prep | I.CN.11.14500 | T&C - March 2027 Possession - Commissioning - Pre-start Briefing Shift 2 | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.TC.s.1.1 | Pre Shift - Prep | I.CN.11.14510 | T&C - March 2027 Possession - Commissioning - Travel to site Shift 2 | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.TC.s.1.1 | Pre Shift - Prep | I.CN.11.14520 | T&C - March 2027 Possession - Commissioning - Pre-start Briefing Shift 3 | 2027-03-14 | 2027-03-14
I2S-7688-MP-74.TC.s.1.1 | Pre Shift - Prep | I.CN.11.14530 | T&C - March 2027 Possession - Commissioning - Travel to site Shift 3 | 2027-03-14 | 2027-03-14
I2S-7688-MP-74.TC.s.1.1 | Pre Shift - Prep | I.CN.11.14540 | T&C - March 2027 Possession - Commissioning - Pre-start Briefing Shift 4 | 2027-03-14 | 2027-03-14
I2S-7688-MP-74.TC.s.1.1 | Pre Shift - Prep | I.CN.11.14550 | T&C - March 2027 Possession - Commissioning - Travel to site Shift 4 | 2027-03-14 | 2027-03-14
I2S-7688-MP-74.TC.s.1.1 | Pre Shift - Prep | I.CN.11.14560 | T&C - March 2027 Possession - Commissioning - Pre-start Briefing Shift 5 | 2027-03-15 | 2027-03-15
I2S-7688-MP-74.TC.s.1.1 | Pre Shift - Prep | I.CN.11.14570 | T&C - March 2027 Possession - Commissioning - Travel to site Shift 5 | 2027-03-15 | 2027-03-15
I2S-7688-MP-74.TC.s.1.1 | Pre Shift - Prep | I.CN.11.14600 | T&C - March 2027 Possession - Commissioning - Track Panel to be installed for 52A Points | 2027-03-13 | 2027-03-13
Stockinbingal |  |  |  | 2027-03-13 | 2027-03-15
I2S-7688-MP-74.TC.s.1.4 | Stockinbingal | I.CN.11.14760 | T&C - March 2027 Possession - Commissioning - Change over wiring in all Existing Locs | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.TC.s.1.4 | Stockinbingal | I.CN.11.14770 | T&C - March 2027 Possession - Commissioning - Installation of points machine 52A | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.TC.s.1.4 | Stockinbingal | I.CN.11.14780 | T&C - March 2027 Possession - Commissioning - Wiring points 52A | 2027-03-13 | 2027-03-14
I2S-7688-MP-74.TC.s.1.4 | Stockinbingal | I.CN.11.14790 | T&C - March 2027 Possession - Commissioning - Test and certify Points 51A | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.TC.s.1.4 | Stockinbingal | I.CN.11.14800 | T&C - March 2027 Possession - Commissioning - Test and certify Points 52A | 2027-03-14 | 2027-03-14
I2S-7688-MP-74.TC.s.1.4 | Stockinbingal | I.CN.11.14810 | T&C - March 2027 Possession - Commissioning - Test and certify Points 51B | 2027-03-14 | 2027-03-14
I2S-7688-MP-74.TC.s.1.4 | Stockinbingal | I.CN.11.14820 | T&C - March 2027 Pos- Unbag and Certify Signals (SL5, SL10, SL7, SL8, SL6, SL6 DIST, SL11, SL29) Tested prior to commis | 2027-03-13 | 2027-03-14
I2S-7688-MP-74.TC.s.1.4 | Stockinbingal | I.CN.11.14830 | T&C - March 2027 Possession - Commissioning - Certify Signalling Plan and TIP | 2027-03-14 | 2027-03-15
I2S-7688-MP-74.TC.s.1.4 | Stockinbingal | I.CN.11.14840 | T&C - March 2027 Possession - Commissioning - DIT Testing Tracks and Points Correspondance - Stockinbingal | 2027-03-14 | 2027-03-14
I2S-7688-MP-74.TC.s.1.4 | Stockinbingal | I.CN.11.14850 | T&C - March 2027 Possession - Commissioning - DIT Testing Up and Down Mains - Stockinbingal | 2027-03-14 | 2027-03-14
I2S-7688-MP-74.TC.s.1.4 | Stockinbingal | I.CN.11.14860 | T&C - March 2027 Possession - Commissioning - DIT Testing CRN - Stockinbingal | 2027-03-14 | 2027-03-14
I2S-7688-MP-74.TC.s.1.4 | Stockinbingal | I.CN.11.14870 | T&C - March 2027 Possession - Commissioning - Aspect Sequence Test | 2027-03-14 | 2027-03-15
Dirnaseer Loop |  |  |  | 2027-03-13 | 2027-03-15
I2S-7688-MP-74.TC.s.1.3 | Dirnaseer Loop | I.CN.11.14740 | T&C - March 2027 Possession - Commissioning - DIT Testing IR Line | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.TC.s.1.3 | Dirnaseer Loop | I.CN.11.14750 | T&C - March 2027 Possession - Commissioning - Contractors Contingency (10% /6 hours) | 2027-03-13 | 2027-03-15
I2S-7688-MP-74.TC.s.1.3 | Dirnaseer Loop | I.CN.11.14730 | T&C - March 2027 Possession - Commissioning - DIT Testing Tracks and Points Correspondance - Dirnaseer Loop | 2027-03-13 | 2027-03-13
Illabo Site |  |  |  | 2027-03-13 | 2027-03-15
I2S-7688-MP-74.TC.s.1.2 | Illabo Site | I.CN.11.14610 | T&C - Sep 2026 Possession - Commissioning - Change over wiring in all Existing Locs | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.TC.s.1.2 | Illabo Site | I.CN.11.14620 | T&C - Sep 2026 Possession - Commissioning - Change over wiring in points machines 51B | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.TC.s.1.2 | Illabo Site | I.CN.11.14630 | T&C - Sep 2026 Possession - Commissioning - Change over wiring in points machines 52A | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.TC.s.1.2 | Illabo Site | I.CN.11.14640 | T&C - Sep 2026 Possession - Commissioning - Test and certify Points 51A | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.TC.s.1.2 | Illabo Site | I.CN.11.14650 | T&C - Sep 2026 Possession - Commissioning - Test and certify Points 51B | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.TC.s.1.2 | Illabo Site | I.CN.11.14660 | T&C - Sep 2026 Possession - Commissioning - Test and certify Points 52A | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.TC.s.1.2 | Illabo Site | I.CN.11.14670 | T&C - Sep 2026 Possession - Unbag and Certify Signals (IJ14, IJ1 and IJ16) (already tested in prior possession) | 2027-03-13 | 2027-03-14
I2S-7688-MP-74.TC.s.1.2 | Illabo Site | I.CN.11.14680 | T&C - Sep 2026 Possession - Commissioning - Night Shift Contingency | 2027-03-14 | 2027-03-14
I2S-7688-MP-74.TC.s.1.2 | Illabo Site | I.CN.11.14690 | T&C - Sep 2026 Possession - Commissioning - Certify Signalling Plan and TIP | 2027-03-14 | 2027-03-15
I2S-7688-MP-74.TC.s.1.2 | Illabo Site | I.CN.11.14700 | T&C - Sep 2026 Possession - Commissioning - DIT Testing Tracks and Points Correspondance - Illabo | 2027-03-14 | 2027-03-15
I2S-7688-MP-74.TC.s.1.2 | Illabo Site | I.CN.11.14710 | T&C - Sep 2026 Possession - Commissioning - DIT Testing Up and Down Mains - Illabo | 2027-03-15 | 2027-03-15
I2S-7688-MP-74.TC.s.1.2 | Illabo Site | I.CN.11.14720 | T&C - Sep 2026 Possession - Commissioning - Aspect Sequence Test | 2027-03-15 | 2027-03-15
Completion Activities
Construction - Site works - defects closure - Post Final Possession (POST POSS)
Construction - Site works - defects - Section 6 - Stockinbingal Junction (37301- 42600)
I2S-7688-MP-74.3.8.8 | Construction - Site works - defects - Section 6 - Stockinbingal Junction (37301- 42600) | I.CN.85.14090 | POST POSS - Sec.6 - defect / rectification works
Construction - Site works - defects - Section 5 - GF section (28301 - 37300)
I2S-7688-MP-74.3.8.1 | Construction - Site works - defects - Section 5 - GF section (28301 - 37300) | I.CN.85.14100 | POST POSS - Sec.5 - defect / rectification works
Construction - Site works - defects - Section 4 - GF section (18501 - 28300)
I2S-7688-MP-74.3.8.2 | Construction - Site works - defects - Section 4 - GF section (18501 - 28300) | I.CN.85.14110 | POST POSS - Sec.4 - defect / rectification works
Construction - Site works - defects - Section 3 - GF section (08841 - 18500)
I2S-7688-MP-74.3.8.3 | Construction - Site works - defects - Section 3 - GF section (08841 - 18500) | I.CN.85.14120 | POST POSS - Sec.3 - defect / rectification works
Construction - Site works - defects - Section 2 - GF section (02901 - 08840)
I2S-7688-MP-74.3.8.4 | Construction - Site works - defects - Section 2 - GF section (02901 - 08840) | I.CN.85.14130 | POST POSS - Sec.2 - defect / rectification works
Construction - Site works - defects - Section 1 - Illabo Junction - (00000 - 02900)
I2S-7688-MP-74.3.8.5 | Construction - Site works - defects - Section 1 - Illabo Junction - (00000 - 02900) | I.CN.85.14140 | POST POSS - Sec.1 - defect / rectification works
Construction - Site works - defects - Site Wide
I2S-7688-MP-74.3.8.6 | Construction - Site works - defects - Site Wide | I.CN.85.14150 | POST POSS - Site Wide - defect / rectification works
I2S-7688-MP-74.3.8.6 | Construction - Site works - defects - Site Wide | I.CN.85.14160 | POST POSS - Site Wide - Demob - Satellite offices
Completion - Completion and Handover Management Plan - CaHMP - Deliverables
CaHMP - Notices to be issued - 120+90+60+20+5 B.days < PC-29-Nov-27
I2S-7688-MP-74.3.7.1 | CaHMP - Notices to be issued - 120+90+60+20+5 B.days < PC-29-Nov-27 | I.PC.1120 | CaHMP - Contract Practical Completion - Written Notice to IRPL - 90 B.days < PC - RWO's return date
I2S-7688-MP-74.3.7.1 | CaHMP - Notices to be issued - 120+90+60+20+5 B.days < PC-29-Nov-27 | I.PC.1110 | CaHMP - Contract Practical Completion - Written Notice to IRPL - 120 B.days - PC-29-Nov-27
I2S-7688-MP-74.3.7.1 | CaHMP - Notices to be issued - 120+90+60+20+5 B.days < PC-29-Nov-27 | I.PC.1130 | CaHMP - Contract Practical Completion - Written Notice to IRPL - 20 B.days - PC-29-Nov-27
I2S-7688-MP-74.3.7.1 | CaHMP - Notices to be issued - 120+90+60+20+5 B.days < PC-29-Nov-27 | I.PC.1140 | CaHMP - Contract Practical Completion - Written Notice to IRPL - 5 B.days - PC-29-Nov-27
I2S-7688-MP-74.3.7.1 | CaHMP - Notices to be issued - 120+90+60+20+5 B.days < PC-29-Nov-27 | I.PC.1190 | CaHMP - Contract Practical Completion - Written Notice to IRPL - 60 B.days - PC-29-Nov-27
CaHMP - Construction Verification - Installation Works Packages - IWP - Fig 6+Table 10
I2S-7688-MP-74.3.7.2 | CaHMP - Construction Verification - Installation Works Packages - IWP - Fig 6+Table 10 | I.PC.1180 | CaHMP - IWP - Civil and Structures - JH Prepare and Submit to IRPL - COR-FM-062
I2S-7688-MP-74.3.7.2 | CaHMP - Construction Verification - Installation Works Packages - IWP - Fig 6+Table 10 | I.PC.1200 | CaHMP - IWP - Track - JH Prepare and Submit to IRPL - COR-FM-063
I2S-7688-MP-74.3.7.2 | CaHMP - Construction Verification - Installation Works Packages - IWP - Fig 6+Table 10 | I.PC.1210 | CaHMP - IWP - Signalling & Electrical - JH Prepare and Submit to IRPL - ESC2104F-03
I2S-7688-MP-74.3.7.2 | CaHMP - Construction Verification - Installation Works Packages - IWP - Fig 6+Table 10 | I.PC.1220 | CaHMP - IWP - Utilities - JH Prepare and Submit to IRPL
CaHMP - Commissioning Works Packages - CWP - Fig 6+Table 10
I2S-7688-MP-74.3.7.3 | CaHMP - Commissioning Works Packages - CWP - Fig 6+Table 10 | I.PC.1230 | CaHMP - CWP - Civil and Structures - JH Prepare and Submit to IRPL - COR-FM-064
I2S-7688-MP-74.3.7.3 | CaHMP - Commissioning Works Packages - CWP - Fig 6+Table 10 | I.PC.1240 | CaHMP - CWP - Track - JH Prepare and Submit to IRPL - COR-FM-065
I2S-7688-MP-74.3.7.3 | CaHMP - Commissioning Works Packages - CWP - Fig 6+Table 10 | I.PC.1250 | CaHMP - CWP - Signalling & Electrical - JH Prepare and Submit to IRPL - ESC2104F-04
I2S-7688-MP-74.3.7.3 | CaHMP - Commissioning Works Packages - CWP - Fig 6+Table 10 | I.PC.1260 | CaHMP - CWP - Utilities - JH Prepare and Submit to IRPL
CaHMP - Completion - Handover Documentation - Works Packages - HOWP - Fig 6+Table 10
I2S-7688-MP-74.3.7.4 | CaHMP - Completion - Handover Documentation - Works Packages - HOWP - Fig 6+Table 10 | I.PC.1270 | CaHMP - HOWP - Civil and Structures - JH Prepare and Submit to IRPL - COR-FM-066
I2S-7688-MP-74.3.7.4 | CaHMP - Completion - Handover Documentation - Works Packages - HOWP - Fig 6+Table 10 | I.PC.1280 | CaHMP - HOWP - Track - JH Prepare and Submit to IRPL - COR-FM-067
I2S-7688-MP-74.3.7.4 | CaHMP - Completion - Handover Documentation - Works Packages - HOWP - Fig 6+Table 10 | I.PC.1290 | CaHMP - HOWP - Signalling & Electrical - JH Prepare and Submit to IRPL - ESC2104F-05
I2S-7688-MP-74.3.7.4 | CaHMP - Completion - Handover Documentation - Works Packages - HOWP - Fig 6+Table 10 | I.PC.1300 | CaHMP - HOWP - Utilities - JH Prepare and Submit to IRPL
I2S-7688-MP-74.3.7.4 | CaHMP - Completion - Handover Documentation - Works Packages - HOWP - Fig 6+Table 10 | I.PC.1320 | CaHMP - HOWP - Environment, Community, Sustainability and Heritage - JH Prepare and Submit to IRPL
CaHMP - Returned Works Owners - RWO - Table 10 - 90 B.days < PC-29-Nov-27
CaHMP - RWO - IWP+CWP+HOWP+RWO's - IRPL+IV reviews and acceptance - 7.4
I2S-7688-MP-74.3.7.5.1 | CaHMP - RWO - IWP+CWP+HOWP+RWO's - IRPL+IV reviews and acceptance - 7.4 | I.PC.1310 | CaHMP - RWO - Written Notice to IRPL + RWO acceptance - 40 B.days after Sep-27 (Final Possession)
I2S-7688-MP-74.3.7.5.1 | CaHMP - RWO - IWP+CWP+HOWP+RWO's - IRPL+IV reviews and acceptance - 7.4 | I.PC.1330 | CaHMP - RWO - all work packages - JH issue IRPL - Schedule 13 notice - Ret.Works Acceptance Requirements
I2S-7688-MP-74.3.7.5.1 | CaHMP - RWO - IWP+CWP+HOWP+RWO's - IRPL+IV reviews and acceptance - 7.4 | I.PC.1340 | CaHMP - RWO - Ret.Works Acceptance Requirements - RWO'a+JH+IRPL+ARTC +IV+TfNSW+CRN - inspection
I2S-7688-MP-74.3.7.5.1 | CaHMP - RWO - IWP+CWP+HOWP+RWO's - IRPL+IV reviews and acceptance - 7.4 | I.PC.1350 | CaHMP - RWO - post inspection - IRPL+IV - Ret.Works Acceptance - "HANDOVER PACKAGE COMPLETION"
I2S-7688-MP-74.3.7.5.1 | CaHMP - RWO - IWP+CWP+HOWP+RWO's - IRPL+IV reviews and acceptance - 7.4 | I.PC.1360 | CaHMP - RWO - post inspection - IRPL+IV - Ret.Works Acceptance - MIlestone - "HANDOVER PACKAGE COMPLETION"
CaHMP - RWO - ARTC - IRPL-Certify - Table 10
I2S-7688-MP-74.3.7.5.6 | CaHMP - RWO - ARTC - IRPL-Certify - Table 10 | I.PC.1370 | CaHMP - RWO's + Certification - ARTC work packages - ARTC+IV
CaHMP - RWO - Coota-GR Council - Independent Verifier - IV-Certify - Table 10
I2S-7688-MP-74.3.7.5.7 | CaHMP - RWO - Coota-GR Council - Independent Verifier - IV-Certify - Table 10 | I.PC.1380 | CaHMP - RWO's + Certification - Coota-GR Council work packges - IV
CaHMP - RWO - Junee Shire Council - Indpendent Verifier - IV-Certify - Table 10
I2S-7688-MP-74.3.7.5.8 | CaHMP - RWO - Junee Shire Council - Indpendent Verifier - IV-Certify - Table 10 | I.PC.1390 | CaHMP - RWO's + Certification - Junee Shire Council work packges - IV
CaHMP - RWO - Transport for New South Wales (TfNSW) - IRPL-Certify - Table 10
I2S-7688-MP-74.3.7.5.9 | CaHMP - RWO - Transport for New South Wales (TfNSW) - IRPL-Certify - Table 10 | I.PC.1400 | CaHMP - RWO's + Certification - TfNSW work packges - IRPL
CaHMP - RWO - Transport Asset Holding Entity (CRN Assets) - IRPL-Certify - Table 10
I2S-7688-MP-74.3.7.5.10 | CaHMP - RWO - Transport Asset Holding Entity (CRN Assets) - IRPL-Certify - Table 10 | I.PC.1410 | CaHMP - RWO's + Certification - CRN work packges - IRPL
CaHMP - RWO - Other Third Parties - private landowners - IRPL-Certify - Table 10
I2S-7688-MP-74.3.7.5.11 | CaHMP - RWO - Other Third Parties - private landowners - IRPL-Certify - Table 10 | I.PC.1420 | CaHMP - RWO's + Certification - private land owners work packges - IRPL
CaHMP - RWO - Other Third Parties - Utilities - IV-Certify - Table 10
I2S-7688-MP-74.3.7.5.12 | CaHMP - RWO - Other Third Parties - Utilities - IV-Certify - Table 10 | I.PC.1430 | CaHMP - RWO's + Certification - Utilities work packges - IV
Completion - Completion & Handover Deliverables - C+HO - CaHMP - Deliverables
Completion - Completion & Handover Deliverables - C+HO - CaHMP - Deliverables - Table 12
CaHMP - C+HO - Work Packages - IWP+CWP+HOWP - Quality
I2S-7688-MP-74.3.7.9.6.1 | CaHMP - C+HO - Work Packages - IWP+CWP+HOWP - Quality | I.PC.1440 | COMPL - C+HO - Deliverable - all work apckages - Quality and Completions Manager
CaHMP - C+HO - As-Built Documentation - Engineering
I2S-7688-MP-74.3.7.9.6.2 | CaHMP - C+HO - As-Built Documentation - Engineering | I.PC.1450 | COMPL - C+HO - Deliverable - As-Built Docs - Design+Eng - List Compilation - Finalise - Engineering Manager
I2S-7688-MP-74.3.7.9.6.2 | CaHMP - C+HO - As-Built Documentation - Engineering | I.PC.1550 | COMPL - C+HO - Deliverable - As-Built Docs - Design+Eng - List Compilation - Start
I2S-7688-MP-74.3.7.9.6.2 | CaHMP - C+HO - As-Built Documentation - Engineering | I.PC.1560 | COMPL - C+HO - Deliverable - As-Built Docs - Design+Eng - List Compilation - Finish
CaHMP - C+HO - Survey
I2S-7688-MP-74.3.7.9.6.3 | CaHMP - C+HO - Survey | I.PC.1460 | COMPL - C+HO - Deliverable - Survey Deliverables - List Compilation - Start
I2S-7688-MP-74.3.7.9.6.3 | CaHMP - C+HO - Survey | I.PC.1530 | COMPL - C+HO - Deliverable - JH submit - Survey Certificate - to IRPL
I2S-7688-MP-74.3.7.9.6.3 | CaHMP - C+HO - Survey | I.PC.1520 | COMPL - C+HO - Deliverable - Survey Deliverables - Survey Manager
I2S-7688-MP-74.3.7.9.6.3 | CaHMP - C+HO - Survey | I.PC.1540 | COMPL - C+HO - Deliverable - Survey Deliverables - List Compilation - Finish
CaHMP - C+HO - Digital Engineering Information
I2S-7688-MP-74.3.7.9.6.4 | CaHMP - C+HO - Digital Engineering Information | I.PC.1470 | COMPL - C+HO - Deliverable - Digital Engineering Information - Survey Manager
I2S-7688-MP-74.3.7.9.6.4 | CaHMP - C+HO - Digital Engineering Information | I.PC.1570 | COMPL - C+HO - Deliverable - Digital Engineering Information - List Compilation - Start
I2S-7688-MP-74.3.7.9.6.4 | CaHMP - C+HO - Digital Engineering Information | I.PC.1580 | COMPL - C+HO - Deliverable - Digital Engineering Information - List Compilation - Finish
CaHMP - C+HO - Warranties - Commercial
I2S-7688-MP-74.3.7.9.6.5 | CaHMP - C+HO - Warranties - Commercial | I.PC.1480 | COMPL - C+HO - Deliverable - Warranties - Commercial Manager
CaHMP - C+HO - Release Forms - Commercial
I2S-7688-MP-74.3.7.9.6.6 | CaHMP - C+HO - Release Forms - Commercial | I.PC.1490 | COMPL - C+HO - Deliverable - Release Forms - Commercial Manager
CaHMP - C+HO - Utilities
I2S-7688-MP-74.3.7.9.6.8 | CaHMP - C+HO - Utilities | I.PC.1500 | COMPL - C+HO - Deliverable - Utilities Assets - Third Party Authorities - Utilities Manager
CaHMP - C+HO - All Other Deliverables - AO - CaHMP-Table 14
I2S-7688-MP-74.3.7.9.7 | CaHMP - C+HO - All Other Deliverables - AO - CaHMP-Table 14 | I.PC.1000 | COMPL - C+HO - AO - condition assessment and/or dilapidation survey reports
I2S-7688-MP-74.3.7.9.7 | CaHMP - C+HO - All Other Deliverables - AO - CaHMP-Table 14 | I.PC.1010 | COMPL - C+HO - AO - a draft Communication and Stakeholder Engagement Report
I2S-7688-MP-74.3.7.9.7 | CaHMP - C+HO - All Other Deliverables - AO - CaHMP-Table 14 | I.PC.1020 | COMPL - C+HO - AO - completed Hazard Log Analysis Report
I2S-7688-MP-74.3.7.9.7 | CaHMP - C+HO - All Other Deliverables - AO - CaHMP-Table 14 | I.PC.1030 | COMPL - C+HO - AO - Commissioning Safety Assurance Report
I2S-7688-MP-74.3.7.9.7 | CaHMP - C+HO - All Other Deliverables - AO - CaHMP-Table 14 | I.PC.1040 | COMPL - C+HO - AO - final Safety Assurance Report for the entire system
I2S-7688-MP-74.3.7.9.7 | CaHMP - C+HO - All Other Deliverables - AO - CaHMP-Table 14 | I.PC.1050 | COMPL - C+HO - AO - ALCAM assessment - all public level crossings
I2S-7688-MP-74.3.7.9.7 | CaHMP - C+HO - All Other Deliverables - AO - CaHMP-Table 14 | I.PC.1060 | COMPL - C+HO - AO - ALCAM assessment - all private level crossings - ARTC standard ATD-16-02
I2S-7688-MP-74.3.7.9.7 | CaHMP - C+HO - All Other Deliverables - AO - CaHMP-Table 14 | I.PC.1070 | COMPL - C+HO - AO - pre-commissioning Road Safety Audit of any Level Crossings
I2S-7688-MP-74.3.7.9.7 | CaHMP - C+HO - All Other Deliverables - AO - CaHMP-Table 14 | I.PC.1080 | COMPL - C+HO - AO - Photographic records provided for each asset
I2S-7688-MP-74.3.7.9.7 | CaHMP - C+HO - All Other Deliverables - AO - CaHMP-Table 14 | I.PC.1090 | COMPL - C+HO - AO - Outstanding Works Register
I2S-7688-MP-74.3.7.9.7 | CaHMP - C+HO - All Other Deliverables - AO - CaHMP-Table 14 | I.PC.1100 | COMPL - C+HO - AO - ARTC Certificate of Practical Completion - Form of EGP2001T-13 - JH Prepare
I2S-7688-MP-74.3.7.9.7 | CaHMP - C+HO - All Other Deliverables - AO - CaHMP-Table 14 | I.PC.1150 | COMPL - C+HO - AO - ARTC Certificate of Practical Completion - Form of EGP2001T-13 - IRPL review - 10 B.days
I2S-7688-MP-74.3.7.9.7 | CaHMP - C+HO - All Other Deliverables - AO - CaHMP-Table 14 | I.PC.1160 | COMPL - C+HO - AO - ARTC Certificate of Practical Completion - Form of EGP2001T-13 - comments addressed
I2S-7688-MP-74.3.7.9.7 | CaHMP - C+HO - All Other Deliverables - AO - CaHMP-Table 14 | I.PC.1170 | COMPL - C+HO - AO - ARTC Certificate of Practical Completion - Form of EGP2001T-13 - signed by ARTC
Completion - Deliverables - Operational Readiness - Sub-NANs - Possessions
Completion - Deliverables - Operational Readiness - CCB Gate 5 - Sub-NANs - Sep-2026
Sep-2026 - CCB Gate 5 - Sub-NAN 3756-3 - Rail Systems Works - Go/No Go - prior to T-2
I2S-7688-MP-74.3.1.7.1 | Sep-2026 - CCB Gate 5 - Sub-NAN 3756-3 - Rail Systems Works - Go/No Go - prior to T-2 | I.PC.1590 | Compl - Sep-2026 - Ops Readiness - CCB Gate 5 - Rail Sys works - Compile documentation
I2S-7688-MP-74.3.1.7.1 | Sep-2026 - CCB Gate 5 - Sub-NAN 3756-3 - Rail Systems Works - Go/No Go - prior to T-2 | I.PC.1600 | Compl - Sep-2026 - Ops Readiness - CCB Gate 5 - Rail Sys works - JH Review and amend
I2S-7688-MP-74.3.1.7.1 | Sep-2026 - CCB Gate 5 - Sub-NAN 3756-3 - Rail Systems Works - Go/No Go - prior to T-2 | I.PC.1610 | Compl - Sep-2026 - Ops Readiness - CCB Gate 5 - Rail Sys works - Finalise and submit to IRPL
Sep-2026 - CCB Gate 5 - Sub-NAN 3756-3 - Ops Readiness - work packages - Go/No Go - prior to T-2
I2S-7688-MP-74.3.1.7.5 | Sep-2026 - CCB Gate 5 - Sub-NAN 3756-3 - Ops Readiness - work packages - Go/No Go - prior to T-2 | I.PC.1620 | Compl - Sep-2026 - Ops Readiness - CCB Gate 5 - Works packages (IWP+CWP) - Compile documentation
I2S-7688-MP-74.3.1.7.5 | Sep-2026 - CCB Gate 5 - Sub-NAN 3756-3 - Ops Readiness - work packages - Go/No Go - prior to T-2 | I.PC.1630 | Compl - Sep-2026 - Ops Readiness - CCB Gate 5 - Works packages (IWP+CWP) - JH Review and amend
I2S-7688-MP-74.3.1.7.5 | Sep-2026 - CCB Gate 5 - Sub-NAN 3756-3 - Ops Readiness - work packages - Go/No Go - prior to T-2 | I.PC.1640 | Compl - Sep-2026 - Ops Readiness - CCB Gate 5 - Works packages (IWP+CWP) - Finalise and submit to IRPL
Sep-2026 - CCB Gate 5 - Sub-NAN 3756-3 - Ops Readiness - Tracker closeout - 6W post possession
I2S-7688-MP-74.3.1.7.6 | Sep-2026 - CCB Gate 5 - Sub-NAN 3756-3 - Ops Readiness - Tracker closeout - 6W post possession | I.PC.1650 | Compl - Sep-2026 - Ops Readiness - CCB Gate 5 - Tracker close-out - Compile documentation
I2S-7688-MP-74.3.1.7.6 | Sep-2026 - CCB Gate 5 - Sub-NAN 3756-3 - Ops Readiness - Tracker closeout - 6W post possession | I.PC.1660 | Compl - Sep-2026 - Ops Readiness - CCB Gate 5 - Tracker close-out - JH Review and amend
I2S-7688-MP-74.3.1.7.6 | Sep-2026 - CCB Gate 5 - Sub-NAN 3756-3 - Ops Readiness - Tracker closeout - 6W post possession | I.PC.1670 | Compl - Sep-2026 - Ops Readiness - CCB Gate 5 - Tracker close-out - Finalise and submit to IRPL
Completion - Deliverables - Operational Readiness - CCB Gate 6 - Sub-NANs - Sep-2027
Sep-2027 - CCB Gate 6 - Sub-NAN 3756-5 - Rail Systems Works - Go/No Go - prior to T-2
I2S-7688-MP-74.3.1.2.1 | Sep-2027 - CCB Gate 6 - Sub-NAN 3756-5 - Rail Systems Works - Go/No Go - prior to T-2 | I.PC.1680 | Compl - Sep-2027 - Ops Readiness - CCB Gate 6 - Rail Sys works - Compile documentation
I2S-7688-MP-74.3.1.2.1 | Sep-2027 - CCB Gate 6 - Sub-NAN 3756-5 - Rail Systems Works - Go/No Go - prior to T-2 | I.PC.1690 | Compl - Sep-2027 - Ops Readiness - CCB Gate 6 - Rail Sys works - JH Review and amend
I2S-7688-MP-74.3.1.2.1 | Sep-2027 - CCB Gate 6 - Sub-NAN 3756-5 - Rail Systems Works - Go/No Go - prior to T-2 | I.PC.1700 | Compl - Sep-2027 - Ops Readiness - CCB Gate 6 - Rail Sys works - Finalise and submit to IRPL
Sep-2027 - CCB Gate 6 - Sub-NAN 3756-5 - Ops Readiness - work packages - Go/No Go - prior to T-2
I2S-7688-MP-74.3.1.2.5 | Sep-2027 - CCB Gate 6 - Sub-NAN 3756-5 - Ops Readiness - work packages - Go/No Go - prior to T-2 | I.PC.1710 | Compl - Sep-2027 - Ops Readiness - CCB Gate 6 - Works packages (IWP+CWP) - Compile documentation
I2S-7688-MP-74.3.1.2.5 | Sep-2027 - CCB Gate 6 - Sub-NAN 3756-5 - Ops Readiness - work packages - Go/No Go - prior to T-2 | I.PC.1720 | Compl - Sep-2027 - Ops Readiness - CCB Gate 6 - Works packages (IWP+CWP) - JH Review and amend
I2S-7688-MP-74.3.1.2.5 | Sep-2027 - CCB Gate 6 - Sub-NAN 3756-5 - Ops Readiness - work packages - Go/No Go - prior to T-2 | I.PC.1730 | Compl - Sep-2027 - Ops Readiness - CCB Gate 6 - Works packages (IWP+CWP) - Finalise and submit to IRPL
Sep-2027 - CCB Gate 6 - Sub-NAN 3756-5 - Ops Readiness - Tracker closeout - 6W post possession
I2S-7688-MP-74.3.1.2.6 | Sep-2027 - CCB Gate 6 - Sub-NAN 3756-5 - Ops Readiness - Tracker closeout - 6W post possession | I.PC.1740 | Compl - Sep-2027 - Ops Readiness - CCB Gate 6 - Tracker close-out - Compile documentation
I2S-7688-MP-74.3.1.2.6 | Sep-2027 - CCB Gate 6 - Sub-NAN 3756-5 - Ops Readiness - Tracker closeout - 6W post possession | I.PC.1750 | Compl - Sep-2027 - Ops Readiness - CCB Gate 6 - Tracker close-out - JH Review and amend
I2S-7688-MP-74.3.1.2.6 | Sep-2027 - CCB Gate 6 - Sub-NAN 3756-5 - Ops Readiness - Tracker closeout - 6W post possession | I.PC.1760 | Compl - Sep-2027 - Ops Readiness - CCB Gate 6 - Tracker close-out - Finalise and submit to IRPL
Sep-2027 - CCB Gate 6 - Sub-NAN 3756-5 - Hold Points
I2S-7688-MP-74.3.1.2.3 | Sep-2027 - CCB Gate 6 - Sub-NAN 3756-5 - Hold Points | I.PC.1770 | Compl - HOWP - Sep-2027 - Ops Readiness - Post POSS - Defect List
I2S-7688-MP-74.3.1.2.3 | Sep-2027 - CCB Gate 6 - Sub-NAN 3756-5 - Hold Points | I.PC.1780 | Compl - Sep-2027 - CCB Gate 6 - Handover Works Package Completion (HOWP) - Hold Point - ARTC + JH
I2S-7688-MP-74.3.1.2.3 | Sep-2027 - CCB Gate 6 - Sub-NAN 3756-5 - Hold Points | I.PC.1790 | Compl - Sep-2027 - CCB Gate 6 - Sub NAN - CCL Checklist #4 Close out - DMP - Pg 127 - ARTC SIG CCB Flow Chart
I2S-7688-MP-74.3.1.2.3 | Sep-2027 - CCB Gate 6 - Sub-NAN 3756-5 - Hold Points | I.PC.1800 | Compl - HOWP - Sep-2027 - Ops Readiness - Post POSS - Defect List closure - Hold Point - IRPL + ARTC + JH
Post Completion Activities |  |  |  | 2025-10-23 | 2026-12-08
I2S-7688-MP-74.2 | Post Completion Activities | CoA-1490 | POST COMP - CoA - E21 - Finalise Operation Noise Compliance Report (ONCR) - after 10 years of ops | 2026-11-18 | 2026-12-08
ISC As built Round 2 Submission
I2S-7688-MP-74.2.4 | ISC As built Round 2 Submission | I.GG.MR.ISC.1510 | POST COMP - ISC Rating - As Built Certification
I2S-7688-MP-74.2.4 | ISC As built Round 2 Submission | I.GG.MR.ISC.1420 | POST COMP - ISC As-built Round Submission 2 - JH Prepare ISC Design Submission R2
I2S-7688-MP-74.2.4 | ISC As built Round 2 Submission | I.GG.MR.ISC.1430 | POST COMP - ISC As-built Round Submission 2 - IRPL Review DR2 and JH Updates as required
I2S-7688-MP-74.2.4 | ISC As built Round 2 Submission | I.GG.MR.ISC.1440 | POST COMP - ISC As-built Round Submission 2 - IRPL Submit DR2 to IS Council and IS Council Verify
I2S-7688-MP-74.2.4 | ISC As built Round 2 Submission | I.GG.MR.ISC.1450 | POST COMP - ISC As-built Round Submission 2 - JH Appeals / Meetings
I2S-7688-MP-74.2.4 | ISC As built Round 2 Submission | I.GG.MR.ISC.1460 | POST COMP - ISC As-built Round Submission 2 - DR2 is Verification / Certification by IS Council
D5, D6, D9, D10, D11 - Operational Monitoring Programs |  |  |  | 2025-10-23 | 2026-01-14
I2S-7688-MP-74.2.6 | D5, D6, D9, D10, D11 - Operational Monitoring Programs | CoA-2020 | POST COMP - CoA - D5, D6, D12 - Prepare Operational Monitoring Programs | 2025-10-23 | 2025-12-03
I2S-7688-MP-74.2.6 | D5, D6, D9, D10, D11 - Operational Monitoring Programs | CoA-2050 | POST COMP - CoA - D10,D11 - Planning Secretary Approves Prepare Operational Monitoring Programs | 2025-12-04 | 2026-01-14
Defect Liablity Period - DLP - CaHMP - 6.3 (Table 8) and 10.1 + 10.1.2 - Class A+B+C - Defects
Defect Liablity Period - DLP - CaHMP - 6.3 (Table 8) - Amended Work Package (AWP)
I2S-7688-MP-74.2.3.1 | Defect Liablity Period - DLP - CaHMP - 6.3 (Table 8) - Amended Work Package (AWP) | I.PC.1820 | DLP - CaHMP - AWP - Civil and Structures - JH Prepare and Submit to IRPL
I2S-7688-MP-74.2.3.1 | Defect Liablity Period - DLP - CaHMP - 6.3 (Table 8) - Amended Work Package (AWP) | I.PC.1830 | DLP - CaHMP - AWP - Track - JH Prepare and Submit to IRPL
I2S-7688-MP-74.2.3.1 | Defect Liablity Period - DLP - CaHMP - 6.3 (Table 8) - Amended Work Package (AWP) | I.PC.1840 | DLP - CaHMP - AWP - Signalling & Electrical - JH Prepare and Submit to IRPL
I2S-7688-MP-74.2.3.1 | Defect Liablity Period - DLP - CaHMP - 6.3 (Table 8) - Amended Work Package (AWP) | I.PC.1850 | DLP - CaHMP - AWP - Utilities - JH Prepare and Submit to IRPL
I2S-7688-MP-74.2.3.1 | Defect Liablity Period - DLP - CaHMP - 6.3 (Table 8) - Amended Work Package (AWP) | I.PC.1860 | DLP - CaHMP - AWP - Environment, Community, Sustainability and Heritage - JH Prepare and Submit to IRPL
Defect Liablity Period - DLP - CaHMP - 10.1 + 10.1.2 - ARTC - Operational Defects
I2S-7688-MP-74.2.3.2 | Defect Liablity Period - DLP - CaHMP - 10.1 + 10.1.2 - ARTC - Operational Defects | I.PC.1870 | DLP - CaHMP - AWP - ARTC - Operational Defects - ARTC Defect Report form AMT-FM-004 - Produce Report
I2S-7688-MP-74.2.3.2 | Defect Liablity Period - DLP - CaHMP - 10.1 + 10.1.2 - ARTC - Operational Defects | I.PC.1880 | DLP - CaHMP - AWP - ARTC - Operational Defects - Defects - Rectified
I2S-7688-MP-74.2.3.2 | Defect Liablity Period - DLP - CaHMP - 10.1 + 10.1.2 - ARTC - Operational Defects | I.PC.1890 | DLP - CaHMP - AWP - ARTC - Operational Defects - Notify ARTC + IRPL
I2S-7688-MP-74.2.3.2 | Defect Liablity Period - DLP - CaHMP - 10.1 + 10.1.2 - ARTC - Operational Defects | I.PC.1900 | DLP - CaHMP - AWP - ARTC - Operational Defects - IRPL - Review
I2S-7688-MP-74.2.3.2 | Defect Liablity Period - DLP - CaHMP - 10.1 + 10.1.2 - ARTC - Operational Defects | I.PC.1910 | DLP - CaHMP - AWP - ARTC - Operational Defects - close out
Defect Liablity Period - DLP - CaHMP - 10.1 + 10.1.2 - CRN - Defects
I2S-7688-MP-74.2.3.4 | Defect Liablity Period - DLP - CaHMP - 10.1 + 10.1.2 - CRN - Defects | I.PC.1920 | DLP - CaHMP - AWP - CRN - Defects - Produce Report
I2S-7688-MP-74.2.3.4 | Defect Liablity Period - DLP - CaHMP - 10.1 + 10.1.2 - CRN - Defects | I.PC.1930 | DLP - CaHMP - AWP - CRN - Defects - Defects - Rectified
I2S-7688-MP-74.2.3.4 | Defect Liablity Period - DLP - CaHMP - 10.1 + 10.1.2 - CRN - Defects | I.PC.1940 | DLP - CaHMP - AWP - CRN - Defects - Notify CRN + IRPL
I2S-7688-MP-74.2.3.4 | Defect Liablity Period - DLP - CaHMP - 10.1 + 10.1.2 - CRN - Defects | I.PC.1950 | DLP - CaHMP - AWP - CRN - Defects - CRN - Review
I2S-7688-MP-74.2.3.4 | Defect Liablity Period - DLP - CaHMP - 10.1 + 10.1.2 - CRN - Defects | I.PC.1960 | DLP - CaHMP - AWP - CRN - Defects - close out
I2S-7688-MP-74.2.3.4 | Defect Liablity Period - DLP - CaHMP - 10.1 + 10.1.2 - CRN - Defects | I.PC.1970 | DLP - CaHMP - AWP - CRN - Defects - IRPL - Review
Defect Liablity Period - DLP - Key Dates
I2S-7688-MP-74.2.3.3 | Defect Liablity Period - DLP - Key Dates | I.PC.0010 | Defect Liablity Period - Post PC - PC+24M
I2S-7688-MP-74.2.3.3 | Defect Liablity Period - DLP - Key Dates | I.PC.1510 | Defect Liablity Period - Post PC - JH Notify IRPL - 90d prior to 24M period completion
I2S-7688-MP-74.2.3.3 | Defect Liablity Period - DLP - Key Dates | I.PC.1810 | Defect Liablity Period - Return Works Defects Fix - Post PC - PC+36M
E84
I2S-7688-MP-74.2.5 | E84 | I.PC.20 | POST COMP - E84 - Undertake sampling once operations start
I2S-7688-MP-74.2.5 | E84 | I.PC.30 | POST COMP - E84 - Prepare report
I2S-7688-MP-74.2.5 | E84 | I.PC.40 | POST COMP - E84 - Submit to IRPL for review
I2S-7688-MP-74.2.5 | E84 | I.PC.50 | POST COMP - E84 - IRPL review period
I2S-7688-MP-74.2.5 | E84 | I.PC.60 | POST COMP - E84 - Respond to comments
I2S-7688-MP-74.2.5 | E84 | I.PC.70 | POST COMP - E84 - Submit report to DCCEEW
Time Chainage
PC
I2S-7688-MP-74.5.5 | PC | TC-710 | TC - Contract Practical Completion - 30 Apr 27
I2S-7688-MP-74.5.5 | PC | TC-1150 | TC - Contingency Prior to PC - LOE
I2S-7688-MP-74.5.5 | PC | TC-850 | TC - Program Delay - 6 Months - LOE
I2S-7688-MP-74.5.5 | PC | TC-890 | TC - Forecast Practical Completion
FDVR
I2S-7688-MP-74.5.8 | FDVR | TC-780 | TC - FDVR Approval - LOE
Possessions
I2S-7688-MP-74.5.7 | Possessions | TC-1130 | Sept 2027 - Possession Contingency - LOE
I2S-7688-MP-74.5.7 | Possessions | TC-1140 | Time Chainage - TC - Sept 2027 - Possession Readiness - LOE
I2S-7688-MP-74.5.7 | Possessions | TC-1100 | Mar 2027 - Possession Contingency - LOE
I2S-7688-MP-74.5.7 | Possessions | TC-1110 | Time Chainage - TC - Mar 2027 - Possession Readiness - LOE
I2S-7688-MP-74.5.7 | Possessions | TC-1040 | Time Chainage - TC - Sec.6 - Missed Possession
I2S-7688-MP-74.5.7 | Possessions | TC-1050 | Time Chainage - TC - Sec.3 - Trackwork
I2S-7688-MP-74.5.7 | Possessions | TC-810 | Time Chainage - TC - Sec.1 - Rail Del
I2S-7688-MP-74.5.7 | Possessions | TC-820 | Time Chainage - TC - Sec.1 - Install Trackwork
I2S-7688-MP-74.5.7 | Possessions | TC-830 | Time Chainage - TC - Sec.1 - Install Trackwork
I2S-7688-MP-74.5.7 | Possessions | TC-840 | Time Chainage - TC - Sec.1 - LX
I2S-7688-MP-74.5.7 | Possessions | TC-880 | Time Chainage - TC -Sec.6 - Trackwork - LOE - possession work
Bridges
I2S-7688-MP-74.5.1 | Bridges | TC-180 | TC - S6 - Dudauman Ck Br - LOE
I2S-7688-MP-74.5.1 | Bridges | TC-190 | TC - S6 - BGW - Phase 2 - LOE
I2S-7688-MP-74.5.1 | Bridges | TC-200 | TC - S6 - BGW - Phase 1 - LOE
I2S-7688-MP-74.5.1 | Bridges | TC-210 | TC - S5 - Powder Horn Ck Br - LOE
I2S-7688-MP-74.5.1 | Bridges | TC-220 | TC - S4 - Old Cootmundra Rail Br - LOE
I2S-7688-MP-74.5.1 | Bridges | TC-230 | TC - S4 - Isobel Ck Trib Br - LOE
I2S-7688-MP-74.5.1 | Bridges | TC-240 | TC - S4 - Isobel Ck Br - LOE
I2S-7688-MP-74.5.1 | Bridges | TC-250 | TC - S3 - Dirnaseer Rd Br - LOE
I2S-7688-MP-74.5.1 | Bridges | TC-260 | TC - S3 - Run Boundary Ck Br - LOE
I2S-7688-MP-74.5.1 | Bridges | TC-270 | TC - S2 - Ulandra Ck Br - LOE
I2S-7688-MP-74.5.1 | Bridges | TC-280 | TC - S1 - Billabong Ck Br - LOE
I2S-7688-MP-74.5.1 | Bridges | TC-1030 | TC - S6 - BGW - Remove Road Diversion & Finish Basin Works - LOE
Utilities
I2S-7688-MP-74.5.11 | Utilities | TC-590 | TC - S5 - Utilities - LOE
I2S-7688-MP-74.5.11 | Utilities | TC-600 | TC - S6 - Utilities - LOE
I2S-7688-MP-74.5.11 | Utilities | TC-610 | TC - S4 - Utilities - LOE
I2S-7688-MP-74.5.11 | Utilities | TC-620 | TC - S3 - Utilities - LOE
I2S-7688-MP-74.5.11 | Utilities | TC-630 | TC - S2 - Utilities - LOE
I2S-7688-MP-74.5.11 | Utilities | TC-640 | TC - S1 - Utilities - LOE
Trackwork
Phase 1
I2S-7688-MP-74.5.2.1 | Phase 1 | TC-290 | TC - S1 - Trackwork Phase 1 - LOE
I2S-7688-MP-74.5.2.1 | Phase 1 | TC-300 | TC - S2 - Trackwork Phase 1 - LOE
I2S-7688-MP-74.5.2.1 | Phase 1 | TC-310 | TC - S3 - Trackwork Phase 1 - LOE
I2S-7688-MP-74.5.2.1 | Phase 1 | TC-320 | TC - S4 - Trackwork Phase 1 - LOE
I2S-7688-MP-74.5.2.1 | Phase 1 | TC-330 | TC - S5 - Trackwork Phase 1 - LOE
I2S-7688-MP-74.5.2.1 | Phase 1 | TC-900 | TC - S6 - Trackwork Phase 1 - LOE
I2S-7688-MP-74.5.2.1 | Phase 1 | TC-910 | TC - S6 - Trackwork Phase 1 - LOE
Phase 2
I2S-7688-MP-74.5.2.3 | Phase 2 | TC-920 | TC - S1 - Trackwork Phase 2 - LOE
I2S-7688-MP-74.5.2.3 | Phase 2 | TC-930 | TC - S2 - Trackwork Phase 2 - LOE
I2S-7688-MP-74.5.2.3 | Phase 2 | TC-950 | TC - S4 - Trackwork Phase 2 - LOE
I2S-7688-MP-74.5.2.3 | Phase 2 | TC-960 | TC - S5 - Trackwork Phase 2 - LOE
I2S-7688-MP-74.5.2.3 | Phase 2 | TC-980 | TC - S6 - Trackwork Phase 2 - LOE
I2S-7688-MP-74.5.2.3 | Phase 2 | TC-990 | TC - S6 - Trackwork Phase 2 - LOE
I2S-7688-MP-74.5.2.3 | Phase 2 | TC-1020 | TC - S3 - Trackwork Phase 2 - LOE
Phase 3
I2S-7688-MP-74.5.2.2 | Phase 3 | TC-1000 | TC - S6 - Trackwork Phase 3 - LOE
I2S-7688-MP-74.5.2.2 | Phase 3 | TC-340 | TC - S6 - Trackwork Phase 1 - LOE
I2S-7688-MP-74.5.2.2 | Phase 3 | TC-350 | TC - S1 - Trackwork Phase 3 - LOE
I2S-7688-MP-74.5.2.2 | Phase 3 | TC-360 | TC - S2 - Trackwork Phase 3 - LOE
I2S-7688-MP-74.5.2.2 | Phase 3 | TC-370 | TC - S3 - Trackwork Phase 3 - LOE
I2S-7688-MP-74.5.2.2 | Phase 3 | TC-380 | TC - S4 - Trackwork Phase 3 - LOE
I2S-7688-MP-74.5.2.2 | Phase 3 | TC-390 | TC - S5 - Trackwork Phase 23 - LOE
I2S-7688-MP-74.5.2.2 | Phase 3 | TC-400 | TC - S6 - Trackwork Phase 3 - LOE
I2S-7688-MP-74.5.2.2 | Phase 3 | TC-1120 | TC - S6 - Trackwork Phase 3 - LOE
Earthworks
Cut
I2S-7688-MP-74.5.4.1 | Cut | TC-410 | TC - S5 - Earthworks / CUT - LOE
I2S-7688-MP-74.5.4.1 | Cut | TC-420 | TC - S6 - Earthworks / CUT - LOE
I2S-7688-MP-74.5.4.1 | Cut | TC-430 | TC - S4 - Earthworks / CUT - LOE
I2S-7688-MP-74.5.4.1 | Cut | TC-440 | TC - S3 - Earthworks / CUT - LOE
I2S-7688-MP-74.5.4.1 | Cut | TC-450 | TC - S2 - Earthworks / CUT - LOE
I2S-7688-MP-74.5.4.1 | Cut | TC-460 | TC - S1 - Earthworks / CUT - LOE
Fill
I2S-7688-MP-74.5.4.2 | Fill | TC-470 | TC - S5 - Earthworks / FILL - LOE
I2S-7688-MP-74.5.4.2 | Fill | TC-490 | TC - S6 - Earthworks / FILL - LOE
I2S-7688-MP-74.5.4.2 | Fill | TC-480 | TC - S4 - Earthworks / FILL - LOE
I2S-7688-MP-74.5.4.2 | Fill | TC-500 | TC - S3 - Earthworks / FILL - LOE
I2S-7688-MP-74.5.4.2 | Fill | TC-510 | TC - S2 - Earthworks / FILL - LOE
I2S-7688-MP-74.5.4.2 | Fill | TC-520 | TC - S1 - Earthworks / FILL - LOE
Capping
I2S-7688-MP-74.5.10 | Capping | TC-530 | TC - S5 - Capping - LOE
I2S-7688-MP-74.5.10 | Capping | TC-540 | TC - S6 - Capping - LOE
I2S-7688-MP-74.5.10 | Capping | TC-550 | TC - S4 - Capping - LOE
I2S-7688-MP-74.5.10 | Capping | TC-560 | TC - S3 - Capping - LOE
I2S-7688-MP-74.5.10 | Capping | TC-570 | TC - S2 - Capping - LOE
I2S-7688-MP-74.5.10 | Capping | TC-580 | TC - S1 - Capping - LOE
Drainage
I2S-7688-MP-74.5.6 | Drainage | TC-720 | TC - S5 - Drainage - LOE
I2S-7688-MP-74.5.6 | Drainage | TC-730 | TC - S6 - Drainage - LOE
I2S-7688-MP-74.5.6 | Drainage | TC-740 | TC - S4 - Drainage - LOE
I2S-7688-MP-74.5.6 | Drainage | TC-750 | TC - S3 - Drainage - LOE
I2S-7688-MP-74.5.6 | Drainage | TC-760 | TC - S2 - Drainage - LOE
I2S-7688-MP-74.5.6 | Drainage | TC-770 | TC - S1 - Drainage - LOE
CSR
I2S-7688-MP-74.5.3 | CSR | TC-650 | TC - S5 - CSR - LOE
I2S-7688-MP-74.5.3 | CSR | TC-660 | TC - S6 - CSR - LOE
I2S-7688-MP-74.5.3 | CSR | TC-670 | TC - S4 - CSR - LOE
I2S-7688-MP-74.5.3 | CSR | TC-680 | TC - S3 - CSR - LOE
I2S-7688-MP-74.5.3 | CSR | TC-690 | TC - S2 - CSR - LOE
I2S-7688-MP-74.5.3 | CSR | TC-700 | TC - S1 - CSR - LOE
Deleted Activities |  |  |  | 2024-09-30 | 2027-03-15
I2S-7688-MP-74.1 | Deleted Activities | I2S-PRED-1000 | Deleted activities - Activity for missing predecessors
I2S-7688-MP-74.1 | Deleted Activities | I2S-SUCC-1000 | Deleted activities - Activity for missing successors
Deleted Activities - Prior to 23/03/26 |  |  |  | 2024-11-29 | 2025-02-28
I2S-7688-MP-74.1.4 | Deleted Activities - Prior to 23/03/26 | I.GG.P.C.10C-500 | PROC - Pkg 59 - Offsite Solid Waste Disposal - Engage Subcontractor - delete | 2024-11-29 | 2025-02-07
I2S-7688-MP-74.1.4 | Deleted Activities - Prior to 23/03/26 | I.GG.P.C.10C-510 | PROC - Pkg 59 - Offsite Solid Waste Disposal - Subcontractor Mob to Site - delete | 2025-02-10 | 2025-02-28
I2S-7688-MP-74.1.4 | Deleted Activities - Prior to 23/03/26 | I.DE.CCB.7020 | DSN - Sig - ILB - CCB G6 - POSS-3 - Prepare & Submit CCR checklist - Not required delete
I2S-7688-MP-74.1.4 | Deleted Activities - Prior to 23/03/26 | I.DE.CCB.7030 | DSN - Sig - ILB - CCB G6 - POSS-3 - IRPL Reviews & Approves CCR Submission - Not required delete
I2S-7688-MP-74.1.4 | Deleted Activities - Prior to 23/03/26 | I.DE.CCB.7040 | DSN - Sig - ILB - CCB G6 - POSS-3 - Meeting - Presentation of CCR Submission to SM Sub CCB - Not required delete
I2S-7688-MP-74.1.4 | Deleted Activities - Prior to 23/03/26 | I.DE.CCB.7050 | DSN - Sig - ILB - CCB G6 - POSS-3 - Configuration Change Acceptance Notice - Not required delete
I2S-7688-MP-74.1.4 | Deleted Activities - Prior to 23/03/26 | I.DE.CCB.7250 | DSN - Sig - ILB - CCB G6 - POSS-3 - IRPL Submits CCB to SM Sub CCB - Not required delete
Deleted Activities - Prior to 20/02/26 |  |  |  | 2024-12-20 | 2026-02-10
I2S-7688-MP-74.1.3 | Deleted Activities - Prior to 20/02/26 | I.GG.P.S.10IG-230 | Deleted - PROC - Sig - Points Motors & Detectors - Free Issued - Package Placement - delete | 2025-03-17 | 2025-03-28
I2S-7688-MP-74.1.3 | Deleted Activities - Prior to 20/02/26 | I.GG.P.S.10IG-240 | Deleted - PROC - Sig - Points Motors & Detectors - Free Issued - Manufacturing & Delivery - delete | 2025-03-31 | 2026-02-10
I2S-7688-MP-74.1.3 | Deleted Activities - Prior to 20/02/26 | I.GG.P.S.10IG-200 | Deleted - PROC - Sig - Points Motors & Detectors - Free Issued - Prepare Tender Documents - delete | 2024-12-20 | 2025-01-31
I2S-7688-MP-74.1.3 | Deleted Activities - Prior to 20/02/26 | I.GG.P.S.10IG-210 | Deleted - PROC - Sig - Points Motors & Detectors - Free Issued - Pricing by Suppliers / Subcontractors - delete | 2025-02-03 | 2025-02-28
I2S-7688-MP-74.1.3 | Deleted Activities - Prior to 20/02/26 | I.GG.P.S.10IG-220 | Deleted - PROC - Sig - Points Motors & Detectors - Free Issued - Package Review / Approval - delete | 2025-03-03 | 2025-03-14
I2S-7688-MP-74.1.3 | Deleted Activities - Prior to 20/02/26 | I.DE.CCB.6910 | Deleted - DSN - Sig - ILB - CCB G6 - POSS-2 - Prepare & Submit CCR checklist - Delete
I2S-7688-MP-74.1.3 | Deleted Activities - Prior to 20/02/26 | I.DE.CCB.6950 | Deleted - DSN - Sig - ILB - CCB G6 - POSS-2 - IRPL Reviews & Approves CCR Submission - delete
I2S-7688-MP-74.1.3 | Deleted Activities - Prior to 20/02/26 | I.DE.CCB.6960 | Deleted - DSN - Sig - ILB - CCB G6 - POSS-2 - Meeting - Presentation of CCR Submission to SM Sub CCB - delete
I2S-7688-MP-74.1.3 | Deleted Activities - Prior to 20/02/26 | I.DE.CCB.6970 | Deleted - DSN - Sig - ILB - CCB G6 - POSS-2 - Configuration Change Acceptance Notice -delete
I2S-7688-MP-74.1.3 | Deleted Activities - Prior to 20/02/26 | I.DE.CCB.7230 | Deleted - DSN - Sig - ILB - CCB G6 - POSS-2 - IRPL Submits CCB to SM Sub CCB - delete
Deleted Activities - prior to 09/01/2026 updates - M3 WAD - ARR 4.2 changes to ARR 4.1 |  |  |  | 2024-12-06 | 2025-07-29
I2S-7688-MP-74.1.2 | Deleted Activities - prior to 09/01/2026 updates - M3 WAD - ARR 4.2 changes to ARR 4.1 | I.GG.WAD.2610 | Deleted - WAD - Major - M3 - BGW - Stage 2 - DDD - ARR 4.1 - Comments Close out - dsn updates
I2S-7688-MP-74.1.2 | Deleted Activities - prior to 09/01/2026 updates - M3 WAD - ARR 4.2 changes to ARR 4.1 | I.GG.WAD.1060 | Deleted - WAD - Major - M3 - BGW - Stage 2 - DDD - ARR 4.1 - Complete Review by TfNSW (20d) / IV (5d) | 2025-05-13 | 2025-07-29
I2S-7688-MP-74.1.2 | Deleted Activities - prior to 09/01/2026 updates - M3 WAD - ARR 4.2 changes to ARR 4.1 | I.GG.WAD.2620 | Deleted - WAD - Major - M3 - BGW - Stage 2 - DDD - ARR 4.1 - TfNSW and IV review and Approve Design
I2S-7688-MP-74.1.2 | Deleted Activities - prior to 09/01/2026 updates - M3 WAD - ARR 4.2 changes to ARR 4.1 | I.GG.WAD.2800 | Deleted - WAD - Major - M3 - BGW - Stage 2 - DDD - ARR 4.1 - submission
I2S-7688-MP-74.1.2 | Deleted Activities - prior to 09/01/2026 updates - M3 WAD - ARR 4.2 changes to ARR 4.1 | I.GG.WAD.2880 | Deleted - WAD - Major - M3 - BGW - Stage 2 - ARR 4.1 - Design Documentation for Review and Acceptance - Milestone
I2S-7688-MP-74.1.2 | Deleted Activities - prior to 09/01/2026 updates - M3 WAD - ARR 4.2 changes to ARR 4.1 | TC-860 | Deleted - Time Chainage - TC - Sec.6 - Trackwork -
I2S-7688-MP-74.1.2 | Deleted Activities - prior to 09/01/2026 updates - M3 WAD - ARR 4.2 changes to ARR 4.1 | I.DE.00.9720 | Deleted - CoA - E66 - Submit Flood Design Ver. Report (FDVR) to BCS, DCCEEW Water, TfNSW and Councils for review | 2024-12-06 | 2025-01-16
Deleted Activities - post 05/12/2025
I2S-7688-MP-74.1.1 | Deleted Activities - post 05/12/2025 | I.GG.WAD.2900 | Deleted - WAD - Minor - M5 - BGW+HS - Close out comments
Deleted Activities - post 31/10/2025 |  |  |  | 2024-12-05 | 2026-11-06
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.GG.P.R.10W-747 | Deleted - PROC - Derailers - IRPL Free-Issue - Manufacturing & Delivery s - 2 no's - no derailers required | 2025-03-14 | 2025-08-29
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.GG.P.C.10C-630 | Deleted - PROC - Pkg 52- Concrete Pump Hire - Engage Subcontractor (Delete - No longer required) | 2025-04-23 | 2025-06-19
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.GG.P.C.10C-640 | Deleted - PROC - Pkg 52- Concrete Pump Hire - Subcontractor Mob to Site (Delete - No longer required) | 2025-06-20 | 2025-07-17
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.28110 | Deleted - CON - Sec.1 - Culvert : E7-RA-418060-1 - Construct Scour Protection
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.22930 | Deleted - CON - Sec.1 - Culvert : E7-RA-419050-1 - Construct Scour Protection | 2025-09-30 | 2025-09-30
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.22900 | Deleted - CON - Sec.1 - Culvert : E7-RA-419050-1 - Place Precast Apron Slab | 2025-09-27 | 2025-09-27
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.65.18790 | Deleted - CON - Sec.2 - Public LX - Culvert ID : E2-RD-423080-1 - "Deleted" - Construct Scour Protection
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.65.15410 | Deleted - CON - Sec.2 - Public LX - Culvert ID : E2-RD-423080-1 - Civil Works complete |  | 2025-12-01
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.65.18370 | Deleted - CON - Sec.2 - Public LX - Culvert ID : E2-RD-423080-1 - Site prep / Detail Excavation | 2025-11-07 | 2025-11-08
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.65.18380 | Deleted - CON - Sec.2 - Public LX - Culvert ID : E2-RD-423080-1 - Structural fill (150mm) / Bedding (150mm) Placement | 2025-11-09 | 2025-11-10
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.65.18390 | Deleted - CON - Sec.2 - Public LX - Culvert ID : E2-RD-423080-1 - Headwall Cut-off Wall Installation (FRP) | 2025-11-09 | 2025-11-10
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.24130 | Deleted - CON - Sec.3 - Culvert : E7-RA-435700-1 - Construct Scour Protection | 2026-04-09 | 2026-04-09
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.27250 | Deleted - CON - Sec.3 - Culvert : E7-RA-430050-1 - Construct Scour Protection | 2026-05-21 | 2026-05-21
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.27620 | Deleted - CON - Sec.3 - Culvert : E7-RA-435150-1 - Place Precast Apron Slab | 2026-03-10 | 2026-03-10
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.27650 | Deleted - CON - Sec.3 - Culvert : E7-RA-435150-1 - Construct Scour Protection | 2026-03-21 | 2026-03-21
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.27750 | Deleted - CON - Sec.3 - Culvert : E7-RA-433860-1 - Construct Scour Protection | 2026-04-07 | 2026-04-07
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.27720 | Deleted - CON - Sec.3 - Culvert : E7-RA-433860-1 - Place Precast Apron Slab | 2026-04-01 | 2026-04-01
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.28150 | Deleted - CON - Sec.3 - Culvert : E7-RD-433452-1 - Construct Scour Protection
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.20410 | Deleted - CON - Sec.5 - Culvert : E7-RA-448900-1 - Construct Scour Protection | 2026-04-22 | 2026-04-22
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.20530 | Deleted - CON - Sec.5 - Culvert : E7-RA-451960-1 - Construct Scour Protection | 2025-11-26 | 2025-11-26
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.21730 | Deleted - CON - Sec.4 - Culvert : E7-RA-445700-1 - Construct Scour Protection | 2025-12-07 | 2025-12-07
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.22690 | Deleted - CON - Sec.4 - Culvert : E7-RA-440130-1 - Construct Scour Protection | 2026-04-14 | 2026-04-14
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.27340 | Deleted - CON - Sec.4 - Culvert : E7-RA-436850-1 - Place Precast Apron Slab | 2026-05-19 | 2026-05-19
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.27370 | Deleted - CON - Sec.4 - Culvert : E7-RA-436850-1 - Construct Scour Protection | 2026-05-24 | 2026-05-24
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.21340 | Deleted - CON - Sec.4 - Culvert : E7-RA-438810-1 - Place Precast Apron Slab | 2026-04-24 | 2026-04-24
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.21370 | Deleted - CON - Sec.4 - Culvert : E7-RA-438810-1 - Construct Scour Protection | 2026-04-30 | 2026-04-30
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.21250 | Deleted - CON - Sec.4 - Culvert : E7-RA-439300-1 - Construct Scour Protection | 2026-03-07 | 2026-03-07
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.22570 | Deleted - CON - Sec.4 - Culvert : E7-RA-440720-1 - Construct Scour Protection | 2025-12-20 | 2025-12-20
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.22450 | Deleted - CON - Sec.4 - Culvert : E7-RA-440830-1 - Construct Scour Protection | 2026-01-14 | 2026-01-14
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.19810 | Deleted - CON - Sec.6 - Culvert : E6-RD-455940-1 - Construct Scour Protection | 2025-09-27 | 2025-09-27
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.29340 | Deleted - CON - Sec.6 - Culvert : E7-RD-456912-1 - Construct Scour Protection
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.29550 | Deleted - CON - Sec.5 - Culvert : M3-RD-1360-1 - FRP Base Slab / Apron Slab / Cut-off Wall
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.29560 | Deleted - CON - Sec.5 - Culvert : M3-RD-1360-1 - 7 day Curing
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.29590 | Deleted - CON - Sec.5 - Culvert : M3-RD-1360-1 - Detail backfill
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.29630 | Deleted - CON - Sec.5 - Culvert : E7-RD-454718-1 - Construct Scour Protection
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.29810 | Deleted - CON - Sec.4 - Culvert : M2-RD-445782-1 - Construct Scour Protection
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.23890 | Deleted - CON - Sec.2 - Culvert : E7-RA-420670-1 - Construct Scour Protection | 2025-10-12 | 2025-10-12
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.23770 | Deleted - CON - Sec.2 - Culvert : E7-RA-423540-1 - Construct Scour Protection | 2025-12-13 | 2025-12-13
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.23530 | Deleted - CON - Sec.2 - Culvert : E7-RA-424570-1 - Construct Scour Protection | 2025-10-02 | 2025-10-02
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.23410 | Deleted - CON - Sec.2 - Culvert : E7-RA-425131-1 - Construct Scour Protection | 2025-11-24 | 2025-11-24
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.23290 | Deleted - CON - Sec.2 - Culvert : E7-RA-425540-1 - Construct Scour Protection | 2025-11-29 | 2025-11-29
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.26770 | Deleted - CON - Sec.2 - Culvert : E7-RA-423060-1 - Construct Scour Protection | 2025-11-10 | 2025-11-10
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.29210 | Deleted - CON - Sec.4 - Culvert :E7-RD-442700-1 - Construct Scour Protection
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.21600 | Deleted - CON - Sec.4 - Culvert : E7-RD-437359-1 - Headwall Cut-off Wall Installation (FRP) | 2025-12-19 | 2025-12-20
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.21610 | Deleted - CON - Sec.4 - Culvert : E7-RD-437359-1 - Construct Scour Protection | 2025-12-21 | 2025-12-21
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.28820 | Deleted - CON - Sec.4 - Culvert : E7-RD-437360-1 - Construct Scour Protection
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.28890 | Deleted - CON - Sec.4 - Culvert : E7-RD-438730-1 - Place Precast Apron Slab
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.28920 | Deleted - CON - Sec.4 - Culvert : E7-RD-438730-1 - Construct Scour Protection
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.23170 | Deleted - CON - Sec.2 - Culvert : E7-RA-425840-1 - Construct Scour Protection | 2026-01-14 | 2026-01-14
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.26650 | Deleted - CON - Sec.2 - Culvert : E7-RA-423450-1 - Construct Scour Protection | 2025-11-26 | 2025-11-27
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.GG.P.R.10W-707 | Deleted - PROC - Derailers - IRPL Free-Issue - Prepare Tender Documents - no derailers required | 2024-12-05 | 2025-01-15
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.GG.P.R.10W-717 | Deleted - PROC - Derailers - IRPL Free-Issue - Pricing by Suppliers / Subcontractors - no derailers required | 2025-01-16 | 2025-02-13
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.GG.P.R.10W-727 | Deleted - PROC - Derailers - IRPL Free-Issue - Package Review / Approval - no derailers required | 2025-02-14 | 2025-02-27
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.GG.P.R.10W-737 | Deleted - PROC - Derailers - IRPL Free-Issue - Package Placement - no derailers required | 2025-02-28 | 2025-03-13
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.24730 | Deleted - CON - Sec.3 - Culvert : E7-RA-430550-1 - Construct Scour Protection | 2026-06-09 | 2026-06-09
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.27820 | Deleted - CON - Sec.3 - Culvert : E7-RA-431160-1 - Place Precast Apron Slab | 2026-04-17 | 2026-04-17
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.27850 | Deleted - CON - Sec.3 - Culvert : E7-RA-431160-1 - Construct Scour Protection | 2026-04-22 | 2026-04-22
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.24490 | Deleted - CON - Sec.3 - Culvert : E7-RA-434325-1 - Construct Scour Protection | 2026-02-20 | 2026-02-20
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.26890 | Deleted - CON - Sec.3 - Culvert : E7-RD-433450-1 - Construct Scour Protection | 2025-12-07 | 2025-12-08
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.26490 | Deleted - CON - Sec.6 - Culvert : C38.300 - 7 day Curing | 2025-11-02 | 2025-11-02
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.26530 | Deleted - CON - Sec.6 - Culvert : C38.300 - Detail backfill | 2025-11-09 | 2025-11-09
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.28350 | Deleted - CON - Sec.5 - Culvert : E7-RA-453720-1 - Construct Scour Protection
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.20650 | Deleted - CON - Sec.5 - Culvert : E7-RA-452940-1 - Construct Scour Protection | 2025-12-10 | 2025-12-10
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.20890 | Deleted - CON - Sec.5 - Culvert : E7-RA-454000-1 - Construct Scour Protection | 2026-01-20 | 2026-01-20
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.13840 | Deleted - CON - Sec.5 - Culvert : E7-RA-446260-1 - Construct Scour Protection | 2026-02-20 | 2026-02-20
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.22210 | Deleted - CON - Sec.4 - Culvert : E7-RA-443320-1 - Construct Scour Protection | 2025-10-03 | 2025-10-03
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.19690 | Deleted - CON - Sec.6 - Culvert : E7-RA-454880-1 - Construct Scour Protection | 2026-01-16 | 2026-01-16
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.19490 | Deleted - CON - Sec.5 - Culvert : E7-RA-447210-1 - Construct Scour Protection | 2026-03-08 | 2026-03-08
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.29260 | Deleted - CON - Sec.5 - Culvert : E7-RD-452450-1 - Construct Scour Protection
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.22090 | Deleted - CON - Sec.4 - Culvert : E7-RA-443484-1 - Construct Scour Protection | 2025-10-27 | 2025-10-27
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.21970 | Deleted - CON - Sec.4 - Culvert : E7-RA-443720-1 - Construct Scour Protection | 2025-11-10 | 2025-11-10
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.21850 | Deleted - CON - Sec.4 - Culvert : 7-RA-444350-1 - Construct Scour Protection | 2025-11-23 | 2025-11-23
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.30180 | Deleted - CON - Sec.4 - Culvert : E7-RA-442560-1 - Construct Scour Protection
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.30320 | Deleted - CON - Sec.4 - Culvert : E7-RA-439475-1 - Construct Scour Protection
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.30620 | Deleted - CON - Sec.4 - Culvert : E7-RA-436880-1 - Construct Scour Protection
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.30720 | Deleted - CON - Sec.4 - Culvert : E7-RA-436105-1 - Construct Scour Protection
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.30860 | Deleted - CON - Sec.3 - Culvert : E7-RA-430650-1 - Construct Scour Protection
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.31480 | Deleted - CON - Sec.2 - Culvert : E7-RD-425670-1 - Construct Scour Protection
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.31810 | Deleted - CON - Sec.2 - Culvert : E7-RD-421367-1 - Construct Scour Protection
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.34.31890 | Deleted - CON - Sec.5 - Culvert : E7-RA-453720-1 - Construct Scour protection
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.65.19181 | Deleted - CON - Sec.2 - Public LX - Culvert ID : E2-RD-423080-1 - Headwall installation
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.65.19191 | CON - Sec.2 - Public LX - Culvert ID : E2-RD-423080-1 - HDPE / RCP Pipe Lay & Backfill
I2S-7688-MP-74.1.25 | Deleted Activities - post 31/10/2025 | I.CN.65.19201 | Deleted - CON - Sec.2 - Public LX - Culvert ID : E2-RD-423080-1 - Headwall Stitch Pour
Culvert ID : E2-RD-423080-1 / Type : 3*900mm HDPE / Ch5565 (13.56m each)
I2S-7688-MP-74.1.25.18 | Culvert ID : E2-RD-423080-1 / Type : 3*900mm HDPE / Ch5565 (13.56m each) | I.CN.34.31670 | Deleted - CON - Sec.2 - Culvert : E2-RD-423080-1 - Trench Excavation / Site Prep
I2S-7688-MP-74.1.25.18 | Culvert ID : E2-RD-423080-1 / Type : 3*900mm HDPE / Ch5565 (13.56m each) | I.CN.34.31680 | Deleted - CON - Sec.2 - Culvert : E2-RD-423080-1 - Foundation Treatment / Bedding
I2S-7688-MP-74.1.25.18 | Culvert ID : E2-RD-423080-1 / Type : 3*900mm HDPE / Ch5565 (13.56m each) | I.CN.34.31690 | Deleted - CON - Sec.2 - Culvert : E2-RD-423080-1 - Place HDPE Pipe
I2S-7688-MP-74.1.25.18 | Culvert ID : E2-RD-423080-1 / Type : 3*900mm HDPE / Ch5565 (13.56m each) | I.CN.34.31700 | Deleted - CON - Sec.2 - Culvert : E2-RD-423080-1 - Backfill Pipe
I2S-7688-MP-74.1.25.18 | Culvert ID : E2-RD-423080-1 / Type : 3*900mm HDPE / Ch5565 (13.56m each) | I.CN.34.31710 | Deleted - CON - Sec.2 - Culvert : E2-RD-423080-1 - Place Precast Wingwall
I2S-7688-MP-74.1.25.18 | Culvert ID : E2-RD-423080-1 / Type : 3*900mm HDPE / Ch5565 (13.56m each) | I.CN.34.31720 | Deleted - CON - Sec.2 - Culvert : E2-RD-423080-1 - Precast stitch pours for precast headwalls
I2S-7688-MP-74.1.25.18 | Culvert ID : E2-RD-423080-1 / Type : 3*900mm HDPE / Ch5565 (13.56m each) | I.CN.34.31730 | Deleted - CON - Sec.2 - Culvert : E2-RD-423080-1 - Construct Scour Protection
I2S-7688-MP-74.1.25.18 | Culvert ID : E2-RD-423080-1 / Type : 3*900mm HDPE / Ch5565 (13.56m each) | I.CN.34.31740 | Deleted - CON - Sec.2 - Culvert : E2-RD-423080-1 - Detailed backfill
Culvert ID : E7-SU-436017-1 / Type : 1*3000x3000mm RCBC / Ch18518
I2S-7688-MP-74.1.25.8 | Culvert ID : E7-SU-436017-1 / Type : 1*3000x3000mm RCBC / Ch18518 | I.CN.65.18475 | Deleted - CON - Sec.4 - Stock Crossing - Culvert : E7-SU-436017-1 - Backfill and Scour Protection
I2S-7688-MP-74.1.25.8 | Culvert ID : E7-SU-436017-1 / Type : 1*3000x3000mm RCBC / Ch18518 | I.CN.65.18480 | Deleted - CON - Sec.4 - Stock Crossing - Culvert : E7-SU-436017-1 - FRP Base Slab
I2S-7688-MP-74.1.25.8 | Culvert ID : E7-SU-436017-1 / Type : 1*3000x3000mm RCBC / Ch18518 | I.CN.65.18610 | Deleted - CON - Sec.4 - Stock Crossing - Culvert : E7-SU-436017-1 - 7 day Curing
I2S-7688-MP-74.1.25.8 | Culvert ID : E7-SU-436017-1 / Type : 1*3000x3000mm RCBC / Ch18518 | I.CN.65.18620 | Deleted - CON - Sec.4 - Stock Crossing - Culvert : E7-SU-436017-1 - Place Precast wingwall and Stich pour
I2S-7688-MP-74.1.25.8 | Culvert ID : E7-SU-436017-1 / Type : 1*3000x3000mm RCBC / Ch18518 | I.CN.65.18455 | Deleted - CON - Sec.4 - Stock Crossing - Culvert : E7-SU-436017-1 - Trench Excavation / Site Prep
I2S-7688-MP-74.1.25.8 | Culvert ID : E7-SU-436017-1 / Type : 1*3000x3000mm RCBC / Ch18518 | I.CN.65.18460 | Deleted - CON - Sec.4 - Stock Crossing - Culvert : E7-SU-436017-1 - Place RCBC crown units
Culvert ID : E7-SU-434988-1 / Type : 1*3000x3000mm RCBC / Ch17480 (7.200m)
I2S-7688-MP-74.1.25.9 | Culvert ID : E7-SU-434988-1 / Type : 1*3000x3000mm RCBC / Ch17480 (7.200m) | I.CN.34.30770 | Deleted - CON - Sec.3 - Culvert : E7-SU-434988-1 - Place RCBC crown units
I2S-7688-MP-74.1.25.9 | Culvert ID : E7-SU-434988-1 / Type : 1*3000x3000mm RCBC / Ch17480 (7.200m) | I.CN.34.30780 | Deleted - CON - Sec.3 - Culvert : E7-SU-434988-1 - Place Precast Wingwall
I2S-7688-MP-74.1.25.9 | Culvert ID : E7-SU-434988-1 / Type : 1*3000x3000mm RCBC / Ch17480 (7.200m) | I.CN.34.30790 | Deleted - CON - Sec.3 - Culvert : E7-SU-434988-1 - Place Precast Stich
I2S-7688-MP-74.1.25.9 | Culvert ID : E7-SU-434988-1 / Type : 1*3000x3000mm RCBC / Ch17480 (7.200m) | I.CN.34.30800 | Deleted - CON - Sec.3 - Culvert : E7-SU-434988-1 - Construct Scour Protection
I2S-7688-MP-74.1.25.9 | Culvert ID : E7-SU-434988-1 / Type : 1*3000x3000mm RCBC / Ch17480 (7.200m) | I.CN.34.30810 | Deleted - CON - Sec.3 - Culvert : E7-SU-434988-1 - Detailed backfill
I2S-7688-MP-74.1.25.9 | Culvert ID : E7-SU-434988-1 / Type : 1*3000x3000mm RCBC / Ch17480 (7.200m) | I.CN.34.30730 | Deleted - CON - Sec.3 - Culvert : E7-SU-434988-1 - FRP Base Slab
I2S-7688-MP-74.1.25.9 | Culvert ID : E7-SU-434988-1 / Type : 1*3000x3000mm RCBC / Ch17480 (7.200m) | I.CN.34.30740 | Deleted - CON - Sec.3 - Culvert : E7-SU-434988-1 - Trench Excavation / Site Prep
I2S-7688-MP-74.1.25.9 | Culvert ID : E7-SU-434988-1 / Type : 1*3000x3000mm RCBC / Ch17480 (7.200m) | I.CN.34.30750 | Deleted - CON - Sec.3 - Culvert : E7-SU-434988-1 - Foundation Treatment / Bedding
I2S-7688-MP-74.1.25.9 | Culvert ID : E7-SU-434988-1 / Type : 1*3000x3000mm RCBC / Ch17480 (7.200m) | I.CN.34.30760 | Deleted - CON - Sec.3 - Culvert : E7-SU-434988-1 - 7 day Curing
Culvert ID : E7-SU-426513-1 / Type : 1*3000x3000mm RCBC / Ch9006 (12m)
I2S-7688-MP-74.1.25.19 | Culvert ID : E7-SU-426513-1 / Type : 1*3000x3000mm RCBC / Ch9006 (12m) | I.CN.34.31180 | Deleted - CON - Sec.3 - Culvert : E7-SU-426513-1 - Construct Scour protection
I2S-7688-MP-74.1.25.19 | Culvert ID : E7-SU-426513-1 / Type : 1*3000x3000mm RCBC / Ch9006 (12m) | I.CN.34.31190 | Deleted - CON - Sec.3 - Culvert : E7-SU-426513-1 - Detailed backfill
I2S-7688-MP-74.1.25.19 | Culvert ID : E7-SU-426513-1 / Type : 1*3000x3000mm RCBC / Ch9006 (12m) | I.CN.34.31200 | Deleted - CON - Sec.3 - Culvert : E7-SU-426513-1 - Place Precast Stich
I2S-7688-MP-74.1.25.19 | Culvert ID : E7-SU-426513-1 / Type : 1*3000x3000mm RCBC / Ch9006 (12m) | I.CN.34.31210 | Deleted - CON - Sec.3 - Culvert : E7-SU-426513-1 - Trench Excavation / Site Prep
I2S-7688-MP-74.1.25.19 | Culvert ID : E7-SU-426513-1 / Type : 1*3000x3000mm RCBC / Ch9006 (12m) | I.CN.34.31220 | Deleted - CON - Sec.3 - Culvert : E7-SU-426513-1 - Place RCBC crown units
I2S-7688-MP-74.1.25.19 | Culvert ID : E7-SU-426513-1 / Type : 1*3000x3000mm RCBC / Ch9006 (12m) | I.CN.34.31230 | Deleted - CON - Sec.3 - Culvert : E7-SU-426513-1 - Foundation Treatment
I2S-7688-MP-74.1.25.19 | Culvert ID : E7-SU-426513-1 / Type : 1*3000x3000mm RCBC / Ch9006 (12m) | I.CN.34.31240 | Deleted - CON - Sec.3 - Culvert : E7-SU-426513-1 - FRP Base Slab
I2S-7688-MP-74.1.25.19 | Culvert ID : E7-SU-426513-1 / Type : 1*3000x3000mm RCBC / Ch9006 (12m) | I.CN.34.31250 | Deleted - CON - Sec.3 - Culvert : E7-SU-426513-1 - 7 day Curing
I2S-7688-MP-74.1.25.19 | Culvert ID : E7-SU-426513-1 / Type : 1*3000x3000mm RCBC / Ch9006 (12m) | I.CN.34.31260 | Deleted - CON - Sec.3 - Culvert : E7-SU-426513-1 - Place Precast wingwall
Culvert ID : E2-RD-425810-1 / Type : 8*900mm HDPE / Ch8283 (19.56m each)
I2S-7688-MP-74.1.25.11 | Culvert ID : E2-RD-425810-1 / Type : 8*900mm HDPE / Ch8283 (19.56m each) | I.CN.34.31270 | Deleted - CON - Sec.2 - Culvert : E2-RD-425810-1 - Foundation Treatment / Bedding
I2S-7688-MP-74.1.25.11 | Culvert ID : E2-RD-425810-1 / Type : 8*900mm HDPE / Ch8283 (19.56m each) | I.CN.34.31280 | Deleted - CON - Sec.2 - Culvert : E2-RD-425810-1 - Place HDPE Pipe
I2S-7688-MP-74.1.25.11 | Culvert ID : E2-RD-425810-1 / Type : 8*900mm HDPE / Ch8283 (19.56m each) | I.CN.34.31290 | Deleted - CON - Sec.2 - Culvert : E2-RD-425810-1 - Backfill Pipe
I2S-7688-MP-74.1.25.11 | Culvert ID : E2-RD-425810-1 / Type : 8*900mm HDPE / Ch8283 (19.56m each) | I.CN.34.31300 | Deleted - CON - Sec.2 - Culvert : E2-RD-425810-1 - Place Precast Wingwall
I2S-7688-MP-74.1.25.11 | Culvert ID : E2-RD-425810-1 / Type : 8*900mm HDPE / Ch8283 (19.56m each) | I.CN.34.31310 | Deleted - CON - Sec.2 - Culvert : E2-RD-425810-1 - Precast stitch pours for precast headwalls
I2S-7688-MP-74.1.25.11 | Culvert ID : E2-RD-425810-1 / Type : 8*900mm HDPE / Ch8283 (19.56m each) | I.CN.34.31320 | Deleted - CON - Sec.2 - Culvert : E2-RD-425810-1 - Construct Scour Protection
I2S-7688-MP-74.1.25.11 | Culvert ID : E2-RD-425810-1 / Type : 8*900mm HDPE / Ch8283 (19.56m each) | I.CN.34.31330 | Deleted - CON - Sec.2 - Culvert : E2-RD-425810-1 - Detailed backfill
I2S-7688-MP-74.1.25.11 | Culvert ID : E2-RD-425810-1 / Type : 8*900mm HDPE / Ch8283 (19.56m each) | I.CN.34.31340 | Deleted - CON - Sec.2 - Culvert : E2-RD-425810-1 - Trench Excavation / Site Prep
Culvert ID : E2-RD-425720-1 / Type : 30*900mm HDPE / Ch8227 (30.43m each)
I2S-7688-MP-74.1.25.13 | Culvert ID : E2-RD-425720-1 / Type : 30*900mm HDPE / Ch8227 (30.43m each) | I.CN.34.31350 | Deleted - CON - Sec.2 - Culvert : E2-RD-425720-1 - Foundation Treatment / Bedding
I2S-7688-MP-74.1.25.13 | Culvert ID : E2-RD-425720-1 / Type : 30*900mm HDPE / Ch8227 (30.43m each) | I.CN.34.31360 | Deleted - CON - Sec.2 - Culvert : E2-RD-425720-1 - Place HDPE Pipe
I2S-7688-MP-74.1.25.13 | Culvert ID : E2-RD-425720-1 / Type : 30*900mm HDPE / Ch8227 (30.43m each) | I.CN.34.31370 | Deleted - CON - Sec.2 - Culvert : E2-RD-425720-1 - Backfill Pipe
I2S-7688-MP-74.1.25.13 | Culvert ID : E2-RD-425720-1 / Type : 30*900mm HDPE / Ch8227 (30.43m each) | I.CN.34.31380 | Deleted - CON - Sec.2 - Culvert : E2-RD-425720-1 - Place Precast Wingwall
I2S-7688-MP-74.1.25.13 | Culvert ID : E2-RD-425720-1 / Type : 30*900mm HDPE / Ch8227 (30.43m each) | I.CN.34.31390 | Deleted - CON - Sec.2 - Culvert : E2-RD-425720-1 - Precast stitch pours for precast headwalls
I2S-7688-MP-74.1.25.13 | Culvert ID : E2-RD-425720-1 / Type : 30*900mm HDPE / Ch8227 (30.43m each) | I.CN.34.31400 | Deleted - CON - Sec.2 - Culvert : E2-RD-425720-1 - Construct Scour Protection
I2S-7688-MP-74.1.25.13 | Culvert ID : E2-RD-425720-1 / Type : 30*900mm HDPE / Ch8227 (30.43m each) | I.CN.34.31410 | Deleted - CON - Sec.2 - Culvert : E2-RD-425720-1 - Detailed backfill
I2S-7688-MP-74.1.25.13 | Culvert ID : E2-RD-425720-1 / Type : 30*900mm HDPE / Ch8227 (30.43m each) | I.CN.34.31420 | Deleted - CON - Sec.2 - Culvert : E2-RD-425720-1 - Trench Excavation / Site Prep
Culvert ID : E7-SU-425154-1 / Type : 1*3000x3000mm RCBC / Ch7693 (7.200m)
I2S-7688-MP-74.1.25.15 | Culvert ID : E7-SU-425154-1 / Type : 1*3000x3000mm RCBC / Ch7693 (7.200m) | I.CN.34.31510 | Deleted - CON - Sec.2 - Culvert : E7-SU-425154-1 - Construct Scour Protection
I2S-7688-MP-74.1.25.15 | Culvert ID : E7-SU-425154-1 / Type : 1*3000x3000mm RCBC / Ch7693 (7.200m) | I.CN.34.31520 | Deleted - CON - Sec.2 - Culvert : E7-SU-425154-1 - Detailed backfill
I2S-7688-MP-74.1.25.15 | Culvert ID : E7-SU-425154-1 / Type : 1*3000x3000mm RCBC / Ch7693 (7.200m) | I.CN.34.31530 | Deleted - CON - Sec.2 - Culvert : E7-SU-425154-1 - Trench Excavation / Site Prep
I2S-7688-MP-74.1.25.15 | Culvert ID : E7-SU-425154-1 / Type : 1*3000x3000mm RCBC / Ch7693 (7.200m) | I.CN.34.31540 | Deleted - CON - Sec.2 - Culvert : E7-SU-425154-1 - Foundation Treatment
I2S-7688-MP-74.1.25.15 | Culvert ID : E7-SU-425154-1 / Type : 1*3000x3000mm RCBC / Ch7693 (7.200m) | I.CN.34.31550 | Deleted - CON - Sec.2 - Culvert : E7-SU-425154-1 - FRP Base Slab
I2S-7688-MP-74.1.25.15 | Culvert ID : E7-SU-425154-1 / Type : 1*3000x3000mm RCBC / Ch7693 (7.200m) | I.CN.34.31560 | Deleted - CON - Sec.2 - Culvert : E7-SU-425154-1 - 7 day Curing
I2S-7688-MP-74.1.25.15 | Culvert ID : E7-SU-425154-1 / Type : 1*3000x3000mm RCBC / Ch7693 (7.200m) | I.CN.34.31570 | Deleted - CON - Sec.2 - Culvert : E7-SU-425154-1 - Place RCBC crown units
I2S-7688-MP-74.1.25.15 | Culvert ID : E7-SU-425154-1 / Type : 1*3000x3000mm RCBC / Ch7693 (7.200m) | I.CN.34.31580 | Deleted - CON - Sec.2 - Culvert : E7-SU-425154-1 - Place Precast wingwall and Stich pour
Culvert ID : E7-SU-423469-1 / Type : 1*3000x3000mm RCBC / Ch5994 (9.60m)
I2S-7688-MP-74.1.25.16 | Culvert ID : E7-SU-423469-1 / Type : 1*3000x3000mm RCBC / Ch5994 (9.60m) | I.CN.34.31590 | Deleted - CON - Sec.2 - Culvert : E7-SU-423469-1 - Construct Scour Protection
I2S-7688-MP-74.1.25.16 | Culvert ID : E7-SU-423469-1 / Type : 1*3000x3000mm RCBC / Ch5994 (9.60m) | I.CN.34.31600 | Deleted - CON - Sec.2 - Culvert : E7-SU-423469-1 - Detailed backfill
I2S-7688-MP-74.1.25.16 | Culvert ID : E7-SU-423469-1 / Type : 1*3000x3000mm RCBC / Ch5994 (9.60m) | I.CN.34.31610 | Deleted - CON - Sec.2 - Culvert : E7-SU-423469-1 - Trench Excavation / Site Prep
I2S-7688-MP-74.1.25.16 | Culvert ID : E7-SU-423469-1 / Type : 1*3000x3000mm RCBC / Ch5994 (9.60m) | I.CN.34.31620 | Deleted - CON - Sec.2 - Culvert : E7-SU-423469-1 - Foundation Treatment
I2S-7688-MP-74.1.25.16 | Culvert ID : E7-SU-423469-1 / Type : 1*3000x3000mm RCBC / Ch5994 (9.60m) | I.CN.34.31630 | Deleted - CON - Sec.2 - Culvert : E7-SU-423469-1 - FRP Base Slab
I2S-7688-MP-74.1.25.16 | Culvert ID : E7-SU-423469-1 / Type : 1*3000x3000mm RCBC / Ch5994 (9.60m) | I.CN.34.31640 | Deleted - CON - Sec.2 - Culvert : E7-SU-423469-1 - 7 day Curing
I2S-7688-MP-74.1.25.16 | Culvert ID : E7-SU-423469-1 / Type : 1*3000x3000mm RCBC / Ch5994 (9.60m) | I.CN.34.31650 | Deleted - CON - Sec.2 - Culvert : E7-SU-423469-1 - Place RCBC crown units
I2S-7688-MP-74.1.25.16 | Culvert ID : E7-SU-423469-1 / Type : 1*3000x3000mm RCBC / Ch5994 (9.60m) | I.CN.34.31660 | Deleted - CON - Sec.2 - Culvert : E7-SU-423469-1 - Place Precast wingwall and Stich pour
Culvert - 008933-03 - 1500 RCP 24m |  |  |  | 2026-02-24 | 2026-03-01
I2S-7688-MP-74.1.25.10 | Culvert - 008933-03 - 1500 RCP 24m | I.CN.65.16400 | Deleted - CON - Sec.3 - Public LX - 008933 - Drainage - LX Culvert - Trench Excavation / Site Prep | 2026-02-24 | 2026-02-24
I2S-7688-MP-74.1.25.10 | Culvert - 008933-03 - 1500 RCP 24m | I.CN.65.16410 | Deleted - CON - Sec.3 - Public LX - 008933 - Drainage - Place RCP Pipe | 2026-02-26 | 2026-02-27
I2S-7688-MP-74.1.25.10 | Culvert - 008933-03 - 1500 RCP 24m | I.CN.65.16420 | Deleted - CON - Sec.3 - Public LX - 008933 - Drainage - Detailed backfill | 2026-02-28 | 2026-03-01
Culvert ID : E7-SU-439180-1 / Type : 1*3000x3000mm RCBC / Ch21672 (14.40m)
I2S-7688-MP-74.1.25.6 | Culvert ID : E7-SU-439180-1 / Type : 1*3000x3000mm RCBC / Ch21672 (14.40m) | I.CN.34.30370 | Deleted - CON - Sec.4 - Culvert : E7-SU-439180-1 - Place RCBC crown units
I2S-7688-MP-74.1.25.6 | Culvert ID : E7-SU-439180-1 / Type : 1*3000x3000mm RCBC / Ch21672 (14.40m) | I.CN.34.30380 | Deleted - CON - Sec.4 - Culvert : E7-SU-439180-1 - Place Precast Wingwall
I2S-7688-MP-74.1.25.6 | Culvert ID : E7-SU-439180-1 / Type : 1*3000x3000mm RCBC / Ch21672 (14.40m) | I.CN.34.30390 | Deleted - CON - Sec.4 - Culvert : E7-SU-439180-1 - Precast stitch pours /cure
I2S-7688-MP-74.1.25.6 | Culvert ID : E7-SU-439180-1 / Type : 1*3000x3000mm RCBC / Ch21672 (14.40m) | I.CN.34.30400 | Deleted - CON - Sec.4 - Culvert : E7-SU-439180-1 - Construct Scour Protection
I2S-7688-MP-74.1.25.6 | Culvert ID : E7-SU-439180-1 / Type : 1*3000x3000mm RCBC / Ch21672 (14.40m) | I.CN.34.30410 | Deleted - CON - Sec.4 - Culvert : E7-SU-439180-1 - Detailed backfill
I2S-7688-MP-74.1.25.6 | Culvert ID : E7-SU-439180-1 / Type : 1*3000x3000mm RCBC / Ch21672 (14.40m) | I.CN.34.30420 | Deleted - CON - Sec.4 - Culvert : E7-SU-439180-1 - FRP Base Slab
I2S-7688-MP-74.1.25.6 | Culvert ID : E7-SU-439180-1 / Type : 1*3000x3000mm RCBC / Ch21672 (14.40m) | I.CN.34.30430 | Deleted - CON - Sec.4 - Culvert : E7-SU-439180-1 - 7 day Curing
I2S-7688-MP-74.1.25.6 | Culvert ID : E7-SU-439180-1 / Type : 1*3000x3000mm RCBC / Ch21672 (14.40m) | I.CN.34.30440 | Deleted - CON - Sec.4 - Culvert : E7-SU-439180-1 - Trench Excavation / Site Prep
I2S-7688-MP-74.1.25.6 | Culvert ID : E7-SU-439180-1 / Type : 1*3000x3000mm RCBC / Ch21672 (14.40m) | I.CN.34.30450 | Deleted - CON - Sec.4 - Culvert : E7-SU-439180-1 - Foundation Treatment
Culvert ID : E7-SU-437414-1 / Type : 2*3000x3000mm RCBC / Ch19906 (7.20m each)
I2S-7688-MP-74.1.25.7 | Culvert ID : E7-SU-437414-1 / Type : 2*3000x3000mm RCBC / Ch19906 (7.20m each) | I.CN.34.30460 | Deleted - CON - Sec.4 - Culvert : E7-SU-437414-1 - Place RCBC crown units
I2S-7688-MP-74.1.25.7 | Culvert ID : E7-SU-437414-1 / Type : 2*3000x3000mm RCBC / Ch19906 (7.20m each) | I.CN.34.30470 | Deleted - CON - Sec.4 - Culvert : E7-SU-437414-1 - Place Precast Wingwall
I2S-7688-MP-74.1.25.7 | Culvert ID : E7-SU-437414-1 / Type : 2*3000x3000mm RCBC / Ch19906 (7.20m each) | I.CN.34.30480 | Deleted - CON - Sec.4 - Culvert : E7-SU-437414-1 - Precast stitch pours /cure
I2S-7688-MP-74.1.25.7 | Culvert ID : E7-SU-437414-1 / Type : 2*3000x3000mm RCBC / Ch19906 (7.20m each) | I.CN.34.30490 | Deleted - CON - Sec.4 - Culvert : E7-SU-437414-1 - Construct Scour Protection
I2S-7688-MP-74.1.25.7 | Culvert ID : E7-SU-437414-1 / Type : 2*3000x3000mm RCBC / Ch19906 (7.20m each) | I.CN.34.30500 | Deleted - CON - Sec.4 - Culvert : E7-SU-437414-1 - Detailed backfill
I2S-7688-MP-74.1.25.7 | Culvert ID : E7-SU-437414-1 / Type : 2*3000x3000mm RCBC / Ch19906 (7.20m each) | I.CN.34.30510 | Deleted - CON - Sec.4 - Culvert : E7-SU-437414-1 - FRP Base Slab
I2S-7688-MP-74.1.25.7 | Culvert ID : E7-SU-437414-1 / Type : 2*3000x3000mm RCBC / Ch19906 (7.20m each) | I.CN.34.30520 | Deleted - CON - Sec.4 - Culvert : E7-SU-437414-1 - 7 day Curing
I2S-7688-MP-74.1.25.7 | Culvert ID : E7-SU-437414-1 / Type : 2*3000x3000mm RCBC / Ch19906 (7.20m each) | I.CN.34.30530 | Deleted - CON - Sec.4 - Culvert : E7-SU-437414-1 - Trench Excavation / Site Prep
I2S-7688-MP-74.1.25.7 | Culvert ID : E7-SU-437414-1 / Type : 2*3000x3000mm RCBC / Ch19906 (7.20m each) | I.CN.34.30540 | Deleted - CON - Sec.4 - Culvert : E7-SU-437414-1 - Foundation Treatment
OLD |  |  |  | 2025-07-23 | 2025-09-10
Fill in Open Drains /Dams |  |  |  | 2025-09-07 | 2025-09-10
I2S-7688-MP-74.1.25.3.5 | Fill in Open Drains /Dams | I.CN.31.14590 | Deleted - CON - Sec.1 - Fill in Open Drains (Total 943 bcm) 175 per d | 2025-09-07 | 2025-09-10
General Fill H1, H2 & H3 & Replace Unsuitable |  |  |  | 2025-07-23 | 2025-08-02
I2S-7688-MP-74.1.25.3.2 | General Fill H1, H2 & H3 & Replace Unsuitable | I.CN.31.6530 | Deleted - CON - Sec.1 - Fill in RMAR - (Total 919 bcm) 500 per d RMAR Fill | 2025-07-23 | 2025-07-23
I2S-7688-MP-74.1.25.3.2 | General Fill H1, H2 & H3 & Replace Unsuitable | I.CN.31.6540 | Deleted - CON - Sec.1 - Fill in Main Alignment (Total 29,241 bcm) 2500 per d | 2025-07-24 | 2025-08-02
OLD-1 |  |  |  | 2025-08-26 | 2026-01-24
Soil |  |  |  | 2025-08-26 | 2025-10-29
I2S-7688-MP-74.1.25.12.5 | Soil | I.CN.31.6750 | Deleted - CON - Sec.2 - Cut Open Drains (8,889bcm) 175 bcm/d | 2025-08-26 | 2025-09-20
I2S-7688-MP-74.1.25.12.5 | Soil | I.CN.31.6760 | Deleted - CON - Sec.2 - Cut Soil Main Alignment (88,396bcm) 2500 bcm/d | 2025-09-21 | 2025-10-06
I2S-7688-MP-74.1.25.12.5 | Soil | I.CN.31.81240 | Deleted - CON - Sec.2 - Cut_ Unsuitable in Dam 1600bcm 500 bcm/d
I2S-7688-MP-74.1.25.12.5 | Soil | I.CN.31.6790 | Deleted - CON - Sec.2 - Cut HW to MW Sandstone (18702bcm) 2500 bcm/d | 2025-08-26 | 2025-10-26
I2S-7688-MP-74.1.25.12.5 | Soil | I.CN.31.14270 | Deleted - CON - Sec.2 - Cut_Open Drain HW to MW (138bcm) 500 bcm/d | 2025-10-27 | 2025-10-29
Fill in Open Drains /Dams |  |  |  | 2025-10-07 | 2025-11-19
I2S-7688-MP-74.1.25.12.6 | Fill in Open Drains /Dams | I.CN.31.81220 | Deleted - CON - Sec.2 - Fill Open Drains (7742bcm) 500 bcm/d | 2025-11-04 | 2025-11-19
I2S-7688-MP-74.1.25.12.6 | Fill in Open Drains /Dams | I.CN.31.81150 | Deleted - CON - Sec.2 - Fill Backfilll Dam (5428bcm) 500 bcm/d | 2025-10-07 | 2025-10-12
General Fill H1, H2 & H3 & Replace Unsuitable |  |  |  | 2025-10-12 | 2026-01-24
I2S-7688-MP-74.1.25.12.2 | General Fill H1, H2 & H3 & Replace Unsuitable | I.CN.31.14600 | Deleted - CON - Sec.2 - Fill RMAR (2242bcm) 500 bcm/d | 2025-10-12 | 2025-10-20
I2S-7688-MP-74.1.25.12.2 | General Fill H1, H2 & H3 & Replace Unsuitable | I.CN.31.6890 | Deleted - CON - Sec.2 - Fill in Main Alignment ( 75,142 bcm) 2500 bcm/d | 2025-12-04 | 2026-01-24
OLD-2 |  |  |  | 2025-08-26 | 2026-04-13
Cut |  |  |  | 2025-08-26 | 2026-02-21
I2S-7688-MP-74.1.25.4.1 | Cut | I.CN.31.7710 | Deleted - CON - Sec.3 - Cut Soil Main Alignment (Total 199,575bcm) 2,500 bcm/d PART 1 | 2025-08-26 | 2025-08-28
I2S-7688-MP-74.1.25.4.1 | Cut | I.CN.31.14370 | Deleted - CON - Sec.3 - Cut HW to MW Sandstone (Total 4,996bcm) 2,500 bcm/d | 2025-10-02 | 2025-10-03
I2S-7688-MP-74.1.25.4.1 | Cut | I.CN.31.14350 | Deleted - CON - Sec.3 - Cut Open Drains (Total 19,595bcm) 175 bcm/d PART 3 | 2025-12-06 | 2025-12-10
I2S-7688-MP-74.1.25.4.1 | Cut | I.CN.31.14360 | Deleted - CON - Sec.3 - Cut Unsuitable in Dams (Total 1,000bcm) 500 bcm/d | 2025-10-22 | 2025-11-02
I2S-7688-MP-74.1.25.4.1 | Cut | I.CN.31.7610 | Deleted - CON - Sec.3 - Cut Soil Main Alignment (Total 199,575bcm) 2,500 bcm/d PART 2 | 2026-01-18 | 2026-02-21
I2S-7688-MP-74.1.25.4.1 | Cut | I.CN.31.7670 | Deleted - CON - Sec.3 - Cut Open Drains (Total 19,595bcm) 175 bcm/d PART 2 | 2025-11-09 | 2025-12-04
I2S-7688-MP-74.1.25.4.1 | Cut | I.CN.31.7680 | Deleted - CON - Sec.3 - Cut HW Dacite (Total 62,722bcm) 2,000 bcm/d | 2025-11-03 | 2025-11-08
I2S-7688-MP-74.1.25.4.1 | Cut | I.CN.31.7690 | Deleted - CON - Sec.3 - Cut Open Drain HW to MW (Total 4,416bcm) 100 bcm/d | 2025-10-04 | 2025-10-21
I2S-7688-MP-74.1.25.4.1 | Cut | I.CN.31.7700 | Deleted - CON - Sec.3 - Cut Open Drains (Total 19,595bcm) 175 bcm/d PART 1 | 2025-08-29 | 2025-10-01
Rock |  |  |  | 2025-12-14 | 2026-04-13
I2S-7688-MP-74.1.25.4.2 | Rock | I.CN.31.7715 | Deleted - CON - Sec.3 - Cut MW Dacite (Total 44,915bcm) 2,000 bcm/d | 2025-12-14 | 2025-12-18
I2S-7688-MP-74.1.25.4.2 | Rock | I.CN.31.7770 | Deleted - CON - Sec.3 - Cut SW Dacite (Total 48,632bcm) 2,000 bcm/d (BLASTING) | 2026-04-08 | 2026-04-13
Fill in Open Drains /Dams |  |  |  | 2026-01-20 | 2026-01-23
I2S-7688-MP-74.1.25.4.5 | Fill in Open Drains /Dams | I.CN.31.15190 | Deleted - CON - Sec.3 - Fill Open Drains (Total 8,484bcm) 175 bcm/d | 2026-01-20 | 2026-01-21
I2S-7688-MP-74.1.25.4.5 | Fill in Open Drains /Dams | I.CN.31.15200 | Deleted - CON - Sec.3 - Fill Backfilll Dam (Total 5894bcm) 1000 bcm/d | 2026-01-22 | 2026-01-23
General Fill H1, H2 & H3 & Replace Unsuitable |  |  |  | 2025-10-16 | 2026-01-26
I2S-7688-MP-74.1.25.4.3 | General Fill H1, H2 & H3 & Replace Unsuitable | I.CN.31.7850 | Deleted - CON - Sec.3 - Fill in Main Alignment (Total 333,906 bcm) 2500 bcm/d PART 3 | 2025-12-20 | 2025-12-23
I2S-7688-MP-74.1.25.4.3 | General Fill H1, H2 & H3 & Replace Unsuitable | I.CN.31.7860 | Deleted - CON - Sec.3 - Fill in Main Alignment ( Total 333,906 bcm) 2500 bcm/d PART 1 | 2025-12-11 | 2025-12-19
I2S-7688-MP-74.1.25.4.3 | General Fill H1, H2 & H3 & Replace Unsuitable | I.CN.31.7880 | Deleted - CON - Sec.3 - Fill RMAR (Total 2,293bcm) 500 bcm/d | 2025-10-16 | 2025-12-10
I2S-7688-MP-74.1.25.4.3 | General Fill H1, H2 & H3 & Replace Unsuitable | I.CN.31.15230 | Deleted - CON - Sec.3 - Fill in Main Alignment (Total 333,906 bcm) 2500 bcm/d PART 2 | 2026-01-26 | 2026-01-26
OLD-3 |  |  |  | 2025-08-26 | 2026-03-18
Soil |  |  |  | 2025-08-26 | 2026-03-08
I2S-7688-MP-74.1.25.20.1 | Soil | I.CN.31.14400 | Deleted - CON - Sec.4 - Cut Open Drains (Total 19701bcm) 175bcm/d PART 3 | 2025-11-07 | 2025-11-08
I2S-7688-MP-74.1.25.20.1 | Soil | I.CN.31.8940 | Deleted - CON - Sec.4 - Cut HW Dacite (Total 34262bcm) 2000 bcm/d | 2025-09-17 | 2025-10-03
I2S-7688-MP-74.1.25.20.1 | Soil | I.CN.31.8950 | Deleted - CON - Sec.4 - Cut HW Rhyolite (Total 100517bcm) 2500bcm/d | 2025-09-09 | 2025-09-13
I2S-7688-MP-74.1.25.20.1 | Soil | I.CN.31.14500 | Deleted - CON - Sec.4 - Cut Open Drain HW to MW (Total 2337bcm) 100 bcm/d | 2025-09-14 | 2025-09-16
I2S-7688-MP-74.1.25.20.1 | Soil | I.CN.31.14510 | Deleted - CON - Sec.4 - Cut Open Drains (Total 19701bcm) 175bcm/d PART 1 | 2025-08-26 | 2025-08-27
I2S-7688-MP-74.1.25.20.1 | Soil | I.CN.31.6120 | Deleted - CON - Sec.4 - Cut Open Drains (Total 19701bcm) 175bcm/d PART 2 | 2025-10-22 | 2025-11-06
I2S-7688-MP-74.1.25.20.1 | Soil | I.CN.31.8870 | Deleted - CON - Sec.4 - Cut Soil Main Alignment (Total 241,218bcm) 2500bcm/d PART 2 | 2025-12-04 | 2026-03-08
I2S-7688-MP-74.1.25.20.1 | Soil | I.CN.31.8960 | Deleted - CON - Sec.4 - Cut Soil Main Alignment (Total 241,218bcm) 2500bcm/d PART 1 | 2025-08-28 | 2025-09-08
I2S-7688-MP-74.1.25.20.1 | Soil | I.CN.31.14390 | Deleted - CON - Sec.4 - Cut Unsuitable in Dams (Total 3400bcm) 500 bcm/d | 2025-08-26 | 2025-08-26
Rock |  |  |  | 2025-09-09 | 2025-10-03
I2S-7688-MP-74.1.25.20.2 | Rock | I.CN.31.9070 | Deleted - CON - Sec.4 - Cut MW Dacite (Total 46790bcm) 2000 bcm/d | 2025-09-26 | 2025-10-03
I2S-7688-MP-74.1.25.20.2 | Rock | I.CN.31.9080 | Deleted - CON - Sec.4 - Cut SW Dacite (Total 71993bcm) 1250 bcm/d Blasting | 2025-09-09 | 2025-09-24
Fill in Open Drains /Dams |  |  |  | 2026-01-24 | 2026-03-18
I2S-7688-MP-74.1.25.20.5 | Fill in Open Drains /Dams | I.CN.31.14750 | Deleted - CON - Sec.4 - Fill Open Drains (Total 6586bcm) 175 bcm/d | 2026-01-24 | 2026-01-24
I2S-7688-MP-74.1.25.20.5 | Fill in Open Drains /Dams | I.CN.31.14950 | Deleted - CON - Sec.4 - Fill Backfilll Dam (Total 7158bcm) 1000 bcm/d | 2026-03-11 | 2026-03-18
Gen Fill (Roads) |  |  |  | 2026-01-05 | 2026-01-05
I2S-7688-MP-74.1.25.20.3 | Gen Fill (Roads) | I.CN.31.9170 | Deleted - CON - Sec.4 - Fill Rd Fill (Total 1417bcm) 500bcm/d | 2026-01-05 | 2026-01-05
General Fill H1, H2 & H3 inc RMAR & replace unsuitable |  |  |  | 2025-09-02 | 2025-12-21
I2S-7688-MP-74.1.25.20.4 | General Fill H1, H2 & H3 inc RMAR & replace unsuitable | I.CN.31.9290 | Deleted - CON - Sec.4 - Fill in Main Alignment (Total 442,273 bcm) 2500 bcm/d PART 3 | 2025-09-17 | 2025-10-27
I2S-7688-MP-74.1.25.20.4 | General Fill H1, H2 & H3 inc RMAR & replace unsuitable | I.CN.31.9310 | Deleted - CON - Sec.4 - Fill in Main Alignment (Total 442,273 bcm) 2500 bcm/d PART 2 | 2025-09-02 | 2025-09-16
I2S-7688-MP-74.1.25.20.4 | General Fill H1, H2 & H3 inc RMAR & replace unsuitable | I.CN.31.9320 | Deleted - CON - Sec.4 - Fill in Main Alignment (Total 442,273 bcm) 2500 bcm/d PART 1 | 2025-09-18 | 2025-11-16
I2S-7688-MP-74.1.25.20.4 | General Fill H1, H2 & H3 inc RMAR & replace unsuitable | I.CN.31.9180 | Deleted - CON - Sec.4 - Fill RMAR (Total 5819bcm) 500 bcm/d | 2025-12-11 | 2025-12-21
OLD-4 |  |  |  | 2025-08-26 | 2026-04-08
Soil |  |  |  | 2025-08-26 | 2025-09-16
I2S-7688-MP-74.1.25.17.1 | Soil | I.CN.31.10519 | Deleted - CON - Sec.5 - Cut Open Drains (Total 6551bcm) 175 bcm/d | 2025-08-26 | 2025-08-28
I2S-7688-MP-74.1.25.17.1 | Soil | I.CN.31.10530 | Deleted - CON - Sec.5 - Cut Open Drain HW to MW (Total 185bcm) 100 bcm/d | 2025-09-02 | 2025-09-03
I2S-7688-MP-74.1.25.17.1 | Soil | I.CN.31.10540 | Deleted - CON - Sec.5 - Cut Unsuitable in Dams (Total 4900bcm) 500 bcm/d | 2025-09-10 | 2025-09-14
I2S-7688-MP-74.1.25.17.1 | Soil | I.CN.31.10550 | Deleted - CON - Sec.5 - Cut HW Dacite (Total 855bcm) 2000 bcm/d | 2025-09-16 | 2025-09-16
I2S-7688-MP-74.1.25.17.1 | Soil | I.CN.31.14520 | Deleted - CON - Sec.5 - Cut Soil Main Alignment (Total 22821bcm) 2500 bcm/d | 2025-08-29 | 2025-09-01
Fill in Open Drains /Dams |  |  |  | 2025-09-17 | 2026-04-08
I2S-7688-MP-74.1.25.17.5 | Fill in Open Drains /Dams | I.CN.31.10620 | Deleted - CON - Sec.5 - Fill Rd Fill (Total 525bcm) 500 bcm/d | 2025-09-17 | 2025-09-17
I2S-7688-MP-74.1.25.17.5 | Fill in Open Drains /Dams | I.CN.31.14620 | Deleted - CON - Sec.5 - Fill Open Drains (Total 1219bcm) 175 bcm/d | 2026-03-29 | 2026-03-29
I2S-7688-MP-74.1.25.17.5 | Fill in Open Drains /Dams | I.CN.31.14640 | Deleted - CON - Sec.5 - Fill Backfilll Dam (Total 10316bcm) 1000 bcm/d | 2026-04-08 | 2026-04-08
General Fill H1, H2 & H3 & Replace Unsuitable |  |  |  | 2025-08-30 | 2025-11-11
I2S-7688-MP-74.1.25.17.3 | General Fill H1, H2 & H3 & Replace Unsuitable | I.CN.31.10670 | Deleted - CON - Sec.5 - Fill in Main Alignment (Total 269,218 bcm) 2500 bcm/d PART 1 | 2025-08-31 | 2025-11-09
I2S-7688-MP-74.1.25.17.3 | General Fill H1, H2 & H3 & Replace Unsuitable | I.CN.31.10680 | Deleted - CON - Sec.5 - Fill in Main Alignment (Total 269,218 bcm) 2500 bcm/d PART 3 | 2025-11-11 | 2025-11-11
I2S-7688-MP-74.1.25.17.3 | General Fill H1, H2 & H3 & Replace Unsuitable | I.CN.31.15260 | Deleted - CON - Sec.5 - Fill in Main Alignment (Total 269,218 bcm) 2500 bcm/d PART 2 | 2025-11-10 | 2025-11-10
I2S-7688-MP-74.1.25.17.3 | General Fill H1, H2 & H3 & Replace Unsuitable | I.CN.31.10660 | Deleted - CON - Sec.5 - Fill RMAR (Total 8921bcm) 500 bcm/d | 2025-08-30 | 2025-08-30
OLD-5 |  |  |  | 2025-09-13 | 2026-11-06
Soil |  |  |  | 2025-09-13 | 2026-11-06
I2S-7688-MP-74.1.25.1.1 | Soil | I.CN.31.14020 | Deleted - CON - Sec.6 - Cut Soil Main Alignment (Total 22,5637bcm) 2,500 bcm/d PART 1 | 2025-10-02 | 2025-10-03
I2S-7688-MP-74.1.25.1.1 | Soil | I.CN.31.14030 | Deleted - CON - Sec.6 - Cut Road Soil (Total 20,600bcm) 500 bcm/d | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.25.1.1 | Soil | I.CN.31.14040 | Deleted - CON - Sec.6 - Cut Open Drain HW to MW (Total 119bcm) 100 bcm/d | 2025-10-04 | 2025-10-04
I2S-7688-MP-74.1.25.1.1 | Soil | I.CN.31.11420 | Deleted - CON - Sec.6 - Cut MW Meta SS (Total 25,714bcm) 2,000 bcm/d | 2026-11-04 | 2026-11-06
I2S-7688-MP-74.1.25.1.1 | Soil | I.CN.31.11450 | Deleted - CON - Sec.6 - Cut HW Meta SS (Total 59,994bcm) 2,000 bcm/d | 2025-09-13 | 2025-11-28
I2S-7688-MP-74.1.25.1.1 | Soil | I.CN.31.12810 | Deleted - CON - Sec.6 - Cut Open Drains (Total 4,585bcm) 175 bcm/d | 2025-09-29 | 2025-10-01
I2S-7688-MP-74.1.25.1.1 | Soil | I.CN.31.12830 | Deleted - CON - Sec.6 - Cut Unsuitable in Dams (Total 2,000bcm) 500 bcm/d | 2025-10-02 | 2025-10-04
I2S-7688-MP-74.1.25.1.1 | Soil | I.CN.31.12820 | Deleted - CON - Sec.6 - Cut Soil Main Alignment (Total 22,5637bcm) 2,500 bcm/d PART 2 | 2025-10-06 | 2025-10-10
Rock |  |  |  | 2025-10-30 | 2025-12-14
I2S-7688-MP-74.1.25.1.2 | Rock | I.CN.31.11460 | Deleted - CON - Sec.6 - Cut HW Dacite (BGW E) (Total 275bcm) 2,000 bcm/d | 2025-10-30 | 2025-12-14
Fill in Open Drains /Dams |  |  |  | 2026-01-06 | 2026-01-08
I2S-7688-MP-74.1.25.1.5 | Fill in Open Drains /Dams | I.CN.31.81230 | Deleted - CON - Sec.6 - Fill Backfilll Dam (Total 4038bcm) 500 bcm/d
I2S-7688-MP-74.1.25.1.5 | Fill in Open Drains /Dams | I.CN.31.15210 | Deleted - CON - Sec.6 - Fill Open Drains (Total 2182bcm) 175 bcm/d | 2026-01-06 | 2026-01-08
General Fill H1, H2 & H3 & Replace Unsuitable |  |  |  | 2025-10-04 | 2025-10-06
I2S-7688-MP-74.1.25.1.3 | General Fill H1, H2 & H3 & Replace Unsuitable | I.CN.31.14050 | Deleted - CON - Sec.6 - Fill in Main Alignment (Total 24,302bcm) 2500 bcm/d | 2025-10-04 | 2025-10-06
Culvert ID : E7-SU-444500-1 / Type : 1*3000x3000mm RCBC / Ch26948 (14.40m each)
I2S-7688-MP-74.1.25.14 | Culvert ID : E7-SU-444500-1 / Type : 1*3000x3000mm RCBC / Ch26948 (14.40m each) | I.CN.34.29860 | Deleted - CON - Sec.4 - Culvert : E7-SU-444500-1 - FRP Base Slab
I2S-7688-MP-74.1.25.14 | Culvert ID : E7-SU-444500-1 / Type : 1*3000x3000mm RCBC / Ch26948 (14.40m each) | I.CN.34.29870 | Deleted - CON - Sec.4 - Culvert : E7-SU-444500-1 - 7 day Curing
I2S-7688-MP-74.1.25.14 | Culvert ID : E7-SU-444500-1 / Type : 1*3000x3000mm RCBC / Ch26948 (14.40m each) | I.CN.34.29880 | Deleted - CON - Sec.4 - Culvert : E7-SU-444500-1 - Trench Excavation / Site Prep
I2S-7688-MP-74.1.25.14 | Culvert ID : E7-SU-444500-1 / Type : 1*3000x3000mm RCBC / Ch26948 (14.40m each) | I.CN.34.29890 | Deleted - CON - Sec.4 - Culvert : E7-SU-444500-1 - Foundation Treatment
I2S-7688-MP-74.1.25.14 | Culvert ID : E7-SU-444500-1 / Type : 1*3000x3000mm RCBC / Ch26948 (14.40m each) | I.CN.34.29900 | Deleted - CON - Sec.4 - Culvert : E7-SU-444500-1 - Place RCBC crown units
I2S-7688-MP-74.1.25.14 | Culvert ID : E7-SU-444500-1 / Type : 1*3000x3000mm RCBC / Ch26948 (14.40m each) | I.CN.34.29910 | Deleted - CON - Sec.4 - Culvert : E7-SU-444500-1 - Place Precast Wingwall
I2S-7688-MP-74.1.25.14 | Culvert ID : E7-SU-444500-1 / Type : 1*3000x3000mm RCBC / Ch26948 (14.40m each) | I.CN.34.29920 | Deleted - CON - Sec.4 - Culvert : E7-SU-444500-1 - Precast stitch pours /cure
I2S-7688-MP-74.1.25.14 | Culvert ID : E7-SU-444500-1 / Type : 1*3000x3000mm RCBC / Ch26948 (14.40m each) | I.CN.34.29930 | Deleted - CON - Sec.4 - Culvert : E7-SU-444500-1 - Construct Scour Protection
I2S-7688-MP-74.1.25.14 | Culvert ID : E7-SU-444500-1 / Type : 1*3000x3000mm RCBC / Ch26948 (14.40m each) | I.CN.34.29940 | Deleted - CON - Sec.4 - Culvert : E7-SU-444500-1 - Detailed backfill
Culvert ID : E7-SU-443400-1 / Type : 1*3000x3000mm RCBC / Ch25891 (16.800m)
I2S-7688-MP-74.1.25.2 | Culvert ID : E7-SU-443400-1 / Type : 1*3000x3000mm RCBC / Ch25891 (16.800m) | I.CN.34.29950 | Deleted - CON - Sec.4 - Culvert : E7-SU-443400-1 - FRP Base Slab
I2S-7688-MP-74.1.25.2 | Culvert ID : E7-SU-443400-1 / Type : 1*3000x3000mm RCBC / Ch25891 (16.800m) | I.CN.34.29960 | Deleted - CON - Sec.4 - Culvert : E7-SU-443400-1 - 7 day Curing
I2S-7688-MP-74.1.25.2 | Culvert ID : E7-SU-443400-1 / Type : 1*3000x3000mm RCBC / Ch25891 (16.800m) | I.CN.34.29970 | Deleted - CON - Sec.4 - Culvert : E7-SU-443400-1 - Trench Excavation / Site Prep
I2S-7688-MP-74.1.25.2 | Culvert ID : E7-SU-443400-1 / Type : 1*3000x3000mm RCBC / Ch25891 (16.800m) | I.CN.34.29980 | Deleted - CON - Sec.4 - Culvert : E7-SU-443400-1 - Foundation Treatment
I2S-7688-MP-74.1.25.2 | Culvert ID : E7-SU-443400-1 / Type : 1*3000x3000mm RCBC / Ch25891 (16.800m) | I.CN.34.29990 | Deleted - CON - Sec.4 - Culvert : E7-SU-443400-1 - Place RCBC crown units
I2S-7688-MP-74.1.25.2 | Culvert ID : E7-SU-443400-1 / Type : 1*3000x3000mm RCBC / Ch25891 (16.800m) | I.CN.34.30000 | Deleted - CON - Sec.4 - Culvert : E7-SU-443400-1 - Place Precast Wingwall
I2S-7688-MP-74.1.25.2 | Culvert ID : E7-SU-443400-1 / Type : 1*3000x3000mm RCBC / Ch25891 (16.800m) | I.CN.34.30010 | Deleted - CON - Sec.4 - Culvert : E7-SU-443400-1 - Precast stitch pours /cure
I2S-7688-MP-74.1.25.2 | Culvert ID : E7-SU-443400-1 / Type : 1*3000x3000mm RCBC / Ch25891 (16.800m) | I.CN.34.30020 | Deleted - CON - Sec.4 - Culvert : E7-SU-443400-1 - Construct Scour Protection
I2S-7688-MP-74.1.25.2 | Culvert ID : E7-SU-443400-1 / Type : 1*3000x3000mm RCBC / Ch25891 (16.800m) | I.CN.34.30030 | Deleted - CON - Sec.4 - Culvert : E7-SU-443400-1 - Detailed backfill
Culvert ID : E7-SU-440914-1 / Type : 1*3000x3000mm RCBC / Ch23406 (7.200m)
I2S-7688-MP-74.1.25.5 | Culvert ID : E7-SU-440914-1 / Type : 1*3000x3000mm RCBC / Ch23406 (7.200m) | I.CN.34.30250 | Deleted - CON - Sec.4 - Culvert : E7-SU-440914-1 - FRP Base Slab
I2S-7688-MP-74.1.25.5 | Culvert ID : E7-SU-440914-1 / Type : 1*3000x3000mm RCBC / Ch23406 (7.200m) | I.CN.34.30260 | Deleted - CON - Sec.4 - Culvert : E7-SU-440914-1 - 7 day Curing
I2S-7688-MP-74.1.25.5 | Culvert ID : E7-SU-440914-1 / Type : 1*3000x3000mm RCBC / Ch23406 (7.200m) | I.CN.34.30270 | Deleted - CON - Sec.4 - Culvert : E7-SU-440914-1 - Trench Excavation / Site Prep
I2S-7688-MP-74.1.25.5 | Culvert ID : E7-SU-440914-1 / Type : 1*3000x3000mm RCBC / Ch23406 (7.200m) | I.CN.34.30280 | Deleted - CON - Sec.4 - Culvert : E7-SU-440914-1 - Foundation Treatment
I2S-7688-MP-74.1.25.5 | Culvert ID : E7-SU-440914-1 / Type : 1*3000x3000mm RCBC / Ch23406 (7.200m) | I.CN.34.30200 | Deleted - CON - Sec.4 - Culvert : E7-SU-440914-1 - Place RCBC crown units
I2S-7688-MP-74.1.25.5 | Culvert ID : E7-SU-440914-1 / Type : 1*3000x3000mm RCBC / Ch23406 (7.200m) | I.CN.34.30210 | Deleted - CON - Sec.4 - Culvert : E7-SU-440914-1 - Place Precast Wingwall
I2S-7688-MP-74.1.25.5 | Culvert ID : E7-SU-440914-1 / Type : 1*3000x3000mm RCBC / Ch23406 (7.200m) | I.CN.34.30220 | Deleted - CON - Sec.4 - Culvert : E7-SU-440914-1 - Precast stitch pours /cure
I2S-7688-MP-74.1.25.5 | Culvert ID : E7-SU-440914-1 / Type : 1*3000x3000mm RCBC / Ch23406 (7.200m) | I.CN.34.30230 | Deleted - CON - Sec.4 - Culvert : E7-SU-440914-1 - Construct Scour Protection
I2S-7688-MP-74.1.25.5 | Culvert ID : E7-SU-440914-1 / Type : 1*3000x3000mm RCBC / Ch23406 (7.200m) | I.CN.34.30240 | Deleted - CON - Sec.4 - Culvert : E7-SU-440914-1 - Detailed backfill
Deleted Activities Possessions post 24/10/2025 |  |  |  | 2025-03-03 | 2026-06-01
Design Stage 2 - Preliminary Design - PDD |  |  |  | 2025-03-03 | 2025-04-22
I2S-7688-MP-74.1.28.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.16600 | Deleted - Issue Responses & Receive Comment Closeout - L5 - Stage 2
I2S-7688-MP-74.1.28.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.16610 | Deleted - Submission to IRPL - L5 - Stage 2
I2S-7688-MP-74.1.28.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.16620 | Deleted - IRPL Review (20 B.days) - L5 - Stage 2
I2S-7688-MP-74.1.28.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.16820 | Deleted - Internal IDR Review (By JHG) - L5 - Stage 2 (Modified)
I2S-7688-MP-74.1.28.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.16830 | Deleted - Design Presentation to IRPL - DPK Presentation L5 - Stage 2 (Modified already part of original
I2S-7688-MP-74.1.28.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.3690 | Deleted - Design Development - Stage 2 - Preliminary Design / PDD -Landscape - L5 - Stage 2 | 2025-03-03 | 2025-04-22
I2S-7688-MP-74.1.28.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-L5 | Deleted - Cost PDD L5
I2S-7688-MP-74.1.28.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.16450 | Deleted - Safety Assurance / SiD - L5 - Stage 1
I2S-7688-MP-74.1.28.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.16560 | Deleted - Internal IDR workshop (By BGE) - L5 - Stage 2
I2S-7688-MP-74.1.28.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.16580 | Deleted - Review of IDR comment response and final review - L5 - Stage 2
I2S-7688-MP-74.1.28.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.16590 | Deleted - Incorporate IDR comments - L5 - Stage 2
Culvert ID : E7-RD-439940-1 / Type : 3*600x300mm RCBC / Ch22427 |  |  |  | 2026-01-17 | 2026-02-08
I2S-7688-MP-74.1.28.26 | Culvert ID : E7-RD-439940-1 / Type : 3*600x300mm RCBC / Ch22427 | I.CN.34.28540 | Deleted - CON - Sec.4 - Culvert ID : E7-RD-439940-1 - Place RCBC crown units
I2S-7688-MP-74.1.28.26 | Culvert ID : E7-RD-439940-1 / Type : 3*600x300mm RCBC / Ch22427 | I.CN.34.21390 | Deleted - CON - Sec.4 - Culvert ID : E7-RD-439940-1 - Trench Excavation / Site Prep | 2026-01-17 | 2026-01-18
I2S-7688-MP-74.1.28.26 | Culvert ID : E7-RD-439940-1 / Type : 3*600x300mm RCBC / Ch22427 | I.CN.34.21400 | Deleted - CON - Sec.4 - Culvert ID : E7-RD-439940-1 - Foundation Treatment / Bedding | 2026-01-19 | 2026-01-20
I2S-7688-MP-74.1.28.26 | Culvert ID : E7-RD-439940-1 / Type : 3*600x300mm RCBC / Ch22427 | I.CN.34.21440 | Deleted - CON - Sec.4 - Culvert ID : E7-RD-439940-1 - FRP Base Slab | 2026-01-21 | 2026-01-31
I2S-7688-MP-74.1.28.26 | Culvert ID : E7-RD-439940-1 / Type : 3*600x300mm RCBC / Ch22427 | I.CN.34.21450 | Deleted - CON - Sec.4 - Culvert ID : E7-RD-439940-1 - 7 day Curing | 2026-02-01 | 2026-02-02
I2S-7688-MP-74.1.28.26 | Culvert ID : E7-RD-439940-1 / Type : 3*600x300mm RCBC / Ch22427 | I.CN.34.21470 | Deleted - CON - Sec.4 - Culvert ID : E7-RD-439940-1 - Place Precast Wingwall | 2026-02-03 | 2026-02-04
I2S-7688-MP-74.1.28.26 | Culvert ID : E7-RD-439940-1 / Type : 3*600x300mm RCBC / Ch22427 | I.CN.34.21480 | Deleted - CON - Sec.4 - Culvert ID : E7-RD-439940-1 - Precast stitch pours for precast headwalls | 2026-02-06 | 2026-02-06
I2S-7688-MP-74.1.28.26 | Culvert ID : E7-RD-439940-1 / Type : 3*600x300mm RCBC / Ch22427 | I.CN.34.21490 | Deleted - CON - Sec.4 - Culvert ID : E7-RD-439940-1 - Construct Scour Protection | 2026-02-07 | 2026-02-07
I2S-7688-MP-74.1.28.26 | Culvert ID : E7-RD-439940-1 / Type : 3*600x300mm RCBC / Ch22427 | I.CN.34.21500 | Deleted - CON - Sec.4 - Culvert ID : E7-RD-439940-1 - Detailed backfill | 2026-02-07 | 2026-02-08
Culvert ID : E7-RA-436010-1 / Type : 1*600mm HDPE / Ch18510 |  |  |  | 2026-04-24 | 2026-05-08
I2S-7688-MP-74.1.28.25 | Culvert ID : E7-RA-436010-1 / Type : 1*600mm HDPE / Ch18510 | I.CN.34.21010 | Deleted - CON - Sec.4 - Culvert ID : E7-RA-436010-1 - Construct Scour Protection | 2026-05-07 | 2026-05-07
I2S-7688-MP-74.1.28.25 | Culvert ID : E7-RA-436010-1 / Type : 1*600mm HDPE / Ch18510 | I.CN.34.21020 | Deleted - CON - Sec.4 - Culvert ID : E7-RA-436010-1 - Detailed backfill | 2026-05-07 | 2026-05-08
I2S-7688-MP-74.1.28.25 | Culvert ID : E7-RA-436010-1 / Type : 1*600mm HDPE / Ch18510 | I.CN.34.20910 | Deleted - CON - Sec.4 - Culvert ID : E7-RA-436010-1 - Trench Excavation / Site Prep | 2026-04-24 | 2026-04-26
I2S-7688-MP-74.1.28.25 | Culvert ID : E7-RA-436010-1 / Type : 1*600mm HDPE / Ch18510 | I.CN.34.20920 | Deleted - CON - Sec.4 - Culvert ID : E7-RA-436010-1 - Foundation Treatment / Bedding | 2026-04-27 | 2026-04-28
I2S-7688-MP-74.1.28.25 | Culvert ID : E7-RA-436010-1 / Type : 1*600mm HDPE / Ch18510 | I.CN.34.20960 | Deleted - CON - Sec.4 - Culvert ID : E7-RA-436010-1 - Place HDPE Pipe | 2026-04-29 | 2026-05-01
I2S-7688-MP-74.1.28.25 | Culvert ID : E7-RA-436010-1 / Type : 1*600mm HDPE / Ch18510 | I.CN.34.20970 | Deleted - CON - Sec.4 - Culvert ID : E7-RA-436010-1 - Backfill Pipe | 2026-05-02 | 2026-05-02
I2S-7688-MP-74.1.28.25 | Culvert ID : E7-RA-436010-1 / Type : 1*600mm HDPE / Ch18510 | I.CN.34.20990 | Deleted - CON - Sec.4 - Culvert ID : E7-RA-436010-1 - Place Precast Wingwall | 2026-05-03 | 2026-05-04
I2S-7688-MP-74.1.28.25 | Culvert ID : E7-RA-436010-1 / Type : 1*600mm HDPE / Ch18510 | I.CN.34.21000 | Deleted - CON - Sec.4 - Culvert ID : E7-RA-436010-1 - Precast stitch pours for precast headwalls | 2026-05-05 | 2026-05-06
Culvert -(019835) - 1200 RCP - 14m Delete |  |  |  | 2026-05-29 | 2026-06-01
I2S-7688-MP-74.1.28.2 | Culvert -(019835) - 1200 RCP - 14m Delete | I.CN.65.17530 | Deleted - Sec.4 - Private LX - PR19835 - Drainage - LX Culvert - Trench Excavation / Site Prep | 2026-05-29 | 2026-05-30
I2S-7688-MP-74.1.28.2 | Culvert -(019835) - 1200 RCP - 14m Delete | I.CN.65.17540 | Deleted - Sec.4 - Private LX - PR19835 - Drainage - Place RCP Pipe | 2026-05-31 | 2026-05-31
I2S-7688-MP-74.1.28.2 | Culvert -(019835) - 1200 RCP - 14m Delete | I.CN.65.17550 | Deleted - Sec.4 - Private LX - PR19835 - Drainage - Detailed backfill | 2026-06-01 | 2026-06-01
Culvert - PR21200-03 - 3*600 HDPE - 43.92m Delete |  |  |  | 2026-05-03 | 2026-05-06
I2S-7688-MP-74.1.28.9 | Culvert - PR21200-03 - 3*600 HDPE - 43.92m Delete | I.CN.65.14230 | Deleted - Sec.4 - Private LX - PR21216 - Drainage - LX Culvert - Trench Excavation / Site Prep | 2026-05-03 | 2026-05-04
I2S-7688-MP-74.1.28.9 | Culvert - PR21200-03 - 3*600 HDPE - 43.92m Delete | I.CN.65.14240 | Deleted - Sec.4 - Private LX - PR21216 - Drainage - Install 600 HDPE - 3 no's | 2026-05-05 | 2026-05-05
I2S-7688-MP-74.1.28.9 | Culvert - PR21200-03 - 3*600 HDPE - 43.92m Delete | I.CN.65.14250 | Deleted - Sec.4 - Private LX - PR21216 - Drainage - Detailed backfill | 2026-05-06 | 2026-05-06
Culvert - PR22750-01 - 1 x 2.4W x 0.9H RCBC - 12m Delete |  |  |  | 2026-05-12 | 2026-05-19
I2S-7688-MP-74.1.28.4 | Culvert - PR22750-01 - 1 x 2.4W x 0.9H RCBC - 12m Delete | I.CN.65.17500 | Deleted - Sec.4 - Private LX - PR22426 - Drainage - LX Culvert - Trench Excavation / Site Prep | 2026-05-12 | 2026-05-12
I2S-7688-MP-74.1.28.4 | Culvert - PR22750-01 - 1 x 2.4W x 0.9H RCBC - 12m Delete | I.CN.65.17510 | Deleted - Sec.4 - Private LX - PR22426 - Drainage - Place RCP Pipe | 2026-05-13 | 2026-05-13
I2S-7688-MP-74.1.28.4 | Culvert - PR22750-01 - 1 x 2.4W x 0.9H RCBC - 12m Delete | I.CN.65.17520 | Deleted - Sec.4 - Private LX - PR22426 - Drainage - Detailed backfill | 2026-05-19 | 2026-05-19
Shutdown 2 - XO/TO Install - March 2026 |  |  |  | 2026-01-13 | 2026-03-16
I2S-7688-MP-74.1.28.20 | Shutdown 2 - XO/TO Install - March 2026 | I.CN.50.20070 | Deleted - Sec.1 - Target Readiness for Possession (March 2026)
I2S-7688-MP-74.1.28.20 | Shutdown 2 - XO/TO Install - March 2026 | I.CN.50.14560 | Deleted - Sec.1 - Possession Commencement (March 2026) | 2026-03-14 | 2026-03-16
I2S-7688-MP-74.1.28.20 | Shutdown 2 - XO/TO Install - March 2026 | I.CN.50.17870 | Deleted - Sec.1 - Float before Possession (March 2026) | 2026-01-13 | 2026-03-13
Rail Safety - Take out |  |  |  | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.1 | Rail Safety - Take out | I.CN.50.14580 | Deleted - Sec.1 - Prestart safe working team | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.1 | Rail Safety - Take out | I.CN.50.14590 | Deleted - Sec.1 - PO's into position (Mar 26) | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.1 | Rail Safety - Take out | I.CN.50.14600 | Deleted - Sec.1 - Take LPA and confirm with Control (Mar 26) | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.1 | Rail Safety - Take out | I.CN.50.14610 | Deleted - Sec.1 - Activity PO's briefed by PPO (Mar 26) | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.1 | Rail Safety - Take out | I.CN.50.14620 | Deleted - Sec.1 - Work Parties briefed by PO's (Mar 26) | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.1 | Rail Safety - Take out | I.CN.50.14630 | Deleted - Sec.1 - Mar 2026 Work commences - Sec.1 | 2026-03-14
I2S-7688-MP-74.1.28.20.1 | Rail Safety - Take out | I.CN.50.14880 | Deleted - Sec.1 - Bring track machines into LPA (Mar 26) | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.1 | Rail Safety - Take out | I.CN.50.14550 | Deleted - Sec.1 - Take out Sec.1 - March 2026 | 2026-03-14
Survey |  |  |  | 2026-03-14 | 2026-03-15
I2S-7688-MP-74.1.28.20.3 | Survey | I.CN.50.14930 | Deleted - Sec.1 - GEDO Up Main for tamping (Mar 26) | 2026-03-14 | 2026-03-15
I2S-7688-MP-74.1.28.20.3 | Survey | I.CN.50.14950 | Deleted - Sec.1 - GEDO Crossover for tamping - 1 (Mar 26) | 2026-03-15 | 2026-03-15
I2S-7688-MP-74.1.28.20.3 | Survey | I.CN.50.14890 | Deleted - Sec.1 - GEDO Dn Main for tamping | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.3 | Survey | I.CN.50.14910 | Deleted - Sec.1 - GEDO Crossover for tamping | 2026-03-15 | 2026-03-15
I2S-7688-MP-74.1.28.20.3 | Survey | I.CN.50.14650 | Deleted - Sec.1 - Mark out track panels for new turnouts to be cut - Turnout - 1 in 18 R1200 (Ilabo) | 2026-03-14 | 2026-03-14
Track |  |  |  | 2026-03-14 | 2026-03-16
I2S-7688-MP-74.1.28.20.4 | Track | I.CN.50.14870 | Deleted - Sec.1 - Place ballast for tamping I2S spur | 2026-03-15 | 2026-03-15
I2S-7688-MP-74.1.28.20.4 | Track | I.CN.50.15030 | Deleted - Sec.1 - Destress Module 01 | 2026-03-15 | 2026-03-15
I2S-7688-MP-74.1.28.20.4 | Track | I.CN.50.15040 | Deleted - Sec.1 - Destress Module 02 | 2026-03-15 | 2026-03-15
I2S-7688-MP-74.1.28.20.4 | Track | I.CN.50.15050 | Deleted - Sec.1 - Destress Module 03 | 2026-03-15 | 2026-03-16
I2S-7688-MP-74.1.28.20.4 | Track | I.CN.50.15060 | Deleted - Sec.1 - Destress Module 04 | 2026-03-15 | 2026-03-16
Up |  |  |  | 2026-03-14 | 2026-03-16
I2S-7688-MP-74.1.28.20.4.1 | Up | I.CN.50.19120 | Deleted - Sec.1 - Deliver - 6 rail short wagons of rails for Illabo end of I2S | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.4.1 | Up | I.CN.50.14690 | Deleted - Sec.1 - Slew Up main line track using excavator | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.4.1 | Up | I.CN.50.14830 | Deleted - Sec.1 - Install closure panel as required Up Mn T/O | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.4.1 | Up | I.CN.50.14860 | Deleted - Sec.1 - Place ballast for tamping Up Mn T/O | 2026-03-15 | 2026-03-15
I2S-7688-MP-74.1.28.20.4.1 | Up | I.CN.50.15090 | Deleted - Sec.1 - Up Main Corrections - 178 - 374 - mar 26 | 2026-03-16 | 2026-03-16
Dn |  |  |  | 2026-03-14 | 2026-03-16
I2S-7688-MP-74.1.28.20.4.2 | Dn | I.CN.50.14820 | Deleted - Sec.1 - Install closure panel as required Up Mn X over | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.4.2 | Dn | I.CN.50.14840 | Deleted - Sec.1 - Install closure panel as required Dn Mn | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.4.2 | Dn | I.CN.50.14850 | Deleted - Sec.1 - Place ballast for tamping X Over | 2026-03-14 | 2026-03-15
I2S-7688-MP-74.1.28.20.4.2 | Dn | I.CN.50.15100 | Deleted - Sec.1 - Dn Main Corrections - 178 - 374 - mar 26 | 2026-03-16 | 2026-03-16
I2S-7688-MP-74.1.28.20.4.2 | Dn | I.CN.50.14700 | Deleted - Sec.1 - Slew Dn main line track using excavator | 2026-03-14 | 2026-03-14
Crossover |  |  |  | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.4.3 | Crossover | I.CN.50.14760 | Deleted - Sec.1 - Crossover - Install bottom ballast and geo - 1 | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.4.3 | Crossover | I.CN.50.14660 | Deleted - Sec.1 - Crossover - Cut Track panels and remove | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.4.3 | Crossover | I.CN.50.14670 | Deleted - Sec.1 - Crossover - Cut Track panels and remove -1 | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.4.3 | Crossover | I.CN.50.14710 | Deleted - Sec.1 - Crossover - Grade out old ballast - 1 | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.4.3 | Crossover | I.CN.50.14720 | Deleted - Sec.1 - Crossover 18.5 R1200 - Proof roll formation - 1 | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.4.3 | Crossover | I.CN.50.14730 | Deleted - Sec.1 - Crossover - Install bottom ballast and geo | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.4.3 | Crossover | I.CN.50.14740 | Deleted - Sec.1 - Crossover - Grade out old ballast | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.4.3 | Crossover | I.CN.50.14750 | Deleted - Sec.1 - Crossover 18.5 R1200 - Proof roll formation | 2026-03-14 | 2026-03-14
turnout |  |  |  | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.4.4 | turnout | I.CN.50.14680 | Deleted - Sec.1 - Possession -Turnout - 1 in 18 R1200 (Ilabo) - Cut Track panels and remove | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.4.4 | turnout | I.CN.50.14780 | Deleted - Sec.1 - Possession -Turnout - 1 in 18 R1200 (Ilabo) - Grade out old ballast | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.4.4 | turnout | I.CN.50.14790 | Deleted - Sec.1 - Possession -Turnout - 1 in 18 R1200 (Ilabo) - Proof roll formation | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.4.4 | turnout | I.CN.50.14800 | Deleted - Sec.1 - Possession -Turnout - 1 in 18 R1200 (Ilabo) - Install bottom ballast and geo | 2026-03-14 | 2026-03-14
S&C |  |  |  | 2026-03-14 | 2026-03-16
I2S-7688-MP-74.1.28.20.2 | S&C | I.CN.50.14640 | Deleted - Sec.1 - Disconnect any signalling infrastructure identified as required | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.2 | S&C | I.CN.50.14970 | Deleted - Sec.1 - Weld out T/O 01 inc panels | 2026-03-15 | 2026-03-15
I2S-7688-MP-74.1.28.20.2 | S&C | I.CN.50.14980 | Deleted - Sec.1 - Turnout 01 S&C installation | 2026-03-15 | 2026-03-15
I2S-7688-MP-74.1.28.20.2 | S&C | I.CN.50.14990 | Deleted - Sec.1 - Weld out T/O 02 inc panels | 2026-03-15 | 2026-03-15
I2S-7688-MP-74.1.28.20.2 | S&C | I.CN.50.15000 | Deleted - Sec.1 - Turnout 02 S&C installation | 2026-03-15 | 2026-03-15
I2S-7688-MP-74.1.28.20.2 | S&C | I.CN.50.15010 | Deleted - Sec.1 - Weld out T/O 03 inc panels | 2026-03-15 | 2026-03-15
I2S-7688-MP-74.1.28.20.2 | S&C | I.CN.50.15020 | Deleted - Sec.1 - Turnout 03 S&C installation | 2026-03-15 | 2026-03-15
I2S-7688-MP-74.1.28.20.2 | S&C | I.CN.50.15070 | Deleted - Sec.1 - Turnout 01 S&C Commissioning | 2026-03-15 | 2026-03-16
I2S-7688-MP-74.1.28.20.2 | S&C | I.CN.50.15080 | Deleted - Sec.1 - Turnout 03 S&C Commissioning | 2026-03-16 | 2026-03-16
Plant Services |  |  |  | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.5 | Plant Services | I.CN.50.14770 | Deleted - Sec.1 - lift in Crossover 18.5 R1200 (PEM/LEM or Crane) ( 00030 to 00178) | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.28.20.5 | Plant Services | I.CN.50.14810 | Deleted - Sec.1 - lift in Turnout 11 in 18 R1200 (Ilabo) PEM/LEM or Crane) (00374) | 2026-03-14 | 2026-03-14
Surfacing |  |  |  | 2026-03-14 | 2026-03-15
I2S-7688-MP-74.1.28.20.6 | Surfacing | I.CN.50.14900 | Deleted - Sec.1 - Tamp Dn Main inc normal for X over | 2026-03-14 | 2026-03-15
I2S-7688-MP-74.1.28.20.6 | Surfacing | I.CN.50.14920 | Deleted - Sec.1 - Tamp Crossover 18.5 R1200 | 2026-03-15 | 2026-03-15
I2S-7688-MP-74.1.28.20.6 | Surfacing | I.CN.50.14940 | Deleted - Sec.1 - Tamp Up Main inc Turnout 18.5 R1200 x2 | 2026-03-15 | 2026-03-15
I2S-7688-MP-74.1.28.20.6 | Surfacing | I.CN.50.14960 | Deleted - Sec.1 - Tamp Diverge T/O 03 | 2026-03-15 | 2026-03-15
Rail Safety - Handback and COntingency |  |  |  | 2026-03-16 | 2026-03-16
I2S-7688-MP-74.1.28.20.7 | Rail Safety - Handback and COntingency | I.CN.50.15110 | Deleted - Sec.1 - Contractors Contingency - 10% - 6hrs | 2026-03-16 | 2026-03-16
I2S-7688-MP-74.1.28.20.7 | Rail Safety - Handback and COntingency | I.CN.50.15120 | Deleted - Sec.1 - Handback LPA | 2026-03-16 | 2026-03-16
I2S-7688-MP-74.1.28.20.7 | Rail Safety - Handback and COntingency | I.CN.50.15130 | Deleted - Sec.1 - Handback/ Possession Complete - March 2026 |  | 2026-03-16
Culvert - PR22750-02 - 450 RCP - 12m Delete |  |  |  | 2026-05-13 | 2026-05-18
I2S-7688-MP-74.1.28.6 | Culvert - PR22750-02 - 450 RCP - 12m Delete | I.CN.65.17470 | Deleted - Sec.4 - Private LX - PR22426 - Drainage - LX Culvert - Trench Excavation / Site Prep | 2026-05-13 | 2026-05-13
I2S-7688-MP-74.1.28.6 | Culvert - PR22750-02 - 450 RCP - 12m Delete | I.CN.65.17480 | Deleted - Sec.4 - Private LX - PR22426 - Drainage - Place RCP Pipe | 2026-05-14 | 2026-05-14
I2S-7688-MP-74.1.28.6 | Culvert - PR22750-02 - 450 RCP - 12m Delete | I.CN.65.17490 | Deleted - Sec.4 - Private LX - PR22426 - Drainage - Detailed backfill | 2026-05-18 | 2026-05-18
Culvert - PR22750-01 - 1200 RCP - 13m Delete |  |  |  | 2026-05-10 | 2026-05-22
I2S-7688-MP-74.1.28.5 | Culvert - PR22750-01 - 1200 RCP - 13m Delete | I.CN.65.14410 | Deleted - Sec.4 - Private LX - PR22426- Drainage - LX Culvert - Trench Excavation / Site Prep | 2026-05-10 | 2026-05-11
I2S-7688-MP-74.1.28.5 | Culvert - PR22750-01 - 1200 RCP - 13m Delete | I.CN.65.14420 | Deleted - Sec.4 - Private LX - PR22426 - Drainage - Place RCP Pipe | 2026-05-12 | 2026-05-13
I2S-7688-MP-74.1.28.5 | Culvert - PR22750-01 - 1200 RCP - 13m Delete | I.CN.65.14430 | Deleted - Sec.4 - Private LX - PR22426 - Drainage - Detailed backfill | 2026-05-14 | 2026-05-14
I2S-7688-MP-74.1.28.5 | Culvert - PR22750-01 - 1200 RCP - 13m Delete | I.CN.65.18400 | Deleted - Sec.4 - Private LX - PR22426 - Drainage - Excavation 1600m2 3m deep - Basin Upstream | 2026-05-10 | 2026-05-22
Culvert - PR30875-02 (450 RCP - 20m) Delete |  |  |  | 2026-04-02 | 2026-04-10
I2S-7688-MP-74.1.28.10 | Culvert - PR30875-02 (450 RCP - 20m) Delete | I.CN.65.17380 | Deleted - Sec.5 - Private LX - Culvert ID : E7-RD-448361-1 - LX Culvert - Trench Excavation/ Culvert site prep | 2026-04-02 | 2026-04-03
I2S-7688-MP-74.1.28.10 | Culvert - PR30875-02 (450 RCP - 20m) Delete | I.CN.65.17390 | Deleted - Sec.5 - Private LX - Culvert ID : E7-RD-448361-1 - Place HDPE Pipe | 2026-04-09 | 2026-04-09
I2S-7688-MP-74.1.28.10 | Culvert - PR30875-02 (450 RCP - 20m) Delete | I.CN.65.17400 | Deleted - Sec.5 - Private LX - Culvert ID : E7-RD-448361-1 - Detailed backfill | 2026-04-10 | 2026-04-10
Culvert - PR30850-03 (2 x 0.9W x 0.45H RCBC - 13m) Delete |  |  |  | 2026-04-04 | 2026-04-09
I2S-7688-MP-74.1.28.11 | Culvert - PR30850-03 (2 x 0.9W x 0.45H RCBC - 13m) Delete | I.CN.65.17350 | Deleted - Sec.5 - Private LX - Culvert ID : E7-RD-448361-1 - Trench Excavation/ Culvert site prep | 2026-04-04 | 2026-04-06
I2S-7688-MP-74.1.28.11 | Culvert - PR30850-03 (2 x 0.9W x 0.45H RCBC - 13m) Delete | I.CN.65.17360 | Deleted - Sec.5 - Private LX - Culvert ID : E7-RD-448361-1 - Place HDPE Pipe | 2026-04-07 | 2026-04-08
I2S-7688-MP-74.1.28.11 | Culvert - PR30850-03 (2 x 0.9W x 0.45H RCBC - 13m) Delete | I.CN.65.17370 | Deleted - Sec.5 - Private LX - Culvert ID : E7-RD-448361-1 - Detailed backfill | 2026-04-09 | 2026-04-09
Culvert - LX-PR32150-04 - (450 RCP - 21m) Delete |  |  |  | 2026-04-06 | 2026-04-09
I2S-7688-MP-74.1.28.12 | Culvert - LX-PR32150-04 - (450 RCP - 21m) Delete | I.CN.65.17290 | Deleted - Sec.5 - Private LX - PR32146 - Drainage - LX Culvert - Trench Excavation/ Culvert site prep | 2026-04-06 | 2026-04-07
I2S-7688-MP-74.1.28.12 | Culvert - LX-PR32150-04 - (450 RCP - 21m) Delete | I.CN.65.17300 | Deleted - Sec.5 - Private LX - PR32146 - Drainage - Place HDPE Pipe | 2026-04-08 | 2026-04-08
I2S-7688-MP-74.1.28.12 | Culvert - LX-PR32150-04 - (450 RCP - 21m) Delete | I.CN.65.17310 | Deleted - Sec.5 - Private LX - PR32146 - Drainage - Detailed backfill | 2026-04-09 | 2026-04-09
Culvert - LX-PR32150-05 - (900 RCP - 14m) Delete |  |  |  | 2026-04-08 | 2026-04-11
I2S-7688-MP-74.1.28.13 | Culvert - LX-PR32150-05 - (900 RCP - 14m) Delete | I.CN.65.17260 | Deleted - Sec.5 - Private LX - PR32146 - Drainage - LX Culvert - Trench Excavation/ Culvert site prep | 2026-04-08 | 2026-04-09
I2S-7688-MP-74.1.28.13 | Culvert - LX-PR32150-05 - (900 RCP - 14m) Delete | I.CN.65.17270 | Deleted - Sec.5 - Private LX - PR32146 - Drainage - Place HDPE Pipe | 2026-04-10 | 2026-04-10
I2S-7688-MP-74.1.28.13 | Culvert - LX-PR32150-05 - (900 RCP - 14m) Delete | I.CN.65.17280 | Deleted - Sec.5 - Private LX - PR32146 - Drainage - Detailed backfill | 2026-04-11 | 2026-04-11
Culvert - LX-PU33780-02 - (1200 RCP - 15m) Delete |  |  |  | 2026-04-29 | 2026-05-02
I2S-7688-MP-74.1.28.17 | Culvert - LX-PU33780-02 - (1200 RCP - 15m) Delete | I.CN.65.17170 | Deleted - Sec.5 - Public LX - PU33766 - Drainage - LX Culvert - Trench Excavation/ Culvert site prep | 2026-04-29 | 2026-04-30
I2S-7688-MP-74.1.28.17 | Culvert - LX-PU33780-02 - (1200 RCP - 15m) Delete | I.CN.65.17180 | Deleted - Sec.5 - Public LX - PU33766 - Drainage - Place RCP Pipe | 2026-05-01 | 2026-05-01
I2S-7688-MP-74.1.28.17 | Culvert - LX-PU33780-02 - (1200 RCP - 15m) Delete | I.CN.65.17190 | Deleted - Sec.5 - Public LX - PU33766 - Drainage - Detailed backfill | 2026-05-02 | 2026-05-02
Culvert - LX-PU33780-03 - (450 RCP - 30m) Delete |  |  |  | 2026-05-01 | 2026-05-04
I2S-7688-MP-74.1.28.18 | Culvert - LX-PU33780-03 - (450 RCP - 30m) Delete | I.CN.65.17210 | Deleted - Sec.5 - Public LX - PU33766 - Drainage - Place RCP Pipe | 2026-05-03 | 2026-05-03
I2S-7688-MP-74.1.28.18 | Culvert - LX-PU33780-03 - (450 RCP - 30m) Delete | I.CN.65.17220 | Deleted - Sec.5 - Public LX - PU33766 - Drainage - Detailed backfill | 2026-05-04 | 2026-05-04
I2S-7688-MP-74.1.28.18 | Culvert - LX-PU33780-03 - (450 RCP - 30m) Delete | I.CN.65.17200 | Deleted - Sec.5 - Public LX - PU33766- Drainage - LX Culvert - Trench Excavation/ Culvert site prep | 2026-05-01 | 2026-05-02
Culvert - LX-PU33780-04 - (450 RCP - Delete |  |  |  | 2026-05-03 | 2026-05-06
I2S-7688-MP-74.1.28.19 | Culvert - LX-PU33780-04 - (450 RCP - Delete | I.CN.65.17250 | Deleted - Sec.5 - Public LX - PU33766 - Drainage - Detailed backfill | 2026-05-06 | 2026-05-06
I2S-7688-MP-74.1.28.19 | Culvert - LX-PU33780-04 - (450 RCP - Delete | I.CN.65.17230 | Deleted - Sec.5 - Public LX - PU33766 - Drainage - LX Culvert - Trench Excavation/ Culvert site prep | 2026-05-03 | 2026-05-04
I2S-7688-MP-74.1.28.19 | Culvert - LX-PU33780-04 - (450 RCP - Delete | I.CN.65.17240 | Deleted - Sec.5 - Public LX - PU33766 - Drainage - Place RCP Pipe | 2026-05-05 | 2026-05-05
Culvert - 039394)-01 - (900 RCP - 16m) Delete |  |  |  | 2026-02-21 | 2026-02-24
I2S-7688-MP-74.1.28.14 | Culvert - 039394)-01 - (900 RCP - 16m) Delete | I.CN.65.13520 | Deleted - Sec.6 - Private LX - PR39394 - Drainage - Place RCP Pipe | 2026-02-23 | 2026-02-23
I2S-7688-MP-74.1.28.14 | Culvert - 039394)-01 - (900 RCP - 16m) Delete | I.CN.65.13530 | Deleted - Sec.6 - Private LX - PR39394 - Drainage - Detailed backfill | 2026-02-24 | 2026-02-24
I2S-7688-MP-74.1.28.14 | Culvert - 039394)-01 - (900 RCP - 16m) Delete | I.CN.65.13510 | Deleted - Sec.6 - Private LX - PR39394 - Drainage - LX Culvert - Trench Excavation / Site Prep | 2026-02-21 | 2026-02-22
Culvert - 039394)-02 - (450 RCP - 11m) Delete |  |  |  | 2026-02-23 | 2026-02-27
I2S-7688-MP-74.1.28.15 | Culvert - 039394)-02 - (450 RCP - 11m) Delete | I.CN.65.17020 | Deleted - Sec.6 - Private LX - PR39394 - Drainage - LX Culvert - Trench Excavation / Site Prep | 2026-02-23 | 2026-02-24
I2S-7688-MP-74.1.28.15 | Culvert - 039394)-02 - (450 RCP - 11m) Delete | I.CN.65.17030 | Deleted - Sec.6 - Private LX - PR39394 - Drainage - Place RCP Pipe | 2026-02-26 | 2026-02-26
I2S-7688-MP-74.1.28.15 | Culvert - 039394)-02 - (450 RCP - 11m) Delete | I.CN.65.17040 | Deleted - Sec.6 - Private LX - PR39394 - Drainage - Detailed backfill | 2026-02-27 | 2026-02-27
Culvert - 039394)- 03 - (450 RCP - 11m) Delete |  |  |  | 2026-02-26 | 2026-03-01
I2S-7688-MP-74.1.28.16 | Culvert - 039394)- 03 - (450 RCP - 11m) Delete | I.CN.65.17050 | Deleted - Sec.6 - Private LX - PR39394 - Drainage - LX Culvert - Trench Excavation / Site Prep | 2026-02-26 | 2026-02-27
I2S-7688-MP-74.1.28.16 | Culvert - 039394)- 03 - (450 RCP - 11m) Delete | I.CN.65.17060 | Deleted - Sec.6 - Private LX - PR39394 - Drainage - Place RCP Pipe | 2026-02-28 | 2026-02-28
I2S-7688-MP-74.1.28.16 | Culvert - 039394)- 03 - (450 RCP - 11m) Delete | I.CN.65.17070 | Deleted - Sec.6 - Private LX - PR39394 - Drainage - Detailed backfill | 2026-03-01 | 2026-03-01
Design Package H8 - Bridges Type 3 - Powder Horn Tributary Creek Underbridges
Design Stage 1 - Feasibility Design - FDD
I2S-7688-MP-74.1.28.30.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15120 | Deleted - Design Presentation to IRPL - DPK Presentation - H8 - Stage 1 (Modified already part of original Contract Pr
I2S-7688-MP-74.1.28.30.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14830 | Deleted - Design Development - Bridges - H8 - Stage 1 - sections 6 (2 off, inc
I2S-7688-MP-74.1.28.30.2 | Design Stage 1 - Feasibility Design - FDD | Cost-FDD-H8 | Deleted - Cost FDD H8
I2S-7688-MP-74.1.28.30.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14840 | Deleted - Internal IDR workshop (By BGE) - H8 - Stage 1
I2S-7688-MP-74.1.28.30.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14860 | Deleted - Review of IDR comment response and final review - H8 - Stage 1
I2S-7688-MP-74.1.28.30.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14870 | Deleted - Incorporate IDR comments - H8 - Stage 1 - Powder Horn Tributary Creek Underbridges
I2S-7688-MP-74.1.28.30.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14880 | Deleted - Issue Responses & Receive Comment Closeout - H8 - Stage 1
I2S-7688-MP-74.1.28.30.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14890 | Deleted - Submission to IRPL - H8 - Stage 1
I2S-7688-MP-74.1.28.30.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14900 | Deleted - IRPL Review (20 B.days) - H8 - Stage 1
I2S-7688-MP-74.1.28.30.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.14910 | Deleted - Start Package H8 - Bridges - H8 - Stage 1 - Powder Horn Tributary Creek Underbridges
I2S-7688-MP-74.1.28.30.2 | Design Stage 1 - Feasibility Design - FDD | I.DE.02.15110 | Deleted - Internal IDR Review (By JHG) - H8 - Stage 1 (Modified)
Design Stage 2 - Preliminary Design - PDD
I2S-7688-MP-74.1.28.30.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14960 | Deleted - Incorporate IDR comments - H8 - Stage 2
I2S-7688-MP-74.1.28.30.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14970 | Deleted - Issue Responses & Receive Comment Closeout - H8 - Stage 2
I2S-7688-MP-74.1.28.30.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14980 | Deleted - Submission to IRPL - H8 - Stage 2
I2S-7688-MP-74.1.28.30.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14990 | Deleted - IRPL Review (20 B.days) - H8 - Stage 2
I2S-7688-MP-74.1.28.30.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.15130 | Deleted - Internal IDR Review (By JHG) - H8 - Stage 2 (Modified)
I2S-7688-MP-74.1.28.30.3 | Design Stage 2 - Preliminary Design - PDD | Cost-PDD-H8 | Deleted - Cost PDD H8
I2S-7688-MP-74.1.28.30.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.15150 | Deleted - Design Presentation to IRPL - DPK Presentation - H8 - Stage 2 (Modified already part of original Contract Pr
I2S-7688-MP-74.1.28.30.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14850 | Deleted - Safety Assurance / SiD - H8 - Stage 1
I2S-7688-MP-74.1.28.30.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14920 | Deleted - Design Development - Stage 2 - Preliminary Design / PDD - Bridges - H8 - Stage 2
I2S-7688-MP-74.1.28.30.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14930 | Deleted - Internal IDR workshop (By BGE) - H8 - Stage 2
I2S-7688-MP-74.1.28.30.3 | Design Stage 2 - Preliminary Design - PDD | I.DE.02.14950 | Deleted - Review of IDR comment response and final review - H8 - Stage 2
Design Stage 3 - Detailed Design - DDD
I2S-7688-MP-74.1.28.30.4 | Design Stage 3 - Detailed Design - DDD | Cost-DDD-H8 | Deleted - Cost DDD H8
I2S-7688-MP-74.1.28.30.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15160 | Deleted - Internal IDR Review (By JHG) - H8 - Stage 3 (Modified)
I2S-7688-MP-74.1.28.30.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.14940 | Deleted - Safety Assurance / SiD - H8- Stage 2
I2S-7688-MP-74.1.28.30.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15000 | Deleted - Design Development - Stage 3 - Detailed Design / DDD - Bridges - H8 - Stage 3 - BGW Bridge
I2S-7688-MP-74.1.28.30.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15010 | Deleted - Internal IDR workshop (By BGE) - H8 - Stage 3
I2S-7688-MP-74.1.28.30.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15020 | Deleted - Review of IDR comment response and final review - H8 - Stage 3 - Bridges
I2S-7688-MP-74.1.28.30.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15030 | Deleted - Incorporate IDR comments - H8 - Stage 3
I2S-7688-MP-74.1.28.30.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15040 | Deleted - Issue Responses & Receive Comment Closeout - H8 - Stage 3
I2S-7688-MP-74.1.28.30.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15050 | Deleted - Submission to IRPL - H8 - Stage 3
I2S-7688-MP-74.1.28.30.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15060 | Deleted - IRPL Review (20 B.days) - H8 - Stage 3
I2S-7688-MP-74.1.28.30.4 | Design Stage 3 - Detailed Design - DDD | I.DE.02.15140 | Deleted - Design Presentation to IRPL - DPK Presentation - H8 - Stage 3 (Modified already part of original Contract Pr
Design Stage 4 - IFC
I2S-7688-MP-74.1.28.30.5 | Design Stage 4 - IFC | Cost-IFC-H8 | Deleted - Cost IFC H8
I2S-7688-MP-74.1.28.30.5 | Design Stage 4 - IFC | I.DE.02.15100 | Deleted - IFC Package Complete H8 - Bridges Powder Horn Tributary Creek Underbridges - H8 - Stage 4
I2S-7688-MP-74.1.28.30.5 | Design Stage 4 - IFC | I.DE.02.15070 | Deleted - Prepare IFC Documentation- Bridges Powder Horn Tributary Creek Underbridges - H8 - Stage 4
I2S-7688-MP-74.1.28.30.5 | Design Stage 4 - IFC | I.DE.02.15080 | Deleted - Submission to IRPL - H8 - Stage 4
I2S-7688-MP-74.1.28.30.5 | Design Stage 4 - IFC | I.DE.02.15090 | Deleted - IRPL Review (5 B.days) - H8 - Stage 4
Culvert - PR22750-03 - 1200 RCP - 12m Delete |  |  |  | 2026-05-14 | 2026-05-17
I2S-7688-MP-74.1.28.7 | Culvert - PR22750-03 - 1200 RCP - 12m Delete | I.CN.65.17440 | Deleted - Sec.4 - Private LX - PR22426 - Drainage - LX Culvert - Trench Excavation / Site Prep | 2026-05-14 | 2026-05-14
I2S-7688-MP-74.1.28.7 | Culvert - PR22750-03 - 1200 RCP - 12m Delete | I.CN.65.17450 | Deleted - Sec.4 - Private LX - PR22426 - Drainage - Place RCP Pipe | 2026-05-16 | 2026-05-16
I2S-7688-MP-74.1.28.7 | Culvert - PR22750-03 - 1200 RCP - 12m Delete | I.CN.65.17460 | Deleted - Sec.4 - Private LX - PR22426 - Drainage - Detailed backfill | 2026-05-17 | 2026-05-17
Culvert - (019835) - 900 RCP - 24m Delete |  |  |  | 2026-05-27 | 2026-05-30
I2S-7688-MP-74.1.28.1 | Culvert - (019835) - 900 RCP - 24m Delete | I.CN.65.14060 | Deleted - Sec.4 - Private LX - PR19835 - Drainage - Place RCP Pipe | 2026-05-29 | 2026-05-29
I2S-7688-MP-74.1.28.1 | Culvert - (019835) - 900 RCP - 24m Delete | I.CN.65.14070 | Deleted - Sec.4 - Private LX - PR19835 - Drainage - Detailed backfill | 2026-05-30 | 2026-05-30
I2S-7688-MP-74.1.28.1 | Culvert - (019835) - 900 RCP - 24m Delete | I.CN.65.14050 | Deleted - Sec.4 - Private LX - PR19835 - Drainage - LX Culvert - Trench Excavation / Site Prep | 2026-05-27 | 2026-05-28
Culvert ID : E7-RA-442560-1 / Type : 12*900mm HDPE / Ch25060 xxxxxxxxx |  |  |  | 2026-01-18 | 2026-02-09
I2S-7688-MP-74.1.28.27 | Culvert ID : E7-RA-442560-1 / Type : 12*900mm HDPE / Ch25060 xxxxxxxxx | I.CN.34.22240 | Deleted - CON - Sec.4 - Culvert ID : E7-RA-442560-1 - Foundation Treatment / Bedding | 2026-01-20 | 2026-01-21
I2S-7688-MP-74.1.28.27 | Culvert ID : E7-RA-442560-1 / Type : 12*900mm HDPE / Ch25060 xxxxxxxxx | I.CN.34.22280 | Deleted - CON - Sec.4 - Culvert ID : E7-RA-442560-1 - Place HDPE Pipe | 2026-01-22 | 2026-02-02
I2S-7688-MP-74.1.28.27 | Culvert ID : E7-RA-442560-1 / Type : 12*900mm HDPE / Ch25060 xxxxxxxxx | I.CN.34.22290 | Deleted - CON - Sec.4 - Culvert ID : E7-RA-442560-1 - Backfill Pipe | 2026-02-03 | 2026-02-03
I2S-7688-MP-74.1.28.27 | Culvert ID : E7-RA-442560-1 / Type : 12*900mm HDPE / Ch25060 xxxxxxxxx | I.CN.34.22310 | Deleted - CON - Sec.4 - Culvert ID : E7-RA-442560-1 - Place Precast Wingwall | 2026-02-04 | 2026-02-04
I2S-7688-MP-74.1.28.27 | Culvert ID : E7-RA-442560-1 / Type : 12*900mm HDPE / Ch25060 xxxxxxxxx | I.CN.34.22320 | Deleted - CON - Sec.4 - Culvert ID : E7-RA-442560-1 - Precast stitch pours for precast headwalls | 2026-02-06 | 2026-02-07
I2S-7688-MP-74.1.28.27 | Culvert ID : E7-RA-442560-1 / Type : 12*900mm HDPE / Ch25060 xxxxxxxxx | I.CN.34.22330 | Deleted - CON - Sec.4 - Culvert ID : E7-RA-442560-1 - Construct Scour Protection | 2026-02-08 | 2026-02-08
I2S-7688-MP-74.1.28.27 | Culvert ID : E7-RA-442560-1 / Type : 12*900mm HDPE / Ch25060 xxxxxxxxx | I.CN.34.22340 | Deleted - CON - Sec.4 - Culvert ID : E7-RA-442560-1 - Detailed backfill | 2026-02-08 | 2026-02-09
I2S-7688-MP-74.1.28.27 | Culvert ID : E7-RA-442560-1 / Type : 12*900mm HDPE / Ch25060 xxxxxxxxx | I.CN.34.22230 | Deleted - CON - Sec.4 - Culvert ID : E7-RA-442560-1 - Trench Excavation / Site Prep | 2026-01-18 | 2026-01-19
Deleted Activities Possessions 24/10/2025 |  |  |  | 2025-02-14 | 2026-03-02
I2S-7688-MP-74.1.24 | Deleted Activities Possessions 24/10/2025 | I.GG.PM.UTIL-1802 | Deleted - Submit final design
I2S-7688-MP-74.1.24 | Deleted Activities Possessions 24/10/2025 | I.GG.PM.UTIL-1812 | Deleted - Certify Design
I2S-7688-MP-74.1.24 | Deleted Activities Possessions 24/10/2025 | I.GG.WAD.2130 | Deleted - Independant review /approve
I2S-7688-MP-74.1.24 | Deleted Activities Possessions 24/10/2025 | I.GG.PM.UTIL-1852 | Deleted - Submit final design
I2S-7688-MP-74.1.24 | Deleted Activities Possessions 24/10/2025 | I.GG.PM.UTIL-1862 | Deleted - Certify Design
I2S-7688-MP-74.1.24 | Deleted Activities Possessions 24/10/2025 | I.GG.PM.UTIL-2122 | Deleted - Submit Easement Proposal to IRPL
I2S-7688-MP-74.1.24 | Deleted Activities Possessions 24/10/2025 | I.GG.PM.UTIL-2132 | Deleted - IRPL to Finalise Easement PS-02 (Indicative)
I2S-7688-MP-74.1.24 | Deleted Activities Possessions 24/10/2025 | I.DE.CCB.7850 | Deleted - CCB Gate 2 Meeting - Presentation of CCR Submission
I2S-7688-MP-74.1.24 | Deleted Activities Possessions 24/10/2025 | I.DE.CCB.7860 | Deleted - Prepare & Submit CCR Checklist /Presentation Material
I2S-7688-MP-74.1.24 | Deleted Activities Possessions 24/10/2025 | I.DE.CCB.7870 | Deleted - UGLRL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.24 | Deleted Activities Possessions 24/10/2025 | I.DE.CCB.7880 | Deleted - UGLRL Submits CCB
I2S-7688-MP-74.1.24 | Deleted Activities Possessions 24/10/2025 | I.DE.CCB.7890 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.24 | Deleted Activities Possessions 24/10/2025 | I.GG.P.S.10SR-72 | Deleted - Prepare Tender Documents - CSR Buried Route | 2025-02-14 | 2025-03-13
I2S-7688-MP-74.1.24 | Deleted Activities Possessions 24/10/2025 | I.GG.P.S.10SR-82 | Deleted - Pricing by Suppliers / Subcontractors - CSR Buried Route | 2025-03-14 | 2025-04-10
I2S-7688-MP-74.1.24 | Deleted Activities Possessions 24/10/2025 | I.GG.P.S.109092 | Deleted - Package Review / Approval - CSR Buried Route | 2025-04-11 | 2025-04-29
I2S-7688-MP-74.1.24 | Deleted Activities Possessions 24/10/2025 | I.GG.P.S.10SR-102 | Deleted - Package Placement - CSR Buried Route | 2025-04-30 | 2025-05-13
I2S-7688-MP-74.1.24 | Deleted Activities Possessions 24/10/2025 | I.GG.P.S.10SR-112 | Deleted - Manufacturing & Delivery - CSR Buried Route | 2025-05-14 | 2025-06-18
I2S-7688-MP-74.1.24 | Deleted Activities Possessions 24/10/2025 | I.GG.PM.UTIL-1792 | Deleted - ARTC Approval
I2S-7688-MP-74.1.24 | Deleted Activities Possessions 24/10/2025 | I.GG.P.FI.6910 | Deleted - Sec.1 - IRPL Free Issue Supplied Material - Rails RT28 60kg tangent profile SC - initial delivery - (del |  | 2026-03-02
Deleted Activities Possessions 17/10/2025 |  |  |  | 2025-09-13 | 2027-03-15
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19130 | Deleted - Sec.6 - Possession - Take out Sec.6 - Possession - March 2027 | 2027-03-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19140 | Deleted - Sec.6 - Possession - Prestart safe working team | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19150 | Deleted - Sec.6 - Possession - PO's into position | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19160 | Deleted - Sec.6 - Possession - Take LPA and confirm with Control | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19170 | Deleted - Sec.6 - Possession - Activity PO's briefed by PPO | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19180 | Deleted - Sec.6 - Possession - Work Parties briefed by PO's | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19190 | Deleted - Sec.6 - Possession- March 2027 - Work commences - Sec.1-6 | 2027-03-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19240 | Deleted - Sec.6 - Disconnect any signalling infrastructure identified as required | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19250 | Deleted - Sec.6 - Mark out track panels for new turnouts to be cut | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19260 | Deleted - Sec.6 - Cut Track panels and remove | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19270 | Deleted - Sec.6 - Grade out old ballast | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19280 | Deleted - Sec.6 - Proof roll formation | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19290 | Deleted - Sec.6 - intsall bottom ballast and geo | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19300 | Deleted - Sec.6 - lift in turnout (PEM/LEM or Crane) | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19310 | Deleted - Sec.6 - Install closure panel as required for T/O | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19320 | Deleted - Sec.6 - Weld out turnout | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19330 | Deleted - Sec.6 - Place ballast for tamping | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19340 | Deleted - Sec.6 - Bring track machines into site from Stockinbingal yard | 2027-03-13 | 2027-03-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19350 | Deleted - Sec.6 - Tamp turnout in though and diverge | 2027-03-13 | 2027-03-14
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19360 | Deleted - Sec.6 - Weld crossing nose | 2027-03-14 | 2027-03-14
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19210 | Deleted - Sec.6 - March 2027 Possession - Contractors Contingency - 10% - 6hrs | 2027-03-15 | 2027-03-15
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19220 | Deleted - Sec.6 - Possession - Handback LPA | 2027-03-15 | 2027-03-15
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19230 | Deleted - Sec.6 - March 2027 Possession - Commissioning - Handback/ Possession Complete |  | 2027-03-15
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18770 | Deleted - Sec.1 - Cut Track panels and remove, stack materials clear for re use - Up | 2025-09-13 | 2025-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.14460 | Deleted - Sec.1 - Disconnect any signalling infrastructure identified as required | 2025-09-13 | 2025-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.14470 | Deleted - Sec.1 - Cut Track panels and remove, stack materials clear for re use - DN | 2025-09-13 | 2025-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18760 | Deleted - Sec.1 - Mark out track panels for removal | 2025-09-13 | 2025-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.14490 | Deleted - Sec.1 - Reconnect any signalling infrastructure identified as required | 2025-09-15 | 2025-09-15
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18850 | Deleted - Sec.1 - Bring track machines into LPA | 2025-09-14 | 2025-09-14
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18940 | Deleted - Sec.1 - Take Track Machines to Illabo to Cross from Up to Dn and bring back into the LPA. | 2025-09-14 | 2025-09-14
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18950 | Deleted - Sec.1 - Take Track Machines to Illabo and exit the LPA. | 2025-09-14 | 2025-09-15
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.13240 | Deleted - Sec.1 - Install bottom ballast and geo (154m) - 220 to 374 (up) | 2025-09-14 | 2025-09-14
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18780 | Deleted - Sec.1 - Reinstate track panel, clip up and weld - up | 2025-09-14 | 2025-09-14
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18790 | Deleted - Sec.1 - Place ballast for tamping -up | 2025-09-14 | 2025-09-14
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18800 | Deleted - Sec.1 - GEDO Up Main for tamping | 2025-09-14 | 2025-09-14
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18810 | Deleted - Sec.1 - Tamp Up Main | 2025-09-14 | 2025-09-14
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18820 | Deleted - Sec.1 - GEDO Up Main | 2025-09-14 | 2025-09-14
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18830 | Deleted - Sec.1 - Destress | 2025-09-14 | 2025-09-15
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18840 | Deleted - Sec.1 - Up Main Corrections - 178 - 374 - sept 25 | 2025-09-15 | 2025-09-15
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18890 | Deleted - Sec.1 - GEDO dn Main for tamping | 2025-09-14 | 2025-09-14
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18900 | Deleted - Sec.1 - Tamp dn Main | 2025-09-14 | 2025-09-14
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18910 | Deleted - Sec.1 - GEDO dn Main | 2025-09-14 | 2025-09-15
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18920 | Deleted - Sec.1 - Destress | 2025-09-15 | 2025-09-15
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18930 | Deleted - Sec.1 - dn Main Corrections - 178 - 374 - sept 25 | 2025-09-15 | 2025-09-15
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18860 | Deleted - Sec.1 - Install bottom ballast and geo (154m) - 220 to 374 (dn) | 2025-09-14 | 2025-09-14
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18870 | Deleted - Sec.1 - Reinstate track panel, clip up and weld -dn | 2025-09-14 | 2025-09-14
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18880 | Deleted - Sec.1 - Place ballast for tamping -dn | 2025-09-14 | 2025-09-14
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.20360 | Deleted - Sec.1 - Install Points 101 A&B C&D crossover - (May 26)
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.20370 | Deleted - Sec.1 - Temping 101 A&B C&D turn out and Points macine - (May 26)
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.20380 | Deleted - Sec.1 - Install Points 101 A&B C&D Points Machine (May 26
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.20390 | Deleted - Sec.1 - Temping 100 A&B turn out and Points macine (May 26)
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.20400 | Deleted - Sec.1 - Handback/ Possession Complete - (May 26)
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.20350 | Deleted - Sec.1 - Possession Starts - (May 26)
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.17990 | Deleted - Sec.6 - Possession - Handback LPA | 2026-09-14 | 2026-09-14
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18000 | Deleted - Sec.6 - Possession - Handback/ Possession Complete - Sep 2026 |  | 2026-09-14
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.17970 | Deleted - Sec.6 - Possession - Stable Track Machines | 2026-09-14 | 2026-09-14
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.17980 | Deleted - Sec.6 - September 2026 Possession - Contractors Contingency - 10% - 6hrs | 2026-09-14 | 2026-09-14
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.12140 | Deleted - Sec.6 - Possession- Rail Laying -Slew CRN track at 36347 to 36600 - eastern end to connect to new Tur | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19100 | Deleted - Sec.6 - Tamp and regulate | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19110 | Deleted - Sec.6 - Destress module | 2026-09-12 | 2026-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19090 | Deleted - Sec.6 - Welding and clamp up - 36347 to 36600 - eastern end | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19080 | Deleted - Sec.6 - Place top ballast - 36347 to 36600 - eastern end | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18970 | Deleted - Sec.6 - Cut Track panel and remove - 36347 to 36600 - eastern end | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18980 | Deleted - Sec.6 - Grade out old material and proof roll - 36347 to 36600 - eastern end | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19060 | Deleted - Sec.6 - Place Bottom Ballast - 500m/day - 36347 to 36600 (163m) - eastern end | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19070 | Deleted - Sec.6 - Sleeper Laying - 800m/day - 36347 to 36600 - eastern end | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.18990 | Deleted - Sec.6 - Poss - Tamp Main Line Parkes Nth | 2026-09-13 | 2026-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.1700 | Deleted - Sec.6 - Destress Main Line Parkes Sth | 2026-09-13 | 2026-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.11730 | Deleted - Sec.6 - Tamp Main Line Parkes Sth | 2026-09-13 | 2026-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.15350 | Deleted - Sec.6 - Sleeper Laying - 800m/day - (across CRN track - 37680 - 37720) | 2026-09-13 | 2026-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.15340 | Deleted - Sec.6 - Rail Laying - 550m/day - (across CRN track - 37680 - 37720) | 2026-09-13 | 2026-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.3180 | Deleted - Sec.6 - Flash Butt Welding and clip up (30 welds/ 412.5 m) (across CRN track - 37680 - 37720) | 2026-09-13 | 2026-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.17800 | Deleted - Sec.6 - Place Top Ballast (across CRN track - 37680 - 37720) | 2026-09-13 | 2026-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.17810 | Deleted - Sec.6 - Tamp and regulate (across CRN track - 37680 - 37720) | 2026-09-13 | 2026-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.2210 | Deleted - Sec.6 - Destress Panel (across CRN track - 37680 - 37720) | 2026-09-13 | 2026-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.14030 | Deleted - Sec.6 - Place Bottom Ballast - 500m/day - 37680 - 37720 (200m) - Across Old CRN Track | 2026-09-13 | 2026-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.5200 | Deleted - Sec.6 - Sleeper Distribution - 860m/day - (across CRN track - 37700 to 37750 (200m) | 2026-09-13 | 2026-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.14450 | Deleted - Sec.6 - Remove old CRN Track west end where new I2S track sits (37700) | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.12880 | Deleted - Sec.6 - Cut Existing CRN track panel in 3 places | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.1340 | Deleted - Sec.6 - IRPL Sleeper Stockpiles - Sec.6 (across CRN track - 37680 - 37720) | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.4660 | Deleted - Sec.6 - Rail Distribution - 860m/day - (across CRN track - 37680 - 37720) | 2026-09-13 | 2026-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.15270 | Deleted - Sec.6 - Cut Track panel and remove (25m) - CRN | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19000 | Deleted - Sec.6 - Grade out old material and proof roll (25m) - CRN | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19010 | Deleted - Sec.6 - Place Bottom Ballast - 500m/day - CRN (25m) | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.15240 | Deleted - Sec.6 - Sleeper Laying - 800m/day - CRN - 44000 to 45000 | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.15230 | Deleted - Sec.6 - Rail Laying - 550m/day - CRN - 44000 to 45000 (25m) | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.15220 | Deleted - Sec.6 - Welding and clamp up -CRN | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.15210 | Deleted - Sec.6 - Tamp and regulate - (25m) - CRN - | 2026-09-12 | 2026-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.15200 | Deleted - Sec.6 - Destress module - (25m) - CRN - | 2026-09-13 | 2026-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.15320 | Deleted - Sec.6 - Cut Track panel and remove - 39200 to 39300 I2S Northern Turnout | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19050 | Deleted - Sec.6 - Grade out old material and proof roll - 39200 to 39300 I2S Northern Turnout | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.17710 | Deleted - Sec.6 - Place Bottom Ballast - 500m/day - 39200 to 39300 (100m) I2S Northern Turnout | 2026-09-12 | 2026-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19020 | Deleted - Sec.6 - Sleeper Laying - 800m/day - 39200 to 39300 I2S Northern Turnout | 2026-09-13 | 2026-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.17770 | Deleted - Sec.6 - Rail Laying - Install TURNOUT - 39200 to 39300 I2S Northern Turnout | 2026-09-13 | 2026-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.19040 | Deleted - Sec.6 - Welding and clamp up - 39200 to 39300 I2S Northern Turnout | 2026-09-13 | 2026-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.2410 | Deleted - Sec.6 - Place top ballast - 39200 to 39300 I2S Northern Turnout | 2026-09-13 | 2026-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.17690 | Deleted - Sec.6 - Tamp and regulate - 39200 to 39300 I2S Northern Turnout | 2026-09-13 | 2026-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.2220 | Deleted - Sec.6 - Destress module - 39200 to 39300 I2S Northern Turnout | 2026-09-13 | 2026-09-13
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.17890 | Deleted - Sec.6 - Possession - Take out Sec.6 - Possession - Sep 2026 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.17910 | Deleted - Sec.6 - Possession - Prestart safe working team | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.17920 | Deleted - Sec.6 - Possession - PO's into position | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.17930 | Deleted - Sec.6 - Possession - Take LPA and confirm with Control | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.17940 | Deleted - Sec.6 - Possession - Activity PO's briefed by PPO | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.17950 | Deleted - Sec.6 - Possession - Work Parties briefed by PO's | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.23 | Deleted Activities Possessions 17/10/2025 | I.CN.50.17960 | Deleted - Sec.6 - Possession- Sep 2026 - Work commences | 2026-09-12
Deleted Activities Possessions 15/10/2025 |  |  |  | 2025-09-13 | 2025-09-13
I2S-7688-MP-74.1.21 | Deleted Activities Possessions 15/10/2025 | I.CN.50.18740 | Deleted - Sec.1 - Work Parties briefed by PO's (Sept 25) | 2025-09-13 | 2025-09-13
I2S-7688-MP-74.1.21 | Deleted Activities Possessions 15/10/2025 | I.CN.50.18750 | Deleted - Sec.1 - Work commences (Sept 25) | 2025-09-13
I2S-7688-MP-74.1.21 | Deleted Activities Possessions 15/10/2025 | I.CN.50.13230 | Deleted - Sec.1 - Take out Sec.1 - Sept 2025 | 2025-09-13
I2S-7688-MP-74.1.21 | Deleted Activities Possessions 15/10/2025 | I.CN.50.18700 | Deleted - Sec.1 - Prestart safe working team (Sept 25) | 2025-09-13 | 2025-09-13
I2S-7688-MP-74.1.21 | Deleted Activities Possessions 15/10/2025 | I.CN.50.18710 | Deleted - Sec.1 - PO's into position (Sept 25) | 2025-09-13 | 2025-09-13
I2S-7688-MP-74.1.21 | Deleted Activities Possessions 15/10/2025 | I.CN.50.18720 | Deleted - Sec.1 - Take LPA and confirm with Control (Sept 25) | 2025-09-13 | 2025-09-13
I2S-7688-MP-74.1.21 | Deleted Activities Possessions 15/10/2025 | I.CN.50.18730 | Deleted - Sec.1 - Activity PO's briefed by PPO (Sept 25) | 2025-09-13 | 2025-09-13
Deleted Activities Prior to14/10/2025 |  |  |  | 2024-09-30 | 2027-03-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.8420 | Deleted - Start Package 3.10 - Drainage (roads) - 3.10 - Stage 1 | 2024-10-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3700 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Road Drainage - 3.10 - Stage 2 | 2025-01-17 | 2025-03-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3710 | Deleted - Design Deliverables Submission for Workshops and comments - Stage 2 drainage (6) - 3.10 - Stage 2 | 2025-03-24 | 2025-03-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3720 | Deleted - Safety Assurance / SiD - 3.10 - Stage 2 | 2025-03-24 | 2025-03-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3730 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 3.10 - Stage 2 | 2025-03-31 | 2025-04-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9330 | Deleted - Submission to IRPL PDR - 2.10 - Stage 2 | 2025-03-10 | 2025-03-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9300 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 2.10 - Stage 2 | 2025-02-24 | 2025-03-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9310 | Deleted - Incorporate IDC & CDR comments - 2.10 - Stage 2 | 2025-03-03 | 2025-03-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9320 | Deleted - Issue Responses & Receive Comment Closeout - 2.10 - Stage 2 | 2025-03-03 | 2025-03-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9560 | Deleted - Sec.4 - Fill - Fill 26 - 2,519ccm - Upper A | 2026-04-07 | 2026-04-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9620 | Deleted - Sec.4 - Fill - Fill 29 - 2,726ccm - Upper A | 2026-03-31 | 2026-04-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9640 | Deleted - Sec.4 - Fill - Fill 30 - 6,615ccm - Upper A | 2026-04-02 | 2026-04-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14630 | Deleted - Sec.5 - Fill - Fill 36 - 4,256ccm - Fill in Open Drains | 2026-03-30 | 2026-04-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12460 | Deleted - Incorporate IDC & CDR / CCB and Stage 1 comments - 2.03 - Stage 2 | 2025-03-17 | 2025-03-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.29050 | Deleted - Sec.6 - Culvert ID : E7-RD-456911-1 - Place HDPE Pipe
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.29060 | Deleted - Sec.6 - Culvert ID : E7-RD-456911-1 - Precast stitch pours for precast headwalls
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.29080 | Deleted - Sec.6 - Culvert ID : E7-RD-456911-1 - Detailed backfill
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-93 | Deleted - Package Review / Approval - Goldenfields Water | 2025-05-05 | 2025-05-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6570 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10350 | Deleted - Sec.4 - Fill - Cut 20 - 300ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-07-02 | 2026-07-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.16150 | Deleted - CoA - C1 - Review and Approved by Planning Secretary -(CEMF) | 2024-10-16 | 2024-11-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7210 | Deleted - Design Deliverables Submission for Workshops and comments - W.01 - Stage 2 | 2025-03-10 | 2025-03-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7230 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - W.01 - Stage 2 | 2025-03-17 | 2025-03-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7240 | Deleted - Incorporate IDC & CDR / CCB and Stage 1 comments - W.01 - Stage 2 | 2025-03-24 | 2025-04-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12750 | Deleted - Safety Assurance / SiD - 1.08 - Stage 3 | 2025-05-05 | 2025-05-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12760 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.08 - Stage 3 | 2025-05-12 | 2025-05-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-2030 | Deleted - CoA - D7 Operational Fauna Connectivity Monitoring, Predator Prevention& Adaptive Mitigation Program impleme | 2026-09-15 | 2026-09-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14320 | Deleted - Sec.3 - Cut - Fill 14 - 584ccm - OD Soil | 2026-01-20 | 2026-01-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14440 | Deleted - Sec.4 - Cut - Fill 26 - 2260ccm - OD Soil | 2025-11-30 | 2025-12-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14450 | Deleted - Sec.4 - Cut - Fill 27 - 150ccm - OD Soil | 2026-02-03 | 2026-02-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14460 | Deleted - Sec.4 - Cut - Fill 28 - 1946ccm - OD Soil | 2026-01-21 | 2026-01-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14470 | Deleted - Sec.4 - Cut - Fill 29 - 1343ccm - OD Soil | 2025-12-13 | 2025-12-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14480 | Deleted - Sec.4 - Cut - Fill 30 - 5,735ccm - OD Soil | 2025-11-20 | 2025-12-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14490 | Deleted - Sec.4 - Cut - Fill 31 - 1,228ccm - OD Soil | 2025-10-04 | 2025-10-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5680 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Roads - BGW - 3.07 - Stage 4 | 2025-06-24 | 2025-07-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12290 | Deleted - Start Package 1.02 - Geotechnical Design - 1.02 - Stage 1 | 2024-11-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8240 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Geotechnical Design - 1.02 - Stage 1 | 2024-11-22 | 2025-01-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2940 | Deleted - Configuration Change Acceptance Notice | 2025-08-05 | 2025-08-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8830 | Deleted - TfNSW/ IV Review (30 B.days) - E8 - Stage 4 - Burley Griffin Way Overbridge | 2025-09-01 | 2025-10-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19960 | Deleted - Sec.4 - Old Cootmundra Rail Br - Pier 1 Pile Cap - 8m3 | 2026-02-18 | 2026-02-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19970 | Deleted - Sec.4 - Old Cootmundra Rail Br - Detailed Earthworks Pier Pile Cap Pier 2 | 2026-03-01 | 2026-03-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19980 | Deleted - Sec.4 - Old Cootmundra Rail Br - Pier 2 Pile Cap - 8m3 | 2026-03-04 | 2026-03-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19990 | Deleted - Sec.4 - Old Cootmundra Rail Br - FRP - [40] MPa/20 in pier 2 headstock - 11m3 | 2026-03-21 | 2026-03-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21570 | Deleted - Sec.4 - Old Cootmundra Rail Br - FRP - [40] MPa/20 in pier 2 - 15m3 | 2026-03-09 | 2026-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19040 | Deleted - Sec.4 - Old Cootmundra Rail Br - Precast Abutment Panels - South Abutment | 2026-06-09 | 2026-06-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19060 | Deleted - Sec.4 - Old Cootmundra Rail Br - Abutment Precast Panels South Abutment Capping | 2026-06-12 | 2026-06-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9100 | Deleted - Sec.4 - Cut - Cut 25 - 66,679ccm -SW NB Rip - rock | 2025-08-30 | 2025-10-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9110 | Deleted - Sec.4 - Cut - Cut 26 - 60,000ccm - Blast - rock | 2025-10-04 | 2025-11-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14230 | Deleted - Sec.4 - Cut - Cut 19 - 8,609ccm - XW /HW - SW NB Rip - rock | 2026-01-08 | 2026-01-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9140 | Deleted - Sec.4 - Fill - PR19800 - 555ccm | 2026-05-14 | 2026-05-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4150 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Level Crossings RD-02 | 2025-04-07 | 2025-04-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2370 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-07-30 | 2025-08-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2380 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-08-19 | 2025-08-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4670 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-02-11 | 2025-02-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4680 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-02-28 | 2025-02-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.8870 | Deleted - Issue Responses & Receive Comment Closeout - 1.10 - Stage 1 | 2024-12-20 | 2025-01-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-692 | Deleted - Optus - Quote & Send Contract | 2025-05-07 | 2025-07-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6060 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6140 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6100 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Bridges - Dudauman Creek Underbridge
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13240 | Deleted - Design Deliverables Submission for Workshops and comments - 2.08 - Stage 1 | 2024-11-28 | 2024-12-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13250 | Deleted - Safety Assurance / SiD - 2.08 - Stage 1 | 2024-11-28 | 2024-12-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8970 | Deleted - Start Package 3.05 - Culverts - Under Rail - 3.05 - Stage 1 | 2024-10-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13450 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 2.08 - Stage 3 | 2025-04-28 | 2025-05-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13520 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Utility Infrastructure - 2.08 - Stage 4 | 2025-06-11 | 2025-07-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8930 | Deleted - IRPL Review (20 B.days) - 3.05 - Stage 1 | 2025-01-31 | 2025-02-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8980 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Culverts - Under Rail - 3.05 - Stage 2 | 2025-01-30 | 2025-04-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8990 | Deleted - Design Deliverables Submission for Workshops and comments - 3.05 - Stage 2 | 2025-03-27 | 2025-04-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2770 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-05-21 | 2025-06-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4610 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-02-24 | 2025-02-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4620 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-03-05 | 2025-03-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15780 | Deleted - CUDLP - JH Respond and incorporate to DPHI comments | 2025-03-05 | 2025-03-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.11260 | Deleted - Sec.5 - Fill - Fill 35 - 74ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-08-03 | 2026-08-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.11270 | Deleted - Sec.5 - Fill - Cut 28 - 111ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-08-04 | 2026-08-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.18440 | Deleted - Sec.5 - Float before Track can finish - Sec.5 - converted LOE | 2026-07-29 | 2026-10-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10220 | Deleted - Incorporate IDC & CDR / CCB and Stage 1 comments - 1.06 - Stage 2 | 2025-03-31 | 2025-04-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15570 | Deleted - CTTAMP - Respond to stakeholder comments | 2025-01-15 | 2025-01-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12020 | Deleted - Safety Assurance / SiD - W.04 - Stage 3 | 2025-05-08 | 2025-05-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14340 | Deleted - Sec.3 - Cut - Fill 16 - 590ccm - OD Soil | 2025-12-11 | 2025-12-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6390 | Deleted - Sec.3 - Cut - Cut 06 - 29,505ccm - OD Soil/ Soil | 2025-11-16 | 2025-12-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12010 | Deleted - Design Deliverables Submission for Workshops and comments - W.04 - Stage 3 | 2025-05-08 | 2025-05-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.15-304 | Deleted - Proponent presents and/or provides proposed project information to Registered Aboriginal Parties (RAP) | 2024-11-20 | 2024-11-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.15-314 | Deleted - Proponent may create an opportunity for registered Aboriginal parties to visit the proposed project site | 2024-11-27 | 2024-12-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-97 | Deleted - JH Horizontal & Vertical Alignment Design for APA Group | 2024-10-17 | 2024-11-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.11970 | Deleted - Issue Responses & Receive Comment Closeout- W.04 - Stage 2 | 2025-03-21 | 2025-03-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | zI.GG.CEMP.16270 | Deleted - Commence Main works (approx 10 months from award - Awaiting CDR) - - Double Up | 2025-07-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.14810 | Deleted - Works can Commence (approx 9-10 months from Award) - Sec.6 - Double Up | 2025-07-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.11960 | Deleted - Incorporate IDC & CDR comments- W.04 - Stage 2 | 2025-03-21 | 2025-03-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.11980 | Deleted - Submission to IRPL PDR - W.04 - Stage 2 | 2025-03-28 | 2025-03-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14310 | Deleted - Sec.3 - Cut - Fill 13 - 586ccm - OD Soil | 2026-02-22 | 2026-02-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.25050 | Deleted - Sec.3 - Culvert ID : E7-RA-427720-1 - Backfill units | 2026-03-08 | 2026-03-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.25060 | Deleted - Sec.3 - Culvert ID : E7-RA-427720-1 - Place Precast Apron Slab | 2026-03-09 | 2026-03-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.24750 | Deleted - Sec.3 - Culvert (12447) - Trench Excavation / Site Prep | 2026-04-26 | 2026-04-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.24760 | Deleted - Sec.3 - Culvert (12447) - Foundation Treatment / Bedding | 2026-04-28 | 2026-04-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13410 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Utility Coordination Plans - 2.08 - Stage 2 | 2024-12-19 | 2025-02-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13460 | Deleted - Incorporate IDC & CDR comments - 2.08 - Stage 3 | 2025-05-05 | 2025-05-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12560 | Deleted - Submission to IRPL DDR - 2.03 - Stage 3 | 2025-06-13 | 2025-06-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12570 | Deleted - IRPL Review (20 B.days) - 2.03 - Stage 3 | 2025-06-16 | 2025-07-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12550 | Deleted - Issue Responses & Receive Comment Closeout - 2.03 - Stage 3 | 2025-06-05 | 2025-06-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12580 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Earthworks Formation Design Documentation - Zone 2 | 2025-06-23 | 2025-08-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12590 | Deleted - Incorporate IDC & CDR / CCB and Stage 3 comments - 2.03 - Stage 4 | 2025-08-05 | 2025-08-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12600 | Deleted - IRPL Review (5 B.days) - 2.03 - Stage 4 | 2025-08-19 | 2025-08-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12610 | Deleted - CDR Package Complete 2.03 - Earthworks Formation Design Documentation - Zone 2 /Sec.2-5 - 2.03 - Stage |  | 2025-08-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14890 | Deleted - Sec.4 - Fill - Fill 29 - 1,384ccm - Fill in Open Drains | 2026-02-20 | 2026-02-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14880 | Deleted - Sec.4 - Fill - Cut 22 - 1,120ccm - Fill in Open Drains | 2026-02-18 | 2026-02-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14900 | Deleted - Sec.4 - Fill - Cut 23 - 579ccm - Fill in Open Drains | 2026-02-23 | 2026-02-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.20840 | Deleted - Sec.5 - Culvert (36490) - Place RCBC crown units - (2.4W x 0.9H RCBC - (2 off) 4m | 2026-01-12 | 2026-01-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9580 | Deleted - Sec.4 - Fill - Fill 27 - 1,036ccm - Upper A | 2026-04-06 | 2026-04-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18010 | Deleted - Sec.5 - Powder Horn Trib Br - Detailed Earthworks Pier Pile Cap Pier 1 | 2026-03-21 | 2026-03-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18160 | Deleted - Sec.5 - Powder Horn Trib Br - Pier 2 Pile Cap - 8m3 | 2026-04-02 | 2026-04-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8510 | Deleted - Sec.3 - Fill - Fill 15 - 596ccm - Capping (Rail | 2026-04-26 | 2026-04-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8520 | Deleted - Sec.3 - Fill - Cut 12 - 429ccm - Capping (Rail | 2026-04-27 | 2026-04-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8530 | Deleted - Sec.3 - Fill - Fill 16 - 498ccm - Capping (Rail | 2026-04-28 | 2026-04-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.29000 | Deleted - Sec.6 - Culvert (37874) - Excavation 2000m2 2m deep - Basin Upstream
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.29010 | Deleted - Sec.6 - Culvert ID : E7-RD-456912-1 - Backfill Pipe
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.29020 | Deleted - Sec.6 - Culvert ID : E7-RD-456912-1 - Place Precast Wingwall
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.29030 | Deleted - Sec.6 - Culvert ID : E7-RD-456911-1 - Trench Excavation / Site Prep
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.22.5690 | Deleted - Sec.6 - PUP - Water - 37315 - WA01A DN300 RCP enveloper pipe for future water. | 2025-08-08 | 2025-08-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.22.13410 | Deleted - Sec.4 - PUP - Water - 24680 - NCP -14 -DN300 RCP enveloper pipe for future water. | 2025-08-12 | 2025-08-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12800 | Deleted - IRPL Review (20 B.days) - 1.08 - Stage 3 | 2025-05-27 | 2025-06-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12400 | Deleted - Start Package D9 - SD-01 - Flooding Model / Assessment - 1st Issue /FDVR
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2260 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-06-24 | 2025-06-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6600 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Corridor
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6610 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6620 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6630 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6640 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9470 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 2.01 - Stage 2 | 2025-03-07 | 2025-03-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9480 | Deleted - Incorporate IDC & CDR comments - 2.01 - Stage 2 | 2025-03-14 | 2025-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5470 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 3.07 - Stage 1 | 2024-12-06 | 2024-12-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.15550 | Deleted - Internal IDR Review (By JHG) - L2 - Stage 3 (Modified)
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8310 | Deleted - Issue Responses & Receive Comment Closeout - L2 - Stage 3 | 2025-07-24 | 2025-07-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20610 | Deleted - Sec.3 - Dirnaseer Rd Br - Install Precast Culvert crown Units | 2026-04-18 | 2026-04-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.11.15510 | Deleted - Stockpile Management
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.WAD.2020 | Deleted - Main work construction
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-2142 | Deleted - CoA - E23 - Secure Environmental approval- Clearing of native vegetation | 2025-03-05 | 2025-04-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9640 | Deleted - IRPL Review (5 B.days) - 3.07 - Stage 4 | 2025-08-13 | 2025-08-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2010 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-06-17 | 2025-06-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21490 | Deleted - Sec.5 - Powder Horn Trib Br - FRP - [40] MPa/10 in pedestal - 2m3 | 2026-07-07 | 2026-07-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21500 | Deleted - Sec.5 - Powder Horn Trib Br - FRP - [40] MPa/20 in Restraint Blocks - 12m3 | 2026-07-07 | 2026-07-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18180 | Deleted - Sec.5 - Powder Horn Trib Br - Back Wall South Abutment - 6m3 | 2026-07-07 | 2026-07-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18310 | Deleted - Sec.5 - Powder Horn Trib Br - Crane Pads for lift | 2026-07-31 | 2026-08-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18320 | Deleted - Sec.5 - Powder Horn Trib Br - Install bridge Support Bearings | 2026-08-02 | 2026-08-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2360 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-07-21 | 2025-07-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9200 | Deleted - Sec.4 - Fill - Fill 23 - 31,394ccm - Lower | 2026-02-21 | 2026-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9270 | Deleted - Sec.4 - Fill - Fill 30 - 9,377ccm - Lower | 2025-11-20 | 2025-11-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9280 | Deleted - Sec.4 - Fill - Fill 31 - 18,952ccm - Lower | 2025-10-28 | 2025-11-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9190 | Deleted - Sec.4 - Fill - Fill 22 - 71,319ccm - Lower | 2025-12-22 | 2026-02-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10710 | Deleted - Sec.5 - Fill - Fill 42 - 1,983ccm - Lower | 2025-11-17 | 2025-11-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13430 | Deleted - Design Deliverables Submission for Workshops and comments - 2.08 - Stage 3 | 2025-04-16 | 2025-04-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13440 | Deleted - Safety Assurance / SiD - 2.08 - Stage 3 | 2025-04-16 | 2025-04-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15870 | Deleted - Sec.3 - SIG - Install New Microlok/MLK/Internal Cable - 2,800m | 2026-05-02 | 2026-05-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15820 | Deleted - Sec.3 - SIG - Install New Signal Cable - 7,068m (24 runs | 2026-03-09 | 2026-03-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15830 | Deleted - Sec.3 - SIG - Install New Power Cable - 21,116m (24 runs | 2026-03-19 | 2026-04-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15860 | Deleted - Sec.3 - SIG - Install New Relay Internal Wiring - 11,400m | 2026-04-27 | 2026-05-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15880 | Deleted - Sec.3 - SIG - Install New Earthing Wire - 900m | 2026-05-14 | 2026-05-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12630 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Utilities Design - Z1 - 1.08 - Stage 1 | 2024-10-17 | 2024-12-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15050 | Deleted - CLHMMP - DPHI Lodgement and DPHI Review (2 weeks/ 14 cd) (1 month after SIMP approval) (To | 2025-02-19 | 2025-03-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15060 | Deleted - CLHMMP - JH Respond and incorporate to DPHI comments (To | 2025-03-19 | 2025-04-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.16220 | Deleted - CUDLP - Initial submiission to IRPL for review (4 weeks/ 28 cd) | 2024-11-12 | 2024-12-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15720 | Deleted - CUDLP - JH Finalise draft (Included in CSWMP) | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.17000 | Deleted - CUDLP - ER to review updated documents and Approve
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18220 | Deleted - Sec.5 - Powder Horn Trib Br - Detailed Earthworks Abutments (2off) | 2026-06-12 | 2026-06-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.20000 | Deleted - 12 weeks XO design /Vendor Review prior to manufacture | 2025-04-01 | 2025-07-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18200 | Deleted - Sec.5 - Powder Horn Trib Br - Detailed Earthworks Pier Pile Cap Abutment 2 | 2026-05-09 | 2026-05-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18210 | Deleted - Sec.5 - Powder Horn Trib Br - S&I Column sleeves to columns (2off) Abutment 2 | 2026-06-09 | 2026-06-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.16000 | Deleted - Sec.6 - Sig - Install New Relay Internal Wiring - 36,480m | 2026-04-26 | 2026-05-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.16010 | Deleted - Sec.6 - Sig - Install New Microlok/MLK/Internal Cable - 8,960m | 2026-05-19 | 2026-06-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.16020 | Deleted - Sec.6 - Sig - Install New Earthing Wire - 2880m | 2026-06-02 | 2026-06-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5690 | Deleted - Incorporate IDC & CDR / CCB and Stage 3 comments - 3.07 - Stage 4 | 2025-07-29 | 2025-08-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11740 | Deleted - Issue Responses & Receive Comment Closeout - 2.05 - Stage 1 | 2025-01-22 | 2025-01-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11750 | Deleted - Submission to IRPL SDR - 2.05 - Stage 1 | 2025-01-30 | 2025-01-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11760 | Deleted - IRPL Review (20 B.days) - 2.05 - Stage 1 | 2025-01-31 | 2025-02-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11770 | Deleted - Start Package 2.05 - Culverts - Under Rail - 2.05 - Stage 1 | 2024-10-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11810 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 2.05 - Stage 2 | 2025-03-28 | 2025-04-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.24000 | Deleted - Sec.3 - Culvert (15961) - Precast stitch pours for precast headwalls | 2026-04-20 | 2026-04-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.16340 | Deleted - CoA - C27 - consultation with TfNSW and relevant Councils -Construction Monitoring Programs | 2024-10-22 | 2024-11-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-1930 | Deleted - CoA - C32 - Approval by Planning Sec. prior to Construction Monitoring Programs ( 1 month before constructi | 2024-11-19 | 2024-11-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5250 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - LXs (Private)
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5260 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5270 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.14340 | Deleted - Sec.4 - IRPL Sleeper Stockpiles - Sec.4 | 2026-08-06 | 2026-08-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.91.14470 | Deleted - Sec.4 - Hold point for QA Inspection with IRPL - Sec.4 - Sleepers | 2026-08-02 | 2026-08-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.91.14520 | Deleted - Sec.4 - Hold point for QA Inspection with IRPL - Sec.4- Rail | 2026-09-24 | 2026-09-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14910 | Deleted - Sec.4 - Fill - Fill 30 -4,144ccm - Fill in Open Drains | 2026-02-24 | 2026-03-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14920 | Deleted - Sec.4 - Fill - Cut 24 - 1,278ccm - Fill in Open Drains | 2026-03-06 | 2026-03-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14930 | Deleted - Sec.4 - Fill - Fill 31 - 953ccm - Fill in Open Drains | 2026-03-08 | 2026-03-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14940 | Deleted - Sec.4 - Fill - Cut 25 - 550ccm - Fill in Open Drains | 2026-03-10 | 2026-03-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1930 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-07-25 | 2025-07-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6450 | Deleted - Internal IDR workshop (By BGE) - D9 - Stage 3 | 2025-06-12 | 2025-06-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9920 | Deleted - Design Presentation to IRPL - DPK Presentation - D9 - Stage 3 (Modified already part of original Contract Pr
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-1192 | Deleted - Telstra Quote & Send Contract | 2025-04-04 | 2025-06-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-1162 | Deleted - Telstra Quote & Send Contract | 2025-04-04 | 2025-06-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-1172 | Deleted - JH Contract Approval - Telstra - Dirnaseer | 2025-06-19 | 2025-07-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-1182 | Deleted - Telstra - Work Can Commence - Dirnaseer LGA |  | 2025-07-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14960 | Deleted - Sec.4 - Fill - Cut 26 - 1,300ccm - Fill in Open Drains | 2026-03-19 | 2026-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14970 | Deleted - Sec.4 - Fill - Cut 27 - 954ccm - Fill in Open Drains | 2026-03-21 | 2026-03-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | A1090 | Deleted - Sec.4 - Fill - Fill 26 - 1,822ccm - E2 Replace unsuitable - Foundation Treatment | 2026-03-20 | 2026-03-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12390 | Deleted - Safety Assurance / SiD - 1.09 - Stage 3 | 2025-05-23 | 2025-05-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12540 | Deleted - TfNSW Review (30 B.days) - Roads - Sec.1 | 2025-04-01 | 2025-05-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9490 | Deleted - Sec.4 - Fill - Cut 17 - 30ccm - Upper A | 2026-04-19 | 2026-04-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.G.101230 | Deleted - Comm. (Existing Telstra/Optus /NBN) Subcontractor Mob to Site | 2025-05-07 | 2025-05-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.G.101240 | Deleted - Engage Goldenfield Water Subcontractor | 2025-04-28 | 2025-06-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.G.101250 | Deleted - Goldenfield Water Subcontractor Mob to Site | 2025-06-24 | 2025-07-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-91 | Deleted - Prepare Tender Docs & Issue RFT - Goldenfields Water | 2025-03-07 | 2025-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.C.10TR-138 | Deleted - Manufacturing & Delivery - Traffic Signals | 2025-05-08 | 2025-07-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.15-324 | Deleted - Proponent provides a copy of notifcation & record of the registered Aboriginal parties to Heritage NSW & rel | 2024-11-20 | 2024-11-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4630 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-03-24 | 2025-03-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10960 | Deleted - Submission to IRPL DDR - 1.04 - Stage 3 | 2025-07-25 | 2025-07-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9120 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 3.05 - Stage 3 | 2025-06-12 | 2025-06-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.11.13260 | Deleted - Sec.6 - Telstra relocation tie in at Grogan Road intersection with Freemans Lane CH41500 | 2025-07-21 | 2025-07-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16720 | Deleted - Sec.3 - Public LX - PU15950 - Drainage - Detailed backfill | 2026-01-26 | 2026-01-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.8650 | Deleted - Sec.3 - Fill - Fill 11 - 204ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-05-24 | 2026-05-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.8660 | Deleted - Sec.3 - Fill - Cut 08 - 141ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-05-26 | 2026-05-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.8670 | Deleted - Sec.3 - Fill - Fill 12 - 118ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-05-27 | 2026-05-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6050 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Bridges - Dudauman Creek Underbridge
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.14510 | Deleted - Possession (Sept 2025) - Leveling Ballast/Track before Crossover placing - LOE | 2025-09-13 | 2025-09-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.13420 | Deleted - Float before Sept 2025 Sec.1 - Track - converted LOE | 2025-07-22 | 2025-09-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10W-687 | Deleted -- Catchpoints (IRPL Free-Issue) - Manufacturing & Delivery - Sec.3 - 4 off (1 in18) - | 2025-03-14 | 2025-09-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10W-697 | Deleted - Catchpoints (IRPL Free-Issue) - Manufacturing & Delivery - Sec.3 - 1 off (1 in10.5) - | 2025-03-14 | 2025-09-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10W-757 | Deleted - Catchpoints (IRPL Free-Issue) - Manufacturing & Delivery - Sec.6 - 2 off - | 2025-03-14 | 2025-09-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15180 | Deleted - Sec.3 - Fill - Fill 19 - 2,321ccm - Fill in Open Drains | 2026-01-14 | 2026-01-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14990 | Deleted - Sec.3 - Fill - Cut 06 - 1,331ccm - Fill in Open Drains | 2025-11-20 | 2025-11-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15000 | Deleted - Sec.3 - Fill - Fill 10 - 329ccm - Fill in Open Drains | 2025-11-23 | 2025-11-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15010 | Deleted - Sec.3 - Fill - Cut 07 - 529ccm - Fill in Open Drains | 2025-11-24 | 2025-11-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15020 | Deleted - Sec.3 - Fill - Fill 11 - 432ccm - Fill in Open Drains | 2025-11-26 | 2025-11-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.24340 | Deleted - Sec.3 - Culvert ID : E7-RA-435050-1 - Place Precast Apron Slab | 2026-03-02 | 2026-03-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10140 | Deleted - Sec.4 - Fill - Fill 29 - 552ccm - Capping (Rail | 2026-06-13 | 2026-06-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10150 | Deleted - Sec.4 - Fill - Cut 23 - 545ccm - Capping (Rail | 2026-06-14 | 2026-06-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10160 | Deleted - Sec.4 - Fill - Fill 30 - 1,141ccm - Capping (Rail | 2026-06-16 | 2026-06-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10170 | Deleted - Sec.4 - Fill - Cut 24 - 1,259ccm - Capping (Rail | 2026-06-18 | 2026-06-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10180 | Deleted - Sec.4 - Fill - Fill 31 - 921ccm - Capping (Rail | 2026-06-20 | 2026-06-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10190 | Deleted - Sec.4 - Fill - Cut 25 - 801ccm - Capping (Rail | 2026-06-21 | 2026-06-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10200 | Deleted - Sec.4 - Fill - Fill 32 - 1,177ccm - Capping (Rail | 2026-06-22 | 2026-06-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10220 | Deleted - Sec.4 - Fill - Cut 26 - 938ccm - Capping (Rail | 2026-06-24 | 2026-06-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9520 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Geotechnical GIR - 2.01 - Stage 3 | 2025-03-21 | 2025-05-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20680 | Deleted - Sec.3 - Dirnaseer Rd Br - Scour protection 2off | 2026-05-21 | 2026-05-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.8100 | Deleted - Sec.3 - Fill - Fill 17 - 11,674ccm - Upper A | 2026-04-17 | 2026-04-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.8130 | Deleted - Sec.3 - Fill - Fill 18 - 3,078ccm - Upper A | 2026-04-24 | 2026-04-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15520 | Deleted - CWMP - DPHI Completion of Review/ Approval (2 weeks/ 14 cd) (1 month after SIMP approval) (To | 2025-03-19 | 2025-04-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15840 | Deleted - CSIMP - Finalise SIMP (To | 2025-01-14 | 2025-01-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.20060 | Deleted - Sec.6 - Possession ( Sep 2026) - Stockinbingal Trackworks - LOE
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.20050 | Deleted - Sec.6 - Float before Possession September 2026 - LOE
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.11.15810 | Deleted - Stockpile Management
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10610 | Deleted - Sec.5 - Cut - Cut 34 - 4,910ccm - OD Soil / Soil | 2025-10-30 | 2025-11-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10970 | Deleted - IRPL Review (20 B.days) - 1.04 - Stage 3 | 2025-07-28 | 2025-08-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5570 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14810 | Deleted - Sec.4 - Fill - Cut 34 - 373ccm - Fill in Open Drains - double up | 2026-03-23 | 2026-03-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14820 | Deleted - Sec.4 - Fill - Fill 25 - 173ccm - Fill in Open Drains | 2026-02-03 | 2026-02-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14830 | Deleted - Sec.4 - Fill - Fill 26 - 476ccm - Fill in Open Drains | 2026-02-04 | 2026-02-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14840 | Deleted - Sec.4 - Fill - Cut 20 - 1,103ccm - Fill in Open Drains | 2026-02-06 | 2026-02-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14850 | Deleted - Sec.4 - Fill - Fill 27 - 222ccm - Fill in Open Drains | 2026-02-08 | 2026-02-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14860 | Deleted - Sec.4 - Fill - Cut 21 - 398ccm - Fill in Open Drains | 2026-02-09 | 2026-02-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14870 | Deleted - Sec.4 - Fill - Fill 28 - 3,781ccm - Fill in Open Drains | 2026-02-10 | 2026-02-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2420 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-07-09 | 2025-07-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2400 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Culverts - Under Rail | 2025-08-04 | 2025-08-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-2332 | Deleted - CoA - E24 - Prepare Biodiversity survey/ Inspection document | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8700 | Deleted - Safety Assurance / SiD - E8 - Stage 3 | 2025-05-30 | 2025-06-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10130 | Deleted - Incorporate IDC & CDR comments - 1.06 - Stage 1 | 2024-12-13 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11210 | Deleted - IRPL Review (20 B.days) - 1.03 - Stage 2 | 2025-03-04 | 2025-03-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11220 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Earthworks Formation Design Documentation - 1.03 - | 2025-03-04 | 2025-04-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8580 | Deleted - Sec.3 - Fill - Cut 15 - 426ccm - Capping (Rail | 2026-05-04 | 2026-05-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8590 | Deleted - Sec.3 - Fill - Fill 19 - 429ccm - Capping (Rail | 2026-05-05 | 2026-05-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8600 | Deleted - Sec.3 - Fill - Cut 16 - 665ccm - Capping (Rail | 2026-05-06 | 2026-05-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8610 | Deleted - Sec.3 - Fill - Fill 20 - 1,905ccm - Capping (Rail | 2026-05-12 | 2026-05-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8410 | Deleted - Sec.3 - Fill - Fill 10 - 1,567ccm - Capping (Rail | 2026-04-04 | 2026-04-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11280 | Deleted - Submission to IRPL DDR - 1.03 - Stage 3 | 2025-05-09 | 2025-05-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11290 | Deleted - IRPL Review (20 B.days) - 1.03 - Stage 3 | 2025-05-12 | 2025-06-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11300 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Earthworks Formation Design Documentation - Zone 1 | 2025-05-26 | 2025-06-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11310 | Deleted - Incorporate IDC & CDR / CCB and Stage 3 comments - 1.03 - Stage 4 | 2025-07-01 | 2025-07-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11320 | Deleted - IRPL Review (5 B.days) - 1.03 - Stage 4 | 2025-07-15 | 2025-07-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.C.169500 | Deleted - Powder Horn Tributary Bridge - Fabrication of Bridge span (Standard PSC Slab Span 14m (IRPL) | 2025-12-16 | 2026-02-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21040. | Deleted - Burley Griffin Way Bridge - Detailed Earthworks Pier Pile Cap Abutment 2
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21050. | Deleted - Burley Griffin Way Bridge - Abutment 2 Pile Cap - 15m3
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21170. | Deleted - Burley Griffin Way Bridge - Precast Abutment Panels - North Abutment
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21180. | Deleted - Burley Griffin Way Bridge - Abutment Precast Panels North Abutment Capping
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21190. | Deleted - Burley Griffin Way Bridge - Mechanically Stabilised Earth Walls (MSE) Walls Construction North Abutment & W
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21140. | Deleted - Burley Griffin Way Bridge - FRP - [40] MPa/20 in Restraint Blocks - 8m3
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-100 | Deleted - APA Group 100% & Approve Final Alignment & Design | 2025-02-14 | 2025-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-101 | Deleted - JH Final Review & Integrate Design | 2025-03-21 | 2025-04-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-102 | Deleted - Prepare Tender Docs and Issue RFT / Pricing by Suppliers /Subcontractors | 2025-04-04 | 2025-06-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-2342 | Deleted - CoA - E24 - Demonstrate to the satisfaction of the Planning Secretary Biodiversity document | 2025-02-05 | 2025-03-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.5-1024 | Deleted - CoA - E133 - IRPL to review updated documents and Approve - Aboriginal Cultural Values PLan |  | 2024-11-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9520 | Deleted - Safety Assurance / SiD - E2 - Stage 3 | 2025-06-24 | 2025-06-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3740 | Deleted - Configuration Change Acceptance Notice | 2025-03-04 | 2025-03-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9910 | Deleted - Internal IDR Review (By JHG) - D9 - Stage 3 (Modified)
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21820 | Deleted - Sec.3 - Dirnaseer Rd Br - FRP - [40] MPa/10 in pedestals / (plinths) - 4m3 | 2026-02-12 | 2026-02-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.91.14500 | Deleted - Sec.6 - Hold point for QA Inspection with IRPL - Sec.6 - 37480 to 38000 - Sleepers | 2026-09-10 | 2026-09-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11910 | Deleted - Issue Responses & Receive Comment Closeout - 2.05 - Stage 3 | 2025-06-20 | 2025-06-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11800 | Deleted - Safety Assurance / SiD - 2.05 - Stage 2 | 2025-03-21 | 2025-03-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11890 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 2.05 - Stage 3 | 2025-06-13 | 2025-06-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11900 | Deleted - Incorporate IDC & CDR comments - 2.05 - Stage 3 | 2025-06-20 | 2025-06-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11920 | Deleted - Submission to IRPL DDR - 2.05 - Stage 3 | 2025-06-27 | 2025-06-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9690 | Deleted - Design Deliverables Submission for Workshops and comments - 3.03 - Stage 1 | 2024-12-13 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9700 | Deleted - Safety Assurance / SiD - 3.03 - Stage 1 | 2024-12-13 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20620 | Deleted - Sec.3 - Dirnaseer Rd Br - Headwall North - 1m3 | 2026-04-21 | 2026-04-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20630 | Deleted - Sec.3 - Dirnaseer Rd Br - Headwall South - 1m3 | 2026-04-24 | 2026-04-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7090 | Deleted - Incorporate IDC & CDR comments - W.05 - Stage 4 | 2025-07-28 | 2025-08-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7110 | Deleted - CDR Package Complete W.05 - Geotech Gap Analysis & SI - W.05 - Stage 4 |  | 2025-08-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9660 | Deleted - IRPL Review (5 B.days) - W.05 - Stage 4 | 2025-08-05 | 2025-08-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7080 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Geotech Gap Analysis & SI - W.05 - Stage 4 | 2025-06-30 | 2025-08-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5110 | Deleted - Incorporate IDC & CDR comments - W.02 - Stage 1 | 2024-12-06 | 2024-12-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8880 | Deleted - Safety Assurance / SiD - 3.05 - Stage 1 | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6580 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6590 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6550 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Corridor
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6740 | Deleted - Configuration Change Acceptance Notice (H6, H7, H8 & H9)
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6700 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Bridges - (H6, H7, H8 & H9)
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6710 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL (H6, H7, H8, & H9)
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6720 | Deleted - IRPL Reviews & Approves CCR Submission (H6, H7, H8 & H9)
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6730 | Deleted - IRPL Submits CCB to SM Sub CCB (H6, H7, H8, & H9)
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.16190 | Deleted - CTTAMP - Initial submiission to IRPL for review (4 weeks/ 28 cd) | 2024-11-13 | 2024-12-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6370 | Deleted - Internal IDR workshop (By BGE) - D9 - Stage 2 | 2025-04-03 | 2025-04-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6390 | Deleted - Review of IDR comment response and final review - D9 - Stage 2 | 2025-04-10 | 2025-04-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6400 | Deleted - Incorporate IDR comments - D9 - Stage 2 | 2025-04-17 | 2025-04-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6410 | Deleted - Issue Responses & Receive Comment Closeout - D9 - Stage 2 | 2025-04-17 | 2025-04-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6420 | Deleted - Submission to IRPL - D9 - Stage 2 | 2025-04-29 | 2025-04-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10940 | Deleted - Incorporate IDC & CDR comments - 1.04 - Stage 3 | 2025-07-18 | 2025-07-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10910 | Deleted - Design Deliverables Submission for Workshops and comments - 1.04 - Stage 3 | 2025-07-04 | 2025-07-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10920 | Deleted - Safety Assurance / SiD - 1.04 - Stage 3 | 2025-07-04 | 2025-07-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10930 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.04 - Stage 3 | 2025-07-11 | 2025-07-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8370 | Deleted - Sec.3 - Fill - Fill 19 - 579ccm - Structural Fill | 2026-05-03 | 2026-05-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.EW.10C-3 | Deleted - Engage Subcontractor - Air Monitoring / Hygienist (Not required) | 2025-02-21 | 2025-04-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.EW.10C-4 | Deleted - Subcontractor Mob to Site - Air Monitoring / Hygienist (Not required) | 2025-04-22 | 2025-04-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18280 | Deleted - Sec.5 - Powder Horn Trib Br - install access walkways | 2026-09-01 | 2026-09-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6860 | Deleted - Sec.2 - Fill - Fill 05 - 5,299ccm - Lower | 2025-10-21 | 2025-10-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.11360 | Deleted - Sec.5 - Fill - Fill 37- 604ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-08-29 | 2026-08-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.85.13410 | Deleted - Sec.2 - Landscaping - Ch2901-6000 - double up | 2026-01-31 | 2026-02-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.85.13960 | Deleted - Sec.2 - Landscaping - Ch2901-8400 | 2026-07-06 | 2026-07-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6870 | Deleted - Sec.2 - Fill - Fill 06 - 9,415ccm - Lower | 2025-11-11 | 2025-11-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9150 | Deleted - Submission to IRPL DDR - 3.05 - Stage 3 | 2025-06-26 | 2025-06-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21670 | Deleted - Sec.4 - Isobel Ck Trib Br - FRP - Tee Roff Diaphragm Beam (2off) - Pier 1 - 3m3 | 2026-05-08 | 2026-05-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21680 | Deleted - Sec.4 - Isobel Ck Trib Br - FRP - Tee Roff Diaphragm Beam (2off) - Pier 2 - 3m3 | 2026-05-08 | 2026-05-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4640 | Deleted - Configuration Change Acceptance Notice | 2025-04-08 | 2025-04-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-612 | Deleted - JH Design & Review/Comment | 2025-02-28 | 2025-03-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-622 | Deleted - Optus - 100% & Approve Final Alignment & Design | 2025-03-14 | 2025-04-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-712 | Deleted - Optus - Work Can Commence - |  | 2025-07-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.10490 | Deleted - CFEMP - DPHI Lodgement and DPHI Review (2 weeks/ 14 cd)-Flood Emergency / Bushfire Emergency Plan CoA -C24, | 2025-04-03 | 2025-04-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.10500 | Deleted - CFEMP - JH Respond and incorporate to DPHI comments-Flood Emergency / Bushfire Emergency Plan CoA -C24, E98 | 2025-04-17 | 2025-05-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10670 | Deleted - Incorporate IDC & CDR / CCB and Stage 3 comments - 1.05 - Stage 4 | 2025-08-12 | 2025-08-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10680 | Deleted - IRPL Review (5 B.days) - 1.05 - Stage 4 | 2025-08-26 | 2025-09-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.18510 | Deleted - Sec.5 - Float before Track can commence - Sec.5 - converted LOE | 2026-07-06 | 2026-10-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15930 | Deleted - Sec.1 - Sig - Install New Relay Internal Wiring - 9,120m - QTY TBC | 2026-01-17 | 2026-01-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3800 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Road Drainage - 3.10 - Stage 3 | 2025-05-01 | 2025-06-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3810 | Deleted - Design Deliverables Submission for Workshops and comments - 3.10 - Stage 3 | 2025-06-05 | 2025-06-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3820 | Deleted - Safety Assurance / SiD - 3.10 - Stage 3 | 2025-06-05 | 2025-06-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.S.10C-360 | Deleted - Engage Subcontractor - underboring (To merge with HDD) | 2025-05-08 | 2025-07-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10W-47 | Deleted - Pricing by Suppliers / Subcontractors- Instrumentation and Montoring (Not required) | 2025-05-23 | 2025-06-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10W-57 | Deleted - Package Review / Approval - Instrumentation and Montoring (Not required) | 2025-06-23 | 2025-07-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10W-67 | Deleted - Package Placement - Instrumentation and Montoring | 2025-07-07 | 2025-07-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.S.10C-370 | Deleted - Subcontractor Mob to Site - underboring | 2025-07-04 | 2025-07-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.27520 | Deleted - Sec.4 - Culvert (22624) - Excavation 1300m2 1m deep - Basin Upstream | 2026-04-03 | 2026-04-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.27500 | Deleted - Sec.4 - Culvert (19330) - Excavation 2000m2 1m deep - Basin Upstream | 2026-05-11 | 2026-05-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.14590 | Deleted - Sec.4 - Sec.4 - Culvert ID : E7-RD-442700-1 - Trench Excavation/ Culvert site prep | 2026-01-05 | 2026-01-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2700 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Geotechnical Design | 2025-08-20 | 2025-08-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10360 | Deleted - Sec.4 - Fill - Fill 27 - 93ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-07-04 | 2026-07-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10370 | Deleted - Sec.4 - Fill - Cut 21 - 300ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-07-06 | 2026-07-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.28450 | Deleted - Sec.5 - Culvert (37212) - Precast stitch pours /cure
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.28460 | Deleted - Sec.5 - Culvert (37212) - Construct Scour protection
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.24800 | Deleted - Sec.3 - Culvert (12447 - Place 20*1200 RCP Pipe | 2026-04-30 | 2026-04-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.24810 | Deleted - Sec.3 - Culvert (12447) - Backfill Pipe | 2026-05-01 | 2026-05-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.24820 | Deleted - Sec.3 - Culvert (12447) - Place Precast Apron Slab | 2026-05-02 | 2026-05-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.24830 | Deleted - Sec.3 - Culvert (12447 - Place Precast Wingwall | 2026-05-03 | 2026-05-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.22.14280 | Deleted - Sec.3 - ELO-15 - Essential Energy Protect LV East Side Ironbong Road - Ch9342 (Not required)
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.28840 | Deleted - Sec.4 - Culvert ID : E7-RD-437360-1 - Excavation 500m2 1.5m deep - Basin Upstream
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9060 | Deleted - Issue Responses & Receive Comment Closeout - 1.10 - Stage 3 | 2025-06-20 | 2025-06-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12200 | Deleted - Start Package 3.07 - Roads - BGW - 3.07 - Stage 1 | 2024-10-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12680 | Deleted - TfNSW/ IV Review (30 B.days) - 3.07 - Stage 1 - BGW Road | 2025-01-06 | 2025-02-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15240 | Deleted - Sec.1 - Sig - Install New DW Locations (3 off +1) (5341 to 470971) | 2026-03-14 | 2026-03-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.11280 | Deleted - Sec.5 - Fill - Fill 36 - 1,107ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-08-06 | 2026-08-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10250 | Deleted - Sec.4 - Fill - Fill 34 - 1,009ccm - Capping (Rail | 2026-06-27 | 2026-06-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.G.101260 | Deleted - Engage Gas Relocation Subcontractor | 2025-04-28 | 2025-06-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20290 | Deleted - Sec.4 - Isobel Ck Br - FRP - [40] MPa/20 in North Abutment Columns - 15m3 | 2026-04-09 | 2026-04-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4200 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Culverts | 2025-03-03 | 2025-03-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11150 | Deleted - Design Deliverables Submission for Workshops and comments - 1.03 - Stage 2 | 2025-02-03 | 2025-02-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5970 | Deleted - Incorporate IDC & CDR / CCB and Stage 3 comments - 3.02 - Stage 4 | 2025-09-03 | 2025-09-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5980 | Deleted - IRPL Review (5 B.days) - 3.02 - Stage 4 | 2025-09-17 | 2025-09-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5990 | Deleted - CDR Package Complete 3.02 - Geotechnical Design - 3.02 - Stage 4 |  | 2025-09-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8540 | Deleted - Sec.3 - Fill - Fill 17 - 1,490ccm - Capping (Rail | 2026-04-29 | 2026-04-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8550 | Deleted - Sec.3 - Fill - Cut 13 - 766ccm - Capping (Rail | 2026-05-01 | 2026-05-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.91.14490 | Deleted - Sec.6 - Hold point for QA Inspection with IRPL - Sec.6 CRN - Sleepers | 2026-03-30 | 2026-04-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19830 | Deleted - Sec.5 - Powder Horn Trib Br - Detailed Earthworks Pile Cap Abutment 1 | 2026-05-03 | 2026-05-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15150 | Deleted - Sec.3 - Fill - Cut 14 - 444ccm - Fill in Open Drains | 2025-12-23 | 2025-12-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.8890 | Deleted - IRPL Review (20 B.days) - 1.10 - Stage 1 | 2025-01-10 | 2025-02-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-702 | Deleted - JH Contract Approval - Optus | 2025-07-17 | 2025-07-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.8860 | Deleted - Incorporate IDC & CDR comments - 1.10 - Stage 1 | 2024-12-20 | 2025-01-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.8880 | Deleted - Submission to IRPL SDR - 1.10 - Stage 1 | 2025-01-10 | 2025-01-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.8900 | Deleted - Start Package 1.10 - Drainage - 1.10 - Stage 1 | 2024-10-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.8970 | Deleted - Issue Responses & Receive Comment Closeout - 1.10 - Stage 2 | 2025-03-31 | 2025-04-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.8980 | Deleted - Submission to IRPL PDR - 1.10 - Stage 2 | 2025-04-07 | 2025-04-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.8990 | Deleted - IRPL Review (20 B.days) - 1.10 - Stage 2 | 2025-04-07 | 2025-05-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9150 | Deleted - TfNSW Review (30 B.days) - 1.10 - Stage 2 - Road Drainage - Sec.1 | 2025-04-07 | 2025-05-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.8920 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Road Drainage - 1.10 - Stage 2 | 2025-01-10 | 2025-03-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9150 | Deleted - Sec.4 - Fill - PR21200 - 102ccm | 2026-05-03 | 2026-05-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9160 | Deleted - Sec.4 - Fill - PR22750 - 143ccm | 2026-05-08 | 2026-05-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14200 | Deleted - Sec.4 - Construct Temporary Creek Crossing - Isobel Creek Tribitary for traffic | 2025-07-13 | 2025-07-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14210 | Deleted - Sec.4 - Construct Temporary Creek Crossing - Isobel Creek for traffic | 2025-07-12 | 2025-07-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8330 | Deleted - Submission to IRPL2 - L2 - Stage 3 | 2025-07-31 | 2025-07-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8340 | Deleted - IRPL Review (20 B.days) - L2 - Stage 3 | 2025-08-01 | 2025-08-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.15560 | Deleted - Design Presentation to IRPL - DPK Presentation L2 - Stage 3 (Modified already part of original Contract Pro
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8180 | Deleted - Safety Assurance / SiD - L2 - Stage 2 | 2025-04-22 | 2025-04-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8260 | Deleted - Design Development - Stage 3 - Detailed Design / DDD - Maintenance plans & Access - L2 - Stage 3 | 2025-05-22 | 2025-07-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8270 | Deleted - Internal IDR workshop (By BGE) - L2 - Stage 3 | 2025-07-10 | 2025-07-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8290 | Deleted - Review of IDR comment response and final review - L2 - Stage 3 | 2025-07-17 | 2025-07-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-1240 | Deleted - CoA - A11 - Staging Report Approved (One month before commencement of construction) | 2025-05-02 | 2025-05-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.16120 | Deleted - CoA - A11/A12 - Develop Staging Report (Delete0 | 2025-03-17 | 2025-03-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.16130 | Deleted - CoA - A11/A12 - Submit Staging Report for Approval with ARTC/IRPL | 2025-04-01 | 2025-05-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-1260 | Deleted - CoA - C1 - Construction Environmental Management Framework (CEMF) endorsed by ER (1 month before lodgement o | 2024-11-13 | 2024-12-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.16140 | Deleted - CoA - C1 - Develop Construction Environmental Management Framework (CEMF) | 2024-09-30 | 2024-10-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9500 | Deleted - Submission to IRPL PDR - 2.01 - Stage 2 | 2025-03-21 | 2025-03-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9510 | Deleted - IRPL Review (20 B.days) - 2.01 - Stage 2 | 2025-03-24 | 2025-04-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.16910 | Deleted - Sec.5 - Powder Horn Ck Br - Pier 2 Pile Cap - 11m3 | 2026-03-24 | 2026-03-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.17110 | Deleted - Sec.5 - Powder Horn Creek Bridge -Deck | 2026-06-14 | 2026-06-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15620 | Deleted - Sec.3 - SIG - Install New LXG - Axle counter/light /booms (2 off) - Ironbong Road | 2026-03-14 | 2026-03-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19700 | Deleted - Sec.4 - Isobel Ck Br - Pier Pad Footing 1 Foundation - 72m3 | 2026-02-23 | 2026-02-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8480 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Geotechnical Design - 1.02 - Stage 4 | 2025-07-28 | 2025-09-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.16160 | Deleted - CoA - C1 - Review and comply with the 0-0000-900-EEC-00-SP -0002 Specification Construction Env. Mang Plan ( | 2024-11-13 | 2024-12-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8260 | Deleted - Safety Assurance / SiD - 1.02 - Stage 1 | 2025-01-24 | 2025-01-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5500 | Deleted - Submission to IRPL SDR - 3.07 - Stage 1 | 2024-12-20 | 2024-12-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20940 | Deleted - Sec.2 - Ulandra Ck Br - Wing Walls - South side 2 No. - 11m3 | 2026-05-06 | 2026-05-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20920 | Deleted - Sec.2 - Ulandra Ck Br - Culvert Wingwalls - South - 8m3 | 2026-04-26 | 2026-04-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7680 | Deleted - Signalling Design FDD+PDD to compare (inc Xmas) (approx 18 weeks) - LOE | 2024-10-25 | 2025-03-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2950 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Rail Systems (Power/Signalling) | 2025-03-19 | 2025-03-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8610 | Deleted - Design Deliverables Submission for Workshops and comments - 1.01 - Stage 2 | 2025-02-17 | 2025-02-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8590 | Deleted - IRPL Review (20 B.days) - 1.01 - Stage 1 | 2024-12-09 | 2025-01-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12300 | Deleted - Start Package 1.01 - Geotechnical GIR - 1.01 - Stage 1 | 2024-10-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8600 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Geotechnical GIR - 1.01 - Stage 2 | 2024-12-06 | 2025-02-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8620 | Deleted - Safety Assurance / SiD - 1.01 - Stage 2 | 2025-02-17 | 2025-02-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8630 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.01 - Stage 2 | 2025-02-24 | 2025-02-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5290 | Deleted - Design Deliverables Submission for Workshops and comments - W.02 - Stage 3 | 2025-04-28 | 2025-05-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5250 | Deleted - Submission to IRPL PDR - W.02 - Stage 2 | 2025-03-17 | 2025-03-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5260 | Deleted - IRPL Review (20 B.days) - W.02 - Stage 2 - Noise | 2025-03-18 | 2025-04-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-1412 | Deleted - Certify Design & Request Cutover
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.8930 | Deleted - Design Deliverables Submission for Workshops and comments - Stage 2 drainage (1) - 1.10 - Stage 2 | 2025-03-17 | 2025-03-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.8940 | Deleted - Safety Assurance / SiD - 1.10 - Stage 2 | 2025-03-17 | 2025-03-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5640 | Deleted - Incorporate IDC & CDR comments - 3.07 - Stage 3 | 2025-06-06 | 2025-06-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12690 | Deleted - TfNSW/ IV Review (30 B.days) - 3.07 - Stage 4 - BGW Road | 2025-08-13 | 2025-09-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-1790 | Deleted - CoA - E84 - Surface Water Monitoring Program in consultation with DCCEEW Water | 2024-11-27 | 2024-12-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12850 | Deleted - Issue Responses & Receive Comment Closeout - 1.08 - Stage 4 | 2025-07-09 | 2025-07-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12740 | Deleted - Design Deliverables Submission for Workshops and comments - 1.08 - Stage 3 | 2025-05-05 | 2025-05-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8250 | Deleted - Design Deliverables Submission for Workshops and comments - 1.02 - Stage 1 | 2025-01-24 | 2025-01-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8320 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Geotechnical Design - 1.02 - Stage 2 | 2025-02-17 | 2025-04-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8330 | Deleted - Design Deliverables Submission for Workshops and comments - 1.02 - Stage 2 | 2025-04-14 | 2025-04-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8340 | Deleted - Safety Assurance / SiD - 1.02 - Stage 2 | 2025-04-14 | 2025-04-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.22.6410 | Deleted - Sec.4 - PUP - Water - 19790 - NCP -12 -DN300 RCP enveloper pipe for future water. | 2025-08-08 | 2025-08-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5850 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Bridges - Powder Horn Creek Underbridge
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5860 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5870 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16760 | Deleted - Sec.3 - Public LX - PU15950 - Drainage - LX Culvert - Trench Excavation/ Culvert site prep | 2026-01-26 | 2026-01-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12620 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Utility Coordination Plans - 1.08 - Stage 1 | 2024-10-17 | 2024-12-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16680 | Deleted - Sec.3 - Public LX - PU15950 - Drainage - Install 900 RCP - 2 off - 5m | 2026-01-23 | 2026-01-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16690 | Deleted - Sec.3 - Public LX - PU15950 - Drainage - Detailed backfill | 2026-01-24 | 2026-01-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14740 | Deleted - Sec.5 - Fill - Cut 34 - 2,627ccm - Fill in Open Drains | 2026-05-14 | 2026-05-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1940 | Deleted - Configuration Change Acceptance Notice | 2025-08-05 | 2025-08-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3700 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Culverts | 2025-03-03 | 2025-03-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3710 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-01-31 | 2025-02-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3630 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-02-18 | 2025-02-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3640 | Deleted - Configuration Change Acceptance Notice | 2025-02-20 | 2025-02-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10020 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Earthworks Formation Design Documentation - Zone 3 / | 2025-06-30 | 2025-08-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10040 | Deleted - IRPL Review (5 B.days) - 3.03 - Stage 4 | 2025-08-20 | 2025-08-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10050 | Deleted - CDR Package Complete 3.03 - Earthworks Formation Design Documentation - Zone 3 /Sec.6 - 3.03 - Stage 4 |  | 2025-08-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-832 | Deleted - NBN Quote & Send Contract | 2025-04-04 | 2025-06-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-742 | Deleted - JH Final Review & Integrate Design -NBN | 2025-03-21 | 2025-04-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-752 | Deleted - JH Design & Review/Comment | 2025-01-31 | 2025-02-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-762 | Deleted - NBN 100% & Approve Final Alignment & Design | 2025-02-14 | 2025-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-842 | Deleted - JH Contract Approval - NBN | 2025-06-19 | 2025-07-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-852 | Deleted - NBN - Work Can Commence - |  | 2025-07-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.C.10TR-118 | Deleted - Package Review / Approval- Street Lighting / Traffic Signals | 2025-04-04 | 2025-04-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.16740 | Deleted - CTTAMP - Draft Presentation to TfNSW (Submit to IRPL) (To
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.10200 | Deleted - CTTAMP - Approvals and Consistency Assessments (To | 2025-01-21 | 2025-01-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-2462 | Deleted - CoA - E39_Old - Removal of Seed from Native Plant and Used as revegetation - Site (To | 2025-01-13 | 2025-01-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-2492 | Deleted - CoA - E39_Old - Seed from native plants to be removed must be collected ALL Seasons - site (To | 2024-09-30 | 2025-05-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.BI-1390 | Deleted - CoA - E40, E41_NEW - IRPL Review and issue Comments -Environmental - Fauna Crossing - Baseline Monitoring (T
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5650 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Bridges - Isobel Creek Tributary Underb
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5900 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Bridges - Powder Horn Creek Underbridge
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5910 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13270 | Deleted - Incorporate IDC & CDR comments - 2.08 - Stage 1 | 2024-12-12 | 2024-12-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5930 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6060 | Deleted - Submission to IRPL SDR - W.09 - Stage 1 | 2024-12-13 | 2024-12-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6030 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - W.09 - Stage 1 | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6040 | Deleted - Incorporate IDC & CDR comments - W.09 - Stage 1 | 2024-12-06 | 2024-12-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6050 | Deleted - Issue Responses & Receive Comment Closeout - W.09 - Stage 1 | 2024-12-06 | 2024-12-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.9830 | Deleted - Sec.4 - Fill - Cut 20 - 1,240ccm - Structural Fill | 2026-05-23 | 2026-05-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.9840 | Deleted - Sec.4 - Fill - Fill 27 - 377ccm - Structural Fill | 2026-05-26 | 2026-05-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9400 | Deleted - Incorporate IDC & CDR comments - 2.01 - Stage 1 | 2024-12-12 | 2024-12-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9380 | Deleted - Safety Assurance / SiD - 2.01 - Stage 1 | 2024-11-28 | 2024-12-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-23 | Deleted - Essential Energy - Work Can Commence - Illabo LGA |  | 2025-07-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-16 | Deleted - Prepare Tender Docs & Issue RFT ASP Lvl1 - Essential Energy - Illabo LGA | 2025-04-22 | 2025-05-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-17 | Deleted - Pricing by Suppliers / Subcontractors - Essential Energy - Illabo LGA | 2025-05-07 | 2025-05-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-128 | Deleted - Telstra Design 80% & Review /Comments | 2024-11-07 | 2025-01-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-129 | Deleted - JH Final Review & Integrate Design -Telstra | 2025-03-21 | 2025-04-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-572 | Deleted - Telstra 100% & Approve Final Alignment & Design | 2025-02-14 | 2025-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-272 | Deleted - Telstra Quote & Send Contract | 2025-04-04 | 2025-06-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-282 | Deleted - JH Contract Approval - Telstra - Cootamundra | 2025-06-19 | 2025-07-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14000 | Deleted - Sec.5 - Cut - Cut 28 - 1,602ccm - MW Rip - Rock | 2025-08-29 | 2025-08-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10640 | Deleted - Sec.5 - Fill - PU33780 - 595ccm | 2026-04-27 | 2026-04-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10650 | Deleted - Sec.5 - Fill - PR34950 - 149ccm | 2026-04-28 | 2026-04-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15940 | Deleted - Sec.1 - Sig - Install New Microlok/MLK/Internal Cable - 2,240m - QTY TBC | 2026-01-29 | 2026-02-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15950 | Deleted - Sec.1 - Sig - Install New Earthing Wire - 720m - QTY TBC | 2026-02-03 | 2026-02-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.74.14880 | Deleted - Sec.1 - Sig - Electrical install / Connected | 2026-02-19 | 2026-02-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15570 | Deleted - Sec.1 - Sig - Install New Main Signals (1 off) - IJ18 - Up - 468.124 | 2026-03-14 | 2026-03-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15580 | Deleted - Sec.1 - Sig - Install New Main Signals (1 off) - 292.6 - Up - 470.971 | 2026-03-14 | 2026-03-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15200 | Deleted - Sec.1 - Sig - Install New Dis. Box Points (4 off) - 51A,51B,52A,52B - 51 pts - 0.200 | 2026-03-14 | 2026-03-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.16030 | Deleted - Sec.1 - Sig - Install New Swing nose - T 250 rad Pts Backdrive (6 off) - 51B,52A,52B - | 2026-03-14 | 2026-03-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.16040 | Deleted - Sec.1 - Sig - Install New Swing nose Dis. Box Points (3 off) - 51B,52A,52B - 51 pts - 0.200 | 2026-03-14 | 2026-03-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.G.101170 | Deleted - General Electircal Subcontractor (Essential Energy) Mob to Site | 2025-06-24 | 2025-07-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.G.101200 | Deleted - Engage General Electircal (LX) Subcontractor | 2025-04-28 | 2025-06-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.22.5730 | Deleted - Sec.6 - PUP - Telstra -comms - 37425,37435,37490,37530,37580 (5 off) | 2025-08-01 | 2025-08-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5580 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5590 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5700 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Bridges - Isobel Creek Tributary Underb
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5710 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5720 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5730 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14720 | Deleted - Sec.5 - Fill - Fill 40 - 539ccm - Fill in Open Drains | 2026-05-08 | 2026-05-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12060 | Deleted - Submission to IRPL DDR - W.04 - Stage 3 | 2025-05-29 | 2025-05-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12080 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Contaminated Land - W.04 - Stage 3 | 2025-04-07 | 2025-05-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12100 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Contaminated Land- W.04 - Stage 4 | 2025-06-06 | 2025-07-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12110 | Deleted - Incorporate IDC & CDR comments- W.04 - Stage 4 | 2025-07-14 | 2025-07-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12120 | Deleted - Issue Responses & Receive Comment Closeout- W.04 - Stage 4 | 2025-07-14 | 2025-07-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12130 | Deleted - IRPL Review (5 B.days) - W.04 - Stage 4 | 2025-07-21 | 2025-07-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12140 | Deleted - CDR Package Complete W.04 - Contaminated Land- W.04 - Stage 4 |  | 2025-07-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6240 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Earthworks - Model - Volumes - Project Wide - W.09 - | 2025-06-12 | 2025-07-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6250 | Deleted - Incorporate IDC & CDR / CCB and Stage 3 comments - W.09 - Stage 4 | 2025-07-10 | 2025-07-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8420 | Deleted - Sec.3 - Fill - Cut 07 - 2,022ccm - Capping (Rail | 2026-04-09 | 2026-04-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8430 | Deleted - Sec.3 - Fill - Fill 11 - 693ccm - Capping (Rail | 2026-04-12 | 2026-04-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.8620 | Deleted - Sec.3 - Fill - Cut 06 - 448ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-04-01 | 2026-04-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.8630 | Deleted - Sec.3 - Fill - Fill 10 - 281ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-05-21 | 2026-05-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.16490 | Deleted - Sec.4 - Isobel Ck Br - Pier Pad Footing 2 Foundation - 72m3 | 2026-03-07 | 2026-03-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.16890 | Deleted - Sec.5 - Powder Horn Ck Br - Pier 1 Pile Cap - 11m3 | 2026-03-09 | 2026-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9490 | Deleted - Issue Responses & Receive Comment Closeout - 2.01 - Stage 2 | 2025-03-14 | 2025-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20490 | Deleted - Sec.3 - Dirnaseer Rd Br - Abutment Precast Panels South Abutment Capping | 2026-03-09 | 2026-03-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20470 | Deleted - Sec.3 - Dirnaseer Rd Br - FRP - [40] MPa/20 in Abutment columns - 9m3 | 2026-02-06 | 2026-02-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10110 | Deleted - Safety Assurance / SiD - 1.06 - Stage 1 | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10120 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.06 - Stage 1 | 2024-12-06 | 2024-12-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.17190 | Deleted - CoA E133 - Aboriginal Cultural Heritage Plan approved
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.17210 | Deleted - CoA E133 - Prepare Draft of CVA methodology by JHL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.17220 | Deleted - CoA E133 - Undertake interviews and develop consultation strategy
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.17090 | Deleted - CoA E133 - Complete Engagement Strategy and Assessment Report
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.17100 | Deleted - CoA E133 -Submit Strategy and Assessment Report to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.17110 | Deleted - CoA E133 - IRPL Review period
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.17130 | Deleted - CoA E133- Submit Report to the Knowledge Keepers for review and finalisation
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.17120 | Deleted - CoA E133 - Update Comments from IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.11.15750 | Deleted - Stockpile Management
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6740 | Deleted - Safety Assurance / SiD - W.06 - Stage 3 | 2025-05-14 | 2025-05-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6820 | Deleted - Issue Responses & Receive Comment Closeout - D8 - Stage 4 | 2025-07-03 | 2025-07-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9660 | Deleted - TfNSW Review (30 B.days) - E2 - Stage 3 - Level Crossings (Public - Junee Shire Council) - BGW | 2025-07-16 | 2025-08-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9430 | Deleted - Sec.4 - Fill - Fill 31 - 3,458ccm - Mid | 2026-04-02 | 2026-04-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6020 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-95 | Deleted - Nominate Subcontractor to Goldenfields Water - Submit Contractor Deed Polls & ITPs Forbes Council | 2025-06-10 | 2025-06-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-96 | Deleted - Goldenfields Water - Work Can Commence - Forbes Council |  | 2025-06-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-1102 | Deleted - Prepare Tender Docs & Issue RFT - Goldenfields Water | 2025-03-07 | 2025-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-1112 | Deleted - Pricing by Suppliers / Subcontractors - Goldenfields Water | 2025-03-21 | 2025-05-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-1122 | Deleted - Package Review / Approval - Goldenfields Water | 2025-05-05 | 2025-05-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7190 | Deleted - IRPL Review (20 B.days) - W.01 - Stage 1 | 2025-02-05 | 2025-03-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-2520 | Deleted - CoA - E15 - OLD Operational Noise and Vibration Review (ONVR) Approved prior to Operations | 2026-09-08 | 2026-09-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12460 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Roads (Private) - 1.09 - Stage 3 | 2025-04-15 | 2025-05-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12530 | Deleted - TfNSW/ IV Review (30 B.days) - Roads - Sec.1 | 2025-06-17 | 2025-07-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4050 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Geotechnical Design GE-04 | 2025-03-03 | 2025-03-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4060 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-01-21 | 2025-01-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5230 | Deleted - Issue Responses & Receive Comment Closeout- W.02 - Stage 2 | 2025-03-10 | 2025-03-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9480 | Deleted - TfNSW Review (30 B.days) - 2.10 - Stage 4 - Road Drainage - Sec.2 to 5 | 2025-08-05 | 2025-09-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8890 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 3.05 - Stage 1 | 2025-01-15 | 2025-01-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8900 | Deleted - Incorporate IDC & CDR comments - 3.05 - Stage 1 | 2025-01-22 | 2025-01-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8910 | Deleted - Issue Responses & Receive Comment Closeout - 3.05 - Stage 1 | 2025-01-22 | 2025-01-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8920 | Deleted - Submission to IRPL SDR - 3.05 - Stage 1 | 2025-01-30 | 2025-01-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.11360 | Deleted - IFC Package Complete H8 - Powder Horn Tributary Creek Underbridges
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-1812 | Deleted - IRPL to Issue Archaeological /Aboriginal Heritage Approval to JH | 2024-09-30 | 2024-09-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10140 | Deleted - Issue Responses & Receive Comment Closeout - 1.06 - Stage 1 | 2024-12-13 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.28960 | Deleted - Sec.6 - Culvert ID : E7-RD-456912-1 - Place HDPE Pipe
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8440 | Deleted - Sec.3 - Fill - Cut 08 - 352ccm - Capping (Rail | 2026-04-13 | 2026-04-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9170 | Deleted - Design Deliverables Submission for Workshops and comments - 2.02 - Stage 2 | 2025-03-18 | 2025-03-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9380 | Deleted - Safety Assurance / SiD - 2.10 - Stage 3 | 2025-05-09 | 2025-05-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9390 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 2.10 - Stage 3 | 2025-05-16 | 2025-05-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9160 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Geotechnical Design - 2.02 - Stage 2 | 2025-01-20 | 2025-03-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9180 | Deleted - Safety Assurance / SiD - 2.02 - Stage 2 | 2025-03-18 | 2025-03-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-2170 | Deleted - CoA - E102 - NEW - Road Upgrade - Council (Road Closure /Diversion Notification - 30 Days) | 2025-02-28 | 2025-05-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-2220 | Deleted - CoA - E102 - NEW - Road Upgrade -Council Approval of design | 2025-04-30 | 2025-05-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-94 | Deleted - Package Placement - Goldenfields Water | 2025-05-19 | 2025-06-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6080 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6090 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6210 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6220 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6230 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6240 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6400 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Corridor
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6410 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6420 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6430 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10690 | Deleted - CDR Package Complete 1.05 - Culverts - Under Rail - 1.05 - Stage 4 |  | 2025-09-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2740 | Deleted - Configuration Change Acceptance Notice | 2025-08-21 | 2025-08-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4510 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-02-18 | 2025-02-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4520 | Deleted - IRPL Reviews & Approves CCR Submission $$$ | 2025-02-27 | 2025-03-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4530 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-03-18 | 2025-03-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4540 | Deleted - Configuration Change Acceptance Notice | 2025-03-20 | 2025-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4500 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Geotechnical Design GE-04 | 2025-03-19 | 2025-03-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11050 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Earthworks Formation Design Documentation - 1.03 - | 2024-10-03 | 2024-11-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11060 | Deleted - Design Deliverables Submission for Workshops and comments - 1.03 - Stage 1 | 2024-11-15 | 2024-11-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2340 | Deleted - Configuration Change Acceptance Notice | 2025-07-17 | 2025-07-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4100 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Earthworks Formation Design Documentatio | 2025-02-19 | 2025-02-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.9870 | Deleted - Sec.4 - Fill - Cut 22 - 1,120ccm - Structural Fill | 2026-05-29 | 2026-05-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.9850 | Deleted - Sec.4 - Fill - Cut 21 - 567ccm - Structural Fill | 2026-05-27 | 2026-05-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.9860 | Deleted - Sec.4 - Fill - Fill 28 - 944ccm - Structural Fill | 2026-05-28 | 2026-05-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.9890 | Deleted - Sec.4 - Fill - Cut 23 - 769ccm - Structural Fill | 2026-06-01 | 2026-06-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.9880 | Deleted - Sec.4 - Fill - Fill 29 - 779ccm - Structural Fill | 2026-05-31 | 2026-05-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.8710 | Deleted - Sec.3 - Fill - Fill 14 - 196ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-06-02 | 2026-06-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2710 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-07-21 | 2025-07-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-1592 | Deleted - EIS Environmental Consistency Assessment- Engaging consultant and preparing heritage impact assessment | 2024-11-29 | 2024-12-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11160 | Deleted - Safety Assurance / SiD - 1.03 - Stage 2 | 2025-02-03 | 2025-02-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11170 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.03 - Stage 2 | 2025-02-10 | 2025-02-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11180 | Deleted - Incorporate IDC & CDR / CCB and Stage 1 comments - 1.03 - Stage 2 | 2025-02-17 | 2025-02-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11190 | Deleted - Issue Responses & Receive Comment Closeout - 1.03 - Stage 2 | 2025-02-24 | 2025-02-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11200 | Deleted - Submission to IRPL PDR - 1.03 - Stage 2 | 2025-03-03 | 2025-03-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15250 | Deleted - Sec.3 - Fill - Fill 14 - 308ccm - Mid | 2025-12-17 | 2025-12-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.7930 | Deleted - Sec.3 - Fill - Fill 18 - 1,693ccm - Mid | 2026-02-16 | 2026-02-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10430 | Deleted - Sec.4 - Fill - Cut 24 - 300ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-07-14 | 2026-07-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20360 | Deleted - Sec.4 - Isobel Ck Br - Spill through Batter Retaining Wall Walls North Batter- - 129m3 | 2026-05-16 | 2026-05-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20370 | Deleted - Sec.4 - Isobel Ck Br - FRP - [40] MPa/20 Spillthrough Batter Retaining Wall Footing South Batter - 37 | 2026-05-29 | 2026-06-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20380 | Deleted - Sec.4 - Isobel Ck Br - Spill through Batter Retaining Wall Walls South Batter - 129m3 | 2026-06-03 | 2026-06-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10440 | Deleted - Sec.4 - Fill - Fill 31 - 444ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-07-17 | 2026-07-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10450 | Deleted - Sec.4 - Fill - Cut 25 - 300ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-07-19 | 2026-07-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10460 | Deleted - Sec.4 - Fill - Fill 32 - 570ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-07-21 | 2026-07-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.C.10C-680 | Deleted - Subcontractor Mob to Site - Temporary Safety Barriers (Not required) | 2024-12-20 | 2025-02-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.C.10C-670 | Deleted - Engage Subcontractor - Temporary Safety Barriers (Not Required) | 2024-10-25 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.C.10TR-128 | Deleted - Package Placement- Traffic Signals | 2025-04-23 | 2025-05-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13470 | Deleted - Issue Responses & Receive Comment Closeout - 2.08 - Stage 3 | 2025-05-05 | 2025-05-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13400 | Deleted - IRPL Review (20 B.days) - 2.08 - Stage 2 | 2025-03-10 | 2025-04-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.17160 | Deleted - CoA E133 - DPHI Lodgement and DPHI Review (2 weeks/ 14 cd)
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5940 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-342 | Deleted - Nominate ASP LvL1 to Essential Energy - Bethungra | 2025-06-25 | 2025-07-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-352 | Deleted - Preconstruction Meeting - Essential Energy | 2025-07-09 | 2025-07-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-372 | Deleted - Essential Energy - Work Can Commence - Bethunugra LGA |  | 2025-08-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-452 | Deleted - Essential Energy - Work Can Commence - Dirnaseer LGA |  | 2025-08-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5520 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5370 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5380 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5390 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5530 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9710 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 3.03 - Stage 1 | 2024-12-20 | 2025-01-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9720 | Deleted - Incorporate IDC & CDR comments - 3.03 - Stage 1 | 2025-01-10 | 2025-01-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9730 | Deleted - Issue Responses & Receive Comment Closeout - 3.03 - Stage 1 | 2025-01-10 | 2025-01-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9740 | Deleted - Submission to IRPL SDR - 3.03 - Stage 1 | 2025-01-17 | 2025-01-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9750 | Deleted - IRPL Review (20 B.days) - 3.03 - Stage 1 | 2025-01-20 | 2025-02-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2750 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Earthworks Formation Design Documentatio | 2025-06-18 | 2025-06-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14650 | Deleted - Sec.5 - Fill - Cut 30 - 1,025ccm - Fill in Open Drains | 2026-04-09 | 2026-04-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14660 | Deleted - Sec.5 - Fill - Fill 37 - 854ccm - Fill in Open Drains | 2026-04-11 | 2026-04-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8490 | Deleted - Incorporate IDC & CDR / CCB and Stage 3 comments - 1.02 - Stage 4 | 2025-08-21 | 2025-09-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.16330 | Deleted - Sec.4 - Isobel Ck Br - FRP - Pad Footings | 2025-12-06 | 2025-12-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21710 | Deleted - Sec.4 - Isobel Ck Br - FRP - Crosshead/Headstock Beams Pad Footing 2 - 13m3 | 2026-03-30 | 2026-04-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.9800 | Deleted - Sec.4 - Fill - Cut 19 - 358ccm - Structural Fill | 2026-05-20 | 2026-05-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11850 | Deleted - IRPL Review (20 B.days) - 2.05 - Stage 2 | 2025-04-23 | 2025-05-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8360 | Deleted - Incorporate IDC & CDR / CCB and Stage 1 comments - 1.02 - Stage 2 | 2025-05-01 | 2025-05-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12580 | Deleted - Incorporate IDC & CDR comments - 1.08 - Stage 1 | 2024-12-12 | 2024-12-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12590 | Deleted - Issue Responses & Receive Comment Closeout - 1.08 - Stage 1 | 2024-12-12 | 2024-12-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12600 | Deleted - Submission to IRPL SDR - 1.08 - Stage 1 | 2024-12-19 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12610 | Deleted - IRPL Review (20 B.days) - 1.08 - Stage 1 | 2024-12-20 | 2025-01-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.24850 | Deleted - Sec.3 - Culvert (12447) - Construct Scour Protection | 2026-05-07 | 2026-05-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.7950 | Deleted - Sec.3 - Fill - Fill 20 - 7,718ccm - Mid | 2026-02-17 | 2026-02-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15240 | Deleted - Sec.3 - Fill - Fill 11 - 533ccm - Mid | 2026-01-27 | 2026-01-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.24840 | Deleted - Sec.3 - Culvert (12447) - Precast stitch pours for precast headwalls | 2026-05-05 | 2026-05-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.24860 | Deleted - Sec.3 - Culvert (12447) - Detailed backfill | 2026-05-08 | 2026-05-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.27460 | Deleted - Sec.3 - Culvert (12447 - Excavation 2000m2 1m deep - Basin Upstream | 2026-04-28 | 2026-05-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.27440 | Deleted - Sec.3 - Culvert (13041) - Excavation 1500m2 1.4m deep - Basin Upstream | 2026-05-31 | 2026-06-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.28940 | Deleted - Sec.6 - Culvert ID : E7-RD-456912-1 - Trench Excavation / Site Prep
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.28950 | Deleted - Sec.6 - Culvert ID : E7-RD-456912-1 - Foundation Treatment / Bedding
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8410 | Deleted - Design Deliverables Submission for Workshops and comments - 1.02 - Stage 3 | 2025-06-30 | 2025-07-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8420 | Deleted - Safety Assurance / SiD - 1.02 - Stage 3 | 2025-06-30 | 2025-07-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8430 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.02 - Stage 3 | 2025-07-04 | 2025-07-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8440 | Deleted - Incorporate IDC & CDR comments - 1.02 - Stage 3 | 2025-07-11 | 2025-07-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.D.10R-95 | Deleted - Package Placement - Asbestos Removal, Cleaning & Sealing | 2025-04-23 | 2025-05-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.D.10R-105 | Deleted - Manufacturing & Delivery - Asbestos Removal, Cleaning & Sealing | 2025-05-08 | 2025-07-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.27540 | Deleted - Sec.4 - Culvert (28197) - Excavation 1500m2 1.5m deep - Basin Upstream | 2025-11-28 | 2025-12-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.8750 | Deleted - Sec.3 - Fill - Fill 16 - 278ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-06-07 | 2026-06-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.14300 | Deleted - Sec.6 - Fill - Fill 43 - 615ccm - Strip/Grade RMAR with type D Material (U5 Class)(acrossTO-37400-37680) | 2026-09-14 | 2026-09-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.14310 | Deleted - Sec.6 - Fill - Fill 43 - 615ccm - Strip/Grade RMAR with type D Material (U5 Class) (across CRN track - | 2026-09-13 | 2026-09-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.8740 | Deleted - Sec.3 - Fill - Cut 12 - 185ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-06-06 | 2026-06-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12520 | Deleted - TfNSW Review (30 B.days) - Roads - Sec.1 | 2025-08-20 | 2025-09-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11690 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Culverts - Under Rail - 2.05 - Stage 1 | 2024-10-03 | 2024-11-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11700 | Deleted - Design Deliverables Submission for Workshops and comments - 2.05 - Stage 1 | 2024-11-22 | 2024-11-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11710 | Deleted - Safety Assurance / SiD - 2.05 - Stage 1 | 2024-11-22 | 2024-11-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11720 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 2.05 - Stage 1 | 2025-01-15 | 2025-01-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9790 | Deleted - Start Package 3.03 - Earthworks Formation Design Documentation - 3.03 - Stage 1 | 2024-11-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9680 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Earthworks Formation Design Documentation - 3.03 - | 2024-11-01 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16780 | Deleted - Sec.3 - Public LX - PU15950 - Drainage - Detailed backfill | 2026-01-28 | 2026-01-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.18160 | Deleted - Sec.3 - Public LX - PU15950 - Drainage - LX Culvert - Trench Excavation/ Culvert site prep | 2026-01-20 | 2026-01-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14730 | Deleted - Sec.5 - Fill - Fill 42 - 2,386ccm - Fill in Open Drains | 2026-05-09 | 2026-05-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21900 | Deleted - Sec.2 - Ulandra Ck Br - FRP - MPa/20 in kerb - 8m3 | 2026-03-01 | 2026-03-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15750 | Deleted - CUDLP - Respond to stakeholder comments | 2025-01-14 | 2025-01-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8460 | Deleted - Sec.3 - Fill - Cut 09 - 1,384ccm - Capping (Rail | 2026-04-15 | 2026-04-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5710 | Deleted - CDR Package Complete 3.07 - Roads - BGW - 3.07 - Stage 4 |  | 2025-09-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.G.101210 | Deleted - General Electircal (LX) Subcontractor Mob to Site | 2025-06-24 | 2025-07-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8450 | Deleted - Sec.3 - Fill - Fill 12 - 271ccm - Capping (Rail | 2026-04-14 | 2026-04-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8470 | Deleted - Sec.3 - Fill - Fill 13 - 735ccm - Capping (Rail | 2026-04-21 | 2026-04-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8480 | Deleted - Sec.3 - Fill - Cut 10 - 412ccm - Capping (Rail | 2026-04-22 | 2026-04-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8490 | Deleted - Sec.3 - Fill - Fill 14 - 442ccm - Capping (Rail | 2026-04-23 | 2026-04-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.15830 | Deleted - Sec.3 - Run Boundary Ck Br - Transverse stressing of prestressed concrete deck and kerb units | 2026-02-16 | 2026-02-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16460 | Deleted - Sec.3 - Public LX - PU15966 - Drainage - LX Culvert - Trench Excavation / Site Prep | 2026-01-18 | 2026-01-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16470 | Deleted - Sec.3 - Public LX - PU15966 - Drainage - Install 900 RCP - 3 off - 6m | 2026-01-19 | 2026-01-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16480 | Deleted - Sec.3 - Public LX - PU15966 - Drainage - Detailed backfill | 2026-01-20 | 2026-01-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.8850 | Deleted - Sec.4 - Cut - Cut 18 - 19,266ccm - OD Soil | 2025-11-09 | 2025-11-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.8990 | Deleted - Sec.4 - Cut SW Dacite (71993bcm) 1250 bcm/d PART 2 | 2025-11-07 | 2025-11-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.9960 | Deleted - Sec.4 - Fill - Cut 26 - 658ccm - Structural Fill | 2026-06-17 | 2026-06-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.9980 | Deleted - Sec.4 - Fill - Cut 27 - 1,321ccm - Structural Fill | 2026-06-18 | 2026-06-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-4 | Deleted - Prepare Tender Docs & Issue RFT - Essential Energy | 2024-12-19 | 2025-01-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-2280 | Deleted - CoA - E155 - NEW - Detailed Site Investigation Report(s) in Condition DSI | 2024-12-19 | 2025-02-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5680 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5690 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3550 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Geotechnical Design GE-04 | 2025-04-16 | 2025-04-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3560 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-03-11 | 2025-03-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3570 | Deleted - IRPL Reviews & Approves CCR Submission - 3.02 - Stage 1 $$$ | 2025-03-20 | 2025-04-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18050 | Deleted - Sec.5 - Powder Horn Trib Br - Excavate platform for piling pad | 2026-01-09 | 2026-01-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5280 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Noise - W.02 - Stage 3 | 2025-03-25 | 2025-05-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5300 | Deleted - Safety Assurance / SiD - W.02 - Stage 3 | 2025-04-28 | 2025-05-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5310 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - W.02 - Stage 3 | 2025-05-02 | 2025-05-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5320 | Deleted - Incorporate IDC & CDR comments - W.02 - Stage 3 | 2025-05-09 | 2025-05-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5330 | Deleted - Issue Responses & Receive Comment Closeout - W.02 - Stage 3 | 2025-05-09 | 2025-05-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5350 | Deleted - Submission to IRPL DDR - W.02 - Stage 3 | 2025-05-16 | 2025-05-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5360 | Deleted - IRPL Review (20 B.days) - W.02 - Stage 3 - Noise | 2025-05-16 | 2025-06-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5380 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Noise - W.02 - Stage 4 | 2025-05-26 | 2025-06-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5390 | Deleted - Incorporate IDC & CDR / CCB and Stage 3 comments - W.02 - Stage 4 | 2025-06-20 | 2025-07-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5400 | Deleted - IRPL Review (5 B.days) - W.02 - Stage 4 - Noise | 2025-06-27 | 2025-07-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5430 | Deleted - CDR Package Complete W.02 - Noise - W.02 - Stage 4 |  | 2025-07-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9390 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 2.01 - Stage 1 | 2024-12-05 | 2024-12-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9410 | Deleted - Issue Responses & Receive Comment Closeout - 2.01 - Stage 1 | 2024-12-12 | 2024-12-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9420 | Deleted - Submission to IRPL SDR - 2.01 - Stage 1 | 2024-12-19 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9430 | Deleted - IRPL Review (20 B.days) - 2.01 - Stage 1 | 2024-12-20 | 2025-01-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12330 | Deleted - Start Package 2.01 - Geotechnical GIR - 2.01 - Stage 1 | 2024-10-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9440 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Geotechnical GIR - 2.01 - Stage 2 | 2024-12-19 | 2025-03-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20730 | Deleted - Sec.3 - Run Boundary Ck Br - Precast Concrete Parapet Panels | 2026-05-20 | 2026-05-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.22.14370 | Deleted - Sec.3 - Essential Energy - Cut Over Planning and Notification (inc permit)
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-18 | Deleted - Package Review / Approval - Essential Energy - Illabo LGA | 2025-05-21 | 2025-06-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15400 | Deleted - Sec.6 - Sig - Install New Dis. Box Points (4 off) - 51A, 51B, 52A, 52B - 51 PTS - 37.573 | 2026-05-16 | 2026-05-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15590 | Deleted - Sec.6 - Sig - existing M23A Points (4 off) - SL113, SL114A, SL114B, SL115 - SL113 - 454.160 | 2026-05-18 | 2026-05-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8640 | Deleted - Incorporate IDC & CDR comments - 1.01 - Stage 2 | 2025-03-03 | 2025-03-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15600 | Deleted - Sec.6 - Sig - existing Dis. Box Points (4 off) - SL113, SL114A, SL114B, SL115 - SL113 - 454.160 (Dele | 2026-05-21 | 2026-05-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.22.13180 | Deleted - Sec.1 - OF01-01 Optus - Relocate Comms Cable - Creek Crossing - Ch800 | 2025-09-13 | 2025-09-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8500 | Deleted - Sec.3 - Fill - Cut 11 - 370ccm - Capping (Rail | 2026-04-24 | 2026-04-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7250 | Deleted - Issue Responses & Receive Comment Closeout - W.01 - Stage 2 | 2025-03-31 | 2025-04-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.7630 | Deleted - Sec.3 - Cut - Cut 10 - 2,581cm - OD Soil | 2026-02-23 | 2026-02-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13530 | Deleted - Incorporate IDC & CDR comments - 2.08 - Stage 4 | 2025-07-16 | 2025-07-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9230 | Deleted - Sec.4 - Fill - Fill 26 - 7,788ccm - Lower | 2026-03-09 | 2026-03-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19580 | Deleted - Sec.3 - Dirnaseer Rd Br - Pier Pile Cap - 5m3 | 2025-12-17 | 2025-12-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.16100 | Deleted - Sec.3 - Dirnaseer Rd Br - Detailed Earthworks Abutment Pile Cap | 2025-12-23 | 2026-01-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20510 | Deleted - Sec.3 - Dirnaseer Rd Br - S&I Column sleeves to columns | 2026-02-19 | 2026-02-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11140 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Earthworks Formation Design Documentation - 1.03 | 2024-12-06 | 2025-02-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10170 | Deleted - Start Package 1.06 - Bridges - 1.06 - Stage 1 | 2024-10-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7530 | Deleted - Issue Responses & Receive Comment Closeout - D7 - Stage 2 | 2025-03-17 | 2025-03-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7540 | Deleted - Submission to IRPL - D7 - Stage 2 | 2025-03-24 | 2025-03-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7550 | Deleted - IRPL Review (20 B.days) - D7 - Stage 2 | 2025-03-25 | 2025-04-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.BI-1400 | Deleted - CoA - E40, E41_NEW - Update & address and Comments - Environmental - Fauna Crossing - Baseline Monitoring (T
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.BI-1410 | Deleted - CoA - E42_NEW - consultation with DPI Fisheries on Watercourse crossings (To
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.BI-1420 | Deleted - CoA - E43_NEW - Fauna access pathways to connectivity (Link to Landscape DDD)
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1060 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-05-19 | 2025-05-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.11370 | Deleted - Sec.5 - Fill - Cut 33 - 330ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-09-01 | 2026-09-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.10220 | Deleted - FDD Package Complete H8 - Powder Horn Tributary Creek Underbridges
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11230 | Deleted - Design Deliverables Submission for Workshops and comments - 1.03 - Stage 3 | 2025-04-15 | 2025-04-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11240 | Deleted - Safety Assurance / SiD - 1.03 - Stage 3 | 2025-04-15 | 2025-04-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20390 | Deleted - Sec.4 - Isobel Ck Br - Install Handrails Spillthrough Batter Retaining Walls | 2026-06-18 | 2026-06-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.18150 | Deleted - Sec.3 - Public LX - PU15950 -10- Drainage - Place RCBC crown units 0.6W x 0.45H RCBC (48 off) 113m | 2026-01-21 | 2026-01-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6260 | Deleted - Issue Responses & Receive Comment Closeout - W.09 - Stage 4 | 2025-07-17 | 2025-07-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6270 | Deleted - CDR Package Complete W.09 - Earthworks - Model - Volumes - Project Wide - W.09 - Stage 4 |  | 2025-07-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9510 | Deleted - IRPL Review (5 B.days) - W.09 - Stage 4 | 2025-07-24 | 2025-07-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1510 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-06-04 | 2025-06-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2280 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-07-18 | 2025-07-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.18430 | Deleted - Sec.4 - Float before Track can commence - Sec.4 - converted LOE | 2026-06-29 | 2026-09-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.91.14350 | Deleted - Sec.1 - Hold point for QA Inspection with IRPL - Sec.1 - Sleepers | 2026-04-19 | 2026-04-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2270 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-07-01 | 2025-07-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.11620 | Deleted - Sec.6 - Fill - Fill 44 - 2,352ccm - Strip/Grade RMAR with type D Material (U5 Class) (39305 - 42480) DEL | 2026-09-12 | 2026-09-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.12870 | Deleted - Sec.6 - Fill - CRN East - 600ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-04-07 | 2026-04-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15140 | Deleted - Sec.3 - Fill - Cut 13 - 468ccm - Fill in Open Drains | 2025-12-22 | 2025-12-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | A1080 | Deleted - Sec.3 - Fill - Fill 18 - 3,217ccm - E2 Replace unsuitable - Foundation Treatment | 2025-12-20 | 2026-01-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.23910 | Deleted - Sec.3 - Culvert (15961) - Trench Excavation / Site Prep | 2026-04-11 | 2026-04-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.23920 | Deleted - Sec.3 - Culvert (15961) - Foundation Treatment / Bedding | 2026-04-13 | 2026-04-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.23960 | Deleted - Sec.3 - Culvert (15961) - Place 4*900 HDPE Pipe | 2026-04-15 | 2026-04-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13280 | Deleted - Issue Responses & Receive Comment Closeout - 2.08 - Stage 1 | 2024-12-12 | 2024-12-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13290 | Deleted - Submission to IRPL SDR - 2.08 - Stage 1 | 2024-12-19 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13300 | Deleted - IRPL Review (20 B.days) - 2.08 - Stage 1 | 2024-12-20 | 2025-01-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13310 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Utility Coordination Plans - 2.08 - Stage 1 | 2024-10-17 | 2024-12-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.17230 | Deleted - CoA E133 - Knowledge Keeper Review Period
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10160 | Deleted - IRPL Review (20 B.days) - 1.06 - Stage 1 | 2025-01-06 | 2025-02-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.12910 | Deleted - Sec.6 - Fill - Fill 43 - 50ccm - Place new material, compact and proof roll- Structural Fill (across CRN | 2026-09-12 | 2026-09-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.22.13420 | Deleted - Sec.4 - PUP - Water - 27600 - NCP -15 -DN300 RCP enveloper pipe for future water. | 2025-08-13 | 2025-08-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.27410 | Deleted - Sec.2 - Culvert (007068) - Excavation 5000m2 0.2m deep - Basin Upstream | 2025-09-20 | 2025-09-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.12850 | Deleted - Sec.6 - Fill - CRN E/W - ccm - Structural Fill | 2026-03-18 | 2026-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.12920 | Deleted - Sec.6 - Fill - Fill 43 - 708ccm - Structural Fill (CRN to Bridge - 37720 - 37950 | 2026-03-10 | 2026-03-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11540 | Deleted - Sec.6 - Fill - Fill 43 - 708ccm - Structural Fill (across old BGW - 37240 - 37400 | 2026-11-10 | 2026-11-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11550 | Deleted - Sec.6 - Fill - Cut 35 - 3,156ccm - Structural Fill (38045 - 39305 | 2026-02-22 | 2026-02-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9910 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Earthworks Formation Design Documentation - 3.03 - | 2025-04-07 | 2025-06-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9920 | Deleted - Design Deliverables Submission for Workshops and comments - Stage 3 - Earthworks Formation Design Document | 2025-05-29 | 2025-06-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9000 | Deleted - Sec.4 - Cut - Cut 18 - 43,137ccm - XW /HW Rip - rock | 2025-11-23 | 2025-12-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9010 | Deleted - Sec.4 - Cut - Cut 19 - 6,600ccm - MW Rip - rock | 2025-12-23 | 2026-01-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9020 | Deleted - Sec.4 - Cut - Cut 20 - 6,493ccm - XW /HW Rip - rock | 2026-03-09 | 2026-03-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-14 | Deleted - Ausgrid Submit Relocation Offer to JH - Essential Energy | 2025-05-21 | 2025-06-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-15 | Deleted - JH Accept Relocation Offer - Essential Energy | 2025-06-04 | 2025-06-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14120 | Deleted - Sec.6 - Fill - Fill 43 - 50ccm - Place new material, compact and proof roll- Upper A (across CRN track- | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10480 | Deleted - IRPL Review (20 B.days) - 1.05 - Stage 1 | 2025-01-31 | 2025-02-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10490 | Deleted - Start Package 1.05 - Culverts - Under Rail - 1.05 - Stage 1 | 2024-10-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9450 | Deleted - Incorporate IDC & CDR comments - 2.10 - Stage 4 | 2025-07-28 | 2025-08-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9460 | Deleted - IRPL Review (5 B.days) - 2.10 - Stage 4 | 2025-08-05 | 2025-08-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5910 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 3.02 - Stage 3 | 2025-07-18 | 2025-07-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5960 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Geotechnical Design - 3.02 - Stage 4 | 2025-08-11 | 2025-09-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12350 | Deleted - Safety Assurance / SiD - 2.03 - Stage 1 | 2024-12-06 | 2024-12-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12410 | Deleted - Start Package 2.03 - Earthworks Formation Design Documentation - 2.03 - Stage 1 | 2024-10-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6500 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Corridor
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6360 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6370 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6380 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6510 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6520 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6530 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6540 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6450 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Corridor
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6460 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6470 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6480 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6490 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11870 | Deleted - Design Deliverables Submission for Workshops and comments - 2.05 - Stage 3 | 2025-06-05 | 2025-06-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11880 | Deleted - Safety Assurance / SiD - 2.05 - Stage 3 | 2025-06-05 | 2025-06-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11940 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Culverts - Under Rail - 2.05 - Stage 4 | 2025-06-30 | 2025-08-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11950 | Deleted - Incorporate IDC & CDR / CCB and Stage 3 comments - 2.05 - Stage 4 | 2025-08-12 | 2025-08-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11960 | Deleted - IRPL Review (5 B.days) - 2.05 - Stage 4 | 2025-08-26 | 2025-09-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11970 | Deleted - CDR Package Complete 2.05 - Culverts - Under Rail - culvert (2-5) - 2.05 - Stage 4 |  | 2025-09-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3420 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-03-12 | 2025-03-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3430 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-03-31 | 2025-03-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6840 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Geotech Gap Analysis & SI - W.05 - Stage 1 | 2024-10-31 | 2025-01-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.D.10R-295 | Deleted - Delivery set A (2.4W / 3.0W) (293 off) - Precast RCBC Culvert Drainage Pipe and Channel | 2025-09-10 | 2025-11-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.D.10R-315 | Deleted - Delivery set B (1.2W ) (160 off)- Precast RCBC Culvert Drainage Pipe and Channel | 2025-09-24 | 2025-10-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.D.10R-325 | Deleted - Fabricate set C (0.9W, 1.8W & 0.6W) (12 off)-- Precast RCBC Culvert Drainage Pipe and Channel | 2025-09-24 | 2025-10-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.D.10R-335 | Deleted - Delivery set C (0.9W, 1.8W & 0.6W) (12 off)- Precast RCBC Culvert Drainage Pipe and Channel | 2025-10-13 | 2025-10-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.D.10R-65 | Deleted - Prepare Tender Documents - Asbestos Removal, Cleaning & Sealing | 2024-10-25 | 2024-11-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.D.10R-75 | Deleted - Pricing by Suppliers / Subcontractors- Asbestos Removal, Cleaning & Sealing | 2024-11-22 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.D.10R-85 | Deleted - Package Review / Approval - Asbestos Removal, Cleaning & Sealing | 2024-12-20 | 2025-01-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9850 | Deleted - Issue Responses & Receive Comment Closeout - 3.03 - Stage 2 | 2025-03-31 | 2025-04-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9820 | Deleted - Safety Assurance / SiD - 3.03 - Stage 2 | 2025-03-10 | 2025-03-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-1602 | Deleted - EIS Environmental Consistency Assessment- Preparing memo | 2024-12-13 | 2025-01-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13510 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Utilities Design - 2.08 - Stage 3 | 2025-03-12 | 2025-04-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2720 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-07-29 | 2025-08-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.11520 | Deleted - Sec.6 - Fill - Fill 43 - 350ccm - Upper A (across old BGW - 37240 - 37400 | 2026-11-09 | 2026-11-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10W-847 | Deleted - Manufacturing & Delivery- Drill and Blast (Not required) | 2025-04-11 | 2025-07-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14090 | Deleted - Sec.6 - Fill - Fill 43 - 50ccm - Place new material, compact and proof roll- Mid (across CRN track - | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14100 | Deleted - Sec.6 - Fill - Fill 43 - 850ccm - Mid (CRN to Bridge - 37720 - 37950 | 2025-10-08 | 2025-10-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.10510 | Deleted - CFEMP - DPHI Completion of Review/Approval (2 weeks/ 14 cd)-Flood Emergency / Bushfire Emergency Plan CoA -C | 2025-05-06 | 2025-05-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15920 | Deleted - ACVA- Consultation with relevant Government agencies (up to 3 weeks) | 2025-02-11 | 2025-03-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9030 | Deleted - Safety Assurance / SiD - 1.10 - Stage 3 | 2025-06-05 | 2025-06-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9040 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.10 - Stage 3 | 2025-06-13 | 2025-06-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9050 | Deleted - Incorporate IDC & CDR comments - 1.10 - Stage 3 | 2025-06-20 | 2025-06-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.15-354 | Deleted - Proponent should provide a copy of this record or documentation to registered Aboriginal parties. | 2024-12-04 | 2024-12-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16740 | Deleted - Sec.3 - Public LX - PU15950 - Drainage - Install 900 RCP - 5 off - 10m | 2026-01-26 | 2026-01-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9440 | Deleted - Sec.4 - Fill - Fill 32 - 4,965ccm - Mid | 2026-04-04 | 2026-04-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9460 | Deleted - Sec.4 - Fill - Fill 33 - 1,575ccm - Mid | 2026-04-08 | 2026-04-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9480 | Deleted - Sec.4 - Fill - Fill 21 - 5,006ccm - Upper A | 2026-04-20 | 2026-04-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.8760 | Deleted - Sec.3 - Fill - Fill 17 - 781ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-06-08 | 2026-06-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.8770 | Deleted - Sec.3 - Fill - Cut 13 - 304ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-06-11 | 2026-06-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14670 | Deleted - Sec.5 - Fill - Cut 31 - 769ccm - Fill in Open Drains | 2026-04-13 | 2026-04-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-82 | Deleted - Pricing by Suppliers / Subcontractors - Goldenfields Water | 2025-03-21 | 2025-05-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-83 | Deleted - Package Review / Approval - Goldenfields Water | 2025-05-05 | 2025-05-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9190 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 2.02 - Stage 2 | 2025-03-25 | 2025-03-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9200 | Deleted - Incorporate IDC & CDR / CCB and Stage 1 comments - 2.02 - Stage 2 | 2025-04-01 | 2025-04-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9210 | Deleted - Issue Responses & Receive Comment Closeout - 2.02 - Stage 2 | 2025-04-08 | 2025-04-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.28500 | Deleted - Sec.5 - Culvert (37212) - Place precast base slabs
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.28470 | Deleted - Sec.5 - Culvert (37212) - Detailed backfill
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6800 | Deleted - Sec.2 - Cut - Cut 05 - 10,558ccm - OD Soil | 2025-10-30 | 2025-11-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1840 | Deleted - Configuration Change Acceptance Notice | 2025-08-05 | 2025-08-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3590 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Road Drainage - 3.10 - Stage 1 | 2024-10-25 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3600 | Deleted - Design Deliverables Submission for Workshops and comments - 3.10 - Stage 1 | 2024-12-13 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9270 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 2.02 - Stage 3 | 2025-06-06 | 2025-06-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9280 | Deleted - Incorporate IDC & CDR comments - 2.02 - Stage 3 | 2025-06-16 | 2025-06-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2780 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-06-10 | 2025-06-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2790 | Deleted - Configuration Change Acceptance Notice | 2025-06-19 | 2025-06-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.28970 | Deleted - Sec.6 - Culvert ID : E7-RD-456912-1 - Precast stitch pours for precast headwalls
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.28980 | Deleted - Sec.6 - Culvert ID : E7-RD-456912-1 - Construct Scour protection
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.28990 | Deleted - Sec.6 - Culvert ID : E7-RD-456912-1 - Detailed backfill
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.16880 | Deleted - CTTAMP - Road Assessment (To
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.10290 | Deleted - CBMP - Respond to stakeholder comments - CoA - C20 (To | 2025-01-29 | 2025-02-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-2080 | Deleted - CoA - D8_NEW - IRPL - Operational Monitoring Program REsults into Operational Monitoring Program Report (Del | 2027-02-15 | 2027-03-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.10650 | Deleted - CPWMP - Respond to stakeholder comments (To | 2025-01-14 | 2025-01-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.10470 | Deleted - CFEMP - Respond to IRPL Gov. stakeholder comments -Flood Emergency / Bushfire Emergency Plan CoA -C24, E98 d | 2025-02-27 | 2025-03-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13570 | Deleted - TfNSW Detailed Design Review - Stage 3 / DDR - all packages - LOE (To | 2025-05-12 | 2025-09-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4080 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-02-19 | 2025-02-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4090 | Deleted - Configuration Change Acceptance Notice | 2025-03-04 | 2025-03-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12390 | Deleted - Submission to IRPL SDR - 2.03 - Stage 1 | 2025-01-10 | 2025-01-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12400 | Deleted - IRPL Review (20 B.days) - 2.03 - Stage 1 | 2025-01-13 | 2025-02-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10930 | Deleted - Sec.5 - Fill - Cut 34 - 7ccm - Upper A | 2026-05-20 | 2026-05-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16770 | Deleted - Sec.3 - Public LX - PU15950 - Drainage - Install 900 RCP - 10 off - 24m | 2026-01-27 | 2026-01-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14430 | Deleted - Sec.4 - Cut - Fill 25 - 77ccm - OD Soil | 2025-11-29 | 2025-11-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.11830 | Deleted - TfNSW Review (30 B.days) - M3 - Stage 4 - Roads - Public (TfNSW) (Not required) | 2025-08-20 | 2025-09-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.27530 | Deleted - Sec.4 - Culvert (23205) - Excavation 3000m2 1.5m deep - Basin Upstream | 2025-12-08 | 2025-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20200 | Deleted - Sec.4 - Isobel Ck Trib Br - Precast Concrete Parapet Panels | 2026-06-21 | 2026-06-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9160 | Deleted - IRPL Review (20 B.days) - 3.05 - Stage 3 | 2025-06-27 | 2025-07-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9090 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Culverts - Under Rail - 3.05 - Stage 3 | 2025-04-30 | 2025-06-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9100 | Deleted - Design Deliverables Submission for Workshops and comments - 3.05 - Stage 3 | 2025-06-04 | 2025-06-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12730 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Utilities Design - 1.08 - Stage 2 | 2024-12-19 | 2025-03-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14260 | Deleted - Sec.2 - Cut - Fill 06 - 880ccm - OD Soil | 2025-10-27 | 2025-10-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10580 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Culverts - Under Rail - 1.05 - Stage 3 | 2025-04-29 | 2025-06-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10590 | Deleted - Design Deliverables Submission for Workshops and comments - 1.05 - Stage 3 | 2025-06-11 | 2025-06-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11010 | Deleted - CDR Package Complete 1.04 - Level Crossings - PU2800 - 1.04 - Stage 4 |  | 2025-11-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11020 | Deleted - TfNSW Review (30 B.days) - 1.04 - Stage 4 - Level Crossings - Illabo | 2025-09-23 | 2025-11-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2800 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Level Crossings | 2025-09-01 | 2025-09-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2810 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-07-28 | 2025-08-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2820 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-08-07 | 2025-08-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2830 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-08-26 | 2025-08-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2840 | Deleted - Configuration Change Acceptance Notice | 2025-09-02 | 2025-09-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4600 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Level Crossings RD-02 | 2025-04-07 | 2025-04-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.27420 | Deleted - Sec.3 - Culvert (17517) - Excavation 2000m2 2m deep - Basin Upstream | 2026-03-23 | 2026-04-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15130 | Deleted - Sec.3 - Fill - Fill 17 - 295ccm - Fill in Open Drains | 2025-12-21 | 2025-12-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7160 | Deleted - Incorporate IDC & CDR comments - W.01 - Stage 1 | 2025-01-08 | 2025-01-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7170 | Deleted - Issue Responses & Receive Comment Closeout - W.01 - Stage 1 | 2025-01-06 | 2025-01-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7180 | Deleted - Submission to IRPL - W.01 - Stage 1 | 2025-01-13 | 2025-01-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9290 | Deleted - Issue Responses & Receive Comment Closeout - 2.02 - Stage 3 | 2025-06-16 | 2025-06-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9300 | Deleted - Submission to IRPL DDR - 2.02 - Stage 3 | 2025-06-23 | 2025-06-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.9990 | Deleted - Sec.4 - Fill - Fill 34 - 1,426ccm - Structural Fill | 2026-06-20 | 2026-06-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.9760 | Deleted - Sec.4 - Fill - Fill 22 - 981ccm - Structural Fill | 2026-05-14 | 2026-05-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.9770 | Deleted - Sec.4 - Fill - Cut 18 - 485ccm - Structural Fill | 2026-05-17 | 2026-05-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.9780 | Deleted - Sec.4 - Fill - Fill 23 - 777ccm - Structural Fill | 2026-05-18 | 2026-05-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.9790 | Deleted - Sec.4 - Fill - Fill 24 - 143ccm - Structural Fill | 2026-05-19 | 2026-05-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.15-514 | Deleted - Proponent considers input provided by RAP and finalises methodology | 2025-06-12 | 2025-06-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.15-524 | Deleted - Proponent seeks information from registered Aboriginal parties to identify:they are object or places of valu | 2025-05-14 | 2025-05-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6560 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9530 | Deleted - Design Deliverables Submission for Workshops and comments - 2.01 - Stage 3 | 2025-05-14 | 2025-05-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9540 | Deleted - Safety Assurance / SiD - 2.01 - Stage 3 | 2025-05-14 | 2025-05-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9550 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 2.01 - Stage 3 | 2025-05-21 | 2025-05-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19820 | Deleted - Sec.5 - Powder Horn Trib Br - FRP - [40] MPa/20 in pier 1 headstock - 9m3 | 2026-04-20 | 2026-04-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.22.5740 | Deleted - Sec.6 - PUP - Telstra -comms - 40660,40688 (4 off) | 2025-07-21 | 2025-07-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2760 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-05-12 | 2025-05-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.G.101270 | Deleted - Gas Relocation Subcontractor Mob to Site | 2025-06-24 | 2025-07-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.G.101290 | Deleted - HDD Subcontractor Mob to Site | 2025-05-07 | 2025-05-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.EW.10909210 | Deleted - Engage Subcontractor - Hotels | 2024-10-25 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.19800 | Deleted - Turnout delivery, 1 Crossover and 1 turnout - link to I.CN.91.14180 |  | 2026-01-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.7910 | Deleted - Sec.3 - Fill - Fill 16 - 1,988ccm - Mid | 2026-02-11 | 2026-02-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1050 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Noise | 2025-06-18 | 2025-06-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.18450 | Deleted - Sec.3 - Float before Track can commence - Sec.3 - converted LOE | 2026-05-16 | 2026-06-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.91.14480 | Deleted - Sec.5 - Hold point for QA Inspection with IRPL - Sec.5 - Sleepers | 2026-10-02 | 2026-10-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.11.13250 | Deleted - Sec.6 - Telstra relocation tie in at Grogan Road intersection with McLaughlins Lane CH 40700 | 2025-07-21 | 2025-07-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8360 | Deleted - Sec.3 - Fill - Cut 15 - 651ccm - Structural Fill | 2026-05-02 | 2026-05-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5550 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Bridges - Isobel Creek Underbridge
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5560 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12510 | Deleted - Design Deliverables Submission for Workshops and comments - 2.03 - Stage 3 | 2025-05-22 | 2025-05-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18290 | Deleted - Sec.5 - Powder Horn Trib Br - FRP Footpath/Steps | 2026-09-04 | 2026-09-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18300 | Deleted - Sec.5 - Powder Horn Trib Br - Install handrail raking/horizontal | 2026-09-14 | 2026-09-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19260 | Deleted - Sec.5 - Powder Horn Trib Br - Completion |  | 2026-09-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8280 | Deleted - Incorporate IDC & CDR comments - 1.02 - Stage 1 | 2025-02-10 | 2025-02-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-2362 | Deleted - CoA - E27 Stop works, assessment, BAM, approval - on unexpected finds (3 months) | 2025-02-19 | 2025-05-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-2152 | Deleted - CoA - E23 - Update & address and Comments - Environmental - Clearing of native vegetation | 2025-06-06 | 2025-06-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-2292 | Deleted - CoA - E23 - IRPL Review and issue Comments - Environmental - Clearing of native vegetation | 2025-05-09 | 2025-06-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-2372 | Deleted - CoA - E25, E26- comfirm Biodiversity impacts to plant types not to exceed in BAM Biodiversity credit report | 2025-02-05 | 2025-02-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4180 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-03-24 | 2025-03-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4190 | Deleted - Configuration Change Acceptance Notice | 2025-04-08 | 2025-04-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20480 | Deleted - Sec.3 - Dirnaseer Rd Br - Abutment Precast Panels North Abutment Capping | 2026-03-03 | 2026-03-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.27450 | Deleted - Sec.3 - Culvert (12542) - Excavation 1300m2 1m deep - Basin Upstream | 2026-05-12 | 2026-05-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13540 | Deleted - Issue Responses & Receive Comment Closeout - 2.08 - Stage 4 | 2025-07-16 | 2025-07-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13550 | Deleted - IRPL Review (5 B.days) - 2.08 - Stage 4 | 2025-07-23 | 2025-07-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13560 | Deleted - CDR Package Complete 2.08 - Utility Infrastructure - 2.08 - Stage 4 |  | 2025-07-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9170 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Road Drainage - 2.10 - Stage 1 | 2024-10-18 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5000 | Deleted - CCB Gate 6 Meeting - Presentation of CCR Submission to SM Sub CCB - Rail Systems | 2026-12-16 | 2026-12-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5010 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2026-11-17 | 2026-11-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5020 | Deleted - IRPL Reviews & Approves CCR Submission | 2026-11-24 | 2026-12-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9030 | Deleted - Sec.4 - Cut - Cut 22 - 16,941ccm - XW /HW Rip - rock | 2026-01-21 | 2026-02-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9060 | Deleted - Sec.4 - Cut - Cut 25 - 9,195ccm - MW Rip - rock | 2025-10-04 | 2025-10-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9090 | Deleted - Sec.4 - Cut - Cut 17 - 46,134ccm - XW /HW - MW Rip - rock | 2025-11-18 | 2025-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10560 | Deleted - Sec.5 - Cut - Fill 37 - 6016ccm - OD Soil / Soil | 2025-09-17 | 2025-09-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10570 | Deleted - Sec.5 - Cut - Cut 31 - 7,052ccm - OD Soil / Soil | 2025-09-29 | 2025-10-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9420 | Deleted - Sec.4 - Fill - Fill 30 - 3,699ccm - Mid | 2026-03-31 | 2026-04-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3820 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-01-15 | 2025-02-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2000 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Roads | 2025-07-16 | 2025-07-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11000 | Deleted - IRPL Review (5 B.days) - 1.04 - Stage 4 | 2025-09-23 | 2025-09-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10900 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Level Crossings - 1.04 - Stage 3 | 2025-05-29 | 2025-07-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.18140 | Deleted - Sec.3 - Public LX - PU15950 - Drainage - Detailed backfill | 2026-01-22 | 2026-01-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.91.14540 | Deleted - Hold point for QA Inspection with IRPL - Sec.3 - Rail | 2026-06-24 | 2026-06-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-722 | Deleted - JH Horizontal & Vertical Alignment Design for NBN | 2024-10-17 | 2024-11-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-732 | Deleted - NBN Design 80% & Review /Comments | 2024-11-07 | 2025-01-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.29070 | Deleted - Sec.6 - Culvert ID : E7-RD-456911-1 - Construct Scour protection
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.29040 | Deleted - Sec.6 - Culvert ID : E7-RD-456911-1 - Foundation Treatment / Bedding
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.7180 | Deleted - Sec.2 - Fill - Cut 04 - 1,193ccm - Capping (Rail | 2026-02-19 | 2026-02-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.7150 | Deleted - Sec.2 - Fill - Cut 03 - 1,750ccm - Capping (Rail | 2026-02-10 | 2026-02-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.7160 | Deleted - Sec.2 - Fill - Fill 05 - 1,234ccm - Capping (Rail | 2026-02-13 | 2026-02-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9450 | Deleted - Design Deliverables Submission for Workshops and comments - 2.01 - Stage 2 | 2025-02-28 | 2025-03-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9460 | Deleted - Safety Assurance / SiD - 2.01 - Stage 2 | 2025-02-28 | 2025-03-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.6720 | Deleted - Sec.1 - Fill - Fill 02 - 395ccm - Strip/Grade RMAR with type D Material (U5 Class | 2025-11-13 | 2025-11-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.6730 | Deleted - Sec.1 - Fill - Fill 03 - 261ccm - Strip/Grade RMAR with type D Material (U5 Class | 2025-11-16 | 2025-11-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.KM.2030 | Deleted - Final Material Delivered to Site - UTILITIES
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19810 | Deleted - Sec.5 - Powder Horn Trib Br - Detailed Earthworks Pier Pile Cap Pier 2 | 2026-03-30 | 2026-04-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8300 | Deleted - Submission to IRPL SDR - 1.02 - Stage 1 | 2025-02-17 | 2025-02-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8310 | Deleted - IRPL Review (20 B.days) - 1.02 - Stage 1 | 2025-02-18 | 2025-03-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.9900 | Deleted - Sec.4 - Fill - Fill 30 - 1,603ccm - Structural Fill | 2026-06-02 | 2026-06-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-2192 | Deleted - CoA - E38_NEW - Update & address and Comments - Environmental Cleared native vegetation | 2025-06-06 | 2025-06-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13320 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Utilities Design -Z2 - 2.08 - Stage 1 | 2024-10-17 | 2024-12-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13330 | Deleted - Start Package 2.08 - Utility Infrastructure - 2.08 - Stage 1 | 2024-10-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5930 | Deleted - Issue Responses & Receive Comment Closeout - 3.02 - Stage 3 | 2025-07-25 | 2025-07-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5940 | Deleted - Submission to IRPL DDR - 3.02 - Stage 3 | 2025-08-01 | 2025-08-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5950 | Deleted - IRPL Review (20 B.days) - 3.02 - Stage 3 | 2025-08-01 | 2025-08-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5880 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Geotechnical Design - BGW - 3.02 - Stage 3 | 2025-06-13 | 2025-07-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5890 | Deleted - Design Deliverables Submission for Workshops and comments - 3.02 - Stage 3 | 2025-07-11 | 2025-07-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5900 | Deleted - Safety Assurance / SiD - 3.02 - Stage 3 | 2025-07-11 | 2025-07-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5990 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2990 | Deleted - Configuration Change Acceptance Notice | 2025-03-20 | 2025-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12060 | Deleted - Safety Assurance / SiD | 2025-04-16 | 2025-04-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.19780 | Deleted - Place Enveloper Pipe - DN300 RCP 1.5m past crdr boundary (50m) - (ch. 5555) | 2025-08-16 | 2025-08-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.ISC.1100 | Deleted - ISC Self-Assessment (Deletet) Not Required | 2025-02-11 | 2025-03-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.ISC.1110 | Deleted - ISC Assessment submission Not Required | 2025-03-04 | 2025-03-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12200 | Deleted - Safety Assurance / SiD - E3- Stage 3 | 2025-06-27 | 2025-07-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12320 | Deleted - TfNSW Review (30 B.days) - E3- Stage 2 - Level Crossings - GF | 2025-05-08 | 2025-06-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12310 | Deleted - TfNSW Review (30 B.days) - E3- Stage 3 - Level Crossings - GF | 2025-07-21 | 2025-09-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15900 | Deleted - ACVA - JH Finalise draft - Aboriginal Cultural Heritage Assessment Report | 2024-11-25 | 2024-12-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15910 | Deleted - ACVA- JH Internal review - Aboriginal Cultural Heritage Assessment Report | 2025-01-06 | 2025-01-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10510 | Deleted - Design Deliverables Submission for Workshops and comments - Stage 2 - culverts - 1.05 - Stage 2 | 2025-03-27 | 2025-04-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10520 | Deleted - Safety Assurance / SiD - 1.05 - Stage 2 | 2025-03-27 | 2025-04-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.C.10C-480 | Deleted - Engage Subcontractor - Pile Trimming | 2025-06-13 | 2025-08-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.C.10C-490 | Deleted - Subcontractor Mob to Site - Pile Trimming | 2025-08-11 | 2025-09-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.C.10TR-98 | Deleted - Prepare Tender Documents - Street Lighting / Traffic Signals | 2025-02-07 | 2025-03-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.C.10TR-108 | Deleted - Pricing by Suppliers / Subcontractors- Street Lighting / Traffic Signals | 2025-03-07 | 2025-04-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9430 | Deleted - IRPL Review (20 B.days) - 2.10 - Stage 3 | 2025-05-30 | 2025-06-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8290 | Deleted - Issue Responses & Receive Comment Closeout - 1.02 - Stage 1 | 2025-02-10 | 2025-02-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.14370 | Deleted - Sec.5 - IRPL Sleeper Stockpiles | 2026-10-06 | 2026-10-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5030 | Deleted - IRPL Submits CCB to SM Sub CCB | 2026-12-11 | 2026-12-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9490 | Deleted - TfNSW Review (30 B.days) - 2.10 - Stage 3 - Road Drainage - Sec.2 to 5 | 2025-05-30 | 2025-07-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-2212 | Deleted - Land Access required by (DROP DEAD) - CH8750 - 11400 (around 9400 RFI#2558) | 2025-07-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-1392 | Deleted - Land Access - Quarry Material | 2025-07-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.11.14340 | Deleted - Build Temporary level Crossing of CRN for Cut to Fill (For BGW) Not required | 2025-08-16 | 2025-08-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.17310 | Deleted - CFEMP - 2nd Submission to ER for review and endorsement - Bushfire Emergency Plan CoA -C24, E98
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.5-254 | Deleted - Prepare & Submit to IRPL PM / Project Verifier - Construction Traffic MP (30 Bdays after Date of Deed) (Dup | 2024-09-30 | 2024-11-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11010 | Deleted - Sec.5 - Fill - Fill 38 - 1,900ccm - Structural Fill | 2026-07-09 | 2026-07-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11020 | Deleted - Sec.5 - Fill - Cut 32 - 1,296ccm - Structural Fill | 2026-07-12 | 2026-07-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15610 | Deleted - CTTAMP - DPHI Completion of Review/Approval (2 weeks/ 14 cd) | 2025-03-20 | 2025-04-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6020 | Deleted - Safety Assurance / SiD - W.09 - Stage 1 | 2024-11-22 | 2024-11-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8760 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Geotechnical GIR - 1.01 - Stage 4 | 2025-05-12 | 2025-06-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2410 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-06-30 | 2025-07-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2440 | Deleted - Configuration Change Acceptance Notice | 2025-08-05 | 2025-08-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2430 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-07-28 | 2025-07-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10760 | Deleted - Sec.5 - Fill - Fill 41 - 1,662ccm - Mid | 2025-11-22 | 2025-11-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10730 | Deleted - Sec.5 - Fill - Fill 36 - 9,651ccm - Mid | 2025-11-11 | 2025-11-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10740 | Deleted - Sec.5 - Fill - Fill 39 - 2,779ccm - Mid | 2025-11-18 | 2025-11-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10750 | Deleted - Sec.5 - Fill - Fill 40 - 2,549ccm - Mid | 2025-11-20 | 2025-11-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10770 | Deleted - Sec.5 - Fill - Fill 42 - 1,059ccm - Mid | 2025-11-23 | 2025-11-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15270 | Deleted - Sec.5 - Fill - Fill 38 - 395ccm - Mid | 2026-04-22 | 2026-04-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-1612 | Deleted - Certify Design
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.22.5720 | Deleted - Sec.6 - PUP - Telstra -comms - 37360, 37375 (5 off) OK | 2025-08-19 | 2025-09-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9400 | Deleted - Incorporate IDC & CDR comments - 2.10 - Stage 3 | 2025-05-23 | 2025-05-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9130 | Deleted - Incorporate IDC & CDR comments - 3.05 - Stage 3 | 2025-06-19 | 2025-06-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9140 | Deleted - Issue Responses & Receive Comment Closeout - 3.05 - Stage 3 | 2025-06-19 | 2025-06-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9200 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Culverts - Under Rail - 3.05 - Stage 4 | 2025-07-04 | 2025-08-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9210 | Deleted - Incorporate IDC & CDR / CCB and Stage 3 comments - 3.05 - Stage 4 | 2025-08-11 | 2025-08-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9220 | Deleted - IRPL Review (5 B.days) - 3.05 - Stage 4 | 2025-08-25 | 2025-08-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9230 | Deleted - CDR Package Complete 3.05 - Culverts - Under Rail - 3.05 - Stage 4 |  | 2025-08-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9830 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 3.03 - Stage 2 | 2025-03-17 | 2025-03-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9840 | Deleted - Incorporate IDC & CDR / CCB and Stage 1 comments - 3.03 - Stage 2 | 2025-03-24 | 2025-04-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9860 | Deleted - Submission to IRPL PDR - 3.03 - Stage 2 | 2025-04-07 | 2025-04-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10820 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Level Crossings - 1.04 - Stage 2 | 2025-02-21 | 2025-04-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10830 | Deleted - Design Deliverables Submission for Workshops and comments - 1.04 - Stage 2 | 2025-04-04 | 2025-04-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10840 | Deleted - Safety Assurance / SiD - 1.04 - Stage 2 | 2025-04-04 | 2025-04-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10850 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.04 - Stage 2 | 2025-04-11 | 2025-04-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10860 | Deleted - Incorporate IDC & CDR / CCB and Stage 1 comments - 1.04 - Stage 2 | 2025-04-22 | 2025-05-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10870 | Deleted - Issue Responses & Receive Comment Closeout - 1.04 - Stage 2 | 2025-04-30 | 2025-05-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9340 | Deleted - IRPL Review (20 B.days) - 2.10 - Stage 2 | 2025-03-11 | 2025-04-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9500 | Deleted - TfNSW Review (30 B.days) - 2.10 - Stage 2 - Road Drainage - Sec.2 to 5 | 2025-03-11 | 2025-04-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9370 | Deleted - Design Deliverables Submission for Workshops and comments - 2.10 - Stage 3 | 2025-05-09 | 2025-05-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10600 | Deleted - Safety Assurance / SiD - 1.05 - Stage 3 | 2025-06-11 | 2025-06-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11040 | Deleted - TfNSW Review (30 B.days) - 1.04 - Stage 2 - Level Crossings - Illabo | 2025-05-08 | 2025-06-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8560 | Deleted - Sec.3 - Fill - Cut 14 - 534ccm - Capping (Rail | 2026-05-02 | 2026-05-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8570 | Deleted - Sec.3 - Fill - Fill 18 - 446ccm - Capping (Rail | 2026-05-03 | 2026-05-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9250 | Deleted - Sec.4 - Fill - Fill 28 - 27,033ccm - Lower | 2025-11-28 | 2025-12-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9260 | Deleted - Sec.4 - Fill - Fill 29 - 1,370ccm - Lower | 2025-11-27 | 2025-11-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12370 | Deleted - Incorporate IDC & CDR comments - 2.03 - Stage 1 | 2024-12-20 | 2025-01-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4820 | Deleted - IRPL Reviews & Approves CCR Submission | 2026-11-30 | 2026-12-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4790 | Deleted - Configuration Change Acceptance Notice | 2026-06-18 | 2026-06-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4800 | Deleted - CCB Gate 6 Meeting - Presentation of CCR Submission to SM Sub CCB - Rail Systems | 2027-01-01 | 2027-01-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4810 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2026-11-23 | 2026-11-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4830 | Deleted - IRPL Submits CCB to SM Sub CCB | 2026-12-17 | 2026-12-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4840 | Deleted - Configuration Change Acceptance Notice | 2027-01-04 | 2027-01-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.16330 | Deleted - CSEMP - IRPL to review updated documents (CoA - C5) | 2025-01-21 | 2025-02-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-1830 | Deleted - CoA - E15 - OLD Develop Draft Operation Noise and Vibration Review (ONVR) - Rail (To | 2026-07-13 | 2026-08-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.16350 | Deleted - CoA - C30- Old - Develop Noise Monitoring Programs | 2024-09-30 | 2024-10-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-9 | Deleted - Relocation Request & Assessment - Essential Energy | 2025-03-07 | 2025-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-10 | Deleted - Utility Design - Essential Energy | 2025-03-21 | 2025-04-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-11 | Deleted - Ausgrid Review & Comment - Essential Energy | 2025-04-04 | 2025-04-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-12 | Deleted - Update Design to Reflect Ausgrid Comments - Essential Energy | 2025-04-22 | 2025-05-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.6740 | Deleted - Sec.1 - Fill - Cut 01 - 835ccm - Capping RMAR | 2025-11-17 | 2025-11-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2960 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-02-04 | 2025-02-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.WAD.1150 | Deleted - Arrange for community consultation and submits media releases to TfNSW |  | 2025-09-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.WAD.2600 | Deleted - IV Review of TfNSW comments
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.WAD.1120 | Deleted - IRPL advises Project Officer of proposed contractors and sub-contractors |  | 2025-09-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.WAD.1130 | Deleted - Submit Project Management Plans (PMPs) and any other pre-construction documentation |  | 2025-09-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10730 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Level Crossings - 1.04 - Stage 1 | 2024-12-05 | 2025-02-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.8150 | Deleted - Sec.3 - Fill - Fill 19 - 1,973ccm - Upper A | 2026-04-27 | 2026-04-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.8170 | Deleted - Sec.3 - Fill - Fill 20 - 16,739ccm - Upper A | 2026-04-28 | 2026-05-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.7970 | Deleted - Sec.3 - Fill - Fill 10 - 4,666ccm - Upper A | 2026-02-17 | 2026-02-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.7990 | Deleted - Sec.3 - Fill - Fill 11 - 3,124ccm - Upper A | 2026-02-20 | 2026-02-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19880 | Deleted - Sec.5 - Powder Horn Trib Br - Approach Transition Slab North - 9m3 | 2026-07-06 | 2026-07-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5120 | Deleted - Issue Responses & Receive Comment Closeout - W.02 - Stage 1 | 2024-12-06 | 2024-12-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5140 | Deleted - Submission to IRPL SDR - W.02 - Stage 1 | 2024-12-13 | 2024-12-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5150 | Deleted - IRPL Review (20 B.days) - W.02 - Stage 1 - Noise | 2024-12-16 | 2025-01-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12240 | Deleted - Start Package W.02 - Noise - W.02 - Stage 1 | 2024-10-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5070 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Noise - W.02 - Stage 1 | 2024-10-03 | 2024-11-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5080 | Deleted - Design Deliverables Submission for Workshops and comments - W.02 - Stage 1 | 2024-11-22 | 2024-11-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5090 | Deleted - Safety Assurance / SiD - W.02 - Stage 1 | 2024-11-22 | 2024-11-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5100 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - W.02 - Stage 1 | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5100 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - E4 - LXs General
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2920 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-07-14 | 2025-07-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20670 | Deleted - Sec.3 - Dirnaseer Rd Br - Wing Walls Culverts - North side 2 off. left & right - 12m3 | 2026-05-16 | 2026-05-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21780 | Deleted - Sec.3 - Dirnaseer Rd Br - Wing Walls Culverts - South side 2 off. left & right - 12m3 | 2026-05-16 | 2026-05-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20600 | Deleted - Sec.3 - Dirnaseer Rd Br - Construct base slab - 24m3 | 2026-04-13 | 2026-04-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9310 | Deleted - IRPL Review (20 B.days) - 2.02 - Stage 3 | 2025-06-23 | 2025-07-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3900 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Drainage - 3.10 - Stage 4 | 2025-07-21 | 2025-08-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4230 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-02-28 | 2025-02-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.17180 | Deleted - CoA E133 - JH Respond and incorporate to DPHI comments
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.17150 | Deleted - CoA E133 - Submit to DPHI for Review (I month prior to Construction)
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.17170 | Deleted - CoA E133 - JH Final Submission to DPHI for Approval
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.17140 | Deleted - CoA E133 - Knowledge Keepers Review Period
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.C.10C-25 | Deleted - Engage Subcontractor - Earthwork Stabilisation | 2024-11-29 | 2025-02-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.C.10C-26 | Deleted - Subcontractor Mob to Site - Earthwork Stabilisation | 2025-02-10 | 2025-02-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19530 | Deleted - Sec.4 - Old Cootmundra Rail Br - Precast Abutment Panels - North Abutment | 2026-06-03 | 2026-06-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1760 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-08-01 | 2025-08-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4250 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - (H1,H2,H3,H4 & H5) | 2025-02-03 | 2025-02-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4260 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2024-12-06 | 2025-01-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1750 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Geotechnical Design | 2025-09-01 | 2025-09-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1770 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-08-11 | 2025-08-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1780 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-08-28 | 2025-08-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1790 | Deleted - Configuration Change Acceptance Notice | 2025-09-02 | 2025-09-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10720 | Deleted - Sec.5 - Fill - Fill 35 - 441ccm - Mid | 2025-11-10 | 2025-11-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.15-224 | Deleted - Following completion of each week of field assessment, provision of clearance advice for early works | 2024-12-02 | 2024-12-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.7840 | Deleted - Sec.3 - Fill - Fill 16 - 7,528ccm - Lower | 2026-01-08 | 2026-01-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.7890 | Deleted - Sec.3 - Fill - Fill 13 - 2,535ccm - Mid | 2026-02-07 | 2026-02-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.7900 | Deleted - Sec.3 - Fill - Fill 15 - 2,454ccm - Mid | 2026-02-09 | 2026-02-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.7920 | Deleted - Sec.3 - Fill - Fill 17 - 4,631ccm - Mid | 2026-02-12 | 2026-02-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1090 | Deleted - Configuration Change Acceptance Notice | 2025-06-19 | 2025-06-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12830 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Utility Infrastructure - 1.08 - Stage 4 | 2025-06-11 | 2025-07-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12840 | Deleted - Incorporate IDC & CDR comments - 1.08 - Stage 4 | 2025-07-02 | 2025-07-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6080 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Earthworks - Model - Volumes - W.09 - Stage 2 | 2024-12-13 | 2025-02-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6090 | Deleted - Design Deliverables Submission for Workshops and comments - Stage 2 | 2025-02-20 | 2025-02-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6100 | Deleted - Safety Assurance / SiD - W.09 - Stage 2 | 2025-02-20 | 2025-02-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6110 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - W.09 - Stage 2 | 2025-02-27 | 2025-03-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6120 | Deleted - Incorporate IDC & CDR / CCB and Stage 1 comments - W.09 - Stage 2 | 2025-03-06 | 2025-03-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9080 | Deleted - IRPL Review (20 B.days) - 1.10 - Stage 3 | 2025-06-30 | 2025-07-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9140 | Deleted - TfNSW Review (30 B.days) - 1.10 - Stage 3 - Road Drainage - Sec.1 | 2025-06-30 | 2025-08-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10620 | Deleted - Incorporate IDC & CDR comments - 1.05 - Stage 3 | 2025-06-25 | 2025-07-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10630 | Deleted - Issue Responses & Receive Comment Closeout - 1.05 - Stage 3 | 2025-06-25 | 2025-07-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10640 | Deleted - Submission to IRPL DDR - 1.05 - Stage 3 | 2025-07-02 | 2025-07-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.74.14660 | Deleted - Sec.6 - CSR - Local ULX | 2026-03-26 | 2026-03-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19710 | Deleted - Sec.6 - BGW Bridge - LOE - Float between 2 phases - LOE | 2026-07-24 | 2026-09-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-562 | Deleted - JH Design & Review/Comment | 2025-01-31 | 2025-02-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-127 | Deleted - JH Horizontal & Vertical Alignment Design for Telstra | 2024-10-17 | 2024-11-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.74.14380 | Deleted - Sec.6 - CSR - Construct Main Cable Route - MCR - 51 Points to SL30 (455057 - 456716) - 1725m | 2026-02-14 | 2026-02-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8230 | Deleted - Sec.3 - Fill - Fill 12 - 373ccm - Structural Fill | 2026-04-11 | 2026-04-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8240 | Deleted - Sec.3 - Fill - Cut 09 - 1,960ccm - Structural Fill | 2026-04-12 | 2026-04-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-2500 | Deleted - CoA - E17_OLD - Operational Noise and Vibration Review (ONVR) Approved prior to Operations | 2026-09-08 | 2026-09-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6480 | Deleted - Incorporate IDR comments - D9 - Stage 3 | 2025-06-25 | 2025-07-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6000 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Bridges - Powder Horn Tributary Creek Un
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6490 | Deleted - Issue Responses & Receive Comment Closeout - D9 - Stage 3 | 2025-06-25 | 2025-07-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6500 | Deleted - Submission to IRPL - D9 - Stage 3 | 2025-07-02 | 2025-07-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6510 | Deleted - IRPL Review (20 B.days) - D9 - Stage 3 | 2025-07-02 | 2025-07-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.15530 | Deleted - Internal IDR Review (By JHG) - L2 - Stage 2 (Modified)
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.15540 | Deleted - Design Presentation to IRPL - DPK Presentation - L2 - Stage 2 (Modified already part of original Contract P
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8070 | Deleted - Safety Assurance / SiD | 2025-02-07 | 2025-02-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8160 | Deleted - Design Development - Stage 2 - Preliminary Design / PDD -Maintenance plans & Access - L2 - Stage 2 | 2025-03-03 | 2025-04-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8170 | Deleted - Internal IDR workshop (By BGE) - L2 - Stage 2 | 2025-04-22 | 2025-04-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8190 | Deleted - Review of IDR comment response and final review - L2 - Stage 2 | 2025-04-30 | 2025-05-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8200 | Deleted - Incorporate IDR comments - L2 - Stage 2 | 2025-05-07 | 2025-05-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8210 | Deleted - Issue Responses & Receive Comment Closeout - L2 - Stage 2 | 2025-05-14 | 2025-05-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10980 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Level Crossings - 1.04 - Stage 4 | 2025-08-05 | 2025-09-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10990 | Deleted - Incorporate IDC & CDR / CCB and Stage 3 comments - 1.04 - Stage 4 | 2025-09-09 | 2025-09-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20050 | Deleted - Sec.4 - Old Cootmundra Rail Br - Pile Cap - 8m3 - North Abutment | 2026-04-16 | 2026-04-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9330 | Deleted - Sec.4 - Fill - Fill 21 - 1,266ccm - Mid | 2025-12-22 | 2025-12-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9340 | Deleted - Sec.4 - Fill - Fill 22 - 2,888ccm - Mid | 2026-02-21 | 2026-02-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9350 | Deleted - Sec.4 - Fill - Fill 23 - 1,422ccm - Mid | 2026-03-21 | 2026-03-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9360 | Deleted - Sec.4 - Fill - Fill 24 - 263ccm - Mid | 2026-03-23 | 2026-03-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9110 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 2.02 - Stage 1 | 2025-01-06 | 2025-01-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9120 | Deleted - Incorporate IDC & CDR comments - 2.02 - Stage 1 | 2025-01-13 | 2025-01-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9140 | Deleted - Submission to IRPL SDR - 2.02 - Stage 1 | 2025-01-20 | 2025-01-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9150 | Deleted - IRPL Review (20 B.days) - 2.02 - Stage 1 | 2025-01-21 | 2025-02-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-2202 | Deleted - Inland Rail Albury to Illabo (A2I) enhancement project completed slew works along IRPLs Main South Line (Not | 2025-03-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.18470 | Deleted - Float before Track can commence - Sec.1 - converted LOE | 2026-03-26 | 2026-04-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.14250 | Deleted - Sec.1 - IRPL Sleeper Stockpiles - Sec.1 | 2026-04-22 | 2026-04-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-742 | Deleted - Land Access Granted - LX 39450 truck swing land | 2025-06-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.ISC.1030 | Deleted - ISC Assessment (Delete Duplicate of Weighting Assessment) | 2024-10-23 | 2024-11-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1540 | Deleted - Configuration Change Acceptance Notice | 2025-07-08 | 2025-07-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1500 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Earthworks - Model - Volumes | 2025-07-07 | 2025-07-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3300 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Earthworks - Model - Volumes | 2025-02-03 | 2025-02-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.11300 | Deleted - Sec.5 - Fill - Cut 30 - 467ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-08-12 | 2026-08-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.11310 | Deleted - Sec.5 - Fill - Fill 37 - 604ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-08-14 | 2026-08-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-2182 | Deleted - CoA - E38_NEW - Riparian land disturbed during construction must be rehabilitated-Cleared native vegetation | 2025-02-06 | 2025-03-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-2312 | Deleted - CoA - E38_NEW - IRPL Review and issue Comments -Environmental -Cleared native vegetation | 2025-05-09 | 2025-06-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.BI-1290 | Deleted - CoA - E42_NEW - consultation with DPI Fisheries on Watercourse crossings (To | 2024-11-27 | 2025-01-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.BI-1310 | Deleted - CoA - E43_NEW - Fauna access pathways to connectivity (To | 2025-04-15 | 2025-05-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-80 | Deleted - Goldenfields Water Review & Approve Design - Goldenfields Water | 2025-01-21 | 2025-02-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-81 | Deleted - Prepare Tender Docs & Issue RFT - Goldenfields Water | 2025-03-07 | 2025-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1640 | Deleted - Configuration Change Acceptance Notice | 2025-09-18 | 2025-09-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9180 | Deleted - Design Deliverables Submission for Workshops and comments - 2.10 - Stage 1 | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9190 | Deleted - Safety Assurance / SiD - 2.10 - Stage 1 | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9200 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 2.10 - Stage 1 | 2024-12-06 | 2024-12-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-13 | Deleted - Ausgrid Review & Approve - Essential Energy | 2025-05-07 | 2025-05-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1600 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Corridor | 2025-09-17 | 2025-09-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1610 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-07-31 | 2025-08-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1620 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-08-13 | 2025-08-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1630 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-09-01 | 2025-09-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9660 | Deleted - Sec.4 - Fill - Fill 31 - 6,444ccm - Upper A | 2026-04-07 | 2026-04-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9730 | Deleted - Sec.4 - Fill - Fill 34 - 10,478ccm - Upper A | 2026-04-18 | 2026-04-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6160 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Earthworks - Model - Volumes - W.09 - Stage 3 | 2025-03-20 | 2025-05-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6170 | Deleted - Design Deliverables Submission for Workshops and comments - W.09 - Stage 3 | 2025-05-14 | 2025-05-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6180 | Deleted - Safety Assurance / SiD - W.09 - Stage 3 | 2025-05-14 | 2025-05-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6190 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - W.09 - Stage 3 | 2025-05-20 | 2025-05-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6200 | Deleted - Incorporate IDC & CDR comments - W.09 - Stage 3 | 2025-05-27 | 2025-06-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6210 | Deleted - Issue Responses & Receive Comment Closeout - W.09 - Stage 3 | 2025-05-27 | 2025-06-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6220 | Deleted - Submission to IRPL DDR - W.09 - Stage 3 | 2025-06-03 | 2025-06-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6230 | Deleted - IRPL Review (20 B.days) - W.09 - Stage 3 | 2025-06-03 | 2025-07-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10090 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Bridges - 1.06 - Stage 1 | 2024-10-18 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10100 | Deleted - Design Deliverables Submission for Workshops and comments - 1.06 - Stage 1 | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21850 | Deleted - Sec.3 - Dirnaseer Rd Br - FRP - Tee Roff Diaphragm Beam (2off) - Pier Dirnaseer Road Underbridge - 3m3 | 2026-03-04 | 2026-03-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20640 | Deleted - Sec.3 - Dirnaseer Rd Br - Apron Slab & Wingwalls & handrail | 2026-05-02 | 2026-05-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.11.15690 | Deleted - Stockpile Management
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.11.15630 | Deleted - Stockpile Management
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.11.15570 | Deleted - Stockpile Management
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4970 | Deleted - IRPL Reviews & Approves CCR Submission (To | 2026-05-21 | 2026-06-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.74.14110 | Deleted - Sec.1 - CSR - Local ULX - Across Track - 418400 | 2025-09-24 | 2025-09-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.74.14120 | Deleted - Sec.1 - CSR - Local ULX - Across Track - 418005 | 2025-09-21 | 2025-09-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.74.14130 | Deleted - Sec.1 - CSR - Local ULX - Axle Counter Q22 (465044) - POSS | 2025-09-13 | 2025-09-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2970 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-02-14 | 2025-03-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15590 | Deleted - CTTAMP - DPHI Lodgement and DPHI Review (2 weeks/ 14 cd) | 2025-02-20 | 2025-03-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15600 | Deleted - CTTAMP - JH Respond and incorporate to DPHI comments | 2025-03-06 | 2025-03-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15620 | Deleted - CTTAMP - approved |  | 2025-04-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6150 | Deleted - IRPL Review (20 B.days) - W.09 - Stage 2 | 2025-03-21 | 2025-04-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13260 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 2.08 - Stage 1 | 2024-12-05 | 2024-12-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6130 | Deleted - Issue Responses & Receive Comment Closeout | 2025-03-13 | 2025-03-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6140 | Deleted - Submission to IRPL PDR - W.09 - Stage 2 | 2025-03-20 | 2025-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-19 | Deleted - Package Placement - Essential Energy - Illabo LGA | 2025-06-04 | 2025-06-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-1672 | Deleted - Land Access required by - All Non-Licenced Areas in Table 1 | 2025-03-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-20 | Deleted - Nominate ASP LvL1 to Essential Energy - Illabo LGA | 2025-06-19 | 2025-07-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10650 | Deleted - IRPL Review (20 B.days) - 1.05 - Stage 3 | 2025-07-03 | 2025-07-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10660 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Culverts - Under Rail - 1.05 - Stage 4 | 2025-07-10 | 2025-08-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.17010 | Deleted - CGMMP - ER to review updated documents and Approve
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15650 | Deleted - CGMMP - Consultation with relevant Government agencies (up to 3 weeks) | 2024-12-10 | 2025-01-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15660 | Deleted - CGMMP - Respond to stakeholder comments | 2025-01-14 | 2025-01-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15670 | Deleted - CGMMP - Submission to ER for review and endorsement and IRPL Review (Delete duplicate) | 2025-01-21 | 2025-02-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15680 | Deleted - CGMMP - DPHI Lodgement and DPHI Review (2 weeks/ 14 cd) (To | 2025-02-19 | 2025-03-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15690 | Deleted - CGMMP - JH Respond and incorporate to DPHI comments (To | 2025-03-05 | 2025-03-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1900 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Culverts | 2025-08-04 | 2025-08-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1910 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-06-27 | 2025-07-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5440 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Roads - BGW - 3.07 - Stage 1 | 2024-10-03 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5450 | Deleted - Design Deliverables Submission for Workshops and comments - 3.07 - Stage 1 | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5460 | Deleted - Safety Assurance / SiD - 3.07 - Stage 1 | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.17130 | Deleted - Sec.5 - Powder Horn Ck Br - FRP - MPa/20 in kerb - | 2026-06-19 | 2026-06-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.85.6040 | Deleted - Sec.5 - Landscaping - Ch28300-37300 | 2026-12-07 | 2026-12-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.11.13200 | Deleted - Telstra relocation along Dudauman Road western verge adjacent to Private Driveway (PR32150) intersection CH3 | 2025-09-10 | 2025-09-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.11.13210 | Deleted - Sec.5 - Telstra relocation along Dudauman Road western verge adjacent to Corbys Lane intersection CH3378 | 2025-09-12 | 2025-09-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-1892 | Deleted - Aboriginal survey/Salvage and walk over (2 weeks) | 2025-06-17 | 2025-07-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-1902 | Deleted - Prepare Aboriginal survey/Salvage Methodology | 2025-05-14 | 2025-06-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.15-544 | Deleted - Proponent prepares draft cultural heritage assessment report and provides it to the RAP for Comment | 2025-05-14 | 2025-05-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.15-554 | Deleted - Registered Aboriginal parties have a minimum of 28 days after proponent provides draft report to review and | 2025-05-28 | 2025-06-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.15-564 | Deleted - Proponent finalises cultural heritage assessment report. Final Report is submitted to Heritage NSW with AHIP | 2025-07-02 | 2025-07-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.15-574 | Deleted - Proponent provides/makes available the fnal cultural heritage assessment report and AHIP application to RAP | 2025-07-10 | 2025-07-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7120 | Deleted - Design Development - Rail Systems (Power/Signalling) - W.01 - Stage 1 | 2024-10-25 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7130 | Deleted - Internal IDR workshop (By BGE) - W.01 - Stage 1 | 2024-12-13 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7150 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - W.01 - Stage 1 | 2024-12-20 | 2025-01-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12330 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Earthworks Formation Design Documentation - 2.03 - | 2024-10-25 | 2024-12-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12340 | Deleted - Design Deliverables Submission for Workshops and comments - 2.03 - Stage 1 | 2024-12-06 | 2024-12-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12360 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 2.03 - Stage 1 | 2024-12-13 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12380 | Deleted - Issue Responses & Receive Comment Closeout - 2.03 - Stage 1 | 2024-12-20 | 2025-01-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12420 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Earthworks Formation Design Documentation - 2.03 | 2025-01-10 | 2025-03-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12430 | Deleted - Design Deliverables Submission for Workshops and comments - 2.03 - Stage 2 | 2025-03-03 | 2025-03-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12440 | Deleted - Safety Assurance / SiD - 2.03 - Stage 2 | 2025-03-03 | 2025-03-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8370 | Deleted - Issue Responses & Receive Comment Closeout - 1.02 - Stage 2 | 2025-05-08 | 2025-05-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8380 | Deleted - Submission to IRPL PDR - 1.02 - Stage 2 | 2025-05-15 | 2025-05-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15540 | Deleted - CTTAMP - JH Finalise draft | 2024-10-01 | 2024-11-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15550 | Deleted - CTTAMP - JH Internal review | 2024-11-06 | 2024-11-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15560 | Deleted - CTTAMP - Consultation with relevant Government agencies (up to 3 weeks) | 2024-12-11 | 2025-01-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.8430 | Deleted - TfNSW Review (30 B.days) - 3.10 - Stage 4 - Road Drainage - Sec.1 | 2025-08-19 | 2025-09-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14280 | Deleted - Sec.2 - Cut - Fill 08 - 3,955ccm - OD Soil | 2025-11-07 | 2025-11-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.22.11930 | Deleted - Sec.1 - PUP Private Power - 1700 - Exist OH power x-ing track & Olympic Hwy. | 2025-07-21 | 2025-07-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14240 | Deleted - Sec.1 - Cut - Cut 01 - 6,279ccm - XW-MW No Rock | 2025-09-07 | 2025-09-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14250 | Deleted - Sec.1 - Cut - Cut 01 - 18,456ccm - MW SS | 2025-09-11 | 2025-09-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.13960 | Deleted - Sec.1 - Clear and grub T/O pads | 2025-10-02 | 2025-10-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.13970 | Deleted - Sec.1 - Clear and grub ballast stockpile | 2025-10-06 | 2025-10-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.WAD.1170 | Deleted - Apply for ROL and sends approved ROL to Project Officer |  | 2025-09-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.WAD.1140 | Deleted - TfNSW Project Officer advises of acceptance of PMPs |  | 2025-09-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.WAD.1160 | Deleted - TfNSW Project Officer provides written approval of Media release |  | 2025-09-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.WAD.1200 | Deleted - TfNSW Project Officer sends IRPL approval to commence Construction letter |  | 2025-10-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11160 | Deleted - Sec.5 - Fill - Cut 31 - 696ccm - Capping (Rail | 2026-07-09 | 2026-07-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9360 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Geotechnical GIR - 2.01 - Stage 1 | 2024-10-10 | 2024-12-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9370 | Deleted - Design Deliverables Submission for Workshops and comments - 2.01 - Stage 1 | 2024-11-28 | 2024-12-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11050 | Deleted - Sec.5 - Fill - Cut 33 - 792ccm - Structural Fill | 2026-07-18 | 2026-07-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11060 | Deleted - Sec.5 - Fill - Fill 40 - 1,693ccm - Structural Fill | 2026-07-19 | 2026-07-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18090 | Deleted - Sec.5 - Powder Horn Trib Br - Construct laydown area /Causeway (inc pipes) | 2026-01-05 | 2026-01-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11080 | Deleted - Sec.5 - Fill - Fill 42 - 1,549ccm - Structural Fill | 2026-07-23 | 2026-07-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11090 | Deleted - Sec.5 - Fill - Cut 34 - 450ccm - Structural Fill | 2026-07-26 | 2026-07-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10990 | Deleted - Sec.5 - Fill - Fill 37 - 1,710ccm - Structural Fill | 2026-07-03 | 2026-07-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11000 | Deleted - Sec.5 - Fill - Cut 31 - 1,011ccm - Structural Fill | 2026-07-07 | 2026-07-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10940 | Deleted - Sec.5 - Fill - Fill 35 - 197ccm - Structural Fill | 2026-06-22 | 2026-06-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10960 | Deleted - Sec.5 - Fill - Fill 36 - 3,146ccm - Structural Fill | 2026-06-24 | 2026-06-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10970 | Deleted - Sec.5 - Fill - Cut 29 - 410ccm - Structural Fill | 2026-06-30 | 2026-06-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10980 | Deleted - Sec.5 - Fill - Cut 30 - 1,128ccm - Structural Fill | 2026-07-01 | 2026-07-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.9810 | Deleted - Sec.4 - Fill - Fill 25 - 177ccm - Structural Fill | 2026-05-21 | 2026-05-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.15820 | Deleted - Sec.3 - Run Boundary Ck Br - Erection of transverse stressing units | 2026-04-09 | 2026-04-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5950 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Bridges - Powder Horn Tributary Creek U
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5960 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5970 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.15-364 | Deleted - Initial findings from survey and test excavation can be provided formally | 2024-12-16 | 2024-12-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.15-494 | Deleted - Proponent presents and/or provides the proposed methodology(s) for the cultural heritage assessment to RAP f | 2025-05-09 | 2025-05-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.15-504 | Deleted - Registered Aboriginal parties have a minimum of 28 days after methodology to provide comment | 2025-05-14 | 2025-06-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10530 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.05 - Stage 2 | 2025-04-03 | 2025-04-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10540 | Deleted - Incorporate IDC & CDR / CCB and Stage 1 comments - 1.05 - Stage 2 | 2025-04-10 | 2025-04-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10550 | Deleted - Issue Responses & Receive Comment Closeout - 1.05 - Stage 2 | 2025-04-17 | 2025-04-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10560 | Deleted - Submission to IRPL PDR - 1.05 - Stage 2 | 2025-04-29 | 2025-04-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10570 | Deleted - IRPL Review (20 B.days) - 1.05 - Stage 2 | 2025-04-30 | 2025-05-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10500 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Culverts - Under Rail - 1.05 - Stage 2 | 2025-01-30 | 2025-04-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.18470 | Deleted - Application for CRN Approval in Principal (AIP)
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.5-1094 | Deleted - CoA - E162 - Prepare & Submit to IRPL/ Planning Sec. Unexpected Finds for Contamination Procedure (Delete pa | 2024-10-29 | 2024-12-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.17990 | Deleted - Sec.5 - Powder Horn Trib Br - Bridge site prep /Temp Fence/Road Barriers | 2025-12-17 | 2025-12-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18000 | Deleted - Sec.5 - Powder Horn Trib Br - Construct site access | 2025-12-22 | 2025-12-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.7820 | Deleted - Sec.3 - Fill - Fill 13 - 15,830ccm - Lower | 2026-01-27 | 2026-02-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.7830 | Deleted - Sec.3 - Fill - Fill 15 - 18,007ccm - Lower | 2026-01-13 | 2026-01-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6010 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5880 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5890 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.16070 | Deleted - Sec.3 - SIG - Install New Swing nose - T 250 rad Pts Backdrive (4 off) - 51A,52 | 2026-08-03 | 2026-08-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.16080 | Deleted - Sec.3 - SIG - Install New Swing nose Dis. Box Points (2 off) - 51A,52 - 51 pts/P.RD 9.151/11.349 (Delet | 2026-08-12 | 2026-08-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9670 | Deleted - TfNSW Review (30 B.days) - E2 - Stage 2 - Level Crossings (Public - Junee Shire Council) | 2025-05-01 | 2025-06-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19890 | Deleted - Sec.5 - Powder Horn Trib Br - Approach Slab South - 9m3 | 2026-07-23 | 2026-07-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18370 | Deleted - Sec.5 - Powder Horn Trib Br - Deck | 2026-08-11 | 2026-08-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18390 | Deleted - Sec.5 - Powder Horn Trib Br - FRP - MPa/20 in kerb - 10m3 | 2026-08-20 | 2026-08-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18400 | Deleted - Sec.5 - Powder Horn Trib Br - Parapet | 2026-08-20 | 2026-08-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19900 | Deleted - Sec.5 - Powder Horn Trib Br - Wing Walls - North side 2 No - 11m3 | 2026-07-12 | 2026-07-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19910 | Deleted - Sec.5 - Powder Horn Trib Br - Wing Walls - South side 2 No. - 11m3 | 2026-07-31 | 2026-08-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18190 | Deleted - Sec.5 - Powder Horn Trib Br - Abutment 1 Pile Cap - 8m3 | 2026-05-09 | 2026-05-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11210 | Deleted - Sec.5 - Fill - Cut 33 - 548ccm - Capping (Rail | 2026-07-20 | 2026-07-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.74.14630 | Deleted - Sec.6 - CSR - Local ULX | 2026-03-19 | 2026-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11240 | Deleted - Sec.5 - Fill - Fill 42 - 1,090ccm - Capping (Rail | 2026-07-26 | 2026-07-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11250 | Deleted - Sec.5 - Fill - Cut 34 - 306ccm - Capping (Rail | 2026-07-28 | 2026-07-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11220 | Deleted - Sec.5 - Fill - Fill 40 - 1,199ccm - Capping (Rail | 2026-07-22 | 2026-07-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18360 | Deleted - Sec.5 - Powder Horn Trib Br - Install/Lift Bridge span (Standard PSC Slab Span 14m (IRPL) (6 off (2 per | 2026-08-07 | 2026-08-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8230 | Deleted - Submission to IRPL - L2 - Stage 2 | 2025-05-21 | 2025-05-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8240 | Deleted - IRPL Review (20 B.days) - L2 - Stage 2 | 2025-05-22 | 2025-06-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3030 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-01-28 | 2025-01-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3040 | Deleted - Configuration Change Acceptance Notice | 2025-02-04 | 2025-02-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9470 | Deleted - Sec.4 - Fill - Fill 34 - 4,358ccm - Mid | 2026-04-09 | 2026-04-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6030 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6040 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12320 | Deleted - Start Package 2.02 - Geotechnical Design - 2.02 - Stage 1 | 2024-10-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5200 | Deleted - Safety Assurance / SiD - W.02 - Stage 2 | 2025-02-17 | 2025-02-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16520 | Deleted - Sec.3 - Public LX - PU15966 - Drainage - LX Culvert - Trench Excavation / Site Prep | 2026-01-20 | 2026-01-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16530 | Deleted - Sec.3 - Public LX - PU15966 - Drainage - Install 900 RCP - 4 off - 8m | 2026-01-21 | 2026-01-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16490 | Deleted - Sec.3 - Public LX - PU15966 - Drainage - LX Culvert - Trench Excavation/ Culvert site prep | 2026-01-19 | 2026-01-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16500 | Deleted - Sec.3 - Public LX - PU15966 - Drainage - Place RCBC crown units 0.6W x 0.45H RCBC (4 off) 8m | 2026-01-20 | 2026-01-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16510 | Deleted - Sec.3 - Public LX - PU15966 - Drainage - Detailed backfill | 2026-01-21 | 2026-01-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16660 | Deleted - Sec.3 - Public LX - PU15950 - Drainage - Detailed backfill | 2026-01-23 | 2026-01-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16640 | Deleted - Sec.3 - Public LX - PU15950 - Drainage - LX Culvert - Trench Excavation/ Culvert site prep | 2026-01-21 | 2026-01-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16650 | Deleted - Sec.3 - Public LX - PU15950 - Drainage - Install 900 RCP - 2 off - 3m | 2026-01-22 | 2026-01-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13420 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Utilities Design - 2.08 - Stage 2 | 2024-12-19 | 2025-02-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13390 | Deleted - Submission to IRPL PDR - 2.08 - Stage 2 | 2025-03-07 | 2025-03-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3310 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2024-12-16 | 2024-12-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3320 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-01-08 | 2025-01-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9470 | Deleted - CDR Package Complete 2.10 - Drainage (roads) - 2.10 - Stage 4 |  | 2025-09-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9830 | Deleted - Internal IDR Review (By JHG) - D8 - Stage 2 (Modified)
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5720 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Geotechnical Design - 3.02 - Stage 1 | 2024-12-06 | 2025-02-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5800 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Geotechnical Design - 3.02 - Stage 2 | 2025-03-10 | 2025-05-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5810 | Deleted - Design Deliverables Submission for Workshops and comments - 3.02 - Stage 2 | 2025-05-08 | 2025-05-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10C-29 | Deleted - Engage Subcontractor - Fencing (To merge with Fencing S&I) - Double Up | 2025-07-11 | 2025-09-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10C-30 | Deleted - Subcontractor Mob to Site - Fencing - Double Up | 2025-09-08 | 2025-09-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3620 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 3.10 - Stage 1 | 2024-12-20 | 2025-01-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6640 | Deleted - Design Development - Stage 2 - Preliminary Design / PDD - Geotechnical Monitoring - D8 - Stage 2 | 2025-01-14 | 2025-03-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6650 | Deleted - Internal IDR workshop (By BGE) - D8 - Stage 2 | 2025-03-12 | 2025-03-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6670 | Deleted - Review of IDR comment response and final review - D8 - Stage 2 | 2025-03-19 | 2025-03-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6680 | Deleted - Incorporate IDR comments - D8 - Stage 2 | 2025-03-26 | 2025-04-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6690 | Deleted - Issue Responses & Receive Comment Closeout - D8 - Stage 2 | 2025-03-26 | 2025-04-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6700 | Deleted - Submission to IRPL - D8 - Stage 2 | 2025-04-02 | 2025-04-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6710 | Deleted - IRPL Review (20 B.days) - D8 - Stage 2 | 2025-04-03 | 2025-05-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2350 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Level Crossings | 2025-08-20 | 2025-08-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.ISC.1150 | Deleted - ISC Revise Assessment | 2026-02-05 | 2026-04-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.ISC.1160 | Deleted - Dispute - Convene Dispute Panel - If Required | 2026-04-13 | 2026-05-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.16990 | Deleted - CFEMP - ER to review updated documents and Approve
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.5-1014 | Deleted - CoA - E133 - Update Plan to Reflect any Comments - Aboriginal Cultural Values PLan | 2024-11-12 | 2024-11-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.4-64 | Deleted - Project Verifier /IRPL Review Period - Electromagnetic Compatibility MP | 2024-11-05 | 2024-12-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.4-74 | Deleted - Update Plan to Reflect any Comments - Electromagnetic Compatibility MP | 2024-12-03 | 2024-12-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14540 | Deleted - Sec.5 - Cut - Fill 39 - 1569ccm - OD Soil / Soil | 2025-10-12 | 2025-10-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11030 | Deleted - TfNSW Review (30 B.days) - 1.04 - Stage 3 - Level Crossings - Illabo | 2025-07-28 | 2025-09-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10600 | Deleted - Sec.5 - Cut - Cut 33 - 6,695ccm - OD Soil / Soil | 2025-10-16 | 2025-10-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10470 | Deleted - Sec.4 - Fill - Fill 31 - 444ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-07-24 | 2026-07-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10480 | Deleted - Sec.4 - Fill - Cut 26 - 300ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-07-27 | 2026-07-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10490 | Deleted - Sec.4 - Fill - Fill 33 - 226ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-07-28 | 2026-07-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4710 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-01-06 | 2025-01-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4720 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-01-15 | 2025-02-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4730 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-02-04 | 2025-02-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4740 | Deleted - Configuration Change Acceptance Notice | 2025-02-20 | 2025-02-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12550 | Deleted - Design Deliverables Submission for Workshops and comments - 1.08 - Stage 1 | 2024-11-28 | 2024-12-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12560 | Deleted - Safety Assurance / SiD - 1.08 - Stage 1 | 2024-11-28 | 2024-12-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12570 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.08 - Stage 1 | 2024-12-05 | 2024-12-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.6630 | Deleted - Sec.1 - Fill - Fill 01 - 1,131ccm - Structural Fill | 2025-10-23 | 2025-10-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.6640 | Deleted - Sec.1 - Fill - Fill 02 - 1,100ccm - Structural Fill | 2025-10-21 | 2025-10-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.6650 | Deleted - Sec.1 - Fill - Fill 03 - 735ccm - Structural Fill | 2025-10-20 | 2025-10-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.6670 | Deleted - Sec.1 - Fill - Fill 01 - 811ccm - Capping (Rail | 2025-10-26 | 2025-10-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.6680 | Deleted - Sec.1 - Fill - Fill 02 - 779ccm - Capping (Rail | 2025-10-24 | 2025-10-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.6690 | Deleted - Sec.1 - Fill - Fill 03 - 520ccm - Capping (Rail | 2025-10-23 | 2025-10-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12450 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 2.03 - Stage 2 | 2025-03-10 | 2025-03-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12370 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Roads (Private) - 1.09 - Stage 2 | 2024-12-20 | 2025-03-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10W-77 | Deleted - Manufacturing & Delivery- Instrumentation and Montoring | 2025-07-21 | 2025-10-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10W-13 | Deleted - Package Review / Approval - Capping & Structural Fill | 2025-02-14 | 2025-02-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10W-14 | Deleted - Package Placement - Capping & Structural Fill | 2025-02-28 | 2025-03-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3400 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Corridor | 2025-04-07 | 2025-04-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2870 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-07-09 | 2025-07-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2880 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-07-28 | 2025-07-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2890 | Deleted - Configuration Change Acceptance Notice | 2025-08-05 | 2025-08-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15500 | Deleted - CWMP - DPHI Lodgement and DPHI Review (2 weeks/ 14 cd) (To | 2025-02-19 | 2025-03-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9260 | Deleted - Safety Assurance / SiD - 2.02 - Stage 3 | 2025-06-02 | 2025-06-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9220 | Deleted - Submission to IRPL PDR - 2.02 - Stage 2 | 2025-04-15 | 2025-04-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9230 | Deleted - IRPL Review (20 B.days) - 2.02 - Stage 2 | 2025-04-16 | 2025-05-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.8860 | Deleted - Sec.4 - Cut - Cut 19 - 5,146ccm - OD Soil | 2025-11-26 | 2025-11-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.74.15080 | Deleted - Sec.4 - CSR - Main Cable Route - MCR - Pull Cable - 24900 to 28500 - Double Up | 2026-07-01 | 2026-07-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.74.14730 | Deleted - Sec.4 - CSR - Local Cable Route - LCR - 14208 - 28500 | 2026-07-07 | 2026-07-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.85.6370 | Deleted - Sec.4 - Landscaping - Ch18500-28300 | 2026-02-09 | 2026-02-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.8880 | Deleted - Sec.4 - Cut - Cut 21 - 11,334ccm - OD Soil / Soil | 2026-01-26 | 2026-02-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.8900 | Deleted - Sec.4 - Cut - Cut 22 - 32,788ccm - OD Soil / Soil | 2025-12-17 | 2026-01-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.8920 | Deleted - Sec.4 - Cut - Cut 23 - 14,650ccm - OD Soil / Soil | 2025-12-02 | 2025-12-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.8930 | Deleted - Sec.4 - Cut - Cut 24 - 61,390ccm - OD Soil / Soil | 2025-10-07 | 2025-11-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14410 | Deleted - Sec.4 - Cut - Fill 23 - 345ccm - OD Soil | 2025-11-23 | 2025-11-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.74.14450 | Deleted - Sec.5 - CSR - Main Cable Route - MCR - Pull Cable --SL3 Dist to SL6 Dist - 32840 - 37300 | 2026-07-23 | 2026-07-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.74.14650 | Deleted - Sec.6 - CSR - Main ULX - 454093 | 2026-03-23 | 2026-03-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.74.14620 | Deleted - Sec.6 - CSR - Local ULX | 2026-03-11 | 2026-03-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21910 | Deleted - Sec.2 - Ulandra Ck Br - Bridge Deck - 40m3 | 2026-02-09 | 2026-02-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.15280 | Deleted - Sec.2 - Ulandra Ck Br - FRP - [40] MPa/20 in Restraint Blocks - 6m3 | 2026-01-26 | 2026-01-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.15290 | Deleted - Sec.2 - Ulandra Ck Br - Abutment Shear Key/External Diaphragm - 2m3 | 2026-02-01 | 2026-02-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20990. | Deleted - Burley Griffin Way Bridge - Detailed Earthworks Pile Cap Abutment 1 -
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21000. | Deleted - Burley Griffin Way Bridge - Abutment 1 Pile Cap - 15m3
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6900 | Deleted - Sec.2 - Fill - Fill 05 - 4,093ccm - Mid | 2025-10-24 | 2025-10-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6910 | Deleted - Sec.2 - Fill - Fill 06 - 1,918ccm - Mid | 2025-11-18 | 2025-11-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6920 | Deleted - Sec.2 - Fill - Fill 08 - 2,374ccm - Mid | 2025-11-24 | 2025-11-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10420 | Deleted - Sec.4 - Fill - Fill 30 - 541ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-07-12 | 2026-07-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3840 | Deleted - Configuration Change Acceptance Notice | 2025-02-20 | 2025-02-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3800 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Roads - BGW | 2025-02-19 | 2025-02-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3810 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-01-06 | 2025-01-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3830 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-02-04 | 2025-02-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9370 | Deleted - Sec.4 - Fill - Fill 25 - 276ccm - Mid | 2026-03-24 | 2026-03-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9380 | Deleted - Sec.4 - Fill - Fill 26 - 1,056ccm - Mid | 2026-03-26 | 2026-03-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9390 | Deleted - Sec.4 - Fill - Fill 27 - 475ccm - Mid | 2026-03-27 | 2026-03-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9400 | Deleted - Sec.4 - Fill - Fill 28 - 2,554ccm - Mid | 2026-03-28 | 2026-03-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9410 | Deleted - Sec.4 - Fill - Fill 29 - 962ccm - Mid | 2026-03-30 | 2026-03-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.7210 | Deleted - Sec.2 - Fill - Fill 08 - 737ccm - Capping (Rail) - up to LX 8160 | 2026-05-11 | 2026-05-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.7220 | Deleted - Sec.2 - Fill - Fill 09 - 2,126ccm - Capping (Rail) - North of LX 8160 | 2026-05-12 | 2026-05-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5740 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5660 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5670 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4270 | Deleted - IRPL Reviews & Approves CCR Submission - (H1, H2 , H3, H4, H5) | 2025-01-13 | 2025-01-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4280 | Deleted - IRPL Submits CCB to SM Sub CCB - (H1,H2, H3, H4 & H5) | 2025-01-31 | 2025-01-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4290 | Deleted - Configuration Change Acceptance Notice - (H1,H2,H3,H4 & H5) | 2025-02-04 | 2025-02-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.15-614 | Deleted - Identify early works numbered priority areas for clearance purposes. (Not Required) | 2024-11-21 | 2024-11-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.13990 | Deleted - Sec.1 - Form Rail Laydown pad | 2025-09-13 | 2025-09-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.25350 | Deleted - Sec.1 - Turnout pad construction - Import gravel, level and compact | 2025-10-06 | 2025-10-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15450 | Deleted - Sec.6 - Sig - Install New Buildings (2 off) (37573 to 454160) | 2026-05-16 | 2026-05-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15970 | Deleted - Sec.6 - Sig - Install New Power Cable - 35,858m (57 runs) | 2026-03-20 | 2026-04-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15990 | Deleted - Sec.6 - Sig - Install New Axle Cable - 6,1317m (18 runs) | 2026-04-20 | 2026-04-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5540 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.74.15180 | Deleted - Sec.6 - Sig - Decommission New Level Crossing across Hibernia/BGW st | 2026-11-04 | 2026-11-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.5-294 | Deleted - CoA - E143 - Prepare & Submit to IRPL/ Planning Sec. Unexpected Heritage Finds and Human Remains Procedure ( | 2024-10-29 | 2024-12-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-2482 | Deleted - CoA - E46 - Cleared native vegetation and other landscape features must be reused as part of the CSSI (Delet | 2025-06-23 | 2025-07-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5750 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 3.02 - Stage 1 | 2025-02-24 | 2025-02-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5760 | Deleted - Incorporate IDC & CDR comments - 3.02 - Stage 1 | 2025-03-03 | 2025-03-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5770 | Deleted - Issue Responses & Receive Comment Closeout - 3.02 - Stage 1 | 2025-03-03 | 2025-03-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5780 | Deleted - Submission to IRPL SDR - 3.02 - Stage 1 | 2025-03-10 | 2025-03-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.74.14030 | Deleted - Sec.1 - CSR - Construct Local Cable Route - LCR - Axle counters between 459.885 to 466.126 | 2025-08-22 | 2025-08-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.74.14040 | Deleted - Sec.1 - CSR - Construct Local Cable Route - LCR - Points between 459.885 to 466.126 | 2025-08-24 | 2025-08-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.74.14070 | Deleted - Sec.1 - CSR - Main ULX - ULX near 52B Points (465193) - POSS | 2025-09-13 | 2025-09-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14330 | Deleted - Sec.3 - Cut - Fill 15 - 302ccm - OD Soil | 2026-01-08 | 2026-01-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.ISC.1130 | Deleted - ISC Revise Assessment | 2025-09-12 | 2025-10-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.BI-1240 | Deleted - CoA - E40_NEW - Baseline monitoring of existing fauna movement corridors, pathways and connectivity - SITE ( | 2024-09-30 | 2024-11-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6960 | Deleted - Incorporate IDC & CDR comments- W.05 - Stage 2 | 2025-04-22 | 2025-04-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6970 | Deleted - Issue Responses & Receive Comment Closeout- W.05 - Stage 2 | 2025-04-22 | 2025-04-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6980 | Deleted - Submission to IRPL PDR - W.05 - Stage 2 | 2025-04-30 | 2025-04-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6990 | Deleted - IRPL Review (20 B.days) - W.05 - Stage 2 | 2025-05-01 | 2025-05-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7000 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Geotech Gap Analysis & SI - W.05 - Stage 3 | 2025-05-08 | 2025-06-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.7720 | Deleted - Sec.3 - Cut - Cut 09 - 31,147ccm - XW-MW / MW SS Rip - rock | 2026-02-22 | 2026-03-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.7730 | Deleted - Sec.3 - Cut - Cut 10 - 9,024ccm - XW-MW / SW NB Rip - rock | 2026-03-27 | 2026-04-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.7760 | Deleted - Sec.3 - Cut - Cut 10 - 8,515ccm - SW NB - rock | 2026-04-02 | 2026-04-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14220 | Deleted - Sec.3 - Construct Temporary Creek Crossing - Run Boundary Creek for traffic | 2025-07-18 | 2025-07-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9360 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Road Drainage - 2.10 - Stage 3 | 2025-03-25 | 2025-05-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9440 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Drainage - 2.10 - Stage 4 | 2025-07-14 | 2025-08-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.74.14390 | Deleted - Sec.6 - CSR - Construct Main Cable Route - MCR - ULX at SL5 to SL115 Location (454910 - 454160) - 780m D | 2026-02-28 | 2026-03-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.14320 | Deleted - Sec.6 - Fill - Fill 43 - 615ccm - Strip/Grade RMAR with type D Material (U5 Class)(CRN to Bridge-37720-3 | 2026-09-14 | 2026-09-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15980 | Deleted - Sec.6 - Sig - Install New Comms Cable - 31,006m (6 runs) | 2026-04-12 | 2026-04-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6880 | Deleted - Sec.2 - Fill - Fill 08 - 1,739ccm - Lower | 2025-11-23 | 2025-11-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2020 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-06-25 | 2025-07-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9840 | Deleted - Design Presentation to IRPL - DPK Presentation - D8 - Stage 2 (Modified already part of original Contract Pr
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5500 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Bridges - Dirnaseer Road Underbridge
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18040 | Deleted - Sec.5 - Powder Horn Trib Br - Batter Slopes & Install "Nylex Cordrain" fixed to vertical face of ballast | 2026-09-01 | 2026-09-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.11810 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Roads (Private) - 3.09 - Stage 2 | 2024-12-20 | 2025-03-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.8250 | Deleted - Safety Assurance / SiD - 3.09 - Stage 3 | 2025-05-23 | 2025-05-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2030 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-07-14 | 2025-07-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2040 | Deleted - Configuration Change Acceptance Notice | 2025-07-17 | 2025-07-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.8730 | Deleted - Sec.3 - Fill - Fill 15 - 289ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-06-04 | 2026-06-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10830 | Deleted - Sec.5 - Fill - Fill 37 - 3,971ccm - Upper A | 2026-04-22 | 2026-04-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10850 | Deleted - Sec.5 - Fill - Fill 38 - 6,131ccm - Upper A | 2026-04-24 | 2026-04-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10870 | Deleted - Sec.5 - Fill - Fill 39 - 7,137ccm - Upper A | 2026-04-29 | 2026-05-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10900 | Deleted - Sec.5 - Fill - Fill 40 - 8,119ccm - Upper A | 2026-05-03 | 2026-05-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10910 | Deleted - Sec.5 - Fill - Fill 41 - 3,374ccm - Upper A | 2026-05-08 | 2026-05-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14130 | Deleted - Sec.6 - Fill - Fill 43 - 3,332ccm - Upper A (CRN to Bridge - 37720 - 37950 | 2025-10-09 | 2025-10-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.11530 | Deleted - Sec.6 - Fill - Cut 35 - 752ccm - Upper A (38045 - 39305 | 2026-02-21 | 2026-02-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14110 | Deleted - Sec.6 - Fill - Fill 43 - 3,332ccm - Upper A (across TO - 37400 - 37680 | 2025-10-13 | 2025-10-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10390 | Deleted - Sec.4 - Fill - Cut 22 - 300ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-07-08 | 2026-07-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4210 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-01-31 | 2025-02-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5510 | Deleted - IRPL Review (20 B.days) - 3.07 - Stage 1 | 2025-01-06 | 2025-02-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10380 | Deleted - Sec.4 - Fill - Fill 28 - 326ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-07-07 | 2026-07-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11730 | Deleted - Incorporate IDC & CDR comments - 2.05 - Stage 1 | 2025-01-22 | 2025-01-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.85.1540 | Deleted - Sec.6 - Landscaping - Ch37300-42600 | 2026-09-13 | 2026-09-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.16050 | Deleted - Sec.1 - Sig - Install New Double backdrive Points (3 off) - 51B,52A,52B - 51 pts - 0.200 | 2026-03-14 | 2026-03-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.85.13950 | Deleted - Sec.1 - Landscaping - Ch000-2900 | 2026-06-10 | 2026-06-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.22.13260 | Deleted - Sec.1 - TE02-01 Telstra - Relocate Comms Cable - Install Ducts - Ch1450 - 1460 - Double Up | 2025-07-28 | 2025-07-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.85.1550 | Deleted - Sec.6 - Landscaping - Batter | 2026-09-14 | 2026-09-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20870 | Deleted - Sec.2 - Ulandra Ck Br - apron slab inlet - 33m3 | 2026-04-09 | 2026-04-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2900 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Culverts - Under Rail | 2025-08-04 | 2025-08-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8290 | Deleted - Sec.3 - Fill - Fill 15 - 839ccm - Structural Fill | 2026-04-20 | 2026-04-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8300 | Deleted - Sec.3 - Fill - Cut 12 - 608ccm - Structural Fill | 2026-04-21 | 2026-04-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8310 | Deleted - Sec.3 - Fill - Fill 16 - 702ccm - Structural Fill | 2026-04-22 | 2026-04-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8320 | Deleted - Sec.3 - Fill - Fill 17 - 2,104ccm - Structural Fill | 2026-04-24 | 2026-04-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8330 | Deleted - Sec.3 - Fill - Cut 13 - 1,073ccm - Structural Fill | 2026-04-28 | 2026-04-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5190 | Deleted - Design Deliverables Submission for Workshops and comments - W.02 - Stage 2 | 2025-02-17 | 2025-02-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-592 | Deleted - Optus - Design 80% & Review /Comments | 2024-12-05 | 2025-02-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-602 | Deleted - JH Final Review & Integrate Design -Optus | 2025-04-22 | 2025-05-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5180 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Noise- W.02 - Stage 2 | 2024-12-13 | 2025-02-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4760 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2026-05-14 | 2026-05-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4770 | Deleted - IRPL Reviews & Approves CCR Submission | 2026-05-21 | 2026-06-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4780 | Deleted - IRPL Submits CCB to SM Sub CCB | 2026-06-10 | 2026-06-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1920 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-07-08 | 2025-07-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9580 | Deleted - Submission to IRPL DDR - 2.01 - Stage 3 | 2025-06-04 | 2025-06-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9590 | Deleted - IRPL Review (20 B.days) - 2.01 - Stage 3 | 2025-06-04 | 2025-07-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9630 | Deleted - CDR Package Complete 2.01 - Geotechnical GIR - 2.01 - Stage 4 |  | 2025-07-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9600 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Geotechnical GIR - 2.01 - Stage 4 | 2025-06-05 | 2025-07-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9610 | Deleted - Incorporate IDC & CDR comments - 2.01 - Stage 4 | 2025-07-04 | 2025-07-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9620 | Deleted - IRPL Review (5 B.days) - 2.01 - Stage 4 | 2025-07-04 | 2025-07-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9080 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Geotechnical Design - 2.02 - Stage 1 | 2024-10-28 | 2024-12-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.14600 | Deleted - Sec.4 - Sec.4 - Culvert ID : E7-RD-442700-1 - Install 1200 RCP (5 off) 12m | 2026-01-06 | 2026-01-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.14610 | Deleted - Sec.4 - Sec.4 - Culvert ID : E7-RD-442700-1 - Detailed backfill | 2026-01-07 | 2026-01-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1080 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-06-16 | 2025-06-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15050 | Deleted - Sec.3 - Fill - Cut 09 - 6,364ccm - Fill in Open Drains | 2025-11-29 | 2025-12-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15060 | Deleted - Sec.3 - Fill - Fill 13 - 1,022ccm - Fill in Open Drains | 2025-12-12 | 2025-12-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15070 | Deleted - Sec.3 - Fill - Cut 10 - 457ccm - Fill in Open Drains | 2025-12-14 | 2025-12-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15080 | Deleted - Sec.3 - Fill - Fill 14 - 463ccm - Fill in Open Drains | 2025-12-16 | 2025-12-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15090 | Deleted - Sec.3 - Fill - Cut 11 - 460ccm - Fill in Open Drains | 2025-12-17 | 2025-12-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15100 | Deleted - Sec.3 - Fill - Fill 15 - 748ccm - Fill in Open Drains | 2025-12-18 | 2025-12-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15110 | Deleted - Sec.3 - Fill - Cut 12 - 507ccm - Fill in Open Drains | 2025-12-19 | 2025-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15120 | Deleted - Sec.3 - Fill - Fill 16 - 626ccm - Fill in Open Drains | 2025-12-20 | 2025-12-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.15-534 | Deleted - Proponent seeks input from registered Aboriginal parties on potential management options | 2025-05-14 | 2025-05-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6350 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Corridor
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14420 | Deleted - Sec.4 - Cut - Fill 24 - 82ccm - OD Soil | 2025-11-24 | 2025-11-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.15-204 | Deleted - Fieldwork survey expected to be one week based on previous scope | 2024-11-25 | 2024-11-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7260 | Deleted - Submission to IRPL - W.01 - Stage 2 | 2025-04-07 | 2025-04-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7140 | Deleted - Safety Assurance / SiD - W.01 - Stage 1 | 2024-12-17 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7270 | Deleted - IRPL Review (20 B.days) - W.01 - Stage 2 | 2025-04-08 | 2025-05-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.15-214 | Deleted - Fieldwork test excavation 3-6 weeks depending on findings of survey | 2024-12-02 | 2024-12-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9000 | Deleted - Safety Assurance / SiD - 3.05 - Stage 2 | 2025-03-27 | 2025-04-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.BI-1340 | Deleted - CoA - E44_NEW - Consultation Fauna Connectivity Strategy (To | 2024-12-02 | 2025-01-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-2010 | Deleted - CoA - D8_NEW- IRPL - End of 10 years consult with BCS to determine whether ongoing monitoring (Deleted) | 2027-03-15 | 2027-03-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15930 | Deleted - ACVP - JH Respond to stakeholder comments - Aboriginal Cultural Heritage Assessment Report (To | 2025-03-04 | 2025-03-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15940 | Deleted - ACVP - JH Submission to RAPS for consideration (To | 2025-03-11 | 2025-04-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.10600 | Deleted - PDD Package Complete H8 - Powder Horn Tributary Creek Underbridges
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.C.10C-660 | Deleted - Subcontractor Mob to Site - Kerb and Gutter | 2025-07-28 | 2025-09-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.C.10C-710 | Deleted - Engage Subcontractor - Formwork (Double Up) | 2025-04-23 | 2025-06-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.C.10C-720 | Deleted - Subcontractor Mob to Site - Formwork (Double Up) | 2025-06-20 | 2025-07-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.10660 | Deleted - PDD Package Complete L5 - Landscape
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6590 | Deleted - Sec.1 - Fill - Fill 01 - 1,780ccm Upper A - UNDER TOA/ inbetween trains DELT | 2025-09-12 | 2025-09-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9250 | Deleted - Design Deliverables Submission for Workshops and comments - 2.02 - Stage 3 | 2025-06-02 | 2025-06-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.28510 | Deleted - Sec.5 - Culvert (37212) - Place 20*750RCP Pipe
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.28530 | Deleted - Sec.5 - Culvert (37212) - Place Precast Wingwall
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-2392 | Deleted - CoA - E32 _NEW- IRPL - CSSI must not result in an impact on Threatened Ecological Communities | 2024-10-30 | 2024-11-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5460 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5470 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5480 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5450 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Bridges - Dirnaseer Road Underbridge
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5630 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5640 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5600 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Bridges - Isobel Creek Underbridge
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14530 | Deleted - Sec.5 - Cut - Fill 38 - 787ccm - OD Soil / Soil | 2025-10-07 | 2025-10-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14550 | Deleted - Sec.5 - Cut - Fill 40 - 1246ccm - OD Soil / Soil | 2025-10-26 | 2025-10-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14560 | Deleted - Sec.5 - Cut - Fill 42 - 1212ccm - OD Soil / Soil | 2025-10-28 | 2025-10-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.11490 | Deleted - Sec.6 - Private LX - PR39450 - 57ccm (39024) | 2026-03-01 | 2026-03-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.8010 | Deleted - Sec.3 - Fill - Fill 12 - 205cm - Upper A | 2026-02-22 | 2026-02-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.8030 | Deleted - Sec.3 - Fill - Fill 13 - 5,115ccm - Upper A | 2026-03-27 | 2026-03-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.8040 | Deleted - Sec.3 - Fill - Cut 10 - 1ccm - Upper A | 2026-04-08 | 2026-04-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14180 | Deleted - Sec.5 - Construct Temporary Creek Crossing - Powder Horn Trib Creek for traffic | 2025-07-21 | 2025-07-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6930 | Deleted - Sec.2 - Fill - Fill 09 - 8,823ccm - Mid | 2026-01-26 | 2026-01-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15220 | Deleted - Sec.2 - Fill - Fill 04 - 6,328ccm - Mid | 2025-10-21 | 2025-10-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6950 | Deleted - Sec.2 - Fill - Cut 03 - 1,800ccm - Upper A | 2025-11-02 | 2025-11-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6960 | Deleted - Sec.2 - Fill - Fill 05 - 8,794ccm - Upper A | 2025-11-03 | 2025-11-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6970 | Deleted - Sec.2 - Fill - Fill 06 - 5,108ccm - Upper A | 2025-11-19 | 2025-11-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6990 | Deleted - Sec.2 - Fill - Fill 07 - 2,024ccm - Upper A | 2025-11-22 | 2025-11-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.7010 | Deleted - Sec.2 - Fill - Fill 08 - 5,125ccm - Upper A | 2025-11-26 | 2025-11-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.7020 | Deleted - Sec.2 - Fill - Fill 09 - 15,383ccm - Upper A | 2026-02-01 | 2026-02-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6940 | Deleted - Sec.2 - Fill - Fill 04 - 11,415ccm - Upper A | 2025-10-26 | 2025-11-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8390 | Deleted - Sec.3 - Fill - Fill 20 - 2,658ccm - Structural Fill | 2026-05-08 | 2026-05-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8340 | Deleted - Sec.3 - Fill - Cut 14 - 740ccm - Structural Fill | 2026-04-30 | 2026-04-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8350 | Deleted - Sec.3 - Fill - Fill 18 - 645ccm - Structural Fill | 2026-05-01 | 2026-05-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8380 | Deleted - Sec.3 - Fill - Cut 16 - 941ccm - Structural Fill | 2026-05-04 | 2026-05-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8260 | Deleted - Sec.3 - Fill - Cut 10 - 103ccm - Structural Fill | 2026-04-17 | 2026-04-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8270 | Deleted - Sec.3 - Fill - Fill 14 - 617ccm - Structural Fill | 2026-04-18 | 2026-04-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8280 | Deleted - Sec.3 - Fill - Cut 11 - 525ccm - Structural Fill | 2026-04-19 | 2026-04-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.5-264 | Deleted - Project Verifier /IRPL Review Period - Construction Traffic MP (Duplicate) | 2024-11-19 | 2024-12-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.5-274 | Deleted - Update Plan to Reflect any Comments - Construction Traffic MP (Duplicate) | 2024-12-17 | 2025-01-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.5-284 | Deleted - IRPL to review updated documents and Approve - Construction Traffic MP (Duplicate) | 2025-01-14 | 2025-01-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13340 | Deleted - Design Deliverables Submission for Workshops and comments - Stage 2 - utilities (2-5) - 2.08 - Stage 2 | 2025-02-14 | 2025-02-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.15-624 | Deleted - Advising Heritage NSW two weeks prior of any proposed test excavation (Not Required) | 2024-11-22 | 2024-11-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15160 | Deleted - Sec.3 - Fill - Fill 18 - 4,277ccm - Fill in Open Drains | 2026-01-05 | 2026-01-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15170 | Deleted - Sec.3 - Fill - Cut 15 - 535ccm - Fill in Open Drains | 2026-01-13 | 2026-01-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3620 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-01-30 | 2025-02-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9130 | Deleted - Issue Responses & Receive Comment Closeout - 2.02 - Stage 1 | 2025-01-13 | 2025-01-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9100 | Deleted - Safety Assurance / SiD - 2.02 - Stage 1 | 2024-12-16 | 2024-12-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5820 | Deleted - Safety Assurance / SiD - 3.02 - Stage 2 | 2025-05-08 | 2025-05-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5830 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 3.02 - Stage 2 | 2025-05-15 | 2025-05-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5840 | Deleted - Incorporate IDC & CDR / CCB and Stage 1 comments - 3.02 - Stage 2 | 2025-05-22 | 2025-06-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5850 | Deleted - Issue Responses & Receive Comment Closeout - 3.02 - Stage 2 | 2025-05-29 | 2025-06-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5860 | Deleted - Submission to IRPL PDR - 3.02 - Stage 2 | 2025-06-05 | 2025-06-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5870 | Deleted - IRPL Review (20 B.days) - 3.02 - Stage 2 | 2025-06-06 | 2025-07-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4240 | Deleted - Configuration Change Acceptance Notice | 2025-03-04 | 2025-03-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15510 | Deleted - CWMP - JH Respond and incorporate to DPHI comments (To | 2025-03-05 | 2025-03-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1520 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-06-13 | 2025-07-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1530 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-07-02 | 2025-07-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.5-1324 | Deleted - JH respond to comments, update LX Treatment Report & re-issue to IRPL for comment closeout
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8730 | Deleted - Issue Responses & Receive Comment Closeout - 1.01 - Stage 3 | 2025-05-02 | 2025-05-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8740 | Deleted - Submission to IRPL DDR - 1.01 - Stage 3 | 2025-05-09 | 2025-05-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.S.10IG-36 | Deleted - Prepare Tender Documents - Signalling Power System | 2025-03-17 | 2025-04-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.S.10IG-37 | Deleted - Pricing by Suppliers / Subcontractors - Signalling Power System | 2025-04-14 | 2025-05-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.S.10IG-38 | Deleted - Package Review / Approval - Signalling Power System | 2025-05-15 | 2025-05-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11560 | Deleted - Sec.6 - Fill - BGW E/W - 17,596ccm - UZF/SMZ/Verge | 2026-02-04 | 2026-03-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.11610 | Deleted - Sec.6 - Fill - Cut 35 - 915ccm - Strip/Grade RMAR with type D Material (U5 Class) (38045 - 39305) DELET | 2026-04-26 | 2026-04-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4980 | Deleted - IRPL Submits CCB to SM Sub CCB (To | 2026-06-10 | 2026-06-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5730 | Deleted - Design Deliverables Submission for Workshops and comments - 3.02 - Stage 1 | 2025-02-17 | 2025-02-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5740 | Deleted - Safety Assurance / SiD - 3.02 - Stage 1 | 2025-02-17 | 2025-02-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4990 | Deleted - Configuration Change Acceptance Notice (To | 2026-06-18 | 2026-06-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6850 | Deleted - Design Deliverables Submission for Workshops and comments - W.05 - Stage 1 | 2025-01-16 | 2025-01-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3780 | Deleted - IRPL Review (20 B.days) - 3.10 - Stage 2 | 2025-04-14 | 2025-05-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.8450 | Deleted - TfNSW Review (30 B.days) - 3.10 - Stage 2 - Road Drainage - Sec.1 | 2025-04-14 | 2025-05-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3870 | Deleted - Submission to IRPL DDR - 3.10 - Stage 3 | 2025-06-27 | 2025-06-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3880 | Deleted - IRPL Review (20 B.days) - 3.10 - Stage 3 | 2025-06-30 | 2025-07-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.8440 | Deleted - TfNSW Review (30 B.days) - 3.10 - Stage 3 - Road Drainage - Sec.1 | 2025-06-30 | 2025-08-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10780 | Deleted - Sec.5 - Fill - Fill 35 - 2,162ccm - Upper A | 2025-11-11 | 2025-11-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10790 | Deleted - Sec.5 - Fill - Cut 28 - 5ccm - Upper A | 2025-11-12 | 2025-11-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10800 | Deleted - Sec.5 - Fill - Fill 36 - 16,459ccm - Upper A | 2025-11-18 | 2025-11-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10820 | Deleted - Sec.5 - Fill - Cut 30 - 62ccm - Upper A | 2025-11-29 | 2025-11-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5510 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5490 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6580 | Deleted - Safety Assurance / SiD - D8 - Stage 1 | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.7310 | Deleted - Sec.2 - Fill - Fill 08 - 381ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-02-27 | 2026-02-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.7320 | Deleted - Sec.2 - Fill - Fill 09 - 1033ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-05-16 | 2026-05-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6200 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Corridor
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6070 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.9910 | Deleted - Sec.4 - Fill - Cut 24 - 1,782ccm - Structural Fill | 2026-06-06 | 2026-06-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.9920 | Deleted - Sec.4 - Fill - Fill 31 - 1,291ccm - Structural Fill | 2026-06-09 | 2026-06-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.9930 | Deleted - Sec.4 - Fill - Cut 25 - 1,691ccm - Structural Fill /C5 | 2026-06-11 | 2026-06-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-21 | Deleted - Preconstruction Meeting - Essential Energy - Illabo LGA | 2025-07-03 | 2025-07-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-22 | Deleted - Project Planning for Commencement Approval - Essential Energy - Illabo LGA | 2025-07-17 | 2025-07-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-302 | Deleted - Prepare Tender Docs & Issue RFT ASP Lvl1 - Essential Energy | 2025-04-22 | 2025-05-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-312 | Deleted - Pricing by Suppliers / Subcontractors - Essential Energy | 2025-05-07 | 2025-05-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-322 | Deleted - Package Review / Approval - Essential Energy | 2025-05-27 | 2025-06-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-1682 | Deleted - Groundwater Licence - Prepare - Surface Water and Groundwater (post monitoring program) - CoA - E84 | 2024-12-12 | 2025-01-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12640 | Deleted - Start Package 1.08 - Utility Infrastructure - 1.08 - Stage 1 | 2024-10-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12650 | Deleted - Design Deliverables Submission for Workshops and comments - Stage 2 - utilities (1) - 1.08 - Stage 2 | 2025-02-28 | 2025-03-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12660 | Deleted - Safety Assurance / SiD - 1.08 - Stage 2 | 2025-02-28 | 2025-03-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14770 | Deleted - Sec.4 - Fill - Fill 22 - 1,124ccm - Fill in Open Drains | 2026-01-28 | 2026-01-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9680 | Deleted - Sec.4 - Fill - Fill 32 - 8,299ccm - Upper A | 2026-04-11 | 2026-04-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9700 | Deleted - Sec.4 - Fill - Cut 26 - 2,839ccm - Upper A | 2026-04-16 | 2026-04-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5210 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - W.02 - Stage 2 | 2025-02-24 | 2025-02-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12520 | Deleted - Safety Assurance / SiD - 2.03 - Stage 3 | 2025-05-22 | 2025-05-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12530 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 2.03 - Stage 3 | 2025-05-29 | 2025-06-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10400 | Deleted - Sec.4 - Fill - Fill 29 - 274ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-07-09 | 2026-07-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10410 | Deleted - Sec.4 - Fill - Cut 23 - 300ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-07-10 | 2026-07-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6550 | Deleted - Sec.1 - Fill - Cut 01 - 590ccm Lower - UNDER TOA/ inbetween trains | 2025-09-11 | 2025-09-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6560 | Deleted - Sec.1 - Fill - Fill 01 - 182ccm Mid - UNDER TOA/ inbetween trains | 2025-09-11 | 2025-09-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6570 | Deleted - Sec.1 - Fill - Fill 02 - 2,654ccm Mid - UNDER TOA/ inbetween trains | 2025-09-12 | 2025-09-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6580 | Deleted - Sec.1 - Fill - Cut 01 - 661ccm Mid - UNDER TOA/ inbetween trains | 2025-09-14 | 2025-09-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.85.1560 | Deleted - Sec.6 - Landscaping - Flat area | 2026-09-16 | 2026-09-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5050 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - LXs General
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5420 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5430 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5440 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5350 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Bridges - Run Boundary Creek Underbridg
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5360 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.S.10IG-39 | Deleted - Package Placement - Signalling Power System | 2025-05-29 | 2025-06-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7200 | Deleted - Design Development - Stage 2 - Preliminary Design / PDD - Rail Systems (Power/Signalling) - W.01 - Stage 2 | 2025-01-13 | 2025-03-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10240 | Deleted - Submission to IRPL PDR - 1.06 - Stage 2 | 2025-04-14 | 2025-04-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15580 | Deleted - CTTAMP - Submission to ER for review and endorsement and IRPL Review | 2025-01-22 | 2025-02-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5220 | Deleted - Incorporate IDC & CDR / CCB and Stage 1 comments- W.02 - Stage 2 | 2025-03-03 | 2025-03-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10230 | Deleted - Issue Responses & Receive Comment Closeout - 1.06 - Stage 2 | 2025-04-07 | 2025-04-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10250 | Deleted - IRPL Review (20 B.days) - 1.06 - Stage 2 | 2025-04-15 | 2025-05-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10310 | Deleted - Issue Responses & Receive Comment Closeout - Bridges - 1.06 - Stage 3 | 2025-06-20 | 2025-06-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.11990 | Deleted - IRPL Review (20 B.days)- W.04 - Stage 2 | 2025-03-31 | 2025-04-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04I.11480 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Contaminated Land- W.04 - Stage 2 | 2025-01-16 | 2025-03-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12710 | Deleted - IRPL Review (20 B.days) - 1.08 - Stage 2 | 2025-03-24 | 2025-04-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12720 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Utility Coordination Plans - 1.08 - Stage 2 | 2024-12-19 | 2025-03-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.91.14510 | Deleted - Sec.6 - Hold point for QA Inspection with IRPL - Sec.6 - North - Sleepers | 2026-03-31 | 2026-04-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8180 | Deleted - Sec.3 - Fill - Cut 06 - 2,097ccm - Structural Fill | 2026-03-27 | 2026-03-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8200 | Deleted - Sec.3 - Fill - Cut 07 - 2,778ccm - Structural Fill | 2026-04-04 | 2026-04-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8210 | Deleted - Sec.3 - Fill - Fill 11 - 934ccm - Structural Fill | 2026-04-09 | 2026-04-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8220 | Deleted - Sec.3 - Fill - Cut 08 - 492ccm - Structural Fill | 2026-04-10 | 2026-04-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20760 | Deleted - Sec.3 - Run Boundary Ck Br - Abutment Shear Key/External Diaphragm - south | 2026-03-03 | 2026-03-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20750 | Deleted - Sec.3 - Run Boundary Ck Br - Abutment Shear Key/External Diaphragm - North | 2026-02-24 | 2026-03-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6600 | Deleted - Sec.1 - Fill - Fill 02 - 6,322ccm Upper A - UNDER TOA/ inbetween trains | 2025-09-14 | 2025-09-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6610 | Deleted - Sec.1 - Fill - Fill 03 - 3,208ccm Upper A DELTEE | 2025-09-19 | 2025-09-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6620 | Deleted - Sec.1 - Fill - Cut 01 - 248ccm - Upper A | 2025-09-24 | 2025-09-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14580 | Deleted - Sec.1 - Fill - Fill 03 - 2720ccm E2 Replace unsuitable - UNDER TOA/ inbetween trains | 2025-07-29 | 2025-08-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15610 | Deleted - Sec.6 - Sig - existing EOL Points (3 off) - SL113EOL, SL114EOL, SL115EOL - SL113 - 454.160 | 2026-05-21 | 2026-05-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.16100 | Deleted - Sec.6 - Sig - Install New Tangential - T 250 rad Pts Backdrive (2 off) - 51A,52A - | 2026-05-16 | 2026-05-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.22.5510 | Deleted - Sec.6 - PUP - IRPL - Rail Power - 37440-37490 - X-ing track at a skew | 2025-07-22 | 2025-07-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.22.5660 | Deleted - Sec.6 - PUP - IRPL - Rail Power - 37580 -37590 - X-ing track at a skew | 2025-07-22 | 2025-07-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15850 | Deleted - Sec.3 - SIG - Install New Axle Cable - 6,596m (31 runs | 2026-04-07 | 2026-04-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12070 | Deleted - IRPL Review (20 B.days) - W.04 - Stage 3 | 2025-05-30 | 2025-06-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12040 | Deleted - Incorporate IDC & CDR comments - W.04 - Stage 3 | 2025-05-22 | 2025-05-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3580 | Deleted - IRPL Submits CCB to SM Sub CCB - 3.02 - Stage 1 | 2025-04-08 | 2025-04-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3590 | Deleted - Configuration Change Acceptance Notice | 2025-04-17 | 2025-04-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8860 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Culverts - Under Rail - 3.05 - Stage 1 | 2024-10-03 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8870 | Deleted - Design Deliverables Submission for Workshops and comments - 3.05 - Stage 1 | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.C.10C-230 | Deleted - Subcontractor Mob to Site - Anti Graffiti | 2025-06-20 | 2025-07-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10790 | Deleted - Submission to IRPL SDR - 1.04 - Stage 1 | 2025-02-21 | 2025-02-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10800 | Deleted - IRPL Review (20 B.days) - 1.04 - Stage 1 | 2025-02-24 | 2025-03-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.C.10C-220 | Deleted - Engage Subcontractor - Anti Graffiti | 2025-04-23 | 2025-06-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14190 | Deleted - Sec.5 - Construct Temporary Creek Crossing - Powder Horn Creek for traffic | 2025-07-23 | 2025-07-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10630 | Deleted - Sec.5 - Fill - PR32150 - 43ccm | 2026-04-01 | 2026-04-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10690 | Deleted - Sec.5 - Fill - Fill 40 - 1,757cm - Lower | 2025-11-12 | 2025-11-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10700 | Deleted - Sec.5 - Fill - Fill 41 - 4,926ccm - Lower | 2025-11-13 | 2025-11-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.18460 | Deleted - Float before Track can commence - Sec.2 - converted LOE | 2026-05-16 | 2026-05-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.8680 | Deleted - Sec.3 - Fill - Cut 09 - 592ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-05-28 | 2026-05-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.8690 | Deleted - Sec.3 - Fill - Fill 13 - 326ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-05-31 | 2026-05-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.8700 | Deleted - Sec.3 - Fill - Cut 10 - 174ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-06-01 | 2026-06-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6110 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6120 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15790 | Deleted - CUDLP - DPHI Completion of Review/approval (2 weeks/ 14 cd) | 2025-03-19 | 2025-04-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-98 | Deleted - APA Group 80% & Review/Comments | 2024-11-07 | 2025-01-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2930 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-07-31 | 2025-07-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3910 | Deleted - Incorporate IDC & CDR comments - 3.10 - Stage 4 | 2025-08-12 | 2025-08-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5110 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5120 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5130 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.9940 | Deleted - Sec.4 - Fill - Fill 32 - 1,655ccm - Structural Fill | 2026-06-13 | 2026-06-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10450 | Deleted - Incorporate IDC & CDR comments - 1.05 - Stage 1 | 2025-01-22 | 2025-01-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13350 | Deleted - Safety Assurance / SiD - 2.08 - Stage 2 | 2025-02-14 | 2025-02-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13360 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 2.08 - Stage 2 | 2025-02-21 | 2025-02-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13370 | Deleted - Incorporate IDC & CDR comments - 2.08 - Stage 2 | 2025-02-28 | 2025-03-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13380 | Deleted - Issue Responses & Receive Comment Closeout - 2.08 - Stage 2 | 2025-02-28 | 2025-03-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.11850 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - W.04 - Stage 1 | 2024-12-05 | 2024-12-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.11870 | Deleted - Issue Responses & Receive Comment Closeout - W.04 - Stage 1 | 2024-12-12 | 2024-12-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.11880 | Deleted - Submission to IRPL SDR - W.04 - Stage 1 | 2024-12-19 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.11890 | Deleted - IRPL Review (20 B.days) - W.04 - Stage 1 | 2024-12-20 | 2025-01-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.11900 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Contaminated Land - W.04 - Stage 1 | 2024-10-17 | 2024-12-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.11920 | Deleted - Start Package W.04 - Contaminated Land - W.04 - Stage 1 | 2024-10-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.8250 | Deleted - Sec.3 - Fill - Fill 13 - 1,026ccm - Structural Fill | 2026-04-15 | 2026-04-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.11930 | Deleted - Design Deliverables Submission for Workshops and comments - W.04 - Stage 2 | 2025-03-07 | 2025-03-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-1132 | Deleted - Package Placement - Goldenfields Water | 2025-05-19 | 2025-06-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-1142 | Deleted - Nominate Subcontractor to Riverina Water - Submit Contractor Deed Polls & ITPs - Riverina Water | 2025-06-10 | 2025-06-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2390 | Deleted - Configuration Change Acceptance Notice | 2025-08-21 | 2025-08-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4160 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-02-24 | 2025-02-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4170 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-03-05 | 2025-03-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10890 | Deleted - IRPL Review (20 B.days) - 1.04 - Stage 2 | 2025-05-08 | 2025-06-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.16380 | Deleted - CBSMP - Respond to stakeholder comments - BioSecurity Management Plan - CoA C17 (To | 2025-01-14 | 2025-01-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8750 | Deleted - IRPL Review (20 B.days) - 1.01 - Stage 3 | 2025-05-09 | 2025-06-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8770 | Deleted - Incorporate IDC & CDR comments - 1.01 - Stage 4 | 2025-06-10 | 2025-06-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8780 | Deleted - IRPL Review (5 B.days) - 1.01 - Stage 4 | 2025-06-17 | 2025-06-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8790 | Deleted - CDR Package Complete 1.01 - Geotechnical GIR - 1.01 - Stage 4 |  | 2025-06-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3610 | Deleted - Safety Assurance / SiD - 3.10 - Stage 1 | 2024-12-13 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10210 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.06 - Stage 2 | 2025-03-24 | 2025-03-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9090 | Deleted - Design Deliverables Submission for Workshops and comments - 2.02 - Stage 1 | 2024-12-16 | 2024-12-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9810 | Deleted - Design Deliverables Submission for Workshops and comments - 3.03 - Stage 2 | 2025-03-10 | 2025-03-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6430 | Deleted - IRPL Review (20 B.days) - D9 - Stage 2 | 2025-04-30 | 2025-05-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9870 | Deleted - IRPL Review (20 B.days) - 3.03 - Stage 2 | 2025-04-08 | 2025-05-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9800 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Earthworks Formation Design Documentation - 3.03 | 2025-01-17 | 2025-03-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9970 | Deleted - Submission to IRPL DDR - 3.03 - Stage 3 | 2025-06-20 | 2025-06-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4650 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Culverts - Under Rail | 2025-03-03 | 2025-03-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9600 | Deleted - Sec.4 - Fill - Fill 28 - 4,484ccm - Upper A | 2026-04-02 | 2026-04-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9070 | Deleted - Submission to IRPL DDR - 1.10 - Stage 3 | 2025-06-27 | 2025-06-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4110 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-01-13 | 2025-01-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4120 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-01-22 | 2025-02-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5920 | Deleted - Incorporate IDC & CDR comments - 3.02 - Stage 3 | 2025-07-25 | 2025-07-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10740 | Deleted - Design Deliverables Submission for Workshops and comments - 1.04 - Stage 1 | 2025-01-31 | 2025-02-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3750 | Deleted - Issue Responses & Receive Comment Closeout - 3.10 - Stage 2 | 2025-04-07 | 2025-04-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3770 | Deleted - Submission to IRPL PDR - 3.10 - Stage 2 | 2025-04-14 | 2025-04-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10180 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Bridges - 1.06 - Stage 2 | 2024-12-20 | 2025-03-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10190 | Deleted - Design Deliverables Submission for Workshops and comments - Stage 2 - bridges (1) - 1.06 - Stage 2 | 2025-03-17 | 2025-03-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10200 | Deleted - Safety Assurance / SiD - 1.06 - Stage 2 | 2025-03-17 | 2025-03-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-2040 | Deleted - CoA - D7_NEW - IRPL - 10 years of monitoring - Handed over to Operations (Deleted) | 2026-09-16 | 2027-02-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.16170 | Deleted - ACVP - Initial submiission to IRPL for review (4 weeks/ 28 cd) (To | 2025-01-13 | 2025-02-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.16470 | Deleted - ACVP - Submit of Draft of CVA methodology to IRPL (To
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12470 | Deleted - Issue Responses & Receive Comment Closeout - 2.03 - Stage 2 | 2025-03-24 | 2025-03-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10880 | Deleted - Submission to IRPL PDR - 1.04 - Stage 2 | 2025-05-07 | 2025-05-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1800 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Earthworks Formation Design Documentatio | 2025-08-04 | 2025-08-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1810 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-06-23 | 2025-06-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1820 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-07-02 | 2025-07-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1830 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-07-21 | 2025-07-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.24010 | Deleted - Sec.3 - Culvert (15961) - Construct Scour Protection | 2026-04-22 | 2026-04-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.23970 | Deleted - Sec.3 - Culvert (15961) - Backfill Pipe | 2026-04-17 | 2026-04-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.23990 | Deleted - Sec.3 - Culvert (15961) - Place Precast Wingwall | 2026-04-18 | 2026-04-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13480 | Deleted - Submission to IRPL DDR - 2.08 - Stage 3 | 2025-05-12 | 2025-05-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13490 | Deleted - IRPL Review (20 B.days) - 2.08 - Stage 3 | 2025-05-13 | 2025-06-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.1070 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-05-27 | 2025-06-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10610 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.05 - Stage 3 | 2025-06-18 | 2025-06-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.20020 | Deleted - IRPL provides Type Approval (require by) |  | 2025-07-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.19730 | Deleted - IRPL directs which Option for Illabo XO is to proceed (IRPL response through IR2200-RTRFI-000141) | 2024-09-30 | 2024-10-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.19740 | Deleted - Detailed Track Design (w.08 pkg) ready - for XO Placement |  | 2025-03-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.19750 | Deleted - IRPL provides Type Approval (require by) |  | 2025-07-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.19760 | Deleted - Design CDR for Track, Signalling and Rail Systems |  | 2025-08-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.19770 | Deleted - Award/ Placement of XO with Manufacturuers |  | 2025-03-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.19780 | Deleted - Lead Time (22 (20-24) Weeks) | 2025-07-02 | 2025-12-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.19790 | Deleted - Delivery to site | 2026-01-06 | 2026-01-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11070 | Deleted - Safety Assurance / SiD - 1.03 - Stage 1 | 2024-11-15 | 2024-11-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11080 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.03 - Stage 1 | 2024-11-22 | 2024-11-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11090 | Deleted - Incorporate IDC & CDR comments - 1.03 - Stage 1 | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11100 | Deleted - Issue Responses & Receive Comment Closeout - 1.03 - Stage 1 | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11110 | Deleted - Submission to IRPL SDR - 1.03 - Stage 1 | 2024-12-06 | 2024-12-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11120 | Deleted - IRPL Review (20 B.days) - 1.03 - Stage 1 | 2024-12-09 | 2025-01-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11130 | Deleted - Start Package 1.03 - Earthworks Formation Design Documentation - 1.03 - Stage 1 | 2024-10-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.G.101160 | Deleted - Engage General Electircal (Essential Energy) Subcontractor | 2025-04-28 | 2025-06-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8530 | Deleted - Design Deliverables Submission for Workshops and comments - 1.01 - Stage 1 | 2024-11-15 | 2024-11-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3330 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-01-28 | 2025-01-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3340 | Deleted - Configuration Change Acceptance Notice | 2025-02-04 | 2025-02-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6000 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Earthworks - Model - Volumes - W.09 - Stage 1 | 2024-10-03 | 2024-11-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6010 | Deleted - Design Deliverables Submission for Workshops and comments - W.09 - Stage 1 | 2024-11-22 | 2024-11-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.7260 | Deleted - Sec.2 - Fill - Fill 05 - 607ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-02-17 | 2026-02-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.7270 | Deleted - Sec.2 - Fill - Fill 06 - 422ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-02-20 | 2026-02-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15640 | Deleted - Sec.1 - Sig - Install New Isolation TX (1 off) (466126) | 2026-02-01 | 2026-02-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.11290 | Deleted - Sec.5 - Fill - Cut 29 - 170ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-08-11 | 2026-08-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14700 | Deleted - Sec.5 - Fill - Fill 39 - 3,068ccm - Fill in Open Drains | 2026-04-19 | 2026-04-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14710 | Deleted - Sec.5 - Fill - Cut 33 - 6,958ccm - Fill in Open Drains | 2026-04-24 | 2026-05-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9320 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Geotechnical Design - 2.02 - Stage 4 | 2025-07-01 | 2025-08-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9330 | Deleted - Incorporate IDC & CDR / CCB and Stage 3 comments - 2.02 - Stage 4 | 2025-08-05 | 2025-08-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9340 | Deleted - IRPL Review (5 B.days) - 2.02 - Stage 4 | 2025-08-19 | 2025-08-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9350 | Deleted - CDR Package Complete 2.02 - Geotechnical Design - 2.02 - Stage 4 |  | 2025-08-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2290 | Deleted - Configuration Change Acceptance Notice | 2025-08-05 | 2025-08-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2250 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Geotechnical Design | 2025-08-04 | 2025-08-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.10230 | Deleted - CTTAMP - Consultation with A2I (To | 2025-03-12 | 2025-03-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.10240 | Deleted - CTTAMP - Consultation with LGAs (To | 2025-03-26 | 2025-04-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10950 | Deleted - Issue Responses & Receive Comment Closeout - 1.04 - Stage 3 | 2025-07-18 | 2025-07-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.6820 | Deleted - Sec.2 - Cut - Fill 09 - 13,084ccm - OD Soil /Soil | 2025-11-07 | 2025-12-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18580 | Deleted - Sec.4 - Isobel Ck Trib Br - Pier Pad Footing 1 Foundation - 50m3 | 2026-03-07 | 2026-03-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.EW.1090123 | Deleted - Subcontractor Mob to Site - Arbonist (delete merged with Pkg 48) | 2025-05-19 | 2025-05-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.10980 | Deleted - DDD Package Complete H8 - Powder Horn Tributary Creek Underbridges
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.27490 | Deleted - Sec.4 - Culvert (18502) - Excavation 1000m2 1m deep - Basin Upstream | 2026-04-27 | 2026-04-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18590 | Deleted - Sec.4 - Isobel Ck Trib Br - Detailed Earthworks Pier Pad Footing 2 | 2026-03-07 | 2026-03-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18610 | Deleted - Sec.4 - Isobel Ck Trib Br - Pier Pad Footing 2 Foundation (inc pier blades) - 50m3 | 2026-03-19 | 2026-03-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19720 | Deleted - Sec.1 - Billabong Ck Br - Demobilise/Mob piling rig | 2026-01-05 | 2026-01-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.14690 | Deleted - Sec.1 - Billabong Ck Br - Place pile concrete | 2026-01-13 | 2026-01-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-292 | Deleted - Telstra - Work Can Commence - Cootamundra LGA |  | 2025-07-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-130 | Deleted - Telstra Quote & Send Contract | 2025-04-04 | 2025-06-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-131 | Deleted - JH Contract Approval - Telstra - Bethungra | 2025-06-19 | 2025-07-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-132 | Deleted - Telstra - Work Can Commence - Bethungra LGA |  | 2025-07-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-242 | Deleted - Telstra Quote & Send Contract | 2025-04-04 | 2025-06-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-252 | Deleted - JH Contract Approval - Telstra - Stockingbingal | 2025-06-19 | 2025-07-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-262 | Deleted - Telstra - Work Can Commence - Stockinbingal LGA |  | 2025-07-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-582 | Deleted - JH Horizontal & Vertical Alignment Design for Optus | 2024-11-14 | 2024-12-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2980 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-03-05 | 2025-03-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-1732 | Deleted - Groundwater Licence - Approval - |  | 2025-07-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10460 | Deleted - Issue Responses & Receive Comment Closeout - 1.05 - Stage 1 | 2025-01-22 | 2025-01-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10470 | Deleted - Submission to IRPL SDR - 1.05 - Stage 1 | 2025-01-30 | 2025-01-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12770 | Deleted - Incorporate IDC & CDR comments - 1.08 - Stage 3 | 2025-05-19 | 2025-05-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12780 | Deleted - Issue Responses & Receive Comment Closeout - 1.08 - Stage 3 | 2025-05-19 | 2025-05-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12790 | Deleted - Submission to IRPL DDR - 1.08 - Stage 3 - Utility Infrastructure - | 2025-05-26 | 2025-05-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12810 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Utility Coordination Plans - 1.08 - Stage 3 | 2025-03-26 | 2025-05-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12820 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Utilities Design - 1.08 - Stage 3 | 2025-03-26 | 2025-05-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.11860 | Deleted - Incorporate IDC & CDR comments - W.04 - Stage 1 | 2024-12-12 | 2024-12-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.11830 | Deleted - Design Deliverables Submission for Workshops and comments - W.04 - Stage 1 | 2024-11-28 | 2024-12-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.11840 | Deleted - Safety Assurance / SiD - W.04 - Stage 1 | 2024-11-28 | 2024-12-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20650 | Deleted - Sec.3 - Dirnaseer Rd Br - apron slab inlet - 16m3 | 2026-05-05 | 2026-05-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20660 | Deleted - Sec.3 - Dirnaseer Rd Br - apron slab outlet - 16m3 | 2026-05-10 | 2026-05-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3480 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-03-25 | 2025-03-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3450 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Stock Underpasses | 2025-04-07 | 2025-04-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3460 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-02-25 | 2025-03-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3470 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-03-06 | 2025-03-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3490 | Deleted - Configuration Change Acceptance Notice | 2025-04-08 | 2025-04-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9880 | Deleted - Internal IDR Review (By JHG) - D9 - Stage 2 (Modified)
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.91.14550 | Deleted - Sec.2 - Hold point for QA Inspection with IRPL- Sec.2 - Rail | 2026-06-02 | 2026-06-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15700 | Deleted - CGMMP - DPHI Completion of Review/Approval (2 weeks/ 14 cd) (1 month after SIMP approval) (To | 2025-03-19 | 2025-04-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.16310 | Deleted - CGMMP - IRPL to review updated documents and Approve (2 weeks/ 14 cd) (To | 2025-03-19 | 2025-04-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-2510 | Deleted - CoA - E15 - OLDsubmission to EPA and Planning Secretary - Operational Noise and Vibration Review (ONVR) - Ra | 2026-08-11 | 2026-09-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8980 | Deleted - Safety Assurance / SiD - L1 - Stage 3 | 2025-06-24 | 2025-06-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.8680 | Deleted - Safety Assurance / SiD - E1 - Stage 3 | 2025-05-16 | 2025-05-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12300 | Deleted - TfNSW Review (30 B.days) - E3- Stage 4 - Level Crossings - GF | 2025-09-16 | 2025-10-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6460 | Deleted - Safety Assurance / SiD - W.07 - Stage 3 | 2025-06-12 | 2025-06-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7580 | Deleted - Safety Assurance / SiD - D7 - Stage 3 | 2025-05-16 | 2025-05-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11560 | Deleted - Safety Assurance / SiD - H1 - Stage 3 | 2025-05-22 | 2025-05-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12270 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Roads (Private) - 1.09 - Stage 1 | 2024-10-03 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5590 | Deleted - IRPL Review (20 B.days) - 3.07 - Stage 2 | 2025-04-08 | 2025-05-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.8050 | Deleted - Sec.3 - Fill - Fill 14 - 2,170ccm - Upper A | 2026-04-09 | 2026-04-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5600 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Roads - BGW - 3.07 - Stage 3 | 2025-04-15 | 2025-05-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5660 | Deleted - Submission to IRPL DDR - 3.07 - Stage 3 | 2025-06-16 | 2025-06-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5670 | Deleted - IRPL Review (20 B.days) - 3.07 - Stage 3 | 2025-06-16 | 2025-07-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12660 | Deleted - TfNSW/ IV Review (30 B.days) - 3.07 - Stage 3 - BGW Road | 2025-06-17 | 2025-07-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5610 | Deleted - Design Deliverables Submission for Workshops and comments - 3.07 - Stage 3 | 2025-05-26 | 2025-05-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5620 | Deleted - Safety Assurance / SiD - 3.07 - Stage 3 | 2025-05-26 | 2025-05-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5630 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 3.07 - Stage 3 | 2025-05-30 | 2025-06-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10750 | Deleted - Safety Assurance / SiD - 1.04 - Stage 1 | 2025-01-31 | 2025-02-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10760 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.04 - Stage 1 | 2025-02-07 | 2025-02-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10770 | Deleted - Incorporate IDC & CDR comments - 1.04 - Stage 1 | 2025-02-14 | 2025-02-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3440 | Deleted - Configuration Change Acceptance Notice | 2025-04-08 | 2025-04-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3410 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-03-03 | 2025-03-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15800 | Deleted - CUDLP approved |  | 2025-04-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10320 | Deleted - Submission to IRPL DDR - 1.06 - Stage 3 | 2025-06-27 | 2025-06-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10330 | Deleted - IRPL Review (20 B.days) - 1.06 - Stage 3 | 2025-06-30 | 2025-07-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10260 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Bridges - 1.06 - Stage 3 | 2025-04-14 | 2025-06-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10270 | Deleted - Design Deliverables Submission for Workshops and comments - 1.06 - Stage 3 | 2025-06-05 | 2025-06-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10500 | Deleted - Sec.4 - Fill - Cut 27 - 300ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-07-29 | 2026-07-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10510 | Deleted - Sec.4 - Fill - Fill 34 - 518ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-08-01 | 2026-08-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10260 | Deleted - Sec.4 - Fill - Fill 21 - 167ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-06-22 | 2026-06-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10270 | Deleted - Sec.4 - Fill - Cut 17 - 300ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-06-23 | 2026-06-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10280 | Deleted - Sec.4 - Fill - Fill 22 - 333ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-06-24 | 2026-06-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10290 | Deleted - Sec.4 - Fill - Cut 18 - 300ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-06-26 | 2026-06-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10300 | Deleted - Sec.4 - Fill - Fill 23 - 280ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-06-27 | 2026-06-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.EW.1090113 | Deleted - Engage Subcontractor - Arbonist (delete merged with Pkg 48) | 2025-03-19 | 2025-05-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7100 | Deleted - Issue Responses & Receive Comment Closeout - W.05 - Stage 4 | 2025-07-28 | 2025-08-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13500 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Utility Coordination Plans - 2.08 - Stage 3 | 2025-03-12 | 2025-04-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.EW.10909220 | Deleted - Subcontractor Mob to Site - Hotels | 2024-12-20 | 2025-01-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.EW.10909230 | Deleted - Engage Subcontractor - Acoustic Specialist (To be | 2025-07-11 | 2025-09-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.EW.10909240 | Deleted - Subcontractor Mob to Site -Security | 2025-09-08 | 2025-09-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9650 | Deleted - TfNSW Review (30 B.days) - E2 - Stage 4 - Level Crossings (Public - Junee Shire Council) - | 2025-09-11 | 2025-10-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12960 | Deleted - Design Development - Roads (Private) - 2.09 - Stage 1 | 2024-10-03 | 2024-11-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13060 | Deleted - Design Development - Stage 2 - Preliminary Design / PDD - Roads (Private) - 2.09 - Stage 2 | 2024-12-06 | 2025-02-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13230 | Deleted - TfNSW Review (30 B.days) - M2 - Stage 2 - Roads - Sec.2 to 5 | 2025-02-25 | 2025-04-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13150 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Roads (Private) - 2.09 - Stage 3 | 2025-03-11 | 2025-04-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.G.101280 | Deleted - Engage HDD Subcontractor | 2025-03-07 | 2025-05-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11330 | Deleted - CDR Package Complete 1.03 - Earthworks Formation Design Documentation - Zone 1 /Sec.1 - 1.03 - Stage |  | 2025-07-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10030 | Deleted - Incorporate IDC & CDR / CCB and Stage 3 comments - 3.03 - Stage 4 | 2025-08-06 | 2025-08-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8450 | Deleted - Issue Responses & Receive Comment Closeout - 1.02 - Stage 3 | 2025-07-11 | 2025-07-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8460 | Deleted - Submission to IRPL DDR - 1.02 - Stage 3 | 2025-07-18 | 2025-07-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8470 | Deleted - IRPL Review (20 B.days) - 1.02 - Stage 3 | 2025-07-18 | 2025-08-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12670 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.08 - Stage 2 | 2025-03-07 | 2025-03-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-103 | Deleted - Package Review / Approval / Package placement | 2025-06-04 | 2025-07-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-1042 | Deleted - Pricing by Suppliers / Subcontractors - Essential Energy - Stockinbingal LGA | 2025-05-07 | 2025-05-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9120 | Deleted - CDR Package Complete 1.10 - Drainage - 1.10 - Stage 4 |  | 2025-10-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9130 | Deleted - TfNSW Review (30 B.days) - 1.10 - Stage 4 - Road Drainage - Sec.1 | 2025-09-02 | 2025-10-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8520 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Geotechnical GIR - 1.01 - Stage 1 | 2024-10-03 | 2024-11-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8540 | Deleted - Safety Assurance / SiD - 1.01 - Stage 1 | 2024-11-15 | 2024-11-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8550 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.01 - Stage 1 | 2024-11-22 | 2024-11-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8560 | Deleted - Incorporate IDC & CDR comments - 1.01 - Stage 1 | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8570 | Deleted - Issue Responses & Receive Comment Closeout - 1.01 - Stage 1 | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8580 | Deleted - Submission to IRPL SDR - 1.01 - Stage 1 | 2024-12-06 | 2024-12-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6070 | Deleted - IRPL Review (20 B.days) - W.09 - Stage 1 | 2024-12-16 | 2025-01-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12210 | Deleted - Start Package W.09 - Earthworks - Model - Volumes - W.09 - Stage 1 | 2024-10-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.5-1004 | Deleted - CoA - E133 - Project Verifier /IRPL Review Period - Aboriginal Cultural Values PLan | 2024-10-15 | 2024-11-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9560 | Deleted - Incorporate IDC & CDR comments - 2.01 - Stage 3 | 2025-05-28 | 2025-06-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9570 | Deleted - Issue Responses & Receive Comment Closeout - 2.01 - Stage 3 | 2025-05-28 | 2025-06-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12690 | Deleted - Issue Responses & Receive Comment Closeout - 1.08 - Stage 2 | 2025-03-14 | 2025-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-104 | Deleted - APA Group - Work Can Commence - Stockinbingal LGA |  | 2025-07-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-542 | Deleted - Nominate Subcontractor to APA Group | 2025-07-03 | 2025-07-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5060 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5070 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5080 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5980 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9210 | Deleted - Incorporate IDC & CDR comments - 2.10 - Stage 1 | 2024-12-13 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9220 | Deleted - Issue Responses & Receive Comment Closeout - 2.10 - Stage 1 | 2024-12-13 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9230 | Deleted - Submission to IRPL SDR - 2.10 - Stage 1 | 2024-12-20 | 2024-12-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9240 | Deleted - IRPL Review (20 B.days) - 2.10 - Stage 1 | 2024-12-20 | 2025-02-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9250 | Deleted - Start Package 2.10 - Drainage - 2.10 - Stage 1 | 2024-10-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9270 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Road Drainage - 2.10 - Stage 2 | 2024-12-20 | 2025-02-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9280 | Deleted - Design Deliverables Submission for Workshops and comments - Stage 2 - drainage (2-5) - 2.10 - Stage 2 | 2025-02-17 | 2025-02-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9290 | Deleted - Safety Assurance / SiD - 2.10 - Stage 2 | 2025-02-17 | 2025-02-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-1152 | Deleted - Goldenfields Water - Work Can Commence - Bethungra LGA |  | 2025-06-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-99 | Deleted - JH Design & Review/Comment | 2025-01-31 | 2025-02-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10W-7 | Deleted - Pricing by Suppliers / Subcontractors - Ballast Matting | 2025-01-16 | 2025-02-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10W-8 | Deleted - Package Review / Approval - Ballast Matting | 2025-02-14 | 2025-02-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10W-11 | Deleted - Prepare Tender Documents - Capping & Structural Fill | 2024-12-05 | 2025-01-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10W-12 | Deleted - Pricing by Suppliers / Subcontractors - Capping & Structural Fill | 2025-01-16 | 2025-02-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10080 | Deleted - Sec.4 - Fill - Fill 26 - 272ccm - Capping (Rail | 2026-06-07 | 2026-06-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10090 | Deleted - Sec.4 - Fill - Cut 20 - 874ccm - Capping (Rail | 2026-06-08 | 2026-06-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10100 | Deleted - Sec.4 - Fill - Fill 27 - 278ccm - Capping (Rail | 2026-06-09 | 2026-06-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10130 | Deleted - Sec.4 - Fill - Cut 22 - 800ccm - Capping (Rail | 2026-06-12 | 2026-06-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.12840 | Deleted - Sec.6 - Fill - CRN East - 1500ccm | 2025-10-11 | 2025-10-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.11500 | Deleted - Sec.6 - Fill - Fill 43 - 100ccm - Lower (across old BGW - 37240 - 37400 | 2026-11-07 | 2026-11-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14060 | Deleted - Sec.6 - Fill - Fill 43 - 30ccm - Place new material, compact and proof roll- Lower (across CRN track - 3 | 2026-09-12 | 2026-09-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14070 | Deleted - Sec.6 - Fill - Fill 43 - 1200ccm - Lower (CRN to Bridge - 37720 - 37950 | 2025-10-06 | 2025-10-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.11510 | Deleted - Sec.6 - Fill - Fill 43 - 159ccm - Mid (across old BGW - 37240 - 37400 | 2026-11-08 | 2026-11-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14080 | Deleted - Sec.6 - Fill - Fill 43 - 650ccm - Mid (across TO - 37400 - 37680 | 2025-10-12 | 2025-10-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.16080 | Deleted - Sec.3 - Dirnaseer Rd Br - Precast Abutment Panels - South Abutment | 2026-03-03 | 2026-03-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9220 | Deleted - Sec.4 - Fill - Fill 25 - 323ccm - Lower | 2026-03-23 | 2026-03-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16750 | Deleted - Sec.3 - Public LX - PU15950 - Drainage - Detailed backfill | 2026-01-27 | 2026-01-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.15-344 | Deleted - Proponent records or documents that information on the proposed project has been presented | 2024-11-27 | 2024-12-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9980 | Deleted - IRPL Review (20 B.days) - 3.03 - Stage 3 | 2025-06-23 | 2025-07-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12050 | Deleted - Issue Responses & Receive Comment Closeout - W.04 - Stage 3 | 2025-05-22 | 2025-05-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.14290 | Deleted - Sec.6 - Fill - CRN West - 600ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-04-19 | 2026-04-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16730 | Deleted - Sec.3 - Public LX - PU15950 - Drainage - LX Culvert - Trench Excavation/ Culvert site prep | 2026-01-24 | 2026-01-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16700 | Deleted - Sec.3 - Public LX - PU15950 - Drainage - LX Culvert - Trench Excavation/ Culvert site prep | 2026-01-23 | 2026-01-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6130 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.8840 | Deleted - Safety Assurance / SiD - 1.10 - Stage 1 | 2024-12-06 | 2024-12-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.8820 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Road Drainage - 1.10 - Stage 1 | 2024-10-18 | 2024-12-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.8830 | Deleted - Design Deliverables Submission for Workshops and comments - 1.10 - Stage 1 | 2024-12-06 | 2024-12-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.11820 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Roads (Private) - 3.09 - Stage 3 | 2025-04-15 | 2025-05-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-1280 | Deleted - CoA - C4- Ancillary Management Plan - AFMP approval period (1 month before installation of any ancillary f | 2025-04-28 | 2025-05-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.5-1104 | Deleted - CoA - E162 - IRPL/ Planning Sec Review Period - Unexpected Finds for Contamination Procedure (Delete Part of | 2024-12-10 | 2025-01-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9930 | Deleted - Safety Assurance / SiD - 3.03 - Stage 3 | 2025-05-29 | 2025-06-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9940 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 3.03 - Stage 3 | 2025-06-05 | 2025-06-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9950 | Deleted - Incorporate IDC & CDR comments - 3.03 - Stage 3 | 2025-06-13 | 2025-06-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9960 | Deleted - Issue Responses & Receive Comment Closeout - 3.03 - Stage 3 | 2025-06-13 | 2025-06-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3600 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Earthworks Formation Design Documentatio | 2025-02-19 | 2025-02-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3610 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-01-20 | 2025-01-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12670 | Deleted - TfNSW/ IV Review (30 B.days) - 3.07 - Stage 2 - BGW Road | 2025-04-08 | 2025-05-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5650 | Deleted - Issue Responses & Receive Comment Closeout - 3.07 - Stage 3 | 2025-06-06 | 2025-06-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6890 | Deleted - Issue Responses & Receive Comment Closeout - W.05 - Stage 1 | 2025-01-31 | 2025-02-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6860 | Deleted - Safety Assurance / SiD - W.05 - Stage 1 | 2025-01-16 | 2025-01-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6870 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - W.05 - Stage 1 | 2025-01-23 | 2025-01-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6880 | Deleted - Incorporate IDC & CDR comments - W.05 - Stage 1 | 2025-01-31 | 2025-02-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6900 | Deleted - Submission to IRPL SDR - W.05 - Stage 1 | 2025-02-07 | 2025-02-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9210 | Deleted - Sec.4 - Fill - Fill 24 - 2,416ccm - Lower | 2026-03-21 | 2026-03-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19540 | Deleted - Sec.4 - Old Cootmundra Rail Br - Abutment Precast Panels North Abutment Capping | 2026-06-07 | 2026-06-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7060 | Deleted - Submission to IRPL DDR - W.05 - Stage 3 | 2025-06-27 | 2025-06-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7070 | Deleted - IRPL Review (20 B.days) - W.05 - Stage 3 | 2025-06-27 | 2025-07-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5790 | Deleted - IRPL Review (20 B.days) - 3.02 - Stage 1 | 2025-03-11 | 2025-04-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12230 | Deleted - Start Package 3.02 - Geotechnical Design - 3.02 - Stage 1 | 2024-12-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8500 | Deleted - IRPL Review (5 B.days) - 1.02 - Stage 4 | 2025-09-04 | 2025-09-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8510 | Deleted - CDR Package Complete 1.02 - Geotechnical Design - 1.02 - Stage 4 |  | 2025-09-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15230 | Deleted - Sec.1 - Sig - Install New LXG (1 off) - Axle counter/light /booms - Olympic Highway | 2026-03-14 | 2026-03-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15680 | Deleted - Sec.1 - Sig - Remove 8 DW Locs | 2027-03-14 | 2027-03-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.74.14870 | Deleted - Sec.1 - Sig - Civil Foundations for new Signallling Buildings | 2025-10-27 | 2025-11-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.74.14890 | Deleted - Sec.1 - Sig - Deliver Huts to site and installation prep | 2026-01-13 | 2026-01-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15250 | Deleted - Sec.1 - Sig - Install New Buildings (2 off) (2809 & 466126) | 2026-01-26 | 2026-01-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15890 | Deleted - Sec.1 - Sig - Install New Signal Cable - 9,489m (22 runs) - QTY TBC | 2026-01-07 | 2026-01-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15900 | Deleted - Sec.1 - Sig - Install New Power Cable - 22,247m (23 runs) - QTY TBC | 2026-02-04 | 2026-02-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15910 | Deleted - Sec.1 - Sig - Install New Comms Cable - 25,585m (10 runs) - QTY TBC | 2026-02-14 | 2026-02-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15920 | Deleted - Sec.1 - Sig - Install New Axle Cable - 21,949m (41 runs) - QTY TBC | 2026-02-24 | 2026-03-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16940 | Deleted - Sec.6 - Private LX - PR38300 (Temporary BGW) - LOE | 2025-10-24 | 2025-11-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15030 | Deleted - Sec.3 - Fill - Cut 08 - 338ccm - Fill in Open Drains | 2025-11-27 | 2025-11-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11070 | Deleted - Sec.5 - Fill - Fill 41 - 481ccm - Structural Fill | 2026-07-22 | 2026-07-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11030 | Deleted - Sec.5 - Fill - Fill 39 - 1,679ccm - Structural Fill | 2026-07-14 | 2026-07-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.5-1164 | Deleted - CoA - E88,E90 - Review & Approved by Planning Secatary - Public Level Crossing Treatment Report | 2024-12-10 | 2025-01-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7020 | Deleted - Safety Assurance / SiD - W.05 - Stage 3 | 2025-06-06 | 2025-06-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7030 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - W.05 - Stage 3 | 2025-06-13 | 2025-06-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7040 | Deleted - Incorporate IDC & CDR comments - W.05 - Stage 3 | 2025-06-20 | 2025-06-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7050 | Deleted - Issue Responses & Receive Comment Closeout - W.05 - Stage 3 | 2025-06-20 | 2025-06-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7480 | Deleted - Design Development - Stage 2 - Preliminary Design / PDD - Geotechnical GIR - D7 - Stage 2 | 2024-12-20 | 2025-03-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7490 | Deleted - Design Deliverables Submission for Workshops and comments - D7 - Stage 2 | 2025-03-03 | 2025-03-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7500 | Deleted - Safety Assurance / SiD - D7 - Stage 2 | 2025-03-03 | 2025-03-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9240 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Geotechnical Design - 2.02 - Stage 3 | 2025-04-15 | 2025-06-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.BI-1350 | Deleted - CoA - E40, E41_NEW - Baseline monitoring of existing fauna movement corridors, pathways and connectivity- RE | 2024-11-07 | 2024-12-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2730 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-08-18 | 2025-08-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.16140 | Deleted - Sec.3 - Dirnaseer Rd Br - Precast Abutment Panels - North Abutment | 2026-02-26 | 2026-03-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19680 | Deleted - Sec.3 - Dirnaseer Rd Br - Abutment Pile Cap - 5m3 | 2026-01-07 | 2026-01-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4220 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-02-11 | 2025-02-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.5-974 | Deleted - CoA - E88,E90 - Update Plan to Reflect any Comments - Public Level Crossing Treatment Report | 2025-01-21 | 2025-02-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.5-1234 | Deleted - CoA - E88,E90 - Review & Endorse by TfNSW/Council - Public Level Crossing Treatment Report
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.5-1314 | Deleted - Road Manager Design Sign off Letter
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.5-1264 | Deleted - CoA - E89,E90 - Update Plan to Reflect any Comments - Public Level Crossing Treatment Report
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16340 | Deleted - Sec.3 - Stock Crossing - SU13480 - STOCK Culvert - Trench Excavation/ Culvert site prep | 2026-05-24 | 2026-05-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.17690 | Deleted - Sec.3 - Stock Crossing - SU13480 - Install 1 x 3W x 3H STOCK culvert - RCBC - 3 off 7m | 2026-05-27 | 2026-05-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-1022 | Deleted - Essential Energy - Work Can Commence - Stockinbingal LGA |  | 2025-07-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-1052 | Deleted - Package Review / Approval - Essential Energy - Stockinbingal LGA | 2025-05-21 | 2025-06-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-1062 | Deleted - Package Placement - Essential Energy - Stockinbingal LGA | 2025-06-04 | 2025-06-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-1072 | Deleted - Nominate ASP LvL1 to Essential Energy - Stockinbingal LGA | 2025-06-19 | 2025-07-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-1082 | Deleted - Preconstruction Meeting - Essential Energy - Stockinbingal LGA | 2025-07-03 | 2025-07-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8390 | Deleted - IRPL Review (20 B.days) - 1.02 - Stage 2 | 2025-05-16 | 2025-06-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8400 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Geotechnical Design - 1.02 - Stage 3 | 2025-05-15 | 2025-07-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-1640 | Deleted - CoA - E73 - Flood Emergency Reponse Plan (FERP) | 2024-11-05 | 2024-11-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9090 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Drainage - 1.10 - Stage 4 | 2025-08-12 | 2025-09-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9100 | Deleted - Incorporate IDC & CDR comments - 1.10 - Stage 4 | 2025-08-26 | 2025-09-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9110 | Deleted - IRPL Review (5 B.days) - 1.10 - Stage 4 | 2025-09-02 | 2025-09-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3720 | Deleted - IRPL Reviews & Approves CCR Submission $$$ | 2025-02-11 | 2025-02-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3730 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-02-28 | 2025-02-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8300 | Deleted - Incorporate IDR comments - L2 - Stage 3 | 2025-07-24 | 2025-07-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7010 | Deleted - Design Deliverables Submission for Workshops and comments - W.05 - Stage 3 | 2025-06-06 | 2025-06-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8650 | Deleted - Issue Responses & Receive Comment Closeout - 1.01 - Stage 2 | 2025-03-03 | 2025-03-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8660 | Deleted - Submission to IRPL PDR - 1.01 - Stage 2 | 2025-03-10 | 2025-03-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5090 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5300 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - E6 - LXs (Private)
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5310 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5320 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5330 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5340 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | A1120 | Deleted - Sec.6 - Fill - Fill 43 - 2,729ccm - E2 Replace unsuitable - Foundation Treatment | 2025-10-07 | 2025-10-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.16090 | Deleted - Sec.3 - SIG - Install New Double backdrive Points (2 off) - 51A,52A - 51 pts/P.RD -9.151/11.349 | 2026-08-24 | 2026-08-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.16110 | Deleted - Sec.3 - SIG - Install New Tangential - T 250 rad Pts Backdrive (1 off) - 53A - | 2026-08-29 | 2026-08-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15330 | Deleted - Sec.3 - SIG - Install New LXG - Axle counter/light /booms (2 off)- Paper Road | 2026-03-09 | 2026-03-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15070 | Deleted - CLHMMP - DPHI Completion of Review/Approval (2 weeks/ 14 cd) (To | 2025-04-02 | 2025-04-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-2350 | Deleted - CoA - E152 -Site Auditor review of CEMP (To | 2025-05-27 | 2025-06-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-2360 | Deleted - CoA - E152 -Site Auditor review of Soil and Water Sub plan (To | 2025-04-16 | 2025-05-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15390 | Deleted - ACHMP - Respond to stakeholder comments - CoA - C23 (To | 2025-03-04 | 2025-03-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.10420 | Deleted - PDD Package Complete D8 - Geotechnical Monitoring
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.11380 | Deleted - Sec.5 - Fill - Fill 40 - 618ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-09-02 | 2026-09-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.11390 | Deleted - Sec.5 - Fill - Fill 41 - 211cm - Strip/Grade RMAR with type D Material (U5 Class | 2026-09-06 | 2026-09-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.11400 | Deleted - Sec.5 - Fill - Fill 42 - 567ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-09-07 | 2026-09-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.11410 | Deleted - Sec.5 - Fill - Cut 34 - 193ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-09-10 | 2026-09-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.7300 | Deleted - Sec.2 - Fill - Cut 05 - 185ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-02-26 | 2026-02-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16670 | Deleted - Sec.3 - Public LX - PU15950 - Drainage - LX Culvert - Trench Excavation/ Culvert site prep | 2026-01-22 | 2026-01-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21220. | Deleted - Burley Griffin Way Bridge - Precast Abutment Panels - South Abutment
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21230. | Deleted - Burley Griffin Way Bridge - Abutment Precast Panels South Abutment Capping
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21240. | Deleted - Burley Griffin Way Bridge - Mechanically Stabilised Earth Walls (MSE) Walls Construction South Abutment & Wi
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10920 | Deleted - Sec.5 - Fill - Fill 42 - 6,492ccm - Upper A | 2026-05-10 | 2026-05-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.22.7540 | Deleted - Sec.4 - TE02-05 Telstra - Abondoned In-Situ West Side Ironbong Road - Ch9342 (Not required) | 2025-08-19 | 2025-08-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-332 | Deleted - Package Placement - Essential Energy | 2025-06-11 | 2025-06-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-2210 | Deleted - CoA - E102 - NEW - Road Upgrade - Repair and upgrade of roads ** Prior to Site Works ** (Not required) | 2025-05-28 | 2025-07-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.24080 | Deleted - Sec.3 - Culvert (17517) - Place 2.4W x 1.5H RCBC (27 units - 64m) | 2026-03-27 | 2026-04-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.29090 | Deleted - Sec.6 - Culvert (37874) - Excavation 2000m2 2m deep - Basin Upstream
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4140 | Deleted - Configuration Change Acceptance Notice | 2025-02-20 | 2025-02-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15760 | Deleted - CUDLP - 2nd Submission to ER for review and endorsement and IRPL Review | 2025-01-21 | 2025-02-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15770 | Deleted - CUDLP - DPHI Lodgement and DPHI Review (2 weeks/ 14 cd) (1 month after SIMP approval) | 2025-02-19 | 2025-03-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4130 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-02-11 | 2025-02-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14760 | Deleted - Sec.4 - Fill - Cut 17 - 833ccm - Fill in Open Drains | 2026-01-26 | 2026-01-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14780 | Deleted - Sec.4 - Fill - Cut 18 - 962ccm - Fill in Open Drains | 2026-01-30 | 2026-01-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14790 | Deleted - Sec.4 - Fill - Fill 23 - 45ccm - Fill in Open Drains | 2026-02-01 | 2026-02-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14800 | Deleted - Sec.4 - Fill - Fill 24 - 175ccm - Fill in Open Drains | 2026-02-02 | 2026-02-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20020 | Deleted - Sec.4 - Old Cootmundra Rail Br - Pile Cap - 8m3 - South Abutment | 2026-03-31 | 2026-04-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.9900 | Deleted - Design Presentation to IRPL - DPK Presentation - D9 - Stage 2 (Modified already part of original Contract Pr
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6300 | Deleted - Safety Assurance / SiD - D9 - Stage 1 | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6360 | Deleted - Design Development - Stage 2 - Preliminary Design / PDD - SD-01 - Flooding Model/Assessment -Final Issue / | 2025-02-06 | 2025-04-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4960 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL (To | 2026-05-14 | 2026-05-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11930 | Deleted - IRPL Review (20 B.days) - 2.05 - Stage 3 | 2025-06-30 | 2025-07-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11860 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Culverts - Under Rail - 2.05 - Stage 3 | 2025-05-01 | 2025-06-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.17720 | Deleted - Sec.3 - Stock Crossing - SU12355 - Install 1 x 3W x 3H STOCK culvert - RCBC - 3 off 7m | 2026-04-23 | 2026-04-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.17730 | Deleted - Sec.3 - Stock Crossing - SU12355 - STOCK Culvert - Detailed backfill | 2026-04-24 | 2026-04-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.25290 | Deleted - Sec.3 - Culvert (09927) - Place Crown units | 2025-12-20 | 2026-01-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3000 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Noise | 2025-02-03 | 2025-02-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4700 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Bridges - sections 1 (1 off) | 2025-02-19 | 2025-02-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-432 | Deleted - Preconstruction Meeting - Essential Energy - Dirnaseer LGA | 2025-07-09 | 2025-07-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-442 | Deleted - Project Planning for Commencement Approval - Essential Energy - Dirnaseer LGA | 2025-07-23 | 2025-08-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-482 | Deleted - Package Review / Approval - Essential Energy - Cootamundra LGA | 2025-05-27 | 2025-06-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-492 | Deleted - Package Placement - Essential Energy - Cootamundra LGA | 2025-06-11 | 2025-06-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-502 | Deleted - Nominate ASP LvL1 to Essential Energy - Cootamundra LGA | 2025-06-25 | 2025-07-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-512 | Deleted - Preconstruction Meeting - Essential Energy - Cootamundra LGA | 2025-07-09 | 2025-07-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.7640 | Deleted - Sec.3 - Cut - Cut 11 - 14,205ccm - OD Soil | 2026-01-09 | 2026-01-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.7580 | Deleted - Sec.3 - Cut - Fill 10 - 647ccm - OD Soil | 2025-12-14 | 2025-12-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.7590 | Deleted - Sec.3 - Cut - Cut 07 - 18,750ccm - OD Soil/ Soil | 2025-12-16 | 2026-01-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.7600 | Deleted - Sec.3 - Cut - Cut 08 - 3,868ccm - OD Soil/ Soil | 2026-01-12 | 2026-01-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.7650 | Deleted - Sec.3 - Cut - Cut 12 - 21,553ccm - OD Soil | 2025-12-12 | 2026-01-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14290 | Deleted - Sec.3 - Cut - Fill 11 - 602ccm - OD Soil | 2026-01-11 | 2026-01-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14300 | Deleted - Sec.3 - Cut - Fill 12 - 194ccm - OD Soil | 2026-01-17 | 2026-01-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20300 | Deleted - Sec.4 - Isobel Ck Br - FRP - [40] MPa/20 in South Abutment Columns - 19m3 | 2026-04-07 | 2026-04-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10110 | Deleted - Sec.4 - Fill - Cut 21 - 407ccm - Capping (Rail | 2026-06-10 | 2026-06-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10120 | Deleted - Sec.4 - Fill - Fill 28 - 671ccm - Capping (Rail | 2026-06-11 | 2026-06-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10010 | Deleted - Sec.4 - Fill - Cut 17 - 720ccm - Capping (Rail | 2026-05-17 | 2026-05-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10020 | Deleted - Sec.4 - Fill - Fill 22 - 699ccm - Capping (Rail | 2026-05-27 | 2026-05-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10030 | Deleted - Sec.4 - Fill - Cut 18 - 343ccm - Capping (Rail | 2026-05-28 | 2026-05-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10040 | Deleted - Sec.4 - Fill - Fill 23 - 550ccm - Capping (Rail | 2026-06-02 | 2026-06-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10050 | Deleted - Sec.4 - Fill - Fill 24 - 104ccm - Capping (Rail | 2026-06-03 | 2026-06-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10060 | Deleted - Sec.4 - Fill - Cut 19 - 254ccm - Capping (Rail | 2026-06-04 | 2026-06-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10310 | Deleted - Sec.4 - Fill - Fill 24 - 78ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-06-28 | 2026-06-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10320 | Deleted - Sec.4 - Fill - Cut 19 - 300ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-06-29 | 2026-06-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.10330 | Deleted - Sec.4 - Fill - Fill 25 - 81ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-06-30 | 2026-06-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3830 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 3.10 - Stage 3 | 2025-06-13 | 2025-06-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.7170 | Deleted - Sec.2 - Fill - Fill 06 - 857ccm - Capping (Rail | 2026-02-16 | 2026-02-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.7190 | Deleted - Sec.2 - Fill - Fill 07 - 548ccm - Capping (Rail | 2026-02-21 | 2026-02-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-412 | Deleted - Package Placement - Essential Energy - Dirnaseer LGA | 2025-06-11 | 2025-06-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-382 | Deleted - Prepare Tender Docs & Issue RFT ASP Lvl1 - Essential Energy - Dirnaseer LGA | 2025-04-22 | 2025-05-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-392 | Deleted - Pricing by Suppliers / Subcontractors - Essential Energy - Dirnaseer LGA | 2025-05-07 | 2025-05-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12680 | Deleted - Incorporate IDC & CDR comments - 1.08 - Stage 2 | 2025-03-14 | 2025-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12700 | Deleted - Submission to IRPL PDR - 1.08 - Stage 2 | 2025-03-21 | 2025-03-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.D.10R-385 | Deleted - Manufacturing - RCP Pipe (450 /600 RCP) (105 units) | 2025-05-23 | 2025-06-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.D.10R-395 | Deleted - Manufacturing - RCP Pipe (900 RCP) (937 units) | 2025-07-10 | 2025-11-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.D.10R-405 | Deleted - Manufacturing - RCP Pipe (1500 /1800 RCP) (149 units) | 2025-05-23 | 2025-07-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.D.10R-555 | Deleted - Delivery - RCP Pipe (300 RCP) (149 units) | 2025-06-20 | 2025-07-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.D.10R-565 | Deleted - Manufacturing - RCP Pipe (300 RCP) (190 units) | 2025-05-23 | 2025-07-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.D.10R-55 | Deleted - Delivery - RCP Pipe (450 /600 RCP) (105 units) | 2025-06-06 | 2025-07-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.D.10R-345 | Deleted - Delivery - RCP Pipe (900 RCP) (937 units) | 2025-07-31 | 2025-12-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.D.10R-365 | Deleted - Delivery - RCP Pipe (1500 /1800 RCP) (149 units) | 2025-06-20 | 2025-07-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10W-9 | Deleted - Package Placement - Ballast Matting | 2025-02-28 | 2025-03-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10W-10 | Deleted - Manufacturing & Delivery - Ballast Matting | 2025-03-14 | 2025-04-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10W-6 | Deleted - Prepare Tender Documents - Ballast Matting | 2024-12-05 | 2025-01-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21330 | Deleted - Sec.6 - Burley Griffin Way Bridge - Approach Slab South - 32m3 |  | 2026-06-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8670 | Deleted - IRPL Review (20 B.days) - 1.01 - Stage 2 | 2025-03-11 | 2025-04-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8680 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Geotechnical GIR - 1.01 - Stage 3 | 2025-03-18 | 2025-04-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8690 | Deleted - Design Deliverables Submission for Workshops and comments - 1.01 - Stage 3 | 2025-04-16 | 2025-04-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8700 | Deleted - Safety Assurance / SiD - 1.01 - Stage 3 | 2025-04-16 | 2025-04-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8710 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.01 - Stage 3 | 2025-04-24 | 2025-05-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8720 | Deleted - Incorporate IDC & CDR comments - 1.01 - Stage 3 | 2025-05-02 | 2025-05-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.16850 | Deleted - CUDLP - IRPL to review updated documents and Approve
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.29100 | Deleted - Sec.6 - Culvert ID : E7-RD-456911-1 - Backfill Pipe
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.29110 | Deleted - Sec.6 - Culvert ID : E7-RD-456911-1 - Place Precast Wingwall
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12480 | Deleted - Submission to IRPL PDR - 2.03 - Stage 2 | 2025-03-31 | 2025-03-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12490 | Deleted - IRPL Review (20 B.days) - 2.03 - Stage 2 | 2025-04-01 | 2025-05-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12500 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Earthworks Formation Design Documentation - 2.03 - | 2025-03-31 | 2025-05-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3010 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2024-12-16 | 2024-12-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.3020 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-01-08 | 2025-01-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5280 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5290 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5400 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Bridges - Run Boundary Creek Underbridg
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5410 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6380 | Deleted - Safety Assurance / SiD - D9 - Stage 2 | 2025-04-03 | 2025-04-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10810 | Deleted - Start Package 1.04 - Level Crossings - 1.04 - Stage 1 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10780 | Deleted - Issue Responses & Receive Comment Closeout - 1.04 - Stage 1 | 2025-02-14 | 2025-02-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-92 | Deleted - Pricing by Suppliers / Subcontractors - Goldenfields Water | 2025-03-21 | 2025-05-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-84 | Deleted - Package Placement - Goldenfields Water | 2025-05-19 | 2025-06-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-85 | Deleted - Nominate Subcontractor to Goldenfields Water - Submit Contractor Deed Polls & ITPs - Riverina Water | 2025-06-10 | 2025-06-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-86 | Deleted - Goldenfields Water - Work Can Commence - Cootamundra LGA |  | 2025-06-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.24020 | Deleted - Sec.3 - Culvert (15961)) - Detailed backfill | 2026-04-22 | 2026-04-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.26850 | Deleted - Sec.3 - Culvert (09006) - Place Crown units | 2025-12-01 | 2025-12-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5040 | Deleted - Configuration Change Acceptance Notice | 2026-12-17 | 2026-12-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.91.14560 | Deleted - Sec.1 - Hold point for QA Inspection with IRPL - Sec.1 - Rail | 2026-04-29 | 2026-05-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11170 | Deleted - Sec.5 - Fill - Fill 38 - 1,346ccm - Capping (Rail | 2026-07-12 | 2026-07-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11180 | Deleted - Sec.5 - Fill - Cut 32 - 908ccm - Capping (Rail | 2026-07-14 | 2026-07-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11190 | Deleted - Sec.5 - Fill - Fill 39 - 1,189ccm - Capping (Rail | 2026-07-18 | 2026-07-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10W-37 | Deleted - Prepare Tender Documents - Instrumentation and Montoring (Not required) | 2025-04-24 | 2025-05-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10240 | Deleted - Sec.4 - Fill - Cut 27 - 934ccm - Capping (Rail | 2026-06-26 | 2026-06-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.10580 | Deleted - Sec.5 - Cut - Cut 32 - 2,825ccm - OD Soil / Soil | 2025-10-09 | 2025-10-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.8720 | Deleted - Sec.3 - Fill - Cut 11 - 163ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-06-03 | 2026-06-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | A1140 | Deleted - Sec.5 - Fill - Fill 37 - 4,833ccm - E2 Replace unsuitable - Foundation Treatment | 2026-04-13 | 2026-04-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.15370 | Deleted - Sec.2 - Ulandra Ck Br - FRP - [ ] MPa/20 in cross girder -2m3 | 2026-02-01 | 2026-02-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-522 | Deleted - Project Planning for Commencement Approval - Essential Energy - Cootamundra LGA | 2025-07-23 | 2025-08-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-532 | Deleted - Essential Energy - Work Can Commence - Cootamundra LGA |  | 2025-08-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-462 | Deleted - Prepare Tender Docs & Issue RFT ASP Lvl1 - Essential Energy - Cootamundra LGA | 2025-04-22 | 2025-05-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-472 | Deleted - Pricing by Suppliers / Subcontractors - Essential Energy - Cootamundra LGA | 2025-05-07 | 2025-05-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6440 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10150 | Deleted - Submission to IRPL SDR - 1.06 - Stage 1 | 2024-12-20 | 2024-12-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3740 | Deleted - Incorporate IDC & CDR comments - 3.10 - Stage 2 | 2025-04-07 | 2025-04-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.17200 | Deleted - CoA E133 - DPHI Completion of Review/Approval (2 weeks/ 14 cd)
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5520 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Roads - BGW - 3.07 - Stage 2 | 2024-12-20 | 2025-03-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5530 | Deleted - Design Deliverables Submission for Workshops and comments - 3.07 - Stage 2 | 2025-03-10 | 2025-03-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5540 | Deleted - Safety Assurance / SiD - 3.07 - Stage 2 | 2025-03-10 | 2025-03-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5550 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 3.07 - Stage 2 | 2025-03-17 | 2025-03-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5560 | Deleted - Incorporate IDC & CDR / CCB and Stage 1 comments - 3.07 - Stage 2 | 2025-03-24 | 2025-04-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5570 | Deleted - Issue Responses & Receive Comment Closeout - 3.07 - Stage 2 | 2025-03-31 | 2025-04-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5580 | Deleted - Submission to IRPL PDR - 3.07 - Stage 2 | 2025-04-07 | 2025-04-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11250 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.03 - Stage 3 | 2025-04-24 | 2025-05-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11260 | Deleted - Incorporate IDC & CDR comments - 1.03 - Stage 3 | 2025-05-02 | 2025-05-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11270 | Deleted - Issue Responses & Receive Comment Closeout - 1.03 - Stage 3 | 2025-05-02 | 2025-05-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3840 | Deleted - Incorporate IDC & CDR comments - 3.10 - Stage 3 | 2025-06-20 | 2025-06-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3850 | Deleted - Issue Responses & Receive Comment Closeout - 3.10 - Stage 3 | 2025-06-20 | 2025-06-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3930 | Deleted - IRPL Review (5 B.days) - 3.10 - Stage 4 | 2025-08-19 | 2025-08-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3950 | Deleted - CDR Package Complete 3.10 - Drainage (roads) - 3.10 - Stage 4 |  | 2025-09-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20850 | Deleted - Sec.2 - Ulandra Ck Br - Headwall South - 3m3 | 2026-04-04 | 2026-04-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.10380 | Deleted - CNVMP - Respond to stakeholder comments - Construction Noise and Vibration Sub- Plan - CoA - C19 (To delet | 2025-01-21 | 2025-01-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8270 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.02 - Stage 1 | 2025-02-03 | 2025-02-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9010 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 3.05 - Stage 2 | 2025-04-03 | 2025-04-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9020 | Deleted - Incorporate IDC & CDR / CCB and Stage 1 comments - 3.05 - Stage 2 | 2025-04-10 | 2025-04-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9030 | Deleted - Issue Responses & Receive Comment Closeout - 3.05 - Stage 2 | 2025-04-17 | 2025-04-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9040 | Deleted - Submission to IRPL PDR - 3.05 - Stage 2 | 2025-04-29 | 2025-04-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9050 | Deleted - IRPL Review (20 B.days) - 3.05 - Stage 2 | 2025-04-30 | 2025-05-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.74.15190 | Deleted - CSR - Construct Main Cable Route - MCR - 291.5 Location to 292.6 Location (469084 - 470971) 1962m
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.15-864 | Deleted - Completion of Aborignal Hertigae Investigation Process (To
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-1810 | Deleted - CoA - E127 - The Proponent must not destroy, modify or otherwise physically affect any heritage items (To de | 2024-11-25 | 2024-12-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4750 | Deleted - CCB Gate 5 Meeting - Presentation of CCR Submission to SM Sub CCB - Rail Systems | 2026-06-17 | 2026-06-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4070 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-01-31 | 2025-02-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12030 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - W.04 - Stage 3 | 2025-05-15 | 2025-05-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5610 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5620 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.9110 | Deleted - Safety Assurance / SiD - 3.05 - Stage 3 | 2025-06-04 | 2025-06-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4660 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-01-31 | 2025-02-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.74.15060 | Deleted - Sec.3 - SIG - Main Cable Route - MCR - Pull Cable - 12450 to 14208 | 2026-03-20 | 2026-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.85.12290 | Deleted - Sec.3 - Landscaping - CH8840-18500 | 2026-07-16 | 2026-08-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.14310 | Deleted - Sec.3 - IRPL Sleeper Stockpiles - Sec.3 | 2026-06-12 | 2026-06-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.91.14460 | Deleted - Sec.3 - Hold point for QA Inspection with IRPL - Sec.3 - Sleepers | 2026-06-09 | 2026-06-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-1202 | Deleted - JH Contract Approval - Telstra - Illabo | 2025-06-19 | 2025-07-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-1212 | Deleted - Telstra- Work Can Commence - illabo LGA |  | 2025-07-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12860 | Deleted - IRPL Review (5 B.days) - 1.08 - Stage 4 | 2025-07-14 | 2025-07-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.12870 | Deleted - CDR Package Complete 1.08 - Utility Infrastructure - 1.08 - Stage 4 |  | 2025-07-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.81190 | Deleted - Sec.2 - Fill - Fill 07 - 1703ccm - Fill in Open Drains | 2025-11-01 | 2025-11-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.81050 | Deleted - Sec.2 - Fill - Cut 03 - 4320ccm - Fill in Open Drains /Backfill Dam | 2025-09-26 | 2025-10-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.81160 | Deleted - Sec.2 - Fill - Fill 06 -226ccm - Fill in Open Drains | 2025-10-29 | 2025-10-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.81180 | Deleted - Sec.2 - Fill - Cut 04 - 1155ccm - Fill in Open Drains | 2025-10-30 | 2025-10-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9500 | Deleted - Sec.4 - Fill - Fill 22 - 5,001ccm - Upper A | 2026-04-16 | 2026-04-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9520 | Deleted - Sec.4 - Fill - Fill 23 - 6,257ccm - Upper A | 2026-04-12 | 2026-04-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9530 | Deleted - Sec.4 - Fill - Fill 24 - 3,634ccm - Upper A | 2026-04-10 | 2026-04-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9550 | Deleted - Sec.4 - Fill - Fill 25 - 1,326ccm - Upper A | 2026-04-09 | 2026-04-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6440 | Deleted - Design Development - Stage 3 - Detailed Design / DDD - Flooding Model / Assessment - D9 - Stage 3 | 2025-04-29 | 2025-06-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6470 | Deleted - Review of IDR comment response and final review - D9 - Stage 3 | 2025-06-18 | 2025-06-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.C.1090133 | Deleted - Engage Subcontractor - Scaffolding | 2025-04-23 | 2025-06-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.C.10914 | Deleted - Subcontractor Mob to Site - Scaffolding | 2025-06-20 | 2025-07-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.21090 | Deleted - Sec.4 - Culvert (22492) - Backfill units | 2026-03-24 | 2026-03-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.27510 | Deleted - Sec.4 - Culvert (22492) - Excavation 1700m2 1m deep - Basin Upstream | 2026-03-11 | 2026-03-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21630 | Deleted - Sec.4 - Isobel Ck Trib Br - FRP - [40] MPa/10 in pedestals - 6m3 | 2026-05-08 | 2026-05-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21640 | Deleted - Sec.4 - Isobel Ck Trib Br - FRP - Restraint Blocks - North Abutment | 2026-05-12 | 2026-05-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21660 | Deleted - Sec.4 - Isobel Ck Trib Br - FRP - Tee Roff Diaphragm Beam - Abutments (2off) - 3m3 | 2026-05-08 | 2026-05-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13220 | Deleted - TfNSW/ IV Review (30 B.days) - Roads - Sec.2 to 5 | 2025-05-12 | 2025-06-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13080 | Deleted - Safety Assurance / SiD - 2.09 - Stage 3 | 2025-04-15 | 2025-04-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.13210 | Deleted - TfNSW Review (30 B.days) - M2 - Stage 4 - Roads - Sec.2 to 5 | 2025-07-15 | 2025-08-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.8280 | Deleted - Safety Assurance / SiD - W.11 - Stage 3 | 2025-07-10 | 2025-07-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.03.11800 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Roads (Private) - 3.09 - Stage 1 | 2024-10-03 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5480 | Deleted - Incorporate IDC & CDR comments - 3.07 - Stage 1 | 2024-12-13 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5490 | Deleted - Issue Responses & Receive Comment Closeout - 3.07 - Stage 1 | 2024-12-13 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.7050 | Deleted - Sec.2 - Fill - Cut 03 - 2,449ccm - Structural Fill | 2026-02-06 | 2026-02-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.7060 | Deleted - Sec.2 - Fill - Fill 05 - 1,735ccm - Structural Fill | 2026-02-10 | 2026-02-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.7070 | Deleted - Sec.2 - Fill - Fill 06 - 1,140ccm - Structural Fill | 2026-02-13 | 2026-02-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20950 | Deleted - Sec.2 - Ulandra Ck Br - FRP - [40] MPa/10 in pedestals - 2m3 | 2026-01-26 | 2026-01-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20800 | Deleted - Sec.2 - Ulandra Ck Br - Precast Concrete Parapet Panels | 2026-03-07 | 2026-03-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20930 | Deleted - Sec.2 - Ulandra Ck Br - Wing Walls - North side 2 No. - 11m3 | 2026-05-01 | 2026-05-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20820 | Deleted - Sec.2 - Ulandra Ck Br - Construct base slab - 48m3 | 2026-03-07 | 2026-03-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20830 | Deleted - Sec.2 - Ulandra Ck Br - Install Precast Culvert crown Units | 2026-03-26 | 2026-03-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20840 | Deleted - Sec.2 - Ulandra Ck Br - Headwall North - 3m3 | 2026-03-31 | 2026-04-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.14280 | Deleted - Sec.2 - IRPL Sleeper Stockpiles - Sec.2 | 2026-05-11 | 2026-05-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.91.14450 | Deleted - Sec.2 - Hold point for QA Inspection with IRPL- Sec.2 - Sleepers | 2026-05-08 | 2026-05-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11150 | Deleted - Sec.5 - Fill - Fill 37 - 1,211ccm - Capping (Rail | 2026-07-07 | 2026-07-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.17900 | Deleted - Sec.6 - Possession ( Sep 2026) - Stockinbingal Trackworks - LOE | 2026-09-12 | 2026-09-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.18540 | Deleted - Sec.6 - Float before Possession September 2026 - LOE | 2026-05-07 | 2026-09-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11780 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Culverts - Under Rail - 2.05 - Stage 2 | 2025-01-30 | 2025-03-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-1692 | Deleted - Groundwater Licence - IRPL Review (Inc Dept of Water) - approx 3-5 months | 2025-01-23 | 2025-06-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-1702 | Deleted - Groundwater Licence - JH Incorporate Comments | 2025-06-19 | 2025-07-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-1712 | Deleted - Groundwater Licence - Draft Issued for Review |  | 2025-07-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-1722 | Deleted - Groundwater Licence - Review and Update | 2025-07-10 | 2025-07-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-2490 | Deleted - CoA - E17_OLD - submission to EPA and Planning Secretary - Operational Noise and Vibration Review (ONVR) - R | 2026-08-11 | 2026-09-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.4-84 | Deleted - IRPL to review updated documents and Approve - Electromagnetic Compatibility MP | 2024-12-17 | 2025-01-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.4-54 | Deleted - Prepare & Submit to IRPL PM / Project Verifier - Electromagnetic Compatibility MP (20 Bdays after Date of De | 2024-09-30 | 2024-11-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10430 | Deleted - Safety Assurance / SiD - 1.05 - Stage 1 | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4690 | Deleted - Configuration Change Acceptance Notice | 2025-03-04 | 2025-03-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10410 | Deleted - Design Development - Stage 1 - Feasibility Design / SDR - Culverts - Under Rail - 1.05 - Stage 1 | 2024-10-03 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10420 | Deleted - Design Deliverables Submission for Workshops and comments - 1.05 - Stage 1 | 2024-11-29 | 2024-12-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10440 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.05 - Stage 1 | 2025-01-15 | 2025-01-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10280 | Deleted - Safety Assurance / SiD - 1.06 - Stage 3 | 2025-06-05 | 2025-06-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10290 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.06 - Stage 3 | 2025-06-13 | 2025-06-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10300 | Deleted - Incorporate IDC & CDR comments - 1.06 - Stage 3 | 2025-06-20 | 2025-06-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10340 | Deleted - Prepare CDR Documentation - Stage 4 - CDR Submission - Bridges - 1.06 - Stage 4 | 2025-07-07 | 2025-08-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10350 | Deleted - Incorporate IDC & CDR / CCB and Stage 3 comments - 1.06 - Stage 4 | 2025-08-19 | 2025-09-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10360 | Deleted - IRPL Review (5 B.days) - 1.06 - Stage 4 | 2025-09-02 | 2025-09-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.10370 | Deleted - CDR Package Complete 1.06 - Bridges - 1.06 - Stage 4 |  | 2025-09-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2850 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Bridges - sections 1 (1 off) | 2025-08-04 | 2025-08-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2860 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-06-30 | 2025-07-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.G.101220 | Deleted - Engage Comm. (Existing Telstra/Optus /NBN) Subcontractor | 2025-03-07 | 2025-05-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.5700 | Deleted - Issue Responses & Receive Comment Closeout - BGW road - 3.07 - Stage 4 | 2025-08-06 | 2025-08-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18270 | Deleted - Sec.5 - Powder Horn Trib Br - Install bridge barriers | 2026-08-29 | 2026-08-31
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.15790 | Deleted - Sec.3 - Run Boundary Ck Br - Delivery /QA of Transverse stressing units | 2026-02-14 | 2026-02-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.8070 | Deleted - Sec.3 - Fill - Fill 15 - 4,394ccm - Upper A | 2026-04-10 | 2026-04-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.8090 | Deleted - Sec.3 - Fill - Fill 16 -4,376ccm - Upper A | 2026-04-14 | 2026-04-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4550 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Earthworks Formation Design Documentatio | 2025-02-03 | 2025-02-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4560 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2024-12-09 | 2024-12-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4570 | Deleted - IRPL Reviews & Approves CCR Submission | 2024-12-18 | 2025-01-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4580 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-01-20 | 2025-01-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4590 | Deleted - Configuration Change Acceptance Notice | 2025-02-04 | 2025-02-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.BI-1300 | Deleted - CoA - E42, E43_NEW - IRPL Review and issue Comments -Environmental - Fauna Connectivity (To | 2025-05-02 | 2025-05-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5800 | Deleted - CCB Gate 3 Meeting - Presentation of CCR Submission to SM Sub CCB - Bridges - Old Cootamundra Road Underbri
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5810 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5820 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5830 | Deleted - IRPL Submits CCB to SM Sub CCB
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5840 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-1562 | Deleted - EIS Environmental Consistency Assessment- Approval | 2025-07-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-1582 | Deleted - EIS Environmental Consistency Assessment- Concept Design with enough information for heritage assessment | 2024-11-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14690 | Deleted - Sec.5 - Fill - Cut 32 - 1,067ccm - Fill in Open Drains | 2026-04-17 | 2026-04-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9410 | Deleted - Issue Responses & Receive Comment Closeout - 2.10 - Stage 3 | 2025-05-23 | 2025-05-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9420 | Deleted - Submission to IRPL DDR - 2.10 - Stage 3 | 2025-05-30 | 2025-05-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.14680 | Deleted - Sec.5 - Fill - Fill 38 - 1,482ccm - Fill in Open Drains | 2026-04-14 | 2026-04-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.7080 | Deleted - Sec.2 - Fill - Cut 04 - 1,682ccm - Structural Fill | 2026-02-16 | 2026-02-18
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.7090 | Deleted - Sec.2 - Fill - Fill 07 - 758ccm - Structural Fill | 2026-02-19 | 2026-02-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.7100 | Deleted - Sec.2 - Fill - Cut 05 - 626ccm - Structural Fill | 2026-02-20 | 2026-02-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.7110 | Deleted - Sec.2 - Fill - Fill 08 - 1,039ccm - Structural Fill up to LX 8160 | 2026-02-21 | 2026-02-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.7120 | Deleted - Sec.2 - Fill - Fill 09 - 2,983ccm - Structural Sec.2 - Fill - North of LX 8160 | 2026-02-23 | 2026-02-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.12940 | Deleted - Sec.2 - Fill - Fill 06 - 1,208cm - Structural Fill | 2026-02-13 | 2026-02-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2330 | Deleted - IRPL Submits CCB to SM Sub CCB | 2025-07-14 | 2025-07-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2300 | Deleted - Meeting - Presentation of CCR Submission to SM Sub CCB - Earthworks Formation Design Documentatio | 2025-07-16 | 2025-07-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2310 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-06-16 | 2025-06-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2320 | Deleted - IRPL Reviews & Approves CCR Submission | 2025-06-25 | 2025-07-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-1092 | Deleted - Project Planning for Commencement Approval - Essential Energy - Stockinbingal LGA | 2025-07-17 | 2025-07-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-77 | Deleted - Develop & Submit Design - Goldenfields Water | 2024-10-17 | 2024-11-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-78 | Deleted - Goldenfields Water Review & Comment -Goldenfields Water | 2024-11-14 | 2025-01-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-79 | Deleted - Redesign Based on Sydeny Water Comments - Goldenfields Water | 2025-01-07 | 2025-01-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5920 | Deleted - IRPL Reviews & Approves CCR Submission
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11820 | Deleted - Incorporate IDC & CDR / CCB and Stage 1 comments - 2.05 - Stage 2 | 2025-04-04 | 2025-04-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11830 | Deleted - Issue Responses & Receive Comment Closeout - 2.05 - Stage 2 | 2025-04-11 | 2025-04-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11840 | Deleted - Submission to IRPL PDR - 2.05 - Stage 2 | 2025-04-22 | 2025-04-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.9820 | Deleted - Sec.4 - Fill - Fill 26 - 383ccm - Structural Fill | 2026-05-22 | 2026-05-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | CoA-1840 | Deleted - CoA - E17_OLD - Develop Draft Operational Noise and Vibration Review (ONVR) Road | 2026-07-13 | 2026-08-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-1612 | Deleted - EIS Environmental Consistency Assessment- Client review /comments/ finalisation | 2025-01-23 | 2025-02-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-1622 | Deleted - EIS Environmental Consistency Assessment- ER Endorsement (1 month) | 2025-03-25 | 2025-05-01
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-1632 | Deleted - EIS Environmental Consistency Assessment- Receiving/Reviewing comments, finalisation | 2025-05-23 | 2025-05-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-1642 | Deleted - EIS Environmental Consistency Assessment- Receipt of approval | 2025-05-30 | 2025-06-05
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7300 | Deleted - Safety Assurance / SiD - Stage 3 | 2025-05-19 | 2025-05-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.3080 | Deleted - Safety Assurance / SiD - W.10 - Stage 3 | 2025-07-21 | 2025-07-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.4950 | Deleted - CCB Gate 5 Meeting - Presentation of CCR Submission to SM Sub CCB - Rail Systems (To | 2026-06-17 | 2026-06-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.11940 | Deleted - Safety Assurance / SiD - W.04 - Stage 2 | 2025-03-07 | 2025-03-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.11950 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - W.04 - Stage 2 | 2025-03-14 | 2025-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.12540 | Deleted - Incorporate IDC & CDR comments - 2.03 - Stage 3 | 2025-06-05 | 2025-06-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.81200 | Deleted - Sec.2 - Fill - Cut 05 - 408ccm - Fill in Open Drains | 2025-11-02 | 2025-11-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.81210 | Deleted - Sec.2 - Fill - Fill 08 - 282ccm - Fill in Open Drains | 2025-11-03 | 2025-11-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.81040 | Deleted - Sec.2 - Fill - Fill 04 - 2000ccm - Backfill Dam | 2025-09-21 | 2025-09-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.10560 | Deleted - CAQMP - Respond to stakeholder comments (To | 2025-01-14 | 2025-01-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.5-994 | Deleted - CoA - E133 - Prepare & Submit to IRPL PM / Project Verifier - Aboriginal Cultural Values PLan | 2024-09-30 | 2024-10-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.10110 | Deleted - CSWMP - JH Respond to stakeholder comments (1w) - CoA - C22 (To | 2025-01-29 | 2025-02-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-2352 | Deleted - CoA - E24 - Field inspections and reporting (LIW) Biodiversity - SITE | 2025-01-13 | 2025-02-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.C.10C-650 | Deleted - Engage Subcontractor - Kerb and Gutter | 2025-05-30 | 2025-07-25
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.02.11790 | Deleted - Design Deliverables Submission for Workshops and comments - Stage 2 - Culverts - 2.05 - Stage 2 | 2025-03-21 | 2025-03-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.5-1114 | Deleted - CoA - E162 - Update Plan to Reflect any Comments - Unexpected Finds for Contamination Procedure (Delete Part | 2025-01-21 | 2025-02-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.5-1124 | Deleted - CoA - E162 - IRPL to review updated documents and Approve - Unexpected Finds for Contamination Procedure (De |  | 2025-02-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-2422 | Deleted - CoA - E34 _NEW - IRPL application for Biodiversity Stewardship Agreement (BSA) (IR2200-RTRFI-000141 | 2024-09-30 | 2024-10-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-2432 | Deleted - CoA - E35, E36, E37_NEW - IRPL Box Gum Woodland Restoration Plan (IR2200-RTRFI-000141) | 2024-10-08 | 2024-11-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-2442 | Deleted - CoA - E35, E36, E37_NEW - IRPL Box Gum Woodland Restoration Plan - Monitoring / results inc. | 2024-10-08 | 2024-10-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.PA-2452 | Deleted - CoA - E35, E36, E37_NEW - IRPL Box Gum Woodland Restoration Report Approved by Planning Secretary | 2024-11-05 | 2024-12-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.22.13430 | Deleted - Sec.1 - PUP Private Power - 1925 - Exist OH power x-ing track & Olympic Hwy. | 2025-07-24 | 2025-07-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.5-1284 | Deleted - CoA - E89,E90 - Review & Approved by Planning Secartary - Private Level Crossing Treatment Report
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.MR.AnF.5-1304 | Deleted - Design Criteria Forms (Individual Propoerty Management Plans)
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18170 | Deleted - Sec.5 - Powder Horn Trib Br - FRP - [40] MPa/20 in pier 2 headstock - 9m3 | 2026-04-27 | 2026-05-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19800 | Deleted - Sec.5 - Powder Horn Trib Br - Pier 1 Pile Cap - 8m3 | 2026-03-24 | 2026-03-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.15040 | Deleted - Sec.3 - Fill - Fill 12 - 142ccm - Fill in Open Drains | 2025-11-28 | 2025-11-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15530 | Deleted - Sec.6 - Sig - Install New Main Signals (2 off) - SL29, SL30 - SL30 - Up/Dn - 456.216/ 456.716 | 2026-04-30 | 2026-05-02
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15540 | Deleted - Sec.6 - Sig - Install New Main Signals (5 off) - SL11,SL12, SL15, SL16, SL18 - SL113 - Up/Dn - apprx.454 | 2026-05-16 | 2026-05-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.50.18490 | Deleted - Sec.6 - Float from GreenField Earthworks to Track team coming onsite - N/A | 2026-03-28 | 2026-03-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16710 | Deleted - Sec.3 - Public LX - PU15950 - Drainage - Install 450 RCP - 4 off - 8m | 2026-01-24 | 2026-01-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.91.14570 | Deleted - Sec.5 - Hold point for QA Inspection with IRPL - Sec.5 - Rail | 2026-09-02 | 2026-09-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.22.13400 | Deleted - Sec.4 - PUP - Water - 21250 - NCP -13 -DN300 RCP enveloper pipe for future water. | 2025-08-11 | 2025-08-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10C-720 | Deleted - Subcontractor Mob to Site - Tamping crew and Tamper 3 | 2025-08-18 | 2025-09-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10C-340 | Deleted - Engage Subcontractor - Tamping | 2025-06-13 | 2025-08-15
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.28520 | Deleted - Sec.5 - Culvert (37212) - Backfill units
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.28480 | Deleted - Sec.5 - Culvert (37212) - Trench Excavation / Site Prep
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.28490 | Deleted - Sec.5 - Culvert (37212) - Foundation Treatment / Bedding
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.8950 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.10 - Stage 2 | 2025-03-24 | 2025-03-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.8960 | Deleted - Incorporate IDC & CDR comments - 1.10 - Stage 2 | 2025-03-31 | 2025-04-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9010 | Deleted - Design Development - Stage 3 - Detailed Design / DDR - Road Drainage - 1.10 - Stage 3 | 2025-04-23 | 2025-06-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.9020 | Deleted - Design Deliverables Submission for Workshops and comments - 1.10 - Stage 3 | 2025-06-05 | 2025-06-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.16840 | Deleted - CUDLP - Resubmission of plan to IRPL for review
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15730 | Deleted - CUDLP - JH Internal review | 2024-11-05 | 2024-11-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.CEMP.15740 | Deleted - CUDLP - Consultation with relevant Government agencies (up to 3 weeks) | 2024-12-10 | 2025-01-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.S.10IG-40 | Deleted - Manufacturing & Delivery - Signalling Power System (14 Wks) | 2025-06-13 | 2025-10-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.17700 | Deleted - Sec.3 - Stock Crossing - SU13480 - STOCK Culvert - Detailed backfill | 2026-05-28 | 2026-05-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.7280 | Deleted - Sec.2 - Fill - Cut 04 - 496ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-02-22 | 2026-02-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.7290 | Deleted - Sec.2 - Fill - Fill 07 - 226ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-02-24 | 2026-02-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.72.15840 | Deleted - Sec.3 - SIG - Install New Comms Cable - 62,320m (4 runs) | 2026-04-04 | 2026-04-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.65.16330 | Deleted - Sec.3 - Stock Crossing - SU12355 - STOCK Culvert - Trench Excavation/ Culvert site prep | 2026-04-21 | 2026-04-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.2910 | Deleted - Prepare & Submit CCR Checklist /Presentation Material to IRPL | 2025-07-03 | 2025-07-09
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.9240 | Deleted - Sec.4 - Fill - Fill 27 - 313ccm - Lower | 2025-12-17 | 2025-12-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20880 | Deleted - Sec.2 - Ulandra Ck Br - apron slab outlet - 33m3 | 2026-04-13 | 2026-04-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20890 | Deleted - Sec.2 - Ulandra Ck Br - Culvert Wingwalls - North - 8m3 | 2026-04-26 | 2026-04-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11230 | Deleted - Sec.5 - Fill - Fill 41 - 341ccm - Capping (Rail | 2026-07-24 | 2026-07-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11100 | Deleted - Sec.5 - Fill - Fill 35 - 139ccm - Capping (Rail | 2026-06-29 | 2026-06-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11120 | Deleted - Sec.5 - Fill - Fill 36 - 2,228ccm - Capping (Rail | 2026-07-01 | 2026-07-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11130 | Deleted - Sec.5 - Fill - Cut 29 - 283ccm - Capping (Rail | 2026-07-04 | 2026-07-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.11140 | Deleted - Sec.5 - Fill - Cut 30 - 781ccm - Capping (Rail | 2026-07-06 | 2026-07-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.11330 | Deleted - Sec.5 - Fill - Fill 38 - 670ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-08-20 | 2026-08-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.11340 | Deleted - Sec.5 - Fill - Cut 32 - 497ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-08-23 | 2026-08-24
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.11350 | Deleted - Sec.5 - Fill - Fill 39 - 592ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-08-26 | 2026-08-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6930 | Deleted - Design Deliverables Submission for Workshops and comments - W.05 - Stage 2 | 2025-04-04 | 2025-04-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6910 | Deleted - IRPL Review (20 B.days) - W.05 - Stage 1 | 2025-02-10 | 2025-03-07
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.04.12180 | Deleted - Start Package W.05 - Geotech Gap Analysis & SI - W.05 - Stage 1 | 2024-10-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6920 | Deleted - Design Development - Stage 2 - Preliminary Design / PDR - Geotech Gap Analysis & SI - W.05 - Stage 2 | 2025-02-07 | 2025-04-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6940 | Deleted - Safety Assurance / SiD - W.05 - Stage 2 | 2025-04-04 | 2025-04-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.6950 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - W.05 - Stage 2 | 2025-04-11 | 2025-04-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7510 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - D7 - Stage 2 | 2025-03-10 | 2025-03-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.81060 | Deleted - Sec.2 - Fill - Fill 04 - 7985ccm - E2 Replace Unsuitable - Foundation Treatment | 2025-09-26 | 2025-10-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.31.81170 | Deleted - Sec.2 - Fill - Fill 07 - 1214ccm - E2 Replace Unsuitable - Foundation Treatment | 2025-11-02 | 2025-11-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.16330 | Deleted - CoA - C27 - Develop Construction Monitoring Programs | 2024-09-30 | 2024-10-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.8850 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.10 - Stage 1 | 2024-12-13 | 2024-12-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10W-15 | Deleted - Manufacturing & Delivery - Capping & Structural Fill | 2025-03-14 | 2025-04-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21540 | Deleted - Sec.5 - Powder Horn Ck Br - FRP - [40] MPa/10 in pedestals - 2m3 | 2026-05-19 | 2026-05-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.D.10R-305 | Deleted - Fabricate set B (1.2W) - Precast RCBC Culvert Drainage Pipe and Channel | 2025-09-02 | 2025-09-23
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.5140 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.D.10R-275 | Deleted - Build Moulds - RCP + RCBC | 2025-07-09 | 2025-08-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.8350 | Deleted - Draft Comment Responses & CDR/IDC Closeout Workshop with Stakeholders - 1.02 - Stage 2 | 2025-04-23 | 2025-04-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.20350 | Deleted - Sec.4 - Isobel Ck Br - FRP - [40] MPa/20 Spillthrough Batter Retaining Wall Footing North Batter - 37m | 2026-05-06 | 2026-05-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.7200 | Deleted - Sec.2 - Fill - Cut 05 - 442ccm - Capping (Rail | 2026-02-22 | 2026-02-22
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | A1230 | Deleted - Sec.4 - Fill - Fill 30 - 2,868ccm - E2 Replace unsuitable - Foundation Treatment | 2026-03-24 | 2026-03-30
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-362 | Deleted - Project Planning for Commencement Approval - Essential Energy | 2025-07-23 | 2025-08-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.33.10070 | Deleted - Sec.4 - Fill - Fill 25 - 128ccm - Capping (Rail | 2026-06-06 | 2026-06-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3630 | Deleted - Incorporate IDC & CDR comments - 3.10 - Stage 1 | 2025-01-10 | 2025-01-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3640 | Deleted - Issue Responses & Receive Comment Closeout - 3.10 - Stage 1 | 2025-01-10 | 2025-01-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3660 | Deleted - Submission to IRPL SDR - 3.10 - Stage 1 | 2025-01-17 | 2025-01-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.01.3670 | Deleted - IRPL Review (20 B.days) - 3.10 - Stage 1 | 2025-01-17 | 2025-02-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.8810 | Deleted - Sec.3 - Fill - Fill 19 - 133ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-06-16 | 2026-06-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.8780 | Deleted - Sec.3 - Fill - Cut 14 - 196ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-06-12 | 2026-06-12
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.8790 | Deleted - Sec.3 - Fill - Fill 18 - 211ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-06-13 | 2026-06-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.8800 | Deleted - Sec.3 - Fill - Cut 15 - 196ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-06-14 | 2026-06-14
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.8820 | Deleted - Sec.3 - Fill - Cut 16 - 285ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-06-17 | 2026-06-17
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.8830 | Deleted - Sec.3 - Fill - Fill 20 - 859ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-06-18 | 2026-06-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-5 | Deleted - Pricing by Suppliers / Subcontractors - Essential Energy | 2025-01-16 | 2025-02-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-6 | Deleted - Package Review / Approval - Essential Energy | 2025-02-07 | 2025-02-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-7 | Deleted - Package Placement - Essential Energy | 2025-02-14 | 2025-02-27
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-8 | Deleted - ASP Lvl3 Engaged - Essential Energy |  | 2025-03-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-1032 | Deleted - Prepare Tender Docs & Issue RFT ASP Lvl1 - Essential Energy - Stockinbingal LGA | 2025-04-22 | 2025-05-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19850 | Deleted - Sec.5 - Powder Horn Trib Br - Abutment 2 Pile Cap - 8m3 | 2026-05-29 | 2026-06-03
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18230 | Deleted - Sec.5 - Powder Horn Trib Br - Cill Beam - North Abutment - 8m3 | 2026-06-23 | 2026-06-29
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18240 | Deleted - Sec.5 - Powder Horn Trib Br - Cill Beam - South Abutment - 8m3 | 2026-06-30 | 2026-07-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19840 | Deleted - Sec.5 - Powder Horn Trib Br - S&I Column sleeves to columns (2off) Abutment 1 | 2026-05-22 | 2026-05-28
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19860 | Deleted - Sec.5 - Powder Horn Trib Br - Site prep Abutment Footings | 2026-06-09 | 2026-06-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19870 | Deleted - Sec.5 - Powder Horn Trib Br - Back Wall North Abutment - 5m3 | 2026-06-30 | 2026-07-04
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21470 | Deleted - Sec.5 - Powder Horn Trib Br - FRP - [40] MPa/20 in pier (2no x 1.5m dia cols x 6.6m ht) Abutment 1 Col | 2026-05-16 | 2026-05-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21480 | Deleted - Sec.5 - Powder Horn Trib Br - FRP - [40] MPa/20 in Abutment 2 - 15m3 | 2026-06-04 | 2026-06-08
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.00.7520 | Deleted - Incorporate IDC & CDR comments - D7 - Stage 2 | 2025-03-17 | 2025-03-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.DE.CCB.6390 | Deleted - Configuration Change Acceptance Notice
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18060 | Deleted - Sec.5 - Powder Horn Trib Br - Demobilise piling rig | 2026-03-21 | 2026-03-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10C-350 | Deleted - Subcontractor Mob to Site - Tamping crew and Tamper 1 | 2025-08-18 | 2025-09-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.P.R.10C-710 | Deleted - Subcontractor Mob to Site - Tamping crew and Tamper 2 | 2025-08-18 | 2025-09-26
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18100 | Deleted - Sec.5 - Powder Horn Trib Br - Place and test platform /Piling Pad | 2026-01-18 | 2026-01-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18110 | Deleted - Sec.5 - Powder Horn Trib Br - Mobilise piling rig | 2026-03-06 | 2026-03-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.18120 | Deleted - Sec.5 - Powder Horn Trib Br - abutment piling consists of 4 x 1200mm dia bored concrete piles | 2026-03-07 | 2026-03-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.19650 | Deleted - Sec.5 - Powder Horn Trib Br - pier piling consist of 4 x 1500mm dia bored concrete piles | 2026-03-11 | 2026-03-20
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21460 | Deleted - Sec.5 - Powder Horn Trib Br - FRP - [40] MPa/20 in pier (2no x 1.5m dia cols x 4.0m ht) Pier 1 Column P | 2026-04-14 | 2026-04-19
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.62.21450 | Deleted - Sec.5 - Powder Horn Trib Br - FRP - [40] MPa/20 in pier (2no x 1.5m dia cols x 4.0m ht) Pier 2 Column P | 2026-04-08 | 2026-04-13
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.7240 | Deleted - Sec.2 - Fill - Cut 02 - 141ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-02-11 | 2026-02-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.45.7250 | Deleted - Sec.2 - Fill - Cut 03 - 704ccm - Strip/Grade RMAR with type D Material (U5 Class | 2026-02-13 | 2026-02-16
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.74.14910 | Deleted - Sec.1 - CSR - Route complete - Sec.1 - double up |  | 2026-01-06
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.27560 | Deleted - Sec.6 - Culvert (37370) - Excavation 2000m2 2m deep - Basin Upstream | 2026-01-06 | 2026-01-11
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.CN.34.27570 | Deleted - Sec.6 - Culvert (37874) - Excavation 2000m2 2m deep - Basin Upstream | 2025-09-16 | 2025-09-21
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-402 | Deleted - Package Review / Approval - Essential Energy - Dirnaseer LGA | 2025-05-27 | 2025-06-10
I2S-7688-MP-74.1.22 | Deleted Activities Prior to14/10/2025 | I.GG.PM.UTIL-422 | Deleted - Nominate ASP LvL1 to Essential Energy - DirnaseerLGA | 2025-06-25 | 2025-07-08