## Planning Template
WBS | WBS Name | Activity ID | Activity Name | Start | Finish | link_01 | link_02 | link_03 | link_04 | Wbs Level
1 | Project Initiation | ACT001 | Kickoff Meeting | 2024-01-01 | 2024-01-05 |  |  |  |  | 1
1.1 | Requirements Gathering | ACT002 | Gather Requirements | 2024-01-06 | 2024-01-15 |  |  |  |  | 2
1.2 | Project Planning | ACT003 | Create Project Plan | 2024-01-16 | 2024-01-25 |  |  |  |  | 2
2 | Development Phase | ACT004 | Development Start | 2024-01-26 | 2024-02-10 |  |  |  |  | 1
2.1 | Design | ACT005 | System Design | 2024-02-11 | 2024-02-20 |  |  |  |  | 2
2.1.1 | UI Design | ACT006 | User Interface Design | 2024-02-21 | 2024-03-01 |  |  |  |  | 3
2.1.2 | Database Design | ACT007 | Database Schema | 2024-03-02 | 2024-03-10 |  |  |  |  | 3